## Sheet Shop Priority TO# List
Production Schedule | [8 empty] | Column1 |  | Sheet Shop | [13 empty] | Column1 | JOB LIST
| TO#'S |  | SKETCH/SPOOL #'S | STATUS | DONE | #VALUE! | L |  | JOB NAME / # |  |  | Z | DATE | PLASMA | SPIRAL | C.LINE | 0 | INSU | LBS. | [5 empty] | JOB NAME / # | (Add new jobs below last entry)
[6 empty] | SIZE | SIZE | METAL |  | SPECIAL | NEED | RANK | RCVD | SQ FT | SQ FT | SQ FT | SQ FT | SQ FT |  | Material | [5 empty] | 121 E WILSON 6230024
[6 empty] | 325 | EST. | ETC. |  | NOTES | DATE | Pounds completed to date this week = | [6 empty] | 10100 |  | Description | # Of Pieces | Lead Time | Original need date | LABCORP 2260026 | ANTIGO 6250017
1 | 41709 |  | 41709 | A |  | 2 | S | ss | LABCORP 2260026 | flex | 2026-04-17 | 1 | 2026-04-10 | 20 | 0 | 0 | 20 | 0 | 50 |  | Roof canvass | 2 | 7 |  | MPS 4260004 | BROOM ST 6240033
2 | 84338 |  | 84338 | A |  | 2 | S |  | MPS 4260004 |  | 2026-04-21 | 2 | 2026-04-20 | 10 | 0 | 0 | 10 | 0 | 20 | 20GA GALV | FCU 1-03 | 8 | 1 |  | MSN 2260030 | CAKE PARKWAY 4260007
3 | 74841 |  | 74841 | A |  | 2 | S | alum | MSN 2260030 |  | 2026-04-21 | 3 | 2026-04-21 | 30 | 0 | 0 | 30 | 0 | 40 |  | Hood tie in | 3 | 0 |  | PROJECT DOVE 6240041 | DC6 6250027
4 | 76415 | w | 76415 | A |  | 2 | S | ss | PROJECT DOVE 6240041 |  | 2026-04-23 | 5 | 2026-04-21 | 10 | 0 | 0 | 10 | 0 | 30 |  | 700 | 4 | 2 |  | DC6 6250027 | DOC JDC 6240023
5 | 75718 |  | 75718,75762,75765 | L |  | 6 | S/M | neal | DC6 6250027 | 1" liner | 2026-04-27 | 9 | 2026-04-21 | 130 | 0 | 0 | 130 | 90 | 210 | 24GA GALVANEAL | Supply sw corridor | 24 | 6 |  | PEWAUKEE HS 6240030 | GRANT ES 6250021
6 | 74684 |  | 74684 | A |  | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2026-04-27 | 10 | 2026-04-16 | 30 | 0 | 0 | 30 | 0 | 50 | 24GA GALVANEAL | Kiln EA | 7 | 11 |  | LAPCOR BIO A 2260011 | LAKE MILLS ES 6250012
7 | 2055 |  | L1-C2-RTU 19 | A |  | 7 | M |  | DC6 6250027 | flex | 2026-04-29 | 14 | 2026-04-09 | 170 | 0 | 0 | 170 | 140 | 420 | 18GA GALV |  | 12 | 20 |  | CHURCHILL 6250022 | MASTON R 6250019
8 | 2060 |  | L1-C3-RTU 14 | A |  | 8 | M |  | DC6 6250027 | flex | 2026-04-29 | 15 | 2026-04-09 | 200 | 0 | 0 | 200 | 100 | 510 | 18GA GALVANEAL |  | 6 | 20 |  | FALL RIVER 6260002 | MONROE 6240018
9 | 41717 | bth | 41717 |  |  |  | S/M | pcd | LAPCOR BIO A 2260011 |  | 2026-04-29 | 16 | 2026-04-21 | [5 empty] | 200 |  | 1st floor |  | 8 |  | ANTIGO 6250017 | MPS 4260004
10 | 6043 | bth | L4-EA-01 | A |  | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-05-01 | 17 | 2026-04-20 | 70 | 40 | 40 | 110 | 0 | 160 | 26GA GALV |  | 32 | 11 |  | GRANT ES 6250021 | OCTOPI 8250035
11 | 6044 | sp | L4-EA-02 | C |  | 5 | S/M |  | CHURCHILL 6250022 |  | 2026-05-01 | 18 | 2026-04-20 | 20 | 100 | 0 | 20 | 0 | 120 | 26GA GALV |  | 32 | 11 |  | WHC 6250007 | PEWAUKEE HS 6240030
12 | 6045 | bth | L4-EA-03 | A |  | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-05-01 | 19 | 2026-04-20 | 70 | 20 | 50 | 120 | 0 | 130 | 26GA GALV |  | 27 | 11 |  | MASTON R 6250019 | PLACON 4260005
13 | 6046 | bth | L4-EA-04 | C |  | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-05-01 | 20 | 2026-04-20 | 50 | 80 | 0 | 50 | 0 | 130 | 26GA GALV |  | 42 | 11 |  | UW STOUT 6250008 | PORTAGE MS 6250018
14 | 6047 |  | L4-SALP-01 | A |  | 5 | S/M |  | CHURCHILL 6250022 | flex | 2026-05-01 | 21 | 2026-04-20 | 120 | 0 | 0 | 120 | 0 | 140 | 26GA GALV |  | 12 | 11 |  | EXACT PASP 2260014 | PROJECT DOVE 6240041
15 | 6048 |  | L4-SALP-02 | L |  | 6 | S/M |  | CHURCHILL 6250022 | flex | 2026-05-01 | 22 | 2026-04-20 | 130 | 0 | 0 | 130 | 0 | 150 | 26GA GALV |  | 13 | 11 |  | SHRINE 6240034 | PROMEGA BTC 6250020
16 | 6049 | bth | L4-SAMP-01 | L |  | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-05-01 | 23 | 2026-04-20 | 70 | 10 | 20 | 90 | 0 | 130 | 24GA GALV |  | 21 | 11 |  | PORTAGE MS 6250018 | SHRINE 6240034
17 | 6050 | bth | L4-SAMP-02 | L |  | 3 | S |  | CHURCHILL 6250022 |  | 2026-05-01 | 24 | 2026-04-20 | 20 | 50 | 0 | 20 | 0 | 80 | 24GA GALV |  | 13 | 11 |  | UWP 6240021 | UW LEVY HALL 6230028
18 | 6051 | bth | L4-SAMP-03 | L |  | 5 | S/M |  | CHURCHILL 6250022 |  | 2026-05-01 | 25 | 2026-04-20 | 60 | 10 | 40 | 100 | 0 | 130 | 24GA GALV |  | 16 | 11 |  | RCIS 6250011 | UW STOUT 6250008
19 | 6052 | bth | L4-SAMP-04 | L |  | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-05-01 | 26 | 2026-04-20 | 70 | 50 | 20 | 90 | 0 | 160 | 24GA GALV |  | 29 | 11 |  | OCTOPI 8250035 | UWP 6240021
20 | 76855 |  | 76854-56 |  |  |  | S/M |  | CHURCHILL 6250022 | dm's | 2026-05-01 | 27 | 2026-04-21 | [5 empty] | 200 |  | Ductmate frames |  | 10 |  | LAKE MILLS ES 6250012 | WAUNAKEE 6230013
21 | 10017 | w | 10017 | A |  | 19 | M/L |  | FALL RIVER 6260002 |  | 2026-05-01 | 28 | 2026-04-02 | 460 | 0 | 0 | 460 | 0 | 1240 | 18GA GALV | Kiln hood, slot hood |  | 29 |  | UWRF 6230010 | WHC 6250007
22 | 82849 | sp | 82849-51,22849 | L |  | 83 | L |  | ANTIGO 6250017 | oval accuflange | 2026-05-04 | 29 | 2026-04-09 | 340 | 1730 | 0 | 340 | 0 | 3470 | 20GA GALV | 2nd floor | 71 | 25 |  | WAUNAKEE 6230013 | WHC 8250008
23 | 82854 |  | 82854 | A |  | 14 | M/L |  | ANTIGO 6250017 | 2" liner, accuflange | 2026-05-04 | 30 | 2026-04-09 | 140 | 30 | 180 | 320 | 250 | 870 | 18GA GALV |  | 8 | 25 |  | PERRENIAL YOGA 10065928 | CHURCHILL 6250022
24 | 74905 | w | 74905A-C | C |  | 12 | M/L |  | GRANT ES 6250021 | 1.5" liner | 2026-05-04 | 31 | 2026-04-21 | 280 | 0 | 0 | 280 | 225 | 1010 | 16GA GALV | Curb adapter | 22 | 13 |  | UW RESEARCH 4250056 | EXACT 2260020
25 | 74906 |  | 74906 | L |  | 18 | M |  | GRANT ES 6250021 |  | 2026-05-04 | 32 | 2026-04-21 | 430 | 0 | 0 | 430 | 0 | 540 | 24GA GALV | EA drops | 55 | 13 |  |  | TERSO 2260019
26 | 74907 |  | 74907,74910,74911 |  |  |  | S/M |  | GRANT ES 6250021 | 1/2" armaflex, flex | 2026-05-04 | 33 | 2026-04-21 | [5 empty] | 150 |  | Ahu 6 sa, raf 6 inlet |  | 13 |  |  | UW AVRL
27 | 74908 |  | 74908-09,74912-14 |  |  |  | S |  | GRANT ES 6250021 | flex | 2026-05-04 | 34 | 2026-04-21 | [5 empty] | 100 |  | Ahu 6 mixed air, raf 6 inlet |  | 13 |  |  | RCIS 6250011
28 | 7000 |  | LL MER-EA 1 |  |  |  | S/M |  | WHC 6250007 |  | 2026-05-04 | 35 | 2026-04-08 | [5 empty] | 280 |  |  | 11 | 26 |  |  | FRANK&ANDREAS 4250061
29 | 7001 |  | LL MER-EA 2 |  |  |  | M |  | WHC 6250007 |  | 2026-05-04 | 36 | 2026-04-08 | [5 empty] | 410 |  |  | 18 | 26 |  |  | CATALENT 6260008
30 | 7002 |  | LL MER-EA 3 |  |  |  | M |  | WHC 6250007 |  | 2026-05-04 | 37 | 2026-04-08 | [5 empty] | 420 |  |  | 14 | 26 |  |  | FALL RIVER 6260002
31 | 7003 |  | LL MER-OA 1 |  |  |  | M |  | WHC 6250007 |  | 2026-05-04 | 38 | 2026-04-08 | [5 empty] | 420 |  |  | 12 | 26 |  |  | LABCORP 2260024
32 | 7004 |  | LL MER-OA 2 |  |  |  | L |  | WHC 6250007 |  | 2026-05-04 | 39 | 2026-04-08 | [5 empty] | 2810 |  |  | 17 | 26 |  |  | MILES BLUFF 30004802
33 | 7005 |  | LL MER-OA 3 |  |  |  | S/M |  | WHC 6250007 |  | 2026-05-04 | 40 | 2026-04-08 | [5 empty] | 300 |  |  | 2 | 26 |  |  | UW RESEARCH 4250056
34 | 7006 |  | LL MER-OA 4 |  |  |  | S/M |  | WHC 6250007 |  | 2026-05-04 | 41 | 2026-04-08 | [5 empty] | 230 |  |  | 6 | 26 |  |  | EXACT PASP 2260014
35 | 7007 |  | LL MER-OA 5 |  |  |  | M |  | WHC 6250007 |  | 2026-05-04 | 42 | 2026-04-08 | [5 empty] | 630 |  |  | 8 | 26 |  |  | LABCORP 2260026
36 | 7008 |  | LL MER-OA 6 |  |  |  | S/M |  | WHC 6250007 |  | 2026-05-04 | 43 | 2026-04-08 | [5 empty] | 230 |  |  | 7 | 26
37 | 7009 |  | LL MER-OA VAV-5-0-1 |  |  |  | M |  | WHC 6250007 | 1" liner | 2026-05-04 | 44 | 2026-04-08 | [5 empty] | 380 |  |  | 13 | 26
38 | 7010 |  | LL MER-RAMP 1 |  |  |  | L |  | WHC 6250007 | dual wall | 2026-05-04 | 45 | 2026-04-08 | [5 empty] | 4790 |  |  | 22 | 26
39 | 7011 |  | LL MER-RAMP 2 |  |  |  | M/L |  | WHC 6250007 |  | 2026-05-04 | 46 | 2026-04-08 | [5 empty] | 1110 |  |  | 9 | 26
40 | 7012 |  | LL MER-RAMP 4 |  |  |  | L |  | WHC 6250007 | dual wall | 2026-05-04 | 47 | 2026-04-08 | [5 empty] | 1510 |  |  | 7 | 26
41 | 7013 |  | LL MER-RAMP 5 |  |  |  | L |  | WHC 6250007 |  | 2026-05-04 | 48 | 2026-04-08 | [5 empty] | 2200 |  |  | 21 | 26
42 | 64740 | sp | 64740 | L |  | 5 | S/M |  | MASTON R 6250019 |  | 2026-05-05 | 49 | 2026-04-20 | 10 | 110 | 0 | 10 | 0 | 130 | 24GA GALVANEAL |  | 20 | 15
43 | 4732 | bth | L2-VAV-1-2-15 | L |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 50 | 2026-04-16 | 30 | 10 | 0 | 30 | 0 | 50 | 24GA GALV |  | 8 | 19
44 | 4733 | bth | L2-VAV-1-2-16 | L |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 51 | 2026-04-16 | 30 | 20 | 0 | 30 | 0 | 60 | 24GA GALV |  | 8 | 19
45 | 4734 | bth | L2-VAV-1-2-17 | A |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 52 | 2026-04-16 | 30 | 10 | 0 | 30 | 0 | 40 | 24GA GALV |  | 7 | 19
46 | 4735 | bth | L2-VAV-1-2-18 | A |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 53 | 2026-04-16 | 30 | 10 | 0 | 30 | 0 | 50 | 24GA GALV |  | 8 | 19
47 | 4736 | bth | L2-VAV-1-2-19 | A |  | 3 | S |  | UW STOUT 6250008 | 1" liner | 2026-05-05 | 54 | 2026-04-16 | 50 | 10 | 0 | 50 | 30 | 70 | 24GA GALV |  | 7 | 19
48 | 4737 | bth | L2-VAV-1-2-19A | C |  | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-05-05 | 55 | 2026-04-16 | 30 | 10 | 0 | 30 | 30 | 50 | 24GA GALVANEAL |  | 4 | 19
49 | 4738 |  | L2-VAV-1-2-20 | A |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 56 | 2026-04-16 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  | 6 | 19
50 | 4739 | bth | L2-VAV-1-2-21 | A |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 57 | 2026-04-16 | 30 | 10 | 0 | 30 | 0 | 40 | 24GA GALV |  | 7 | 19
51 | 4740 | bth | L2-VAV-1-2-22 | A |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 58 | 2026-04-16 | 20 | 10 | 0 | 20 | 0 | 30 | 24GA GALV |  | 8 | 19
52 | 4741 |  | L2-VAV-1-2-23 | A |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 59 | 2026-04-16 | 20 | 20 | 0 | 20 | 0 | 40 | 24GA GALV |  | 8 | 19
53 | 4742 | bth | L2-VAV-1-2-24 | A |  | 3 | S |  | UW STOUT 6250008 | 1" liner | 2026-05-05 | 60 | 2026-04-16 | 60 | 10 | 0 | 60 | 20 | 100 | 24GA GALV |  | 11 | 19
54 | 4743 | bth | L2-VAV-1-2-25 | A |  | 4 | S |  | UW STOUT 6250008 | 1" liner | 2026-05-05 | 61 | 2026-04-16 | 40 | 40 | 0 | 40 | 0 | 90 | 24GA GALV |  | 14 | 19
55 | 4744 | bth | L2-VAV-1-2-26 | A |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 62 | 2026-04-16 | 30 | 10 | 0 | 30 | 0 | 50 | 24GA GALV |  | 6 | 19
56 | 4747 | bth | L2-VAV-1-2-29 | A |  | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | 63 | 2026-04-16 | 40 | 0 | 0 | 40 | 0 | 60 | 24GA GALV |  | 6 | 19
57 | 85174 | sp | 85174-75 |  |  |  | S |  | UW STOUT 6250008 |  | 2026-05-05 | 64 | 2026-04-21 | [5 empty] | 100 |  | L3-samp 2 |  | 14
58 | 3016 |  | SA 1 | A |  | 12 | M |  | EXACT PASP 2260014 |  | 2026-05-06 | 65 | 2026-04-14 | 170 | 0 | 110 | 280 | 0 | 390 | 24GA GALV |  | 15 | 22
59 | 3017 |  | SA 2 | A |  | 8 | S/M |  | EXACT PASP 2260014 |  | 2026-05-06 | 66 | 2026-04-14 | 70 | 0 | 110 | 180 | 0 | 240 | 24GA GALV |  | 12 | 22
60 | 3018 |  | EA 4 | A |  | 26 | M/L |  | EXACT PASP 2260014 |  | 2026-05-06 | 67 | 2026-04-14 | 350 | 0 | 280 | 630 | 0 | 910 | 24GA GALV |  | 30 | 22
61 | 3019 |  | EA 5 | A |  | 22 | M/L |  | EXACT PASP 2260014 |  | 2026-05-06 | 68 | 2026-04-14 | 260 | 0 | 270 | 530 | 0 | 850 | 22GA GALV |  | 22 | 22
62 | 3020 |  | EA 6 | A |  | 13 | M |  | EXACT PASP 2260014 |  | 2026-05-06 | 69 | 2026-04-14 | 130 | 0 | 190 | 320 | 0 | 430 | 24GA GALV |  | 21 | 22
63 | 3021 | sp | EA 4.1 | A |  | 2 | S |  | EXACT PASP 2260014 |  | 2026-05-06 | 70 | 2026-04-14 | 20 | 30 | 0 | 20 | 0 | 60 | 24GA GALV |  | 7 | 22
64 | 3022 | sp | EA 4.2 | A |  | 8 | S/M |  | EXACT PASP 2260014 |  | 2026-05-06 | 71 | 2026-04-14 | 10 | 190 | 0 | 10 | 0 | 240 | 24GA GALV |  | 18 | 22
65 | 3023 | sp | EA 4.3 | A |  | 3 | S |  | EXACT PASP 2260014 |  | 2026-05-06 | 72 | 2026-04-14 | 10 | 50 | 0 | 10 | 0 | 80 | 24GA GALV |  | 13 | 22
66 | 3024 | sp | EA 5.1 | A |  | 3 | S |  | EXACT PASP 2260014 |  | 2026-05-06 | 73 | 2026-04-14 | 10 | 60 | 0 | 10 | 0 | 90 | 24GA GALV |  | 8 | 22
67 | 3025 | sp | EA 5.2 | A |  | 4 | S |  | EXACT PASP 2260014 |  | 2026-05-06 | 74 | 2026-04-14 | 10 | 70 | 0 | 10 | 0 | 100 | 24GA GALV |  | 15 | 22
68 | 3026 | sp | EA 5.3 | A |  | 6 | S/M |  | EXACT PASP 2260014 |  | 2026-05-06 | 75 | 2026-04-14 | 20 | 120 | 0 | 20 | 0 | 170 | 24GA GALV |  | 25 | 22
69 | 3027 | sp | EA 6.1 | A |  | 4 | S/M |  | EXACT PASP 2260014 |  | 2026-05-06 | 76 | 2026-04-14 | 10 | 90 | 0 | 10 | 0 | 120 | 24GA GALV |  | 16 | 22
70 | 3028 | sp | EA 6.2 | A |  | 4 | S/M |  | EXACT PASP 2260014 |  | 2026-05-06 | 77 | 2026-04-14 | 10 | 80 | 0 | 10 | 0 | 110 | 24GA GALV |  | 16 | 22
71 | 3029 | sp | EA 6.3 | A |  | 3 | S |  | EXACT PASP 2260014 |  | 2026-05-06 | 78 | 2026-04-14 | 70 | 0 | 0 | 70 | 0 | 80 |  |  | 8 | 22
72 | 3030 | sp | SA 1.1 | L |  | 6 | S/M |  | EXACT PASP 2260014 |  | 2026-05-06 | 79 | 2026-04-14 | 10 | 130 | 0 | 10 | 0 | 160 | 24GA GALV |  | 9 | 22
73 | 3031 | sp | SA 2.1 | L |  | 5 | S/M |  | EXACT PASP 2260014 |  | 2026-05-06 | 80 | 2026-04-14 | 10 | 110 | 0 | 10 | 0 | 130 | 24GA GALV |  | 9 | 22
74 | 2131 |  | L1-E3-RTU 20 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-07 | 81 | 2026-04-21 | [5 empty] | 120 |  |  |  | 16
75 | 2132 |  | L1-E3-RTU 21 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-07 | 82 | 2026-04-21 | [5 empty] | 150 |  |  |  | 16
76 | 2133 |  | L1-E3-RTU 22 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-07 | 83 | 2026-04-21 | [5 empty] | 130 |  |  |  | 16
77 | 2134 |  | L1-E3-RTU 23 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-07 | 84 | 2026-04-21 | [5 empty] | 150 |  |  |  | 16
78 | 82955 | sp | 82955 | A |  | 2 | S |  | WHC 6250007 |  | 2026-05-07 | 86 | 2026-04-06 | 50 | 0 | 0 | 50 | 0 | 90 | 22GA GALV | 2nd floor sleeves | 53 | 31
79 | 76857 |  | 76857 |  |  |  | S |  | CHURCHILL 6250022 |  | 2026-05-08 | 87 | 2026-04-21 | [5 empty] | 100 |  | L4-ea-01 |  | 17
80 | 82847 | sp | 82847-48,22847 | A |  | 43 | L |  | ANTIGO 6250017 | oval accuflange | 2026-05-11 | 88 | 2026-04-09 | 170 | 890 | 0 | 170 | 0 | 1820 | 20GA GALV | 2nd floor | 44 | 32
81 | 1281 | bth | L5-EA-1 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 89 | 2026-04-15 | [5 empty] | 100 |  |  |  | 26
82 | 1282 | bth | L5-EA-2 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 90 | 2026-04-15 | [5 empty] | 50 |  |  |  | 26
83 | 1283 | bth | L5-EA-3 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 91 | 2026-04-15 | [5 empty] | 140 |  |  |  | 26
84 | 1284 | bth | L5-EA-4 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 92 | 2026-04-15 | [5 empty] | 140 |  |  |  | 26
85 | 1285 | bth | L5-EA-5 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 93 | 2026-04-15 | [5 empty] | 120 |  |  |  | 26
86 | 1286 | bth | L5-EA-6 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 94 | 2026-04-15 | [5 empty] | 100 |  |  |  | 26
87 | 1287 | bth | L5-EA-7 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 95 | 2026-04-15 | [5 empty] | 100 |  |  |  | 26
88 | 1288 | bth | L5-EA-8 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 96 | 2026-04-15 | [5 empty] | 90 |  |  |  | 26
89 | 1289 | bth | L5-EA-9 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 97 | 2026-04-15 | [5 empty] | 130 |  |  |  | 26
90 | 1290 |  | L5-SAMP-1 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 98 | 2026-04-15 | [5 empty] | 100 |  |  |  | 26
91 | 1291 |  | L5-SAMP-2 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 99 | 2026-04-15 | [5 empty] | 130 |  |  |  | 26
92 | 1292 |  | L5-SAMP-3 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 100 | 2026-04-15 | [5 empty] | 140 |  |  |  | 26
93 | 1293 |  | L5-SAMP-4 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 101 | 2026-04-15 | [5 empty] | 120 |  |  |  | 26
94 | 1294 |  | L5-SAMP-5 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 102 | 2026-04-15 | [5 empty] | 70 |  |  |  | 26
95 | 1295 |  | L5-SAMP-6 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 103 | 2026-04-15 | [5 empty] | 120 |  |  |  | 26
96 | 1296 |  | L5-SAMP-7 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 104 | 2026-04-15 | [5 empty] | 80 |  |  |  | 26
97 | 1297 |  | L5-SAMP-8 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 105 | 2026-04-15 | [5 empty] | 130 |  |  |  | 26
98 | 1298 |  | L5-SAMP-9 |  |  |  | S |  | SHRINE 6240034 |  | 2026-05-11 | 106 | 2026-04-15 | [5 empty] | 80 |  |  |  | 26
99 | 1299 |  | L5-SAMP-10 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 107 | 2026-04-15 | [5 empty] | 140 |  |  |  | 26
100 | 1300 |  | L5-SAMP-11 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 108 | 2026-04-15 | [5 empty] | 110 |  |  |  | 26
101 | 1301 |  | L5-SAMP-12 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 109 | 2026-04-15 | [5 empty] | 180 |  |  |  | 26
102 | 1302 |  | L5-SAMP-13 |  |  |  | S/M |  | SHRINE 6240034 |  | 2026-05-11 | 110 | 2026-04-15 | [5 empty] | 210 |  |  |  | 26
103 | 2066 |  | L1-A3A-SAMP 70 |  |  |  | M/L | neal | DC6 6250027 | 1" liner, VD | 2026-05-12 | 111 | 2026-04-16 | [5 empty] | 890 |  |  |  | 26
104 | 2067 |  | L1-A3A-SAMP 74 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-05-12 | 112 | 2026-04-16 | [5 empty] | 310 |  |  |  | 26
105 | 2068 |  | L1-A3A-SALP 73 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-12 | 113 | 2026-04-16 | [5 empty] | 420 |  |  |  | 26
106 | 2069 |  | L1-A3A-SALP 75 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-12 | 114 | 2026-04-16 | [5 empty] | 430 |  |  |  | 26
107 | 2070 |  | L1-A3A-RA 69 |  |  |  | M | neal | DC6 6250027 | 1" liner, VD | 2026-05-12 | 115 | 2026-04-16 | [5 empty] | 530 |  |  |  | 26
108 | 2071 | bth | L1-A3C-SAMP 85 |  |  |  | L | neal | DC6 6250027 |  | 2026-05-12 | 116 | 2026-04-16 | [5 empty] | 1720 |  |  |  | 26
109 | 2072 | bth | L1-A3C-SAMP 86 |  |  |  | M | neal | DC6 6250027 |  | 2026-05-12 | 117 | 2026-04-16 | [5 empty] | 610 |  |  |  | 26
110 | 2073 | bth | L1-A3C-SAMP 87 |  |  |  | M | neal | DC6 6250027 |  | 2026-05-12 | 118 | 2026-04-16 | [5 empty] | 630 |  |  |  | 26
111 | 2074 |  | L1-A3C-SALP 83 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-12 | 119 | 2026-04-16 | [5 empty] | 710 |  |  |  | 26
112 | 2075 | bth | L1-A3C-SALP 84 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-05-12 | 120 | 2026-04-16 | [5 empty] | 290 |  |  |  | 26
113 | 2076 |  | L1-A3C-SALP 88 |  |  |  | S/M | neal | DC6 6250027 | 1" liner | 2026-05-12 | 121 | 2026-04-16 | [5 empty] | 150 |  |  |  | 26
114 | 2077 | bth | L1-A3C-SALP 89 |  |  |  | S/M | neal | DC6 6250027 | 1" liner | 2026-05-12 | 122 | 2026-04-16 | [5 empty] | 270 |  |  |  | 26
115 | 2078 |  | L1-A3C-RA 79 |  |  |  | M | neal | DC6 6250027 |  | 2026-05-12 | 123 | 2026-04-16 | [5 empty] | 740 |  |  |  | 26
116 | 2079 |  | L1-A3C-RA 80 |  |  |  | M/L | neal | DC6 6250027 |  | 2026-05-12 | 124 | 2026-04-16 | [5 empty] | 860 |  |  |  | 26
117 | 2080 |  | L1-A3C-RA 81 |  |  |  | L | neal | DC6 6250027 | 1" liner | 2026-05-12 | 125 | 2026-04-16 | [5 empty] | 2640 |  |  |  | 26
118 | 2081 | bth | L1-A3C-EA 82 |  |  |  | S |  | DC6 6250027 |  | 2026-05-12 | 126 | 2026-04-16 | [5 empty] | 90 |  |  |  | 26
119 | 4748 |  | L2-TA 01 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 127 | 2026-04-16 | [5 empty] | 160 |  |  |  | 26
120 | 4749 |  | L2-TA 02 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 128 | 2026-04-16 | [5 empty] | 150 |  |  |  | 26
121 | 4750 |  | L2-TA 03 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 129 | 2026-04-16 | [5 empty] | 190 |  |  |  | 26
122 | 4751 |  | L2-TA 04 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 130 | 2026-04-16 | [5 empty] | 140 |  |  |  | 26
123 | 4752 |  | L2-TA 05 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 131 | 2026-04-16 | [5 empty] | 150 |  |  |  | 26
124 | 4753 |  | L2-TA 06 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 132 | 2026-04-16 | [5 empty] | 140 |  |  |  | 26
125 | 4754 |  | L2-TA 07 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 133 | 2026-04-16 | [5 empty] | 140 |  |  |  | 26
126 | 4755 |  | L2-TA 08 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 134 | 2026-04-16 | [5 empty] | 230 |  |  |  | 26
127 | 4756 |  | L2-TA 09 |  |  |  | S/M |  | UW STOUT 6250008 | 1' liner | 2026-05-12 | 135 | 2026-04-16 | [5 empty] | 320 |  |  |  | 26
128 | 2091 | sp | L1-A2C-SAMP 61 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-05-14 | 136 | 2026-04-20 | [5 empty] | 300 |  |  |  | 24
129 | 2092 |  | L1-A2C-RA 53 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-14 | 137 | 2026-04-20 | [5 empty] | 550 |  |  |  | 24
130 | 2093 | bth | L1-A2C-SALP 51 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-14 | 138 | 2026-04-20 | [5 empty] | 370 |  |  |  | 24
131 | 2094 | bth | L1-A2C-SALP 56 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-14 | 139 | 2026-04-20 | [5 empty] | 400 |  |  |  | 24
132 | 2095 | w | L1-A2C-SALP 57 |  |  |  | M/L | neal | DC6 6250027 | 1" liner | 2026-05-14 | 140 | 2026-04-20 | [5 empty] | 880 |  |  |  | 24
133 | 82956 | sp | 82956 |  |  |  | S |  | WHC 6250007 |  | 2026-05-14 | 143 | 2026-04-06 | [5 empty] | 100 |  | 3rd floor sleeves |  | 38
134 | 82959 | sp | 82959 |  |  |  | S |  | WHC 6250007 |  | 2026-05-14 | 144 | 2026-04-06 | [5 empty] | 100 |  | L5 boiler room |  | 38
135 | 7014 |  | LL MER-SAMP 1 |  |  |  | M/L |  | WHC 6250007 | dual wall | 2026-05-14 | 145 | 2026-04-09 | [5 empty] | 940 |  |  | 7 | 35
136 | 7015 |  | LL MER-SAMP 2 |  |  |  | M/L |  | WHC 6250007 | dual wall | 2026-05-14 | 146 | 2026-04-09 | [5 empty] | 1100 |  |  | 7 | 35
137 | 7016 |  | LL MER-SAMP 5 |  |  |  | L |  | WHC 6250007 | dual wall | 2026-05-14 | 147 | 2026-04-09 | [5 empty] | 2170 |  |  |  | 35
138 | 7017 |  | LL MER-SAMP 6 |  |  |  | S/M |  | WHC 6250007 |  | 2026-05-14 | 148 | 2026-04-09 | [5 empty] | 240 |  |  |  | 35
139 | 7018 |  | LL MER-SAMP 7 |  |  |  | L |  | WHC 6250007 |  | 2026-05-14 | 149 | 2026-04-09 | [5 empty] | 1530 |  |  |  | 35
140 | 7019 |  | LL MER-SAMP 8 |  |  |  | M |  | WHC 6250007 |  | 2026-05-14 | 150 | 2026-04-09 | [5 empty] | 390 |  |  |  | 35
141 | 7020 | sp | LL MER-SAMP 10 |  |  |  | S/M |  | WHC 6250007 |  | 2026-05-14 | 151 | 2026-04-09 | [5 empty] | 180 |  |  |  | 35
142 | 7021 |  | LL MER-SAMP 3 |  |  |  | M/L |  | WHC 6250007 | 1" dual wall | 2026-05-14 | 152 | 2026-04-09 | [5 empty] | 870 |  |  |  | 35
143 | 7022 |  | LL MER-SAMP 4 |  |  |  | M/L |  | WHC 6250007 |  | 2026-05-14 | 153 | 2026-04-09 | [5 empty] | 880 |  |  |  | 35
144 | 7023 |  | LL MER-SAMP 9 |  |  |  | M |  | WHC 6250007 |  | 2026-05-14 | 154 | 2026-04-09 | [5 empty] | 470 |  |  |  | 35
145 | 7024 |  | LL MER-RAMP 3 |  |  |  | L |  | WHC 6250007 |  | 2026-05-14 | 155 | 2026-04-09 | [5 empty] | 1340 |  |  |  | 35
146 | 7025 |  | LL MER-RAMP 6 |  |  |  | S/M |  | WHC 6250007 |  | 2026-05-14 | 156 | 2026-04-09 | [5 empty] | 350 |  |  |  | 35
147 | 2125 |  | L1-E2-RTU 24 |  |  |  | M | neal | DC6 6250027 | 1" liner, flex | 2026-05-15 | 157 | 2026-04-21 | [5 empty] | 380 |  |  |  | 24
148 | 2126 |  | L1-E2-RTU 25 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-15 | 158 | 2026-04-21 | [5 empty] | 130 |  |  |  | 24
149 | 2127 |  | L1-E2-RTU 26 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-15 | 159 | 2026-04-21 | [5 empty] | 160 |  |  |  | 24
150 | 2128 |  | L1-E2-RTU 27 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-15 | 160 | 2026-04-21 | [5 empty] | 160 |  |  |  | 24
151 | 2129 |  | L1-E2-RTU 28 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-15 | 161 | 2026-04-21 | [5 empty] | 140 |  |  |  | 24
152 | 2130 |  | L1-E2-RTU 29 |  |  |  | M | neal | DC6 6250027 | 1" liner, flex | 2026-05-15 | 162 | 2026-04-21 | [5 empty] | 370 |  |  |  | 24
153 | 76668 |  | 76668 |  |  |  | S |  | PORTAGE MS 6250018 | 1" liner | 2026-05-15 | 163 | 2026-04-20 | [5 empty] | 100 |  | RE 12-13 |  | 25
154 | 4704 |  | L2-CAV-4-2-1 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-05-15 | 164 | 2026-04-06 | [5 empty] | 240 |  |  |  | 39
155 | 4705 |  | L2-VAV-1-2-1 |  |  |  | S |  | UW STOUT 6250008 | 1" liner | 2026-05-15 | 165 | 2026-04-06 | [5 empty] | 50 |  |  |  | 39
156 | 4706 |  | L2-VAV-1-2-6 |  |  |  | S/M | neal | UW STOUT 6250008 | 1" liner | 2026-05-15 | 166 | 2026-04-06 | [5 empty] | 210 |  |  |  | 39
157 | 4707 |  | L2-VAV-1-2-7 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-05-15 | 167 | 2026-04-06 | [5 empty] | 200 |  |  |  | 39
158 | 4708 |  | L2-VAV-1-2-8 |  |  |  | S/M | neal | UW STOUT 6250008 | 1" liner | 2026-05-15 | 168 | 2026-04-06 | [5 empty] | 200 |  |  |  | 39
159 | 4709 | sp | L3-SHAFT EA D 1 |  |  |  | S | alum | UW STOUT 6250008 |  | 2026-05-15 | 169 | 2026-04-06 | [5 empty] | 20 |  |  |  | 39
160 | 4710 | sp | L3-SHAFT EA D 2 |  |  |  | S | alum | UW STOUT 6250008 |  | 2026-05-15 | 170 | 2026-04-06 | [5 empty] | 20 |  |  |  | 39
161 | 4711 | sp | L4-SHAFT EA D 1 |  |  |  | S | alum | UW STOUT 6250008 |  | 2026-05-15 | 171 | 2026-04-06 | [5 empty] | 20 |  |  |  | 39
162 | 4712 | sp | L4-SHAFT EA D 2 |  |  |  | S | alum | UW STOUT 6250008 |  | 2026-05-15 | 172 | 2026-04-06 | [5 empty] | 20 |  |  |  | 39
163 | 4713 | sp | L5-SHAFT EA D 1 |  |  |  | S | alum | UW STOUT 6250008 |  | 2026-05-15 | 173 | 2026-04-06 | [5 empty] | 20 |  |  |  | 39
164 | 4714 | sp | L5-SHAFT EA D 2 |  |  |  | S | alum | UW STOUT 6250008 |  | 2026-05-15 | 174 | 2026-04-06 | [5 empty] | 20 |  |  |  | 39
165 | 2096 |  | L1-A3D-RA 65 |  |  |  | L | neal | DC6 6250027 | 1" liner, VD | 2026-05-19 | 175 | 2026-04-20 | [5 empty] | 1890 |  |  |  | 29
166 | 2097 |  | L1-A3D-RA 68 |  |  |  | M | neal | DC6 6250027 | 1" liner, VD | 2026-05-19 | 176 | 2026-04-20 | [5 empty] | 460 |  |  |  | 29
167 | 2098 | bth | L1-A3D-SAMP 66 |  |  |  | L | neal | DC6 6250027 | 1" liner | 2026-05-19 | 177 | 2026-04-20 | [5 empty] | 1560 |  |  |  | 29
168 | 2099 |  | L1-A3D-SAMP 67 |  |  |  | M | neal | DC6 6250027 | 1" liner, VD | 2026-05-19 | 178 | 2026-04-20 | [5 empty] | 720 |  |  |  | 29
169 | 2100 | bth | L1-A3D-SAMP 96 |  |  |  | L | neal | DC6 6250027 |  | 2026-05-19 | 179 | 2026-04-20 | [5 empty] | 1930 |  |  |  | 29
170 | 2101 | bth | L1-A3D-SAMP 97 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-19 | 180 | 2026-04-20 | [5 empty] | 590 |  |  |  | 29
171 | 2102 | bth | L1-A3D-SALP 92 |  |  |  | S/M | neal | DC6 6250027 | 1" liner | 2026-05-19 | 181 | 2026-04-20 | [5 empty] | 320 |  |  |  | 29
172 | 2103 |  | L1-A3D-SALP 93 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-19 | 182 | 2026-04-20 | [5 empty] | 740 |  |  |  | 29
173 | 2104 | bth | L1-A3D-SALP 94 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-05-19 | 183 | 2026-04-20 | [5 empty] | 300 |  |  |  | 29
174 | 2105 |  | L1-A3D-SALP 95 |  |  |  | S/M | neal | DC6 6250027 | 1" liner | 2026-05-19 | 184 | 2026-04-20 | [5 empty] | 160 |  |  |  | 29
175 | 4715 | bth | L2-VAV-1-2-11 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-05-19 | 185 | 2026-04-06 | [5 empty] | 260 |  |  |  | 43
176 | 4716 | bth | L2-VAV-2-2-10 |  |  |  | S |  | UW STOUT 6250008 | 1" liner | 2026-05-19 | 186 | 2026-04-06 | [5 empty] | 30 |  |  |  | 43
177 | 4717 | bth | L2-VAV-2-2-11 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-05-19 | 187 | 2026-04-06 | [5 empty] | 120 |  |  |  | 43
178 | 4718 | bth | L2-VAV-2-2-12 |  |  |  | S |  | UW STOUT 6250008 |  | 2026-05-19 | 188 | 2026-04-06 | [5 empty] | 60 |  |  |  | 43
179 | 4719 | bth | L2-VAV-2-2-13 |  |  |  | S |  | UW STOUT 6250008 | 1" liner | 2026-05-19 | 189 | 2026-04-06 | [5 empty] | 60 |  |  |  | 43
180 | 4720 | bth | L2-VAV-2-2-14 |  |  |  | M |  | UW STOUT 6250008 | 1" liner | 2026-05-19 | 190 | 2026-04-06 | [5 empty] | 390 |  |  |  | 43
181 | 4721 | bth | L2-VAV-2-2-15 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-05-19 | 191 | 2026-04-06 | [5 empty] | 210 |  |  |  | 43
182 | 4722 | bth | L2-VAV-2-2-16 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-05-19 | 192 | 2026-04-06 | [5 empty] | 180 |  |  |  | 43
183 | 4723 | bth | L2-VAV-2-2-18 |  |  |  | S/M | neal | UW STOUT 6250008 | 1" liner | 2026-05-19 | 193 | 2026-04-06 | [5 empty] | 240 |  |  |  | 43
184 | 4724 | bth | L2-VAV-2-2-19 |  |  |  | S/M | neal | UW STOUT 6250008 | 1" liner | 2026-05-19 | 194 | 2026-04-06 | [5 empty] | 310 |  |  |  | 43
185 | 4725 | bth | L2-VAV-2-2-23 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-05-19 | 195 | 2026-04-06 | [5 empty] | 120 |  |  |  | 43
186 | 4778 |  | L1-SAMP 11 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-19 | 196 | 2026-04-21 | [5 empty] | 1100 |  |  |  | 28
187 | 4779 | bth | L1-SAMP 12 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-19 | 197 | 2026-04-21 | [5 empty] | 1020 |  |  |  | 28
188 | 4789 | bth | L1-SAMP 02 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-19 | 198 | 2026-04-21 | [5 empty] | 910 |  |  |  | 28
189 | 4790 |  | L1-SAMP 03 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-19 | 199 | 2026-04-21 | [5 empty] | 1020 |  |  |  | 28
190 | 4793 |  | L1-SAMP 06 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-05-19 | 200 | 2026-04-21 | [5 empty] | 590 |  |  |  | 28
191 | 4794 | bth | L1-SAMP 07 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-05-19 | 201 | 2026-04-21 | [5 empty] | 180 |  |  |  | 28
192 | 4795 | bth | L1-SAMP 08 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-05-19 | 202 | 2026-04-21 | [5 empty] | 710 |  |  |  | 28
193 | 4797 | bth | L1-SAMP 10 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-05-19 | 203 | 2026-04-21 | [5 empty] | 370 |  |  |  | 28
194 | 3032 |  | EA 1 |  |  |  | S/M |  | EXACT PASP 2260014 |  | 2026-05-20 | 204 | 2026-04-20 | [5 empty] | 220 |  |  |  | 30
195 | 3033 |  | EA 2 |  |  |  | M |  | EXACT PASP 2260014 |  | 2026-05-20 | 205 | 2026-04-20 | [5 empty] | 570 |  |  |  | 30
196 | 3034 |  | EA 3 |  |  |  | M |  | EXACT PASP 2260014 |  | 2026-05-20 | 206 | 2026-04-20 | [5 empty] | 510 |  |  |  | 30
197 | 3035 |  | RA 1 |  |  |  | S/M |  | EXACT PASP 2260014 |  | 2026-05-20 | 207 | 2026-04-20 | [5 empty] | 240 |  |  |  | 30
198 | 3036 | sp | EA 2.1 |  |  |  | S/M |  | EXACT PASP 2260014 |  | 2026-05-20 | 208 | 2026-04-20 | [5 empty] | 190 |  |  |  | 30
199 | 3037 | sp | EA 3.1 |  |  |  | S/M |  | EXACT PASP 2260014 |  | 2026-05-20 | 209 | 2026-04-20 | [5 empty] | 170 |  |  |  | 30
200 | 3038 | sp | EA 3.2 |  |  |  | S/M |  | EXACT PASP 2260014 |  | 2026-05-20 | 210 | 2026-04-20 | [5 empty] | 300 |  |  |  | 30
201 | 2082 | bth | L1-A2A-SAMP 46 |  |  |  | L | neal | DC6 6250027 | flex | 2026-05-21 | 211 | 2026-04-16 | [5 empty] | 1490 |  |  |  | 35
202 | 2083 | bth | L1-A2A-SAMP 47 |  |  |  | L | neal | DC6 6250027 | flex | 2026-05-21 | 212 | 2026-04-16 | [5 empty] | 1730 |  |  |  | 35
203 | 2084 |  | L1-A2A-RA 52 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-21 | 213 | 2026-04-16 | [5 empty] | 300 |  |  |  | 35
204 | 2085 |  | L1-A2A-RA 56 |  |  |  | M/L | neal | DC6 6250027 |  | 2026-05-21 | 214 | 2026-04-16 | [5 empty] | 880 |  |  |  | 35
205 | 2086 |  | L1-A2A-RA 57 |  |  |  | M | neal | DC6 6250027 |  | 2026-05-21 | 215 | 2026-04-16 | [5 empty] | 800 |  |  |  | 35
206 | 2087 | bth | L1-A2A-SALP 50 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-21 | 216 | 2026-04-16 | [5 empty] | 260 |  |  |  | 35
207 | 2088 |  | L1-A2A-SALP 58 |  |  |  | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-05-21 | 217 | 2026-04-16 | [5 empty] | 210 |  |  |  | 35
208 | 2089 | bth | L1-A2A-SALP 60 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-05-21 | 218 | 2026-04-16 | [5 empty] | 270 |  |  |  | 35
209 | 2090 | bth | L1-A2A-EA 62 |  |  |  | S | neal | DC6 6250027 | flex | 2026-05-21 | 219 | 2026-04-16 | [5 empty] | 80 |  |  |  | 35
210 | 76126 |  | 76126 |  |  |  | S |  | UWP 6240021 |  | 2026-05-21 | 220 | 2026-04-01 | [5 empty] | 100 |  | DOAS 1 CB 39 |  | 50
211 | 82957 | sp | 82957 |  |  |  | S |  | WHC 6250007 |  | 2026-05-21 | 222 | 2026-04-06 | [5 empty] | 100 |  | 4th floor sleeves |  | 45
212 | 74680 |  | 74680 |  |  |  | S | neal | FALL RIVER 6260002 |  | 2026-05-25 | 223 | 2026-04-10 | [5 empty] | 100 |  | MAU's |  | 45
213 | 74681 | sp | 74681-82 |  |  |  | S |  | FALL RIVER 6260002 |  | 2026-05-25 | 224 | 2026-04-10 | [5 empty] | 100 |  | VE 7&8 |  | 45
214 | 76358 |  | 76358 |  |  |  | S | neal | FALL RIVER 6260002 |  | 2026-05-25 | 225 | 2026-04-10 | [5 empty] | 100 |  | Transfers |  | 45
215 | 76359 | bth | 76359 |  |  |  | S | neal | FALL RIVER 6260002 | flex | 2026-05-25 | 226 | 2026-04-10 | [5 empty] | 100 |  | BCU 1 |  | 45
216 | 76360 | bth | 76360 |  |  |  | S | neal | FALL RIVER 6260002 |  | 2026-05-25 | 227 | 2026-04-10 | [5 empty] | 100 |  | Clean lab 1131 |  | 45
217 | 76361 | bth | 76361 |  |  |  | S | neal | FALL RIVER 6260002 |  | 2026-05-25 | 228 | 2026-04-10 | [5 empty] | 100 |  | Noted |  | 45
218 | 76362 | bth | 76362 |  |  |  | S | neal | FALL RIVER 6260002 | flex | 2026-05-25 | 229 | 2026-04-10 | [5 empty] | 100 |  | Noted |  | 45
219 | 76363 |  | 76363 |  |  |  | S | neal | FALL RIVER 6260002 | flex, VD | 2026-05-25 | 230 | 2026-04-10 | [5 empty] | 100 |  | Auto lab DF 1 |  | 45
220 | 76364 |  | 76364 |  |  |  | S | neal | FALL RIVER 6260002 | VD | 2026-05-25 | 231 | 2026-04-10 | [5 empty] | 100 |  | Auto lab EA |  | 45
221 | 76366 |  | 76366 |  |  |  | S | neal | FALL RIVER 6260002 | VD | 2026-05-25 | 232 | 2026-04-10 | [5 empty] | 100 |  | EA auto lab |  | 45
222 | 76367 | bth | 76367-68 |  |  |  | S | neal | FALL RIVER 6260002 | flex | 2026-05-25 | 233 | 2026-04-10 | [5 empty] | 100 |  | Animal lab |  | 45
223 | 76845 |  | 76845 |  |  |  | S | neal | FALL RIVER 6260002 |  | 2026-05-25 | 234 | 2026-04-10 | [5 empty] | 100 |  | Animal lab EA |  | 45
224 | 76846 | sp | 76846 |  |  |  | S |  | FALL RIVER 6260002 |  | 2026-05-25 | 235 | 2026-04-10 | [5 empty] | 100 |  | Reception |  | 45
225 | 74686 |  | 74686-90 |  |  |  | S/M | neal | FALL RIVER 6260002 |  | 2026-05-25 | 236 | 2026-04-21 | [5 empty] | 200 |  | Drops |  | 34
226 | 2106 |  | L1-A3B-SAMP 72 |  |  |  | M/L | neal | DC6 6250027 | 1" liner | 2026-05-26 | 237 | 2026-04-20 | [5 empty] | 920 |  |  |  | 36
227 | 2107 | sp | L1-A3B-SAMP 77 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-05-26 | 238 | 2026-04-20 | [5 empty] | 310 |  |  |  | 36
228 | 2108 | bth | L1-A3B-SALP 76 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-26 | 239 | 2026-04-20 | [5 empty] | 360 |  |  |  | 36
229 | 2109 |  | L1-A3B-SALP 78 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-26 | 240 | 2026-04-20 | [5 empty] | 370 |  |  |  | 36
230 | 2110 |  | L1-A3B-RA 71 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-05-26 | 241 | 2026-04-20 | [5 empty] | 550 |  |  |  | 36
231 | 4768 | bth | L1-SAMP 21 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-05-26 | 242 | 2026-04-21 | [5 empty] | 510 |  |  |  | 35
232 | 4769 | bth | L1-SAMP 22 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-26 | 243 | 2026-04-21 | [5 empty] | 950 |  |  |  | 35
233 | 4770 | bth | L1-SAMP 23 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-26 | 244 | 2026-04-21 | [5 empty] | 890 |  |  |  | 35
234 | 4774 |  | L1-SAMP 27 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-26 | 245 | 2026-04-21 | [5 empty] | 880 |  |  |  | 35
235 | 4775 |  | L1-SAMP 28 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-05-26 | 246 | 2026-04-21 | [5 empty] | 740 |  |  |  | 35
236 | 4783 |  | L1-SAMP 16 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-26 | 247 | 2026-04-21 | [5 empty] | 1260 |  |  |  | 35
237 | 4784 | bth | L1-SAMP 17 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-05-26 | 248 | 2026-04-21 | [5 empty] | 750 |  |  |  | 35
238 | 4785 | bth | L1-SAMP 18 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-05-26 | 249 | 2026-04-21 | [5 empty] | 570 |  |  |  | 35
239 | 4786 | bth | L1-SAMP 19 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-05-26 | 250 | 2026-04-21 | [5 empty] | 680 |  |  |  | 35
240 | 4787 | bth | L1-SAMP 20 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-26 | 251 | 2026-04-21 | [5 empty] | 970 |  |  |  | 35
241 | 4788 |  | L1-SAMP 01 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-05-26 | 252 | 2026-04-21 | [5 empty] | 1200 |  |  |  | 35
242 | 82958 | sp | 82958 |  |  |  | S |  | WHC 6250007 |  | 2026-05-28 | 253 | 2026-04-06 | [5 empty] | 100 |  | Level 5 sleeves |  | 52
243 | 4726 |  | L2-TA 10 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-05-30 | 254 | 2026-04-07 | [5 empty] | 120 |  |  |  | 53
244 | 4727 | bth | L2-VAV-1-2-10 |  |  |  | M |  | UW STOUT 6250008 | 1" liner | 2026-05-30 | 255 | 2026-04-07 | [5 empty] | 420 |  |  |  | 53
245 | 4762 | w | L2-CEA 01 |  |  |  | S/M | ss | UW STOUT 6250008 |  | 2026-05-30 | 256 | 2026-04-21 | [5 empty] | 260 |  |  |  | 39
246 | 4771 | bth | L1-SAMP 24 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-06-02 | 257 | 2026-04-21 | [5 empty] | 720 |  |  |  | 42
247 | 4772 | bth | L1-SAMP 25 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-06-02 | 258 | 2026-04-21 | [5 empty] | 550 |  |  |  | 42
248 | 4773 | bth | L1-SAMP 26 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-06-02 | 259 | 2026-04-21 | [5 empty] | 210 |  |  |  | 42
249 | 4776 |  | L1-SAMP 29 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-06-02 | 260 | 2026-04-21 | [5 empty] | 160 |  |  |  | 42
250 | 4777 |  | L1-SAMP 30 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-06-02 | 261 | 2026-04-21 | [5 empty] | 220 |  |  |  | 42
251 | 4780 | sp | L1-SAMP 13 |  |  |  | S |  | UW STOUT 6250008 |  | 2026-06-02 | 262 | 2026-04-21 | [5 empty] | 100 |  |  |  | 42
252 | 4781 |  | L1-SAMP 14 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-06-02 | 263 | 2026-04-21 | [5 empty] | 490 |  |  |  | 42
253 | 4782 |  | L1-SAMP 15 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-06-02 | 264 | 2026-04-21 | [5 empty] | 760 |  |  |  | 42
254 | 4791 |  | L1-SAMP 04 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-06-02 | 265 | 2026-04-21 | [5 empty] | 430 |  |  |  | 42
255 | 4792 | bth | L1-SAMP 05 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-06-02 | 266 | 2026-04-21 | [5 empty] | 450 |  |  |  | 42
256 | 4796 | bth | L1-SAMP 09 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-06-02 | 267 | 2026-04-21 | [5 empty] | 110 |  |  |  | 42
257 | 2111 | bth | L1-A2D-SAMP 64 |  |  |  | M/L | neal | DC6 6250027 | 1" liner | 2026-06-03 | 268 | 2026-04-20 | [5 empty] | 1180 |  |  |  | 44
258 | 2112 | bth | L1-A2D-RA 55 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-06-03 | 269 | 2026-04-20 | [5 empty] | 580 |  |  |  | 44
259 | 2113 | bth | L1-A2D-SALP 52 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-06-03 | 270 | 2026-04-20 | [5 empty] | 400 |  |  |  | 44
260 | 2114 |  | L1-A2D-SALP 53 |  |  |  | M | neal | DC6 6250027 | 1" liner | 2026-06-03 | 271 | 2026-04-20 | [5 empty] | 410 |  |  |  | 44
261 | 2115 | bth | L1-A2B-SAMP 43 |  |  |  | L | neal | DC6 6250027 | 1" liner, flex | 2026-06-03 | 272 | 2026-04-21 | [5 empty] | 1390 |  |  |  | 43
262 | 2116 | bth | L1-A2B-SAMP 44 |  |  |  | L | neal | DC6 6250027 | 1" liner, flex | 2026-06-03 | 273 | 2026-04-21 | [5 empty] | 1680 |  |  |  | 43
263 | 2117 | bth | L1-A2B-SAMP 45 |  |  |  | M/L | neal | DC6 6250027 | flex | 2026-06-03 | 274 | 2026-04-21 | [5 empty] | 1290 |  |  |  | 43
264 | 2118 | bth | L1-A2B-SALP 48 |  |  |  | M/L | neal | DC6 6250027 | 1" liner, flex | 2026-06-03 | 275 | 2026-04-21 | [5 empty] | 1120 |  |  |  | 43
265 | 2119 | bth | L1-A2B-SALP 58 |  |  |  | M | neal | DC6 6250027 | 1" liner, flex | 2026-06-03 | 276 | 2026-04-21 | [5 empty] | 400 |  |  |  | 43
266 | 2120 |  | L1-A2B-SALP 59 |  |  |  | M | ss,neal | DC6 6250027 | 1" liner, flex | 2026-06-03 | 277 | 2026-04-21 | [5 empty] | 760 |  |  |  | 43
267 | 2121 |  | L1-A2B-RA 52 |  |  |  | L | neal | DC6 6250027 | 1" liner, flex | 2026-06-03 | 278 | 2026-04-21 | [5 empty] | 2640 |  |  |  | 43
268 | 2122 |  | L1-A2B-RA 53 |  |  |  | M | neal | DC6 6250027 |  | 2026-06-03 | 279 | 2026-04-21 | [5 empty] | 710 |  |  |  | 43
269 | 2123 |  | L1-A2B-RA 54 |  |  |  | L | neal | DC6 6250027 | 1" liner, flex | 2026-06-03 | 280 | 2026-04-21 | [5 empty] | 2640 |  |  |  | 43
270 | 2124 |  | L1-A2B-RA 63 |  |  |  | M | neal | DC6 6250027 | 1" liner, flex | 2026-06-03 | 281 | 2026-04-21 | [5 empty] | 480 |  |  |  | 43
271 | 7026 | bth | LL-DC SA 1 |  |  |  | S | neal | WHC 6250007 |  | 2026-06-04 | 282 | 2026-04-09 | [5 empty] | 100 |  |  |  | 56
272 | 7027 | sp | LL-EA 1 |  |  |  | S/M | pcd | WHC 6250007 |  | 2026-06-04 | 283 | 2026-04-09 | [5 empty] | 150 |  |  |  | 56
273 | 7028 |  | LL-EA 2 |  |  |  | M | neal | WHC 6250007 |  | 2026-06-04 | 284 | 2026-04-09 | [5 empty] | 380 |  |  |  | 56
274 | 7029 |  | LL-EA 3 |  |  |  | S/M | neal | WHC 6250007 |  | 2026-06-04 | 285 | 2026-04-09 | [5 empty] | 290 |  |  |  | 56
275 | 7030 |  | LL-EA 4 |  |  |  | S/M | neal | WHC 6250007 |  | 2026-06-04 | 286 | 2026-04-09 | [5 empty] | 130 |  |  |  | 56
276 | 7031 |  | LL-EA 5 |  |  |  | S/M | neal | WHC 6250007 |  | 2026-06-04 | 287 | 2026-04-09 | [5 empty] | 210 |  |  |  | 56
277 | 7032 |  | LL-RA 1 |  |  |  | M | neal | WHC 6250007 |  | 2026-06-04 | 288 | 2026-04-09 | [5 empty] | 770 |  |  |  | 56
278 | 7033 |  | LL-RA 2 |  |  |  | M | neal | WHC 6250007 |  | 2026-06-04 | 289 | 2026-04-09 | [5 empty] | 480 |  |  |  | 56
279 | 7034 |  | LL-RA 3 |  |  |  | M/L | neal | WHC 6250007 |  | 2026-06-04 | 290 | 2026-04-09 | [5 empty] | 820 |  |  |  | 56
280 | 7035 |  | LL-RA 4 |  |  |  | M | neal | WHC 6250007 | VD | 2026-06-04 | 291 | 2026-04-09 | [5 empty] | 520 |  |  |  | 56
281 | 7036 |  | LL-RA 5 |  |  |  | S/M | neal | WHC 6250007 | bird screen, VD | 2026-06-04 | 292 | 2026-04-09 | [5 empty] | 260 |  |  |  | 56
282 | 7037 | bth | LL-SAMP 1 |  |  |  | M |  | WHC 6250007 |  | 2026-06-04 | 293 | 2026-04-09 | [5 empty] | 740 |  |  |  | 56
283 | 7038 | bth | LL-SAMP 2 |  |  |  | M |  | WHC 6250007 |  | 2026-06-04 | 294 | 2026-04-09 | [5 empty] | 470 |  |  |  | 56
284 | 7039 | bth | LL-SAMP 3 |  |  |  | M |  | WHC 6250007 |  | 2026-06-04 | 295 | 2026-04-09 | [5 empty] | 450 |  |  |  | 56
285 | 7040 | bth | LL-SAMP 4 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-04 | 296 | 2026-04-09 | [5 empty] | 300 |  |  |  | 56
286 | 7041 | bth | LL-SAMP 5 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-04 | 297 | 2026-04-09 | [5 empty] | 180 |  |  |  | 56
287 | 2063 |  | L1-G0.3-RTU 31 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-06-08 | 298 | 2026-04-10 | [5 empty] | 180 |  |  |  | 59
288 | 2064 |  | L1-G0.3-RTU 32 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-06-08 | 299 | 2026-04-10 | [5 empty] | 330 |  |  |  | 59
289 | 2065 |  | L1-G0.1-RTU 30 |  |  |  | S/M | neal | DC6 6250027 |  | 2026-06-08 | 300 | 2026-04-10 | [5 empty] | 220 |  |  |  | 59
290 | 76034 |  | 76034 |  |  |  | S |  | RCIS 6250011 | 1" liner | 2026-06-08 | 301 | 2026-03-31 | [5 empty] | 100 |  | Curb adapter |  | 69
291 | 4763 |  | L2-TA 11 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner, bs | 2026-06-09 | 302 | 2026-04-21 | [5 empty] | 150 |  |  |  | 49
292 | 4764 |  | L2-TA 12 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner, bs | 2026-06-09 | 303 | 2026-04-21 | [5 empty] | 280 |  |  |  | 49
293 | 4765 |  | L2-TA 13 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner, bs | 2026-06-09 | 304 | 2026-04-21 | [5 empty] | 240 |  |  |  | 49
294 | 4766 |  | L2-TA 14 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner, bs | 2026-06-09 | 305 | 2026-04-21 | [5 empty] | 280 |  |  |  | 49
295 | 4767 |  | L2-TA 15 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner, bs | 2026-06-09 | 306 | 2026-04-21 | [5 empty] | 170 |  |  |  | 49
296 | 4728 | bth | L2-VAV-2-2-20 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-06-11 | 307 | 2026-04-13 | [5 empty] | 280 |  |  |  | 59
297 | 4729 | bth | L2-VAV-2-2-21 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-06-11 | 308 | 2026-04-13 | [5 empty] | 300 |  |  |  | 59
298 | 4730 | bth | L2-VAV-2-2-22 |  |  |  | S |  | UW STOUT 6250008 | 1" liner | 2026-06-11 | 309 | 2026-04-13 | [5 empty] | 50 |  |  |  | 59
299 | 7042 |  | LL-TA 1 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 310 | 2026-04-10 | [5 empty] | 200 |  |  |  | 62
300 | 7043 |  | LL-TA 2 |  |  |  | S |  | WHC 6250007 |  | 2026-06-11 | 311 | 2026-04-10 | [5 empty] | 40 |  |  |  | 62
301 | 7044 |  | LL-VAV-1-0-1 |  |  |  | S |  | WHC 6250007 |  | 2026-06-11 | 312 | 2026-04-10 | [5 empty] | 100 |  |  |  | 62
302 | 7045 |  | LL-VAV-1-0-2 |  |  |  | S |  | WHC 6250007 |  | 2026-06-11 | 313 | 2026-04-10 | [5 empty] | 50 |  |  |  | 62
303 | 7046 |  | LL-VAV-1-0-3 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 314 | 2026-04-10 | [5 empty] | 110 |  |  |  | 62
304 | 7047 |  | LL-VAV-1-0-4 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 315 | 2026-04-10 | [5 empty] | 160 |  |  |  | 62
305 | 7048 |  | LL-VAV-1-0-5 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 316 | 2026-04-10 | [5 empty] | 290 |  |  |  | 62
306 | 7049 |  | LL-VAV-1-0-6 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 317 | 2026-04-10 | [5 empty] | 140 |  |  |  | 62
307 | 7050 |  | LL-VAV-1-0-7 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 318 | 2026-04-10 | [5 empty] | 140 |  |  |  | 62
308 | 7051 |  | LL-VAV-1-0-8 |  |  |  | S |  | WHC 6250007 |  | 2026-06-11 | 319 | 2026-04-10 | [5 empty] | 80 |  |  |  | 62
309 | 7052 |  | LL-VAV-1-0-9 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 320 | 2026-04-10 | [5 empty] | 220 |  |  |  | 62
310 | 7053 |  | LL-VAV-1-0-10 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 321 | 2026-04-10 | [5 empty] | 120 |  |  |  | 62
311 | 7054 |  | LL-VAV-E-5-0-1 |  |  |  | S |  | WHC 6250007 |  | 2026-06-11 | 322 | 2026-04-10 | [5 empty] | 60 |  |  |  | 62
312 | 7055 |  | LL-FCU-0-4 |  |  |  | S/M |  | WHC 6250007 |  | 2026-06-11 | 323 | 2026-04-10 | [5 empty] | 330 |  |  |  | 62
313 | 4757 |  | L2-TA 16 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-06-20 | 324 | 2026-04-20 | [5 empty] | 110 |  |  |  | 61
314 | 4758 |  | L2-TA 17 |  |  |  | M |  | UW STOUT 6250008 | 1" liner | 2026-06-20 | 325 | 2026-04-20 | [5 empty] | 430 |  |  |  | 61
315 | 4759 |  | L2-TA 18 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-06-20 | 326 | 2026-04-20 | [5 empty] | 310 |  |  |  | 61
316 | 4760 |  | L2-TA 19 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-06-20 | 327 | 2026-04-20 | [5 empty] | 230 |  |  |  | 61
317 | 4761 |  | L2-TA 20 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-06-20 | 328 | 2026-04-20 | [5 empty] | 140 |  |  |  | 61
318 | 74835 | w | 74835 |  |  |  | S/M | ss | OCTOPI 8250035 |  | 2026-06-30 | 329 | 2026-03-17 | [5 empty] | 150 |  | Trench drains |  | 105
319 | 4585 | bth | L3-SAT-2-3-12 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 330 | 2026-04-22 | [5 empty] | 510 |  |  |  | 70
320 | 4586 | bth | L3-SAT-2-3-13 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 331 | 2026-04-22 | [5 empty] | 470 |  |  |  | 70
321 | 4587 | bth | L3-SAT-2-3-14 |  |  |  | S/M |  | UW STOUT 6250008 | 1" liner | 2026-07-01 | 332 | 2026-04-22 | [5 empty] | 140 |  |  |  | 70
322 | 4588 | bth | L3-SAT-2-3-17 |  |  |  | S |  | UW STOUT 6250008 | 1" liner | 2026-07-01 | 333 | 2026-04-22 | [5 empty] | 80 |  |  |  | 70
323 | 4641 | bth | L2-SAMP 27.5 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 334 | 2026-03-17 | [5 empty] | 600 |  |  |  | 106
324 | 4642 |  | L2-SAMP 28 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 335 | 2026-03-17 | [5 empty] | 500 |  |  |  | 106
325 | 4643 |  | L2-SAMP 29 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-07-01 | 336 | 2026-03-17 | [5 empty] | 840 |  |  |  | 106
326 | 4644 | bth | L2-SAMP 30 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 337 | 2026-03-17 | [5 empty] | 800 |  |  |  | 106
327 | 4645 |  | L2-SAMP 31 |  |  |  | L |  | UW STOUT 6250008 |  | 2026-07-01 | 338 | 2026-03-17 | [5 empty] | 3840 |  |  |  | 106
328 | 4646 |  | L2-SAMP 32 |  |  |  | L |  | UW STOUT 6250008 |  | 2026-07-01 | 339 | 2026-03-17 | [5 empty] | 1560 |  |  |  | 106
329 | 4647 |  | L2-SAMP 33 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-07-01 | 340 | 2026-03-17 | [5 empty] | 290 |  |  |  | 106
330 | 4677 |  | L2-SAMP 01 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-07-01 | 341 | 2026-03-20 | [5 empty] | 1200 |  |  |  | 103
331 | 4663 |  | L2-RAMP-20 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 342 | 2026-03-23 | [5 empty] | 370 |  |  |  | 100
332 | 4664 | bth | L2-RAMP-21 |  |  |  | L |  | UW STOUT 6250008 | spiralmate | 2026-07-01 | 343 | 2026-03-23 | [5 empty] | 2740 |  |  |  | 100
333 | 4665 | bth | L2-RAMP-22 |  |  |  | L |  | UW STOUT 6250008 | spiralmate | 2026-07-01 | 344 | 2026-03-23 | [5 empty] | 1710 |  |  |  | 100
334 | 4666 |  | L2-RAMP-24 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-07-01 | 345 | 2026-03-23 | [5 empty] | 960 |  |  |  | 100
335 | 4667 |  | L2-RAMP-25.5 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 346 | 2026-03-23 | [5 empty] | 540 |  |  |  | 100
336 | 4668 |  | L2-RAMP-01 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 347 | 2026-03-23 | [5 empty] | 500 |  |  |  | 100
337 | 4669 |  | L2-RAMP-02 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-07-01 | 348 | 2026-03-23 | [5 empty] | 340 |  |  |  | 100
338 | 4670 |  | L2-RAMP-03 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 349 | 2026-03-23 | [5 empty] | 420 |  |  |  | 100
339 | 4671 |  | L2-RAMP-04 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 350 | 2026-03-23 | [5 empty] | 380 |  |  |  | 100
340 | 4672 |  | L2-RAMP-05 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-07-01 | 351 | 2026-03-23 | [5 empty] | 260 |  |  |  | 100
341 | 4673 |  | L2-RAMP-06 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 352 | 2026-03-23 | [5 empty] | 360 |  |  |  | 100
342 | 4674 |  | L2-RAMP-07 |  |  |  | S/M |  | UW STOUT 6250008 |  | 2026-07-01 | 353 | 2026-03-23 | [5 empty] | 170 |  |  |  | 100
343 | 4675 |  | L2-RAMP-08 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 354 | 2026-03-23 | [5 empty] | 690 |  |  |  | 100
344 | 4676 |  | L2-RAMP-09 |  |  |  | M |  | UW STOUT 6250008 |  | 2026-07-01 | 355 | 2026-03-23 | [5 empty] | 440 |  |  |  | 100
345 | 4665 | bth | L2-RAMP-23 |  |  |  | M/L |  | UW STOUT 6250008 |  | 2026-07-01 | 356 | 2026-03-24 | [5 empty] | 1230 |  |  |  | 99
346 | 7056 | sp | LL-VAV-1-0-11 |  |  |  | S/M | neal | WHC 6250007 | 1" liner | 2026-11-01 | 357 | 2026-04-13 | [5 empty] | 290 |  |  |  | 202
347 | 7057 | sp | LL-VAV-1-0-12 |  |  |  | M | neal | WHC 6250007 | 1" liner | 2026-11-01 | 358 | 2026-04-13 | [5 empty] | 380 |  |  |  | 202
348 | 74843 |  | 74843 |  |  |  | S |  | RCIS 6250011 |  | 2026-04-23 | 6 | 2026-04-22 | [5 empty] | 100 |  | Roof fan | 1 | 1
349 | 85176 |  | 85176 |  |  |  | S |  | UW STOUT 6250008 |  | 2026-04-28 | 12 | 2026-04-22 | [5 empty] | 100 |  | L3-sat-1-3-52 | 2 | 6
350 | 77332 |  | 77332-33 |  |  |  | S |  | LAKE MILLS ES 6250012 |  | 2026-04-28 | 11 | 2026-04-22 | [5 empty] | 100 |  | Hp 74 grilles | 12 | 6
351 | 2131 |  | A0.1-FPB 0152-01 |  |  |  | M |  | DC6 6250027 | 1" liner | 2026-05-07 | 85 | 2026-04-22 | [5 empty] | 440 |  |  |  | 15
352 | 77369 | w | 77369 |  |  |  | S | ss | UWRF 6230010 | birdscreen | 2026-04-28 | 13 | 2026-04-22 | [5 empty] | 100 |  | Missing hood | 3 | 6
353 | 76471 |  | 76471 |  |  |  | S | neal | WAUNAKEE 6230013 |  | 2026-04-24 | 8 | 2026-04-22 | [5 empty] | 50 |  | RG | 1 | 2
354 | 74693 |  | 74693 |  |  |  | S |  | PORTAGE MS 6250018 | 1/2" liner | 2026-05-14 | 141 | 2026-04-22 | [5 empty] | 100 | 22GA GALV | UV protector | 1 | 22
355 | 76669 |  | 76669-70 |  |  |  | S | neal | PORTAGE MS 6250018 |  | 2026-05-14 | 142 | 2026-04-22 | [5 empty] | 100 | 20GA GALVANEAL | Pipe enclosures | 46 | 22
356 | 84342 |  | 84342 |  |  |  | S |  | PERRENIAL YOGA 10065928 |  | 2026-04-22 | 4 | 2026-04-22 | [5 empty] | 20 |  |  | 1 | 0
357 | 84339 | bth | 84339 |  |  |  | S |  | UW RESEARCH 4250056 |  | 2026-04-24 | 7 | 2026-04-22 | [5 empty] | 50 |  |  | 5 | 2
358 | 76130 |  | 76130-32 |  |  |  | S |  | UWP 6240021 |  | 2026-05-21 | 221 | 2026-04-22 | [5 empty] | 100 |  | DOAS 1 sa cb 40 |  | 29
359 | [12 empty] | 2026-04-22
360 | [12 empty] | 2026-04-22
361 | [12 empty] | 2026-04-22
362 | [12 empty] | 2026-04-22
363 | [12 empty] | 2026-04-22
364 | [12 empty] | 2026-04-22
365 | [12 empty] | 2026-04-22
366 | [12 empty] | 2026-04-22
367 | [12 empty] | 2026-04-22
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587

## Completed TO# List 2026
COMPLETED TO#'s | [10 empty] | SHEET SHOP - 2026
| TO#'S |  | SKETCH/SPOOL #'S | STATUS | DONE | SIZE |  | METAL | JOB NAME |  |  |  | DATE | PLASMA | SPIRAL | C.LINE | C.LINE | INSU | LBS. | [6 empty] | Short
COMPLETED | [6 empty] | EST. |  |  | SPECIAL | NEED | Priority | RCVD | SQ FT | SQ FT | SQ FT | STATUS | SQ FT | [7 empty] | Order %
DATE | [6 empty] | SIZE | ETC. |  | NOTES | DATE | 0.5 | Pounds completed to date this week = | [7 empty] | Description | # OF PIECES | Lead Time | Original need date
[9 empty] | WEEK OF 1-5-2026 | [16 empty] | % Under 14
2026-01-06 | 53953 | w | 53953 | A | DONE | 15 | M | ss | 121 WILSON ST 6230024 | 3" dual wall | 2025-12-30 | Z | 2025-12-10 | 330 | 0 | 0 |  | 80 | 360 |  | Stainless elbow |  | 20 |  |  | 46.49%
2026-01-07 | 82757 | bth | 82757-59 | A | DONE | 88 | L |  | ANTIGO 6250017 | 1"&2" liner, nosing | 2026-01-12 | Z | 2025-12-29 | 630 | 160 | 660 |  | 810 | 2190 |  | VAV-1 |  | 14
2026-01-07 | 82761 |  | 82765,82762 | A | DONE | 19 | M |  | ANTIGO 6250017 | CD | 2026-01-12 | Z | 2025-12-30 | 310 | 0 | 0 |  | 0 | 470 |  | BCU 1-2-3 |  | 13
2026-01-07 | 82763 |  | 82763 | A | DONE | 6 | S/M |  | ANTIGO 6250017 | 1" liner, nosing | 2026-01-12 | Z | 2026-01-05 | 130 | 0 | 0 |  | 20 | 150 |  | RE-1A,1B |  | 7
2026-01-05 | 74266 |  | 74266 | A | DONE | 2 | S |  | BARTILLION 6240024 | birdscreen | 2026-01-08 | Z | 2025-12-29 | 10 | 0 | 0 |  | 0 | 20 |  | Ex vent |  | 10
2026-01-05 | 74267 |  | 74267 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2026-01-08 | Z | 2025-12-31 | 10 | 0 | 0 |  | 10 | 20 |  | Grille box |  | 8
2026-01-08 | 1526 |  | UNIT 203 M4.56 | A | DONE | 2 | S |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 26
2026-01-06 | 58176x |  | 58176x | A | DONE | 9 | S/M | alum | BROOM ST 6240033 |  | 2026-01-06 | Z | 2025-12-31 | 100 | 120 | 0 |  | 0 | 210 |  | Sleeves |  | 6
2026-01-07 | 74826 |  | 74826 | A | DONE | 3 | S |  | BROOM ST 6240033 |  | 2026-01-08 | Z | 2026-01-07 | 20 | 0 | 0 |  | 0 | 60 |  | Heat box |  | 1
2026-01-05 | 78071 |  | 78071 | A | DONE | 2 | S |  | BROOM ST 6240033 |  | 2026-01-06 | Z | 2025-12-31 | 40 | 0 | 0 |  | 0 | 50 |  | DOAS 4 |  | 6
2026-01-05 | 1503 |  | UNIT 334 M4.67 | A | DONE | 18 | M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 330 | 0 | 40 |  | 0 | 450 |  |  |  | 25
2026-01-05 | 1504 |  | UNIT 335 M4.68 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 100 | 0 | 0 |  | 0 | 90 |  |  |  | 25
2026-01-05 | 1505 |  | UNIT 336 M4.69 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 100 | 0 | 0 |  | 0 | 110 |  |  |  | 25
2026-01-05 | 1506 |  | UNIT 337 M4.70 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 270 | 0 | 40 |  | 0 | 290 |  |  |  | 25
2026-01-05 | 1507 |  | UNIT 338 M4.71 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 270 | 0 | 0 |  | 0 | 280 |  |  |  | 25
2026-01-05 | 1508 |  | UNIT 339 M4.72 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 240 | 0 | 40 |  | 0 | 260 |  |  |  | 25
2026-01-05 | 1509 |  | UNIT 341 M4.73 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 80 | 0 | 0 |  | 0 | 80 |  |  |  | 25
2026-01-05 | 1510 |  | UNIT 342 M4.74 | A | DONE | 9 | S/M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 210 | 0 | 0 |  | 0 | 220 |  |  |  | 25
2026-01-05 | 1511 |  | UNIT 345 M4.76 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 80 | 0 | 0 |  | 0 | 80 |  |  |  | 25
2026-01-08 | 1523 |  | UNIT 445 M4.76 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-01-12 | Z | 2025-12-16 | 80 | 0 | 0 |  | 0 | 80 |  |  |  | 27
2026-01-09 | 79480 |  | 79480-2 | A | DONE | 20 | M |  | BROOM ST. 6240033 | paint black | 2026-01-12 | Z | 2025-12-02 | 400 | 0 | 0 |  | 270 | 490 |  | Grille boxes part 2 |  | 41
2026-01-08 | 74108r |  | 74108 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2026-01-08 | Z | 2026-01-08 | 30 | 0 | 0 |  | 0 | 40 |  | Remake |  | 0
2026-01-05 | 74111 | sp | 74111-12 | A | DONE | 11 | S/M | pcd | DELLSHIRE 6240017 | birdscreen | 2026-01-05 | Z | 2025-12-29 | 90 | 130 | 0 |  | 0 | 270 |  | Food prep add. |  | 7
2026-01-07 | 74113 | bth | 74113 | A | DONE | 7 | S/M |  | DELLSHIRE 6240017 |  | 2026-01-12 | Z | 2026-01-05 | 30 | 130 | 0 |  | 0 | 160 |  |  |  | 7
2026-01-07 | 74208 |  | 74208 | A | DONE | 4 | S |  | DELLSHIRE 6240017 | paint black | 2026-01-12 | Z | 2026-01-07 | 50 | 0 | 30 |  | 0 | 90 |  | 1st tie in 109A |  | 5
2026-01-06 | 75291 |  | 75291-92,95-96 | A | DONE | 56 | L |  | DELLSHIRE 6240017 |  | 2026-01-08 | Z | 2025-12-29 | 530 | 0 | 140 |  | 0 | 1390 |  | AHU 8 |  | 10
2026-01-06 | 3159 | sp | Z2-SAT-1-1-6_2 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-09-17 | 20 | 170 | 0 |  | 0 | 170 |  |  |  | 113 | 2025-11-13 | 2025-11-06
2026-01-06 | 3160 | bth | Z2-SAT-1-1-7_1 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | 1" liner | 2026-01-08 | Z | 2025-09-17 | 40 | 90 | 0 |  | 20 | 130 |  |  |  | 113 | 2025-11-13 | 2025-11-06
2026-01-06 | 3161 | bth | Z2-SAT-1-1-7_2 | A | DONE | 14 | S/M |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-09-17 | 160 | 90 | 60 |  | 0 | 340 |  |  |  | 113 | 2025-11-13 | 2025-11-06
2026-01-06 | 3162 | bth | Z2-SAT-1-1-8_1 | A | DONE | 11 | S/M |  | DOC JDC 6240023 | 1" liner | 2026-01-08 | Z | 2025-09-17 | 110 | 70 | 50 |  | 50 | 260 |  |  |  | 113 | 2025-11-13 | 2025-11-06
2026-01-06 | 3163 | bth | Z2-SAT-1-1-8_2 | A | DONE | 15 | M |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-09-17 | 130 | 80 | 130 |  | 0 | 370 |  |  |  | 113 | 2025-11-13 | 2025-11-06
2026-01-06 | 56095 |  | 56095 | A | DONE | 2 | S |  | DOC JDC 6240023 | MOD, flex | 2026-01-08 | Z | 2025-12-24 | 10 | 0 | 0 |  | 0 | 20 |  | Misc |  | 15
2026-01-05 | 56096 |  | 56096 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-12-24 | 10 | 0 | 0 |  | 0 | 10 |  | Z1-EA-20 |  | 15
2026-01-06 | 56100 |  | 56100 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2026-01-05 | 10 | 10 | 0 |  | 0 | 20 |  | Zone 2 misc |  | 3
2026-01-05 | 661 | sp | Z1-EA 1 | A | DONE | 3 | S | neal | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-07-22 | 10 | 50 | 0 |  | 0 | 70 |  |  |  | 170 | 2025-10-23 | 2025-11-20
2026-01-06 | 669 |  | Z1-EA 8 | A | DONE | 14 | S/M | pt.neal | DOC JDC 6240023 | VD's | 2026-01-08 | Z | 2025-07-22 | 210 | 0 | 80 |  | 0 | 350 |  |  |  | 170 | 2025-10-23
2026-01-05 | 670 |  | Z1-EA 9 | A | DONE | 10 | S/M |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-07-22 | 120 | 0 | 90 |  | 0 | 250 |  |  |  | 170 | 2025-10-23
2026-01-05 | 718 |  | Z2-EA 49 | A | DONE | 15 | M |  | DOC JDC 6240023 |  | 2026-01-15 | Z | 2025-07-30 | 110 | 0 | 170 |  | 0 | 360 |  |  |  | 169 | 2025-09-04 | 2025-11-20
2026-01-06 | 722 |  | Z2-EA 53 | A | DONE | 11 | S/M |  | DOC JDC 6240023 | VD | 2026-01-15 | Z | 2025-07-30 | 100 | 0 | 130 |  | 0 | 270 |  |  |  | 169 | 2025-09-04 | 2025-11-20
2026-01-05 | 725 | bth | Z2-EA 56 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | VD | 2026-01-08 | Z | 2025-07-30 | 70 | 0 | 40 |  | 0 | 140 |  |  |  | 162 | 2025-09-04 | 2025-11-20
2026-01-06 | 74352 |  | 74352-54 | A | DONE | 54 | L |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-12-23 | 490 | 0 | 0 |  | 0 | 1330 |  | Louvers |  | 16
2026-01-06 | 74355 |  | 74355 | A | DONE | 8 | S/M |  | DOC JDC 6240023 | flex | 2026-01-08 | Z | 2025-12-29 | 90 | 0 | 0 |  | 0 | 180 |  | Crack unit outs |  | 10
2026-01-06 | 74356 |  | 74356 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-12-30 | 40 | 0 | 0 |  | 0 | 180 |  | RF-4 |  | 9
2026-01-06 | 84397 |  | 84397-98 | A | DONE | 2 | S |  | DOC JDC 6240023 | flex | 2026-01-08 | Z | 2025-12-23 | 10 | 0 | 0 |  | 0 | 40 |  | Flexes |  | 16
2026-01-06 | 84399 |  | 84399-00,74351 | A | DONE | 17 | M |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-12-23 | 180 | 0 | 0 |  | 0 | 420 |  | Tie ins |  | 16
2026-01-06 | 84746 |  | 84746 | A | DONE | 2 | S |  | E386 |  | 2026-01-09 | Z | 2026-01-05 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 4
2026-01-07 | 81331 | bth | 81331-34 | A | DONE | 15 | M |  | GRANT ELEM. 6250021 |  | 2026-01-12 | Z | 2025-12-18 | 90 | 190 | 60 |  | 0 | 370 |  | VAV 1-4, 1-5 |  | 25
2026-01-05 | 83677 |  | 83677 | A | DONE | 2 | S |  | MONROE 6240018 |  | 2026-01-07 | Z | 2025-12-24 | 20 | 0 | 0 |  | 0 | 20 |  | F mech |  | 14
2026-01-08 | 83736 |  | 83736-36A | A | DONE | 2 | S | neal | MONROE 6240018 | birdscreen | 2026-01-14 | Z | 2026-01-07 | 30 | 0 | 0 |  | 0 | 40 |  | Spray space |  | 7
2026-01-08 | 83737 |  | 83737 | A | DONE | 2 | S | neal | MONROE 6240018 |  | 2026-01-14 | Z | 2026-01-07 | 20 | 0 | 0 |  | 0 | 20 |  | BCU-5B SA |  | 7
2026-01-08 | 77205 |  | 77205 | A | DONE | 2 | S |  | PECATONICA 6240005 | paint black | 2026-01-12 | Z | 2026-01-05 | 40 | 0 | 0 |  | 20 | 50 |  | UV-6 |  | 7
2026-01-07 | 74658 | bth | 74658-60 | A | DONE | 32 | M | neal | PEWAUKEE HS 6240030 | birdscreen | 2026-01-12 | Z | 2025-12-29 | 160 | 320 | 220 |  | 0 | 800 |  | Rm H114, phase 5,6 |  | 14
2026-01-09 | 74663 |  | 74663 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | CD | 2026-01-12 | Z | 2025-12-29 | 30 | 0 | 0 |  | 0 | 30 |  | RE 15 damper |  | 14
2026-01-06 | 74664 | sp | 74664 | A | DONE | 4 | S | neal | PEWAUKEE HS 6240030 |  | 2026-01-06 | Z | 2025-12-30 | 0 | 60 | 0 |  | 0 | 80 |  | DC drops |  | 7
2026-01-08 | 74668 | sp | 74668 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2026-01-12 | Z | 2026-01-06 | 20 | 0 | 0 |  | 0 | 30 |  | DC fitting |  | 6
2026-01-06 | 74824 |  | 74824 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2026-01-12 | Z | 2026-01-06 | 0 | 0 | 30 |  | 0 | 40 |  |  |  | 6
2026-01-08 | 74827 |  | 74827 | A | DONE | 3 | S |  | PEWAUKEE HS 6240030 | CD | 2026-01-12 | Z | 2026-01-08 | 60 | 0 | 0 |  | 0 | 60 |  | RM H114 |  | 4
2026-01-08 | 76401 |  | 76401-02 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2026-01-12 | Z | 2026-01-07 | 40 | 0 | 0 |  | 10 | 60 |  | E house |  | 5
2026-01-06 | 81864 | bth | 81864 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2026-01-08 | Z | 2026-01-05 | 30 | 20 | 0 |  | 0 | 50 |  | VAV 12-1 |  | 3
2026-01-05 | 74084 | bth | 74084-89 | A | DONE | 14 | S/M |  | QBE 4250054 |  | 2026-01-05 | Z | 2025-12-23 | 100 | 240 | 0 |  | 0 | 330 |  | VAV-308-314 |  | 13
2026-01-05 | 74091 | bth | 74091-98 | A | DONE | 27 | M |  | QBE 4250054 |  | 2026-01-05 | Z | 2025-12-23 | 210 | 300 | 50 |  | 0 | 670 |  | VAV-301-306 |  | 13
2026-01-05 | 74099 | bth | 74099 | A | DONE | 6 | S/M |  | QBE 4250054 |  | 2026-01-05 | Z | 2025-12-23 | 50 | 110 | 0 |  | 0 | 150 |  | VAV-311 |  | 13
2026-01-08 | 76402 |  | 76402-03 | A | DONE | 15 | M |  | QBE 4250054 | 1" liner | 2026-01-13 | Z | 2026-01-06 | 390 | 0 | 0 |  | 270 | 360 |  | Transfers |  | 7
2026-01-09 | 76411 | bth | 76411-17 | A | DONE | 8 | S/M |  | QBE 4250054 |  | 2026-01-13 | Z | 2026-01-06 | 70 | 130 | 0 |  | 0 | 180 |  | RVAV's |  | 7
2026-01-07 | 83756 |  | 83756 | A | DONE | 2 | S |  | S PRINTING 4240030 |  | 2026-01-07 | Z | 2026-01-07 | 20 | 0 | 0 |  | 0 | 30 |  | Angles |  | 0
2026-01-05 | 1066 |  | L1-RA-03 | A | DONE | 12 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 140 | 0 | 80 |  | 0 | 280 |  |  |  | 13
2026-01-05 | 1068 |  | L1-RA-05 | A | DONE | 13 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 100 | 0 | 110 |  | 0 | 320 |  |  |  | 13
2026-01-05 | 1070 |  | L1-RA-07 | A | DONE | 12 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 90 | 0 | 160 |  | 0 | 300 |  |  |  | 13
2026-01-05 | 1071 |  | L1-RA-08 | A | DONE | 14 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 180 | 0 | 80 |  | 0 | 330 |  |  |  | 13
2026-01-07 | 85452 |  | 85452 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-01-12 | Z | 2026-01-06 | 30 | 0 | 0 |  | 0 | 40 |  | Mock up room lvl 2 |  | 6
2026-01-05 | 74822 |  | 74822 | A | DONE | 2 | S |  | SPH 6240039 |  | 2026-01-09 | Z | 2025-12-23 | 50 | 0 | 0 |  | 0 | 50 |  |  |  | 17
2026-01-07 | 76102 |  | 76102 | A | DONE | 3 | S |  | SWH MOB 6250012 |  | 2026-01-12 | Z | 2026-01-07 | 20 | 0 | 0 |  | 0 | 60 |  | Panel water trough |  | 5
2026-01-06 | 76101 |  | 76101 | A | DONE | 8 | S/M |  | SWH MOB 6250015 |  | 2026-01-12 | Z | 2026-01-02 | 110 | 0 | 0 |  | 0 | 190 |  | RTU-1 Chase |  | 10
2026-01-08 | 76103 |  | 76103 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2026-01-12 | Z | 2026-01-08 | 20 | 0 | 0 |  | 0 | 30 |  | End cap remake |  | 4
2026-01-07 | 76669 |  | 76669,72,74,76 | A | DONE | 15 | M |  | SWH MOB 6250015 | VD | 2026-01-12 | Z | 2025-11-21 | 180 | 0 | 130 |  | 0 | 360 |  | 1st flr east vav lpsa |  | 52
2026-01-08 | 76670 | sp | 76670,71,73,75,77 | A | DONE | 11 | S/M |  | SWH MOB 6250015 | VD | 2026-01-12 | Z | 2025-11-21 | 100 | 170 | 0 |  | 0 | 270 |  | 1st flr east vav lpsa |  | 52
2026-01-07 | 76678 |  | 76678,80,81,83,85 | A | DONE | 18 | M |  | SWH MOB 6250015 | VD | 2026-01-12 | Z | 2025-11-21 | 310 | 0 | 60 |  | 0 | 430 |  | 1st flr east vav lpsa |  | 52
2026-01-07 | 76679 | sp | 76679,82,84,86 | A | DONE | 11 | S/M |  | SWH MOB 6250015 | VD | 2026-01-12 | Z | 2025-11-21 | 80 | 190 | 0 |  | 0 | 260 |  | 1st flr east vav lpsa |  | 52
2026-01-07 | 76698 | bth | 76698-99 | A | DONE | 4 | S |  | SWH MOB 6250015 |  | 2026-01-12 | Z | 2025-12-31 | 30 | 70 | 0 |  | 0 | 90 |  | Misc |  | 12
2026-01-08 | 77066 |  | 77066-69 | A | DONE | 15 | M |  | TOMAH HEALTH 6250006 |  | 2026-01-13 | Z | 2026-01-06 | 240 | 0 | 60 |  | 0 | 360 |  | FP-VAV |  | 7
2026-01-06 | 76137 |  | 76137 | A | DONE | 9 | S/M |  | UW LEVY HALL 6230028 |  | 2026-01-06 | Z | 2025-12-29 | 150 | 0 | 0 |  | 0 | 220 |  | Penthouse |  | 8
2026-01-05 | 76138 |  | 76138 | A | DONE | 15 | M |  | UW LEVY HALL 6230028 |  | 2026-01-06 | Z | 2025-12-30 | 140 | 0 | 0 |  | 0 | 360 |  | Angles |  | 7
2026-01-08 | 76139 |  | 76139 | A | DONE | 16 | M |  | UW LEVY HALL 6230028 |  | 2026-01-13 | Z | 2026-01-06 | 200 | 0 | 0 |  | 0 | 400 |  | Penthouse |  | 7
2026-01-05 | 78318 |  | 78318 | A | DONE | 4 | S |  | UW LEVY HALL 6230028 |  | 2026-01-06 | Z | 2025-12-23 | 80 | 0 | 0 |  | 0 | 100 |  | L3 return drops |  | 14
2026-01-05 | 78319 |  | 78319 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 |  | 2026-01-06 | Z | 2025-12-24 | 20 | 0 | 0 |  | 0 | 20 |  | L2 BCU-1 SA |  | 13
2026-01-07 | 78320 |  | 78320 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 |  | 2026-01-13 | Z | 2026-01-07 | 10 | 0 | 0 |  | 0 | 20 |  | L3 SAT 3-3-27 |  | 6
2026-01-07 | 78354 |  | 78354 | A | DONE | 12 | S/M |  | UW LEVY HALL 6230028 | 1" liner | 2026-01-13 | Z | 2026-01-06 | 0 | 0 | 0 |  | 545 | 300 |  | Liner strips |  | 7
2026-01-08 | 4097 |  | L4-RA 1 | A | DONE | 24 | M |  | UW STOUT 6250008 |  | 2026-01-13 | Z | 2025-12-03 | 250 | 0 | 100 |  | 0 | 580 |  |  |  | 41
2026-01-08 | 4098 |  | L4-RA 2 | A | DONE | 6 | S/M |  | UW STOUT 6250008 |  | 2026-01-13 | Z | 2025-12-03 | 100 | 0 | 0 |  | 0 | 150 |  |  |  | 41
2026-01-08 | 4099 |  | L4-RA 3 | A | DONE | 70 | L |  | UW STOUT 6250008 |  | 2026-01-13 | Z | 2025-12-03 | 700 | 0 | 190 |  | 0 | 1730 |  |  |  | 41
2026-01-08 | 4100 |  | L4-RA 4 | A | DONE | 43 | M/L |  | UW STOUT 6250008 |  | 2026-01-13 | Z | 2025-12-03 | 370 | 0 | 110 |  | 0 | 1070 |  |  |  | 41
2026-01-09 | 4101 |  | L4-RA 5 | A | DONE | 61 | L |  | UW STOUT 6250008 |  | 2026-01-13 | Z | 2025-12-03 | 340 | 0 | 320 |  | 0 | 1510 |  |  |  | 41
2026-01-09 | 4105 |  | L4-RA 9 | A | DONE | 50 | M/L |  | UW STOUT 6250008 |  | 2026-01-13 | Z | 2025-12-03 | 250 | 0 | 310 |  | 0 | 1230 |  |  |  | 41
2026-01-08 | 4116 |  | L4-RA 20 | A | DONE | 6 | S/M |  | UW STOUT 6250008 | birdscreen | 2026-01-13 | Z | 2025-12-03 | 70 | 0 | 0 |  | 0 | 130 |  |  |  | 41
2026-01-08 | 4117 |  | L4-RA 21 | A | DONE | 5 | S/M |  | UW STOUT 6250008 | birdscreen | 2026-01-13 | Z | 2025-12-03 | 80 | 0 | 0 |  | 0 | 120 |  |  |  | 41
2026-01-08 | 4118 |  | L4-RA 22 | A | DONE | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-01-13 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 41
2026-01-08 | 4119 |  | L4-RA 23 | A | DONE | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-01-13 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 41
2026-01-08 | 4120 |  | L4-RA 24 | A | DONE | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-01-13 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 41
2026-01-08 | 4121 |  | L4-RA 25 | A | DONE | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-01-13 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 41
2026-01-08 | 4122 |  | L4-RA 26 | A | DONE | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-01-13 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 41
2026-01-08 | 4123 |  | L4-RA 27 | A | DONE | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-01-13 | Z | 2025-12-03 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 41
2026-01-08 | 4124 | sp | L4-EA 1 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-12-10 | 10 | 40 | 0 |  | 0 | 40 |  |  |  | 41
2026-01-08 | 4125 | sp | L4-EA 2 | A | DONE | 4 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-12-10 | 10 | 70 | 0 |  | 0 | 80 |  |  |  | 41
2026-01-08 | 4126 | sp | L4-EA 3 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-12-10 | 10 | 30 | 0 |  | 0 | 30 |  |  |  | 41
2026-01-08 | 4128 | bth | L4-EA 5 | A | DONE | 5 | S/M |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-12-10 | 30 | 60 | 20 |  | 0 | 110 |  |  |  | 41
2026-01-08 | 4130 | bth | L4-EA 7 | A | DONE | 7 | S/M |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-12-10 | 50 | 40 | 50 |  | 0 | 160 |  |  |  | 41
2026-01-09 | 74828 |  | 74828 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-12 | Z | 2026-01-08 | 40 | 0 | 0 |  | 0 | 40 |  | L4-SAMP 25 |  | 4
2026-01-05 | 77361 |  | 77361 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2026-01-06 | Z | 2025-12-29 | 20 | 0 | 0 |  | 0 | 20 |  | CB 138 |  | 8
2026-01-05 | 73826 |  | 73826 | A | DONE | 4 | S |  | WAUNAKEE 6230013 | paint black | 2026-01-09 | Z | 2026-01-02 | 70 | 0 | 0 |  | 0 | 80 |  | EA grille box |  | 7
2026-01-06 | 73827 |  | 73827 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2026-01-09 | Z | 2026-01-06 | 30 | 0 | 0 |  | 0 | 50 |  | RA grill box |  | 3
2026-01-08 | 75417 | sp | 75417 | A | DONE | 5 | S/M | neal | WAUNAKEE 6230013 |  | 2026-01-09 | Z | 2025-12-22 | 40 | 30 | 0 |  | 0 | 120 |  | DC splits |  | 18
2026-01-07 | 82940 | bth | 82940-44 | A | DONE | 24 | M |  | WAUNAKEE 6230013 |  | 2026-01-09 | Z | 2025-12-24 | 390 | 20 | 0 |  | 0 | 580 |  | Outs |  | 16
2026-01-06 | 82946 |  | 82946 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2026-01-09 | Z | 2026-01-05 | 30 | 0 | 0 |  | 20 | 40 |  | 1st A return |  | 4
2026-01-09 | 10737 |  | 10737 | A | DONE | 2 | S |  | WHS 8250008 | pipe caps | 2026-01-09 | Z | 2026-01-08 | 10 | 0 | 0 |  | 0 | 20 |  | Pipe caps |  | 1
[6 empty] | 1227 | [13 empty] | 29120 | [5 empty] | 39% Short
[9 empty] | WEEK OF 1-12-2026 | [16 empty] | % Under 14
2026-01-15 | 82767 |  | 82767 | A | DONE | 6 | S/M |  | ANTIGO 6250017 |  | 2026-01-26 | Z | 2026-01-12 | 100 | 0 | 0 |  | 0 | 150 |  | RE-1A and 1B |  | 14 |  |  | 45.74%
2026-01-15 | 82774 |  | 82774 | A | DONE | 13 | S/M | neal | ANTIGO 6250017 |  | 2026-01-16 | Z | 2026-01-15 | 100 | 0 | 0 |  | 0 | 310 |  |  |  | 1
2026-01-12 | 1524 |  | UNIT 200 M4.54 | A | DONE | 12 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 240 | 0 | 90 |  | 0 | 300 |  |  |  | 26
2026-01-12 | 1525 |  | UNIT 201 M4.55 | A | DONE | 12 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 190 | 0 | 80 |  | 0 | 290 |  |  |  | 26
2026-01-12 | 1527 | bth | UNIT 205 M4.57 | A | DONE | 6 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 70 | 70 | 0 |  | 0 | 150 |  |  |  | 26
2026-01-12 | 1528 | bth | UNIT 206 M4.58 | A | DONE | 6 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 80 | 70 | 0 |  | 0 | 150 |  |  |  | 26
2026-01-12 | 1529 | bth | UNIT 207 M4.59 | A | DONE | 6 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 60 | 70 | 0 |  | 0 | 150 |  |  |  | 26
2026-01-12 | 1530 | bth | UNIT 208 M4.60 | A | DONE | 6 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 60 | 70 | 0 |  | 0 | 150 |  |  |  | 26
2026-01-12 | 1531 | bth | UNIT 209 M4.57 | A | DONE | 7 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 70 | 70 | 0 |  | 0 | 160 |  |  |  | 26
2026-01-12 | 1532 | bth | UNIT 210 M4.58 | A | DONE | 6 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 60 | 70 | 0 |  | 0 | 150 |  |  |  | 26
2026-01-12 | 1533 | bth | UNIT 211 M4.59 | A | DONE | 6 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 60 | 70 | 0 |  | 0 | 150 |  |  |  | 26
2026-01-12 | 1534 | bth | UNIT 212 M4.60 | A | DONE | 6 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 60 | 70 | 0 |  | 0 | 150 |  |  |  | 26
2026-01-12 | 1535 |  | UNIT 214 M4.61 | A | DONE | 2 | S |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 26
2026-01-12 | 1536 |  | UNIT 215 M4.62 | A | DONE | 4 | S |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 90 | 0 | 0 |  | 0 | 100 |  |  |  | 26
2026-01-12 | 1537 |  | UNIT 217 M4.63 | A | DONE | 8 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 120 | 0 | 90 |  | 0 | 180 |  |  |  | 26
2026-01-12 | 1538 |  | UNIT 218 M4.64 | A | DONE | 14 | S/M |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2025-12-18 | 230 | 0 | 150 |  | 0 | 350 |  |  |  | 26
2026-01-12 | 1557 |  | DOAS-1 L1-L5 | A | DONE | 14 | S/M |  | BROOM ST 6240033 |  | 2026-01-15 | Z | 2025-12-30 | 80 | 0 | 250 |  | 0 | 330 |  |  |  | 16
2026-01-12 | 1558 |  | JC EXHAUST-WT | A | DONE | 14 | S/M |  | BROOM ST 6240033 |  | 2026-01-15 | Z | 2025-12-30 | 170 | 0 | 90 |  | 0 | 340 |  |  |  | 16
2026-01-12 | 1559 |  | STAIR 4 DUCT RISER | A | DONE | 25 | M |  | BROOM ST 6240033 |  | 2026-01-15 | Z | 2025-12-30 | 90 | 0 | 340 |  | 0 | 610 |  |  |  | 16
2026-01-12 | 1560 |  | STAIR 5 DUCT RISER | A | DONE | 14 | S/M |  | BROOM ST 6240033 |  | 2026-01-15 | Z | 2025-12-30 | 80 | 0 | 210 |  | 0 | 350 |  |  |  | 16
2026-01-12 | 1561 |  | TRASH EXHAUST-WT | A | DONE | 21 | M |  | BROOM ST 6240033 |  | 2026-01-15 | Z | 2025-12-30 | 90 | 0 | 320 |  | 0 | 520 |  |  |  | 16
2026-01-14 | 74830 |  | 74830 | A | DONE | 4 | S |  | BROOM ST 6240033 |  | 2026-01-15 | Z | 2026-01-12 | 50 | 0 | 0 |  | 0 | 90 |  | Parts trays |  | 3
2026-01-12 | 79494 | bth | 79494 | A | DONE | 3 | S |  | BROOM ST 6240033 |  | 2026-01-13 | Z | 2026-01-07 | 60 | 10 | 0 |  | 0 | 60 |  | X55 East |  | 6
2026-01-16 | 79495 |  | 79495 | A | DONE | 30 | M |  | BROOM ST 6240033 |  | 2026-01-26 | Z | 2026-01-12 | 620 | 0 | 0 |  | 0 | 730 |  | Angles |  | 14
2026-01-14 | 1554 |  | 58182-84 | A | DONE | 20 | M |  | BROOM ST. 6240033 | rivet nuts | 2026-01-15 | Z | 2025-12-23 | 230 | 0 | 0 |  | 0 | 500 |  | OA kits |  | 23
2026-01-16 | 1555 |  | 58182-84 | A | DONE | 16 | M |  | BROOM ST. 6240033 | rivet nuts | 2026-01-22 | Z | 2025-12-23 | 160 | 0 | 0 |  | 0 | 400 |  | OA kits |  | 30
2026-01-16 | 74205 |  | 74205-06 | A | DONE | 118 | L | pcd | DELLSHIRE 6240017 |  | 2026-01-19 | Z | 2026-01-05 | 1000 | 0 | 1100 |  | 0 | 2950 |  | Pool mech SA, RA |  | 14
2026-01-14 | 74207 |  | 74207 | A | DONE | 2 | S | pcd | DELLSHIRE 6240017 |  | 2026-01-19 | Z | 2026-01-06 | 20 | 0 | 0 |  | 0 | 20 |  | Noted |  | 13
2026-01-15 | 74210 |  | 74210-14 | A | DONE | 26 | M | neal | DELLSHIRE 6240017 | 1" liner | 2026-01-22 | Z | 2026-01-07 | 440 | 0 | 50 |  | 240 | 640 |  | VAV's mech 308,3rd lobby |  | 15
2026-01-15 | 75300 | bth | 75300 | A | DONE | 14 | S/M |  | DELLSHIRE 6240017 |  | 2026-01-22 | Z | 2026-01-07 | 190 | 30 | 0 |  | 0 | 340 |  | AHU 6-7 |  | 15
2026-01-15 | 76453 |  | 76453 | A | DONE | 38 | M/L |  | DELLSHIRE 6240017 |  | 2026-01-19 | Z | 2026-01-09 | 520 | 0 | 100 |  | 0 | 930 |  | AHU 6-7 |  | 10
2026-01-16 | 95927 |  | 95927 | A | DONE | 4 | S |  | DELLSHIRE 6240017 |  | 2026-01-19 | Z | 2026-01-06 | 40 | 0 | 0 |  | 0 | 100 |  | Drain pan |  | 13
2026-01-12 | 74358 | w | 74358 | A | DONE | 2 | S |  | DOC JDC |  | 2026-01-15 | Z | 2026-01-08 | 10 | 0 | 0 |  | 0 | 20 |  | Curb rail cap |  | 7
2026-01-15 | 3151 |  | Z2-SAT-1-1-2 | A | DONE | 9 | S/M |  | DOC JDC 6240023 | 1" liner | 2026-01-22 | Z | 2025-09-17 | 120 | 70 | 0 |  | 30 | 220 |  |  |  | 127 | 2025-11-13 | 2025-11-06
2026-01-13 | 3153 | sp | Z2-SAT-1-1-3_2 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2026-01-15 | Z | 2025-09-17 | 20 | 160 | 0 |  | 0 | 180 |  |  |  | 120 | 2025-11-13 | 2025-11-06
2026-01-13 | 3154 |  | Z2-SAT-1-1-4_1 | A | DONE | 10 | S/M |  | DOC JDC 6240023 | 1" liner | 2026-01-15 | Z | 2025-09-17 | 80 | 90 | 50 |  | 50 | 240 |  |  |  | 120 | 2025-11-13 | 2025-11-06
2026-01-13 | 3155 |  | Z2-SAT-1-1-4_2 | A | DONE | 19 | M |  | DOC JDC 6240023 |  | 2026-01-15 | Z | 2025-09-17 | 210 | 80 | 130 |  | 0 | 460 |  |  |  | 120 | 2025-11-13 | 2025-11-06
2026-01-13 | 3156 | bth | Z2-SAT-1-1-5_1 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | 1" liner | 2026-01-15 | Z | 2025-09-17 | 50 | 100 | 0 |  | 30 | 150 |  |  |  | 120 | 2025-11-13 | 2025-11-06
2026-01-13 | 3157 | bth | Z2-SAT-1-1-5_2 | A | DONE | 15 | M |  | DOC JDC 6240023 |  | 2026-01-15 | Z | 2025-09-17 | 180 | 70 | 80 |  | 0 | 360 |  |  |  | 120 | 2025-11-13 | 2025-11-06
2026-01-16 | 3158 |  | Z2-SAT-1-1-6_1 | A | DONE | 15 | M |  | DOC JDC 6240023 | 1" liner | 2026-01-22 | Z | 2025-09-17 | 310 | 0 | 0 |  | 30 | 370 |  |  |  | 127 | 2025-11-13 | 2025-11-06
2026-01-15 | 56101 | bth | 56101-02 | A | DONE | 8 | S/M | neal | DOC JDC 6240023 |  | 2026-01-16 | Z | 2026-01-12 | 120 | 10 | 0 |  | 0 | 180 |  | Misc, MUA-3 |  | 4
2026-01-13 | 56103 | sp | 56103 | A | DONE | 2 | S | neal | DOC JDC 6240023 |  | 2026-01-15 | Z | 2026-01-12 | 20 | 20 | 0 |  | 0 | 40 |  | Misc |  | 3
2026-01-16 | 56107 |  | 56107 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-19 | Z | 2026-01-16 | 30 | 0 | 0 |  | 0 | 40 |  | Tap changes |  | 3
2026-01-16 | 715 |  | Z2-EA 46 | A | DONE | 11 | S/M |  | DOC JDC 6240023 | VD's | 2026-01-22 | Z | 2025-07-30 | 160 | 0 | 80 |  | 0 | 270 |  |  |  | 176 | 2025-09-04 | 2025-11-20
2026-01-16 | 74357 | w | 74357 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2026-01-19 | Z | 2026-01-05 | 40 | 0 | 0 |  | 0 | 80 |  | OA boiler roof |  | 14
2026-01-15 | 74359 |  | 74359-60 | A | DONE | 14 | S/M |  | DOC JDC 6240023 |  | 2026-01-19 | Z | 2026-01-12 | 160 | 0 | 0 |  | 0 | 340 |  | OA louver tie ins |  | 7
2026-01-16 | 98135 |  | 98135 | A | DONE | 2 | S | ss | EXACT SEQ 8250025 |  | 2026-01-22 | Z | 2026-01-16 | 30 | 0 | 0 |  | 0 | 20 |  | Stainless plates |  | 6
2026-01-16 | 98134 |  | 98134 | A | DONE | 2 | S | ss | EXACT TL3 8240019 |  | 2026-01-14 | Z | 2026-01-09 | 10 | 0 | 0 |  |  | 30 |  |  |  | 5
2026-01-14 | 77065 |  | 77065 | A | DONE | 2 | S |  | GRANT 6250021 |  | 2026-01-19 | Z | 2026-01-06 | 20 | 0 | 0 |  | 0 | 30 |  | Diffuser tie ins |  | 13
2026-01-16 | 74763 | sp | 74763 | A | DONE | 5 | S/M |  | GREAT WOLF 4250055 |  | 2026-01-23 | Z | 2026-01-13 | 20 | 110 | 0 |  | 0 | 110 |  | Exhaust duct |  | 10
2026-01-15 | 74767 | sp | 74767 | A | DONE | 2 | S |  | GREAT WOLF 4250055 |  | 2026-01-23 | Z | 2026-01-13 | 20 | 0 | 0 |  | 0 | 20 |  | Exhaust duct |  | 10
2026-01-14 | 74768 |  | 74768 | A | DONE | 3 | S |  | KALAHARI 4250064 |  | 2026-01-14 | Z | 2026-01-14 | 40 | 0 | 0 |  | 30 | 70 |  |  |  | 0
2026-01-12 | 83628 | w | 83628 | A | DONE | 12 | S/M | ss | MONROE 6240018 |  | 2026-01-13 | Z | 2026-01-06 | 130 | 0 | 0 |  | 0 | 280 |  | North kitchen hood |  | 7
2026-01-15 | 83629 |  | 83629 | A | DONE | 12 | S/M |  | MONROE 6240018 | CD | 2026-01-21 | Z | 2026-01-09 | 190 | 0 | 0 |  | 0 | 280 |  | Kitchen hood supply |  | 12
2026-01-13 | 83678 |  | 83678 | A | DONE | 6 | S/M | neal | MONROE 6240018 | flex | 2026-01-14 | Z | 2026-01-07 | 80 | 0 | 0 |  | 0 | 130 |  | C section |  | 7
2026-01-13 | 83728 |  | 83728-35 | A | DONE | 26 | M | neal | MONROE 6240018 |  | 2026-01-14 | Z | 2026-01-06 | 540 | 0 | 0 |  | 10 | 650 |  | BCU-5B OA |  | 8
2026-01-15 | 83738 |  | 83738-39 | A | DONE | 4 | S | neal | MONROE 6240018 | flex | 2026-01-21 | Z | 2026-01-09 | 60 | 0 | 0 |  | 0 | 90 |  | IF-1 |  | 12
2026-01-15 | 84916 |  | 84916-17 | A | DONE | 4 | S |  | MONROE 6240018 | flex | 2026-01-17 | Z | 2026-01-09 | 50 | 0 | 0 |  | 10 | 80 |  |  |  | 8
2026-01-15 | 74764 | bth | 74764-66 | A | DONE | 11 | S/M |  | NEW YORK LIFE 4260001 |  | 2026-01-20 | Z | 2026-01-13 | 110 | 180 | 0 |  | 0 | 270 |  | FCU's |  | 7 | 2026-01-20
2026-01-12 | 74829 |  | 74829 | A | DONE | 2 | S |  | NEW YORK LIFE 4260001 |  | 2026-01-12 | Z | 2026-01-12 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 0
2026-01-12 | 84747 |  | 84747 | A | DONE | 2 | S |  | NEW YORK LIFE 4260001 |  | 2026-01-12 | Z | 2026-01-12 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2026-01-16 | 84748 | bth | 84748-50,74759-60 | A | DONE | 45 | M/L |  | NEW YORK LIFE 4260001 |  | 2026-01-20 | Z | 2026-01-13 | 290 | 890 | 30 |  | 0 | 1120 |  | FCU's |  | 7 | 2026-01-20
2026-01-13 | 74666 |  | 74666-67 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | 2" liner, flex | 2026-01-14 | Z | 2026-01-05 | 20 | 0 | 0 |  | 10 | 30 |  | Curb caps |  | 9
2026-01-13 | 74669 | sp | 74669 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2026-01-14 | Z | 2026-01-08 | 20 | 0 | 0 |  | 0 | 30 |  | Dust collector |  | 6
2026-01-13 | 74670 |  | 74670 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2026-01-14 | Z | 2026-01-08 | 10 | 0 | 0 |  | 0 | 20 |  | Dust collector |  | 6
2026-01-14 | 74673 |  | 74673-74 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2026-01-19 | Z | 2026-01-09 | 20 | 0 | 0 |  | 10 | 50 |  | Curb cap |  | 10
2026-01-14 | 74675 |  | 74675 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2026-01-19 | Z | 2026-01-12 | 20 | 0 | 0 |  | 0 | 40 |  | RE 15 |  | 7
2026-01-13 | 76248 | w | 76248-50 | A | DONE | 22 | M | ss | PROJECT DOVE 6240041 | flex, spiralmate | 2026-01-14 | Z | 2026-01-07 | 360 | 0 | 0 |  | 20 | 550 |  | 1900-10-26 |  | 7
2026-01-13 | 76379 | sp | 76379 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2026-01-14 | Z | 2026-01-13 | 0 | 0 | 0 |  | 0 | 60 |  | Pulled spiral |  | 1
2026-01-15 | 76380 |  | 76380 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-01-20 | Z | 2026-01-14 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 6
2026-01-15 | 3816 |  | LG-SAMP-04 | A | DONE | 43 | M/L |  | PROMEGA BTC 6250020 |  | 2026-01-20 | Z | 2026-01-13 | 230 | 0 | 410 |  | 0 | 1070 |  |  |  | 7 | 2026-01-20
2026-01-15 | 3818 | bth | LG-SAMP-06 | A | DONE | 55 | L |  | PROMEGA BTC 6250020 |  | 2026-01-20 | Z | 2026-01-13 | 340 | 80 | 520 |  | 0 | 1360 |  |  |  | 7 | 2026-01-20
2026-01-12 | 76404 | bth | 76404-10 | A | DONE | 18 | M |  | QBE 4250054 |  | 2026-01-13 | Z | 2026-01-06 | 160 | 310 | 0 |  | 0 | 430 |  | RVAV's |  | 7
2026-01-16 | 76418 | sp | 76418 | A | DONE | 2 | S |  | QBE 4250054 |  | 2026-01-20 | Z | 2026-01-16 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 4
2026-01-12 | 76002 |  | 76002-04 | A | DONE | 9 | S/M |  | SPH 6240039 | flex | 2026-01-13 | Z | 2026-01-07 | 120 | 0 | 0 |  | 0 | 210 |  | OR-8 Supply |  | 6
2026-01-12 | 76008 |  | 76005,76008 | A | DONE | 14 | S/M |  | SPH 6240039 |  | 2026-01-13 | Z | 2026-01-08 | 240 | 0 | 60 |  | 0 | 350 |  | PR return |  | 5
2026-01-14 | 76009 |  | 76009 | A | DONE | 2 | S |  | SPH 6240039 |  | 2026-01-16 | Z | 2026-01-12 | 30 | 0 | 0 |  | 0 | 40 |  | RA |  | 4
2026-01-13 | 76104 |  | 76104 | A | DONE | 2 | S |  | SWH MOB 6250015 | paint black | 2026-01-19 | Z | 2026-01-08 | 30 | 0 | 0 |  | 10 | 30 |  | Elevator equip room |  | 11
2026-01-14 | 76151 |  | 76151 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2026-01-19 | Z | 2026-01-13 | 10 | 0 | 0 |  | 0 | 20 |  | EF 3 south |  | 6
2026-01-14 | 74762 | bth | 74762 | A | DONE | 8 | S/M |  | THERMO FISHER 10066879 |  | 2026-01-16 | Z | 2026-01-13 | 40 | 130 | 0 |  | 0 | 180 |  | Lab 3315 |  | 3
2026-01-12 | 77104 |  | 77104 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2026-01-13 | Z | 2026-01-09 | 20 | 0 | 0 |  | 0 | 50 |  | FP box change |  | 4
2026-01-12 | 72558 |  | 72558 | A | DONE | 5 | S/M |  | UW LEVY HALL 6230028 |  | 2026-01-13 | Z | 2026-01-12 | 40 | 0 | 0 |  | 0 | 110 |  | Plenum flashing |  | 1
2026-01-16 | 76140 |  | 76140-41 | A | DONE | 10 | S/M |  | UW LEVY HALL 6230028 | MOD | 2026-01-20 | Z | 2026-01-09 | 150 | 0 | 0 |  | 0 | 230 |  | Elevator room |  | 11 | 2026-01-20
2026-01-13 | 76142 |  | 76142-43 | A | DONE | 15 | M |  | UW LEVY HALL 6230028 |  | 2026-01-15 | Z | 2026-01-12 | 165 | 0 | 0 |  | 30 | 370 |  | Penthouse |  | 3
2026-01-13 | 76144 |  | 76144 | A | DONE | 11 | S/M |  | UW LEVY HALL 6230028 |  | 2026-01-15 | Z | 2026-01-12 | 60 | 0 | 0 |  | 0 | 260 |  | Penthouse |  | 3
2026-01-15 | 76145 |  | 76145 | A | DONE | 6 | S/M |  | UW LEVY HALL 6230028 | 2" liner | 2026-01-20 | Z | 2026-01-14 | 60 | 0 | 0 |  | 50 | 140 |  |  |  | 6
2026-01-12 | 78321 |  | 78321 | A | DONE | 4 | S |  | UW LEVY HALL 6230028 |  | 2026-01-20 | Z | 2026-01-08 | 20 | 0 | 0 |  | 700 | 100 |  | L3 CB 293 |  | 12
2026-01-16 | 011626 |  | 011626 | A | DONE | 2 | S |  | UW LEVY HALL 6240028 |  | 2026-01-16 | Z | 2026-01-16 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2026-01-16 | 74859 |  | 74859 | A | DONE | 10 | S/M |  | UW LEVY HALL 6240028 |  | 2026-01-22 | Z | 2026-01-16 | 250 | 0 | 0 |  | 0 | 230 |  | Flashing |  | 6
2026-01-13 | 4032 | bth | L4-VAV-1-4-32 | A | DONE | 11 | S/M |  | UW STOUT 6250008 | 1" liner, VD | 2026-01-20 | Z | 2025-11-26 | 130 | 0 | 90 |  | 50 | 270 |  |  |  | 55
2026-01-15 | 4033 | bth | L4-VAV-1-4-33 | A | DONE | 18 | M |  | UW STOUT 6250008 | 1" liner, VD | 2026-01-20 | Z | 2025-11-26 | 180 | 30 | 170 |  | 40 | 430 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4034 | bth | L4-VAV-2-4-25 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner | 2026-01-20 | Z | 2025-11-26 | 40 | 30 | 0 |  | 20 | 70 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4035 | bth | L4-VAV-2-4-26 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, VD | 2026-01-20 | Z | 2025-11-26 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4036 | bth | L4-VAV-2-4-27 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4037 | bth | L4-VAV-2-4-28 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4038 | bth | L4-VAV-2-4-29 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1" liner, VD | 2026-01-20 | Z | 2025-11-26 | 50 | 10 | 0 |  | 30 | 80 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4039 | bth | L4-VAV-2-4-30 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4040 | bth | L4-VAV-2-4-31 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 55 | 2026-01-20
2026-01-13 | 4041 |  | L4-VAV-2-4-32 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-01-20 | Z | 2025-11-26 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 55
2026-01-14 | 4042 | bth | L4-VAV-2-4-33 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4043 | bth | L4-VAV-2-4-34 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4044 | bth | L4-VAV-2-4-35 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4045 | bth | L4-VAV-2-4-36 | A | DONE | 2 | S |  | UW STOUT 6250008 | VD | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4046 | bth | L4-VAV-2-4-38 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4047 | bth | L4-VAV-2-4-39 | A | DONE | 2 | S |  | UW STOUT 6250008 | VD | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4048 | bth | L4-VAV-2-4-40 | A | DONE | 2 | S |  | UW STOUT 6250008 | VD | 2026-01-20 | Z | 2025-11-26 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4049 | bth | L4-VAV-2-4-41 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4050 | bth | L4-VAV-2-4-42 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-01-20 | Z | 2025-11-26 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4051 | bth | L4-VAV-2-4-43 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4052 | bth | L4-VAV-2-4-44 | A | DONE | 3 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 40 | 20 | 0 |  | 0 | 60 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4053 | bth | L4-VAV-2-4-45 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 40 | 10 | 0 |  | 0 | 50 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4054 | bth | L4-VAV-2-4-46 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4055 |  | L4-VAV-2-4-47 | A | DONE | 5 | S/M |  | UW STOUT 6250008 | 1" liner, VD | 2026-01-20 | Z | 2025-11-26 | 60 | 0 | 20 |  | 30 | 110 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4056 | bth | L4-VAV-2-4-48 | A | DONE | 21 | M |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 520 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4057 | bth | L4-VAV-2-4-49 | A | DONE | 3 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 40 | 10 | 0 |  | 0 | 60 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4058 | bth | L4-VAV-2-4-50 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4059 | bth | L4-VAV-2-4-51 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 55 | 2026-01-20
2026-01-14 | 4060 | bth | L4-VAV-2-4-52 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 50 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4061 | bth | L4-VAV-2-4-53 | A | DONE | 3 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 40 | 10 | 0 |  | 0 | 60 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4062 | bth | L4-VAV-2-4-54 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 40 | 10 | 0 |  | 0 | 50 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4063 | bth | L4-VAV-2-4-55 | A | DONE | 3 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 30 | 10 | 20 |  | 0 | 60 |  |  |  | 55 | 2026-01-20
2026-01-15 | 4064 | bth | L4-VAV-2-4-59 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-11-26 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 55 | 2026-01-20
2026-01-13 | 4127 |  | L4-EA 4 | A | DONE | 8 | S/M |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-12-10 | 80 | 0 | 60 |  | 0 | 180 |  |  |  | 41
2026-01-12 | 4129 | bth | L4-EA 6 | A | DONE | 8 | S/M |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2025-12-10 | 90 | 20 | 50 |  | 0 | 180 |  |  |  | 41
2026-01-16 | 84554 |  | 84554 | A | DONE | 45 | M/L |  | UW STOUT 6250008 |  | 2026-01-20 | Z | 2026-01-12 | 450 | 0 | 0 |  | 0 | 1120 |  | Hangers, end cap |  | 8 | 2026-01-20
2026-01-12 | 10001 |  | 10001 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2026-01-13 | Z | 2026-01-08 | 60 | 30 | 0 |  | 0 | 100 |  | Laser lab |  | 5
2026-01-15 | 83757 |  | 83757 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2026-01-20 | Z | 2026-01-14 | 20 | 0 | 0 |  | 0 | 20 |  | End cap |  | 6
2026-01-12 | 83399 | w | 83399 | A | DONE | 2 | S | ss | WAUNAKEE 6230013 |  | 2026-01-14 | Z | 2026-01-06 | 10 | 0 | 0 |  | 0 | 20 |  | Dishwasher hood |  | 8
2026-01-13 | 95839 |  | 95839 | A | DONE | 2 | S |  | WHC 8250008 | pipe shop | 2026-01-13 | Z | 2026-01-13 | 20 | 0 | 0 |  | 0 | 50 |  | Pipe shop |  | 0
[6 empty] | 1197 | [13 empty] | 28380 | [5 empty] | 43% short
[9 empty] | WEEK OF 1-19-2026 | [16 empty] | % Under 14
2026-01-19 | 82768 | w | 82768 | A | DONE | 6 | S/M | ss | ANTIGO 6250017 |  | 2026-01-26 | Z | 2026-01-12 | 60 | 0 | 0 |  | 0 | 150 |  | RE-12 |  | 14 |  |  | 32.37%
2026-01-20 | 82771 |  | 82771 | A | DONE | 13 | S/M |  | ANTIGO 6250017 | 2" liner | 2026-01-26 | Z | 2026-01-14 | 200 | 0 | 80 |  | 190 | 320 |  | Area A north V-2 SA |  | 12
2026-01-20 | 82772 |  | 82772 | A | DONE | 5 | S/M | neal | ANTIGO 6250017 | 1" liner | 2026-01-26 | Z | 2026-01-14 | 80 | 0 | 0 |  | 50 | 110 |  | AHU-1 RA |  | 12
2026-01-21 | 82773 | sp | 82773 | A | DONE | 9 | S/M |  | ANTIGO 6250017 |  | 2026-01-26 | Z | 2026-01-14 | 40 | 150 | 0 |  | 0 | 220 |  | Area A north V-2 SA |  | 12
2026-01-23 | 82776 | sp | 82776 | A | DONE | 5 | S/M |  | ANTIGO 6250017 |  | 2026-02-02 | Z | 2026-01-20 | 30 | 90 | 0 |  | 0 | 110 |  | Area A north RE 6 EA |  | 13
2026-01-20 | 82777 |  | 82777 | A | DONE | 5 | S/M |  | ANTIGO 6250017 | 2" liner | 2026-01-26 | Z | 2026-01-19 | 80 | 0 | 0 |  | 60 | 110 |  | Area A north V1 SA |  | 7
2026-01-22 | 83760 |  | 83760 | A | DONE | 2 | S |  | ANTIGO 6250017 |  | 2026-01-26 | Z | 2026-01-21 | 10 | 0 | 0 |  | 0 | 20 |  | Heto |  | 5
2026-01-20 | 53962 | w | 53962 | A | DONE | 2 | S |  | BABCOCK HALL 2250052 |  | 2026-01-26 | Z | 2026-01-16 | 10 | 0 | 0 |  | 0 | 20 |  | Damper |  | 10
2026-01-20 | 74268 |  | 74268 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2026-01-21 | Z | 2026-01-16 | 10 | 0 | 0 |  | 0 | 20 |  | damper piece |  | 5
2026-01-23 | 80916 | w | 80916 | A | DONE | 2 | S |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 10 | 0 | 0 |  | 0 | 50 |  | Genny exhaust |  | 14
2026-01-22 | 1216 |  | UNIT 100 M4.31 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 280 | 0 | 30 |  | 0 | 300 |  |  |  | 83
2026-01-22 | 1217 |  | UNIT 101 M4.32 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 290 | 0 | 20 |  | 0 | 290 |  |  |  | 83
2026-01-20 | 1218 |  | UNIT 103 M4.33 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 83
2026-01-21 | 1219 |  | UNIT 105 M4.34 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 140 | 0 | 0 |  | 0 | 150 |  |  |  | 83
2026-01-21 | 1220 |  | UNIT 106 M4.35 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 100 | 70 | 0 |  | 0 | 170 |  |  |  | 83
2026-01-20 | 1221 |  | UNIT 107 M4.36 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 80 | 0 | 0 |  | 0 | 80 |  |  |  | 83
2026-01-21 | 1222 |  | UNIT 108 M4.37 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 110 | 70 | 0 |  | 0 | 190 |  |  |  | 83
2026-01-21 | 1223 |  | UNIT 109 M4.38 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 120 | 0 | 50 |  | 0 | 180 |  |  |  | 83
2026-01-20 | 1224 |  | UNIT 109 M4.38A | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 90 | 0 | 70 |  | 0 | 160 |  |  |  | 83
2026-01-21 | 1225 |  | UNIT 110 M4.35 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 100 | 70 | 0 |  | 0 | 180 |  |  |  | 83
2026-01-20 | 1226 |  | UNIT 111 M4.39 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 80 | 0 | 30 |  | 0 | 110 |  |  |  | 83
2026-01-21 | 1227 |  | UNIT 111 M4.39A | A | DONE | 3 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 60 | 0 | 0 |  | 0 | 60 |  |  |  | 83
2026-01-21 | 1228 |  | UNIT 113 M4.40 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 100 | 0 | 30 |  | 0 | 120 |  |  |  | 83
2026-01-20 | 1229 |  | UNIT 113 M4.40A | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 80 | 0 | 0 |  | 0 | 80 |  |  |  | 83
2026-01-21 | 1230 |  | UNIT 115 M4.41 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 80 | 0 | 30 |  | 0 | 110 |  |  |  | 83
2026-01-21 | 1231 |  | UNIT 115 M4.41A | A | DONE | 3 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 60 | 0 | 0 |  | 0 | 60 |  |  |  | 83
2026-01-22 | 1232 |  | UNIT 116 M4.37 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 110 | 70 | 0 |  | 0 | 190 |  |  |  | 83
2026-01-20 | 1233 |  | UNIT 118 M4.42 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 50 | 0 | 0 |  | 0 | 50 |  |  |  | 83
2026-01-22 | 1234 |  | UNIT 119 M4.43 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 90 | 0 | 0 |  | 0 | 110 |  |  |  | 83
2026-01-20 | 1235 |  | UNIT 121 M4.44 | A | DONE | 9 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 210 | 0 | 0 |  | 0 | 220 |  |  |  | 83
2026-01-20 | 1236 |  | UNIT 122 M4.45 | A | DONE | 16 | M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-11-05 | 390 | 0 | 20 |  | 0 | 380 |  |  |  | 83 |  | 2025-09-02
2026-01-21 | 1539 |  | UNIT 300 M4.90 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 180 | 0 | 90 |  | 0 | 270 |  |  |  | 35
2026-01-20 | 1540 |  | UNIT 301 M4.91 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 150 | 0 | 110 |  | 0 | 270 |  |  |  | 35
2026-01-21 | 1541 |  | UNIT 303 M4.56 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 35
2026-01-22 | 1542 | bth | UNIT 305 M4.57 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 80 | 70 | 0 |  | 0 | 150 |  |  |  | 35
2026-01-22 | 1543 | bth | UNIT 306 M4.58 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 70 | 70 | 0 |  | 0 | 150 |  |  |  | 35
2026-01-22 | 1544 | bth | UNIT 307 M4.59 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 80 | 70 | 0 |  | 0 | 160 |  |  |  | 35
2026-01-22 | 1545 | bth | UNIT 308 M4.60 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 80 | 70 | 0 |  | 0 | 160 |  |  |  | 35
2026-01-22 | 1546 | bth | UNIT 309 M4.57 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 100 | 70 | 0 |  | 0 | 170 |  |  |  | 35
2026-01-22 | 1547 | bth | UNIT 310 M4.58 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 80 | 70 | 0 |  | 0 | 150 |  |  |  | 35
2026-01-22 | 1548 | bth | UNIT 311 M4.59 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 90 | 70 | 0 |  | 0 | 160 |  |  |  | 35
2026-01-22 | 1549 | bth | UNIT 312 M4.60 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 70 | 70 | 0 |  | 0 | 150 |  |  |  | 35
2026-01-21 | 1550 |  | UNIT 314 M4.61 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 35
2026-01-21 | 1551 |  | UNIT 315 M4.62 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 90 | 0 | 0 |  | 0 | 100 |  |  |  | 35
2026-01-21 | 1552 |  | UNIT 317 M4.63 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 110 | 0 | 90 |  | 0 | 180 |  |  |  | 35
2026-01-22 | 1553 |  | UNIT 318 M4.92 | A | DONE | 22 | M |  | BROOM ST. 6240033 |  | 2026-01-27 | Z | 2025-12-23 | 430 | 0 | 210 |  | 0 | 530 |  |  |  | 35
2026-01-22 | 1556 |  | 58182-84 | A | DONE | 17 | M |  | BROOM ST. 6240033 | rivet nuts | 2026-01-29 | Z | 2025-12-23 | 170 | 0 | 0 |  | 0 | 410 |  | OA kits |  | 37
2026-01-23 | 75728 |  | 75728 | A | DONE | 4 | S |  | DC6 6250027 |  | 2026-01-27 | Z | 2026-01-21 | 50 | 0 | 0 |  | 0 | 90 |  | Flashing |  | 6
2026-01-23 | 75729 |  | 75729 | A | DONE | 2 | S |  | DC6 6250027 |  | 2026-01-27 | Z | 2026-01-22 | 20 | 0 | 0 |  | 0 | 30 |  | Cone flashing |  | 5
2026-01-20 | 73663 |  | 73663-64 | A | DONE | 20 | M |  | DELLSHIRE 6240017 | 1" liner | 2026-01-26 | Z | 2026-01-14 | 350 | 0 | 0 |  | 230 | 480 |  | VTAC Plenums |  | 12
2026-01-19 | 74119 | sp | 74119 | A | DONE | 9 | S/M | alum | DELLSHIRE 6240017 | dymonic | 2026-01-22 | Z | 2026-01-12 | 190 | 230 | 0 |  | 0 | 210 |  | Dryer venting |  | 10
2026-01-21 | 74120 | sp | 74120 | A | DONE | 4 | S |  | DELLSHIRE 6240017 |  | 2026-01-26 | Z | 2026-01-14 | 40 | 120 | 0 |  | 0 | 80 |  | Flat iron exhaust |  | 12
2026-01-20 | 74215 |  | 74215 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2026-01-26 | Z | 2026-01-15 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 11
2026-01-21 | 76451 |  | 76451-52,75297-99 | A | DONE | 84 | L |  | DELLSHIRE 6240017 |  | 2026-01-22 | Z | 2026-01-07 | 950 | 0 | 270 |  | 0 | 2090 |  | AHU 6-7 |  | 15
2026-01-20 | 76456 | bth | 76456-59 | A | DONE | 8 | S/M |  | DELLSHIRE 6240017 |  | 2026-01-22 | Z | 2026-01-15 | 110 | 40 | 0 |  | 0 | 190 |  |  |  | 7
2026-01-21 | 10003 |  | 10003 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2026-01-22 | Z | 2026-01-20 | 10 | 0 | 0 |  | 10 | 20 |  | Remake |  | 2
2026-01-20 | 3150 | bth | Z2-SAT-1-1-1 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2026-01-22 | Z | 2025-09-17 | 30 | 0 | 0 |  | 10 | 30 |  |  |  | 127 | 2025-11-13 | 2025-11-06
2026-01-19 | 3152 | bth | Z2-SAT-1-1-3_1 | A | DONE | 19 | M |  | DOC JDC 6240023 | 1" liner | 2026-01-22 | Z | 2025-09-17 | 290 | 0 | 0 |  | 50 | 460 |  |  |  | 127 | 2025-11-13 | 2025-11-06
2026-01-19 | 56104 | bth | 56104-05 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2026-01-22 | Z | 2026-01-14 | 50 | 0 | 0 |  | 0 | 60 |  | OA 06 |  | 8
2026-01-19 | 716 |  | Z2-EA 47 | A | DONE | 14 | S/M |  | DOC JDC 6240023 | VD | 2026-01-22 | Z | 2025-07-30 | 300 | 0 | 0 |  | 0 | 350 |  |  |  | 176 | 2025-09-04 | 2025-11-20
2026-01-21 | 74361 |  | 74361 | A | DONE | 17 | M |  | DOC JDC 6240023 |  | 2026-01-27 | Z | 2026-01-16 | 280 | 0 | 40 |  | 160 | 420 |  | REL tie ins |  | 11
2026-01-22 | 74365 | w | 74365 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2026-01-27 | Z | 2026-01-16 | 40 | 0 | 0 |  | 0 | 150 |  | Drain pan crac unit |  | 11
2026-01-20 | 74366 | sp | 74366 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-26 | Z | 2026-01-19 | 0 | 20 | 0 |  | 0 | 30 |  | RF-4 |  | 7
2026-01-19 | 755 | w | Z1-DISHWASHER EA 1 | A | DONE | 9 | S/M | ss | DOC JDC 6240023 | MOD | 2026-01-22 | Z | 2025-08-05 | 80 | 0 | 0 |  | 0 | 210 |  |  |  | 170 |  | 2025-11-20
2026-01-20 | 76602 |  | 76602-03,56108 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2026-01-22 | Z | 2026-01-16 | 50 | 0 | 0 |  | 0 | 70 |  | Z1 OA |  | 6
2026-01-20 | 76604 |  | 76604 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2026-01-22 | Z | 2026-01-20 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 2
2026-01-21 | 97729 |  | 97729 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-29 | Z | 2026-01-16 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 13
2026-01-20 | 97732 |  | 97732 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-29 | Z | 2026-01-19 | 10 | 0 | 0 |  | 10 | 20 |  |  |  | 10
2026-01-20 | 83759 |  | 83759 | A | DONE | 2 | S |  | EMPLOYEE 1000381 |  | 2026-01-21 | Z | 2026-01-20 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2026-01-21 | 81336 | bth | 81336-42 | A | DONE | 53 | L | alum | GRANT ELEM 6250021 |  | 2026-01-26 | Z | 2026-01-12 | 220 | 480 | 530 |  | 0 | 1310 |  | Phase 4 |  | 14
2026-01-22 | 74771 |  | 74771 | A | DONE | 4 | S |  | GREAT WOLF 4250055 |  | 2026-01-13 | Z | 2026-01-22 | 50 | 0 | 0 |  | 0 | 80 |  | Exh. |  | -9
2026-01-23 | 74772 |  | 74772 | A | DONE | 2 | S |  | GREAT WOLF 4250055 |  | 2026-01-23 | Z | 2026-01-23 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2026-01-19 | 64667r |  | 64667r | A | DONE | 2 | S |  | MAUSTON R 6250019 |  | 2026-01-20 | Z | 2026-01-19 | 10 | 0 | 0 |  | 0 | 20 |  | Remake |  | 1
2026-01-22 | 64712 |  | 64712 | A | DONE | 5 | S/M | alum | MAUSTON R 6250019 |  | 2026-01-26 | Z | 2026-01-16 | 200 | 0 | 0 |  | 0 | 120 |  | EA |  | 10
2026-01-22 | 83630 | sp | 83630 | L | DONE | 3 | S |  | MONROE 6240018 |  | 2026-01-28 | Z | 2026-01-14 | 0 | 80 | 0 |  | 30 | 70 |  | Dual wall |  | 14
2026-01-23 | 83632 | sp | 83632-33 | A | DONE | 6 | S/M | neal | MONROE 6240018 |  | 2026-01-28 | Z | 2026-01-21 | 20 | 100 | 0 |  | 0 | 140 |  | E section exhaust |  | 7
2026-01-22 | 83740 | sp | 83740-41 | A | DONE | 10 | S/M | neal | MONROE 6240018 |  | 2026-01-28 | Z | 2026-01-16 | 40 | 160 | 0 |  | 0 | 230 |  | Spray space |  | 12
2026-01-22 | 84921 |  | 84921-30 | A | DONE | 25 | M |  | MONROE 6240018 |  | 2026-01-28 | Z | 2026-01-14 | 420 | 60 | 40 |  | 10 | 610 |  | Concessions |  | 14
2026-01-22 | 97997 |  | 97997-98000 | A | DONE | 3 | S | ss | MONROE 6240018 |  | 2026-01-28 | Z | 2026-01-16 | 20 | 0 | 0 |  | 10 | 60 |  | Hangers |  | 12
2026-01-20 | 74676 |  | 74676 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2026-01-28 | Z | 2026-01-16 | 20 | 0 | 0 |  | 0 | 30 |  | Kiln room RFI |  | 12
2026-01-22 | 74677 | sp | 74677 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2026-02-02 | Z | 2026-01-16 | 20 | 0 | 0 |  | 0 | 20 |  | H112E |  | 17
2026-01-22 | 76380 |  | 76380a | A | DONE | 7 | S/M |  | PROJECT DOVE 6240041 |  | 2026-01-23 | Z | 2026-01-21 | 120 | 0 | 0 |  | 0 | 170 |  | Flashing |  | 2
2026-01-22 | 76381 |  | 76381 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-01-30 | Z | 2026-01-20 | 10 | 0 | 0 |  | 0 | 20 |  | 600 |  | 10
2026-01-19 | 3817 | bth | LG-SAMP-05 | A | DONE | 27 | M |  | PROMEGA BTC 6250020 |  | 2026-01-20 | Z | 2026-01-13 | 240 | 80 | 210 |  | 0 | 670 |  |  |  | 7 | 2026-01-20
2026-01-23 | 3819 | bth | LG-SAMP-01 | A | DONE | 87 | L |  | PROMEGA BTC 6250020 |  | 2026-01-28 | Z | 2026-01-13 | 920 | 40 | 270 |  | 0 | 2160 |  |  |  | 15
2026-01-22 | 3821 | bth | LG-SAMP-03 | A | DONE | 30 | M |  | PROMEGA BTC 6250020 |  | 2026-01-28 | Z | 2026-01-13 | 300 | 40 | 140 |  | 0 | 730 |  |  |  | 15
2026-01-22 | 81865 |  | 81865 | A | DONE | 7 | S/M |  | PROMEGA BTC 6250020 |  | 2026-01-26 | Z | 2026-01-20 | 70 | 0 | 0 |  | 0 | 170 |  | Misc |  | 6
2026-01-22 | 81866 |  | 81866 | A | DONE | 4 | S |  | PROMEGA BTC 6250020 |  | 2026-01-28 | Z | 2026-01-21 | 60 | 0 | 0 |  | 0 | 80 |  | Misc. |  | 7
2026-01-22 | 83761 |  | 83761 | A | DONE | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-01-23 | Z | 2026-01-22 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2026-01-21 | 76011 |  | 76011 | A | DONE | 2 | S | neal | RCIS 6250011 |  | 2026-02-02 | Z | 2026-01-19 | 20 | 0 | 0 |  | 0 | 20 |  | Angle |  | 14
2026-01-21 | 85454 |  | 85454 | A | DONE | 4 | S |  | SHRINE 6240034 | 1" liner | 2026-02-02 | Z | 2026-01-20 | 10 | 0 | 60 |  | 10 | 80 |  | Level 1 |  | 13
2026-01-20 | 76010 | sp | 76010 | A | DONE | 2 | S |  | SPH 6240039 |  | 2026-01-26 | Z | 2026-01-14 | 10 | 0 | 0 |  | 0 | 20 |  | RAV 4-49 |  | 12
2026-01-20 | 77207 |  | 77207 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2026-01-26 | Z | 2026-01-19 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2026-01-19 | 74770 |  | 74770 | A | DONE | 2 | S | pcd | THERMO FISHER 10066879 | birdscreen | 2026-01-19 | Z | 2026-01-19 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2026-01-19 | 77106 |  | 77106 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2026-01-27 | Z | 2026-01-16 | 40 | 0 | 0 |  | 0 | 40 |  | FP VAV returns |  | 11
2026-01-21 | 76140r |  | 76140r | A | DONE | 6 | S/M |  | UW LEVY HALL 6230018 |  | 2026-01-22 | Z | 2026-01-21 | 130 | 0 | 0 |  | 0 | 150 |  | Elevator room |  | 1
2026-01-19 | 53959 |  | 53959-60 | A | DONE | 12 | S/M |  | UW LEVY HALL 6230028 |  | 2026-01-20 | Z | 2026-01-09 | 90 | 0 | 0 |  | 50 | 280 |  | Penthouse |  | 11 | 2026-01-20
2026-01-20 | 74861 |  | 74861 | A | DONE | 6 | S/M |  | UW LEVY HALL 6230028 | paint black | 2026-01-27 | Z | 2026-01-19 | 80 | 0 | 0 |  | 100 | 140 |  | L4/L5 RG-4 |  | 8
2026-01-20 | 74857 |  | 74857 | A | DONE | 2 | S |  | UW LEVY HALL 6240028 |  | 2026-01-20 | Z | 2026-01-16 | 30 | 0 | 0 |  | 0 | 30 |  | LL VAV covers |  | 4
2026-01-22 | 74860 | sp | 74860 | A | DONE | 2 | S |  | UW LEVY HALL 6240028 |  | 2026-01-29 | Z | 2026-01-16 | 40 | 0 | 0 |  | 0 | 50 |  | L3/L4 Reducers |  | 13
2026-01-19 | 76146 |  | 76146 | A | DONE | 8 | S/M |  | UW LEVY HALL 6240028 |  | 2026-01-20 | Z | 2026-01-16 | 30 | 0 | 0 |  | 0 | 180 |  | Penthouse |  | 4
2026-01-19 | 4065 |  | L4-VAV-1-4-13_1 | A | DONE | 6 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 100 | 0 | 0 |  | 50 | 140 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4066 |  | L4-VAV-1-4-13_2 | A | DONE | 7 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 100 | 0 | 0 |  | 0 | 160 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4067 |  | L4-VAV-1-4-13_3 | A | DONE | 7 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 80 | 0 | 0 |  | 0 | 170 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4068 |  | L4-VAV-1-4-13_4 | A | DONE | 7 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 70 | 0 | 0 |  | 0 | 160 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4069 |  | L4-VAV-1-4-13_5 | A | DONE | 5 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 60 | 0 | 0 |  | 0 | 120 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4070 |  | L4-VAV-1-4-13_6 | A | DONE | 6 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 80 | 0 | 0 |  | 0 | 140 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4071 |  | L4-VAV-1-4-14 | A | DONE | 6 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 90 | 0 | 0 |  | 0 | 130 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4072 | bth | L4-VAV-1-4-15 | A | DONE | 4 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 50 | 20 | 0 |  | 0 | 80 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4073 |  | L4-VAV-1-4-17 | A | DONE | 5 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 50 | 50 | 0 |  | 0 | 110 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4074 | bth | L4-VAV-1-4-19 | A | DONE | 23 | M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 180 | 320 | 0 |  | 50 | 570 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4075 | bth | L4-VAV-2-4-4 | A | DONE | 4 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 40 | 40 | 0 |  | 0 | 90 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4076 | bth | L4-VAV-2-4-5 | A | DONE | 4 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 60 | 20 | 0 |  | 30 | 80 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4077 | bth | L4-VAV-2-4-6 | A | DONE | 4 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 60 | 20 | 0 |  | 0 | 80 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4078 | bth | L4-VAV-2-4-7 | A | DONE | 5 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 60 | 60 | 0 |  | 0 | 120 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4079 | bth | L4-VAV-2-4-8_1 | A | DONE | 6 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 80 | 50 | 0 |  | 30 | 140 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4080 |  | L4-VAV-2-4-8_2 | A | DONE | 14 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 220 | 0 | 0 |  | 0 | 350 |  |  |  | 51 | 2026-01-27
2026-01-19 | 4081 |  | L4-VAV-2-4-8_3 | A | DONE | 12 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 160 | 0 | 0 |  | 0 | 280 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4082 |  | L4-VAV-2-4-8_4 | A | DONE | 20 | M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 280 | 0 | 0 |  | 0 | 500 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4083 | bth | L4-VAV-2-4-8_11 | A | DONE | 3 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 30 | 30 | 0 |  | 0 | 60 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4084 | bth | L4-VAV-2-4-8_12 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4085 |  | L4-VAV-2-4-8_13 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4086 | bth | L4-VAV-2-4-8_14 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4087 | bth | L4-VAV-2-4-8_15 | A | DONE | 3 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 40 | 10 | 0 |  | 0 | 60 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4088 | bth | L4-VAV-2-4-8_16 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4089 | bth | L4-VAV-2-4-8_17 | A | DONE | 9 | S/M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 60 | 100 | 30 |  | 50 | 210 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4090 | bth | L4-VAV-2-4-8_18 | A | DONE | 15 | M |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 110 | 240 | 0 |  | 50 | 370 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4091 | bth | L4-VAV-2-4-8_19 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4092 | bth | L4-VAV-2-4-8_20 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4093 | bth | L4-VAV-2-4-8_21 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 30 | 10 | 0 |  | 0 | 30 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4094 | bth | L4-VAV-2-4-8_22 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4095 | bth | L4-VAV-2-4-8_23 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 51 | 2026-01-27
2026-01-20 | 4096 | bth | L4-VAV-2-4-8_24 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-21 | Z | 2025-12-01 | 40 | 10 | 0 |  | 0 | 50 |  |  |  | 51 | 2026-01-27
2026-01-22 | 4131 |  | L4-TA 134 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 70 | 0 | 0 |  | 40 | 80 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4132 |  | L4-TA 138 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4133 |  | L4-TA 139 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4134 |  | L4-TA 140 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 44 | 2026-02-03
2026-01-22 | 4136 |  | L4-TA 142 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 44 | 2026-02-03
2026-01-22 | 4137 |  | L4-TA 143 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 50 | 0 | 0 |  | 30 | 50 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4138 |  | L4-TA 144 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 44 | 2026-02-03
2026-01-22 | 4139 |  | L4-TA 145 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 44 | 2026-02-03
2026-01-22 | 4140 |  | L4-TA 146 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 44 | 2026-02-03
2026-01-22 | 4141 |  | L4-TA 147 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4142 |  | L4-TA 148 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 44 | 2026-02-03
2026-01-22 | 4143 |  | L4-TA 149 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4144 |  | L4-TA 150 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4145 |  | L4-TA 151 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4146 |  | L4-TA 152 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4147 |  | L4-TA 153 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 44 | 2026-02-03
2026-01-21 | 4148 |  | L4-TA 154 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 44 | 2026-02-03
2026-01-22 | 4149 |  | L4-TA 155 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 50 | 0 | 0 |  | 30 | 50 |  |  |  | 44 | 2026-02-03
2026-01-22 | 4150 |  | L4-TA 1 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 40 | 0 | 0 |  | 40 | 70 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4154 |  | L4-TA 5 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 40 | 40 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4155 |  | L4-TA 6 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4156 |  | L4-TA 7 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4157 |  | L4-TA 8 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 30 | 60 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4159 |  | L4-TA 10 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4160 |  | L4-TA 11 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 43 | 2026-02-03
2026-01-23 | 4161 |  | L4-TA 12 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4162 |  | L4-TA 13 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 43 | 2026-02-03
2026-01-21 | 4163 |  | L4-TA 14 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4164 |  | L4-TA 15 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 60 | 0 | 0 |  | 30 | 60 |  |  |  | 43 | 2026-02-03
2026-01-21 | 4165 |  | L4-TA 16 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4166 |  | L4-TA 17 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4167 |  | L4-TA 18 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 40 | 0 | 30 |  | 60 | 90 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4168 |  | L4-TA 19 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4169 |  | L4-TA 20 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 43 | 2026-02-03
2026-01-21 | 4170 |  | L4-TA 21 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 43 | 2026-02-03
2026-01-21 | 4171 |  | L4-TA 22 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 43 | 2026-02-03
2026-01-22 | 4176 |  | L4-TA 27 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4177 |  | L4-TA 28 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 42 | 2026-02-03
2026-01-21 | 4178 |  | L4-TA 29 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4179 |  | L4-TA 30 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 42 | 2026-02-03
2026-01-23 | 4181 |  | L4-TA 32 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 60 | 0 | 0 |  | 40 | 60 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4183 |  | L4-TA 34 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 42 | 2026-02-03
2026-01-21 | 4186 |  | L4-TA 37 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 42 | 2026-02-03
2026-01-21 | 4188 |  | L4-TA 39 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4190 |  | L4-TA 41 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4191 |  | L4-TA 42 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4192 |  | L4-TA 43 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 42 | 2026-02-03
2026-01-21 | 4197 |  | L4-TA 48 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 42 | 2026-02-03
2026-01-21 | 4198 |  | L4-TA 49 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 42 | 2026-02-03
2026-01-21 | 4199 |  | L4-TA 50 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4200 |  | L4-TA 51 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4201 |  | L4-TA 52 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 42 | 2026-02-03
2026-01-23 | 4204 |  | L4-TA 55 | A | DONE | 6 | S/M |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 110 | 0 | 0 |  | 60 | 130 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4205 |  | L4-TA 56 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4209 |  | L4-TA 135 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 42 | 2026-02-03
2026-01-22 | 4210 |  | L4-TA 136 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 42 | 2026-02-03
2026-01-23 | 4289 | sp | L5-SHAFT EA D 1 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2026-01-23 | 4290 | sp | L5-SHAFT EA D 2 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2026-01-21 | 4291 |  | L5-SHAFT EA E 1 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 13
2026-01-21 | 4292 | sp | L5-SHAFT EA E 2 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2026-01-21 | 4303 | sp | L4-SHAFT EA D 1 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2026-01-21 | 4304 | sp | L4-SHAFT EA D 2 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2026-01-21 | 4305 |  | L4-SHAFT EA E 1 | A | DONE | 5 | S/M |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 40 | 50 | 0 |  | 0 | 110 |  |  |  | 13
2026-01-21 | 4306 | sp | L4-SHAFT EA E 2 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 10 | 30 | 0 |  | 0 | 30 |  |  |  | 13
2026-01-22 | 4312 |  | L4-SHAFT SAMP C 1 | A | DONE | 16 | M |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 0 | 170 | 0 |  | 0 | 390 |  |  |  | 13
2026-01-22 | 4314 |  | L4-SHAFT SAMP H 1 | A | DONE | 17 | M |  | UW STOUT 6250008 |  | 2026-05-01 | Z | 2026-01-14 | 140 | 60 | 0 |  | 0 | 410 |  |  |  | 107 | 2026-01-27
2026-01-21 | 4320 |  | L3-SHAFT EA B 1 | A | DONE | 7 | S/M |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 140 | 0 | 0 |  | 0 | 160 |  |  |  | 13
2026-01-22 | 4321 | sp | L3-SHAFT EA D 1 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2026-01-22 | 4322 | sp | L3-SHAFT EA D 2 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2026-01-21 | 4323 |  | L3-SHAFT EA E 1 | A | DONE | 4 | S |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 40 | 30 | 0 |  | 0 | 80 |  |  |  | 13
2026-01-23 | 4329 |  | L3-SHAFT SAMP C 1 | A | DONE | 16 | M |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 0 | 170 | 0 |  | 0 | 380 |  |  |  | 13
2026-01-22 | 4330 |  | L3-SHAFT SAMP F 1 | A | DONE | 15 | M |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 0 | 160 | 0 |  | 0 | 360 |  |  |  | 13
2026-01-20 | 76601 | sp | 76601 | L | DONE | 10 | S/M |  | UWH 2250039 |  | 2026-01-22 | Z | 2026-01-19 | 130 | 20 | 0 |  | 0 | 240 |  | EA |  | 3
2026-01-19 | 82947 | bth | 82947-48 | A | DONE | 6 | S/M |  | WAUNAKEE 6230013 |  | 2026-01-21 | Z | 2026-01-15 | 50 | 110 | 0 |  | 0 | 150 |  |  |  | 6
[6 empty] | 1320 | [13 empty] | 30070 | [5 empty] | 23% Short
[9 empty] | WEEK OF 1-26-2026 | [16 empty] | % Under 14
2026-01-26 | 82775 |  | 82775 | A | DONE | 8 | S/M |  | ANTIGO 6250017 |  | 2026-02-02 | Z | 2026-01-20 | 150 | 0 | 30 |  | 90 | 200 |  | Area A north RE 6 EA |  | 13 |  |  | 29.7%
2026-01-28 | 82781 |  | 82881-83 | A | DONE | 12 | S/M |  | ANTIGO 6250017 | 1" liner | 2026-02-02 | Z | 2026-01-23 | 150 | 0 | 0 |  | 80 | 290 |  | Grille boxes 2nd floor |  | 10
2026-01-29 | 82786 | sp | 82786 | A | done | 5 | S/M |  | ANTIGO 6250017 |  | 2026-02-02 | Z | 2026-01-28 | 10 | 110 | 0 |  | 0 | 110 |  | West tower corridor duct |  | 5
2026-01-28 | 1595 |  | UNIT 400 M4.90 | A | DONE | 11 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 240 | 0 | 30 |  | 0 | 270 |  | Drive |  | 14
2026-01-28 | 1596 |  | UNIT 401 M4.91 | A | DONE | 12 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 190 | 0 | 80 |  | 0 | 290 |  |  |  | 14 | 2026-01-27
2026-01-28 | 1597 |  | UNIT 403 M4.56 | A | DONE | 2 | S |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 14 | 2026-01-27
2026-01-29 | 1598 | bth | UNIT 405 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 70 | 70 | 0 |  | 0 | 150 |  |  |  | 14 | 2026-01-27
2026-01-30 | 1600 | bth | UNIT 407 M4.59 | A | done | 7 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 70 | 70 | 0 |  | 0 | 160 |  |  |  | 14
2026-01-29 | 1601 | bth | UNIT 408 M4.60 | A | done | 7 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 70 | 70 | 0 |  | 0 | 160 |  | TA |  | 14
2026-01-29 | 1602 | bth | UNIT 409 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 70 | 70 | 0 |  | 0 | 150 |  | Dampers |  | 14
2026-01-29 | 1604 | bth | UNIT 411 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 80 | 70 | 0 |  | 0 | 150 |  | VAV SAT 2-1-8 |  | 14
2026-01-29 | 1606 |  | UNIT 414 M4.61 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 40 | 0 | 0 |  | 0 | 40 |  | CB 145 |  | 14
2026-01-29 | 1607 |  | UNIT 415 M4.62 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 90 | 0 | 0 |  | 0 | 100 |  | Penthouse OA 27 |  | 14
2026-01-29 | 1608 |  | UNIT 417 M4.63 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 120 | 0 | 90 |  | 0 | 180 |  |  |  | 14
2026-01-29 | 1609 |  | UNIT 418 M4.92 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 260 | 0 | 60 |  | 0 | 300 |  | Pipe shop |  | 14
2026-01-30 | 1658 |  | TRASH EXHAUST L6E-L10E | A | done | 21 | M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-29 | 80 | 0 | 320 |  | 0 | 510 |  |  |  | 6
2026-01-27 | 58186 | sp | 58186 | A | DONE | 5 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-19 | 70 | 60 | 0 |  | 0 | 110 |  |  |  | 15
2026-01-26 | 58187 |  | 58187 | A | DONE | 10 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 220 | 0 | 0 |  | 0 | 230 |  | Woods FE |  | 14
2026-01-27 | 58188 |  | 58188 | A | DONE | 2 | S |  | BROOM ST 6240033 |  | 2026-02-06 | Z | 2026-01-23 | 20 | 0 | 0 |  | 0 | 40 |  | Kitchen |  | 14
2026-01-27 | 1513 | bth | UNIT 432 M4.65 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 60 | 80 | 0 |  | 0 | 160 |  | Flashing |  | 49
2026-01-28 | 1514 |  | UNIT 433 M4.66 | A | DONE | 10 | S/M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 210 | 0 | 0 |  | 0 | 230 |  | Roof duct, BCU's |  | 49
2026-01-28 | 1515 |  | UNIT 434 M4.67 | A | DONE | 18 | M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 390 | 0 | 40 |  | 0 | 450 |  | FE Metals |  | 49
2026-01-27 | 1516 |  | UNIT 435 M4.68 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 90 | 0 | 0 |  | 0 | 100 |  |  |  | 49
2026-01-28 | 1517 |  | UNIT 436 M4.69 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 100 | 0 | 0 |  | 0 | 110 |  |  |  | 49
2026-01-28 | 1518 |  | UNIT 437 M4.70 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 240 | 0 | 40 |  | 0 | 290 |  | 700 |  | 49
2026-01-28 | 1519 |  | UNIT 438 M4.71 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 270 | 0 | 0 |  | 0 | 280 |  | L2 600 |  | 49
2026-01-28 | 1520 |  | UNIT 439 M4.72 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 240 | 0 | 40 |  | 0 | 260 |  |  |  | 49
2026-01-27 | 1521 |  | UNIT 441 M4.73 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 70 | 0 | 0 |  | 0 | 80 |  | Transfer |  | 49
2026-01-28 | 1522 |  | UNIT 442 M4.74 | A | DONE | 9 | S/M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 210 | 0 | 40 |  | 0 | 220 |  | Organ flashing |  | 49
2026-01-30 | 33246 |  | 33246 | A | done | 3 | S |  | CHURCHILL 8250030 |  | 2026-02-03 | Z | 2026-01-29 | 40 | 0 | 0 |  | 0 | 70 |  | Sleeves |  | 5
2026-01-28 | 74121 | bth | 74121 | A | DONE | 5 | S/M |  | DELLSHIRE 6240017 |  | 2026-02-02 | Z | 2026-01-23 | 30 | 70 | 0 |  | 0 | 110 |  |  |  | 10
2026-01-28 | 74122 | bth | 74122 | A | DONE | 9 | S/M |  | DELLSHIRE 6240017 |  | 2026-02-02 | Z | 2026-01-28 | 90 | 130 | 0 |  | 0 | 220 |  |  |  | 5
2026-01-28 | 74216 |  | 74216,76463 | A | DONE | 7 | S/M |  | DELLSHIRE 6240017 |  | 2026-02-02 | Z | 2026-01-23 | 110 | 0 | 0 |  | 0 | 170 |  |  |  | 10
2026-01-26 | 76460 |  | 76460-62 | A | DONE | 4 | S |  | DELLSHIRE 6240017 |  | 2026-01-29 | Z | 2026-01-22 | 50 | 0 | 0 |  | 30 | 80 |  |  |  | 7
2026-01-29 | 76464 | sp | 76464 | A | done | 2 | S |  | DELLSHIRE 6240017 |  | 2026-02-02 | Z | 2026-01-28 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 5
2026-01-29 | 4802 |  | Z2-FE WELD 6 | A | done | 2 | S | neal | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-28 | 10 | 0 | 0 |  | 0 | 30 |  |  |  | 8
2026-01-26 | 56109 |  | 56109 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-29 | Z | 2026-01-26 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2026-01-29 | 56110 |  | 56110 | A | done | 3 | S |  | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-23 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 13
2026-01-29 | 56111 |  | 56111 | A | done | 3 | S |  | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-23 | 30 | 20 | 0 |  | 0 | 60 |  |  |  | 13
2026-01-27 | 56112 |  | 56112 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2026-01-29 | Z | 2026-01-23 | 10 | 0 | 0 |  | 10 | 20 |  |  |  | 6
2026-01-28 | 56113 |  | 56113 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2026-01-29 | Z | 2026-01-23 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 6
2026-01-27 | 56114 |  | 56114 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-29 | Z | 2026-01-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2026-01-29 | 56115 |  | 56115 | A | done | 3 | S |  | DOC JDC 6240023 | flex | 2026-02-05 | Z | 2026-01-28 | 10 | 0 | 0 |  | 0 | 70 |  |  |  | 8
2026-01-29 | 56116 |  | 56116 | A | done | 8 |  |  | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-28 | 0 | 0 | 170 |  | 0 | 200 |  |  |  | 8
2026-01-30 | 56117 |  | 56117 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-02 | Z | 2026-01-30 | 30 | 0 | 0 |  | 0 | 40 |  | Zone 3 |  | 3
2026-01-30 | 717 | bth | Z2-EA 48 | A | done | 9 | S/M |  | DOC JDC 6240023 |  | 2026-01-29 | Z | 2025-07-30 | 140 | 20 | 0 |  | 0 | 220 |  |  |  | 183 | 2025-09-04 | 2025-11-20
2026-01-29 | 74367 |  | 74367-69 | A | done | 8 | S/M |  | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-21 | 80 | 0 | 0 |  | 0 | 200 |  |  |  | 15
2026-01-26 | 74370 |  | 74370 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2026-01-29 | Z | 2026-01-23 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2026-01-29 | 74371 |  | 74371 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-23 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 13
2026-01-28 | 756 | w | Z1 KITCHEN EA 1 | A | DONE | 17 | M | bi | DOC JDC 6240023 |  | 2026-01-29 | Z | 2025-08-05 | 130 | 0 | 0 |  | 0 | 420 |  |  |  | 177
2026-01-30 | 97732a |  | 97732a | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-03 | Z | 2026-01-29 | 10 | 0 | 0 |  | 10 | 30 |  |  |  | 5
2026-01-26 | 98140 |  | 98140 | A | DONE | 2 | S |  | EXACT TL3 8240019 |  | 2026-01-28 | Z | 2026-01-21 | 10 | 0 | 0 |  | 0 | 30 |  |  |  | 7
2026-01-27 | 106943 |  | 106943 | A | DONE | 2 | S |  | GRANT 6250021 | Pipe shop | 2026-02-09 | Z | 2026-01-23 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 17
2026-01-27 | 74775 | bth | 74775 | A | DONE | 5 | S/M | neal | GREAT WOLF 4250055 |  | 2026-01-29 | Z | 2026-01-23 | 30 | 100 | 0 |  | 10 | 120 |  |  |  | 6
2026-01-28 | 75901 |  | 75901 | A | DONE | 2 | S | alum | KALAHRI 4250012 |  | 2026-01-28 | Z | 2026-01-28 | 50 | 0 | 0 |  | 0 | 40 |  |  |  | 0
2026-01-30 | 69577 | bth | 69577-79 | A | done | 37 | M/L | pcd | LABCORP 2250055 |  | 2026-02-05 | Z | 2026-01-23 | 270 | 530 | 0 |  | 0 | 920 |  | 1st floor |  | 13
2026-01-28 | 69580 | bth | 69580 | A | DONE | 15 | M | pcd | LAPCORP 2250055 |  | 2026-02-05 | Z | 2026-01-23 | 130 | 200 | 0 |  | 0 | 370 |  |  |  | 13
2026-01-28 | 69581 |  | 69581 | A | DONE | 2 | S |  | LAPCORP 2250055 |  | 2026-02-05 | Z | 2026-01-23 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 13
2026-01-29 | 64725 |  | 64725 | A | done | 2 | S | neal | MAUSTON R 6250019 |  | 2026-02-06 | Z | 2026-01-23 | 30 | 0 | 0 |  | 0 | 50 |  | Misc level 1 |  | 14
2026-01-29 | 83765 |  | 83765 | A | done | 2 | S |  | MONONA GROVE 10067311 |  | 2026-02-03 | Z | 2026-01-29 | 10 | 0 | 0 |  | 0 | 40 |  | Level 1 |  | 5
2026-01-27 | 74357 | sp | 74357 | A | DONE | 2 | S | neal | MONROE 6240018 |  | 2026-02-04 | Z | 2026-01-26 | 10 | 20 | 0 |  | 0 | 40 |  | AHU flashings |  | 9
2026-01-29 | 74358 |  | 74358-59 | A | done | 11 | S/M | neal | MONROE 6240018 | 1" liner | 2026-02-04 | Z | 2026-01-26 | 110 | 0 | 0 |  | 90 | 270 |  |  |  | 9 | 2026-02-03
2026-01-26 | 83634 |  | 83634 | A | DONE | 2 | S |  | MONROE 6240018 |  | 2026-01-28 | Z | 2026-01-22 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 6 | 2026-02-03
2026-01-29 | 83634r |  | 83634r | A | done | 2 | S |  | MONROE 6240018 |  | 2026-02-04 | Z | 2026-01-28 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 7 | 2026-02-03
2026-01-29 | 83635 |  | 83635 | A | done | 5 | S/M |  | MONROE 6240018 | 1" liner | 2026-02-04 | Z | 2026-01-23 | 80 | 0 | 0 |  | 70 | 110 |  |  |  | 12 | 2026-02-03
2026-01-27 | 83679 |  | 83679-80 | A | DONE | 13 | S/M | neal | MONROE 6240018 |  | 2026-02-04 | Z | 2026-01-23 | 150 | 0 | 0 |  | 0 | 320 |  |  |  | 12 | 2026-02-03
2026-01-26 | 83742 | bth | 83742 | A | DONE | 9 | S/M | neal | MONROE 6240018 |  | 2026-01-28 | Z | 2026-01-16 | 110 | 80 | 0 |  | 0 | 210 |  |  |  | 12 | 2026-02-03
2026-01-27 | 83747 | bth | 83747-49 | A | DONE | 16 | M |  | MONROE 6240018 |  | 2026-01-28 | Z | 2026-01-23 | 90 | 130 | 0 |  | 0 | 400 |  |  |  | 5 | 2026-02-03
2026-01-29 | 83750 | bth | 83750 | A | done | 3 | S | neal | MONROE 6240018 |  | 2026-02-04 | Z | 2026-01-26 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 9 | 2026-02-03
2026-01-26 | 74773 |  | 74773 | A | DONE | 7 | S/M |  | NY LIFE 4260001 |  | 2026-01-26 | Z | 2026-01-23 | 100 | 0 | 0 |  | 0 | 160 |  |  |  | 3 | 2026-02-03
2026-01-26 | 74774 |  | 74774 | A | DONE | 2 | S |  | NY LIFE 4260001 |  | 2026-01-27 | Z | 2026-01-26 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 1 | 2026-02-03
2026-01-27 | 76501 |  | 76501 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-02-04 | Z | 2026-01-26 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 9 | 2026-02-03
2026-01-27 | 76502 |  | 76502 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-02-04 | Z | 2026-01-26 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 9 | 2026-02-03
2026-01-28 | 76503 | sp | 76503 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-02-04 | Z | 2026-01-23 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 12 | 2026-02-03
2026-01-28 | 76504 |  | 76504 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2026-02-04 | Z | 2026-01-23 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 12 | 2026-02-03
2026-01-26 | 3820 | bth | LG-SAMP-02 | A | DONE | 58 | L |  | PROMEGA BTC 6250020 |  | 2026-01-28 | Z | 2026-01-13 | 530 | 50 | 220 |  | 0 | 1430 |  |  |  | 15 | 2026-02-03
2026-01-29 | 3822 |  | LG-RA-03 | A | done | 44 | M/L |  | PROMEGA BTC 6250020 |  | 2026-02-03 | Z | 2026-01-13 | 410 | 0 | 160 |  | 0 | 1090 |  |  |  | 21 | 2026-02-03
2026-01-28 | 3823 |  | LG-RA-05 | A | DONE | 30 | M |  | PROMEGA BTC 6250020 |  | 2026-02-03 | Z | 2026-01-13 | 160 | 0 | 290 |  | 0 | 730 |  |  |  | 21 | 2026-02-03
2026-01-30 | 3825 |  | LG-RA-02 | A | done | 28 | M |  | PROMEGA BTC 6250020 |  | 2026-02-11 | Z | 2026-01-13 | 410 | 0 | 90 |  | 0 | 700 |  |  |  | 29
2026-01-28 | 3834 | bth | LG-SALP-1 | A | DONE | 22 | M |  | PROMEGA BTC 6250020 |  | 2026-02-05 | Z | 2026-01-22 | 150 | 90 | 190 |  | 0 | 550 |  |  |  | 14 | 2026-02-03
2026-01-30 | 81875 |  | 81875 | A | done | 8 | S/M |  | PROMEGA BTC 6250020 |  | 2026-02-05 | Z | 2026-01-29 | 80 | 0 | 0 |  | 0 | 190 |  | Supply |  | 7
2026-01-26 | 76419 |  | 76419 | A | DONE | 2 | S |  | QBE 4250054 | 1" liner | 2026-01-28 | Z | 2026-01-26 | 40 | 0 | 0 |  | 40 | 50 |  |  |  | 2 | 2026-02-03
2026-01-30 | 76421 |  | 76421 | A | done | 2 | S |  | QBE 4250054 | 1" liner | 2026-02-04 | Z | 2026-01-30 | 20 | 0 | 0 |  | 20 | 20 |  | Transfer |  | 5
2026-01-27 | 76843 |  | 76843 | A | DONE | 2 | S |  | SBC 6230023 |  | 2026-02-06 | Z | 2026-01-26 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 11 | 2026-02-03
2026-01-29 | 83764 |  | 83764 | A | DONE | 2 | S | ss | SERVICE 1006214 |  | 2026-01-29 | Z | 2026-01-29 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 0 | 2026-02-03
2026-01-27 | 1073 |  | L2-EA-01 | A | DONE | 8 | S/M |  | SHRINE 6240034 | neal | 2026-02-02 | Z | 2026-01-05 | 130 | 0 | 0 |  | 0 | 190 |  |  |  | 28 | 2026-02-03
2026-01-27 | 1074 |  | L2-EA-02 | A | DONE | 6 | S/M |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 110 | 0 | 0 |  | 0 | 150 |  |  |  | 28 | 2026-02-03
2026-01-27 | 1075 |  | L2-EA-03 | A | DONE | 4 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 80 | 0 | 0 |  | 0 | 100 |  |  |  | 28 | 2026-02-03
2026-01-27 | 1078 |  | L2-EA-06 | A | DONE | 5 | S/M |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 80 | 0 | 0 |  | 0 | 120 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1079 |  | L2-EA-07 | A | DONE | 4 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 70 | 0 | 0 |  | 0 | 90 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1080 |  | L2-EA-08 | A | DONE | 4 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1081 |  | L2-EA-09 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1082 |  | L2-EA-11 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1084 |  | L2-EA-13 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1085 |  | L2-EA-14 | A | DONE | 3 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 50 | 0 | 0 |  | 0 | 70 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1086 |  | L2-EA-15 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1087 |  | L2-EA-16 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1088 |  | L2-EA-17 | A | DONE | 3 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1089 |  | L2-EA-18 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1091 |  | L2-RA-01 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-05 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 28 | 2026-02-10
2026-01-27 | 1092 |  | L2-SAMP-01 | A | DONE | 3 | S |  | SHRINE 6240034 | neal | 2026-02-02 | Z | 2026-01-06 | 50 | 0 | 0 |  | 0 | 70 |  |  |  | 27 | 2026-02-10
2026-01-26 | 1093 |  | L2-SAMP-02 | A | DONE | 2 | S |  | SHRINE 6240034 | neal | 2026-02-02 | Z | 2026-01-06 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 27 | 2026-02-10
2026-01-27 | 1095 |  | L2-SAMP-04 | A | DONE | 4 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-06 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 27 | 2026-02-10
2026-01-27 | 1097 |  | L2-SAMP-06 | A | DONE | 3 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-06 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 27 | 2026-02-10
2026-01-26 | 1099 |  | L2-SAMP-08 | A | DONE | 6 | S/M |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-06 | 110 | 0 | 0 |  | 0 | 140 |  |  |  | 27 | 2026-02-10
2026-01-27 | 1103 |  | L2-SAMP-13 | A | DONE | 4 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-06 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 27 | 2026-02-10
2026-01-26 | 1106 |  | L2-SAMP-16 | A | DONE | 4 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-06 | 80 | 0 | 0 |  | 0 | 100 |  |  |  | 27 | 2026-02-10
2026-01-27 | 1107 |  | L2-SAMP-17 | A | DONE | 4 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-06 | 70 | 0 | 0 |  | 0 | 90 |  |  |  | 27 | 2026-02-10
2026-01-26 | 1109 |  | L2-SAMP-19 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-06 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 27 | 2026-02-10
2026-01-28 | 1114 |  | L1-SAMP-01 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-23 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 10 | 2026-02-10
2026-01-26 | 85453 |  | 85453 | A | DONE | 5 | S/M |  | SHRINE 6240034 |  | 2026-02-02 | Z | 2026-01-16 | 80 | 0 | 0 |  | 10 | 110 |  |  |  | 17 | 2026-02-10
2026-01-29 | 85456 |  | 85456 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-09 | Z | 2026-01-23 | 20 | 0 | 0 |  | 10 | 30 |  |  |  | 17 | 2026-02-10
2026-01-29 | 85457 |  | 85457 | A | done | 5 | S/M |  | SHRINE 6240034 |  | 2026-02-03 | Z | 2026-01-29 | 80 | 0 | 0 |  | 0 | 120 |  |  |  | 5 | 2026-02-10
2026-01-30 | 85458 |  | 85458 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-09 | Z | 2026-01-30 | 10 | 0 | 0 |  | 10 | 20 |  | VAV 126 |  | 10
2026-01-27 | 85455 |  | 85455 | A | DONE | 2 | S |  | SHRINE 6240037 |  | 2026-02-02 | Z | 2026-01-21 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 12 | 2026-02-10
2026-01-28 | 77208 |  | 77208 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2026-02-02 | Z | 2026-01-23 | 10 | 0 | 0 |  | 0 | 30 |  |  |  | 10 | 2026-02-10
2026-01-29 | 77107 |  | 77107 | A | done | 2 | S |  | TOMAH HEALTH 6250006 |  | 2026-02-03 | Z | 2026-01-28 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 6 | 2026-02-10
2026-01-29 | 77108 | sp | 77108 | A | done | 2 | S |  | TOMAH HEALTH 6250006 |  | 2026-02-03 | Z | 2026-01-28 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 6 | 2026-02-10
2026-01-29 | 83766 |  | 83766 | A | done | 2 | S |  | TOMAH HEALTH 6250006 |  | 2026-02-03 | Z | 2026-01-29 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 5 | 2026-02-10
2026-01-29 | 53963 | bth | 53963 | A | done | 3 | S |  | UW LEVY HALL 6230028 |  | 2026-02-03 | Z | 2026-01-23 | 50 | 10 | 0 |  | 30 | 70 |  |  |  | 11 | 2026-02-10
2026-01-28 | 78326 |  | 78326 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | 1" liner | 2026-02-03 | Z | 2026-01-23 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 11 | 2026-02-10
2026-01-27 | 78327 |  | 78327 | A | DONE | 3 | S |  | UW LEVY HALL 6230028 |  | 2026-02-03 | Z | 2026-01-26 | 20 | 0 | 0 |  | 0 | 70 |  |  |  | 8 | 2026-02-10
2026-01-30 | 96965 |  | 96965 | A | done | 3 | S |  | UW LEVY HALL 8230028 |  | 2026-02-10 | Z | 2026-01-30 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 11
2026-01-30 | 4001 | bth | L4-VAV-1-4-20 | A | done | 7 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-02-06 | Z | 2025-11-24 | 50 | 90 | 0 |  | 30 | 170 |  |  |  | 74 | 2026-03-01
2026-01-29 | 4003 | bth | L4-VAV-1-4-22 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-06 | Z | 2025-11-24 | 20 | 10 | 0 |  | 0 | 40 |  |  |  | 74 | 2026-02-10
2026-01-30 | 4004 | bth | L4-VAV-1-4-23 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-02-06 | Z | 2025-11-24 | 30 | 10 | 0 |  | 20 | 50 |  |  |  | 74 | 2026-03-01
2026-01-30 | 4005 | bth | L4-VAV-1-4-24 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-06 | Z | 2025-11-24 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 74 | 2026-03-01
2026-01-30 | 4006 | bth | L4-VAV-1-4-25 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-06 | Z | 2025-11-24 | 20 | 10 | 0 |  | 0 | 40 |  |  |  | 74 | 2026-03-01
2026-01-30 | 4007 | bth | L4-VAV-1-4-26 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-02-06 | Z | 2025-11-24 | 30 | 10 | 0 |  | 30 | 50 |  |  |  | 74 | 2026-03-01
2026-01-30 | 4008 | bth | L4-VAV-1-4-27 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-02-06 | Z | 2025-11-24 | 30 | 10 | 0 |  | 10 | 50 |  |  |  | 74 | 2026-03-01
2026-01-30 | 4009 | bth | L4-VAV-1-4-28 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-06 | Z | 2025-11-24 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 74 | 2026-03-01
2026-01-30 | 4010 | bth | L4-VAV-1-4-29 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-06 | Z | 2025-11-24 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 74 | 2026-03-01
2026-01-30 | 4011 | bth | L4-VAV-1-4-30 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-06 | Z | 2025-11-24 | 20 | 10 | 0 |  | 0 | 40 |  |  |  | 74 | 2026-03-01
2026-01-30 | 4012 | bth | L4-VAV-1-4-31_1 | A | done | 9 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-02-06 | Z | 2025-11-24 | 180 | 10 | 0 |  | 40 | 220 |  |  |  | 74 | 2026-03-01
2026-01-29 | 4013 |  | L4-VAV-1-4-31_2 | A | done | 6 | S/M |  | UW STOUT 6250008 |  | 2026-02-06 | Z | 2025-11-24 | 70 | 0 | 30 |  | 0 | 130 |  |  |  | 74
2026-01-30 | 4014 |  | L4-CAV-4-1-1 | A | done | 9 | S/M |  | UW STOUT 6250008 | VD | 2026-02-09 | Z | 2025-11-25 | 140 | 10 | 0 |  | 30 | 210 |  |  |  | 76
2026-01-30 | 4018 |  | L4-VAV-1-4-2 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-02-09 | Z | 2025-11-25 | 30 | 60 | 40 |  | 50 | 160 |  |  |  | 76
2026-01-29 | 4019 | bth | L4-VAV-1-4-3 | A | done | 4 | S |  | UW STOUT 6250008 | 1" liner, VD | 2026-02-03 | Z | 2025-11-26 | 40 | 50 | 0 |  | 20 | 100 |  |  |  | 69
2026-01-29 | 4020 | bth | L4-VAV-1-4-4 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-03 | Z | 2025-11-26 | 40 | 10 | 0 |  | 0 | 50 |  | Pipe shop |  | 69
2026-01-29 | 4021 | bth | L4-VAV-1-4-5 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-03 | Z | 2025-11-26 | 40 | 10 | 0 |  | 0 | 50 |  |  |  | 69
2026-01-29 | 4022 | bth | L4-VAV-1-4-6 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-03 | Z | 2025-11-26 | 40 | 10 | 0 |  | 0 | 50 |  |  |  | 69
2026-01-29 | 4023 | bth | L4-VAV-1-4-8 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-03 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 69
2026-01-29 | 4024 | bth | L4-VAV-1-4-9 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-03 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 69 | 2025-10-23 | 2025-11-20
2026-01-29 | 4025 | bth | L4-VAV-1-4-10 | A | done | 2 | S |  | UW STOUT 6250008 | VD | 2026-02-03 | Z | 2025-11-26 | 30 | 10 | 0 |  | 0 | 40 |  | Dust collector hangers |  | 69
2026-01-29 | 4026 | bth | L4-VAV-1-4-11 | A | done | 3 | S |  | UW STOUT 6250008 | VD | 2026-02-03 | Z | 2025-11-26 | 30 | 30 | 0 |  | 0 | 60 |  | Misc |  | 69
2026-01-29 | 4027 | bth | L4-VAV-2-4-1 | A | done | 7 | S/M |  | UW STOUT 6250008 | 1" liner, VD | 2026-02-03 | Z | 2025-11-26 | 70 | 60 | 30 |  | 30 | 160 |  |  |  | 69
2026-01-29 | 4028 | bth | L4-VAV-2-4-2 | A | done | 8 | S/M |  | UW STOUT 6250008 | 1" liner, VD | 2026-02-03 | Z | 2025-11-26 | 80 | 60 | 30 |  | 30 | 190 |  | SA 1 |  | 69
2026-01-29 | 4029 | bth | L4-VAV-2-4-3 | A | done | 6 | S/M |  | UW STOUT 6250008 | 1" liner, VD | 2026-02-03 | Z | 2025-11-26 | 70 | 30 | 30 |  | 30 | 130 |  |  |  | 69 | 2026-01-27
2026-01-29 | 4030 | bth | L4-VAV-2-4-9 | A | done | 3 | S |  | UW STOUT 6250008 | 1" liner, VD | 2026-02-03 | Z | 2025-11-26 | 40 | 20 | 0 |  | 30 | 70 |  |  |  | 69 | 2026-01-27
2026-01-29 | 4031 | bth | L4-VAV-2-4-10 | A | done | 3 | S |  | UW STOUT 6250008 | 1" liner | 2026-02-03 | Z | 2025-11-26 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 69 | 2026-01-27
2026-01-26 | 4135 |  | L4-TA 141 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-17 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 44 | 2026-01-27
2026-01-26 | 4151 |  | L4-TA 2 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 70 | 0 | 0 |  | 40 | 80 |  |  |  | 43 | 2026-01-27
2026-01-26 | 4152 |  | L4-TA 3 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 43 | 2026-01-27
2026-01-26 | 4153 |  | L4-TA 4 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 43
2026-01-26 | 4158 |  | L4-TA 9 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 50 | 0 | 0 |  | 50 | 80 |  |  |  | 43 | 2026-02-10
2026-01-26 | 4172 |  | L4-TA 23 | A | DONE | 14 | S/M |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-01-30 | Z | 2025-12-18 | 180 | 0 | 60 |  | 170 | 350 |  |  |  | 43 | 2026-02-10
2026-01-26 | 4173 |  | L4-TA 24 | A | DONE | 9 | S/M |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 150 | 0 | 0 |  | 80 | 210 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4174 |  | L4-TA 25 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 70 | 0 | 0 |  | 40 | 80 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4175 |  | L4-TA 26 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4180 |  | L4-TA 31 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 50 | 0 | 0 |  | 50 | 70 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4182 |  | L4-TA 33 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 40 | 0 | 30 |  | 50 | 80 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4184 |  | L4-TA 35 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 40 | 0 | 0 |  | 20 | 40 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4185 |  | L4-TA 36 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4187 |  | L4-TA 38 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4189 |  | L4-TA 40 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4193 |  | L4-TA 44 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 50 | 0 | 0 |  | 30 | 50 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4194 |  | L4-TA 45 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 42 | 2026-02-10
2026-01-26 | 4195 |  | L4-TA 46 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 40 | 0 | 0 |  | 30 | 50 |  | EF 48 |  | 42
2026-01-30 | 4196 |  | L4-TA 47 | A | done | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 42 | 2026-02-03
2026-01-26 | 4202 |  | L4-TA 53 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 50 | 0 | 0 |  | 40 | 60 |  | EF 48 |  | 42
2026-01-26 | 4203 |  | L4-TA 54 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 60 | 0 | 0 |  | 30 | 70 |  | 1st floor |  | 42
2026-01-26 | 4206 |  | L4-TA 57 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 60 | 0 | 0 |  | 40 | 70 |  | 1st floor |  | 42
2026-01-26 | 4207 |  | L4-TA 58 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 42
2026-01-26 | 4208 |  | L4-TA 59 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 42
2026-01-26 | 4211 |  | L4-TA 137 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-01-30 | Z | 2025-12-19 | 70 | 0 | 0 |  | 60 | 90 |  | Shelfs |  | 42
2026-01-27 | 4212 |  | L4-TA 60 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 30 | 70 |  | Exhaust |  | 43
2026-01-28 | 4213 |  | L4-TA 61 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 70 |  | FEC change |  | 43
2026-01-28 | 4214 |  | L4-TA 62 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 70 |  | MAU 1/2 CB |  | 43
2026-01-27 | 4215 |  | L4-TA 63 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4216 |  | L4-TA 64 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-27 | 4217 |  | L4-TA 65 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | Area A south |  | 43
2026-01-27 | 4218 |  | L4-TA 66 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 43
2026-01-30 | 4219 |  | L4-TA 67 | A | done | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4220 |  | L4-TA 68 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-27 | 4221 |  | L4-TA 69 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 43
2026-01-27 | 4222 |  | L4-TA 70 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-01-27
2026-01-27 | 4223 |  | L4-TA 71 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | L3 Transfer |  | 43
2026-01-27 | 4224 |  | L4-TA 72 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4225 |  | L4-TA 73 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-29 | 4226 |  | L4-TA 74 | A | done | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4227 |  | L4-TA 75 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4228 |  | L4-TA 76 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4229 |  | L4-TA 77 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4230 |  | L4-TA 78 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 50 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4231 |  | L4-TA 79 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4232 |  | L4-TA 80 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4233 |  | L4-TA 81 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4234 |  | L4-TA 82 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4235 |  | L4-TA 83 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4236 |  | L4-TA 84 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4237 |  | L4-TA 85 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4238 |  | L4-TA 86 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4239 |  | L4-TA 87 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 70 | 0 | 0 |  | 60 | 90 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4240 |  | L4-TA 88 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 40 | 50 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4241 |  | L4-TA 89 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4242 |  | L4-TA 90 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4243 |  | L4-TA 91 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4244 |  | L4-TA 92 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4245 |  | L4-TA 93 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-27 | 4246 |  | L4-TA 94 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 43
2026-01-27 | 4247 |  | L4-TA 95 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-27 | 4248 |  | L4-TA 96 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-28 | 4249 |  | L4-TA 97 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 30 | 50 |  | V 2 SA |  | 43
2026-01-27 | 4250 |  | L4-TA 98 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | LL IT TA |  | 43
2026-01-27 | 4251 |  | L4-TA 99 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 43
2026-01-27 | 4252 |  | L4-TA 100 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-27 | 4253 |  | L4-TA 101 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 43
2026-01-27 | 4254 |  | L4-TA 102 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-28 | 4255 |  | L4-TA 103 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-27 | 4256 |  | L4-TA 104 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | FD Add |  | 43
2026-01-27 | 4257 |  | L4-TA 105 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | FD Add |  | 43
2026-01-27 | 4258 |  | L4-TA 106 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  | Room 1204 |  | 43
2026-01-30 | 4259 |  | L4-TA 107 | A | done | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4260 |  | L4-TA 108 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4261 |  | L4-TA 109 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-10
2026-01-28 | 4262 |  | L4-TA 110 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-17
2026-01-28 | 4263 |  | L4-TA 111 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-17
2026-01-28 | 4264 |  | L4-TA 112 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 43 | 2026-02-17
2026-01-28 | 4265 |  | L4-TA 113 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-17
2026-01-28 | 4266 |  | L4-TA 114 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43 | 2026-02-17
2026-01-28 | 4267 |  | L4-TA 115 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 43 | 2026-02-17
2026-01-28 | 4268 |  | L4-TA 116 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 30 |  | Spray space EA |  | 43
2026-01-28 | 4269 |  | L4-TA 117 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  | A1 bathroom transfers |  | 43
2026-01-28 | 4270 |  | L4-TA 118 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-28 | 4271 |  | L4-TA 119 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | Weld exhaust hangers |  | 43
2026-01-28 | 4272 |  | L4-TA 120 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | CB 140 |  | 43
2026-01-27 | 4273 |  | L4-TA 121 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  | REL Air new taps |  | 43
2026-01-28 | 4274 |  | L4-TA 122 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 30 | 0 | 0 |  | 20 | 40 |  | Roof canvas |  | 43
2026-01-28 | 4275 |  | L4-TA 123 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | SEC Grilles |  | 43
2026-01-28 | 4276 |  | L4-TA 124 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  | HP SA |  | 43
2026-01-28 | 4277 |  | L4-TA 125 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 40 | 60 |  | B-RAMP-02 |  | 43
2026-01-28 | 4278 |  | L4-TA 126 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 43
2026-01-28 | 4279 |  | L4-TA 127 | A | DONE | 2 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 20 | 0 | 0 |  | 20 | 30 |  | Grease duct patch |  | 43
2026-01-28 | 4280 |  | L4-TA 128 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 43
2026-01-28 | 4281 |  | L4-TA 129 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 43
2026-01-29 | 4282 |  | L4-TA 130 | A | done | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 80 |  | Angles |  | 43
2026-01-28 | 4283 |  | L4-TA 131 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 43 | 2026-02-17
2026-01-28 | 4284 |  | L4-TA 132 | A | DONE | 4 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 50 | 0 | 0 |  | 40 | 80 |  | Metals DC |  | 43
2026-01-28 | 4285 |  | L4-TA 133 | A | DONE | 3 | S |  | UW STOUT 6250008 | 1' liner, birdscreen | 2026-02-03 | Z | 2025-12-22 | 40 | 0 | 0 |  | 40 | 70 |  | Mezz tie in |  | 43
2026-01-28 | 4286 | w | L5-SHAFT CEA D 1 | A | DONE | 3 | S | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 13
2026-01-27 | 4287 | w | L5-SHAFT CEA E 1 | A | DONE | 5 | S/M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 30 | 0 | 0 |  | 0 | 120 |  | Service |  | 13
2026-01-27 | 4288 | w | L5-SHAFT CEA E 2 | A | DONE | 3 | S | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 30 | 0 | 0 |  | 0 | 70 |  |  |  | 13
2026-01-29 | 4298 | w | L4-SHAFT CEA C 1 | A | done | 9 | S/M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 60 | 0 | 0 |  | 0 | 220 |  |  |  | 13
2026-01-28 | 4299 | w | L4-SHAFT CEA D 1 | A | DONE | 6 | S/M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 60 | 0 | 0 |  | 0 | 140 |  |  |  | 13 | 2026-02-17 | 2026-02-17
2026-01-30 | 4300 | w | L4-SHAFT CEA E 1 | A | done | 15 | M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 90 | 0 | 0 |  | 0 | 360 |  |  |  | 13
2026-01-30 | 4301 | w | L4-SHAFT CEA E 2 | A | done | 8 | S/M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 50 | 0 | 0 |  | 0 | 180 |  |  |  | 13
2026-01-28 | 4313 |  | L4-SHAFT SAMP F 1 | A | DONE | 15 | M |  | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 0 | 160 | 0 |  | 0 | 360 |  |  |  | 13 | 2026-02-17
2026-01-29 | 4316 | w | L3-SHAFT CEA C 1 | A | DONE | 9 | S/M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 70 | 0 | 0 |  | 0 | 220 |  |  |  | 13 | 2026-02-17
2026-01-28 | 4317 | w | L3-SHAFT CEA D 1 | A | DONE | 6 | S/M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 50 | 0 | 0 |  | 0 | 150 |  |  |  | 13 | 2026-02-17
2026-01-29 | 4319 | w | L3-SHAFT CEA E 2 | A | DONE | 12 | S/M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 70 | 0 | 0 |  | 0 | 290 |  |  |  | 13 | 2026-02-17
2026-01-28 | 83763 |  | 83763 | A | DONE | 2 | S |  | VA CLINIC 4250052 |  | 2026-01-28 | Z | 2026-01-28 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 0 | 2026-02-17
2026-01-29 | 75419 |  | 75419 | A | done | 2 | S | bi | WAUNAKEE 6230013 |  | 2026-02-06 | Z | 2026-01-29 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 8
2026-01-30 | 83433 | w | 83433 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-02-05 | Z | 2026-01-30 | 10 | 0 | 0 |  | 0 | 20 |  | Dust collector |  | 6
2026-01-30 | 83434 |  | 83434 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-02-05 | Z | 2026-01-30 | 10 | 0 | 0 |  | 0 | 20 |  | Tech Ed |  | 6
2026-01-28 | 83435 |  | 83435 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2026-01-30 | Z | 2026-01-28 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 2 | 2026-03-01
2026-01-26 | 95840 |  | 95840 | A | DONE | 24 | M |  | WHC 8250008 | pipe shop | 2026-02-02 | Z | 2026-01-26 | 180 | 0 | 0 |  | 0 | 590 |  |  |  | 7 | 2026-03-01
[6 empty] | 1298 | [13 empty] | 29430 | [5 empty] | 23% short
[9 empty] | WEEK OF 2-2-2026 | [16 empty] | % Under 14
2026-02-03 | 82778 |  | 82778,80,85 | A | done | 18 | M |  | ANTIGO 6250017 | 2" liner | 2026-02-09 | Z | 2026-01-23 | 250 | 0 | 110 |  | 250 | 450 |  | V-3,V-6,TA |  | 17 |  |  | 67.23%
2026-02-03 | 82779 | sp | 82779 | A | done | 9 | S/M |  | ANTIGO 6250017 |  | 2026-02-09 | Z | 2026-01-23 | 50 | 170 | 0 |  | 0 | 210 |  | V-3,V-4 |  | 17
2026-02-03 | 82787 | bth | 82787 | A | done | 4 | S |  | ANTIGO 6250017 |  | 2026-02-09 | Z | 2026-01-30 | 50 | 30 | 0 |  | 30 | 80 |  |  |  | 10
2026-02-02 | 82788 | sp | 82788 | A | done | 5 | S/M |  | ANTIGO 6250017 |  | 2026-02-09 | Z | 2026-02-03 | 10 | 110 | 0 |  | 0 | 110 |  | V1 SA |  | 6
2026-02-05 | 82790 |  | 82790 | A | done | 2 | S |  | ANTIGO 6250017 | 1" liner | 2026-02-09 | Z | 2026-02-04 | 10 | 0 | 0 |  | 10 | 20 |  | Commons TA |  | 5
2026-02-02 | 10004 |  | 10004 | A | done | 54 | L |  | BROOM ST 6240033 | paint black | 2026-02-10 | Z | 2026-01-19 | 900 | 0 | 0 |  | 740 | 1350 |  | Grille boxes part 3 |  | 22
2026-02-02 | 1599 | bth | UNIT 406 M5.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 60 | 70 | 0 |  | 0 | 150 |  |  |  | 14
2026-02-03 | 1603 | bth | UNIT 410 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 60 | 70 | 0 |  | 0 | 150 |  |  |  | 14
2026-02-02 | 1605 | bth | UNIT 412 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-03 | Z | 2026-01-20 | 60 | 70 | 0 |  | 0 | 150 |  |  |  | 14
2026-02-03 | 1640 | bth | L1-SALP-01 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 40 | 140 | 0 |  | 0 | 200 |  |  |  | 16
2026-02-03 | 1641 | bth | L1-SALP-02 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 20 | 80 | 0 |  | 0 | 110 |  |  |  | 16
2026-02-02 | 1642 | bth | L1-SALP-03 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 30 | 130 | 0 |  | 0 | 190 |  |  |  | 16
2026-02-02 | 1643 | bth | L1-SALP-04 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 50 | 100 | 0 |  | 0 | 140 |  |  |  | 16
2026-02-02 | 1644 | bth | L1-SALP-05 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 16
2026-02-03 | 1645 | bth | L1-SALP-06 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 40 | 180 | 0 |  | 0 | 240 |  |  |  | 16
2026-02-02 | 1646 | bth | L1-SALP-07 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 70 | 190 | 0 |  | 0 | 240 |  |  |  | 16
2026-02-03 | 1647 | bth | L1-SALP-08 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 30 | 140 | 0 |  | 0 | 200 |  |  |  | 16
2026-02-02 | 1648 | bth | L1-SALP-09 | A | done | 14 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 50 | 240 | 0 |  | 0 | 330 |  |  |  | 16
2026-02-02 | 1649 | bth | L1-SALP-10 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 30 | 140 | 0 |  | 0 | 210 |  |  |  | 16
2026-02-02 | 1650 | bth | L1-SALP-11 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 50 | 110 | 0 |  | 0 | 140 |  |  |  | 16
2026-02-02 | 1651 | bth | L1-SALP-12 | A | done | 7 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 30 | 100 | 0 |  | 0 | 160 |  |  |  | 16
2026-02-02 | 1652 | bth | L1-SALP-13 | A | done | 5 | S/M | alum | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 90 | 110 | 0 |  | 0 | 120 |  |  |  | 16
2026-02-03 | 1653 | bth | L1-SALP-14 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 30 | 50 | 0 |  | 0 | 90 |  |  |  | 16
2026-02-03 | 1654 | bth | L1-SALP-15 | A | done | 15 | M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 50 | 280 | 0 |  | 0 | 370 |  |  |  | 16
2026-02-03 | 1655 | bth | L1-SALP-16 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 30 | 220 | 0 |  | 0 | 290 |  |  |  | 16
2026-02-03 | 1656 | bth | L1-SALP-17 | A | done | 14 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 40 | 240 | 0 |  | 0 | 330 |  |  |  | 16
2026-02-02 | 1657 | bth | L1-SALP-18 | A | done | 13 | S/M |  | BROOM ST 6240033 |  | 2026-02-04 | Z | 2026-01-19 | 60 | 220 | 0 |  | 0 | 310 |  |  |  | 16
2026-02-03 | 1659 |  | UNIT 844 M4.103 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 80 | 0 | 40 |  | 0 | 110 |  |  |  | 13
2026-02-03 | 1660 |  | UNIT 845 M4.104 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 60 | 0 | 30 |  | 0 | 90 |  |  |  | 13
2026-02-03 | 1661 |  | UNIT 847 M4.105 | A | done | 13 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 160 | 0 | 170 |  | 0 | 310 |  |  |  | 13
2026-02-03 | 1662 |  | UNIT 849 M4.106 | A | done | 13 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 180 | 0 | 110 |  | 0 | 320 |  |  |  | 13
2026-02-03 | 1663 |  | UNIT 851 M4.107 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 50 | 0 | 60 |  | 0 | 110 |  |  |  | 13
2026-02-02 | 1664 |  | UNIT 853 M4.108 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 210 | 0 | 110 |  | 0 | 290 |  |  |  | 13
2026-02-02 | 1665 |  | UNIT 854 M4.109 | A | done | 13 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 220 | 0 | 80 |  | 0 | 310 |  |  |  | 13
2026-02-05 | 1666 | bth | UNIT 855 M4.110 | A | done | 7 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 90 | 80 | 0 |  | 0 | 170 |  |  |  | 13
2026-02-02 | 1667 |  | UNIT 857 M4.111 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 176 | 0 | 100 |  | 0 | 280 |  |  |  | 13
2026-02-02 | 1668 |  | UNIT 858 M4.112 | A | done | 13 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 220 | 0 | 110 |  | 0 | 320 |  |  |  | 13
2026-02-03 | 1669 |  | UNIT 860 M4.113 | A | done | 14 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 190 | 0 | 110 |  | 0 | 330 |  |  |  | 13
2026-02-03 | 1670 |  | UNIT 862 M4.114 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-01-29 | 90 | 0 | 20 |  | 0 | 120 |  |  |  | 13
2026-02-05 | 79496 | sp | 79496 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-10 | Z | 2026-02-04 | 90 | 60 | 0 |  | 0 | 130 |  | East oval misc |  | 6
2026-02-02 | 1512 | bth | UNIT 431 M4.65 | A | done | 7 | S/M |  | BROOM ST. 6240033 |  | 2026-02-03 | Z | 2025-12-16 | 80 | 80 | 0 |  | 0 | 160 |  |  |  | 49 | 2026-01-27
2026-02-02 | 74217 | sp | 74217 | A | done | 2 | S |  | DELLSHIRE 6240017 |  | 2026-02-06 | Z | 2026-01-30 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 7
2026-02-02 | 4797 | sp | Z2-FE WELD 1 | A | done | 14 | S/M | neal | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-28 | 120 | 50 | 0 |  | 0 | 340 |  |  |  | 8
2026-02-02 | 4798 | sp | Z2-FE WELD 2 | A | done | 6 | S/M | neal | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-28 | 30 | 40 | 0 |  | 0 | 130 |  |  |  | 8
2026-02-02 | 4799 | sp | Z2-FE WELD 3 | A | done | 5 | S/M | neal | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-28 | 40 | 20 | 0 |  | 0 | 110 |  |  |  | 8
2026-02-02 | 4800 | sp | Z2-FE WELD 4 | A | done | 6 | S/M | neal | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-28 | 30 | 60 | 0 |  | 0 | 150 |  |  |  | 8
2026-02-04 | 4801 | sp | Z2-FE WELD 5 | A | done | 9 | S/M | neal | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-01-28 | 30 | 80 | 0 |  | 0 | 210 |  |  |  | 8
2026-02-04 | 56118 |  | 56118 | A | done | 2 | S |  | DOC JDC 6240023 | 1" liner | 2026-02-03 | Z | 2026-01-30 | 20 | 0 | 0 |  | 20 | 20 |  | Lined Duct |  | 4
2026-02-04 | 56119 |  | 56119 | A | done | 2 | S | neal | DOC JDC 6240023 | MOD | 2026-02-05 | Z | 2026-02-02 | 20 | 0 | 0 |  | 0 | 40 |  | Zone 1 |  | 3
2026-02-04 | 56120 |  | 56120 | A | done | 8 | S/M |  | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-02-02 | 80 | 0 | 0 |  | 0 | 180 |  | Firestop angles |  | 3
2026-02-04 | 56121 |  | 56121 | A | done | 3 | S |  | DOC JDC 6240023 | 1" liner | 2026-02-05 | Z | 2026-02-03 | 30 | 0 | 30 |  | 40 | 60 |  | Remake |  | 2
2026-02-05 | 56122 |  | 56122 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-05 | Z | 2026-02-05 | 10 | 0 | 0 |  | 0 | 30 |  | Zone 1 |  | 0
2026-02-06 | 74374 |  | 74374 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-12 | Z | 2026-02-03 | 30 | 0 | 0 |  | 0 | 60 |  | RF 4 penthouse |  | 9
2026-02-05 | 75602 | bth | 75602 | A | done | 8 | S/M |  | EVANSVILLE HS 4250049 |  | 2026-02-10 | Z | 2026-02-03 | 100 | 80 | 0 |  | 0 | 160 |  | HP metal |  | 7
2026-02-04 | 77563 |  | 77563 | A | done | 2 | S | ss | EXACT SEQ. 2250029 |  | 2026-02-09 | Z | 2026-02-03 | 10 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2026-02-04 | 77565 |  | 77565 | A | done | 2 | S | ss | EXACT SEQ. 2250029 |  | 2026-02-09 | Z | 2026-02-03 | 10 | 0 | 0 |  | 0 | 20 |  | Snorkel hood base |  | 6
2026-02-04 | 98134a |  | 98134a | A | done | 2 | S | ss | EXACT TL3 8240019 |  | 2026-02-09 | Z | 2026-01-29 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 11
2026-02-05 | 74851 | sp | 74851 | A | done | 2 | S |  | GRANT 6250021 |  | 2026-02-09 | Z | 2026-02-02 | 0 | 20 | 0 |  | 0 | 20 |  | Grill ext. |  | 7
2026-02-04 | 74852 |  | 74852 | A | done | 4 | S |  | GRANT 6250021 | 1" liner | 2026-02-09 | Z | 2026-02-02 | 60 | 0 | 0 |  | 50 | 80 |  | Library Trans. |  | 7
2026-02-04 | 83681 |  | 83681 | A | done | 2 | S | neal | MONROE 6240018 |  | 2026-02-04 | Z | 2026-02-03 | 10 | 0 | 0 |  | 0 | 40 |  | Flashing |  | 1
2026-02-04 | 83741 |  | 83741 | A | done | 6 | S/M | neal | MONROE 6240018 |  | 2026-02-04 | Z | 2026-02-03 | 20 | 70 | 0 |  | 0 | 150 |  | Remake |  | 1
2026-02-05 | 84931 |  | 84931 | A | done | 2 | S |  | MONROE 6240018 |  | 2026-02-11 | Z | 2026-02-05 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 6
2026-02-05 | 76354 |  | 76354-55 | A | done | 4 | S | neal | PEWAUKEE HS 6240030 |  | 2026-02-12 | Z | 2026-02-02 | 40 | 20 | 30 |  | 0 | 100 |  | Paint booth |  | 10
2026-02-04 | 3842 | bth | LG-SAMP-07 | A | done | 16 | M |  | PROJECT BTC 6250020 |  | 2026-02-09 | Z | 2026-01-23 | 240 | 30 | 60 |  | 0 | 380 |  |  |  | 17
2026-02-04 | 3843 | bth | LG-SAMP-08 | A | done | 38 | M/L |  | PROJECT BTC 6250020 |  | 2026-02-09 | Z | 2026-01-23 | 210 | 190 | 330 |  | 0 | 940 |  |  |  | 17
2026-02-04 | 3854 | bth | LG-SAMP-20 | A | done | 21 | M |  | PROJECT BTC 6250020 |  | 2026-02-09 | Z | 2026-01-23 | 190 | 140 | 120 |  | 0 | 510 |  |  |  | 17
2026-02-04 | 3855 | bth | LG-SAMP-21 | A | done | 31 | M |  | PROJECT BTC 6250020 |  | 2026-02-09 | Z | 2026-01-23 | 320 | 80 | 170 |  | 0 | 770 |  |  |  | 17
2026-02-05 | 76385 |  | 76385 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-02-12 | Z | 2026-02-04 | 10 | 0 | 0 |  | 0 | 20 |  | 300 IDF |  | 8
2026-02-06 | 76386 |  | 76386 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-02-12 | Z | 2026-02-05 | 10 | 0 | 0 |  | 0 | 20 |  | Wastewater |  | 7
2026-02-04 | 3824 | bth | LG-RA-06 | A | done | 38 | M/L |  | PROMEGA BTC 6250020 |  | 2026-02-03 | Z | 2026-01-13 | 260 | 60 | 240 |  | 0 | 940 |  |  |  | 21
2026-02-04 | 3826 | bth | LG-RA-04 | A | done | 57 | L |  | PROMEGA BTC 6250020 |  | 2026-02-11 | Z | 2026-01-13 | 310 | 10 | 480 |  | 0 | 1420 |  |  |  | 29
2026-02-04 | 3827 | bth | LG-RA-06 | A | done | 55 | L |  | PROMEGA BTC 6250020 |  | 2026-02-11 | Z | 2026-01-13 | 240 | 10 | 410 |  | 0 | 1370 |  |  |  | 29
2026-02-04 | 3828 |  | LG-RA-07 | A | done | 41 | M/L |  | PROMEGA BTC 6250020 |  | 2026-02-11 | Z | 2026-01-13 | 160 | 0 | 290 |  | 0 | 1010 |  |  |  | 29
2026-02-04 | 3835 | bth | LG-SAMP-19 | A | done | 33 | M/L |  | PROMEGA BTC 6250020 |  | 2026-02-05 | Z | 2026-01-22 | 330 | 50 | 170 |  | 0 | 810 |  |  |  | 14
2026-02-04 | 81871 | bth | 81871-73 | A | done | 26 | M |  | PROMEGA BTC 6250020 |  | 2026-02-05 | Z | 2026-01-29 | 280 | 130 | 0 |  | 0 | 640 |  | VAV 11-1 |  | 7
2026-02-05 | 76844 |  | 76844 | A | done | 2 | S |  | SBC 6230023 |  | 2026-02-13 | Z | 2026-02-05 | 20 | 0 | 0 |  | 0 | 20 |  | FCU 18 RA |  | 8
2026-02-04 | 1115 |  | L2-EA-04 | A | done | 5 | S/M |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 90 | 0 | 0 |  | 0 | 120 |  |  |  | 12
2026-02-04 | 1116 |  | L2-EA-05 | A | done | 4 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 60 | 0 | 0 |  | 0 | 90 |  |  |  | 12
2026-02-04 | 1117 |  | L2-EA-12 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 12
2026-02-04 | 1118 |  | L2-SAMP-03 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 12
2026-02-04 | 1119 |  | L2-SAMP-05 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 12
2026-02-04 | 1120 |  | L2-SAMP-07 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 12
2026-02-04 | 1121 |  | L2-SAMP-09 | A | done | 3 | S |  | SHRINE 6240034 | 1" liner | 2026-02-10 | Z | 2026-01-29 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 12
2026-02-04 | 1122 |  | L2-SAMP-10 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 12
2026-02-04 | 1123 |  | L2-SAMP-12 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 12
2026-02-04 | 1124 |  | L2-SAMP-14 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 12
2026-02-04 | 1125 |  | L2-SAMP-15 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 12
2026-02-04 | 1126 |  | L2-SAMP-18 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 12
2026-02-04 | 1127 |  | L2-SAMP-20 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 12
2026-02-04 | 1128 |  | L2-SAMP-21 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 12
2026-02-04 | 1129 |  | L2-SAMP-22 | A | done | 4 | S |  | SHRINE 6240034 | 1" liner | 2026-02-10 | Z | 2026-01-29 | 80 | 0 | 0 |  | 10 | 100 |  |  |  | 12 |  |  |  |  | 2024-09-25
2026-02-04 | 1130 |  | L2-SAMP-23 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-10 | Z | 2026-01-29 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 12 |  |  |  |  | 2024-09-25
2026-02-06 | 76030 | bth | 76030-31 | A | done | 2 | S |  | SPH 6240039 | 1" liner | 2026-02-12 | Z | 2026-01-30 | 30 | 20 | 0 |  | 10 | 80 |  | RAC 4-55 |  | 13
2026-02-05 | 76032 |  | 76032 | A | done | 2 | S |  | SPH 6240039 | paint black | 2026-02-13 | Z | 2026-02-03 | 30 | 0 | 0 |  | 30 | 40 |  | Reg boxes |  | 10
2026-02-05 | 98376 |  | 98376 | A | done | 7 | S/M |  | SWH MOB 6250015 |  | 2026-02-16 | Z | 2026-02-04 | 160 | 0 | 0 |  | 0 | 270 |  | Angles |  | 12
2026-02-04 | 76423 | bth | 76423-25 | A | done | 22 | M |  | THE HUB 4250061 |  | 2026-02-06 | Z | 2026-02-02 | 270 | 320 | 0 |  | 0 | 540 |  |  |  | 4
2026-02-04 | 76426 | bth | 76426-27 | A | done | 8 | S/M |  | THE HUB 4250061 |  | 2026-02-06 | Z | 2026-02-03 | 70 | 120 | 0 |  | 0 | 180 |  |  |  | 3
2026-02-06 | 76428 | sp | 76428-32 | A | done | 33 | M/L |  | THE HUB 4250061 |  | 2026-02-10 | Z | 2026-02-04 | 120 | 690 | 0 |  | 0 | 850 |  | HP |  | 6
2026-02-04 | 78330 |  | 78330 | A | done | 2 | S |  | UW LEVY HALL 6230028 |  | 2026-02-11 | Z | 2026-01-30 | 10 | 0 | 0 |  | 0 | 30 |  | EF 4 tie in |  | 12
2026-02-04 | 4000 | bth | L4-VAV-1-4-18 | A | done | 14 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-02-06 | Z | 2025-11-24 | 90 | 170 | 0 |  | 50 | 330 |  |  | SEMI | 74 | 2026-03-01
2026-02-04 | 4002 | bth | L4-VAV-1-4-21 | L | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-06 | Z | 2025-11-24 | 20 | 10 | 0 |  | 0 | 30 |  |  | SEMI | 74 | 2026-03-01
2026-02-04 | 4015 |  | L4-CAV-4-1-2 | A | done | 2 | S |  | UW STOUT 6250008 | VD | 2026-02-09 | Z | 2025-11-25 | 10 | 30 | 0 |  | 0 | 40 |  |  |  | 76
2026-02-04 | 4016 |  | L4-CAV-4-1-3 | A | done | 5 | S/M |  | UW STOUT 6250008 |  | 2026-02-09 | Z | 2025-11-25 | 20 | 0 | 60 |  | 0 | 110 |  |  |  | 76
2026-02-04 | 4017 |  | L4-VAV-1-4-1 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-09 | Z | 2025-11-25 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 76
2026-02-04 | 4318 | w | L3-SHAFT CEA E 1 | A | done | 11 | S/M | ss | UW STOUT 6250008 |  | 2026-01-27 | Z | 2026-01-14 | 70 | 0 | 0 |  | 0 | 270 |  |  |  | 13
2026-02-05 | 4333 |  | L3-SAMP 1 | A | done | 22 | M/L |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-29 | 360 | 0 | 170 |  | 0 | 1180 |  |  | SEMI | 13 | 2026-02-17
2026-02-06 | 4334 | bth | L3-SAMP 2 | A | done | 32 | L |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-29 | 240 | 90 | 470 |  | 0 | 1490 |  |  | SEMI | 13 | 2026-02-17
2026-02-06 | 4339 | bth | L3-SAMP 7 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-29 | 70 | 50 | 50 |  | 0 | 270 |  |  | SEMI | 13 | 2026-02-17
2026-02-05 | 4342 |  | L3-SAMP 13 | A | done | 29 | L |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 550 | 0 | 160 |  | 0 | 1470 |  |  | SEMI | 12 | 2026-02-24
2026-02-06 | 4347 | bth | L3-SAMP 20 | A | done | 12 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 100 | 50 | 150 |  | 0 | 470 |  |  | SEMI | 12 | 2026-02-24
2026-02-06 | 4348 |  | L3-SAMP 21 | A | done | 18 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 280 | 0 | 150 |  | 0 | 700 |  |  | SEMI | 12 | 2026-02-24
2026-02-06 | 4350 | bth | L3-SAMP 8 | A | done | 8 | S/M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 80 | 30 | 90 |  | 0 | 230 |  |  | SEMI | 9 | 2026-03-03
2026-02-06 | 4353 | bth | L3-SAMP 22 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 70 | 60 | 30 |  | 0 | 180 |  |  | SEMI | 9 | 2026-03-03
2026-02-06 | 4354 | bth | L3-SAMP 23 | A | done | 13 | S/M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 140 | 110 | 60 |  | 0 | 350 |  |  | SEMI | 9 | 2026-03-03
2026-02-06 | 4355 |  | L3-SAMP 25 | A | done | 21 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 150 | 0 | 360 |  | 0 | 770 |  |  | SEMI | 9 | 2026-03-03
2026-02-06 | 77362 |  | 77362 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-10 | Z | 2026-02-04 | 10 | 0 | 0 |  | 0 | 40 |  | Shaft C |  | 6
2026-02-06 | 84561 |  | 84561 | A | done | 9 | M |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 210 | 0 | 0 |  | 0 | 450 |  | Flashing |  | 12
2026-02-06 | 75419a |  | 75419a | A | done | 2 | S | bi | WAUNAKEE 6230013 |  | 2026-02-06 | Z | 2026-02-06 | 10 | 0 | 0 |  | 0 | 20 |  | Grease duct remake |  | 0
2026-02-05 | 83431 | w | 83431 | A | done | 2 | S | neal | WAUNAKEE 6230013 |  | 2026-02-06 | Z | 2026-01-28 | 30 | 0 | 0 |  | 0 | 70 |  | Dust collectors |  | 9
[6 empty] | 1191 | [13 empty] | 31640 | [5 empty] | 52% short
[9 empty] | WEEK OF 2-9-2026 | [16 empty] | % Under 14
2026-02-10 | 82793 |  | 82793 | A | done | 2 | S | neal | ANTIGO 6250017 | 2" liner | 2026-02-16 | Z | 2026-02-06 | 20 | 0 | 0 |  | 20 | 40 |  | BCU 1 |  | 10 |  |  | 59.09%
2026-02-11 | 58176 | sp | 58176-78 | A | done | 8 | S/M | alum | BROOM ST 6240033 |  | 2026-02-17 | Z | 2026-01-06 | 80 | 120 | 0 |  | 0 | 200 |  | West sleeves |  | 42
2026-02-09 | 58189 |  | 58189 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-02-16 | Z | 2026-02-02 | 30 | 0 | 0 |  | 0 | 40 |  | 3rd floor west |  | 14
2026-02-10 | 79497 | sp | 79497 | A | done | 2 | S | neal | BROOM ST 6240033 |  | 2026-02-11 | Z | 2026-02-09 | 0 | 30 | 0 |  | 0 | 40 |  | SALP 08 outs |  | 2
2026-02-10 | 79498 | sp | 79498 | A | done | 6 | S/M |  | BROOM ST 6240033 | 1" liner | 2026-02-11 | Z | 2026-02-09 | 40 | 100 | 0 |  | 20 | 170 |  | Jhf office |  | 2
2026-02-13 | 79499 | bth | 79499 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-02-17 | Z | 2026-02-11 | 110 | 0 | 0 | 110 | 0 | 130 |  | 2A misc |  | 6
2026-02-12 | 99997 |  | 58182-84 | A | done | 7 | M |  | BROOM ST 6240033 | rivet nuts | 2026-02-17 | Z | 2026-01-02 | 170 | 0 | 0 | 170 | 0 | 410 |  | OA kits |  | 46
2026-02-09 | 74218 |  | 74218 | A | done | 6 | S/M | pcd | DELLSHIRE 6240017 | paint black | 2026-02-11 | Z | 2026-02-09 | 130 | 0 | 0 |  | 70 | 190 |  | Misc |  | 2
2026-02-10 | 56123 | w | 56123-24 | A | done | 4 | S/M |  | DOC JDC 6240023 | 1" liner | 2026-02-12 | Z | 2026-02-10 | 80 | 0 | 0 |  | 20 | 240 |  | Misc tie ins |  | 2
2026-02-11 | 74166 |  | 74166 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-12 | Z | 2026-02-11 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 1
2026-02-09 | 74358a |  | 74358a | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-12 | Z | 2026-02-06 | 10 | 0 | 0 |  | 0 | 20 |  | Curb rail caps |  | 6
2026-02-09 | 74372 |  | 74372-73 | A | done | 7 | S/M |  | DOC JDC 6240023 | flex, paint black, bs | 2026-02-12 | Z | 2026-02-03 | 130 | 0 | 30 |  | 40 | 200 |  | MUA 2, Compressor rm |  | 9
2026-02-11 | 10006 |  | 10006 | A | done | 2 | S |  | FAIRCHILD 20010220 | paint black | 2026-02-12 | Z | 2026-02-11 | 30 | 0 | 0 |  | 30 | 60 |  | Pans |  | 1
2026-02-11 | 74853 |  | 74853 | A | done | 4 | S/M |  | GRANT ES 6250021 | paint black | 2026-02-16 | Z | 2026-02-05 | 80 | 0 | 0 |  | 80 | 110 |  | Area B bathrooms |  | 11
2026-02-11 | 10005 |  | 10005 | A | done | 2 | S | alum | MADISON CD 3250020 |  | 2026-02-13 | Z | 2026-02-06 | 10 | 0 | 0 |  | 0 | 20 |  | Flue |  | 7
2026-02-11 | 64688 |  | 64688 | A | done | 2 | S | alum | MAUSTON R 6250019 |  | 2026-02-24 | Z | 2026-02-10 | 20 | 0 | 0 |  | 0 | 20 |  | EA curb drop |  | 14
2026-02-12 | 74361 | sp | 74361 | A | done | 10 | S/M | neal | MONROE 6240018 | spiralmate | 2026-02-18 | Z | 2026-02-09 | 0 | 230 | 0 | 0 | 0 | 320 |  | DC 1 and 2 inlet |  | 9
2026-02-12 | 74364 | sp | 74364 | A | done | 7 | S/M | neal | MONROE 6240018 | spiralmate | 2026-02-18 | Z | 2026-02-09 | 40 | 120 | 0 | 40 | 0 | 220 |  | Woods DC RA |  | 9
2026-02-09 | 74367 |  | 74367 | A | done | 2 | S | neal | MONROE 6240018 | 1" liner | 2026-02-11 | Z | 2026-02-06 | 20 | 0 | 0 |  | 10 | 70 |  | Curb cap |  | 5
2026-02-10 | 74368 | sp | 74368 | A | done | 2 | S | alum | MONROE 6240018 | birdscreen | 2026-02-11 | Z | 2026-02-06 | 10 | 40 | 0 |  | 0 | 40 |  | Dryers, spray space |  | 5
2026-02-10 | 83638 | w | 83638-39 | A | done | 2 | S |  | MONROE 6240018 |  | 2026-02-11 | Z | 2026-02-10 | 20 | 0 | 0 |  | 10 | 50 |  |  |  | 1
2026-02-12 | 83641 | bth | 83641 | A | done | 2 | S | neal | MONROE 6240018 | 1" liner | 2026-02-18 | Z | 2026-02-10 | 30 | 20 | 0 | 30 | 10 | 70 |  | Storage D section |  | 8
2026-02-12 | 83642 |  | 83642 | A | done | 2 | S | neal | MONROE 6240018 |  | 2026-02-18 | Z | 2026-02-12 | 10 | 0 | 0 | 10 | 0 | 20 |  | Solder hood |  | 6
2026-02-13 | 83770 |  | 83770 | A | done | 2 | S | neal | MONROE 6240018 |  | 2026-02-13 | Z | 2026-02-13 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 0
2026-02-09 | 76434 |  | 76434 | A | done | 2 | S |  | OAKWOOD 10065389 |  | 2026-02-12 | Z | 2026-02-05 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 7
2026-02-09 | 76433 |  | 76433 | A | done | 2 | S |  | OAKWOOD 10065390 | 1" liner | 2026-02-12 | Z | 2026-02-05 | 30 | 0 | 0 |  | 20 | 30 |  | APT 621 |  | 7
2026-02-09 | 76356 |  | 76356 | A | done | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2026-02-13 | Z | 2026-02-09 | 10 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 4
2026-02-11 | 75603 |  | 75603 | A | done | 2 | S |  | PLACON 4260005 |  | 2026-02-19 | Z | 2026-02-05 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 14
2026-02-12 | 76382 |  | 76382-84 | A | done | 23 | M/L | ss | PROJECT DOVE 6240041 | flex | 2026-02-12 | Z | 2026-02-04 | 560 | 0 | 0 | 560 | 0 | 1250 |  | 300 |  | 8
2026-02-10 | 76012 |  | 76012-27 | A | done | 151 | L |  | RCIS 6250011 |  | 2026-02-11 | Z | 2026-01-23 | 2150 | 0 | 1610 |  | 0 | 6510 |  | C Mezz | SEMI | 19 | 2026-06-22
2026-02-12 | 10007 |  | 10007 | A | done | 2 | S |  | SBC 6230023 |  | 2026-02-13 | Z | 2026-02-12 | 10 | 0 | 0 | 10 | 0 | 20 |  |  |  | 1
2026-02-13 | 1131 | w | B- KE- 01 | A | done | 7 | M | ss | SHRINE 6240034 |  | 2026-02-16 | Z | 2026-02-03 | 160 | 0 | 0 | 160 | 0 | 400 |  |  |  | 13
2026-02-13 | 1133 | w | B- KE- 03 | A | done | 4 | S/M | ss | SHRINE 6240034 |  | 2026-02-16 | Z | 2026-02-03 | 100 | 0 | 0 | 100 | 0 | 290 |  |  |  | 13
2026-02-11 | 1134 |  | B- OA- 01 | A | done | 16 | M |  | SHRINE 6240034 | flex | 2026-02-16 | Z | 2026-02-03 | 360 | 0 | 40 |  | 0 | 790 |  |  |  | 13
2026-02-10 | 85459 |  | 85459 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-12 | Z | 2026-02-04 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 8
2026-02-11 | 85460 |  | 85460-61 | A | done | 7 | S/M |  | SHRINE 6240034 | 1" liner | 2026-02-16 | Z | 2026-02-05 | 170 | 0 | 0 |  | 80 | 230 |  | Misc level 1 |  | 11
2026-02-11 | 85462 |  | 85462 | A | done | 2 | S |  | SHRINE 6240034 | paint black | 2026-02-16 | Z | 2026-02-06 | 30 | 0 | 0 |  | 10 | 50 |  | Level 1 misc |  | 10
2026-02-12 | 85463 | w | 85463 | A | done | 4 | S/M | bi | SHRINE 6240034 |  | 2026-02-23 | Z | 2026-02-09 | 100 | 0 | 0 | 100 | 0 | 340 |  | KH 1 Hood |  | 14
2026-02-11 | 83768 |  | 83768 | A | done | 2 | S |  | TA 1000381 |  | 2026-02-12 | Z | 2026-02-11 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 1
2026-02-09 | 76435 |  | 76435 | A | done | 2 | S |  | THE HUB 4250061 |  | 2026-02-10 | Z | 2026-02-09 | 10 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2026-02-12 | 74868 |  | 74868 | A | done | 2 | S |  | UW LEVY HALL 6230028 | 1" liner | 2026-02-17 | Z | 2026-02-06 | 40 | 0 | 0 | 40 | 40 | 70 |  | L4 ceiling tie ins |  | 11
2026-02-13 | 74872 |  | 74872 | A | done | 2 | S |  | UW LEVY HALL 6230028 |  | 2026-02-17 | Z | 2026-02-12 | 10 | 0 | 0 | 10 | 0 | 20 |  | LL SAMP |  | 5
2026-02-12 | 2966 |  | L4-SAMP 16 | A | done | 26 | L |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-10-22 | 380 | 0 | 260 | 640 | 0 | 1440 |  | Partially needed Duct |  | 117 | 2026-04-01
2026-02-11 | 2967 |  | L4-SAMP 17 | A | done | 19 | M/L |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-10-22 | 100 | 0 | 360 |  | 0 | 1160 |  |  |  | 117 | 2026-04-01
2026-02-11 | 2968 | bth | L4-SAMP 18 | A | done | 14 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-10-22 | 200 | 20 | 120 |  | 0 | 680 |  |  |  | 117 | 2026-04-01
2026-02-11 | 2996 | bth | L4-VAV-2-4-56 | A | done | 12 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-11-24 | 150 | 20 | 130 |  | 0 | 400 |  |  |  | 84 | 2026-04-01
2026-02-11 | 2997 |  | L4-VAV-2-4-57-1 | A | done | 12 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-11-24 | 220 | 0 | 80 |  | 50 | 410 |  |  |  | 84 | 2026-04-01
2026-02-10 | 2998 |  | L4-VAV-2-4-57-2 | A | done | 8 | S/M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-11-24 | 100 | 0 | 90 |  | 0 | 250 |  |  |  | 84 | 2026-04-01
2026-02-10 | 2999 | bth | L4-VAV-2-4-58 | A | done | 4 | S |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-11-24 | 50 | 10 | 20 |  | 0 | 90 |  |  |  | 84 | 2026-04-01
2026-02-10 | 4102 |  | L4-RA 6 | A | done | 6 | S/M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-12-03 | 70 | 0 | 80 |  | 0 | 320 |  |  |  | 75 | 2026-04-01
2026-02-10 | 4103 |  | L4-RA 7 | A | done | 9 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-12-03 | 150 | 0 | 60 |  | 0 | 450 |  |  |  | 75 | 2026-04-01
2026-02-10 | 4104 |  | L4-RA 8 | A | done | 16 | M/L |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2025-12-03 | 110 | 0 | 270 |  | 0 | 890 |  |  |  | 75 | 2026-04-01
2026-02-10 | 4106 |  | L4-RA 10 | A | done | 17 | M/L |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 200 | 0 | 220 |  | 0 | 980 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4107 |  | L4-RA 11 | A | done | 32 | L |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 510 | 0 | 270 |  | 0 | 1810 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4108 |  | L4-RA 12 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4109 |  | L4-RA 13 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4110 |  | L4-RA 14 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4111 |  | L4-RA 15 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4112 |  | L4-RA 16 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4113 |  | L4-RA 17 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4114 |  | L4-RA 18 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 75 | 2026-04-01
2026-02-11 | 4115 |  | L4-RA 19 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-02-16 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 75 | 2026-04-01
2026-02-10 | 4293 | sp | L5-SHAFT EA H 1 | A | done | 2 | S | pcd | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 10 | 10 | 0 |  | 0 | 20 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4294 |  | L5-SHAFT EA H 2 | A | done | 2 | S | pcd | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4295 | sp | L5-SHAFT EA H 3 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 30 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4302 |  | L4-SHAFT EA B 1 | A | done | 4 | S |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 50 | 30 | 0 |  | 0 | 100 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4307 | sp | L4-SHAFT EA H 1 | A | done | 2 | S | pcd | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4308 |  | L4-SHAFT EA H 2 | A | done | 4 | S/M | pcd | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 0 | 80 | 0 |  | 0 | 120 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4309 | sp | L4-SHAFT EA H 3 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4310 |  | L4-SHAFT RA H 1 | A | done | 6 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 150 | 0 | 0 |  | 0 | 400 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4311 |  | L4-SHAFT RA J 1 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 110 | 60 | 0 |  | 0 | 320 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4315 |  | L4-SHAFT SAMP J 1 | A | done | 9 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 160 | 0 | 60 |  | 0 | 450 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4324 | sp | L3-SHAFT EA H 1 | A | done | 2 | S | pcd | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 10 | 20 | 0 |  | 0 | 30 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4325 |  | L3-SHAFT EA H 2 | A | done | 3 | S | pcd | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 20 | 0 | 50 |  | 0 | 100 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4326 | sp | L3-SHAFT EA H 3 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4327 |  | L3-SHAFT RA H 1 | A | done | 10 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 70 | 0 | 170 |  | 0 | 560 |  |  |  | 33 | 2026-05-01
2026-02-10 | 4328 |  | L3-SHAFT RA J 1 | A | done | 10 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 160 | 0 | 80 |  | 0 | 560 |  |  |  | 33 | 2026-05-01
2026-02-11 | 4331 |  | L3-SHAFT SAMP H 1 | A | done | 10 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 70 | 0 | 170 |  | 0 | 590 |  |  |  | 33 | 2026-05-01
2026-02-11 | 4332 |  | L3-SHAFT SAMP J 1 | A | done | 11 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-01-14 | 170 | 0 | 90 |  | 0 | 650 |  |  |  | 33 | 2026-05-01
2026-02-09 | 4335 | bth | L3-SAMP 3 | A | done | 30 | M/L |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-29 | 210 | 130 | 400 |  | 0 | 1270 |  |  | SEMI | 13 | 2026-02-17
2026-02-09 | 4336 | bth | L3-SAMP 4 | A | done | 12 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-29 | 30 | 20 | 250 |  | 0 | 470 |  |  | SEMI | 13 | 2026-02-17
2026-02-09 | 4337 | bth | L3-SAMP 5 | A | done | 9 | S/M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-29 | 70 | 50 | 100 |  | 0 | 290 |  |  | SEMI | 13 | 2026-02-17
2026-02-09 | 4338 | bth | L3-SAMP 6 | A | done | 13 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-29 | 140 | 180 | 0 |  | 0 | 420 |  |  | SEMI | 13 | 2026-02-17
2026-02-10 | 4340 | bth | L3-SAMP 11 | A | done | 26 | L |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-29 | 10 | 20 | 610 |  | 0 | 1370 |  |  | SEMI | 13 | 2026-02-17
2026-02-09 | 4341 | bth | L3-SAMP 12 | A | done | 14 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 30 | 80 | 220 |  | 0 | 490 |  |  | SEMI | 12 | 2026-02-24
2026-02-09 | 4343 | bth | L3-SAMP 16 | A | done | 12 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 140 | 90 | 60 |  | 0 | 450 |  |  | SEMI | 12 | 2026-02-24
2026-02-09 | 4344 | bth | L3-SAMP 17 | A | done | 19 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 20 | 40 | 400 |  | 0 | 740 |  |  | SEMI | 12 | 2026-02-24
2026-02-09 | 4345 |  | L3-SAMP 18 | A | done | 18 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 200 | 0 | 240 |  | 0 | 740 |  |  | SEMI | 12 | 2026-02-24
2026-02-09 | 4346 | bth | L3-SAMP 19 | A | done | 6 | S/M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 40 | 50 | 50 |  | 0 | 150 |  |  | SEMI | 12 | 2026-02-24
2026-02-09 | 4349 |  | L3-SAMP 24 | A | done | 14 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-01-30 | 240 | 0 | 100 |  | 0 | 580 |  |  | SEMI | 12 | 2026-02-24
2026-02-10 | 4351 | bth | L3-SAMP 9 | A | done | 9 | S/M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 20 | 40 | 150 |  | 0 | 250 |  |  | SEMI | 9 | 2026-03-03
2026-02-10 | 4352 | bth | L3-SAMP 10 | A | done | 6 | S/M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 30 | 90 | 30 |  | 0 | 150 |  |  | SEMI | 9 | 2026-03-03
2026-02-09 | 4356 | bth | L3-SAMP 26 | A | done | 3 | S |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 60 | 10 | 0 |  | 0 | 80 |  |  | SEMI | 9 | 2026-03-03
2026-02-09 | 4357 | bth | L3-SAMP 27 | A | done | 20 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 170 | 50 | 270 |  | 0 | 620 |  |  | SEMI | 9 | 2026-03-03
2026-02-09 | 4358 | bth | L3-SAMP 28 | A | done | 13 | M |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 100 | 50 | 170 |  | 0 | 360 |  |  | SEMI | 9 | 2026-03-03
2026-02-09 | 4359 |  | L3-SAMP 29 | A | done | 24 | M/L |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 250 | 0 | 350 |  | 0 | 1020 |  |  | SEMI | 9 | 2026-03-03
2026-02-09 | 4360 | bth | L3-SAMP 30 | A | done | 19 | M/L |  | UW STOUT 6250008 |  | 2026-02-11 | Z | 2026-02-02 | 310 | 40 | 110 |  | 0 | 1020 |  |  | SEMI | 9 | 2026-03-03
2026-02-12 | 4361 |  | L3-SAMP 14 | A | done | 25 | L |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-02-03 | 370 | 250 | 0 | 370 | 0 | 1560 |  |  |  | 13 | 2026-05-01
2026-02-12 | 4362 |  | L3-SAMP 15 | A | done | 36 | L |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-02-03 | 760 | 0 | 140 | 900 | 0 | 2570 |  |  |  | 13 | 2026-05-01
2026-02-11 | 4363 | bth | L3-SAMP 31 | A | done | 21 | M/L |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-02-03 | 140 | 20 | 350 |  | 0 | 1030 |  |  |  | 13 | 2026-05-01
2026-02-11 | 4364 |  | L3-SAMP 32 | A | done | 17 | M |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-02-03 | 110 | 0 | 300 |  | 0 | 770 |  |  |  | 13 | 2026-05-01
2026-02-12 | 4365 | bth | L3-SAMP 33 | A | done | 18 | M/L |  | UW STOUT 6250008 |  | 2026-02-16 | Z | 2026-02-03 | 270 | 40 | 120 | 390 | 0 | 880 |  |  |  | 13 | 2026-05-01
2026-02-13 | 4366 |  | L3-RAMP 1 | A | done | 34 | L |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 490 | 0 | 340 | 830 | 0 | 1680 |  |  |  | 12 | 2026-03-10
2026-02-13 | 4370 |  | L3-RAMP 5 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 30 | 0 | 0 | 30 | 0 | 50 |  |  |  | 12 | 2026-03-10
2026-02-11 | 4371 |  | L3-RAMP 6 | A | done | 23 | M/L |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 240 | 0 | 330 |  | 0 | 1210 |  |  |  | 12 | 2026-03-10 |  |  |  | 2024-09-25
2026-02-12 | 4372 |  | L3-RAMP 7 | A | done | 28 | L |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 340 | 0 | 340 | 680 | 0 | 1360 |  |  |  | 12 | 2026-03-10 |  |  |  | 2024-09-25
2026-02-12 | 77363 |  | 77363 | A | done | 4 | S/M |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-12 | 100 | 0 | 0 | 100 | 0 | 180 |  | Flat stock |  | 5 |  |  |  |  | 2024-09-25
2026-02-13 | 84563 |  | 84563 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-12 | 10 | 0 | 0 | 10 | 0 | 20 |  | VAV red 4th |  | 5
2026-02-11 | 74370 |  | 74370 | A | done | 2 | S |  | UWW METALS LAB 6250001 |  | 2026-02-20 | Z | 2026-02-06 | 0 | 0 | 0 |  | 0 | 30 |  | Ductmate frames |  | 14
2026-02-12 | 73829 |  | 73829 | A | done | 4 | S |  | WAUNAKEE 6230013 | paint black | 2026-02-13 | Z | 2026-02-11 | 80 | 0 | 0 | 80 | 10 | 100 |  |  |  | 2
[6 empty] | 1088 | [13 empty] | 48050
[9 empty] | WEEK OF 2-16-2026 | [16 empty] | % Under 14
2026-02-17 | 82796 |  | 82796 | A | done | 5 | S/M |  | ANTIGO 6250017 | 1" liner | 2026-02-17 | Z | 2026-02-13 | 110 | 0 | 0 | 110 | 90 | 170 |  |  |  | 4 |  |  | 71.32%
2026-02-16 | 82800 |  | 82800 | A | done | 2 | S |  | ANTIGO 6250017 |  | 2026-02-17 | Z | 2026-02-13 | 10 | 40 | 0 | 10 | 0 | 50 | 24GA GALV | Coupling |  | 4
2026-02-19 | 1562 | bth | UNIT 531 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 60 | 80 | 0 | 60 | 0 | 160 |  |  |  | 49
2026-02-18 | 1563 | bth | UNIT 532 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 70 | 80 | 0 | 70 | 0 | 170 |  |  |  | 49
2026-02-18 | 1564 |  | UNIT 533 M4.66 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 140 | 0 | 70 | 210 | 0 | 220 |  |  |  | 49
2026-02-18 | 1565 |  | UNIT 534 M4.67 | A | done | 15 | M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 170 | 0 | 190 | 360 | 0 | 420 |  |  |  | 49
2026-02-18 | 1566 |  | UNIT 535 M4.68 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 90 | 0 | 0 | 90 | 0 | 100 |  |  |  | 49
2026-02-18 | 1567 |  | UNIT 536 M4.69 | A | done | 4 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 80 | 0 | 20 | 100 | 0 | 110 |  |  |  | 49
2026-02-18 | 1568 |  | UNIT 537 M4.70 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 220 | 0 | 70 | 290 | 0 | 290 |  |  |  | 49
2026-02-18 | 1569 |  | UNIT 538 M4.71 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 160 | 0 | 120 | 280 | 0 | 270 |  |  |  | 49
2026-02-18 | 1570 |  | UNIT 539 M4.72 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 240 | 0 | 0 | 240 | 0 | 260 |  |  |  | 49
2026-02-18 | 1571 |  | UNIT 541 M4.73 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 60 | 0 | 20 | 80 | 0 | 80 |  |  |  | 49
2026-02-18 | 1572 |  | UNIT 542 M4.74 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-01-07 | 190 | 0 | 20 | 210 | 0 | 220 |  |  |  | 49
2026-02-19 | 1671 | bth | L1-EA-01 | A | done | 55 | S/M | neal | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 40 | 1330 | 0 | 40 | 0 | 200 | 24GA GALV |  |  | 7
2026-02-19 | 1672 | sp | L1-EA-02 | A | done | 5 | S/M | neal | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 30 | 90 | 0 | 30 | 0 | 140 | 24GA GALV |  |  | 7
2026-02-19 | 1673 | bth | L1-EA-03 | A | done | 7 | S/M | neal | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 40 | 120 | 0 | 40 | 0 | 180 | 24GA GALV |  |  | 7
2026-02-19 | 1674 | sp | L1-EA-04 | A | done | 10 | S/M | neal | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 30 | 210 | 0 | 30 | 0 | 270 | 24GA GALV |  |  | 7
2026-02-20 | 1675 | bth | L1-EA-05 | A | done | 7 | S/M | neal | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 70 | 100 | 0 | 70 | 0 | 200 |  |  |  | 7
2026-02-19 | 1676 | sp | L1-EA-06 | A | done | 9 | S/M | neal | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 40 | 170 | 0 | 40 | 0 | 220 | 26GA GALV |  |  | 7
2026-02-19 | 1677 |  | L1-EA-07 | A | done | 6 | S/M |  | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 100 | 0 | 30 | 130 | 0 | 130 | 26GA GALV |  |  | 7
2026-02-19 | 1678 |  | L1-EA-08 | A | done | 3 | S |  | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 70 | 0 | 0 | 70 | 0 | 90 | 26GA GALV |  |  | 7
2026-02-19 | 1679 | sp | L1-EA-09 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 20 | 160 | 0 | 20 | 0 | 170 | 26GA GALV |  |  | 7
2026-02-19 | 1680 | bth | L1-EA-10 | A | done | 11 | S/M | alum | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 210 | 10 | 50 | 260 | 0 | 190 | 18GA GALV |  |  | 7
2026-02-19 | 1681 | sp | L1-EA-11 | A | done | 4 | S | alum | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 20 | 70 | 0 | 20 | 0 | 50 | 18GA GALV |  |  | 7
2026-02-19 | 1682 |  | L1-EA-12 | A | done | 16 | S/M | alum | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 230 | 0 | 170 | 400 | 0 | 300 | 18GA GALV |  |  | 7
2026-02-19 | 1683 |  | L1-EA-13 | A | done | 20 | M | neal | BROOM ST 6240033 | flex, birdscreen | 2026-02-23 | Z | 2026-02-16 | 240 | 0 | 240 | 480 | 0 | 670 | 24GA GALV |  |  | 7
2026-02-20 | 1684 | bth | L1-OA-01 | A | done | 10 | S/M | neal | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 110 | 120 | 0 | 110 | 0 | 270 | 26GA GALV |  |  | 7
2026-02-20 | 1685 | bth | L1-OA-02 | A | done | 8 | S/M | neal | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 90 | 110 | 0 | 90 | 0 | 240 | 24GA GALV |  |  | 7
2026-02-19 | 1686 | sp | L1-OA-03 | A | done | 8 | S/M | neal | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 10 | 180 | 0 | 10 | 0 | 210 | 24GA GALV |  |  | 7
2026-02-19 | 1687 |  | L1-OA-04 | A | done | 8 | S/M |  | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 130 | 0 | 50 | 180 | 0 | 190 | 26GA GALV |  |  | 7
2026-02-20 | 1688 | bth | L1-OA-05 | A | done | 10 | S/M | neal | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 90 | 140 | 0 | 90 | 0 | 270 | 24GA GALV |  |  | 7
2026-02-20 | 1689 | sp | L1-OA-06 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 30 | 170 | 0 | 30 | 0 | 180 | 24GA GALV |  |  | 7
2026-02-19 | 1690 | sp | L1-OA-07 | A | done | 8 | S/M | neal | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 40 | 160 | 0 | 40 | 0 | 250 | 24GA GALV |  |  | 7
2026-02-19 | 1691 |  | L1-OA-08 | A | done | 5 | S/M |  | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 80 | 0 | 30 | 110 | 0 | 140 | 24GA GALV |  |  | 7
2026-02-19 | 1692 |  | L1-OA-09 | A | done | 5 | S/M |  | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 70 | 0 | 40 | 110 | 0 | 110 | 26GA GALV |  |  | 7
2026-02-19 | 1693 | bth | L1-OA-10 | A | done | 10 | S/M | neal | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 50 | 180 | 0 | 50 | 0 | 280 | 24GA GALV |  |  | 7
2026-02-19 | 1694 |  | L1-OA-11 | A | done | 5 | S/M |  | BROOM ST 6240033 | flex | 2026-02-23 | Z | 2026-02-16 | 80 | 0 | 30 | 110 | 0 | 120 | 26GA GALV |  |  | 7
2026-02-19 | 1696 | bth | L1-RA-02 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 30 | 120 | 30 | 60 | 0 | 190 | 24GA GALV |  |  | 7
2026-02-19 | 1698 | bth | L1-RA-04 | A | done | 7 | S/M |  | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 60 | 110 | 0 | 60 | 0 | 180 | 26GA GALV |  |  | 7
2026-02-19 | 1699 |  | L1-RA-05 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 0 | 50 | 26GA GALV |  |  | 7
2026-02-17 | 58190 | sp | 58190 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-02-24 | Z | 2026-02-12 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | 3rd floor west |  | 12
2026-02-19 | 78263 | sp | 78263 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 10 | 20 | 0 | 10 | 0 | 20 | 26GA GALV | L1 Amenties |  | 7
2026-02-19 | 79536 | sp | 79536-39 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 50 | 60 | 0 | 50 | 0 | 110 | 24GA GALV | Misc |  | 7
2026-02-16 | 56128 | bth | 56128 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-16 | Z | 2026-02-16 | 20 | 30 | 0 | 20 | 0 | 60 |  | VD's in wall |  | 0
2026-02-16 | 56129 |  | 56129 | A | done | 3 | S/M |  | DOC JDC 6240023 | MOD, paint black | 2026-02-16 | Z | 2026-02-16 | 70 | 0 | 0 | 70 | 40 | 110 |  | MUA 2 |  | 0
2026-02-18 | 56132 | bth | 56132 | A | done | 21 | S/M | alum | DOC JDC 6240023 |  | 2026-02-19 | Z | 2026-02-16 | 170 | 340 | 0 | 170 | 0 | 280 |  | Zone 2 and 3 |  | 3
2026-02-18 | 56134 | sp | 56134-35 | A | done | 2 | S/M | neal | DOC JDC 6240023 |  | 2026-02-19 | Z | 2026-02-17 | 10 | 40 | 0 | 10 | 0 | 110 | 20GA GALV | Weld exhaust |  | 2
2026-02-18 | 73556 |  | 73556 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-19 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 0 | 70 | 22GA GALV | REL 1 tie in |  | 3
2026-02-17 | 74167 |  | 74167-69 | A | done | 4 | S/M |  | DOC JDC 6240023 | paint black | 2026-02-19 | Z | 2026-02-16 | 80 | 0 | 0 | 80 | 40 | 110 | 24GA GALV | OA to ceiling |  | 3
2026-02-20 | 83772 |  | 83772 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-24 | Z | 2026-02-20 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV |  |  | 4
2026-02-19 | 74779 | bth | 74779-80 | A | done | 11 | S/M |  | FRANK&ANDREAS 4250061 |  | 2026-02-23 | Z | 2026-02-16 | 190 | 80 | 0 | 190 | 100 | 330 | 26GA GALV |  |  | 7
2026-02-17 | 74854 |  | 74854,74857 | A | done | 23 | M/L |  | GRANT ES 6250021 |  | 2026-02-23 | Z | 2026-02-10 | 90 | 0 | 470 | 560 | 0 | 830 |  | Phase 5 |  | 13
2026-02-17 | 74855 | bth | 74855-56,58-60 | A | done | 24 | M |  | GRANT ES 6250021 |  | 2026-02-23 | Z | 2026-02-10 | 120 | 410 | 70 | 190 | 0 | 620 |  | Phase 5 |  | 13
2026-02-18 | 74861 |  | 74861 | A | done | 2 | S |  | GRANT ES 6250021 |  | 2026-02-23 | Z | 2026-02-12 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV | Phase 5 main |  | 11
2026-02-19 | 74862 |  | 74862 | A | done | 4 | S/M |  | GRANT ES 6250021 |  | 2026-03-02 | Z | 2026-02-16 | 20 | 0 | 70 | 90 | 0 | 110 | 24GA GALV | Phase 5 main |  | 14
2026-02-17 | 41708 |  | 41708 | A | done | 4 | S/M |  | LABCORP 2250055 | 1" liner | 2026-02-18 | Z | 2026-02-13 | 90 | 0 | 0 | 90 | 80 | 110 |  | Transfer |  | 5
2026-02-20 | 64723 |  | 64723-24,64726-28 | A | done | 26 | M/L |  | MAUSTON R 6250019 |  | 2026-02-24 | Z | 2026-02-10 | 410 | 0 | 240 | 650 | 0 | 930 |  | Mech OA |  | 14
2026-02-16 | 74360 |  | 74360 | A | done | 7 | S/M | neal | MONROE 6240018 | 1" liner | 2026-02-18 | Z | 2026-02-06 | 90 | 0 | 80 | 170 | 150 | 300 |  | Woods dc RA |  | 12
2026-02-18 | 74362 | sp | 74362 | A | done | 4 | S/M | neal | MONROE 6240018 | spiralmate | 2026-02-18 | Z | 2026-02-09 | 90 | 0 | 0 | 90 | 0 | 270 |  | DC 1 and 2 fitting |  | 9
2026-02-20 | 74365 | w | 74365-66 | A | done | 9 | M | bi | MONROE 6240018 | angle rings | 2026-02-26 | Z | 2026-02-10 | 210 | 0 | 0 | 210 | 210 | 530 |  | Woods dc discharge |  | 16
2026-02-16 | 83643 |  | 83643 | A | done | 2 | S | ss | MONROE 6240018 |  | 2026-02-17 | Z | 2026-02-16 | 10 | 0 | 0 | 10 | 0 | 20 |  | Kitchen hood patch |  | 1
2026-02-20 | 83645 |  | 83645 | A | done | 4 | S/M | neal | MONROE 6240018 | 1" liner, paint black | 2026-03-03 | Z | 2026-02-18 | 90 | 0 | 0 | 90 | 70 | 210 |  | Dust collector |  | 13
2026-02-20 | 83682 |  | 83682 | A | done | 3 | S | neal | MONROE 6240018 |  | 2026-02-25 | Z | 2026-02-17 | 60 | 0 | 0 | 60 | 0 | 80 | 24GA GALVANEAL | BCU 6 |  | 8
2026-02-19 | 10007 | w | 10007 | A | done | 2 | S | ss | OCTOPI 8250035 |  | 2026-02-20 | Z | 2026-02-18 | 10 | 0 | 0 | 10 | 0 | 20 |  | Drain basket |  | 2
2026-02-19 | 83771 |  | 83771 | A | done | 2 | S |  | PEWAUKEE HS 6240030 |  | 2026-02-19 | Z | 2026-02-19 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 0
2026-02-17 | 76388 |  | 76388 | A | done | 5 | S/M | ss | PROJECT DOVE 6240041 | flex | 2026-02-17 | Z | 2026-02-10 | 120 | 0 | 0 | 120 | 0 | 310 |  | 1900-10-26 |  | 7
2026-02-19 | 76396 |  | 76396 | A | done | 2 | S | ss | PROJECT DOVE 6240041 |  | 2026-02-25 | Z | 2026-02-18 | 10 | 0 | 0 | 10 | 0 | 50 |  | 300 |  | 7
2026-02-19 | 83769 | w | 83769 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-02-19 | Z | 2026-02-13 | 20 | 0 | 0 | 20 | 0 | 30 |  | Celso weld |  | 6
2026-02-17 | 3829 | bth | LG-EA-01 | A | done | 22 | M/L |  | PROMEGA BTC 6250020 |  | 2026-02-18 | Z | 2026-01-13 | 450 | 20 | 60 | 510 | 0 | 1100 |  |  |  | 36
2026-02-17 | 3830 |  | LG-EA-02 | A | done | 20 | M/L |  | PROMEGA BTC 6250020 |  | 2026-02-18 | Z | 2026-01-13 | 270 | 0 | 220 | 490 | 0 | 1160 |  |  |  | 36
2026-02-17 | 3831 | bth | LG-EA-03 | A | done | 14 | M |  | PROMEGA BTC 6250020 |  | 2026-02-18 | Z | 2026-01-13 | 170 | 30 | 140 | 310 | 0 | 480 |  |  |  | 36
2026-02-17 | 3832 | bth | LG-EA-04 | A | done | 21 | M |  | PROMEGA BTC 6250020 |  | 2026-02-18 | Z | 2026-01-13 | 250 | 30 | 230 | 480 | 0 | 790 |  |  |  | 36
2026-02-17 | 3833 | bth | LG-EA-05 | A | done | 10 | S/M |  | PROMEGA BTC 6250020 |  | 2026-02-18 | Z | 2026-01-13 | 170 | 10 | 70 | 240 | 0 | 350 |  |  |  | 36
2026-02-18 | 3836 | bth | LG-SAMP-01 | A | done | 16 | M |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 190 | 60 | 130 | 320 | 0 | 490 |  |  |  | 33
2026-02-18 | 3837 | bth | LG-SAMP-02 | A | done | 16 | M |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 210 | 60 | 130 | 340 | 0 | 510 |  |  |  | 33
2026-02-18 | 3838 | bth | LG-SAMP-03 | A | done | 14 | M |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 180 | 100 | 70 | 250 | 0 | 420 |  |  |  | 33
2026-02-18 | 3839 | bth | LG-SAMP-04 | A | done | 6 | S/M |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 70 | 40 | 40 | 110 | 0 | 200 |  |  |  | 33
2026-02-18 | 3840 | bth | LG-SAMP-05 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 30 | 10 | 0 | 30 | 0 | 40 |  |  |  | 33
2026-02-18 | 3841 | bth | LG-SAMP-06 | A | done | 4 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 30 | 70 | 0 | 30 | 0 | 90 |  |  |  | 33
2026-02-18 | 3844 | bth | LG-SAMP-09 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 20 | 20 | 0 | 20 | 0 | 40 |  |  |  | 33
2026-02-18 | 3845 | bth | LG-SAMP-10 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 20 | 30 | 0 | 20 | 0 | 50 |  |  |  | 33
2026-02-18 | 3846 | bth | LG-SAMP-11 | A | done | 3 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 30 | 40 | 0 | 30 | 0 | 60 |  |  |  | 33
2026-02-18 | 3847 | bth | LG-SAMP-12 | A | done | 10 | S/M |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 120 | 110 | 0 | 120 | 0 | 250 |  |  |  | 33
2026-02-18 | 3848 | bth | LG-SAMP-13 | A | done | 9 | S/M |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 100 | 50 | 60 | 160 | 0 | 260 |  |  |  | 33
2026-02-18 | 3849 | bth | LG-SAMP-14 | A | done | 14 | M |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 190 | 40 | 110 | 300 | 0 | 430 |  |  |  | 33
2026-02-18 | 3850 | bth | LG-SAMP-15 | A | done | 8 | S/M |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 130 | 40 | 30 | 160 | 0 | 240 |  |  |  | 33
2026-02-18 | 3851 | bth | LG-SAMP-16 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 20 | 10 | 0 | 20 | 0 | 30 |  |  |  | 33
2026-02-17 | 3852 | bth | LG-SAMP-17 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 20 | 10 | 0 | 20 | 0 | 30 |  |  |  | 33
2026-02-18 | 3853 | bth | LG-SAMP-18 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 10 | 20 | 0 | 10 | 0 | 40 |  |  |  | 33
2026-02-17 | 3856 | bth | LG-SAMP-22 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-01-23 | 20 | 20 | 0 | 20 | 0 | 50 |  |  |  | 33
2026-02-17 | 81876 |  | 81876 | A | done | 5 | S/M |  | PROMEGA BTC 6250020 |  | 2026-02-18 | Z | 2026-02-16 | 110 | 0 | 0 | 110 | 0 | 270 | 18GA GALV | Misc |  | 2
2026-02-17 | 76436 |  | 76436 | A | done | 2 | S |  | QBE 4250054 | bird screen | 2026-02-18 | Z | 2026-02-16 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | IT Exhaust |  | 2
2026-02-19 | 76437 |  | 76437 | A | done | 2 | S |  | QBE 4250054 |  | 2026-02-20 | Z | 2026-02-19 | 30 | 0 | 0 | 30 | 0 | 30 | 26GA GALV |  |  | 1
2026-02-16 | 1132 | w | B- KE- 02 | A | done | 10 | M | ss | SHRINE 6240034 |  | 2026-02-16 | Z | 2026-02-03 | 230 | 0 | 0 | 230 | 0 | 490 |  |  |  | 13
2026-02-19 | 85464 | bth | 85464 | A | done | 4 | S |  | SHRINE 6240034 | paint black | 2026-02-23 | Z | 2026-02-12 | 30 | 70 | 0 | 30 | 20 | 90 | 24GA GALV | Misc |  | 11
2026-02-18 | 85465 |  | 85465 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-23 | Z | 2026-02-13 | 10 | 0 | 0 | 10 | 10 | 20 | 24GA GALV | Basement hall |  | 10
2026-02-19 | 85466 |  | 85466-67 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-03-02 | Z | 2026-02-18 | 150 | 0 | 0 | 150 | 0 | 200 | 24GA GALV | Misc level 1 |  | 12
2026-02-19 | 85468 |  | 85468 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-02-23 | Z | 2026-02-18 | 10 | 0 | 0 | 10 | 0 | 20 |  | Level 2 mock up |  | 5
2026-02-18 | 74778 | sp | 74778 | A | done | 4 | S |  | THERMO FISHER 10066879 |  | 2026-02-20 | Z | 2026-02-16 | 30 | 50 | 0 | 30 | 0 | 80 | 26GA GALV |  |  | 4
2026-02-19 | 74781 | sp | 74781 | A | done | 2 | S | pcd | THERMO FISHER 10067771 |  | 2026-02-20 | Z | 2026-02-18 | 20 | 20 | 0 | 20 | 0 | 50 | 24GA GALV | LAB 3309 |  | 2
2026-02-18 | 77070 |  | 77070-72 | A | done | 4 | S/M |  | TOMAH HEALTH 6250006 | paint black | 2026-02-19 | Z | 2026-02-13 | 90 | 0 | 0 | 90 | 30 | 130 |  | Ceiling tie ins |  | 6
2026-02-18 | 77073 |  | 77073 | A | done | 2 | S |  | TOMAH HEALTH 6250006 |  | 2026-02-19 | Z | 2026-02-13 | 30 | 0 | 0 | 30 | 0 | 60 |  | Roof exhaust |  | 6
2026-02-18 | 77074 |  | 77074 | A | done | 2 | S |  | TOMAH HEALTH 6250006 | paint black | 2026-02-20 | Z | 2026-02-18 | 10 | 0 | 0 | 10 | 10 | 20 | 24GA GALV | Prof develop tie in |  | 2
2026-02-18 | 77113 |  | 77113 | A | done | 2 | S |  | TOMAH HEALTH 6250006 | paint black | 2026-02-23 | Z | 2026-02-17 | 10 | 0 | 0 | 10 | 10 | 20 | 24GA GALV | Bathroom transfers |  | 6
2026-02-18 | 69086 |  | 69086 | A | done | 3 | S |  | UW AVRL 6240038 | 1" liner | 2026-02-18 | Z | 2026-02-16 | 60 | 0 | 0 | 60 | 60 | 80 |  | Transfers |  | 2
2026-02-18 | 74869 |  | 74869 | A | done | 10 | M/L |  | UW LEVY HALL 6230028 |  | 2026-02-24 | Z | 2026-02-11 | 250 | 0 | 0 | 250 | 0 | 980 |  | Sleeves |  | 13
2026-02-20 | 74878 |  | 74878 | A | done | 4 | S/M |  | UW LEVY HALL 6230028 | MOD | 2026-02-24 | Z | 2026-02-13 | 80 | 0 | 0 | 80 | 0 | 110 | 24GA GALV | LL Utility SA 1 |  | 11
2026-02-20 | 4338r |  | 4338r | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-24 | Z | 2026-02-20 | 10 | 30 | 0 | 10 | 0 | 50 | 24GA GALV | Remake |  | 4
2026-02-16 | 4367 |  | L3-RAMP 2 | A | done | 19 | M/L |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 200 | 0 | 270 | 470 | 0 | 1050 |  |  |  | 12 | 2026-03-10
2026-02-16 | 4368 |  | L3-RAMP 3 | A | done | 22 | M/L |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 270 | 0 | 270 | 540 | 0 | 1200 |  |  |  | 12 | 2026-03-10
2026-02-16 | 4369 |  | L3-RAMP 4 | A | done | 16 | M |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 320 | 0 | 60 | 380 | 0 | 630 |  |  |  | 12 | 2026-03-10
2026-02-17 | 4373 |  | L3-RAMP 8 | A | done | 14 | M |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 240 | 0 | 110 | 350 | 0 | 780 |  |  |  | 12 | 2026-03-10
2026-02-16 | 4374 |  | L3-RAMP 9 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 20 | 0 | 0 | 20 | 0 | 50 |  |  |  | 12 | 2026-03-10
2026-02-16 | 4375 |  | L3-RAMP 10 | A | done | 8 | M |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 180 | 0 | 0 | 180 | 0 | 420 |  |  |  | 12 | 2026-03-10
2026-02-16 | 4376 |  | L3-RAMP 11 | A | done | 24 | M/L |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 220 | 0 | 380 | 600 | 0 | 1220 |  |  |  | 12 | 2026-03-10
2026-02-16 | 4377 |  | L3-RAMP 12 | A | done | 28 | L |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 410 | 0 | 270 | 680 | 0 | 1610 |  |  |  | 12 | 2026-03-10
2026-02-16 | 4378 |  | L3-RAMP 13 | A | done | 10 | M |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 90 | 0 | 160 | 250 | 0 | 600 |  |  |  | 12 | 2026-03-10
2026-02-17 | 4379 |  | L3-RAMP 14 | A | done | 13 | M |  | UW STOUT 6250008 |  | 2026-02-17 | Z | 2026-02-05 | 150 | 0 | 170 | 320 | 0 | 770 |  |  |  | 12 | 2026-03-10
2026-02-17 | 4380 | bth | L3-EA 1 | A | done | 6 | S/M |  | UW STOUT 6250008 |  | 2026-02-20 | Z | 2026-02-10 | 20 | 130 | 0 | 20 | 0 | 140 |  |  |  | 10 | 2026-03-10
2026-02-17 | 4381 |  | L3-EA 2 | A | done | 4 | S/M |  | UW STOUT 6250008 |  | 2026-02-20 | Z | 2026-02-10 | 70 | 0 | 30 | 100 | 0 | 140 |  |  |  | 10 | 2026-03-10
2026-02-17 | 4382 | bth | L3-EA 3 | A | done | 8 | S/M |  | UW STOUT 6250008 |  | 2026-02-20 | Z | 2026-02-10 | 60 | 60 | 60 | 120 | 0 | 190 |  |  |  | 10 | 2026-03-10
2026-02-17 | 4383 | bth | L3-EA 4 | A | done | 5 | S/M |  | UW STOUT 6250008 |  | 2026-02-20 | Z | 2026-02-10 | 50 | 60 | 0 | 50 | 0 | 110 |  |  |  | 10 | 2026-03-10
2026-02-17 | 4384 |  | L3-EA 5 | A | done | 3 | S |  | UW STOUT 6250008 |  | 2026-02-20 | Z | 2026-02-10 | 60 | 0 | 0 | 60 | 0 | 100 |  |  |  | 10 | 2026-03-10
2026-02-19 | 84567 |  | 84567 | A | done | 2 | S |  | UW STOUT 6250008 | flex | 2026-03-03 | Z | 2026-02-16 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | FCU 19 |  | 15
2026-02-18 | 75421 |  | 75421 | A | done | 2 | S |  | WAUNAKEE 6230013 | 1" liner | 2026-02-20 | Z | 2026-02-16 | 50 | 0 | 0 | 50 | 30 | 80 | 24GA GALV | Grill box |  | 4
2026-02-20 | 75423 | w | 75423 | A | done | 6 | M | neal | WAUNAKEE 6230013 |  | 2026-02-27 | Z | 2026-02-16 | 140 | 0 | 0 | 140 | 0 | 380 | 18GA GALV | EBB raceway |  | 11
2026-02-17 | 75424 | w | 75424 | A | done | 2 | S/M | ss | WAUNAKEE 6230013 |  | 2026-02-27 | Z | 2026-02-16 | 50 | 0 | 0 | 50 | 0 | 140 |  | Ex hood shroud |  | 11
2026-02-17 | 75425 |  | 75425 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-02-20 | Z | 2026-02-16 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | Printers |  | 4
2026-02-20 | 10007 | w | 10007 | A | done | 2 | S | ss | WILDERNESS 10065544 |  | 2026-02-20 | Z | 2026-02-19 | 10 | 0 | 0 | 10 | 0 | 20 |  | Caps |  | 1
[6 empty] | 1009 | [13 empty] | 33250
[9 empty] | WEEK OF 2-23-2026 | [16 empty] | % Under 14
2026-02-24 | 2458 |  | 2458 | A | done | 2 | S | neal | ANTIGO 6250017 |  | 2026-03-23 | Z | 2026-02-09 | 30 | 0 | 0 | 30 | 0 | 70 | 18GA GALVANEAL | Gym hangers |  | 42 |  |  | 22.22%
2026-02-26 | 82795 |  | 82795,97-99,82801-02 | A | done | 118 | L |  | ANTIGO 6250017 | accu-flange | 2026-03-09 | Z | 2026-02-18 | 540 | 2230 | 180 | 720 | 110 | 5200 | 18GA GALV | 1st floor |  | 19
2026-02-25 | 82804 |  | 82804 | A | done | 22 | M/L |  | ANTIGO 6250017 | 1" liner | 2026-03-16 | Z | 2026-02-20 | 210 | 0 | 340 | 550 | 490 | 1060 | 22GA GALV | 1st floor area B |  | 24
2026-02-24 | 82805 |  | 82805 | A | done | 3 | S |  | ANTIGO 6250017 |  | 2026-02-26 | Z | 2026-02-23 | 10 | 50 | 0 | 10 | 0 | 70 |  | Flashing |  | 3
2026-02-24 | 82806 |  | 82806 | A | done | 2 | S |  | ANTIGO 6250017 |  | 2026-02-26 | Z | 2026-02-24 | 40 | 0 | 0 | 40 | 0 | 60 | 24GA GALV | Misc |  | 2
2026-02-25 | 82807 |  | 82807 | A | done | 2 | S |  | ANTIGO 6250017 |  | 2026-02-26 | Z | 2026-02-25 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALV |  |  | 1
2026-02-27 | 82811 |  | 82811 | A | done | 2 | S |  | ANTIGO 6250017 |  | 2026-03-02 | Z | 2026-02-26 | 20 | 0 | 0 | 20 | 0 | 60 | 16GA GALV | Floor sleeve |  | 4
2026-02-27 | 83776 |  | 83776 | A | done | 7 | M |  | ANTIGO 6250017 |  | 2026-02-27 | Z | 2026-02-26 | 170 | 0 | 0 | 170 | 0 | 360 | 18GA GALV |  |  | 1
2026-02-24 | 10000 |  | 58182-84 | A | done | 8 | M |  | BROOM ST 6240033 | rivet nuts | 2026-03-03 | Z | 2026-01-06 | 180 | 0 | 0 | 180 | 0 | 500 | 18GA GALV | 5th floor west |  | 56
2026-02-24 | 1573 | bth | UNIT 631 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 70 | 80 | 0 | 70 | 0 | 170 |  |  |  | 55
2026-02-24 | 1574 | bth | UNIT 632 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 70 | 80 | 0 | 70 | 0 | 170 | 26GA GALV |  |  | 55
2026-02-24 | 1575 |  | UNIT 633 M4.66 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 140 | 0 | 70 | 210 | 0 | 220 | 26GA GALV |  |  | 55
2026-02-23 | 1576 |  | UNIT 634 M4.67 | A | done | 15 | M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 170 | 0 | 190 | 360 | 0 | 420 | 26GA GALV |  |  | 55
2026-02-23 | 1577 |  | UNIT 635 M4.68 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  |  | 55
2026-02-23 | 1578 |  | UNIT 636 M4.69 | A | done | 4 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 80 | 20 | 0 | 80 | 0 | 110 | 26GA GALV |  |  | 55
2026-02-23 | 1579 |  | UNIT 637 M4.70 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 220 | 0 | 70 | 290 | 0 | 290 | 26GA GALV |  |  | 55
2026-02-23 | 1580 |  | UNIT 638 M4.71 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 160 | 0 | 120 | 280 | 0 | 270 | 26GA GALV |  |  | 55
2026-02-24 | 1581 |  | UNIT 639 M4.72 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 240 | 0 | 0 | 240 | 0 | 260 | 26GA GALV |  |  | 55
2026-02-23 | 1582 |  | UNIT 641 M4.73 | A | done | 3 | S |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 70 | 0 | 0 | 70 | 0 | 80 | 26GA GALV |  |  | 55
2026-02-24 | 1583 |  | UNIT 642 M4.74 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-07 | 190 | 0 | 20 | 210 | 0 | 220 | 26GA GALV |  |  | 55
2026-02-24 | 1610 |  | UNIT 500 M4.90 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 240 | 0 | 30 | 270 | 0 | 270 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-23 | 1611 |  | UNIT 501 M4.91 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 190 | 0 | 80 | 270 | 0 | 290 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-23 | 1612 |  | UNIT 503 M4.56 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1613 | bth | UNIT 505 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 150 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1614 | bth | UNIT 506 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1615 | bth | UNIT 507 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 150 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1616 | bth | UNIT 508 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 160 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1617 | bth | UNIT 509 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 150 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1618 | bth | UNIT 510 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1619 | bth | UNIT 511 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 150 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1620 | bth | UNIT 512 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-23 | 1621 |  | UNIT 514 M4.61 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-23 | 1622 |  | UNIT 515 M4.62 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1623 |  | UNIT 517 M4.63 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 100 | 0 | 90 | 190 | 0 | 180 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-23 | 1624 |  | UNIT 518 M4.92 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-01-20 | 230 | 0 | 60 | 290 | 0 | 300 | 26GA GALV |  |  | 42 | 2026-02-24
2026-02-24 | 1625 |  | UNIT 600 M4.90 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 190 | 0 | 80 | 270 | 0 | 270 | 26GA GALV |  |  | 49
2026-02-24 | 1626 |  | UNIT 601 M4.91 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 150 | 0 | 110 | 260 | 0 | 290 | 26GA GALV |  |  | 49
2026-02-25 | 1628 | bth | UNIT 605 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 160 | 26GA GALV |  |  | 49
2026-02-26 | 1629 | bth | UNIT 606 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 49
2026-02-26 | 1630 | bth | UNIT 607 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 150 | 26GA GALV |  |  | 49
2026-02-26 | 1631 | bth | UNIT 608 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 160 | 26GA GALV |  |  | 49
2026-02-26 | 1632 | bth | UNIT 609 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 160 | 26GA GALV |  |  | 49
2026-02-25 | 1633 | bth | UNIT 610 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 49
2026-02-26 | 1634 | bth | UNIT 611 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 150 | 26GA GALV |  |  | 49
2026-02-26 | 1635 | bth | UNIT 612 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 70 | 70 | 0 | 70 | 0 | 150 | 26GA GALV |  |  | 49
2026-02-25 | 1636 |  | UNIT 614 M4.61 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  |  | 49
2026-02-25 | 1637 |  | UNIT 615 M4.62 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 100 | 0 | 0 | 100 | 0 | 100 | 26GA GALV |  |  | 49
2026-02-25 | 1638 |  | UNIT 617 M4.63 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 100 | 0 | 90 | 190 | 0 | 180 | 26GA GALV |  |  | 49
2026-02-25 | 1639 |  | UNIT 618 M4.92 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 230 | 0 | 60 | 290 | 0 | 300 | 26GA GALV |  |  | 49
2026-02-24 | 1695 | bth | L1-RA-01 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-02-25 | Z | 2026-02-16 | 80 | 120 | 0 | 80 | 0 | 180 | 26GA GALV |  |  | 9
2026-02-23 | 1697 | bth | L1-RA-03 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-02-23 | Z | 2026-02-16 | 100 | 190 | 0 | 100 | 0 | 290 | 26GA GALV |  |  | 7
2026-02-24 | 1700 |  | DOAS-2 RISER L6-L10 | A | done | 15 | M |  | BROOM ST 6240033 |  | 2026-03-04 | Z | 2026-02-19 | 70 | 0 | 290 | 360 | 0 | 460 | 24GA GALV |  |  | 13
2026-02-24 | 1701 |  | STAIR 2 RISER L6-L10 | A | done | 20 | M |  | BROOM ST 6240033 |  | 2026-03-04 | Z | 2026-02-19 | 80 | 0 | 420 | 500 | 0 | 720 | 22GA GALV |  |  | 13
2026-02-24 | 1702 |  | DOAS-4 RISER L6-L9 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-03-04 | Z | 2026-02-19 | 70 | 0 | 170 | 240 | 0 | 250 | 26GA GALV |  |  | 13
2026-02-26 | 58182 |  | 58182,58184 | A | done | 8 | M |  | BROOM ST 6240033 | rivet nuts | 2026-03-10 | Z | 2026-02-10 | 180 | 0 | 0 | 180 | 0 | 500 | 18GA GALV | OA kits |  | 28
2026-02-27 | 58191 |  | 58191 | A | done | 3 | S/M |  | BROOM ST 6240033 | rivet nuts | 2026-03-03 | Z | 2026-02-12 | 60 | 0 | 0 | 60 | 0 | 170 | 18GA GALV | OA kits |  | 19
2026-02-25 | 58192 |  | 58192 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-02-24 | 20 | 0 | 0 | 20 | 0 | 30 | 26GA GALV | DOAS 1 |  | 7
2026-02-23 | 75051 |  | 75051 | A | done | 4 | S/M |  | BROOM ST 6240033 |  | 2026-02-24 | Z | 2026-02-23 | 80 | 0 | 0 | 80 | 0 | 120 | 26GA GALV | DOAS 4 |  | 1
2026-02-24 | 75052 |  | 75052 | A | done | 36 | M/L |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-02-24 | 900 | 0 | 0 | 900 | 0 | 1050 | 24GA GALV | Flashing |  | 7
2026-02-23 | 78262 |  | 78262 | A | done | 7 | S/M | neal | BROOM ST 6240033 | paint black | 2026-03-02 | Z | 2026-02-12 | 170 | 0 | 0 | 170 | 140 | 300 | 24GA GALV | L1 amenties |  | 18
2026-02-24 | 79500 | w | 79500 | A | done | 2 | S | ss | BROOM ST 6240033 |  | 2026-03-04 | Z | 2026-02-18 | 40 | 0 | 0 | 40 | 0 | 70 |  | Condensate pans |  | 14
2026-02-27 | 83775 |  | 83775 | A | done | 7 | S/M |  | BROOM ST 6240033 |  | 2026-02-27 | Z | 2026-02-26 | 170 | 0 | 0 | 170 | 0 | 280 | 20GA GALV |  |  | 1
2026-02-27 | 2006 |  | L1-A0.2-RA 20 | A | done | 36 | L | neal | DC6 6250027 | 1" liner,flex,bs | 2026-03-19 | Z | 2026-02-23 | 810 | 0 | 90 | 900 | 810 | 1710 | 22GA GALV |  |  | 24
2026-02-26 | 2009 |  | L1-A0.2-EA 23 | A | done | 14 | M | neal | DC6 6250027 | 1" liner,flex,bs | 2026-03-19 | Z | 2026-02-23 | 210 | 0 | 140 | 350 | 0 | 470 | 24GA GALV |  |  | 24
2026-02-27 | 2022 | bth | L1-A0.2-SALP 38 | A | done | 8 | S/M |  | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 100 | 100 | 0 | 100 | 0 | 250 | 24GA GALV |  |  | 24
2026-02-23 | 74124 |  | 74124 | A | done | 10 | S/M |  | DELLSHIRE 6240017 | 1" liner | 2026-02-24 | Z | 2026-02-23 | 250 | 0 | 0 | 250 | 50 | 350 |  | Mixed Reality |  | 1
2026-02-24 | 74220 | bth | 75220 | A | done | 2 | S |  | DELLSHIRE 6240017 |  | 2026-02-25 | Z | 2026-02-23 | 30 | 10 | 0 | 30 | 0 | 40 | 24GA GALV | Misc |  | 2
2026-02-25 | 56137 |  | 56137 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-02-26 | Z | 2026-02-24 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALV | Template |  | 2
2026-02-24 | 74401 |  | 74401 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-05 | Z | 2026-02-19 | 10 | 0 | 0 | 10 | 0 | 40 |  | Dryer venting |  | 14
2026-02-23 | 74402 | w | 74402 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-05 | Z | 2026-02-19 | 20 | 0 | 0 | 20 | 10 | 50 | 18GA GALV | Dryer venting |  | 14
2026-02-24 | 74876 | sp | 74876 | A | done | 5 | S/M | neal | GRANT ES 6250021 |  | 2026-03-09 | Z | 2026-02-19 | 20 | 100 | 0 | 20 | 0 | 130 | 24GA GALV | Storage room |  | 18
2026-02-26 | 77304 |  | 77304-07,77316,77320 | A | done | 51 | L |  | LAKE MILLS ES 6250012 | 2" liner | 2026-03-16 | Z | 2026-02-23 | 320 | 10 | 940 | 1260 | 770 | 1580 | 24GA GALV | HP's |  | 21
2026-02-26 | 77308 |  | 77308-09,77312 | A | done | 19 | M |  | LAKE MILLS ES 6250012 | 1" liner | 2026-03-16 | Z | 2026-02-23 | 170 | 0 | 300 | 470 | 230 | 580 | 24GA GALV | ERU 1 SA |  | 21
2026-02-26 | 77317 |  | 77317-19,77321-22 | A | done | 14 | M |  | LAKE MILLS ES 6250012 | 1" liner | 2026-03-16 | Z | 2026-02-23 | 340 | 0 | 0 | 340 | 290 | 500 | 24GA GALV | HP's |  | 21
2026-02-26 | 83773 |  | 83773 | A | done | 2 | S | neal | MONROE 62400178 |  | 2026-02-26 | Z | 2026-02-26 | 30 | 0 | 0 | 30 | 0 | 30 | 24GA GALVANEAL |  |  | 0
2026-02-24 | 74363 |  | 74363 | A | done | 2 | S/M | neal | MONROE 6240018 | spiralmate | 2026-02-26 | Z | 2026-02-09 | 50 | 0 | 0 | 50 | 0 | 160 |  | Woods DC RA |  | 17
2026-02-24 | 83640 |  | 83640 | A | done | 2 | S |  | MONROE 6240018 |  | 2026-02-26 | Z | 2026-02-10 | 30 | 0 | 0 | 30 | 0 | 50 |  | Grille extensions |  | 16
2026-02-23 | 83646 | w | 83646 | A | done | 2 | S | neal | MONROE 6240018 |  | 2026-03-03 | Z | 2026-02-18 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALV | Floor sweeps |  | 13
2026-02-24 | 83647 | sp | 83647 | A | done | 2 | S | neal | MONROE 6240018 |  | 2026-03-03 | Z | 2026-02-23 | 0 | 30 | 0 | 0 | 0 | 30 |  | DC drops |  | 8
2026-02-24 | 83648 |  | 83648 | A | done | 2 | S |  | MONROE 6240018 | flex | 2026-03-03 | Z | 2026-02-23 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV | 2nd floor hoods |  | 8
2026-02-25 | 74831 | w | 74831 | A | done | 2 | S | ss | OCTOPI 8250035 |  | 2026-02-26 | Z | 2026-02-25 | 10 | 0 | 0 | 10 | 0 | 20 |  | Drain |  | 1
2026-02-25 | 76651 |  | 76651-52 | A | done | 12 | M |  | PORTAGE MS 6250018 | 1" liner | 2026-03-05 | Z | 2026-02-23 | 280 | 0 | 0 | 280 | 90 | 380 | 24GA GALV | TA phase 1 |  | 10
2026-02-26 | 76303 |  | 76303 | A | done | 3 | S |  | PROJECT DOVE 6240041 | birdscreen, flex | 2026-03-04 | Z | 2026-02-12 | 60 | 0 | 0 | 60 | 0 | 90 | 24GA GALV | ERV |  | 20
2026-02-24 | 3857 | bth | LG-RA-1 | A | done | 10 | S/M |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 140 | 60 | 50 | 190 | 0 | 320 | 24GA GALV |  |  | 40
2026-02-24 | 3858 | sp | LG-RA-2 | A | done | 6 | S/M |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 30 | 110 | 0 | 30 | 0 | 140 | 24GA GALV |  |  | 40
2026-02-24 | 3859 | sp | LG-RA-3 | A | done | 4 | S |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 20 | 70 | 0 | 20 | 0 | 90 | 24GA GALV |  |  | 40
2026-02-24 | 3860 | bth | LG-RA-4 | A | done | 26 | M |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 310 | 170 | 150 | 460 | 0 | 790 | 24GA GALV |  |  | 40
2026-02-24 | 3861 | sp | LG-RA-5 | A | done | 4 | S |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 20 | 60 | 0 | 20 | 0 | 90 | 24GA GALV |  |  | 40
2026-02-24 | 3862 | sp | LG-RA-6 | A | done | 4 | S |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 10 | 70 | 0 | 10 | 0 | 70 | 24GA GALV |  |  | 40
2026-02-24 | 3863 | sp | LG-RA-7 | A | done | 7 | S/M |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 50 | 120 | 0 | 50 | 0 | 170 | 24GA GALV |  |  | 40
2026-02-24 | 3864 | bth | LG-RA-8 | A | done | 16 | M |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 80 | 230 | 70 | 150 | 0 | 410 | 24GA GALV |  |  | 40
2026-02-24 | 3865 | bth | LG-RA-9 | A | done | 22 | M |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 200 | 210 | 130 | 330 | 0 | 630 | 24GA GALV |  |  | 40
2026-02-24 | 3866 | bth | LG-RA-10 | A | done | 29 | M/L |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 280 | 190 | 240 | 520 | 0 | 930 | 24GA GALV |  |  | 40
2026-02-24 | 3867 | bth | LG-RA-11 | A | done | 9 | S/M |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 70 | 140 | 0 | 70 | 0 | 230 | 24GA GALV |  |  | 40
2026-02-24 | 3868 | sp | LG-RA-12 | A | done | 4 | S |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 20 | 70 | 0 | 20 | 0 | 90 | 24GA GALV |  |  | 40
2026-02-25 | 3869 | bth | LG-RA-13 | A | done | 4 | S |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 30 | 30 | 20 | 50 | 0 | 90 | 24GA GALV |  |  | 40
2026-02-25 | 3870 | bth | LG-RA-14 | A | done | 3 | S |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 30 | 40 | 0 | 30 | 0 | 70 | 24GA GALV |  |  | 40
2026-02-24 | 3871 | bth | LG-RA-15 | A | done | 7 | S/M |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-01-23 | 70 | 60 | 40 | 110 | 0 | 190 | 24GA GALV |  |  | 40
2026-02-27 | 3872 | sp | LG-EA-2 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 10 | 10 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 47
2026-02-27 | 3873 | sp | LG-EA-3 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 30 | 20 | 0 | 30 | 0 | 70 | 24GA GALV |  |  | 47
2026-02-27 | 3874 | bth | LG-EA-4 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 20 | 10 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 47
2026-02-27 | 3875 | sp | LG-EA-5 | A | done | 3 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 40 | 30 | 0 | 40 | 0 | 80 | 24GA GALV |  |  | 47
2026-02-27 | 3877 | sp | LG-EA-7 | A | done | 3 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 30 | 30 | 0 | 30 | 0 | 80 | 22GA GALV |  |  | 47
2026-02-27 | 3881 | sp | LG-EA-11 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 10 | 20 | 0 | 10 | 0 | 30 | 24GA GALV |  |  | 47
2026-02-27 | 3882 | sp | LG-EA-12 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 10 | 20 | 0 | 10 | 0 | 30 | 24GA GALV |  |  | 47
2026-02-27 | 3883 | sp | LG-EA-13 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 10 | 20 | 0 | 10 | 0 | 30 | 24GA GALV |  |  | 47
2026-02-24 | 81870 |  | 81870,74 | A | done | 21 | M/L |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-02-03 | 370 | 0 | 150 | 520 | 0 | 1090 | 18GA GALV | Penthouse supply |  | 29
2026-02-25 | 81877 |  | 81877 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-04 | Z | 2026-02-24 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV | Misc. |  | 8
2026-02-24 | 81880 |  | 81880 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-02-25 | Z | 2026-02-24 | 0 | 0 | 0 | 0 | 0 | 30 |  | Misc. |  | 1 |  |  | % Under 14
2026-02-27 | 1135 |  | SOUTH CHASE-EA-01 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-02-24 | 30 | 0 | 70 | 100 | 0 | 120 | 24GA GALV |  |  | 21 |  |  | 35.14%
2026-02-27 | 1136 |  | SOUTH CHASE-EA-02 | A | done | 4 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-02-24 | 20 | 0 | 70 | 90 | 0 | 100 | 24GA GALV |  |  | 21
2026-02-27 | 1143 |  | SOUTH CHASE-SAMP-02 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-02-24 | 30 | 0 | 30 | 60 | 0 | 60 | 24GA GALV |  |  | 21
2026-02-26 | 1149 |  | NORTH CHASE-EA-01 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-02-24 | 30 | 0 | 60 | 90 | 0 | 120 | 24GA GALV |  |  | 21
2026-02-26 | 1150 |  | NORTH CHASE-EA-02 | A | done | 4 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-02-24 | 20 | 0 | 60 | 80 | 0 | 90 | 24GA GALV |  |  | 21
2026-02-27 | 1154 |  | NORTH CHASE-RAMP-02 | A | done | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-02-24 | 20 | 0 | 90 | 110 | 90 | 180 | 24GA GALV |  |  | 21
2026-02-27 | 83777 |  | 83777 | A | done | 7 | S/M | neal | SHRINE 6240034 |  | 2026-02-27 | Z | 2026-02-26 | 170 | 0 | 0 | 170 | 0 | 280 | 20GA GALVANEAL |  |  | 1
2026-02-23 | 85469 |  | 85469 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-02 | Z | 2026-02-19 | 20 | 0 | 0 | 20 | 10 | 20 | 24GA GALV | Level 1 hall 124 RA |  | 11
2026-02-25 | 85470 |  | 85470 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-09 | Z | 2026-02-24 | 10 | 0 | 0 | 10 | 10 | 20 | 18GA GALV | Misc |  | 13
2026-02-27 | 85471 | w | 85471 | A | done | 2 | S | ss | SHRINE 6240034 |  | 2026-03-09 | Z | 2026-02-26 | 20 | 0 | 0 | 20 | 0 | 40 |  | Dishwasher |  | 11
2026-02-25 | 77075 |  | 77075 | A | done | 2 | S |  | TOMAH HEALTH 6250006 | paint black | 2026-03-03 | Z | 2026-02-24 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | Ceiling |  | 7
2026-02-24 | 74879 |  | 74879 | A | done | 2 | S |  | UW LEVY HALL 6230028 | 1" liner | 2026-03-03 | Z | 2026-02-18 | 10 | 0 | 0 | 10 | 10 | 20 | 24GA GALV | L2 classroom |  | 13
2026-02-23 | 4334r |  | 4334r | A | done | 19 | M |  | UW STOUT 6250008 |  | 2026-02-23 | Z | 2026-02-23 | 0 | 0 | 460 | 460 | 0 | 400 |  | remake |  | 0
2026-02-23 | 4385 |  | L5-SAMP 1 | A | done | 17 | M/L |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-02-11 | 200 | 0 | 220 | 420 | 0 | 960 |  |  |  | 27 | 2026-03-10
2026-02-23 | 4386 |  | L5-SAMP 2 | A | done | 15 | M/L |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-02-11 | 300 | 0 | 60 | 360 | 0 | 850 |  |  |  | 27 | 2026-03-10
2026-02-23 | 4387 |  | L5-SAMP 3 | A | done | 12 | M |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-02-11 | 230 | 0 | 60 | 290 | 0 | 660 |  |  |  | 27 | 2026-03-10
2026-02-23 | 4388 |  | L5-SAMP 4 | A | done | 8 | M |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-02-11 | 180 | 0 | 0 | 180 | 0 | 460 | 20GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4389 |  | L5-SAMP 5 | A | done | 25 | L |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-02-11 | 30 | 0 | 590 | 620 | 0 | 1350 | 20GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4390 |  | L5-SAMP 6 | A | done | 12 | M/L |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-02-11 | 280 | 0 | 0 | 280 | 0 | 820 | 18GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4391 |  | L3-TA 1 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 30 | 0 | 0 | 30 | 30 | 50 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4392 |  | L3-TA 2 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 40 | 0 | 0 | 40 | 30 | 60 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4393 |  | L3-TA 3 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 30 | 0 | 0 | 30 | 30 | 50 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4394 |  | L3-TA 4 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 30 | 0 | 0 | 30 | 30 | 50 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4395 |  | L3-TA 5 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 30 | 0 | 0 | 30 | 30 | 40 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4396 |  | L3-TA 6 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4397 |  | L3-TA 7 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 30 | 0 | 0 | 30 | 30 | 40 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4398 |  | L3-TA 8 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-23 | 4399 |  | L3-TA 9 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-10 | Z | 2026-02-11 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 27 | 2026-03-10
2026-02-27 | 83774 |  | 83774 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-02-27 | Z | 2026-02-26 | 170 | 0 | 0 | 170 | 0 | 200 | 24GA GALV |  |  | 1
2026-02-24 | 84566 | sp | 84566 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-03 | Z | 2026-02-16 | 10 | 10 | 0 | 10 | 0 | 20 | 24GA GALV | VAV outs |  | 15
2026-02-23 | 84569 |  | 84569 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-02-24 | Z | 2026-02-23 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | VAV 1-4-23 |  | 1
2026-02-25 | 84570 |  | 84570 | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-03-10 | Z | 2026-02-24 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | L4 RA 9 |  | 14
2026-02-26 | 84571 |  | 84571 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-02-25 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV | VAV 2-4-14 |  | 13
2026-02-27 | 84572 |  | 84572 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-02-26 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | Salp 4th |  | 12
2026-02-26 | 76119 |  | 76119-22 | A | done | 12 | M |  | UWP 6240031 |  | 2026-03-05 | Z | 2026-02-16 | 300 | 0 | 0 | 300 | 0 | 580 | 18GA GALV | Exhaust louver, EF 4, OA |  | 17
2026-02-25 | 75426 |  | 75426-28 | A | done | 6 | S/M |  | WAUNAKEE 6230013 | paint black | 2026-02-27 | Z | 2026-02-23 | 130 | 0 | 0 | 130 | 80 | 200 | 24GA GALV | RA outs |  | 4
2026-02-27 | 83779 |  | 83779 | A | done | 2 | S |  | WHC 8250008 |  | 2026-02-27 | Z | 2026-02-27 | 10 | 0 | 0 | 10 | 0 | 20 |  |  |  | 0
[6 empty] | 1180 | [13 empty] | 39490
[9 empty] | WEEK OF 3-2-2026 | [16 empty] | % Under 14
2026-03-05 | 82791 |  | 82791-92 | A | done | 37 | M/L | neal | ANTIGO 6250017 |  | 2026-03-23 | Z | 2026-02-09 | 160 | 760 | 0 | 160 | 0 | 1150 | 24GA GALVANEAL | Gym SA |  | 42 |  |  | 25.31%
2026-03-05 | 82803 |  | 82803 | A | done | 12 | M |  | ANTIGO 6250017 | 2" liner | 2026-03-16 | Z | 2026-02-20 | 180 | 0 | 100 | 280 | 250 | 470 | 22GA GALV | 1st floor area B |  | 24
2026-03-02 | 82810 |  | 82810 | A | done | 3 | S | neal | ANTIGO 6250017 |  | 2026-03-09 | Z | 2026-02-26 | 60 | 0 | 0 | 60 | 0 | 100 | 24GA GALVANEAL | BCU 1 |  | 11
2026-03-05 | 1627 |  | UNIT 603 M4.56 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-01-20 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  |  | 49
2026-03-04 | 1733 |  | LL1E-EA-01 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 110 | 0 | 0 | 110 | 0 | 140 | 26GA GALV |  |  | 3
2026-03-05 | 1734 |  | LL1E-EA-02 | A | done | 16 | M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 240 | 0 | 160 | 400 | 0 | 560 | 24GA GALV |  |  | 3
2026-03-04 | 1735 |  | LL1E-EA-03 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 120 | 0 | 150 | 270 | 0 | 330 | 26GA GALV |  |  | 3
2026-03-04 | 1736 |  | LL1E-EA-04 | A | done | 14 | M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 140 | 0 | 200 | 340 | 0 | 450 | 24GA GALV |  |  | 3
2026-03-04 | 1737 |  | LL1E-OA-01 | A | done | 17 | M/L |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 420 | 0 | 0 | 420 | 0 | 1030 | 18GA GALV |  |  | 3
2026-03-04 | 1738 |  | LL1E-OA-02 | A | done | 13 | M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 110 | 0 | 200 | 310 | 0 | 410 | 24GA GALV |  |  | 3
2026-03-04 | 1739 |  | LL1E-OA-03 | A | done | 28 | M/L |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 170 | 0 | 510 | 680 | 0 | 1050 | 20GA GALV |  |  | 3
2026-03-04 | 1740 |  | LL1E-RA-01 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 50 | 0 | 0 | 50 | 0 | 80 | 24GA GALV |  |  | 3
2026-03-04 | 1741 |  | LL1E-RA-02 | A | done | 4 | S/M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 60 | 0 | 30 | 90 | 0 | 120 | 24GA GALV |  |  | 3
2026-03-03 | 1742 |  | LL1E-SALP-01 | A | done | 7 | S/M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 90 | 0 | 70 | 160 | 0 | 160 | 26GA GALV |  |  | 3
2026-03-03 | 1743 |  | LL1E-SALP-02 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 100 | 0 | 170 | 270 | 0 | 260 | 26GA GALV |  |  | 3
2026-03-04 | 1744 |  | LL1E-SALP-03 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 150 | 0 | 0 | 150 | 0 | 330 | 20GA GALV |  |  | 3
2026-03-04 | 1745 |  | LL1E-SALP-04 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-03-05 | Z | 2026-03-02 | 120 | 0 | 120 | 240 | 0 | 280 | 26GA GALV |  |  | 3
2026-03-05 | 58194 |  | 58194 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-02-27 | 120 | 0 | 0 | 120 | 0 | 130 | 26GA GALV | Grille boxes |  | 18
2026-03-02 | 78264 | sp | 78264 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-10 | Z | 2026-02-27 | 10 | 30 | 0 | 10 | 0 | 40 | 24GA GALV |  |  | 11
2026-03-02 | 79535 | sp | 79535 | A | done | 21 | M |  | BROOM ST 6240033 |  | 2026-03-09 | Z | 2026-02-19 | 230 | 290 | 0 | 230 | 0 | 540 | 24GA GALV | East wp |  | 18
2026-03-03 | 87788 |  | 87788 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-03 | Z | 2026-03-02 | 30 | 0 | 0 | 30 | 0 | 90 | 18GA GALV |  |  | 1
2026-03-06 | 75604 | sp | 75604-05 | A | done | 10 | S/M |  | CAKE PARKWAY 4260007 |  | 2026-03-10 | Z | 2026-03-03 | 30 | 220 | 0 | 30 | 0 | 240 | 24GA GALV | Exhaust |  | 7
2026-03-02 | 2007 |  | L1-A0.2-RA 21 | A | done | 28 | M/L | neal | DC6 6250027 | 1" liner,flex,bs | 2026-03-19 | Z | 2026-02-23 | 420 | 0 | 260 | 680 | 580 | 1120 | 18GA GALVANEAL |  |  | 24
2026-03-03 | 2014 | bth | L1-A0.2-SAMP 12 | A | done | 15 | M | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 300 | 70 | 0 | 300 | 160 | 510 | 24GA GALV |  |  | 24
2026-03-04 | 2015 | bth | L1-A0.2-SALP 13 | A | done | 8 | S/M |  | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 130 | 20 | 50 | 180 | 70 | 270 | 24GA GALV |  |  | 24
2026-03-04 | 2016 | bth | L1-A0.2-SALP 14 | A | done | 7 | S/M |  | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 80 | 30 | 60 | 140 | 40 | 220 | 24GA GALV |  |  | 24
2026-03-06 | 2018 | bth | L1-A0.2-SALP 16 | A | done | 7 | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 130 | 20 | 20 | 150 | 60 | 230 | 24GA GALV |  |  | 24
2026-03-03 | 2020 | bth | L1-A0.2-SALP 18 | A | done | 4 | S/M |  | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 70 | 10 | 0 | 70 | 50 | 110 | 24GA GALV |  |  | 24
2026-03-05 | 2021 | bth | L1-A0.2-SALP 19 | A | done | 6 | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 60 | 10 | 70 | 130 | 40 | 210 | 24GA GALV |  |  | 24
2026-03-04 | 75702 | w | 75702 | A | done | 2 | S | ss | DC6 6250027 | birdscreen | 2026-03-23 | Z | 2026-02-20 | 30 | 0 | 0 | 30 | 0 | 90 |  | Roof exhuast |  | 31
2026-03-02 | 83778 |  | 83778 | A | done | 4 | S/M |  | DC6 6250027 |  | 2026-03-04 | Z | 2026-02-26 | 100 | 0 | 0 | 100 | 0 | 200 | 20GA GALV |  |  | 6
2026-03-05 | 56136 |  | 56136 | A | done | 2 | S | neal | DOC JDC 6240023 |  | 2026-03-23 | Z | 2026-02-23 | 40 | 0 | 0 | 40 | 0 | 90 |  | Gussets |  | 28
2026-03-05 | 56138 |  | 56138 | A | done | 4 | S/M |  | DOC JDC 6240023 | paint black | 2026-03-09 | Z | 2026-03-04 | 90 | 0 | 0 | 90 | 60 | 130 |  | Ceiling finish |  | 5
2026-03-05 | 56139 | bth | 56139 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-09 | Z | 2026-03-04 | 10 | 40 | 0 | 10 | 0 | 70 | 18GA GALVANEAL | Misc |  | 5
2026-03-05 | 74832 |  | 74832 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-09 | Z | 2026-03-04 | 10 | 0 | 0 | 10 | 0 | 20 | 22GA GALV | Dampers |  | 5
2026-03-03 | 77310 | sp | 77310 | A | done | 35 | M |  | LAKE MILLS ES 6250012 |  | 2026-03-16 | Z | 2026-02-23 | 50 | 810 | 0 | 50 | 0 | 790 | 24GA GALV | ERU 1 SA |  | 21
2026-03-03 | 83649 |  | 83649 | A | done | 2 | S | neal | MONROE 6240018 |  | 2026-03-04 | Z | 2026-03-03 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALVANEAL | BCU c section |  | 1
2026-03-05 | 83650 |  | 83650 | A | done | 2 | S |  | MONROE 6240018 |  | 2026-03-10 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 0 | 40 | 20GA GALVANEAL | Flashing |  | 6
2026-03-04 | 74783 | bth | 74783-85 | A | done | 16 | M |  | MPS 4260004 |  | 2026-03-06 | Z | 2026-03-02 | 80 | 240 | 60 | 140 | 0 | 360 | 26GA GALV | FCU 1-2 |  | 4
2026-03-05 | 74786 | bth | 74786-88 | A | done | 15 | M |  | MPS 4260004 |  | 2026-03-09 | Z | 2026-03-03 | 180 | 190 | 0 | 180 | 0 | 440 | 22GA GALV | FCU's |  | 6
2026-03-06 | 74794 |  | 74794 | A | done | 2 | S |  | MPS 4260004 |  | 2026-03-10 | Z | 2026-03-06 | 20 | 0 | 0 | 20 | 20 | 20 | 26GA GALV |  |  | 4
2026-03-05 | 76398 | w | 76398 | A | done | 7 | M | ss | PROJECT DOVE 6240041 |  | 2026-03-05 | Z | 2026-03-03 | 170 | 0 | 0 | 170 | 0 | 640 |  |  |  | 2
2026-03-02 | 3876 | sp | LG-EA-6 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 20 | 30 | 0 | 20 | 0 | 70 | 24GA GALV |  |  | 47
2026-03-02 | 3878 | sp | LG-EA-8 | A | done | 6 | S/M |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 30 | 110 | 0 | 30 | 0 | 180 | 24GA GALV |  |  | 47
2026-03-02 | 3879 | sp | LG-EA-9 | A | done | 5 | S/M |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 30 | 90 | 0 | 30 | 0 | 140 | 24GA GALV |  |  | 47
2026-03-03 | 3880 | sp | LG-EA-10 | A | done | 5 | S/M |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-01-23 | 50 | 70 | 0 | 50 | 0 | 160 | 22GA GALV |  |  | 47
2026-03-02 | 83782 |  | 83782 | A | done | 2 | S | ss | RCJ 6220018 |  | 2026-03-02 | Z | 2026-03-02 | 10 | 0 | 0 | 10 | 0 | 20 |  |  |  | 0
2026-03-04 | 03326 |  | 03326 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-05 | Z | 2026-03-03 | 10 | 0 | 0 | 10 | 0 | 20 |  |  |  | 2
2026-03-02 | 1139 |  | SOUTH CHASE-RAMP-01 | A | done | 3 | S/M |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-02-24 | 30 | 0 | 40 | 70 | 60 | 110 | 22GA GALV |  |  | 21
2026-03-04 | 1140 |  | SOUTH CHASE-RAMP-02 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-02-24 | 20 | 0 | 80 | 100 | 90 | 160 | 24GA GALV |  |  | 21
2026-03-02 | 1142 |  | SOUTH CHASE-SAMP-01 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-02-24 | 0 | 0 | 50 | 50 | 0 | 60 |  |  |  | 21
2026-03-05 | 1146 |  | SOUTH CHASE-SAMP-05 | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-02-24 | 0 | 0 | 50 | 50 | 40 | 80 |  |  |  | 21
2026-03-04 | 1147 |  | SOUTH CHASE-SAMP-06 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-02-24 | 0 | 0 | 90 | 90 | 80 | 170 | 20GA GALV |  |  | 21
2026-03-02 | 1157 |  | NORTH CHASE-SAMP-01 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-02-24 | 0 | 0 | 30 | 30 | 0 | 30 |  |  |  | 21
2026-03-02 | 1158 |  | NORTH CHASE-SAMP-02 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-02-24 | 0 | 0 | 70 | 70 | 0 | 90 |  |  |  | 21
2026-03-03 | 1161 |  | NORTH CHASE-SAMP-05 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-02-24 | 50 | 0 | 50 | 100 | 80 | 140 | 22GA GALV |  |  | 21
2026-03-04 | 1162 |  | NORTH CHASE-SAMP-06 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-02-24 | 0 | 0 | 90 | 90 | 90 | 150 |  |  |  | 21
2026-03-05 | 1168 |  | L2-EA-04 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 90 | 0 | 0 | 90 | 0 | 120 | 24GA GALV |  |  | 14
2026-03-06 | 1169 |  | L2-EA-05 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 60 | 0 | 0 | 60 | 0 | 70 | 26GA GALV |  |  | 14
2026-03-06 | 1176 |  | L2-EA-12 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 40 | 0 | 0 | 40 | 0 | 60 | 26GA GALV |  |  | 14
2026-03-05 | 1183 |  | L2-RA-01 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 14
2026-03-05 | 1184 |  | L2-SAMP-03 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 30 | 0 | 0 | 30 | 0 | 50 | 24GA GALV |  |  | 14
2026-03-05 | 1185 |  | L2-SAMP-05 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 14
2026-03-05 | 1186 |  | L2-SAMP-07 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 14
2026-03-05 | 1187 |  | L2-SAMP-09 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 40 | 0 | 0 | 40 | 30 | 60 |  |  |  | 14
2026-03-05 | 1188 |  | L2-SAMP-10 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV |  |  | 14
2026-03-05 | 1189 |  | L2-SAMP-12 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 14
2026-03-06 | 1190 |  | L2-SAMP-14 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV |  |  | 14
2026-03-06 | 1193 |  | L2-SAMP-20 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV |  |  | 14
2026-03-06 | 1195 |  | L2-SAMP-22 | A | done | 4 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 80 | 0 | 0 | 80 | 0 | 80 | 26GA GALV |  |  | 14
2026-03-05 | 85469r |  | 85469r | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-09 | Z | 2026-03-02 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | Remake |  | 7
2026-03-05 | 85473 |  | 85473 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-09 | Z | 2026-03-02 | 30 | 0 | 0 | 30 | 0 | 30 | 26GA GALV | L1 misc |  | 7
2026-03-04 | 85474 |  | 85474 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-09 | Z | 2026-03-02 | 40 | 0 | 0 | 40 | 0 | 60 | 24GA GALV | L2 misc |  | 7
2026-03-06 | 85475 |  | 85475 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 30 | 60 | 24GA GALV | B SAMP 07 |  | 13
2026-03-02 | 74782 | sp | 74782 | A | done | 2 | S |  | THERMO FISHER 10066879 |  | 2026-03-04 | Z | 2026-03-02 | 0 | 10 | 0 | 0 | 0 | 20 | 26GA GALV |  |  | 2
2026-03-02 | 74880 |  | 74880 | A | done | 2 | S |  | UW LEVY HALL 6230028 | birdscreen | 2026-03-10 | Z | 2026-03-02 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | LL utility room |  | 8
2026-03-05 | 78333 |  | 78333-34 | A | done | 3 | S/M |  | UW LEVY HALL 6230028 | 1" liner, paint black | 2026-03-10 | Z | 2026-03-03 | 70 | 0 | 0 | 70 | 60 | 110 | 24GA GALV | L5 Tie ins |  | 7
2026-03-05 | 78335 |  | 78335 | A | done | 2 | S |  | UW LEVY HALL 6230028 |  | 2026-03-10 | Z | 2026-03-03 | 10 | 0 | 0 | 10 | 0 | 50 | 22GA GALV | L1 class room |  | 7
2026-03-03 | 4400 |  | L3-TA 10 | A | done | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 60 | 0 | 0 | 60 | 60 | 100 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4401 |  | L3-TA 11 | A | done | 4 | S/M |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 100 | 0 | 0 | 100 | 90 | 170 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4402 |  | L3-TA 12 | A | done | 4 | S/M |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 80 | 0 | 0 | 80 | 70 | 140 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4403 |  | L3-TA 13 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4404 |  | L3-TA 14 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 50 | 0 | 0 | 50 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4405 |  | L3-TA 15 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4406 |  | L3-TA 16 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 30 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4407 |  | L3-TA 17 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 30 | 50 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4408 |  | L3-TA 18 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4409 |  | L3-TA 19 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 30 | 60 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4410 |  | L3-TA 20 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4411 |  | L3-TA 21 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 30 | 50 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4412 |  | L3-TA 22 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4413 |  | L3-TA 23 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 30 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4414 |  | L3-TA 24 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 30 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4415 |  | L3-TA 25 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4416 |  | L3-TA 26 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4417 |  | L3-TA 27 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4418 |  | L3-TA 28 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4419 |  | L3-TA 29 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4420 |  | L3-TA 30 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4421 |  | L3-TA 31 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4422 |  | L3-TA 32 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4423 |  | L3-TA 33 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4424 |  | L3-TA 34 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4425 |  | L3-TA 35 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4426 |  | L3-TA 36 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4427 |  | L3-TA 37 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4428 |  | L3-TA 38 | A | done | 4 | S/M |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 80 | 0 | 0 | 80 | 70 | 120 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4429 |  | L3-TA 39 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4430 |  | L3-TA 40 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 10 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4432 |  | L3-TA 42 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4433 |  | L3-TA 43 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4434 |  | L3-TA 44 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 30 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4435 |  | L3-TA 45 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4436 |  | L3-TA 46 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4437 |  | L3-TA 47 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4438 |  | L3-TA 48 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4439 |  | L3-TA 49 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4440 |  | L3-TA 50 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4441 |  | L3-TA 51 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4442 |  | L3-TA 52 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4443 |  | L3-TA 53 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-02 | 4444 |  | L3-TA 54 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 30 | 60 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-04 | 4445 |  | L3-TA 55 | A | done | 4 | S/M |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 80 | 0 | 0 | 80 | 80 | 130 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4446 |  | L3-TA 56 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 30 | 60 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4447 |  | L3-TA 57 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4448 |  | L3-TA 58 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 50 | 0 | 0 | 50 | 40 | 70 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-03 | 4449 |  | L3-TA 59 | A | done | 4 | S/M |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 80 | 0 | 0 | 80 | 80 | 140 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-04 | 4450 | bth | L3-SAT-1-3-20 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-03 | 4452 | bth | L3-SAT-1-3-22 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4453 | bth | L3-SAT-1-3-24 | A | done | 8 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-12 | Z | 2026-02-25 | 120 | 20 | 60 | 180 | 30 | 250 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-03 | 4454 |  | L3-SAT-1-3-25 | A | done | 10 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-12 | Z | 2026-02-25 | 70 | 0 | 160 | 230 | 30 | 290 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4455 | bth | L3-SAT-1-3-26 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-03 | 4456 |  | L3-SAT-1-3-27 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-05 | 4457 | bth | L3-SAT-1-3-28 | A | done | 3 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-12 | Z | 2026-02-25 | 40 | 20 | 0 | 40 | 30 | 70 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4458 | bth | L3-SAT-1-3-29 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-03 | 4459 |  | L3-SAT-1-3-30 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4460 | bth | L3-SAT-1-3-31 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-03 | 4461 |  | L3-SAT-1-3-32 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4462 | bth | L3-SAT-1-3-33 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4463 | bth | L3-SAT-1-3-34 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 40 | 10 | 0 | 40 | 0 | 60 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4464 | bth | L3-SAT-1-3-35 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 40 | 10 | 0 | 40 | 0 | 60 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4465 | bth | L3-SAT-1-3-36 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4466 | bth | L3-SAT-1-3-37 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4467 | bth | L3-SAT-1-3-38 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-04 | 4468 | bth | L3-SAT-1-3-39 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 20 | 0 | 20 | 0 | 50 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-03 | 4469 |  | L3-SAT-1-3-40 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 0 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-05 | 4470 | bth | L3-SAT-1-3-41 | A | done | 7 | S/M | neal | UW STOUT 6250008 | 1" liner | 2026-03-12 | Z | 2026-02-25 | 60 | 60 | 50 | 110 | 30 | 210 | 24GA GALVANEAL |  |  | 15 | 2026-04-01
2026-03-05 | 4471 | bth | L3-SAT-1-3-42 | A | done | 18 | M | neal | UW STOUT 6250008 | 1" liner | 2026-03-12 | Z | 2026-02-25 | 170 | 270 | 0 | 170 | 40 | 570 | 24GA GALVANEAL |  |  | 15 | 2026-04-01
2026-03-06 | 4473 | w | L2-SHAFT CEA E2 | A | done | 2 | S/M | ss | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 40 | 0 | 0 | 40 | 0 | 180 |  |  |  | 14
2026-03-05 | 4474 |  | L2-SHAFT EA B1 | A | done | 5 | S/M |  | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 40 | 0 | 70 | 110 | 0 | 130 | 24GA GALV |  |  | 14
2026-03-06 | 4475 | sp | L2-SHAFT EA E2 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 10 | 20 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 14
2026-03-06 | 4476 | sp | L2-SHAFT EA H1 | A | done | 2 | S | pcd | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 10 | 20 | 0 | 10 | 0 | 30 | 24GA PCD |  |  | 14
2026-03-04 | 4477 |  | L2-SHAFT EA H2 | A | done | 3 | S | pcd | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 40 | 0 | 30 | 70 | 0 | 100 | 24GA PCD |  |  | 14
2026-03-06 | 4478 |  | L2-SHAFT RA H1 | A | done | 18 | M/L | neal | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 450 | 0 | 0 | 450 | 0 | 1220 | 18GA GALV |  |  | 14
2026-03-06 | 4480 |  | L2-SHAFT SAMP F1 | A | done | 5 | S/M |  | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 50 | 0 | 60 | 110 | 0 | 250 | 18GA GALV |  |  | 14
2026-03-06 | 4481 |  | L2-SHAFT SAMP H1 | A | done | 11 | M |  | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 170 | 0 | 100 | 270 | 0 | 770 | 18GA GALV |  |  | 14
2026-03-04 | 84573 |  | 84573 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-02 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV | VAV reducers |  | 15
2026-03-05 | 85171 |  | 85171 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-10 | Z | 2026-03-04 | 30 | 0 | 0 | 30 | 0 | 60 | 22GA GALV | L3 SAMP 24 |  | 6
2026-03-02 | 83780 |  | 83780 | A | done | 2 | S |  | WAREHOUSE 2260009 |  | 2026-02-27 | Z | 2026-02-27 | 20 | 30 | 0 | 20 | 0 | 80 | 20GA GALV |  |  | 0
2026-03-02 | 73830 |  | 73830 | A | done | 2 | S |  | WAUNAKEE 6230013 | paint black | 2026-03-04 | Z | 2026-03-02 | 40 | 0 | 0 | 40 | 20 | 60 | 24GA GALV | RA outs |  | 2
2026-03-06 | 75429 |  | 75429 | A | done | 2 | S |  | WAUNAKEE 6230013 | paint gray | 2026-03-20 | Z | 2026-03-06 | 10 | 0 | 0 | 10 | 10 | 20 | 24GA GALV |  |  | 14
2026-03-06 | 95843 |  | 95843 | A | done | 5 | M |  | WHC 8250008 |  | 2026-03-10 | Z | 2026-03-04 | 120 | 0 | 0 | 120 | 0 | 390 | 18GA GALV | Roof drains |  | 6
[6 empty] | 756 | [13 empty] | 24530
[9 empty] | WEEK OF 3-9-2026 | [16 empty] | % Under 14
2026-03-10 | 87789 |  | 87789 | A | done | 2 | S |  | 121 E WILSON 6230024 |  | 2026-03-10 | Z | 2026-03-04 | 10 | 0 | 0 | 10 | 0 | 50 |  | Flat stock |  | 6 |  |  | 36.92%
2026-03-11 | 82813 |  | 82813-14 | A | done | 18 | M | neal | ANTIGO 6250017 |  | 2026-03-23 | Z | 2026-03-09 | 450 | 0 | 0 | 450 | 0 | 710 | 22GA GALV | Gym SA |  | 14
2026-03-12 | 82815 | w | 82815-17 | A | done | 5 | S/M | ss | ANTIGO 6250017 |  | 2026-03-16 | Z | 2026-03-09 | 120 | 0 | 0 | 120 | 0 | 300 |  | Dishwasher hood |  | 7
2026-03-13 | 1588 |  | UNIT 735 M4.68 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  |  | 75
2026-03-12 | 1769 | bth | UNIT 945 M4.117 | A | done | 18 | M |  | BROOM ST 6240033 |  | 2026-03-18 | Z | 2026-03-09 | 320 | 0 | 110 | 430 | 0 | 440 | 26GA GALV |  |  | 9
2026-03-12 | 1771 |  | UNIT 949 M4.119 | A | done | 18 | M |  | BROOM ST 6240033 |  | 2026-03-18 | Z | 2026-03-09 | 290 | 0 | 140 | 430 | 0 | 420 | 26GA GALV |  |  | 9
2026-03-12 | 1785 |  | STAIR 4 RISER L6-L10 | A | done | 18 | M |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-10 | 80 | 0 | 370 | 450 | 0 | 650 | 22GA GALV |  |  | 7
2026-03-12 | 1786 |  | STAIR 5 RISER L6-L10 | A | done | 13 | S/M |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-10 | 40 | 0 | 270 | 310 | 0 | 310 | 26GA GALV |  |  | 7
2026-03-12 | 1787 |  | TRASH EXHAUST L6W-L10W | A | done | 17 | M |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-10 | 80 | 0 | 340 | 420 | 0 | 580 | 26GA GALV |  |  | 7
2026-03-11 | 75053 |  | 75353 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-10 | 40 | 0 | 0 | 40 | 0 | 50 | 26GA GALV | Basement |  | 7
2026-03-11 | 79474 |  | 79474-75,79486 | A | done | 16 | M/L |  | BROOM ST 6240033 | rivet nuts | 2026-03-30 | Z | 2026-02-26 | 380 | 0 | 0 | 380 | 0 | 990 | 18GA GALV | OA Kits |  | 32
2026-03-12 | 79548 |  | 79548-49 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-12 | 110 | 0 | 0 | 110 | 0 | 180 | 26GA GALV | 141 Misc East |  | 5
2026-03-13 | 79550 | sp | 79550 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-12 | 0 | 50 | 0 | 0 | 0 | 40 |  | Misc spiral |  | 5
2026-03-11 | 80413 |  | 80413 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-10 | 20 | 0 | 0 | 20 | 0 | 30 | 26GA GALV | 853 plenum |  | 7
2026-03-10 | 84350 |  | 84350 | A | done | 2 | S | neal | CC E391/1 |  | 2026-03-13 | Z | 2026-03-10 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV |  |  | 3
2026-03-09 | 2008 |  | L1-A0.2-RA 22 | A | done | 28 | L | neal | DC6 6250027 | 1" liner,flex,bs | 2026-03-19 | Z | 2026-02-23 | 680 | 0 | 0 | 680 | 540 | 1400 | 18GA GALV |  |  | 24
2026-03-10 | 2010 |  | L1-A0.2-SAMP 8 | A | done | 41 | L | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 840 | 0 | 180 | 1020 | 880 | 2440 | 18GA GALV |  |  | 24
2026-03-10 | 2011 | bth | L1-A0.2-SAMP 9 | A | done | 30 | M/L | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 90 | 100 | 560 | 650 | 0 | 1150 | 24GA GALV |  |  | 24
2026-03-10 | 2012 | bth | L1-A0.2-SAMP 10 | A | done | 13 | M | neal | DC6 6250027 | 1" liner, flex, bs | 2026-03-19 | Z | 2026-02-23 | 150 | 30 | 130 | 280 | 240 | 430 | 24GA GALV |  |  | 24
2026-03-09 | 2013 | bth | L1-A0.2-SAMP 11 | A | done | 10 | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 90 | 50 | 100 | 190 | 70 | 300 | 24GA GALV |  |  | 24
2026-03-09 | 2017 | bth | L1-A0.2-SALP 15 | A | done | 5 | S/M | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 60 | 20 | 30 | 90 | 50 | 140 | 24GA GALV |  |  | 24
2026-03-09 | 2019 | bth | L1-A0.2-SALP 17 | A | done | 12 | M | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 140 | 30 | 130 | 270 | 240 | 420 | 24GA GALV |  |  | 24
2026-03-09 | 2023 | bth | L1-A0.2-SAMP 39 | A | done | 45 | L | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 280 | 110 | 730 | 1010 | 120 | 2160 | 24GA GALVANEAL |  |  | 24
2026-03-09 | 2024 | bth | L1-A0.2-SAMP 40 | A | done | 19 | M | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 110 | 40 | 310 | 420 | 380 | 620 | 24GA GALVANEAL |  |  | 24
2026-03-10 | 2025 | bth | L1-A0.2-SAMP 41 | A | done | 26 | M/L | neal | DC6 6250027 | 1" liner, flex | 2026-03-19 | Z | 2026-02-23 | 350 | 50 | 250 | 600 | 0 | 940 | 24GA GALV |  |  | 24
2026-03-12 | 2026 | bth | L1-A0.1-EA 1 | A | done | 23 | M |  | DC6 6250027 | VD, flex | 2026-03-23 | Z | 2026-02-25 | 120 | 130 | 320 | 440 | 0 | 690 | 24GA GALV |  |  | 26
2026-03-11 | 2027 | bth | L1-A0.1-SAMP 2 | A | done | 23 | M |  | DC6 6250027 | flex | 2026-03-23 | Z | 2026-02-25 | 240 | 30 | 290 | 530 | 0 | 720 | 24GA GALV |  |  | 26
2026-03-12 | 2028 |  | L1-A0.1-SALP 3 | A | done | 12 | M |  | DC6 6250027 | 1" liner,flex | 2026-03-23 | Z | 2026-02-25 | 160 | 0 | 130 | 290 | 50 | 390 | 24GA GALV |  |  | 26
2026-03-12 | 2029 | bth | L1-A0.1-SALP 4 | A | done | 13 | S/M |  | DC6 6250027 | 1" liner,flex | 2026-03-23 | Z | 2026-02-25 | 110 | 200 | 0 | 110 | 60 | 330 | 24GA GALV |  |  | 26
2026-03-11 | 2030 |  | L1-A0.1-SALP 6 | A | done | 9 | S/M |  | DC6 6250027 | 1" liner,flex | 2026-03-23 | Z | 2026-02-25 | 120 | 0 | 100 | 220 | 70 | 310 | 24GA GALV |  |  | 26
2026-03-12 | 2031 | bth | L1-A0.1-SALP 5 | A | done | 12 | M |  | DC6 6250027 | 1" liner,flex | 2026-03-23 | Z | 2026-02-25 | 130 | 50 | 110 | 240 | 80 | 380 | 24GA GALV |  |  | 26
2026-03-10 | 75751 |  | 75751-54 | A | done | 10 | M | neal | DC6 6250027 | 1" liner | 2026-03-19 | Z | 2026-03-03 | 240 | 0 | 0 | 240 | 160 | 440 | 18GA GALVANEAL | RTU's drops |  | 16
2026-03-13 | 2009x |  | 2009x | A | done | 3 | S |  | DC6 6250027 |  | 2026-03-13 | Z | 2026-03-13 | 70 | 0 | 0 | 70 | 0 | 90 | 24GA GALV | Damaged pieces |  | 0
2026-03-13 | 2024x |  | 2024x | A | done | 2 | S |  | DC6 6250027 |  | 2026-03-13 | Z | 2026-03-13 | 40 | 0 | 0 | 40 | 30 | 70 | 24GA GALVANEAL | Damaged pieces |  | 0
2026-03-09 | 56140 |  | 56140 | A | done | 2 | S | neal | DOC JDC 6240023 |  | 2026-03-10 | Z | 2026-03-09 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALVANEAL |  |  | 1
2026-03-13 | 56141 |  | 56141 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-13 | Z | 2026-03-13 | 20 | 0 | 0 | 20 | 0 | 40 | 24GA GALV | Zone Z OA |  | 0
2026-03-13 | 84318 |  | 84318 | A | done | 14 | M |  | FRANK&ANDREA 4250061 |  | 2026-03-18 | Z | 2026-03-12 | 180 | 0 | 150 | 330 | 0 | 360 | 26GA GALV | Mau SA/RA |  | 6
2026-03-12 | 74866 |  | 74866-67 | A | done | 6 | S/M |  | GRANT ES 6250021 | 1/2" armaflex | 2026-03-23 | Z | 2026-02-25 | 60 | 0 | 70 | 130 | 100 | 170 | 24GA GALV | Front office |  | 26
2026-03-10 | 77008 | sp | 77008,81346 | A | done | 7 | S/M |  | GRANT ES 6250021 |  | 2026-03-23 | Z | 2026-02-25 | 10 | 160 | 0 | 10 | 0 | 150 | 24GA GALV | Front office |  | 26
2026-03-12 | 77010 |  | 77010,74863-65 | A | done | 16 | M |  | GRANT ES 6250021 |  | 2026-03-23 | Z | 2026-02-25 | 100 | 0 | 280 | 380 | 0 | 490 | 24GA GALV | Front office |  | 26
2026-03-11 | 77011 |  | 77011-12,77018,77020,22-23 | A | done | 12 | M |  | GRANT ES 6250021 |  | 2026-03-23 | Z | 2026-03-04 | 110 | 0 | 180 | 290 | 0 | 370 | 24GA GALV | VAV's |  | 19
2026-03-10 | 77013 | sp | 77013 | A | done | 5 | S |  | GRANT ES 6250021 |  | 2026-03-23 | Z | 2026-03-04 | 10 | 100 | 0 | 10 | 0 | 100 | 24GA GALV | VAV's |  | 19
2026-03-10 | 77014 |  | 77014-17,77019,77021 | A | done | 8 | S/M |  | GRANT ES 6250021 |  | 2026-03-23 | Z | 2026-03-04 | 50 | 130 | 0 | 50 | 0 | 200 | 24GA GALV | VAV's |  | 19
2026-03-11 | 81343 |  | 81343,45,47-49,77006-07,09 | A | done | 24 | M/L |  | GRANT ES 6250021 |  | 2026-03-23 | Z | 2026-02-25 | 200 | 0 | 400 | 600 | 0 | 820 | 24GA GALV | Front office |  | 26
2026-03-10 | 81344 | bth | 81344,77005 | A | done | 4 | S |  | GRANT ES 6250021 |  | 2026-03-23 | Z | 2026-02-25 | 20 | 80 | 0 | 20 | 0 | 100 | 24GA GALV | Front office |  | 26
2026-03-09 | 77324 | sp | 77324-25 | A | done | 22 | M |  | LAKE MILLS ES 6250012 |  | 2026-03-23 | Z | 2026-03-02 | 60 | 470 | 0 | 60 | 0 | 510 | 24GA GALV | ERU 1 exhaust |  | 21
2026-03-11 | 83781 |  | 83781 | A | done | 2 | S |  | LAKE MILLS ES 6250012 | 2" liner | 2026-03-23 | Z | 2026-03-02 | 50 | 0 | 0 | 50 | 40 | 80 | 24GA GALV |  |  | 21
2026-03-09 | 74790 |  | 74790 | A | done | 2 | S |  | MPS 4260004 |  | 2026-03-11 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 0 | 50 | 26GA GALV | FCU's |  | 6
2026-03-09 | 74791 | sp | 74791-93 | A | done | 26 | M |  | MPS 4260004 |  | 2026-03-11 | Z | 2026-03-05 | 80 | 550 | 0 | 80 | 0 | 590 | 26GA GALV | FCU's |  | 6
2026-03-10 | 74795 | bth | 74795,74797-98 | A | done | 32 | M |  | MPS 4260004 |  | 2026-03-13 | Z | 2026-03-09 | 180 | 610 | 0 | 180 | 0 | 750 | 24GA GALV | FCU's |  | 4
2026-03-09 | 74796 |  | 74796 | A | done | 2 | S |  | MPS 4260004 |  | 2026-03-13 | Z | 2026-03-09 | 30 | 0 | 0 | 30 | 0 | 40 | 26GA GALV | FCU 1-06 RA |  | 4
2026-03-10 | 84310 |  | 84310 | A | done | 2 | S |  | MPS 4260004 |  | 2026-03-11 | Z | 2026-03-09 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV |  |  | 2
2026-03-12 | 84311 |  | 84311,84313 | A | done | 5 | S/M |  | MPS 4260004 |  | 2026-03-17 | Z | 2026-03-10 | 60 | 0 | 60 | 120 | 0 | 130 | 26GA GALV | FCU's |  | 7
2026-03-13 | 84315 |  | 84315 | A | done | 2 | S |  | MPS 4260004 |  | 2026-03-17 | Z | 2026-03-10 | 40 | 0 | 0 | 40 | 0 | 50 | 26GA GALV | EF1 |  | 7
2026-03-12 | 84316 | sp | 84316 | A | done | 10 | S/M |  | MPS 4260004 |  | 2026-03-17 | Z | 2026-03-10 | 30 | 200 | 0 | 30 | 0 | 210 | 26GA GALV | EF1 |  | 7
2026-03-11 | 75606 |  | 75606 | A | done | 10 | S/M |  | PLACON 4260005 | backdraft damper | 2026-03-19 | Z | 2026-03-05 | 130 | 0 | 100 | 230 | 0 | 220 | 26GA GALV | Exhaust |  | 14
2026-03-13 | 74573 | bth | 74573-76 | A | done | 29 | M/L | neal | PORTAGE MS 6250018 | spiralmate | 2026-03-20 | Z | 2026-02-20 | 170 | 550 | 0 | 170 | 0 | 1090 | 18GA GALVANEAL | AHU 2 SA gym |  | 28
2026-03-13 | 76390 |  | 76390-91 | A | done | 18 | M |  | PROJECT DOVE 6240041 |  | 2026-03-19 | Z | 2026-03-10 | 430 | 0 | 0 | 430 | 140 | 700 | 18GA GALV | SW 400 |  | 9
2026-03-09 | 76393 |  | 76393-95 | A | done | 42 | M/L |  | PROJECT DOVE 6240041 | 1" dual wall | 2026-03-19 | Z | 2026-03-04 | 1030 | 0 | 0 | 1030 | 0 | 1210 | 18GA GALV | SW 400 |  | 15 | DELETED
2026-03-10 | 76399 |  | 76399 | A | done | 2 | S | neal | PROJECT DOVE 6240041 |  | 2026-03-19 | Z | 2026-03-09 | 40 | 0 | 0 | 40 | 0 | 50 | 22GA GALVANEAL | Flashing 400 |  | 10
2026-03-11 | 3884 | sp | LG-TA-01 | C | done | 27 | M |  | PROMEGA BTC 6250020 |  | 2026-03-18 | Z | 2026-01-23 | 120 | 540 | 0 | 120 | 0 | 660 | 24GA GALV |  |  | 54
2026-03-11 | 3885 | sp | LG-TA-02 | C | done | 21 | M |  | PROMEGA BTC 6250020 |  | 2026-03-18 | Z | 2026-01-23 | 130 | 380 | 0 | 130 | 0 | 520 | 24GA GALV |  |  | 54
2026-03-09 | 81881 |  | 81881 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-11 | Z | 2026-03-09 | 20 | 0 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | 2
2026-03-10 | 1153 |  | NORTH CHASE-RAMP-01 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-02-24 | 30 | 0 | 50 | 80 | 60 | 120 | 24GA GALV |  |  | 21
2026-03-09 | 1191 |  | L2-SAMP-15 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 14
2026-03-09 | 1192 |  | L2-SAMP-18 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 14
2026-03-09 | 1194 |  | L2-SAMP-21 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 50 | 0 | 0 | 50 | 0 | 70 | 26GA GALV |  |  | 14
2026-03-09 | 1196 |  | L2-SAMP-23 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-03 | 20 | 0 | 0 | 20 | 0 | 30 | 26GA GALV |  |  | 14
2026-03-10 | 1197 |  | SOUTH CHASE-EA-02 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-04 | 50 | 0 | 30 | 80 | 0 | 110 | 24GA GALV |  |  | 13
2026-03-10 | 1198 |  | SOUTH CHASE-SAMP-02 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-04 | 30 | 0 | 30 | 60 | 0 | 70 | 24GA GALV |  |  | 13
2026-03-10 | 1199 |  | NORTH CHASE-RAMP-02 | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 10 | 20 | 24GA GALV |  |  | 13
2026-03-10 | 1200 |  | L3.5-SALP-01 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-09 | 90 | 0 | 0 | 90 | 0 | 140 | 22GA GALV |  |  | 8
2026-03-10 | 1201 |  | L3-SALP-02 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-09 | 90 | 0 | 0 | 90 | 0 | 150 | 22GA GALV |  |  | 8
2026-03-10 | 1202 |  | L3.5-SALP-03 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-09 | 90 | 0 | 0 | 90 | 0 | 150 | 22GA GALV |  |  | 8
2026-03-10 | 1203 |  | L3.5-SALP-04 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-17 | Z | 2026-03-09 | 90 | 0 | 0 | 90 | 0 | 150 | 22GA GALV |  |  | 8
2026-03-10 | 2000 |  | NORTH CHASE-SAMP-05 | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-03-17 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 13
2026-03-10 | 77211 | sp | 77211 | A | done | 2 | S |  | SWH MOB 6250015 |  | 2026-03-16 | Z | 2026-03-09 | 20 | 0 | 0 | 20 | 0 | 30 |  |  |  | 7
2026-03-09 | 74882 |  | 74882,74884 | A | done | 3 | S |  | UW LEVY HALL 6230028 | 1" liner | 2026-03-17 | Z | 2026-03-04 | 60 | 0 | 0 | 60 | 50 | 90 | 24GA GALV | L4 room 4188 |  | 13
2026-03-11 | 78334r |  | 78334r | A | done | 2 | S |  | UW LEVY HALL 6230028 |  | 2026-03-17 | Z | 2026-04-22 | 10 | 0 | 0 | 10 | 10 | 20 | 24GA GALV | Remake |  | -36
2026-03-10 | 4431 |  | L3-TA 41 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-12 | Z | 2026-02-16 | 30 | 0 | 0 | 30 | 30 | 40 | 24GA GALV |  |  | 24 | 2026-04-01
2026-03-10 | 4451 |  | L3-SAT-1-3-21 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-12 | Z | 2026-02-25 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | 15 | 2026-04-01
2026-03-09 | 4479 |  | L2-SHAFT RA J1 | A | done | 16 | M/L |  | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 200 | 0 | 190 | 390 | 0 | 840 | 18GA GALV |  |  | 14
2026-03-09 | 4482 |  | L2-SHAFT SAMP J1 | A | done | 14 | M/L |  | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 130 | 0 | 200 | 330 | 0 | 820 |  |  |  | 14
2026-03-12 | 4483 |  | L3-TA 115 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 50 | 0 | 0 | 50 | 40 | 70 | 24GA GALV |  |  | 20
2026-03-12 | 4484 |  | L3-TA 116 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 30 | 60 | 24GA GALV |  |  | 20
2026-03-10 | 4485 |  | L3-TA 117 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-10 | 4486 |  | L3-TA 118 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4487 |  | L3-TA 119 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 30 | 60 | 24GA GALV |  |  | 20
2026-03-10 | 4489 |  | L3-TA 121 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-10 | 4490 |  | L3-TA 122 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-10 | 4491 |  | L3-TA 123 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-10 | 4492 |  | L3-TA 124 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 20
2026-03-10 | 4493 |  | L3-TA 125 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-10 | 4494 |  | L3-TA 126 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-12 | 4495 |  | L3-TA 127 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-10 | 4496 |  | L3-TA 128 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-10 | 4497 |  | L3-TA 129 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 20
2026-03-10 | 4498 |  | L3-TA 130 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 20
2026-03-10 | 4499 |  | L3-TA 131 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 20
2026-03-12 | 4500 |  | L3-TA 132 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4501 |  | L3-TA 133 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4502 |  | L3-TA 134 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4503 |  | L3-TA 135 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4504 |  | L3-TA 136 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-12 | 4505 |  | L3-TA 137 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-12 | 4506 |  | L3-TA 138 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-12 | 4507 |  | L3-TA 139 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-12 | 4508 |  | L3-TA 140 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 20
2026-03-12 | 4509 |  | L3-TA 141 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4510 |  | L3-TA 142 | A | done | 4 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 90 | 0 | 0 | 90 | 70 | 200 | 22GA GALV |  |  | 20
2026-03-12 | 4511 |  | L3-TA 143 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 50 | 0 | 0 | 50 | 40 | 80 | 24GA GALV |  |  | 20
2026-03-12 | 4512 |  | L3-TA 144 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 50 | 0 | 0 | 50 | 40 | 80 | 24GA GALV |  |  | 20
2026-03-12 | 4513 |  | L3-TA 145 | A | done | 7 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 160 | 0 | 0 | 160 | 150 | 310 | 22GA GALV |  |  | 20
2026-03-12 | 4514 |  | L3-TA 146 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4515 |  | L3-TA 147 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 20
2026-03-12 | 4516 |  | L3-TA 148 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4517 |  | L3-TA 149 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 20
2026-03-12 | 4518 |  | L3-TA 150 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 20
2026-03-12 | 4519 |  | L3-TA 151 | A | done | 3 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 70 | 0 | 0 | 70 | 60 | 110 | 24GA GALV |  |  | 20
2026-03-12 | 4520 |  | L3-TA 152 | A | done | 4 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 80 | 0 | 0 | 80 | 70 | 110 | 24GA GALV |  |  | 20
2026-03-12 | 4521 |  | L3-TA 153 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV |  |  | 20
2026-03-12 | 77364 |  | 77364 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-13 | Z | 2026-03-12 | 10 | 0 | 0 | 10 | 0 | 30 | 20GA GALV | Roof main |  | 1
2026-03-12 | 84577 |  | 84577-80 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-17 | Z | 2026-03-10 | 40 | 0 | 0 | 40 | 30 | 70 | 24GA GALV | Outs |  | 7
2026-03-09 | 75430 | bth | 75430 | A | done | 2 | S | neal | WAUNAKEE 6230013 |  | 2026-03-13 | Z | 2026-03-09 | 10 | 10 | 0 | 10 | 0 | 20 | 24GA GALVANEAL | Printer |  | 4
2026-03-09 | 75431 |  | 75431 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-03-13 | Z | 2026-03-09 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV | 2A RA |  | 4
2026-03-12 | 75432 |  | 75432-36 | A | done | 5 | S/M |  | WAUNAKEE 6230013 | paint black | 2026-03-18 | Z | 2026-03-12 | 120 | 0 | 0 | 120 | 30 | 170 | 24GA GALV | Grille boxes |  | 6
2026-03-12 | 10009 |  | 95845 | A | done | 2 | S |  | WHC 8250008 |  | 2026-03-13 | Z | 2026-03-12 | 10 | 0 | 0 | 10 | 0 | 30 | 18GA GALV | Pipe shop |  | 1
2026-03-11 | 74833 |  | 74833 | A | done | 2 | S |  | WHC 8250008 |  | 2026-03-17 | Z | 2026-04-22 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALV | Pipe shop |  | -36
2026-03-11 | 95844 |  | 95844 | A | done | 2 | S |  | WHC 8250008 |  | 2026-03-17 | Z | 2026-04-22 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALV | Pipe shop |  | -36
2026-03-11 | 99005 |  | 99005 | A | done | 2 | S |  | WHC 8250008 |  | 2026-03-11 | Z | 2026-03-11 | 10 | 0 | 0 | 10 | 0 | 50 |  | Pipe shop caps |  | 0
[6 empty] | 1021 | [12 empty] | 33920
[9 empty] | WEEK OF 3-16-2026 | [16 empty] | % Under 14
2026-03-20 | 74838 |  | 74838 | A | done | 2 | S |  | 121 E WILSON 6230024 |  | 2026-03-24 | Z | 2026-03-17 | 10 | 0 | 0 | 10 | 0 | 20 | 20GA GALV |  |  | 7 |  |  | 46.74%
2026-03-20 | 82818 |  | 82818-19,21-24,28-29 | A | done | 53 | L |  | ANTIGO 6250017 | 1" liner, 2" liner | 2026-03-30 | Z | 2026-03-13 | 820 | 0 | 490 | 1310 | 1020 | 1730 | 24GA GALV |  |  | 17
2026-03-20 | 82820 |  | 82820,25,27 | A | done | 51 | M/L |  | ANTIGO 6250017 |  | 2026-03-30 | Z | 2026-03-13 | 130 | 1130 | 0 | 130 | 0 | 1290 | 24GA GALV | Area B |  | 17
2026-03-20 | 82833 |  | 82833 | A | done | 12 | M | neal | ANTIGO 6250017 |  | 2026-03-30 | Z | 2026-03-18 | 300 | 0 | 0 | 300 | 0 | 640 | 22GA GALV | AHU 1 RA |  | 12
2026-03-17 | 1584 | bth | UNIT 731 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 70 | 80 | 0 | 70 | 0 | 160 | 26GA GALV |  |  | 75
2026-03-17 | 1585 | bth | UNIT 732 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 70 | 80 | 0 | 70 | 0 | 170 | 26GA GALV |  |  | 75
2026-03-17 | 1586 |  | UNIT 733 M4.66 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 150 | 0 | 70 | 220 | 0 | 220 | 26GA GALV |  |  | 75
2026-03-17 | 1587 |  | UNIT 734 M4.67 | A | done | 15 | M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 170 | 0 | 190 | 360 | 0 | 420 | 24GA GALV |  |  | 75
2026-03-17 | 1589 |  | UNIT 736 M4.69 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 90 | 0 | 20 | 110 | 0 | 110 | 26GA GALV |  |  | 75
2026-03-17 | 1590 |  | UNIT 737 M4.70 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 220 | 0 | 70 | 290 | 0 | 290 | 26GA GALV |  |  | 75
2026-03-17 | 1591 |  | UNIT 738 M4.71 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 160 | 0 | 120 | 280 | 0 | 270 | 26GA GALV |  |  | 75
2026-03-17 | 1592 |  | UNIT 739 M4.72 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 240 | 0 | 0 | 240 | 0 | 260 | 26GA GALV |  |  | 75
2026-03-17 | 1593 |  | UNIT 741 M4.73 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 60 | 0 | 20 | 80 | 0 | 80 | 26GA GALV |  |  | 75
2026-03-17 | 1594 |  | UNIT 742 M4.74 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-03-23 | Z | 2026-01-07 | 190 | 0 | 20 | 210 | 0 | 220 | 26GA GALV |  |  | 75
2026-03-20 | 1703 |  | UNIT 700 M4.90 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 240 | 0 | 30 | 270 | 0 | 270 | 26GA GALV |  |  | 32
2026-03-20 | 1704 |  | UNIT 701 M4.91 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 150 | 0 | 110 | 260 | 0 | 290 | 26GA GALV |  |  | 32
2026-03-20 | 1705 |  | UNIT 703 M4.56 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  |  | 32
2026-03-20 | 1714 |  | UNIT 714 M4.61 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  |  | 32
2026-03-17 | 1768 | bth | UNIT 943 M4.116 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-03-18 | Z | 2026-03-09 | 60 | 0 | 60 | 120 | 0 | 110 | 26GA GALV |  |  | 9
2026-03-17 | 1770 |  | UNIT 947 M4.118 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-03-18 | Z | 2026-03-09 | 130 | 0 | 140 | 270 | 0 | 270 | 26GA GALV |  |  | 9
2026-03-17 | 1783 |  | DOAS-1 RISER L6-L10 | A | done | 16 | M |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-10 | 110 | 0 | 290 | 400 | 0 | 510 | 24GA GALV |  |  | 7
2026-03-17 | 1784 |  | JC EXHAUST L5W-L10W | A | done | 14 | S/M |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-10 | 80 | 0 | 270 | 350 | 0 | 350 | 26GA GALV |  |  | 7
2026-03-19 | 10008 |  | 58182 | A | done | 5 | S/M |  | BROOM ST 6240033 | rivet nuts | 2026-03-31 | Z | 2026-03-04 | 110 | 0 | 0 | 110 | 0 | 260 | 18GA GALV | OA kits |  | 27
2026-03-20 | 58187 |  | 58187 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-03-17 | 110 | 0 | 0 | 110 | 0 | 120 | 26GA GALV | West tower corridor duct |  | 14
2026-03-17 | 58195 |  | 58195 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-18 | Z | 2026-03-16 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | LL west |  | 2
2026-03-19 | 75056 |  | 75056 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-24 | Z | 2026-03-04 | 130 | 0 | 0 | 130 | 0 | 150 | 26GA GALV | East misc |  | 20
2026-03-17 | 75454 |  | 75054-55 | A | done | 3 | S/M |  | BROOM ST 6240033 | flex, birdscreen | 2026-03-18 | Z | 2026-03-12 | 70 | 0 | 0 | 70 | 0 | 140 | 18GA GALV | Mau 1, Doas 4, basement |  | 6
2026-03-17 | 78265 | sp | 78265 | A | done | 3 | S |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-04 | 40 | 20 | 0 | 40 | 0 | 60 | 26GA GALV | OA |  | 13
2026-03-17 | 78266 |  | 78266 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-17 | Z | 2026-03-04 | 10 | 0 | 0 | 10 | 0 | 20 |  | Exh air |  | 13
2026-03-19 | 78270 |  | 78270 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-24 | Z | 2026-03-18 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | OA |  | 6
2026-03-19 | 78271 | sp | 78271 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-24 | Z | 2026-03-18 | 10 | 10 | 0 | 10 | 0 | 20 |  | EA |  | 6
2026-03-17 | 1666r | sp | UNIT 855 M4.110r | A | done | 3 | S |  | BROOM ST 6240033 |  | 2026-03-20 | Z | 2026-03-12 | 10 | 60 | 0 | 10 | 0 | 70 | 24GA GALV | Remake |  | 8
2026-03-18 | 2000 | bth | L1-A0.4-SALP 33 | A | done | 8 | S/M | neal | DC6 6250027 | 1" liner, flex, bs | 2026-03-23 | Z | 2026-02-19 | 140 | 10 | 40 | 180 | 150 | 250 | 24GA GALVANEAL |  |  | 32 | 2026-03-23
2026-03-19 | 2001 |  | L1-A0.4-SALP 34 | A | done | 14 | M | neal | DC6 6250027 | 1" liner, flex, bs | 2026-03-23 | Z | 2026-02-19 | 120 | 0 | 210 | 330 | 70 | 450 | 24GA GALVANEAL |  |  | 32 | 2026-03-23
2026-03-19 | 2002 |  | L1-A0.4-SALP 35 | A | done | 20 | M | neal | DC6 6250027 | 1" liner, flex, bs | 2026-03-23 | Z | 2026-02-19 | 180 | 0 | 300 | 480 | 370 | 710 | 24GA GALVANEAL |  |  | 32 | 2026-03-23
2026-03-19 | 2003 | bth | L1-A0.4-SALP 36 | A | done | 27 | M/L | neal | DC6 6250027 | 1" liner, flex, bs | 2026-03-23 | Z | 2026-02-19 | 280 | 130 | 260 | 540 | 580 | 930 | 24GA GALVANEAL |  |  | 32 | 2026-03-23
2026-03-17 | 2004 |  | L1-A0.4-SALP 37 | A | done | 8 | M | neal | DC6 6250027 | 1" liner, flex, bs | 2026-03-23 | Z | 2026-02-19 | 200 | 0 | 0 | 200 | 180 | 360 | 24GA GALVANEAL |  |  | 32 | 2026-03-23
2026-03-18 | 2005 |  | L1-A0.4-SALP 42 | A | done | 8 | S/M | neal | DC6 6250027 |  | 2026-03-23 | Z | 2026-02-19 | 100 | 0 | 90 | 190 | 0 | 260 | 24GA GALVANEAL |  |  | 32 | 2026-03-23
2026-03-18 | 2032 |  | L1-A0.1-RA 7 | A | done | 20 | M |  | DC6 6250027 | 1" liner | 2026-03-23 | Z | 2026-02-25 | 490 | 0 | 0 | 490 | 420 | 800 | 24GA GALV |  |  | 26
2026-03-19 | 2033 | bth | L1-A0.3-SAMP 24 | A | done | 64 | L | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 470 | 180 | 930 | 1400 | 240 | 3050 | 18GA GALV |  |  | 32
2026-03-20 | 2034 | bth | L1-A0.3-SAMP 25 | A | done | 40 | L | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 260 | 190 | 540 | 800 | 600 | 1420 | 24GA GALVANEAL |  |  | 32
2026-03-19 | 2035 | bth | L1-A0.3-SAMP 26 | A | done | 22 | M | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 100 | 70 | 360 | 460 | 400 | 710 | 24GA GALVANEAL |  |  | 32
2026-03-19 | 2037 | bth | L1-A0.3-SALP 28 | A | done | 12 | M | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 160 | 30 | 110 | 270 | 210 | 410 | 24GA GALVANEAL |  |  | 32
2026-03-18 | 2038 | bth | L1-A0.3-SALP 29 | A | done | 5 | S/M | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 60 | 30 | 20 | 80 | 50 | 140 | 24GA GALV |  |  | 32
2026-03-17 | 2040 |  | L1-A0.3-SALP 31 | A | done | 8 | S/M | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 60 | 0 | 130 | 190 | 10 | 250 | 24GA GALV |  |  | 32
2026-03-18 | 2048 |  | L1-A2A-RTU 3 | A | done | 4 | S/M | neal | DC6 6250027 | 1" liner | 2026-03-19 | Z | 2026-03-17 | 100 | 0 | 0 | 100 | 90 | 150 | 24GA GALVANEAL |  |  | 2
2026-03-18 | 2049 |  | L1-A2A-RTU 2 | A | done | 2 | S | neal | DC6 6250027 | 1" liner | 2026-03-19 | Z | 2026-03-17 | 50 | 0 | 0 | 50 | 40 | 90 | 24GA GALVANEAL |  |  | 2
2026-03-19 | 2050 |  | L1-A0.2-RTU 1 | A | done | 3 | S/M | neal | DC6 6250027 | 1" liner | 2026-03-23 | Z | 2026-03-17 | 70 | 0 | 0 | 70 | 70 | 210 | 18GA GALVANEAL | Changed spool |  | 6
2026-03-20 | 53965 |  | 53965 | A | done | 8 | M |  | DC6 6250027 |  | 2026-03-23 | Z | 2026-03-17 | 190 | 0 | 0 | 190 | 0 | 410 | 18GA GALV | Backing |  | 6
2026-03-19 | 74403 |  | 74403 | A | done | 2 | S |  | DC6 6250027 |  | 2026-03-19 | Z | 2026-03-13 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV |  |  | 6
2026-03-19 | 56142 |  | 56142 | A | done | 2 | S | neal | DOC JDC 6240023 |  | 2026-03-20 | Z | 2026-03-19 | 20 | 0 | 0 | 20 | 0 | 40 | 24GA GALV | Misc outs |  | 1
2026-03-19 | 56143 |  | 56143 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-19 | Z | 2026-03-17 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | Penthouse HRU 2 |  | 2
2026-03-19 | 74837 |  | 74837 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-19 | Z | 2026-03-17 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 2
2026-03-17 | 84319 | sp | 84319 | A | done | 10 | S/M |  | FRANK&ANDREA 4250061 |  | 2026-03-18 | Z | 2026-03-12 | 60 | 170 | 0 | 60 | 0 | 210 | 26GA GALV | Mau SA |  | 6
2026-03-19 | 84320 |  | 84320 | A | done | 2 | S |  | FRANK&ANDREAS 4250061 |  | 2026-03-19 | Z | 2026-03-17 | 20 | 0 | 0 | 20 | 0 | 20 | 24GA GALV |  |  | 2
2026-03-19 | 74868 |  | 74868,71,72,74 | A | done | 15 | M |  | GRANT ES 6250021 |  | 2026-03-30 | Z | 2026-03-17 | 70 | 0 | 290 | 360 | 0 | 440 | 24GA GALV | Phase 6 |  | 13
2026-03-20 | 74870 | sp | 74870,73,75 | A | done | 19 | M |  | GRANT ES 6250021 |  | 2026-03-30 | Z | 2026-03-17 | 30 | 430 | 0 | 30 | 0 | 430 | 24GA GALV | Phase 6 |  | 13
2026-03-18 | 41843 | w | 41843 | A | done | 2 | S/M |  | MAUSTON R 6250019 |  | 2026-03-20 | Z | 2026-03-18 | 50 | 0 | 0 | 50 | 0 | 170 | 18GA GALV | Drain pan |  | 2
2026-03-19 | 74799 |  | 74799-74800 | A | done | 6 | S/M |  | MPS 4260004 |  | 2026-03-23 | Z | 2026-04-22 | 60 | 40 | 50 | 110 | 0 | 140 | 26GA GALV | FCU's |  | -30
2026-03-18 | 84312 | bth | 84312,84314 | A | done | 18 | M |  | MPS 4260004 |  | 2026-03-17 | Z | 2026-03-10 | 150 | 120 | 180 | 330 | 0 | 450 | 26GA GALV | FCU's |  | 7
2026-03-20 | 74834 | w | 74834 | A | done | 2 | S | ss | OCTOPI 8250035 |  | 2026-03-26 | Z | 2026-03-17 | 10 | 0 | 0 | 10 | 0 | 30 |  |  |  | 9
2026-03-17 | 74567 | bth | 74567-72 | A | done | 42 | M/L | neal | PORTAGE MS 6250018 | spiralmate | 2026-03-20 | Z | 2026-02-20 | 180 | 870 | 0 | 180 | 0 | 1260 | 24GA GALVANEAL | AHU 1 SA gym |  | 28
2026-03-18 | 76657 |  | 76657-59,76661 | A | done | 10 | S/M |  | PORTAGE MS 6250018 | paint black | 2026-03-19 | Z | 2026-03-12 | 200 | 0 | 30 | 230 | 20 | 310 | 24GA GALV | BCU 4 RA |  | 7
2026-03-20 | 76663 |  | 76663, 107727 | A | done | 2 | S |  | PORTAGE MS 6250018 |  | 2026-03-24 | Z | 2026-03-20 | 40 | 0 | 0 | 40 | 0 | 100 | 20GA GALV | RE curb cap |  | 4
2026-03-18 | 76660 | bth | 76660 | A | done | 4 | S |  | PORTAGE MS 6250018 | 2" liner | 2026-03-19 | Z | 2026-03-12 | 60 | 30 | 0 | 60 | 40 | 100 | 20GA GALV | BCU 4 SA |  | 7
2026-03-18 | 76405 | w | 76405-07 | A | done | 4 | S/M |  | PROJECT DOVE 6240041 | 1.5" liner | 2026-03-19 | Z | 2026-03-12 | 100 | 0 | 0 | 100 | 80 | 270 | 18GA GALV | Curbs |  | 7
2026-03-18 | 76408 | w | 76408-09 | A | done | 3 | S/M |  | PROJECT DOVE 6240041 | 1.5" liner | 2026-03-19 | Z | 2026-03-12 | 60 | 0 | 0 | 60 | 40 | 150 | 18GA GALV | Curb caps |  | 7
2026-03-17 | 76410 |  | 76410 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-03-19 | Z | 2026-03-12 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV |  |  | 7
2026-03-20 | 76411 |  | 76411 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-03-26 | Z | 2026-03-20 | 10 | 0 | 0 | 10 | 0 | 30 | 24GA GALV | 600 Cone flashing |  | 6
2026-03-18 | 3886 | sp | LG-TA-03 | A | done | 22 | M |  | PROMEGA BTC 6250020 |  | 2026-03-18 | Z | 2026-01-23 | 120 | 420 | 0 | 120 | 0 | 560 | 24GA GALV |  |  | 54
2026-03-18 | 81882 |  | 81882 | A | done | 32 | L |  | PROMEGA BTC 6250020 |  | 2026-03-25 | Z | 2026-03-12 | 380 | 0 | 420 | 800 | 0 | 1670 | 20GA GALV | Penthouse OA |  | 13
2026-03-17 | 81884 |  | 81884 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-23 | Z | 2026-03-17 | 10 | 0 | 0 | 10 | 0 | 30 |  | Misc |  | 6
2026-03-20 | 74836 | sp | 74836 | A | done | 2 | S | alum | SERVICE 10067969 | birdscreen | 2026-03-24 | Z | 2026-03-17 | 10 | 0 | 0 | 10 | 0 | 20 |  |  |  | 7
2026-03-18 | 10010 |  | 10010 | A | done | 3 | S | alum | SERVICE 10068247 | birdscreen | 2026-03-23 | Z | 2026-03-17 | 70 | 0 | 0 | 70 | 0 | 60 |  |  |  | 6
2026-03-17 | 85472 |  | 85472 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner, flex | 2026-03-17 | Z | 2026-03-02 | 100 | 0 | 0 | 100 | 80 | 140 | 24GA GALV | TF-1 |  | 15
2026-03-18 | 1139r |  | 1139r | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-03-23 | Z | 2026-03-18 | 30 | 0 | 0 | 30 | 20 | 40 | 22GA GALV |  |  | 5
2026-03-18 | 1202r |  | L3.5-SALP-03 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-03-20 | Z | 2026-03-18 | 90 | 0 | 0 | 90 | 0 | 150 | 22GA GALV | Remake |  | 2
2026-03-18 | 4472 | w | L2-SHAFT CEA E1 | A | done | 3 | S/M | ss | UW STOUT 6250008 |  | 2026-03-17 | Z | 2026-03-03 | 60 | 0 | 0 | 60 | 0 | 190 |  |  |  | 14
2026-03-20 | 4488 |  | L3-TA 120 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-24 | Z | 2026-03-04 | 30 | 0 | 0 | 30 | 30 | 50 | 24GA GALV |  |  | 20
2026-03-19 | 4525 |  | L3-TA 64 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 26
2026-03-19 | 4527 |  | L3-TA 66 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-18 | 4528 |  | L3-TA 67 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 26
2026-03-19 | 4534 |  | L3-TA 73 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 50 | 0 | 0 | 50 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-19 | 4536 |  | L3-TA 75 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 50 | 0 | 0 | 50 | 50 | 80 | 24GA GALV |  |  | 26
2026-03-19 | 4537 |  | L3-TA 76 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-19 | 4540 |  | L3-TA 79 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-19 | 4543 |  | L3-TA 82 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-19 | 4545 |  | L3-SAT-2-3-6 | A | done | 13 | M | neal | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-09 | 70 | 240 | 0 | 70 | 50 | 380 | 24GA GALVANEAL |  |  | 22
2026-03-19 | 4546 |  | L3-SAT-2-3-7 | A | done | 9 | S/M |  | UW STOUT 6250008 |  | 2026-03-31 | Z | 2026-03-09 | 80 | 100 | 40 | 120 | 30 | 250 | 24GA GALV |  |  | 22
2026-03-19 | 4550 |  | L3-SAT-2-3-10_2 | A | done | 4 | S |  | UW STOUT 6250008 |  | 2026-03-31 | Z | 2026-03-09 | 30 | 60 | 0 | 30 | 0 | 90 | 24GA GALV |  |  | 22
2026-03-17 | 84581 |  | 84581-82 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-24 | Z | 2026-03-12 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV |  |  | 12
2026-03-20 | 82951 | sp | 82951-52 | A | done | 5 | S/M |  | WHC 6250007 |  | 2026-03-31 | Z | 2026-03-09 | 110 | 0 | 0 | 110 | 50 | 180 | 22GA GALV | Duct sleeves LL |  | 22
[6 empty] | 860 | [12 empty] | 27850 | 27850
WEEK OF 3-23-2026
2026-03-23 | 82834 |  | 82834 | A | done | 10 | M |  | ANTIGO 6250017 | 2" liner | 2026-03-30 | Z | 2026-03-18 | 230 | 0 | 0 | 230 | 180 | 560 | 20GA GALV | AHU 1 SA |  | 12
2026-03-24 | 82835 |  | 82835 | A | done | 2 | S | neal | ANTIGO 6250017 |  | 2026-03-30 | Z | 2026-03-23 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALVANEAL | BCU 1 OA |  | 7
2026-03-24 | 1706 | bth | UNIT 705 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 32
2026-03-24 | 1707 | bth | UNIT 706 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 32
2026-03-23 | 1708 | bth | UNIT 707 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 32
2026-03-23 | 1709 | bth | UNIT 708 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 32
2026-03-23 | 1710 | bth | UNIT 709 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 32
2026-03-23 | 1711 | bth | UNIT 710 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 32
2026-03-23 | 1712 | bth | UNIT 711 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 32
2026-03-24 | 1713 | bth | UNIT 712 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 32
2026-03-24 | 1715 |  | UNIT 715 M4.62 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  |  | 32
2026-03-24 | 1716 |  | UNIT 717 M4.63 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 100 | 0 | 90 | 190 | 0 | 180 | 26GA GALV |  |  | 32
2026-03-24 | 1717 |  | UNIT 718 M4.92 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-02-27 | 230 | 0 | 60 | 290 | 0 | 300 | 26GA GALV |  |  | 32
2026-03-26 | 1746 | bth | UNIT 831 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 70 | 80 | 0 | 70 | 0 | 160 | 26GA GALV |  |  | 36
2026-03-26 | 1747 | bth | UNIT 832 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 70 | 80 | 0 | 70 | 0 | 170 | 26GA GALV |  |  | 36
2026-03-25 | 1748 |  | UNIT 833 M4.66 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 150 | 0 | 70 | 220 | 0 | 220 | 26GA GALV |  |  | 36
2026-03-25 | 1749 |  | UNIT 834 M4.67 | A | done | 15 | M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 170 | 0 | 190 | 360 | 0 | 420 | 26GA GALV |  |  | 36
2026-03-25 | 1750 |  | UNIT 835 M4.68 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  |  | 36
2026-03-25 | 1751 |  | UNIT 836 M4.69 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 90 | 0 | 20 | 110 | 0 | 110 | 26GA GALV |  |  | 36
2026-03-25 | 1752 |  | UNIT 837 M4.70 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 220 | 0 | 70 | 290 | 0 | 290 | 26GA GALV |  |  | 36
2026-03-25 | 1753 |  | UNIT 838 M4.71 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 160 | 0 | 120 | 280 | 0 | 270 | 26GA GALV |  |  | 36
2026-03-25 | 1754 |  | UNIT 839 M4.72 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 240 | 0 | 0 | 240 | 0 | 260 | 26GA GALV |  |  | 36
2026-03-25 | 1755 |  | UNIT 841 M4.73 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 60 | 0 | 20 | 80 | 0 | 80 | 26GA GALV |  |  | 36
2026-03-25 | 1756 |  | UNIT 842 M4.102 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-04-07 | Z | 2026-03-02 | 170 | 0 | 40 | 210 | 0 | 230 | 26GA GALV |  |  | 36
2026-03-25 | 10011 | sp | 58176-78 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-04-06 | Z | 2026-03-23 | 80 | 120 | 0 | 80 | 0 | 200 | 24GA GALV | West sleeves |  | 14
2026-03-26 | 10013 |  | 10013 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-04-06 | Z | 2026-03-23 | 120 | 0 | 0 | 120 | 0 | 130 | 26GA GALV | Grilles boxes |  | 14
2026-03-24 | 58196 |  | 58196 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-03-18 | 110 | 0 | 0 | 110 | 0 | 130 | 26GA GALV | West tower |  | 13
2026-03-23 | 58197 |  | 58197 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-03-20 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV |  |  | 11
2026-03-25 | 58198 |  | 58198 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-03-25 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | 5th west |  | 6
2026-03-24 | 75057 |  | 75057 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-30 | Z | 2026-03-23 | 20 | 0 | 0 | 20 | 0 | 30 | 26GA GALV | LL1 HRV 1 |  | 7
2026-03-25 | 75058 | sp | 75058 | A | done | 2 | S/M |  | BROOM ST 6240033 |  | 2026-03-26 | Z | 2026-03-25 | 20 | 0 | 0 | 20 | 0 | 130 | 18GA GALV | L15 A roof |  | 1
2026-03-25 | 75651 |  | 75651 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-03-24 | 20 | 0 | 0 | 20 | 0 | 20 | 26GA GALV | Stair 5 out |  | 7
2026-03-26 | 78272 |  | 78272 | A | done | 2 | S | alum | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-03-26 | 10 | 0 | 0 | 10 | 0 | 20 |  | Exhaust |  | 5
2026-03-24 | 87790 |  | 87790 | A | done | 2 | S |  | BROOM ST 6240033 | Pipe shop | 2026-03-30 | Z | 2026-03-24 | 10 | 0 | 0 | 10 | 0 | 20 |  | Pipe shop sleeves |  | 6
2026-03-23 | 76851 |  | 76851 | A | done | 2 | S |  | CHURCHILL 6250022 |  | 2026-03-27 | Z | 2026-03-20 | 20 | 0 | 0 | 20 | 0 | 50 | 18GA GALV | Spiral supports |  | 7
2026-03-23 | 6000 | sp | STAIR A RISER-SALP-01 | A | done | 12 | M |  | CHURCHILL HOTEL 6250022 |  | 2026-03-27 | Z | 2026-03-17 | 40 | 260 | 0 | 40 | 0 | 380 | 24GA GALV |  |  | 10
2026-03-23 | 6002 | bth | STAIR A RISER-SALP-03 | A | done | 8 | S/M |  | CHURCHILL HOTEL 6250022 |  | 2026-03-27 | Z | 2026-03-17 | 40 | 160 | 0 | 40 | 0 | 270 | 24GA GALV |  |  | 10
2026-03-23 | 6001 | sp | STAIR A RISER-SALP-02 | A | done | 6 | S/M |  | CHURCHILL HOTEL 6250022 |  | 2026-03-27 | Z | 2026-03-17 | 20 | 110 | 0 | 20 | 0 | 160 | 24GA GALV |  |  | 10
2026-03-23 | 2041 |  | L1-A0.3-RA 32 | A | done | 26 | M/L | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 640 | 0 | 0 | 640 | 570 | 1090 | 22GA GALVANEAL |  |  | 32
2026-03-24 | 2042 |  | L1-A3D-RTU 4 | A | done | 6 | S/M | neal | DC6 6250027 | 1" liner | 2026-04-02 | Z | 2026-03-17 | 140 | 0 | 0 | 140 | 120 | 310 | 20GA GALVANEAL |  |  | 16
2026-03-25 | 2043 |  | L1-A3D-RTU 5 | A | done | 6 | S/M | neal | DC6 6250027 | 1" liner | 2026-04-02 | Z | 2026-03-17 | 130 | 0 | 0 | 130 | 110 | 210 | 24GA GALVANEAL |  |  | 16
2026-03-24 | 2044 |  | L1-A3D-RTU 6 | A | done | 7 | S/M | neal | DC6 6250027 | 1" liner | 2026-04-02 | Z | 2026-03-17 | 160 | 0 | 0 | 160 | 140 | 230 | 24GA GALVANEAL |  |  | 16
2026-03-24 | 2045 |  | L1-A2D-RTU 7 | A | done | 6 | S/M | neal | DC6 6250027 | 1" liner | 2026-04-02 | Z | 2026-03-17 | 150 | 0 | 0 | 150 | 130 | 230 | 24GA GALVANEAL |  |  | 16
2026-03-24 | 2046 |  | L1-A2B-RTU 8 | A | done | 5 | S/M | neal | DC6 6250027 | 1" liner | 2026-04-02 | Z | 2026-03-17 | 120 | 0 | 0 | 120 | 110 | 190 | 24GA GALVANEAL |  |  | 16
2026-03-24 | 2047 |  | L1-A2B-RTU 9 | A | done | 6 | M | neal | DC6 6250027 | 1" liner | 2026-04-02 | Z | 2026-03-17 | 130 | 0 | 0 | 130 | 110 | 360 | 18GA GALVANEAL |  |  | 16
2026-03-23 | 53964 | sp | 53964 | A | done | 2 | S |  | DC6 6250027 |  | 2026-03-25 | Z | 2026-03-20 | 30 | 0 | 0 | 30 | 0 | 50 | 20GA GALV | Sleeves |  | 5
2026-03-26 | 75706 |  | 75706-07 | A | done | 10 | M | neal | DC6 6250027 | 1" liner | 2026-04-02 | Z | 2026-04-22 | 230 | 0 | 0 | 230 | 190 | 440 | 24GA GALVANEAL |  |  | -20
2026-03-23 | 75709 |  | 75709 | A | done | 2 | S |  | DC6 6250027 |  | 2026-03-25 | Z | 2026-03-23 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | EF 1 |  | 2
2026-03-26 | 56149 |  | 56149 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-04-01 | Z | 2026-03-26 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | Ceiling |  | 6
2026-03-26 | 56150 | w | 56150 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-27 | Z | 2026-03-25 | 20 | 0 | 0 | 20 | 10 | 40 | 18GA GALV | FE 2 on roof |  | 2
2026-03-25 | 74404 |  | 74404 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-03-27 | Z | 2026-03-25 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | Dryer venting |  | 2
2026-03-24 | 101381 | w | 101381 | A | done | 2 | S | ss | DOC JDC 6240023 |  | 2026-04-01 | Z | 2026-03-23 | 10 | 0 | 0 | 10 | 0 | 20 |  | Drain pan |  | 9
2026-03-24 | 75607 |  | 75607 | A | done | 2 | S |  | EVANSVILLE 4250049 | flex | 2026-03-25 | Z | 2026-03-24 | 10 | 0 | 0 | 10 | 10 | 20 | 26GA GALV | D137 |  | 1
2026-03-26 | 77578 |  | 77578 | A | done | 3 | S/M |  | EXACT 2250034 | 1" liner | 2026-04-08 | Z | 2026-03-25 | 70 | 0 | 0 | 70 | 70 | 110 | 24GA GALV | Transfer |  | 14
2026-03-27 | 77579 | sp | 77579-80 | A | done | 6 | S/M |  | EXACT 2250034 |  | 2026-04-08 | Z | 2026-03-25 | 50 | 90 | 0 | 50 | 0 | 170 | 24GA GALV | SA |  | 14
2026-03-23 | 77566 | sp | 77566 | A | done | 12 | S/M |  | EXACT 2260020 |  | 2026-03-30 | Z | 2026-03-17 | 50 | 240 | 0 | 50 | 0 | 340 | 24GA GALV | Spiral |  | 13
2026-03-26 | 77568 |  | 77568-71 | A | done | 21 | M |  | EXACT 2260020 |  | 2026-03-30 | Z | 2026-03-17 | 240 | 0 | 280 | 520 | 0 | 680 | 24GA GALV | EA |  | 13
2026-03-26 | 77572 |  | 77572-77 | A | done | 29 | M/L |  | EXACT 2260020 |  | 2026-03-30 | Z | 2026-03-19 | 250 | 0 | 470 | 720 | 0 | 910 | 24GA GALV | EA |  | 11
2026-03-25 | 41845 |  | 41845,47,49 | A | done | 10 | M |  | MASTON R 6250019 | flex, paint black | 2026-04-02 | Z | 2026-03-17 | 250 | 0 | 0 | 250 | 160 | 560 | 18GA GALV | Louver tie ins |  | 16
2026-03-24 | 64730 |  | 64730 | A | done | 2 | S | alum | MASTON R 6250019 |  | 2026-04-02 | Z | 2026-03-17 | 40 | 0 | 0 | 40 | 0 | 30 |  | EA |  | 16
2026-03-25 | 64732 |  | 64732,35,36,38 | A | done | 7 | S/M |  | MASTON R 6250019 |  | 2026-04-02 | Z | 2026-03-17 | 170 | 0 | 0 | 170 | 0 | 240 | 24GA GALV | RA, OA |  | 16
2026-03-25 | 64734 |  | 64734 | A | done | 3 | S/M | neal | MASTON R 6250019 | paint black | 2026-04-02 | Z | 2026-03-17 | 60 | 0 | 0 | 60 | 50 | 120 | 22GA GALVANEAL | DH |  | 16
2026-03-26 | 84321 |  | 84321 | A | done | 2 | S |  | MPS 4260004 |  | 2026-03-26 | Z | 2026-03-26 | 0 | 0 | 0 | 0 | 0 | 20 |  | DM's |  | 0
2026-03-24 | 74834 | w | 74834 | A | done | 2 | S | ss | OCTOPI 8250035 |  | 2026-03-24 | Z | 2026-03-23 | 10 | 0 | 0 | 10 | 0 | 20 |  | Remake |  | 1
2026-03-23 | 76412 |  | 76412 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-03-26 | Z | 2026-03-20 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALV | 600 |  | 6
2026-03-27 | 81883 |  | 81883 | A | done | 18 | M/L |  | PROMEGA BTC 6250020 |  | 2026-04-08 | Z | 2026-03-12 | 290 | 0 | 160 | 450 | 0 | 930 | 18GA GALV | Penthouse SA |  | 27
2026-03-23 | 81888 |  | 81888 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-03-25 | Z | 2026-03-20 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV | Misc |  | 5
2026-03-25 | 1137 |  | SOUTH CHASE-EA-03 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-02-24 | 0 | 0 | 60 | 60 | 0 | 70 |  |  |  | 41
2026-03-25 | 1138 |  | SOUTH CHASE-EA-04 | A | done | 4 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-02-24 | 20 | 0 | 60 | 80 | 0 | 80 | 26GA GALV |  |  | 41
2026-03-26 | 1141 |  | SOUTH CHASE-RAMP-03 | A | done | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-02-24 | 30 | 0 | 80 | 110 | 100 | 180 | 22GA GALV |  |  | 41
2026-03-26 | 1144 |  | SOUTH CHASE-SAMP-03 | A | done | 3 | S |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-02-24 | 10 | 0 | 50 | 60 | 50 | 90 | 24GA GALV |  |  | 41
2026-03-26 | 1145 |  | SOUTH CHASE-SAMP-04 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-02-24 | 0 | 0 | 80 | 80 | 70 | 110 |  |  |  | 41
2026-03-26 | 1148 |  | SOUTH CHASE-SAMP-07 | A | done | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-02-24 | 20 | 0 | 90 | 110 | 90 | 180 | 24GA GALV |  |  | 41
2026-03-25 | 1151 |  | NORTH CHASE-EA-03 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-02-24 | 10 | 0 | 50 | 60 | 0 | 80 | 24GA GALV |  |  | 41
2026-03-25 | 1152 |  | NORTH CHASE-EA-04 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-02-24 | 30 | 0 | 30 | 60 | 0 | 60 | 26GA GALV |  |  | 41
2026-03-26 | 1155 |  | NORTH CHASE-RAMP-03 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-02-24 | 0 | 0 | 90 | 90 | 80 | 160 |  |  |  | 41
2026-03-26 | 1156 |  | NORTH CHASE-RAMP-04 | A | done | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-02-24 | 110 | 0 | 0 | 110 | 90 | 170 | 22GA GALV |  |  | 41
2026-03-25 | 1159 |  | NORTH CHASE-SAMP-03 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-02-24 | 20 | 0 | 50 | 70 | 0 | 80 | 24GA GALV |  |  | 41
2026-03-26 | 1160 |  | NORTH CHASE-SAMP-04 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-02-24 | 50 | 0 | 0 | 50 | 0 | 60 | 24GA GALV |  |  | 41
2026-03-26 | 1163 |  | NORTH CHASE-SAMP-07 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-02-24 | 0 | 0 | 90 | 90 | 90 | 150 |  |  |  | 41
2026-03-26 | 1164 |  | NORTH CHASE-SAMP-08 | A | done | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-02-24 | 60 | 0 | 50 | 110 | 90 | 170 | 20GA GALV |  |  | 41
2026-03-26 | 1204 |  | L3-EA-01 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-03-25 | 60 | 0 | 0 | 60 | 0 | 60 | 26GA GALV |  |  | 12
2026-03-26 | 1205 |  | L3-EA-02 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-03-25 | 50 | 0 | 0 | 50 | 0 | 60 | 26GA GALV |  |  | 12
2026-03-27 | 1206 |  | L3-SALP-01 | A | done | 3 | S |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-03-25 | 60 | 0 | 0 | 60 | 50 | 70 | 26GA GALV |  |  | 12
2026-03-26 | 1207 |  | L3-SALP-02 | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-03-25 | 50 | 0 | 0 | 50 | 50 | 60 | 26GA GALV |  |  | 12
2026-03-26 | 1208 |  | L3-SALP-03 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-03-25 | 100 | 0 | 0 | 100 | 90 | 110 | 26GA GALV |  |  | 12
2026-03-26 | 1209 | bth | L3-SAMP-01 | A | done | 3 | S |  | SHRINE 6240034 | 1" liner | 2026-04-06 | Z | 2026-03-25 | 50 | 10 | 0 | 50 | 40 | 70 | 24GA GALV |  |  | 12
2026-03-24 | 85476 |  | 85476-77 | A | done | 7 | S/M |  | SHRINE 6240034 | flex | 2026-03-30 | Z | 2026-03-18 | 160 | 0 | 0 | 160 | 0 | 350 | 22GA GALV | ERV-1 |  | 12
2026-03-23 | 85478 |  | 85478-79 | A | done | 13 | M/L |  | SHRINE 6240034 | 1" liner | 2026-03-30 | Z | 2026-03-17 | 320 | 0 | 0 | 320 | 150 | 880 | 18GA GALV | Misc |  | 13
2026-03-23 | 81886 |  | 81886 | A | done | 2 | S |  | TERSO 2260019 |  | 2026-03-24 | Z | 2026-03-20 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV | Misc |  | 4
2026-03-27 | 81887 | sp | 81887 | A | done | 8 | S/M |  | TERSO 2260019 |  | 2026-04-13 | Z | 2026-03-23 | 20 | 180 | 0 | 20 | 0 | 250 | 24GA GALVANEAL | Misc |  | 21
2026-03-26 | 74903 | sp | 74903 | A | done | 18 | M |  | TOMAH HEALTH 2250045 |  | 2026-04-08 | Z | 2026-03-25 | 20 | 410 | 0 | 20 | 0 | 410 | 24GA GALV | Exhaust |  | 14
2026-03-25 | 69088 | w | 69088 | A | done | 2 | S | ss | UW AVRL |  | 2026-03-30 | Z | 2026-03-20 | 10 | 0 | 0 | 10 | 0 | 20 |  |  |  | 10
2026-03-26 | 78338 |  | 78338,78337 | A | done | 4 | S/M |  | UW LEVY HALL 6230028 | paint black | 2026-03-31 | Z | 2026-03-24 | 80 | 0 | 0 | 80 | 70 | 180 | 20GA GALV | OA louver tie ins |  | 7
2026-03-23 | 4522 |  | L3-TA 60 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-23 | 4523 |  | L3-TA 61 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 50 | 0 | 0 | 50 | 50 | 80 | 24GA GALV |  |  | 26
2026-03-23 | 4524 |  | L3-TA 62 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 50 | 0 | 0 | 50 | 50 | 80 | 24GA GALV |  |  | 26
2026-03-24 | 4526 |  | L3-TA 65 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-23 | 4529 |  | L3-TA 68 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV |  |  | 26
2026-03-23 | 4530 |  | L3-TA 69 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV |  |  | 26
2026-03-23 | 4531 |  | L3-TA 70 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 20 | 0 | 0 | 20 | 10 | 30 | 24GA GALV |  |  | 26
2026-03-23 | 4532 |  | L3-TA 71 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 30 | 60 | 24GA GALV |  |  | 26
2026-03-23 | 4533 |  | L3-TA 72 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 50 | 0 | 0 | 50 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-23 | 4535 |  | L3-TA 74 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 50 | 0 | 0 | 50 | 50 | 80 | 24GA GALV |  |  | 26
2026-03-23 | 4538 |  | L3-TA 77 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-23 | 4539 |  | L3-TA 78 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV |  |  | 26
2026-03-23 | 4541 |  | L3-TA 80 | A | done | 4 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 80 | 0 | 0 | 80 | 70 | 180 | 20GA GALV |  |  | 26
2026-03-24 | 4542 |  | L3-TA 81 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-05 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV |  |  | 26
2026-03-24 | 4544 |  | L3-SAT-2-3-5 | A | done | 12 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-09 | 110 | 100 | 90 | 200 | 30 | 340 | 24GA GALV |  |  | 22
2026-03-23 | 4547 |  | L3-SAT-2-3-8 | A | done | 6 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-09 | 60 | 40 | 30 | 90 | 30 | 150 | 24GA GALV |  |  | 22
2026-03-25 | 4548 |  | L3-SAT-2-3-9 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-31 | Z | 2026-03-09 | 20 | 20 | 0 | 20 | 0 | 60 | 24GA GALVANEAL |  |  | 22
2026-03-23 | 4549 |  | L3-SAT-2-3-10_1 | A | done | 10 | S/M | neal | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-09 | 120 | 20 | 90 | 210 | 40 | 310 | 24GA GALV |  |  | 22
2026-03-24 | 4551 |  | L3-SAT-2-3-11 | A | done | 5 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-09 | 80 | 40 | 0 | 80 | 30 | 140 | 24GA GALV |  |  | 22
2026-03-24 | 4552 |  | L3-SAT-2-3-16_1 | A | done | 16 | M | neal | UW STOUT 6250008 | 1" liner | 2026-03-31 | Z | 2026-03-09 | 260 | 0 | 130 | 390 | 40 | 530 | 24GA GALVANEAL |  |  | 22
2026-03-24 | 4553 |  | L3-SAT-2-3-16_2 | A | done | 15 | M | neal | UW STOUT 6250008 |  | 2026-03-31 | Z | 2026-03-09 | 370 | 0 | 0 | 370 | 0 | 510 | 24GA GALV |  |  | 22
2026-03-24 | 4589 |  | L3-TA 83 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-23 | 4590 |  | L3-TA 84 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4591 |  | L3-TA 85 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4592 |  | L3-TA 86 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4593 |  | L3-TA 87 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4594 |  | L3-TA 88 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-23 | 4596 |  | L3-TA 90 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4597 |  | L3-TA 91 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4598 |  | L3-TA 92 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 50 | 0 | 0 | 50 | 40 | 90 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4599 |  | L3-TA 93 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4600 |  | L3-TA 94 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 50 | 0 | 0 | 50 | 40 | 100 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4601 |  | L3-TA 95 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4602 |  | L3-TA 96 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 30 | 60 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4603 |  | L3-TA 97 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 30 | 50 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4604 |  | L3-TA 98 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4605 |  | L3-TA 99 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 40 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4606 |  | L3-TA 100 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4607 |  | L3-TA 101 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4608 |  | L3-TA 102 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 50 | 0 | 0 | 50 | 40 | 70 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4609 |  | L3-TA 103 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4610 |  | L3-TA 104 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 30 | 50 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4611 |  | L3-TA 105 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4612 |  | L3-TA 106 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4613 |  | L3-TA 107 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4614 |  | L3-TA 108 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4615 |  | L3-TA 109 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4616 |  | L3-TA 110 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4617 |  | L3-TA 111 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 40 | 0 | 0 | 40 | 40 | 70 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4618 |  | L3-TA 112 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 50 | 0 | 0 | 50 | 50 | 70 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4619 |  | L3-TA 113 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 50 | 0 | 0 | 50 | 40 | 70 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4620 |  | L3-TA 114 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 50 | 0 | 0 | 50 | 40 | 70 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4621 |  | L3-TA 154 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 30 | 0 | 0 | 30 | 30 | 70 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-24 | 4622 |  | L3-TA 155 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 30 | 0 | 0 | 30 | 30 | 60 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-03-26 | 4678 |  | L2-SAMP 02 | A | done | 24 | M/L |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 150 | 60 | 370 | 520 | 0 | 980 | 20GA GALV |  |  | 18
2026-03-26 | 4679 |  | L2-SAMP 03 | A | done | 11 | M |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 40 | 60 | 160 | 200 | 0 | 460 | 20GA GALV |  |  | 18
2026-03-26 | 4680 |  | L2-SAMP 04 | A | done | 17 | M/L |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 100 | 50 | 270 | 370 | 0 | 830 | 20GA GALV |  |  | 18
2026-03-27 | 4681 |  | L2-SAMP 05 | A | done | 14 | M |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 100 | 20 | 220 | 320 | 0 | 580 | 24GA GALV |  |  | 18
2026-03-26 | 4682 |  | L2-SAMP 06 | A | done | 14 | M |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 60 | 90 | 190 | 250 | 0 | 520 | 24GA GALV |  |  | 18
2026-03-26 | 4684 |  | L2-SAMP 08 | A | done | 11 | M |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 110 | 70 | 80 | 190 | 0 | 400 | 20GA GALV |  |  | 18
2026-03-26 | 4685 |  | L2-SAMP 09 | A | done | 15 | M |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 30 | 30 | 310 | 340 | 0 | 760 | 24GA GALV |  |  | 18
2026-03-25 | 4688 |  | L1-SHAFT SAMP C1 | A | done | 6 | M |  | UW STOUT 6250008 |  | 2026-03-31 | Z | 2026-03-24 | 90 | 0 | 60 | 150 | 0 | 370 | 18GA GALV |  |  | 7
2026-03-24 | 10014 |  | 10014, prefab hangers | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-03-30 | Z | 2026-03-24 | 10 | 0 | 0 | 10 | 0 | 80 | 18GA GALVANEAL | Duct hangers |  | 6
2026-03-26 | 84584 |  | 84584 | A | done | 2 | S |  | UW STOUT 6250008 | paint black | 2026-04-07 | Z | 2026-03-25 | 40 | 0 | 0 | 40 | 50 | 70 | 24GA GALV | 4th BR |  | 13
2026-03-26 | 76106 |  | 76106-11 | A | done | 40 | L |  | UWP 6240021 |  | 2026-04-02 | Z | 2026-02-04 | 690 | 0 | 290 | 980 | 20 | 2720 | 24GA GALV |  |  | 57
2026-03-26 | 76123 |  | 76123 | A | done | 2 | S |  | UWP 6240021 | 2" rigid liner | 2026-04-09 | Z | 2026-02-17 | 30 | 0 | 0 | 30 | 30 | 100 | 18GA GALV | Roof curb caps |  | 51
2026-03-25 | 76124 |  | 76124 | A | done | 2 | S |  | UWP 6240021 |  | 2026-04-09 | Z | 2026-03-02 | 40 | 0 | 0 | 40 | 0 | 80 | 20GA GALV | Caps |  | 38
2026-03-26 | 76125 |  | 76125 | A | done | 2 | S |  | UWP 6240021 | 1" liner, paint black | 2026-04-09 | Z | 2026-03-20 | 10 | 0 | 0 | 10 | 10 | 20 | 24GA GALV | Tfer duct |  | 20
2026-03-26 | 76106r |  | 76106r | A | done | 2 | S/M |  | UWP 6240021 |  | 2026-04-02 | Z | 2026-03-24 | 50 | 0 | 0 | 50 | 0 | 140 | 20GA GALV | Remake |  | 9
2026-03-27 | 76110r |  | 76110r | A | done | 2 | S/M |  | UWP 6240021 |  | 2026-04-02 | Z | 2026-03-25 | 50 | 0 | 0 | 50 | 0 | 140 | 20GA GALV | Remake |  | 8
[6 empty] | 893 | [12 empty] | 30840
WEEK OF 3-30-2026
2026-03-31 | 82838 |  | 82838 | A | done | 16 | M |  | ANTIGO 6250017 | 2" liner, 1" liner | 2026-04-13 | Z | 2026-03-25 | 290 | 0 | 90 | 380 | 260 | 530 | 24GA GALV | V-10,V-12,V-14 |  | 19
2026-04-01 | 82841 |  | 82841 | A | done | 21 | L | neal | ANTIGO 6250017 | 2" liner, 1" liner | 2026-04-13 | Z | 2026-03-30 | 410 | 0 | 110 | 520 | 470 | 1370 | 18GA GALV | 1st floor area B |  | 14
2026-03-31 | 82843 |  | 82843 | A | done | 2 | S |  | ANTIGO 6250017 |  | 2026-04-06 | Z | 2026-03-30 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALV |  |  | 7
2026-04-01 | 320560 |  | 320560 | A | done | 2 | S |  | ANTIGO 6250017 |  | 2026-04-13 | Z | 2026-03-30 | 20 | 0 | 0 | 20 | 0 | 50 | 18GA GALV | Prefab hangers |  | 14
2026-03-31 | 1718 |  | UNIT 800 M4.90 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 240 | 0 | 30 | 270 | 0 | 270 | 26GA GALV |  |  | 43
2026-03-31 | 1719 |  | UNIT 801 M4.91 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 190 | 0 | 80 | 270 | 0 | 290 | 26GA GALV |  |  | 43
2026-03-31 | 1720 | bth | UNIT 803 M4.56 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  |  | 43
2026-03-31 | 1721 | bth | UNIT 805 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 43
2026-03-31 | 1722 | bth | UNIT 806 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 43
2026-03-31 | 1723 | bth | UNIT 807 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 43
2026-03-31 | 1724 | bth | UNIT 808 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 43
2026-03-31 | 1725 | bth | UNIT 809 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 43
2026-03-31 | 1726 | bth | UNIT 810 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 43
2026-03-31 | 1727 | bth | UNIT 811 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 43
2026-03-31 | 1728 |  | UNIT 812 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  |  | 43
2026-03-31 | 1729 |  | UNIT 814 M4.61 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  |  | 43
2026-03-31 | 1730 |  | UNIT 815 M4.62 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  |  | 43
2026-03-31 | 1731 |  | UNIT 817 M4.63 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 120 | 0 | 70 | 190 | 0 | 180 | 26GA GALV |  |  | 43
2026-03-31 | 1732 |  | UNIT 818 M4.92 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-02 | 230 | 0 | 60 | 290 | 0 | 300 | 26GA GALV |  |  | 43
2026-03-30 | 1818 |  | UNIT 1043 M4.116 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-04-02 | Z | 2026-03-26 | 60 | 0 | 60 | 120 | 0 | 160 | 26GA GALV |  |  | 7
2026-03-30 | 1819 |  | UNIT 1045 M4.120 | A | done | 18 | M |  | BROOM ST 6240033 |  | 2026-04-02 | Z | 2026-03-26 | 270 | 0 | 160 | 430 | 0 | 440 | 26GA GALV |  |  | 7
2026-03-30 | 1820 |  | UNIT 1047 M4.118 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-04-02 | Z | 2026-03-26 | 130 | 0 | 140 | 270 | 0 | 270 | 26GA GALV |  |  | 7
2026-03-30 | 1821 |  | UNIT 1049 M4.119 | A | done | 17 | M |  | BROOM ST 6240033 |  | 2026-04-02 | Z | 2026-03-26 | 220 | 0 | 200 | 420 | 0 | 420 | 26GA GALV |  |  | 7
2026-03-30 | 1822 |  | UNIT 1143 M4.116 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-04-02 | Z | 2026-03-26 | 60 | 0 | 60 | 120 | 0 | 160 | 26GA GALV |  |  | 7
2026-03-31 | 1823 |  | UNIT 1145 M4.120 | A | done | 18 | M |  | BROOM ST 6240033 |  | 2026-04-02 | Z | 2026-03-26 | 300 | 0 | 130 | 430 | 0 | 430 | 26GA GALV |  |  | 7
2026-03-31 | 1824 |  | UNIT 1147 M4.118 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-04-02 | Z | 2026-03-26 | 130 | 0 | 140 | 270 | 0 | 270 | 26GA GALV |  |  | 7
2026-03-30 | 1825 |  | UNIT 1149 M4.119 | A | done | 18 | M |  | BROOM ST 6240033 |  | 2026-04-02 | Z | 2026-03-26 | 290 | 0 | 140 | 430 | 0 | 420 | 26GA GALV |  |  | 7
2026-03-30 | 10010 |  | 58182 | A | done | 5 | S/M |  | BROOM ST 6240033 | rivet nuts | 2026-04-14 | Z | 2026-03-17 | 110 | 0 | 0 | 110 | 0 | 260 | 18GA GALV | OA kits |  | 28
2026-04-01 | 10014 | sp | 58194 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-31 | 120 | 0 | 0 | 120 | 0 | 130 | 26GA GALV | Grill boxes |  | 14
2026-03-31 | 58199 |  | 58199 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-06 | Z | 2026-03-30 | 40 | 0 | 0 | 40 | 0 | 60 | 22GA GALV | Stair 4 West |  | 7
2026-03-31 | 58200 |  | 58200 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-06 | Z | 2026-03-30 | 20 | 0 | 0 | 20 | 0 | 30 | 26GA GALV | West 1st |  | 7
2026-04-01 | 80451 |  | 80451 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-30 | 25 | 0 | 0 | 25 | 0 | 30 | 26GA GALV |  |  | 15
2026-03-30 | 75055r |  | 75055r | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-03-31 | Z | 2026-03-30 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | Remake |  | 1
2026-03-30 | 6003 | bth | L7-EA-01 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 60 | 40 | 40 | 100 | 0 | 140 | 26GA GALV |  |  | 7
2026-03-30 | 6004 | sp | L7-EA-02 | A | done | 5 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 20 | 100 | 0 | 20 | 0 | 120 | 26GA GALV |  |  | 7
2026-03-30 | 6005 | bth | L7-EA-03 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 60 | 20 | 50 | 110 | 0 | 130 | 26GA GALV |  |  | 7
2026-03-30 | 6006 | bth | L7-EA-04 | A | done | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 40 | 60 | 0 | 40 | 0 | 110 | 26GA GALV |  |  | 7
2026-03-30 | 6007 |  | L7-SALP-01 | A | done | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 100 | 0 | 0 | 100 | 0 | 120 | 26GA GALV |  |  | 7
2026-03-30 | 6008 |  | L7-SALP-02 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 130 | 0 | 0 | 130 | 0 | 150 | 26GA GALV |  |  | 7
2026-03-30 | 6009 | bth | L7-SAMP-01 | A | done | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 90 | 10 | 0 | 90 | 0 | 130 | 24GA GALV |  |  | 7
2026-03-30 | 6010 | bth | L7-SAMP-02 | A | done | 3 | S |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 20 | 50 | 0 | 20 | 0 | 70 | 24GA GALV |  |  | 7
2026-03-30 | 6011 | bth | L7-SAMP-03 | A | done | 5 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 60 | 10 | 40 | 100 | 0 | 130 | 24GA GALV |  |  | 7
2026-03-30 | 6012 | bth | L7-SAMP-04 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-02 | Z | 2026-03-26 | 70 | 50 | 20 | 90 | 0 | 160 | 24GA GALV |  |  | 7
2026-04-01 | 6013 |  | L6-SALP-01 | A | done | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 100 | 0 | 0 | 100 | 0 | 120 | 26GA GALV |  |  | 11
2026-04-01 | 6014 |  | L6-SALP-02 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 130 | 0 | 0 | 130 | 0 | 150 | 26GA GALV |  |  | 11
2026-04-01 | 6015 | bth | L6-EA-01 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 60 | 40 | 40 | 100 | 0 | 140 | 26GA GALV |  |  | 11
2026-04-01 | 6016 | sp | L6-EA-02 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 30 | 100 | 0 | 30 | 0 | 130 | 26GA GALV |  |  | 11
2026-04-01 | 6017 | bth | L6-EA-03 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 70 | 20 | 50 | 120 | 0 | 130 | 26GA GALV |  |  | 11
2026-04-01 | 6018 | bth | L6-EA-04 | A | done | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 40 | 60 | 0 | 40 | 0 | 110 | 26GA GALV |  |  | 11
2026-04-01 | 6019 | bth | L6-SAMP-01 | A | done | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 90 | 10 | 0 | 90 | 0 | 130 | 24GA GALV |  |  | 11
2026-04-01 | 6020 | bth | L6-SAMP-02 | A | done | 3 | S |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 20 | 50 | 0 | 20 | 0 | 70 | 26GA GALV |  |  | 11
2026-04-01 | 6021 | bth | L6-SAMP-03 | A | done | 5 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 60 | 10 | 40 | 100 | 0 | 130 | 24GA GALV |  |  | 11
2026-04-01 | 6022 | bth | L6-SAMP-04 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-03-30 | 70 | 50 | 20 | 90 | 0 | 140 | 26GA GALV |  |  | 11
2026-03-30 | 10012 | w | 10012 | A | done | 2 | S |  | CHURCHILL 6250022 |  | 2026-04-03 | Z | 2026-03-23 | 10 | 0 | 0 | 10 | 0 | 30 | 18GA GALV | Curb extention |  | 11
2026-03-30 | 2036 | bth | L1-A0.3-SALP 27 | A | done | 12 | M | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 190 | 30 | 80 | 270 | 240 | 430 | 24GA GALVANEAL |  |  | 32
2026-03-30 | 2039 | bth | L1-A0.3-SALP 30 | A | done | 13 | M | neal | DC6 6250027 | 1" liner | 2026-03-30 | Z | 2026-02-26 | 130 | 10 | 180 | 310 | 250 | 460 | 24GA GALVANEAL |  |  | 32
2026-03-30 | 53966 |  | 53966 | A | done | 2 | S | neal | DC6 6250027 | 1" liner | 2026-03-31 | Z | 2026-03-30 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALVANEAL |  |  | 1
2026-04-02 | 75716 |  | 75716 | A | done | 2 | S/M | neal | DC6 6250027 | 1" liner | 2026-04-07 | Z | 2026-04-01 | 40 | 0 | 0 | 40 | 40 | 160 | 18GA GALVANEAL | RTU 1 SA |  | 6
2026-03-30 | 75851 |  | 75851 | A | done | 2 | S |  | DC6 6250027 | flex | 2026-04-01 | Z | 2026-03-30 | 10 | 0 | 0 | 10 | 0 | 20 |  | EF-1 |  | 2
2026-04-01 | 10016 |  | 10016 | A | done | 2 | S |  | DELLSHIRE 6240017 | paint black | 2026-04-02 | Z | 2026-03-31 | 20 | 0 | 0 | 20 | 30 | 40 | 24GA GALV | Square to round |  | 2
2026-04-02 | 56144 | w | 56144-45 | A | done | 2 | S/M | bi | DOC JDC 6240023 |  | 2026-04-03 | Z | 2026-03-30 | 30 | 0 | 0 | 30 | 0 | 180 |  | Dust collector |  | 4
2026-04-02 | 56147 | sp | 56147 | A | done | 4 | S/M |  | DOC JDC 6240023 | spiralmate | 2026-04-06 | Z | 2026-04-01 | 30 | 50 | 0 | 30 | 0 | 140 | 18GA GALV | Dust collector |  | 5
2026-03-31 | 56148 |  | 56148 | A | done | 2 | S |  | DOC JDC 6240023 | paint black | 2026-04-01 | Z | 2026-03-30 | 50 | 0 | 0 | 50 | 30 | 80 | 24GA GALV | Ceiling tie ins |  | 2
2026-04-02 | 95670 |  | 95670 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-04-03 | Z | 2026-04-02 | 10 | 0 | 0 | 10 | 0 | 30 |  |  |  | 1
2026-04-02 | 77581 |  | 77581 | A | done | 3 | S |  | EXACT 2260020 |  | 2026-04-08 | Z | 2026-04-01 | 30 | 0 | 40 | 70 | 0 | 90 | 24GA GALV | EA |  | 7
2026-04-01 | 84323 |  | 84323 | A | done | 10 | S/M |  | FRANK&ANDREAS 4250061 |  | 2026-04-06 | Z | 2026-03-31 | 80 | 0 | 150 | 230 | 0 | 240 | 24GA GALV | MAU OA |  | 6
2026-04-02 | 84325 | sp | 84325 | A | done | 5 | S |  | FRANK&ANDREAS 4250061 |  | 2026-04-06 | Z | 2026-04-02 | 10 | 100 | 0 | 10 | 0 | 100 | 26GA GALV | Bath EA |  | 4
2026-04-01 | 77027 |  | 77027,77029-30 | A | done | 6 | S/M |  | GRANT ES 6250021 |  | 2026-04-06 | Z | 2026-03-30 | 50 | 0 | 90 | 140 | 0 | 180 | 24GA GALV | VAV's |  | 7
2026-03-31 | 77028 | sp | 77028,77031 | A | done | 4 | S |  | GRANT ES 6250021 |  | 2026-04-06 | Z | 2026-03-30 | 20 | 80 | 0 | 20 | 0 | 100 | 24GA GALV | VAV's |  | 7
2026-04-01 | 77032 |  | 77032 | A | done | 4 | S/M |  | GRANT ES 6250021 |  | 2026-04-13 | Z | 2026-03-31 | 100 | 0 | 0 | 100 | 0 | 160 | 22GA GALV | Front office drop |  | 13
2026-03-31 | 78791 | bth | 78791 | A | done | 2 | S |  | MONROE 6240018 |  | 2026-04-02 | Z | 2026-03-30 | 10 | 20 | 0 | 10 | 0 | 30 | 24GA GALV | Concessions |  | 3
2026-04-01 | 84324 | sp | 84324 | A | done | 2 | S |  | MPS 4260004 |  | 2026-04-02 | Z | 2026-04-01 | 20 | 20 | 0 | 20 | 0 | 30 | 26GA GALV | DOAS |  | 1
2026-04-02 | 84326 |  | 84326 | A | done | 2 | S |  | MPS 4260004 |  | 2026-04-02 | Z | 2026-04-02 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | FCU 1 |  | 0
2026-04-01 | 74682 |  | 74682-84 | A | done | 6 | S/M | neal | PORTAGE MS 6250018 |  | 2026-04-06 | Z | 2026-03-31 | 140 | 0 | 0 | 140 | 0 | 280 | 20GA GALVANEAL | Pipe enclosures |  | 6
2026-03-31 | 76664 |  | 76664 | A | done | 2 | S |  | PORTAGE MS 6250018 |  | 2026-03-31 | Z | 2026-03-31 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | Dampers |  | 0
2026-04-02 | 76665 |  | 76665 | A | done | 2 | S |  | PORTAGE MS 6250018 |  | 2026-04-02 | Z | 2026-04-01 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | SA |  | 1
2026-04-01 | 76413 |  | 76413 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-04-07 | Z | 2026-03-31 | 10 | 0 | 0 | 10 | 0 | 30 | 24GA GALV | Cone flashing |  | 7
2026-04-02 | 76414 |  | 76414 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2026-04-07 | Z | 2026-04-01 | 50 | 0 | 0 | 50 | 0 | 60 |  | MAU 5, 7 |  | 6
2026-03-31 | 76033 | w | 76033 | A | done | 2 | S |  | RCIS 6250011 |  | 2026-04-13 | Z | 2026-03-30 | 10 | 0 | 0 | 10 | 0 | 20 |  | Roof cap |  | 14
2026-04-02 | 1210 |  | L3.5-EA-01 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 30 | 0 | 40 | 70 | 0 | 80 | 24GA GALV |  |  | 13
2026-04-02 | 1211 |  | L3.5-EA-02 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 20 | 0 | 110 | 130 | 0 | 120 | 26GA GALV |  |  | 13
2026-04-02 | 1213 | sp | L3.5-EA-04 | A | done | 5 | S/M |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 10 | 100 | 0 | 10 | 0 | 110 | 24GA GALV |  |  | 13
2026-04-02 | 1214 |  | L3.5-EA-05 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 60 | 0 | 30 | 90 | 0 | 110 | 24GA GALV |  |  | 13
2026-04-02 | 1215 |  | L3.5-RA-01 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 100 | 0 | 0 | 100 | 0 | 140 | 24GA GALV |  |  | 13
2026-04-02 | 1217 |  | L3.5-RA-03 | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 10 | 0 | 40 | 50 | 50 | 70 | 24GA GALV |  |  | 13
2026-04-02 | 1218 |  | L3.5-RA-04 | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 30 | 0 | 0 | 30 | 20 | 40 | 22GA GALV |  |  | 13
2026-04-02 | 1223 |  | L3.5-SALP-09 | A | done | 9 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 140 | 0 | 70 | 210 | 120 | 280 | 22GA GALV |  |  | 13
2026-04-02 | 1226 |  | L3.5-SALP-12 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 100 | 0 | 0 | 100 | 90 | 170 | 24GA GALV |  |  | 13
2026-03-31 | 85480 |  | 85480-82 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-06 | Z | 2026-03-30 | 60 | 0 | 0 | 60 | 0 | 80 | 24GA GALV | South chase |  | 7
2026-03-30 | 81885 |  | 81885 | A | done | 39 | L |  | TERSO 2260019 |  | 2026-04-13 | Z | 2026-03-23 | 150 | 0 | 820 | 970 | 0 | 1450 | 22GA GALVANEAL | Misc |  | 21
2026-03-30 | 74901 |  | 74901-02 | A | done | 10 | S/M |  | TOMAH HEALTH 2250045 |  | 2026-04-08 | Z | 2026-03-25 | 240 | 0 | 0 | 240 | 0 | 320 | 24GA GALV | Exhaust |  | 14
2026-04-01 | 72561 |  | 72561 | A | done | 2 | S |  | UW LEVY HALL 6230028 |  | 2026-04-06 | Z | 2026-04-01 | 10 | 0 | 0 | 10 | 0 | 20 |  | L4 room 4202 |  | 5
2026-04-02 | 4554 | bth | L3-SAT-1-3-1 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 50 | 10 | 100 | 150 | 0 | 210 | 24GA GALV |  |  | -8
2026-03-31 | 4556 | bth | L3-SAT-1-3-3 | A | done | 3 | S | neal | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 30 | 30 | 0 | 30 | 50 | 70 | 24GA GALVANEAL |  |  | -8
2026-03-30 | 4557 | bth | L3-SAT-1-3-4 | A | done | 2 | S | neal | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 30 | 0 | 20 | 0 | 60 | 24GA GALVANEAL |  |  | -8
2026-04-02 | 4558 | bth | L3-SAT-1-3-6 | A | done | 4 | S | neal | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 20 | 60 | 0 | 20 | 30 | 90 | 24GA GALV |  |  | -8
2026-04-01 | 4560 |  | L3-SAT-1-3-44 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 40 | 10 | 0 | 40 | 0 | 60 | 24GA GALV |  |  | -8
2026-04-02 | 4561 | bth | L3-SAT-1-3-45 | A | done | 8 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 80 | 30 | 80 | 160 | 30 | 230 | 24GA GALV |  |  | -8
2026-04-02 | 4562 | bth | L3-SAT-1-3-46 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 10 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | -8
2026-04-02 | 4563 | bth | L3-SAT-1-3-47 | A | done | 3 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 30 | 30 | 0 | 30 | 0 | 70 | 24GA GALV |  |  | -8
2026-04-01 | 4564 |  | L3-SAT-1-3-48 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 0 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-02 | 4565 | bth | L3-SAT-1-3-49 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-02 | 4566 | bth | L3-SAT-1-3-50 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-02 | 4567 | bth | L3-SAT-1-3-51 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 30 | 10 | 0 | 30 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-02 | 4570 | bth | L3-SAT-1-3-54 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-02 | 4576 | bth | L3-SAT-1-3-60 | A | done | 6 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 50 | 80 | 0 | 50 | 30 | 140 | 24GA GALV |  |  | -8
2026-04-02 | 4577 | bth | L3-SAT-2-3-1 | A | done | 5 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 90 | 20 | 0 | 90 | 30 | 130 | 24GA GALV |  |  | -8
2026-04-02 | 4578 | bth | L3-SAT-2-3-2 | A | done | 4 | S |  | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 60 | 10 | 10 | 70 | 10 | 100 | 24GA GALV |  |  | -8
2026-04-02 | 4579 | bth | L3-SAT-2-3-3_1 | A | done | 8 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 110 | 30 | 40 | 150 | 40 | 220 | 24GA GALV |  |  | -8
2026-04-02 | 4581 | bth | L3-SAT-2-3-4_1 | A | done | 6 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 120 | 20 | 0 | 120 | 30 | 180 | 24GA GALV |  |  | -8
2026-03-30 | 4595 |  | L3-TA 89 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-03-31 | Z | 2026-03-18 | 20 | 0 | 0 | 20 | 20 | 30 | 24GA GALV | Build ahead |  | 13 | 2026-04-30
2026-04-01 | 4623 | bth | L2-SAMP 11 | A | done | 14 | M |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-04-22 | 140 | 30 | 170 | 310 | 0 | 650 | 18GA GALV |  |  | -15
2026-03-31 | 4624 | bth | L2-SAMP 12 | A | done | 14 | M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 100 | 110 | 120 | 220 | 0 | 560 | 18GA GALV |  |  | -8
2026-04-01 | 4625 |  | L2-SAMP 13 | A | done | 10 | M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-03-13 | 160 | 0 | 80 | 240 | 0 | 500 | 20GA GALV |  |  | 32
2026-04-01 | 4626 |  | L2-SAMP 15 | A | done | 17 | M/L |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-03-13 | 220 | 0 | 190 | 410 | 0 | 850 | 18GA GALV |  |  | 32
2026-04-01 | 4627 | bth | L2-SAMP 16 | A | done | 27 | L |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-03-13 | 120 | 50 | 500 | 620 | 0 | 1380 | 20GA GALV |  |  | 32
2026-04-01 | 4628 | bth | L2-SAMP 17 | A | done | 15 | M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-03-13 | 150 | 20 | 200 | 350 | 0 | 700 | 20GA GALV |  |  | 32
2026-04-01 | 4629 | bth | L2-SAMP 19 | A | done | 10 | M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-03-13 | 40 | 40 | 170 | 210 | 0 | 360 | 22GA GALV |  |  | 32
2026-04-01 | 4634 | bth | L2-SAMP 21 | A | done | 19 | M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 70 | 10 | 390 | 460 | 0 | 710 | 20GA GALV |  |  | -8
2026-04-01 | 4635 | bth | L2-SAMP 24 | A | done | 24 | M/L |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 290 | 80 | 220 | 510 | 0 | 970 | 22GA GALV |  |  | -8
2026-03-30 | 4683 |  | L2-SAMP 07 | A | done | 8 | M |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 150 | 0 | 50 | 200 | 0 | 410 | 20GA GALV |  |  | 18
2026-03-30 | 4686 |  | L2-SAMP 10 | A | done | 13 | M |  | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-03-20 | 80 | 30 | 210 | 290 | 0 | 650 | 18GA GALV |  |  | 18
2026-03-30 | 4687 | w | L1-SHAFT CEA C 1 | A | done | 3 | S/M | ss | UW STOUT 6250008 |  | 2026-03-31 | Z | 2026-03-24 | 60 | 0 | 0 | 60 | 0 | 190 |  |  |  | 7
2026-04-01 | 84585 |  | 84585,prefab hangers | A | done | 11 | M | neal | UW STOUT 6250008 |  | 2026-04-07 | Z | 2026-04-01 | 270 | 0 | 0 | 270 | 0 | 450 | 24GA GALV | Flashing, hangers |  | 6
2026-03-30 | 84894 |  | 84894-95 | A | done | 3 | S/M |  | UW STOUT 6250008 |  | 2026-03-31 | Z | 2026-03-26 | 70 | 0 | 0 | 70 | 0 | 130 | 22GA GALV | Salp |  | 5
2026-04-02 | 4173R |  | 4173R | A | done | 2 | S |  | UW STOUT 6250008 | birdscreen | 2026-04-03 | Z | 2026-04-02 | 10 | 0 | 0 | 10 | 0 | 20 |  |  |  | 1
2026-03-30 | 76112 |  | 76112-14 | A | done | 59 | L |  | UWP 6240021 |  | 2026-04-09 | Z | 2026-02-04 | 300 | 0 | 1160 | 1460 | 0 | 2230 | 24GA GALV | DOAS 1 SA |  | 64
2026-03-31 | 76115 |  | 76115-18 | A | done | 25 | M/L |  | UWP 6240021 |  | 2026-04-09 | Z | 2026-02-17 | 240 | 0 | 380 | 620 | 0 | 1220 | 24GA GALV | DOAS 1 RA |  | 51
2026-04-02 | 76127 |  | 76127 | A | done | 2 | S |  | UWP 6240021 |  | 2026-04-09 | Z | 2026-04-01 | 10 | 0 | 0 | 10 | 0 | 20 | 20GA GALV | louver cap |  | 8
2026-03-31 | 76112r |  | 76112r | A | done | 7 | S/M |  | UWP 6240021 |  | 2026-04-09 | Z | 2026-03-31 | 70 | 0 | 100 | 170 | 0 | 230 | 24GA GALV |  |  | 9
2026-03-31 | 76465 |  | 76465 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-04-01 | Z | 2026-03-31 | 10 | 0 | 0 | 10 | 0 | 20 | 20GA GALV | Wall sleeve |  | 1
[6 empty] | 908 | [12 empty] | 30040 | [6 empty] | 63.4% Short
WEEK OF 4-6-2026
2026-04-07 | 82837 | sp | 82837,82839 | A | done | 47 | L |  | ANTIGO 6250017 | oval accuflange | 2026-04-13 | Z | 2026-03-25 | 120 | 1040 | 0 | 120 | 0 | 1520 | 24GA GALV | Area B north SA |  | 19
2026-04-06 | 82845 | w | 82845 | A | done | 2 | S |  | ANTIGO 6250017 |  | 2026-04-07 | Z | 2026-04-02 | 20 | 0 | 0 | 20 | 0 | 50 | 18GA GALV | AHU 1 |  | 5
2026-04-07 | 1757 |  | UNIT 931 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 70 | 80 | 0 | 70 | 0 | 160 | 26GA GALV |  |  | 36
2026-04-07 | 1758 |  | UNIT 932 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 70 | 80 | 0 | 70 | 0 | 170 | 26GA GALV |  |  | 36
2026-04-07 | 1759 |  | UNIT 933 M4.66 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 150 | 0 | 70 | 220 | 0 | 220 | 26GA GALV |  |  | 36
2026-04-07 | 1760 |  | UNIT 934 M4.67 | A | done | 15 | M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 170 | 0 | 190 | 360 | 0 | 420 | 26GA GALV |  |  | 36
2026-04-07 | 1761 |  | UNIT 935 M4.68 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  |  | 36
2026-04-07 | 1762 |  | UNIT 936 M4.69 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 90 | 0 | 20 | 110 | 0 | 110 | 26GA GALV |  |  | 36
2026-04-07 | 1763 |  | UNIT 937 M4.70 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 220 | 0 | 70 | 290 | 0 | 290 | 26GA GALV |  |  | 36
2026-04-07 | 1764 |  | UNIT 938 M4.71 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 160 | 0 | 120 | 280 | 0 | 270 | 26GA GALV |  |  | 36
2026-04-07 | 1765 |  | UNIT 939 M4.72 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 240 | 0 | 0 | 240 | 0 | 260 | 26GA GALV |  |  | 36
2026-04-07 | 1766 |  | UNIT 941 M4.73 | A | done | 3 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 70 | 0 | 0 | 70 | 0 | 80 | 26GA GALV |  |  | 36
2026-04-07 | 1767 |  | UNIT 942 M4.115 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-03-09 | 180 | 0 | 60 | 240 | 0 | 250 | 26GA GALV |  |  | 36
2026-04-07 | 1772 | bth | UNIT 1031 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 70 | 80 | 0 | 70 | 0 | 170 | 26GA GALV |  |  | 43
2026-04-08 | 1773 | bth | UNIT 1032 M4.65 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 70 | 80 | 0 | 70 | 0 | 170 | 26GA GALV |  | 19 | 43
2026-04-07 | 1774 |  | UNIT 1033 M4.66 | A | done | 9 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 150 | 0 | 70 | 220 | 0 | 220 | 26GA GALV |  | 34 | 43
2026-04-08 | 1775 |  | UNIT 1034 M4.67 | A | done | 15 | M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 170 | 0 | 190 | 360 | 0 | 420 | 26GA GALV |  | 48 | 43
2026-04-08 | 1776 |  | UNIT 1035 M4.68 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  | 22 | 43
2026-04-08 | 1779 |  | UNIT 1038 M4.71 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 160 | 0 | 120 | 280 | 0 | 270 | 26GA GALV |  | 35 | 43
2026-04-07 | 1781 |  | UNIT 1041 M4.73 | A | done | 3 | S |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 70 | 0 | 0 | 70 | 0 | 80 | 26GA GALV |  | 16 | 43
2026-04-08 | 1782 |  | UNIT 1042 M4.115 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 210 | 0 | 30 | 240 | 0 | 260 | 26GA GALV |  | 36 | 43
2026-04-09 | 10015 | sp | 58194 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-31 | 120 | 0 | 0 | 120 | 0 | 130 | 26GA GALV | Grill boxes |  | 21
2026-04-08 | 78274 |  | 78274-76 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-04-08 | Z | 2026-04-07 | 180 | 0 | 0 | 180 | 0 | 280 | 24GA GALV | L1 amenities | 20 | 1
2026-04-07 | 78277 |  | 78277 | A | done | 2 | S | alum | BROOM ST 6240033 |  | 2026-04-08 | Z | 2026-04-07 | 30 | 0 | 0 | 30 | 0 | 20 |  | L1 amenities | 3 | 1
2026-04-08 | 80452 |  | 80452 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-04-06 | 40 | 0 | 0 | 40 | 0 | 50 | 26GA GALV | West |  | 8
2026-04-09 | 10019 |  | 10019 | A | done | 3 | S/M |  | CATALENT 6260008 |  | 2026-04-10 | Z | 2026-04-08 | 60 | 0 | 0 | 60 | 0 | 160 |  | Flat stock | 12 | 2
2026-04-09 | 6023 | bth | L5-EA-01 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 60 | 40 | 40 | 100 | 0 | 140 | 26GA GALV |  | 32 | 10
2026-04-09 | 6024 | sp | L5-EA-02 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 30 | 100 | 0 | 30 | 0 | 120 | 26GA GALV |  | 29 | 10
2026-04-09 | 6025 | bth | L5-EA-03 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 110 | 20 | 0 | 110 | 0 | 130 | 26GA GALV |  | 28 | 10
2026-04-09 | 6026 | bth | L5-EA-04 | A | done | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 40 | 60 | 0 | 40 | 0 | 110 | 26GA GALV |  | 41 | 10
2026-04-09 | 6027 |  | L5-SALP-01 | A | done | 5 | S/M |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 110 | 0 | 0 | 110 | 0 | 160 | 24GA GALV |  | 12 | 10
2026-04-09 | 6028 |  | L5-SALP-02 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 130 | 0 | 0 | 130 | 0 | 170 | 24GA GALV |  | 13 | 10
2026-04-09 | 6029 | bth | L5-SAMP-01 | A | done | 4 | S/M |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 90 | 10 | 0 | 90 | 0 | 130 | 24GA GALV |  | 19 | 10
2026-04-09 | 6030 | bth | L5-SAMP-02 | A | done | 3 | S |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 20 | 50 | 0 | 20 | 0 | 70 | 26GA GALV |  | 15 | 10
2026-04-09 | 6031 | bth | L5-SAMP-03 | A | done | 5 | S |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 60 | 10 | 40 | 100 | 0 | 100 | 26GA GALV |  | 15 | 10
2026-04-09 | 6032 | bth | L5-SAMP-04 | A | done | 6 | S/M |  | CHURCHILL 6250022 |  | 2026-04-17 | Z | 2026-04-07 | 70 | 50 | 20 | 90 | 0 | 170 | 24GA GALV |  | 26 | 10
2026-04-06 | 76852 |  | 76852 | A | done | 2 | S |  | CHURCHILL 6250022 |  | 2026-04-10 | Z | 2026-04-06 | 20 | 0 | 0 | 20 | 0 | 20 |  | 7th floor angle |  | 4
2026-04-09 | 2051 |  | L1-B3d-RTU 10 | A | done | 4 | S/M |  | DC6 6250027 | flex | 2026-04-22 | Z | 2026-04-08 | 80 | 0 | 0 | 80 | 70 | 120 | 24GA GALVANEAL |  | 6 | 14
2026-04-06 | 53967 |  | 53967 | 2 | done | 2 | S |  | DC6 6250027 |  | 2026-04-07 | Z | 2026-04-06 | 10 | 0 | 0 | 10 | 0 | 20 |  | Trailer flashing |  | 1
2026-04-09 | 75757 |  | 75757-58 | A | done | 12 | S/M | neal | DC6 6250027 |  | 2026-04-15 | Z | 2026-04-09 | 280 | 0 | 0 | 280 | 0 | 340 | 24GA GALV | EF drops, flashing | 31 | 6
2026-04-06 | 74180 |  | 74180 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-04-07 | Z | 2026-04-06 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV | OA hood |  | 1
2026-04-07 | 74181 |  | 74181 | A | done | 4 | S/M |  | DOC JDC 6240023 |  | 2026-04-08 | Z | 2026-04-06 | 90 | 0 | 0 | 90 | 0 | 150 | 24GA GALV | MUA-1 OA |  | 2
2026-04-08 | 74185 |  | 74185 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-04-10 | Z | 2026-04-07 | 40 | 0 | 0 | 40 | 30 | 50 | 24GA GALV | Ceiling tie ins | 6 | 3
2026-04-09 | 77582 |  | 77582 | A | done | 2 | S |  | EXACT 2260020 | paint black | 2026-04-13 | Z | 2026-04-08 | 50 | 0 | 0 | 50 | 20 | 70 | 24GA GALV | EA out | 12 | 5
2026-04-08 | 74840 | w | 74840 | A | done | 2 | S | ss | EXACT TL3 8240019 |  | 2026-04-09 | Z | 2026-04-08 | 10 | 0 | 0 | 10 | 0 | 20 |  | Coffee shop | 1 | 1
2026-04-07 | 77024 | bth | 77024-26 | A | done | 2 | S |  | GRANT ES 6250021 |  | 2026-04-06 | Z | 2026-03-30 | 20 | 20 | 0 | 20 | 0 | 40 | 24GA GALV | VAV's |  | 7
2026-04-08 | 77114 |  | 77114 | A | done | 2 | S |  | GRANT ES 6250021 |  | 2026-04-13 | Z | 2026-04-08 | 10 | 0 | 0 | 10 | 0 | 20 |  | Phase 6 bath |  | 5
2026-04-08 | 78794 | bth | 78794-95 | A | done | 9 | S/M |  | JPC LEGACY 2260013 | 1/2" liner | 2026-04-13 | Z | 2026-04-06 | 130 | 30 | 60 | 190 | 100 | 240 | 26GA GALV | VAV |  | 7
2026-04-07 | 41710 | w | 41710-12 | A | done | 10 | S/M | ss | LABCORP 2250031 |  | 2026-04-09 | Z | 2026-04-02 | 130 | 100 | 0 | 130 | 0 | 310 | 24GA GALV | Cage wash |  | 7
2026-04-08 | 41713 | sp | 41713 | A | done | 2 | S | ss | LABCORP 2250031 |  | 2026-04-09 | Z | 2026-04-07 | 10 | 30 | 0 | 10 | 0 | 40 |  | 3rd floor cage wash | 4 | 2
2026-04-07 | 77327 |  | 77327,77329 | A | done | 4 | S/M |  | LAKE MILLS ES 6250012 | 1" liner | 2026-04-13 | Z | 2026-04-02 | 90 | 0 | 0 | 90 | 40 | 120 | 24GA GALV | Misc |  | 11
2026-04-09 | 42897 |  | 42897 | A | done | 2 | S |  | MILES BLUFF 30004802 | 1" liner | 2026-04-27 | Z | 2026-04-08 | 40 | 0 | 0 | 40 | 30 | 70 | 20GA GALV | AHU top | 6 | 19
2026-04-08 | 84327 |  | 84327 | A | done | 10 | M |  | MPS 4260004 |  | 2026-04-15 | Z | 2026-04-07 | 250 | 0 | 0 | 250 | 0 | 390 | 24GA GALV | FCU | 18 | 8
2026-04-09 | 84328 | sp | 84328-30 | A | done | 16 | M |  | MPS 4260004 |  | 2026-04-15 | Z | 2026-04-07 | 100 | 280 | 0 | 100 | 0 | 370 | 26GA GALV | FCU | 55 | 8
2026-04-09 | 84331 | bth | 84331-34 | A | done | 12 | S/M |  | MPS 4260004 |  | 2026-04-15 | Z | 2026-04-07 | 150 | 50 | 80 | 230 | 40 | 280 | 26GA GALV | Basement | 32 | 8
2026-04-07 | 74839 |  | 74839 | A | done | 2 | S |  | PE 10067973 |  | 2026-04-07 | Z | 2026-04-07 | 40 | 0 | 0 | 40 | 0 | 80 | 24GA GALV | Flat stock |  | 0
2026-04-06 | 76666 |  | 76666 | 2 | done | 2 | S |  | PORTAGE MS 6250018 | 1" liner | 2026-04-06 | Z | 2026-04-06 | 40 | 0 | 0 | 40 | 0 | 60 | 24GA GALV | RE drops |  | 0
2026-04-08 | 83954 |  | 83954 | A | done | 2 | S |  | PROMEGA BTC 6250020 |  | 2026-04-09 | Z | 2026-04-07 | 50 | 0 | 0 | 50 | 0 | 70 | 24GA GALV | Misc | 2 | 2
2026-04-06 | 1212 | bth | L3.5-EA-03 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 70 | 80 | 0 | 70 | 0 | 150 | 26GA GALV |  |  | 13
2026-04-06 | 1216 |  | L3.5-RA-02 | A | done | 3 | S |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 60 | 0 | 0 | 60 | 60 | 100 | 24GA GALV |  |  | 13
2026-04-06 | 1219 | bth | L3.5-SALP-05 | A | done | 4 | S |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 60 | 40 | 0 | 60 | 50 | 100 | 24GA GALV |  |  | 13
2026-04-06 | 1220 | bth | L3.5-SALP-06 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 20 | 30 | 0 | 20 | 0 | 60 | 24GA GALV |  |  | 13
2026-04-06 | 1221 | bth | L3.5-SALP-07 | A | done | 8 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 120 | 10 | 60 | 180 | 70 | 300 | 22GA GALV |  |  | 13
2026-04-06 | 1222 | bth | L3.5-SALP-08 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 60 | 30 | 40 | 100 | 70 | 130 | 24GA GALV |  |  | 13
2026-04-06 | 1224 |  | L3.5-SALP-10 | A | done | 17 | M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 410 | 0 | 0 | 410 | 110 | 800 | 22GA GALV |  |  | 13
2026-04-07 | 1225 |  | L3.5-SALP-11 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 80 | 0 | 0 | 80 | 70 | 140 | 24GA GALV |  |  | 13
2026-04-06 | 1227 | bth | L3.5-SALP-13 | A | done | 6 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 130 | 20 | 0 | 130 | 60 | 190 | 24GA GALV |  |  | 13
2026-04-06 | 1228 |  | L3.5-SALP-14 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 80 | 0 | 0 | 80 | 70 | 130 | 24GA GALV |  |  | 13
2026-04-07 | 1229 |  | L3.5-SALP-15 | A | done | 6 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 70 | 0 | 80 | 150 | 130 | 220 | 24GA GALV |  |  | 13
2026-04-06 | 1230 |  | L3.5-SALP-16 | A | done | 6 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 90 | 0 | 40 | 130 | 110 | 250 | 24GA GALV |  |  | 13
2026-04-07 | 1231 |  | L3.5-SALP-17 | A | done | 8 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 60 | 0 | 130 | 190 | 180 | 350 | 20GA GALV |  |  | 13
2026-04-06 | 1232 |  | L3.5-SALP-18 | A | done | 3 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 60 | 0 | 0 | 60 | 60 | 120 | 24GA GALV |  |  | 13
2026-04-06 | 1233 | sp | L3.5-SALP-19 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 10 | 40 | 0 | 10 | 0 | 50 | 24GA GALV |  |  | 13
2026-04-06 | 1234 | sp | L3.5-SALP-20 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 20 | 40 | 0 | 20 | 0 | 60 | 24GA GALV |  |  | 13
2026-04-06 | 1235 | sp | L3.5-SALP-21 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 10 | 50 | 0 | 10 | 0 | 70 | 24GA GALV |  |  | 13
2026-04-06 | 1236 | sp | L3.5-SALP-22 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 10 | 40 | 0 | 10 | 0 | 60 | 24GA GALV |  |  | 13
2026-04-06 | 1237 | sp | L3.5-SALP-23 | A | done | 3 | S |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 10 | 60 | 0 | 10 | 0 | 70 | 24GA GALV |  |  | 13
2026-04-06 | 1238 | sp | L3.5-SALP-24 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 10 | 40 | 0 | 10 | 0 | 50 | 24GA GALV |  |  | 13
2026-04-06 | 1239 |  | L3.5-SAMP-01 | A | done | 8 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 130 | 0 | 50 | 180 | 150 | 280 | 24GA GALV |  |  | 13
2026-04-06 | 1240 | bth | L3.5-SAMP-02 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 60 | 30 | 0 | 60 | 50 | 130 | 24GA GALV |  |  | 13
2026-04-06 | 1241 | bth | L3.5-SAMP-03 | A | done | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 40 | 20 | 50 | 90 | 50 | 150 | 24GA GALV |  |  | 13
2026-04-06 | 1242 | bth | L3.5-SAMP-04 | A | done | 6 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 120 | 20 | 0 | 120 | 90 | 200 | 24GA GALV |  |  | 13
2026-04-07 | 1243 |  | L3.5-SAMP-05 | A | done | 12 | M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 130 | 0 | 170 | 300 | 260 | 540 | 22GA GALV |  |  | 13
2026-04-07 | 1244 |  | L3.5-SAMP-06 | A | done | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 120 | 0 | 0 | 120 | 100 | 170 | 24GA GALV |  |  | 13
2026-04-06 | 1245 | bth | L3.5-SAMP-07 | A | done | 6 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 80 | 40 | 30 | 110 | 80 | 190 | 24GA GALV |  |  | 13
2026-04-06 | 1246 | bth | L3.5-SAMP-08 | A | done | 6 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 110 | 20 | 0 | 110 | 90 | 190 | 24GA GALV |  |  | 13
2026-04-07 | 1247 |  | L3.5-SAMP-09 | A | done | 3 | S |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 60 | 0 | 0 | 60 | 30 | 90 | 24GA GALV |  |  | 13
2026-04-06 | 1248 |  | L3.5-SAMP-10 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 50 | 0 | 30 | 80 | 80 | 120 | 24GA GALV |  |  | 13
2026-04-06 | 1249 | sp | L3.5-SAMP-11 | A | done | 5 | S/M |  | SHRINE 6240034 |  | 2026-04-13 | Z | 2026-03-31 | 50 | 70 | 0 | 50 | 0 | 150 | 24GA GALV |  |  | 13
2026-04-07 | 1250 |  | L3.5-TA-1 | A | done | 10 | M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 240 | 0 | 0 | 240 | 140 | 450 | 20GA GALV |  |  | 13
2026-04-06 | 1251 |  | L3.5-TA-2 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 60 | 0 | 30 | 90 | 70 | 110 | 24GA GALV |  |  | 13
2026-04-07 | 1252 |  | L3.5-TA-3 | A | done | 10 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 180 | 0 | 50 | 230 | 110 | 330 | 22GA GALV |  |  | 13
2026-04-06 | 1253 |  | L3.5-TA-4 | A | done | 3 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-03-31 | 60 | 0 | 0 | 60 | 60 | 120 | 22GA GALV |  |  | 13
2026-04-08 | 85483 |  | 85483 | A | done | 4 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-13 | Z | 2026-04-02 | 100 | 0 | 0 | 100 | 110 | 250 | 20GA GALV | Misc |  | 11
2026-04-09 | 85484 |  | 85484 | A | done | 2 | S |  | SHRINE 6240034 | paint black | 2026-04-20 | Z | 2026-04-08 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV | Misc | 9 | 12
2026-04-08 | 77212 | sp | 77212 | A | done | 3 | S/M |  | SWH MOB 6250015 |  | 2026-04-08 | Z | 2026-04-06 | 70 | 0 | 0 | 70 | 0 | 230 | 16GA GALV |  |  | 2
2026-04-08 | 72562 |  | 72562 | A | done | 2 | S |  | UW LEVY HALL 6230028 | 1" liner | 2026-04-07 | Z | 2026-04-07 | 40 | 0 | 0 | 40 | 40 | 60 | 24GA GALV | Ceiling tie ins |  | 0
2026-04-06 | 72575 |  | 72575 | A | done | 4 | S/M |  | UW LEVY HALL 6230028 | paint black | 2026-04-07 | Z | 2026-04-06 | 90 | 0 | 0 | 90 | 80 | 200 | 20GA GALV | Loading dock |  | 1
2026-04-09 | 78401 |  | 78401 | A | done | 2 | S |  | UW LEVY HALL 6230028 | paint black | 2026-04-10 | Z | 2026-04-09 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV | Misc tie ins | 4 | 1
2026-04-08 | 4555 | bth | L3-SAT-1-3-2 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 90 | 10 | 70 | 160 | 0 | 210 | 24GA GALV |  |  | -8
2026-04-06 | 4559 | bth | L3-SAT-1-3-43 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 20 | 20 | 0 | 20 | 20 | 50 | 24GA GALV |  |  | -8
2026-04-06 | 4568 | bth | L3-SAT-1-3-52 | A | done | 4 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 30 | 50 | 0 | 30 | 0 | 90 | 24GA GALV |  |  | -8
2026-04-06 | 4569 | bth | L3-SAT-1-3-53 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-08 | 4571 | bth | L3-SAT-1-3-55 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 10 | 0 | 20 | 0 | 50 | 24GA GALV |  |  | -8
2026-04-08 | 4572 | bth | L3-SAT-1-3-56 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-08 | 4573 | bth | L3-SAT-1-3-57 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-06 | 4574 | bth | L3-SAT-1-3-58 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 30 | 10 | 0 | 30 | 0 | 40 | 24GA GALV |  |  | -8
2026-04-08 | 4575 |  | L3-SAT-1-3-59 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  |  | -8
2026-04-08 | 4580 | bth | L3-SAT-2-3-3_2 | A | done | 4 | S/M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 50 | 10 | 40 | 90 | 0 | 130 | 24GA GALV |  |  | -8
2026-04-08 | 4582 | bth | L3-SAT-2-3-4_2 | A | done | 5 | S/M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-04-22 | 70 | 10 | 40 | 110 | 0 | 150 | 24GA GALV |  |  | -8
2026-04-06 | 4583 | bth | L3-SAT-2-3-18 | A | done | 13 | M |  | UW STOUT 6250008 | 1" liner | 2026-04-14 | Z | 2026-04-22 | 260 | 0 | 60 | 320 | 30 | 440 | 24GA GALV |  |  | -8
2026-04-08 | 4630 | bth | L2-SAMP 20 | A | done | 8 | S/M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-03-13 | 60 | 30 | 110 | 170 | 0 | 270 | 24GA GALV |  | 16 | 39
2026-04-08 | 4631 |  | L2-SAMP 18 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-03-13 | 100 | 0 | 70 | 170 | 0 | 310 | 22GA GALV |  | 18 | 39
2026-04-08 | 4632 |  | L2-SAMP 13.5 | A | done | 6 | S/M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-03-13 | 60 | 0 | 80 | 140 | 0 | 310 | 18GA GALV |  | 4 | 39
2026-04-08 | 4637 |  | L2-SAMP 22 | A | done | 9 | S/M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-03-17 | 140 | 0 | 70 | 210 | 0 | 340 | 22GA GALV |  | 9 | 35
2026-04-08 | 4638 | bth | L2-SAMP 23 | A | done | 12 | S/M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-03-17 | 60 | 50 | 170 | 230 | 0 | 340 | 24GA GALV |  | 20 | 35
2026-04-09 | 4639 | bth | L2-SAMP 26 | A | done | 10 | M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-03-17 | 220 | 20 | 0 | 220 | 0 | 550 | 18GA GALV |  | 11 | 35
2026-04-08 | 4640 | bth | L2-SAMP 27 | A | done | 6 | S/M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-03-17 | 40 | 30 | 60 | 100 | 0 | 220 |  |  | 8 | 35
2026-04-07 | 77365 |  | 77365 | A | done | 3 | S |  | UW STOUT 6250008 | 1" liner, birdscreen | 2026-04-14 | Z | 2026-04-02 | 70 | 0 | 0 | 70 | 60 | 100 | 24GA GALV | L3 TA 152 |  | 12
2026-04-09 | 78356 |  | 78356 | A | done | 2 | S |  | VET MED 6210014 |  | 2026-04-13 | Z | 2026-04-09 | 10 | 0 | 0 | 10 | 0 | 20 | 22GA GALV |  | 2 | 4
2026-04-06 | 10018 |  | 10018 | 20 | done | 2 | S |  | WHC 6250007 | pipe shop | 2026-04-06 | Z | 2026-04-02 | 20 | 0 | 0 | 20 | 0 | 60 |  | Pipe shop sleeves |  | 4
2026-04-07 | 82953 | sp | 82953 | A | done | 2 | S |  | WHC 6250007 |  | 2026-04-23 | Z | 2026-04-06 | 50 | 0 | 0 | 50 | 0 | 90 | 22GA GALV | Ground floor sleeves |  | 17
2026-04-10 | 74186 |  | 74186 | A | done | 2 | S |  | DOC JDC 6240023 | 1" board | 2026-04-13 | Z | 2026-04-09 | 20 | 0 | 0 | 20 | 10 | 80 | 18GA GALV | Dust coll on the roof | 5 | 4
2026-04-10 | 75059 |  | 75059 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-04-09 | 40 | 0 | 0 | 40 | 0 | 50 | 26GA GALV | DOAS taps | 10 | 5
2026-04-10 | 77045 |  | 77045,74896,74899 | A | done | 23 | M |  | GRANT ES 6250021 |  | 2026-04-27 | Z | 2026-04-01 | 140 | 0 | 430 | 570 | 0 | 770 | 24GA GALV | Main | 31 | 26
2026-04-10 | 97802 |  | 97802 | A | done | 2 | S |  | BROOM ST 6240033 | pipe shop | 2026-04-14 | Z | 2026-04-10 | 10 | 0 | 0 |  | 0 | 30 |  | Pipe shop caps | 11 | 4
2026-04-10 | 80453 |  | 80453 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-14 | Z | 2026-04-10 | 20 | 0 | 0 |  | 0 | 30 | 26GA GALV | West end caps | 9 | 4
2026-04-10 | 82842 | sp | 82842 | A | done | 3 | S/M |  | ANTIGO 6250017 | foam board | 2026-04-27 | Z | 2026-04-07 | 60 | 0 | 0 | 60 | 70 | 170 | 18GA GALV | Sleeves | 28 | 20 |  |  | 61.7% Short
[6 empty] | 738 | [12 empty] | 22930
WEEK OF 4-13-2026
2026-04-13 | 82837 | sp | 82837 | A | done | 3 | S |  | ANTIGO 6250017 | oval accu flange | 2026-04-13 | Z | 2026-03-30 | 0 | 60 | 0 | 0 | 0 | 90 |  | Area B north SA |  | 14
2026-04-14 | 82852 | sp | 82852 | A | done | 4 | S/M |  | ANTIGO 6250017 |  | 2026-04-20 | Z | 2026-04-09 | 80 | 0 | 0 | 80 | 0 | 230 | 20GA GALV | 1st floor area A | 4 | 11
2026-04-13 | 1778 |  | UNIT 1037 M4.70 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 210 | 0 | 70 | 280 | 0 | 290 | 26GA GALV |  | 44 | 43
2026-04-13 | 1780 |  | UNIT 1039 M4.72 | A | done | 10 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 240 | 0 | 0 | 240 | 0 | 260 | 26GA GALV |  | 40 | 43
2026-04-14 | 1788 |  | UNIT 900 M4.90 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 240 | 0 | 30 | 270 | 0 | 270 | 26GA GALV |  | 43 | 34
2026-04-15 | 1789 |  | UNIT 901 M4.91 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 190 | 0 | 80 | 270 | 0 | 290 | 26GA GALV |  | 38 | 34
2026-04-14 | 1790 |  | UNIT 903 M4.56 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  | 10 | 34
2026-04-15 | 1791 | bth | UNIT 905 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 14 | 34
2026-04-14 | 1792 | bth | UNIT 906 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 13 | 34
2026-04-14 | 1793 | bth | UNIT 907 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 12 | 34
2026-04-14 | 1794 | bth | UNIT 908 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 12 | 34
2026-04-15 | 1795 | bth | UNIT 909 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 200 | 26GA GALV |  | 14 | 34
2026-04-15 | 1796 | bth | UNIT 910 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 13 | 34
2026-04-15 | 1797 | bth | UNIT 911 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 12 | 34
2026-04-14 | 1798 | bth | UNIT 912 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 12 | 34
2026-04-15 | 1799 |  | UNIT 914 M4.61 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  | 10 | 34
2026-04-14 | 1800 |  | UNIT 915 M4.62 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  | 19 | 34
2026-04-14 | 1801 |  | UNIT 917 M4.63 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 120 | 0 | 70 | 190 | 0 | 180 | 26GA GALV |  | 25 | 34
2026-04-14 | 1802 |  | UNIT 918 M4.92 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 230 | 0 | 60 | 290 | 0 | 300 | 26GA GALV |  | 52 | 34
2026-04-15 | 1803 |  | UNIT 1000 M4.90 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 240 | 0 | 30 | 270 | 0 | 270 | 26GA GALV |  | 43 | 34
2026-04-15 | 1804 |  | UNIT 1001 M4.91 | A | done | 11 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 190 | 0 | 80 | 270 | 0 | 290 | 26GA GALV |  | 38 | 34
2026-04-15 | 1805 |  | UNIT 1003 M4.56 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  | 10 | 34
2026-04-15 | 1806 | bth | UNIT 1005 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 14 | 34
2026-04-15 | 1807 | bth | UNIT 1006 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 13 | 34
2026-04-15 | 1808 | bth | UNIT 1007 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 12 | 34
2026-04-15 | 1809 | bth | UNIT 1008 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 12 | 34
2026-04-15 | 1810 | bth | UNIT 1009 M4.57 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 14 | 34
2026-04-15 | 1811 | bth | UNIT 1010 M4.58 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 13 | 34
2026-04-15 | 1812 | bth | UNIT 1011 M4.59 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 12 | 34
2026-04-15 | 1813 | bth | UNIT 1012 M4.60 | A | done | 6 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 60 | 70 | 0 | 60 | 0 | 150 | 26GA GALV |  | 12 | 34
2026-04-15 | 1814 |  | UNIT 1014 M4.61 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 40 | 0 | 0 | 40 | 0 | 40 | 26GA GALV |  | 10 | 34
2026-04-15 | 1815 |  | UNIT 1015 M4.62 | A | done | 4 | S |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 90 | 0 | 0 | 90 | 0 | 100 | 26GA GALV |  | 19 | 34
2026-04-15 | 1816 |  | UNIT 1017 M4.63 | A | done | 8 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 120 | 0 | 70 | 190 | 0 | 180 | 26GA GALV |  | 25 | 34
2026-04-15 | 1817 |  | UNIT 1018 M4.92 | A | done | 12 | S/M |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-03-25 | 230 | 0 | 60 | 290 | 0 | 300 | 26GA GALV |  | 52 | 34
2026-04-13 | 1826 |  | DOAS-2 RISER L11-LR | A | done | 21 | M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-04-09 | 220 | 0 | 300 | 520 | 0 | 600 | 26GA GALV |  | 18 | 12
2026-04-13 | 1827 |  | DOAS-3 RISER | A | done | 24 | M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-04-09 | 210 | 0 | 390 | 600 | 0 | 640 | 26GA GALV |  | 30 | 12
2026-04-13 | 1828 |  | STAIR 2 RISER L11-LR | A | done | 25 | M/L |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-04-09 | 190 | 0 | 420 | 610 | 0 | 1000 | 20GA GALV |  | 18 | 12
2026-04-14 | 1829 |  | TRASH EXHAUST L11E-LRE | A | done | 21 | M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-04-09 | 120 | 0 | 390 | 510 | 0 | 640 | 24GA GALV |  | 27 | 12
2026-04-13 | 75060 |  | 75060-62 | A | done | 10 | M |  | BROOM ST 6240033 | mod | 2026-04-14 | Z | 2026-04-09 | 230 | 0 | 0 | 230 | 0 | 680 | 18GA GALV | Gen room EA | 8 | 19
2026-04-13 | 75063 |  | 75063 | A | done | 16 | M |  | BROOM ST 6240033 |  | 2026-04-16 | Z | 2026-04-13 | 390 | 0 | 0 | 390 | 0 | 450 | 26GA GALV | East tower | 38 | 3
2026-04-15 | 75064 |  | 75064 | A | done | 2 | S | alum | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-04-15 | 30 | 0 | 0 | 30 | 0 | 20 |  | EA amenities | 1 | 6
2026-04-16 | 75065 |  | 75065 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-16 | Z | 2026-04-16 | 50 | 0 | 0 | 50 | 0 | 100 | 22GA GALV | Gen EA | 1 | 0
2026-04-16 | 75651 |  | 75651 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-16 | Z | 2026-04-16 | 20 | 0 | 0 | 20 | 0 | 20 | 26GA GALV | Stair 5 out | 1 | 0
2026-04-13 | 78278 |  | 78278 | A | done | 2 | S | alum | BROOM ST 6240033 | flex | 2026-04-21 | Z | 2026-04-10 | 30 | 0 | 0 | 30 | 0 | 30 |  | EA | 1 | 11
2026-04-14 | 80454 |  | 80454 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-04-14 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV | LL west | 1 | 7
2026-04-16 | 6036 |  | DUCT RISER OA-02 | A | done | 18 | M |  | CHURCHILL 6250022 |  | 2026-04-23 | Z | 2026-04-15 | 50 | 0 | 390 | 440 | 0 | 600 | 24GA GALV |  | 15 | 8
2026-04-13 | 2052 |  | L1-B3d-RTU 11 | A | done | 4 | S/M |  | DC6 6250027 | flex | 2026-04-22 | Z | 2026-04-08 | 90 | 0 | 0 | 90 | 80 | 160 | 24GA GALVANEAL |  | 6 | 14
2026-04-13 | 2053 |  | L1-B3d-RTU 12 | A | done | 4 | S/M |  | DC6 6250027 | flex | 2026-04-22 | Z | 2026-04-08 | 90 | 0 | 0 | 90 | 80 | 140 | 24GA GALVANEAL |  | 6 | 14
2026-04-13 | 2054 |  | L1-B3d-RTU 13 | A | done | 4 | S/M |  | DC6 6250027 | flex | 2026-04-22 | Z | 2026-04-08 | 80 | 0 | 0 | 80 | 70 | 130 | 24GA GALVANEAL |  | 12 | 14
2026-04-13 | 53968 |  | 53968-69 | A | done | 8 | M |  | DC6 6250027 |  | 2026-04-15 | Z | 2026-04-13 | 180 | 0 | 0 | 180 | 0 | 440 | 18GA GALV | Backing | 53 | 2
2026-04-14 | 89490 | sp | 89490 | A | done | 2 | S |  | DMB 10068645 |  | 2026-04-14 | Z | 2026-04-14 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  | 1 | 0
2026-04-16 | 74452 |  | 74452 | A | done | 6 | S/M |  | DOC JDC 6240023 | paint black | 2026-04-20 | Z | 2026-04-15 | 130 | 0 | 0 | 130 | 90 | 170 | 24GA GALV | ceiling tie ins | 20 | 5
2026-04-16 | 74456 |  | 74456,101384 | A | done | 2 | S |  | DOC JDC 6240023 | 1" liner, paint black | 2026-04-20 | Z | 2026-04-15 | 30 | 0 | 0 | 30 | 20 | 40 | 24GA GALV | Kitchen transfer | 5 | 5
2026-04-16 | 74683 | sp | 74683 | A | done | 2 | S |  | FALL RIVER 6260002 |  | 2026-04-29 | Z | 2026-04-15 | 20 | 0 | 0 | 20 | 0 | 40 | 18GA GALV | Sleeves | 6 | 14
2026-04-13 | 74895 | sp | 74895 | A | done | 22 | M |  | GRANT ES 6250021 |  | 2026-04-27 | Z | 2026-04-01 | 80 | 450 | 0 | 80 | 0 | 520 | 24GA GALV | VAV's | 52 | 26
2026-04-16 | 41716 |  | 41716 | A | done | 2 | S |  | LABCORP 2250055 |  | 2026-04-20 | Z | 2026-04-16 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | Patch | 1 | 4
2026-04-15 | 41714 |  | 41714-15 | A | done | 2 | S/M |  | LABCORP 2260026 |  | 2026-04-15 | Z | 2026-04-09 | 20 | 0 | 0 | 20 | 0 | 110 |  |  | 10 | 6
2026-04-15 | 41850 |  | 41850 | A | done | 2 | S |  | MASTON R 6250019 |  | 2026-04-15 | Z | 2026-04-15 | 40 | 0 | 0 | 40 | 0 | 90 | 22GA GALV | MUA | 1 | 0
2026-04-15 | 78796 |  | 78796 | A | done | 2 | S |  | MONROE 6240018 |  | 2026-04-17 | Z | 2026-04-14 | 40 | 0 | 0 | 40 | 0 | 100 | 16GA GALV |  | 4 | 3
2026-04-15 | 84335 |  | 84335 | A | done | 2 | S |  | MPS 4260004 | 1" liner | 2026-04-17 | Z | 2026-04-15 | 40 | 0 | 0 | 40 | 20 | 70 | 20GA GALV | Access doors | 2 | 2
2026-04-16 | 83956 | sp | 83956 | A | done | 2 | S | pcd | PROMEGA BTC 6250020 |  | 2026-04-21 | Z | 2026-04-15 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA PCD | Misc | 7 | 6
2026-04-13 | 1254 |  | NORTH CHASE-EA-05 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-04-27 | Z | 2026-04-09 | 60 | 0 | 80 | 140 | 0 | 180 | 24GA GALV |  | 9 | 18
2026-04-13 | 1255 |  | NORTH CHASE-SAMP-09 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-04-27 | Z | 2026-04-09 | 40 | 0 | 90 | 130 | 0 | 160 | 24GA GALV |  | 8 | 18
2026-04-13 | 1256 |  | SOUTH CHASE-EA-05 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-04-27 | Z | 2026-04-09 | 100 | 0 | 50 | 150 | 0 | 190 | 24GA GALV |  | 15 | 18
2026-04-13 | 1257 |  | SOUTH CHASE-EA-06 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-04-27 | Z | 2026-04-09 | 10 | 0 | 30 | 40 | 0 | 50 | 24GA GALV |  | 3 | 18
2026-04-13 | 1258 |  | SOUTH CHASE-SAMP-08 | A | done | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-04-27 | Z | 2026-04-09 | 30 | 0 | 90 | 120 | 100 | 170 | 24GA GALV |  | 10 | 18
2026-04-13 | 1259 |  | SOUTH CHASE-SAMP-09 | A | done | 3 | S |  | SHRINE 6240034 | 1" liner | 2026-04-27 | Z | 2026-04-09 | 20 | 0 | 40 | 60 | 40 | 80 | 24GA GALV |  | 5 | 18
2026-04-14 | 1260 |  | L4-EA-01 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 100 | 0 | 0 | 100 | 0 | 140 | 24GA GALV |  | 26 | 25
2026-04-14 | 1261 |  | L4-EA-02 | A | done | 5 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 110 | 0 | 0 | 110 | 0 | 150 | 24GA GALV |  | 26 | 25
2026-04-13 | 1262 |  | L4-EA-03 | A | done | 4 | S |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 50 | 0 | 30 | 80 | 0 | 100 | 24GA GALV |  | 17 | 25
2026-04-14 | 1263 |  | L4-EA-04 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 130 | 0 | 0 | 130 | 0 | 180 | 24GA GALV |  | 38 | 25
2026-04-14 | 1264 |  | L4-EA-05 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 100 | 0 | 40 | 140 | 0 | 190 | 24GA GALV |  | 25 | 25
2026-04-14 | 1265 |  | L4-EA-06 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 130 | 0 | 0 | 130 | 0 | 190 | 24GA GALV |  | 21 | 25
2026-04-14 | 1266 |  | L4-EA-07 | A | done | 9 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 170 | 0 | 40 | 210 | 0 | 270 | 24GA GALV |  | 38 | 25
2026-04-15 | 1267 |  | L4-EA-08 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 140 | 0 | 0 | 140 | 0 | 200 | 24GA GALV |  | 36 | 25
2026-04-15 | 1268 |  | L4-SAMP-1 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 50 | 0 | 0 | 50 | 0 | 80 | 24GA GALV |  | 6 | 25
2026-04-14 | 1269 |  | L4-SAMP-2 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 30 | 0 | 60 | 90 | 0 | 110 | 24GA GALV |  | 11 | 25
2026-04-14 | 1270 |  | L4-SAMP-3 | A | done | 5 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 50 | 0 | 70 | 120 | 0 | 160 | 24GA GALV |  | 19 | 25
2026-04-14 | 1271 |  | L4-SAMP-4 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 50 | 0 | 0 | 50 | 0 | 80 | 24GA GALV |  | 14 | 25
2026-04-14 | 1272 |  | L4-SAMP-5 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 50 | 0 | 0 | 50 | 0 | 70 | 24GA GALV |  | 13 | 25
2026-04-14 | 1273 |  | L4-SAMP-6 | A | done | 6 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 130 | 0 | 0 | 130 | 0 | 180 | 24GA GALV |  | 26 | 25
2026-04-14 | 1274 |  | L4-SAMP-7 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 90 | 0 | 0 | 90 | 0 | 130 | 24GA GALV |  | 21 | 25
2026-04-14 | 1275 |  | L4-SAMP-8 | A | done | 4 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 100 | 0 | 0 | 100 | 0 | 160 | 24GA GALV |  | 24 | 25
2026-04-15 | 1276 |  | L4-SAMP-9 | A | done | 5 | S/M |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 100 | 0 | 20 | 120 | 0 | 150 | 24GA GALV |  | 26 | 25
2026-04-14 | 1277 | bth | L4-SAMP-10 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 20 | 10 | 0 | 20 | 0 | 50 | 24GA GALV |  | 5 | 25
2026-04-14 | 1278 |  | L4-SAMP-11 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 20 | 0 | 0 | 20 | 0 | 50 | 24GA GALV |  | 4 | 25
2026-04-14 | 1279 |  | L4-SAMP-12 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 10 | 0 | 0 | 10 | 0 | 30 | 24GA GALV |  | 2 | 25
2026-04-14 | 1280 |  | L4-SAMP-13 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-05-04 | Z | 2026-04-09 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  | 4 | 25
2026-04-15 | 85485 |  | 85485 | A | done | 2 | S |  | SHRINE 6240034 |  | 2026-04-20 | Z | 2026-04-15 | 0 | 0 | 50 | 50 | 0 | 60 |  | Misc L2 | 3 | 5
2026-04-13 | 77115 | sp | 77115 | A | done | 2 | S |  | TOMAH LAB 2250045 |  | 2026-04-14 | Z | 2026-04-10 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | Misc | 8 | 4
2026-04-15 | 72577 | sp | 72577 | A | done | 2 | S |  | UW LEVY HALL 6230028 |  | 2026-04-16 | Z | 2026-04-14 | 20 | 30 | 0 | 20 | 0 | 60 | 24GA GALV |  | 2 | 2
2026-04-14 | 84322 |  | 84322 | A | done | 4 | S/M |  | UW RESEARCH 4250056 | 1" liner | 2026-04-23 | Z | 2026-04-07 | 80 | 0 | 0 | 80 | 60 | 150 | 20GA GALV | MAU 1 | 10 | 16
2026-04-15 | 4584 |  | L3-SAT-2-3-15 | A | done | 13 | M |  | UW STOUT 6250008 | 1" liner | 2026-04-28 | Z | 2026-04-22 | 150 | 0 | 170 | 320 | 10 | 420 | 24GA GALV |  | 14 | 6
2026-04-13 | 4633 |  | L2-SAMP 14 | A | done | 12 | M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-03-13 | 160 | 0 | 120 | 280 | 0 | 740 | 18GA GALV |  | 4 | 39
2026-04-15 | 4636 | bth | L2-SAMP 25 | A | done | 18 | M |  | UW STOUT 6250008 |  | 2026-04-14 | Z | 2026-03-17 | 60 | 20 | 350 | 410 | 0 | 640 | 20GA GALV |  |  | 28
2026-04-15 | 4648 |  | L2-RAMP-10 | A | done | 6 | S/M |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 130 | 0 | 0 | 130 | 0 | 280 | 20GA GALV |  | 6 | 36
2026-04-15 | 4649 |  | L2-RAMP-11 | A | done | 7 | S/M |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 40 | 0 | 120 | 160 | 0 | 350 | 20GA GALV |  | 6 | 36
2026-04-15 | 4650 |  | L2-RAMP-12 | A | done | 12 | M |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 170 | 0 | 120 | 290 | 0 | 640 | 20GA GALV |  | 8 | 36
2026-04-15 | 4651 |  | L2-RAMP-13 | A | done | 10 | M |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 110 | 0 | 120 | 230 | 0 | 540 | 18GA GALV |  | 5 | 36
2026-04-15 | 4652 |  | L2-RAMP-14 | A | done | 6 | M |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 90 | 0 | 60 | 150 | 0 | 380 | 18GA GALV |  | 3 | 36
2026-04-15 | 4653 |  | L2-RAMP-16 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 30 | 0 | 0 | 30 | 0 | 60 | 22GA GALV |  | 2 | 36
2026-04-15 | 4654 |  | L2-RAMP-18 | A | done | 27 | L |  | UW STOUT 6250008 | v damper | 2026-04-28 | Z | 2026-03-23 | 200 | 0 | 470 | 670 | 0 | 1540 | 18GA GALV |  | 19 | 36
2026-04-15 | 4656 |  | L2-RAMP-25 | A | done | 9 | M |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 220 | 0 | 0 | 220 | 0 | 510 | 18GA GALV |  | 8 | 36
2026-04-15 | 4657 |  | L2-RAMP-26 | A | done | 23 | M/L |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 130 | 0 | 440 | 570 | 0 | 1130 | 20GA GALV |  | 18 | 36
2026-04-15 | 4658 |  | L2-RAMP-27 | A | done | 21 | M/L |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 200 | 0 | 320 | 520 | 0 | 1090 | 18GA GALV |  | 20 | 36
2026-04-16 | 4659 |  | L2-RAMP-19 | A | done | 16 | M/L |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 390 | 0 | 0 | 390 | 0 | 1030 | 18GA GALV |  | 5 | 36
2026-04-16 | 4660 |  | L2-RAMP-19.5 | A | done | 39 | L |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-03-23 | 830 | 0 | 140 | 970 | 0 | 2800 | 18GA GALV |  | 8 | 36
2026-04-16 | 4661 |  | L2-RAMP-15 | A | done | 11 | M | neal | UW STOUT 6250008 | v damper | 2026-04-28 | Z | 2026-03-23 | 200 | 0 | 60 | 260 | 0 | 610 | 18GA GALVANEAL |  | 8 | 36
2026-04-15 | 4689 |  | L3-SAT-1-3-5 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-04-28 | Z | 2026-04-01 | 40 | 0 | 0 | 40 | 20 | 30 | 24GA GALV |  | 4 | 27
2026-04-15 | 4690 |  | L3-SAT-1-3-7 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-04-28 | Z | 2026-04-01 | 20 | 10 | 0 | 20 | 20 | 30 | 24GA GALV |  | 5 | 27
2026-04-15 | 4691 |  | L3-SAT-1-3-8 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 20 | 10 | 0 | 20 | 0 | 30 | 24GA GALV |  | 4 | 27
2026-04-15 | 4692 |  | L3-SAT-1-3-9 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  | 6 | 27
2026-04-16 | 4693 |  | L3-SAT-1-3-10 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 20 | 10 | 0 | 20 | 0 | 30 | 24GA GALV |  | 5 | 27
2026-04-16 | 4694 |  | L3-SAT-1-3-11 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  | 6 | 27
2026-04-16 | 4695 |  | L3-SAT-1-3-12 | A | done | 3 | S | neal | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 50 | 10 | 0 | 50 | 0 | 90 | 24GA GALV |  | 14 | 27
2026-04-16 | 4696 |  | L3-SAT-1-3-13 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  | 4 | 27
2026-04-16 | 4697 |  | L3-SAT-1-3-14 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV |  | 3 | 27
2026-04-16 | 4698 |  | L3-SAT-1-3-15 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 20 | 10 | 0 | 20 | 0 | 40 | 24GA GALV |  | 4 | 27
2026-04-16 | 4699 |  | L3-SAT-1-3-16 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 20 | 0 | 0 | 20 | 0 | 40 | 24GA GALV |  | 3 | 27
2026-04-16 | 4701 |  | L3-SAT-1-3-18 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 30 | 10 | 0 | 30 | 0 | 60 | 24GA GALV |  | 8 | 27
2026-04-16 | 4703 |  | L3-CAV-4-3-1 | A | done | 10 | S/M |  | UW STOUT 6250008 | 1" liner | 2026-04-28 | Z | 2026-04-01 | 120 | 110 | 0 | 120 | 0 | 260 | 24GA GALV |  | 36 | 27
2026-04-15 | 77366 |  | 77366 | A | done | 10 | S/M |  | UW STOUT 6250008 |  | 2026-04-21 | Z | 2026-04-15 | 250 | 0 | 0 | 250 | 0 | 290 | 24GA GALV | Flashing | 120 | 6
2026-04-14 | 75437 | sp | 75437 | A | done | 3 | S |  | WAUNAKEE 6230013 |  | 2026-04-17 | Z | 2026-04-13 | 20 | 50 | 0 | 20 | 0 | 80 | 24GA GALV | EA | 9 | 4
2026-04-16 | 83431r |  | 83431 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-04-17 | Z | 2026-04-16 | 30 | 0 | 0 | 30 | 0 | 30 | 18GA GALV | Dust collector | 2 | 1
2026-04-13 | 82954 | sp | 82954 | A | done | 3 | S/M |  | WHC 6250007 |  | 2026-04-30 | Z | 2026-04-06 | 70 | 0 | 0 | 70 | 10 | 120 | 22GA GALV | Mezz level | 68 | 24
2026-04-13 | 89489 | sp | 89489 | A | done | 2 | S |  | WHC 6250007 |  | 2026-04-13 | Z | 2026-04-13 | 10 | 0 | 0 | 10 | 10 | 20 | 22GA GALV | Sleeve | 1 | 0
2026-04-14 | 95846 |  | 95846 | A | done | 2 | S |  | WHC 8250008 |  | 2026-04-14 | Z | 2026-04-14 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALV |  | 2 | 0
2026-04-15 | 10020 |  | 10020 | A | done | 9 | M |  | WSC 2260025 |  | 2026-04-15 | Z | 2026-04-14 | 210 | 0 | 0 | 210 | 0 | 610 | 18GA GALV |  | 72 | 1
2026-04-17 | 84337 | bth | 84337 | A | done | 2 | S |  | MPS 4260004 |  | 2026-04-17 | Z | 2026-04-16 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV |  | 4 | 1
2026-04-17 | 85488 |  | 85488 | A | done | 3 | S/M |  | SHRINE 6240034 |  | 2026-04-20 | Z | 2026-04-16 | 60 | 0 | 0 | 60 | 0 | 180 | 18GA GALV | Existing AHU repair | 16 | 4
2026-04-17 | 75066 |  | 75066 | A | done | 3 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-04-16 | 70 | 0 | 0 | 70 | 0 | 120 | 22GA GALV | Oval hangers | 146 | 5
2026-04-17 | 84336 |  | 84336 | A | done | 2 | S |  | PERNNIAL YOGA 10066867 |  | 2026-04-21 | Z | 2026-04-16 | 10 | 0 | 0 | 10 | 0 | 20 | 26GA GALV |  | 2 | 5
2026-04-17 | 55136 |  | 55136 | A | done | 2 | S |  | PROJECT DOVE 6240041 | birdscreen | 2026-04-22 | Z | 2026-04-16 | 10 | 0 | 0 | 10 | 0 | 40 | 24GA GALV | Birdscreen | 1 | 6
2026-04-17 | 6034 |  | DUCT RISER EA-02 | A | done | 23 | M |  | CHURCHILL 6250022 |  | 2026-04-23 | Z | 2026-04-15 | 430 | 0 | 130 | 560 | 0 | 770 | 24GA GALV |  | 32 | 8
2026-04-17 | 6038 |  | DUCT RISER SAMP-02 | A | done | 25 | M/L |  | CHURCHILL 6250022 |  | 2026-04-23 | Z | 2026-04-15 | 360 | 0 | 250 | 610 | 0 | 930 | 24GA GALV |  | 28 | 8
2026-04-17 | 76853 |  | 76853 | A | done | 2 | S |  | CHURCHILL 6250022 |  | 2026-04-23 | Z | 2026-04-16 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV | End caps | 17 | 7
2026-04-17 | 4662 |  | L2-RAMP-17 | A | done | 11 | M | neal | UW STOUT 6250008 | v damper | 2026-04-28 | Z | 2026-03-23 | 160 | 0 | 100 | 260 | 0 | 450 | 20GA GALV |  | 10 | 36
2026-04-17 | 4700 |  | L3-SAT-1-3-17 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-01 | 40 | 0 | 0 | 40 | 0 | 50 | 24GA GALV |  | 5 | 27
2026-04-17 | 4702 |  | L3-SAT-1-3-19 | A | done | 2 | S |  | UW STOUT 6250008 | 1" liner | 2026-04-28 | Z | 2026-04-01 | 20 | 10 | 0 | 20 | 20 | 40 | 24GA GALV |  | 6 | 27
2026-04-17 | 84586 |  | 84586 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-16 | 20 | 0 | 0 | 20 | 0 | 20 | 24GA GALV | 2nd SAMP | 3 | 12
2026-04-17 | 10020 |  | 58182 | A | done | 5 | S/M |  | BROOM ST 6240033 | rivet nuts | 2026-04-29 | Z | 2026-04-16 | 110 | 0 | 0 | 110 | 0 | 260 | 18GA GALV | OA kits | 27 | 13
2026-04-17 | 3013 |  | SA 7.2 | A | done | 7 | S/M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 20 | 140 | 0 | 20 | 0 | 180 | 24GA GALV |  | 11 | 15
2026-04-17 | 3014 |  | SA 8.1 | A | done | 6 | S/M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 20 | 110 | 0 | 20 | 0 | 150 | 24GA GALV |  | 12 | 15
2026-04-17 | 3015 |  | SA 8.2 | A | done | 5 | S/M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 10 | 100 | 0 | 10 | 0 | 130 | 24GA GALV |  | 24 | 15
2026-04-17 | 74459 |  | 74459 | A | done | 2 | S |  | DOC JDC 6240023 |  | 2026-04-20 | Z | 2026-04-17 | 10 | 0 | 0 | 10 | 0 | 30 | 18GA GALVANEAL | Hole cover | 1 | 3
2026-04-17 | 76751 |  | 76751 | A | done | 2 | S |  | PORTAGE MS 6250018 |  | 2026-04-20 | Z | 2026-04-17 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALVANEAL | SGI room | 1 | 3 |  |  | 35.2% Short
[6 empty] | 966 | [12 empty] | 34580
WEEK OF 4-20-2026
2026-04-20 | 1777 |  | UNIT 1036 M4.69 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-03-09 | 90 | 0 | 20 | 110 | 0 | 110 | 26GA GALV |  | 17 | 43
2026-04-21 | 10021 |  | 58194 | A | done | 5 | S/M |  | BROOM ST 6240033 |  | 2026-05-05 | Z | 2026-04-16 | 120 | 0 | 0 | 120 | 0 | 130 | 26GA GALV | Grille boxes west | 26 | 19
2026-04-20 | 75067 |  | 75067 | A | done | 4 | S/M |  | BROOM ST 6240033 | paint black | 2026-04-28 | Z | 2026-04-16 | 100 | 0 | 0 | 100 | 90 | 110 | 26GA GALV |  | 27 | 12
2026-04-20 | 80455 |  | 80455 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-21 | Z | 2026-04-20 | 20 | 0 | 0 | 20 | 0 | 20 | 26GA GALV | 8th west | 2 | 1
2026-04-21 | 80456 |  | 80456 | A | done | 2 | S |  | BROOM ST 6240033 |  | 2026-04-28 | Z | 2026-04-21 | 40 | 0 | 0 | 40 | 0 | 40 |  | 8th floor | 1 | 7
2026-04-20 | 6033 |  | DUCT RISER EA-01 | A | done | 19 | M |  | CHURCHILL 6250022 |  | 2026-04-30 | Z | 2026-04-15 | 280 | 0 | 190 | 470 | 0 | 690 | 24GA GALV |  | 18 | 15
2026-04-20 | 6035 |  | DUCT RISER OA-01 | A | done | 12 | S/M |  | CHURCHILL 6250022 |  | 2026-04-30 | Z | 2026-04-15 | 20 | 0 | 260 | 280 | 0 | 350 | 24GA GALV |  | 90 | 15
2026-04-21 | 6037 |  | DUCT RISER SAMP-01 | A | done | 21 | M/L |  | CHURCHILL 6250022 |  | 2026-04-30 | Z | 2026-04-15 | 330 | 0 | 190 | 520 | 0 | 850 | 20GA GALV |  | 22 | 15
2026-04-20 | 6039 |  | EF-1 DUCT RISER EA-01 | A | done | 10 | S/M |  | CHURCHILL 6250022 |  | 2026-04-30 | Z | 2026-04-15 | 100 | 0 | 150 | 250 | 0 | 270 | 26GA GALV |  | 13 | 15
2026-04-20 | 6040 |  | EF-1 DUCT RISER EA-02 | A | done | 16 | M |  | CHURCHILL 6250022 |  | 2026-04-30 | Z | 2026-04-15 | 110 | 0 | 270 | 380 | 0 | 410 | 26GA GALV |  | 21 | 15
2026-04-20 | 6041 |  | SF-1 DUCT RISER SALP-01 | A | done | 10 | S/M |  | CHURCHILL 6250022 |  | 2026-04-30 | Z | 2026-04-15 | 70 | 0 | 170 | 240 | 0 | 250 | 26GA GALV |  | 13 | 15
2026-04-20 | 6042 |  | SF-1 DUCT RISER SALP-02 | A | done | 12 | S/M |  | CHURCHILL 6250022 |  | 2026-04-30 | Z | 2026-04-15 | 70 | 0 | 220 | 290 | 0 | 300 | 26GA GALV |  | 18 | 15
2026-04-20 | 2056 |  | L1-C2-RTU 17 | A | done | 4 | S/M |  | DC6 6250027 | flex | 2026-04-29 | Z | 2026-04-09 | 90 | 0 | 0 | 90 | 80 | 140 | 24GA GALVANEAL |  | 6 | 20
2026-04-20 | 2057 |  | L1-C2-RTU 18 | A | done | 4 | S/M |  | DC6 6250027 | flex | 2026-04-29 | Z | 2026-04-09 | 90 | 0 | 0 | 90 | 80 | 160 | 22GA GALVANEAL |  | 6 | 20
2026-04-20 | 2058 |  | L1-C3-RTU 16 | A | done | 4 | S/M |  | DC6 6250027 | flex | 2026-04-29 | Z | 2026-04-09 | 90 | 0 | 0 | 90 | 80 | 140 | 24GA GALVANEAL |  | 6 | 20
2026-04-20 | 2059 |  | L1-C3-RTU 15 | A | done | 4 | S/M |  | DC6 6250027 | flex | 2026-04-29 | Z | 2026-04-09 | 80 | 0 | 0 | 80 | 60 | 120 | 24GA GALVANEAL |  | 6 | 20
2026-04-20 | 74842 |  | 74842 | A | done | 2 | S |  | EMP 1000110 |  | 2026-04-17 | Z | 2026-04-17 | 10 | 0 | 0 | 10 | 0 | 20 | 24GA GALV |  | 1 | 0
2026-04-20 | 3000 |  | SA 3 | A | done | 28 | M/L |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 270 | 0 | 410 | 680 | 0 | 910 | 24GA GALV |  | 28 | 15
2026-04-20 | 3001 |  | SA 4 | A | done | 12 | M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 60 | 0 | 240 | 300 | 0 | 380 | 24GA GALV |  | 18 | 15
2026-04-20 | 3002 |  | SA 5 | A | done | 19 | M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 290 | 0 | 180 | 470 | 0 | 690 | 24GA GALV |  | 18 | 15
2026-04-20 | 3003 |  | SA 6 | A | done | 20 | M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 130 | 0 | 350 | 480 | 0 | 620 | 24GA GALV |  | 29 | 15
2026-04-20 | 3004 |  | SA 7 | A | done | 19 | M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 200 | 0 | 270 | 470 | 0 | 650 | 24GA GALV |  | 24 | 15
2026-04-20 | 3005 |  | SA 8 | A | done | 27 | M/L |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 270 | 0 | 390 | 660 | 0 | 880 | 24GA GALV |  | 41 | 15
2026-04-20 | 3006 |  | SA 3.1 | A | done | 2 | S |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 0 | 20 | 0 | 0 | 0 | 20 |  |  | 2 | 15
2026-04-20 | 3007 |  | SA 3.2 | A | done | 4 | S |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 10 | 70 | 0 | 10 | 0 | 90 | 24GA GALV |  | 7 | 15
2026-04-20 | 3008 |  | SA 4.1 | A | done | 2 | S |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 10 | 40 | 0 | 10 | 0 | 70 | 24GA GALV |  | 7 | 15
2026-04-20 | 3009 |  | SA 5.1 | A | done | 2 | S |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 0 | 40 | 0 | 0 | 0 | 40 |  |  | 3 | 15
2026-04-20 | 3010 |  | SA 6.1 | A | done | 2 | S |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 0 | 50 | 0 | 0 | 0 | 60 |  |  | 3 | 15
2026-04-20 | 3011 |  | SA 6.2 | A | done | 4 | S/M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 10 | 80 | 0 | 10 | 0 | 110 | 24GA GALV |  | 7 | 15
2026-04-20 | 3012 |  | SA 7.1 | A | done | 8 | S/M |  | EXACT PASP 2260014 |  | 2026-04-29 | Z | 2026-04-14 | 20 | 160 | 0 | 20 | 0 | 200 | 24GA GALV |  | 12 | 15
2026-04-20 | 76467 |  | 76467 | A | done | 2 | S |  | LAKE MILLS ES 6250012 |  | 2026-05-01 | Z | 2026-04-20 | 20 | 0 | 0 | 20 | 0 | 40 | 20GA GALV |  | 9 | 11
2026-04-21 | 76470 | sp | 76467 | A | done | 4 | S/M |  | LAKE MILLS ES 6250012 |  | 2026-05-01 | Z | 2026-04-20 | 90 | 0 | 0 | 90 | 0 | 130 | 24GA GALV |  | 36 | 11
2026-04-20 | 77331 |  | 77331 | A | done | 2 | S |  | LAKE MILLS ES 6250012 | 1" liner | 2026-04-21 | Z | 2026-04-20 | 30 | 0 | 0 | 30 | 30 | 50 | 24GA GALV | Misc | 1 | 1
2026-04-20 | 76753 | w | 76753 | A | done | 2 | S |  | PORTAGE MS 6250018 |  | 2026-04-23 | Z | 2026-04-17 | 10 | 0 | 0 | 10 | 10 | 30 | 18GA GALV | Pipe curb extension | 1 | 6
2026-04-20 | 85486 |  | 85486 | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-04-27 | Z | 2026-04-16 | 50 | 0 | 0 | 50 | 40 | 60 | 24GA GALV | L2 misc | 10 | 11
2026-04-20 | 85487 |  | 85487 | A | done | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-04-27 | Z | 2026-04-17 | 20 | 0 | 0 | 20 | 10 | 50 | 18GA GALV | Misc | 4 | 10
2026-04-21 | 4731 |  | L2-VAV-1-2-14 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | Z | 2026-04-16 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV |  | 5 | 19
2026-04-21 | 4745 |  | L2-VAV-1-2-27 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | Z | 2026-04-16 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV |  | 5 | 19
2026-04-21 | 4746 |  | L2-VAV-1-2-28 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-05-05 | Z | 2026-04-16 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV |  | 5 | 19
2026-04-21 | 77368 |  | 77368 | A | done | 2 | S |  | UW STOUT 6250008 |  | 2026-04-28 | Z | 2026-04-20 | 30 | 0 | 0 | 30 | 0 | 100 | 18GA GALV | Roof | 1 | 8
2026-04-20 | 76128 |  | 76128 | A | done | 6 | S/M |  | UWP 6240021 |  | 2026-04-23 | Z | 2026-04-08 | 140 | 0 | 0 | 140 | 0 | 320 | 20GA GALV | AHU 4 SA | 7 | 15
2026-04-20 | 76129 |  | 76129 | A | done | 2 | S |  | UWP 6240021 |  | 2026-04-30 | Z | 2026-04-16 | 30 | 0 | 0 | 30 | 0 | 40 | 24GA GALV | DOAS 1 SA | 1 | 14
2026-04-20 | 75362 |  | 75362 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-04-24 | Z | 2026-04-17 | 20 | 0 | 0 | 20 | 0 | 30 | 24GA GALV | RG | 3 | 7
2026-04-20 | 75367 | sp | 75367 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-04-24 | Z | 2026-04-17 | 10 | 0 | 0 | 10 | 0 | 20 | 18GA GALVANEAL | Tech ed dc | 6 | 7
2026-04-20 | 76468 |  | 76468 | A | done | 2 | S |  | WAUNAKEE 6230013 |  | 2026-04-24 | Z | 2026-04-20 | 10 | 0 | 0 | 10 | 10 | 20 | 24GA GALVANEAL |  | 1 | 4
2026-04-21 | 75101 |  | 75101 | A | done | 4 | S/M |  | WHC 6250007 |  | 2026-04-27 | Z | 2026-04-20 | 100 | 0 | 0 | 100 | 0 | 260 | 18GA GALV |  | 7 | 7
2026-04-21 | [5 empty] | 325 | [12 empty] | 10100
2026-04-21
2026-04-21
2026-04-21
2026-04-21
2026-04-21
2026-04-21
2025-11-06
2025-11-06
2025-11-06
Formulas:
DATE = IF([TO#'S]<>"",TODAY(),"")

## Completed TO# List 2025
COMPLETED TO#'s | [10 empty] | SHEET SHOP - 2025
| TO#'S |  | SKETCH/SPOOL #'S | STATUS | DONE | SIZE |  | METAL | JOB NAME |  |  |  | DATE | PLASMA | SPIRAL | C.LINE | C.LINE | INSU | LBS.
COMPLETED | [6 empty] | EST. |  |  | SPECIAL | NEED | Priority | RCVD | SQ FT | SQ FT | SQ FT | STATUS | SQ FT
DATE | [6 empty] | SIZE | ETC. |  | NOTES | DATE | 0.5 | Pounds completed to date this week = | [5 empty] | 1910224 |  | Description | Semi / # | Lead Time | Original need date
WEEK OF 1-6-2025
2025-01-10 | 1216 |  | 81946 - 81947 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 | bird s. , CD | 2025-01-15 | Z | 2025-01-03 | 300 | 0 | 0 |  | 0 | 1010 |  | MAU-2 D-4 , MAU-3 D-5 |  | 12
2025-01-08 | 2248 |  | 80080 | A | DONE | 10 | S-M |  | 121 E. WILSON 6230024 | paint | 2025-01-10 | Z | 2024-07-25 | 50 | 0 | 190 | F | 20 | 270 |  | DOAS-2 / OA-5 |  | 169
2025-01-08 | 3662 |  | 80101 , 80107 | A | DONE | 21 | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-10 | Z | 2024-07-30 | 130 | 0 | 390 | F | 0 | 550 |  | EF-3,4 , EA-6 |  | 164
2025-01-08 | 3695 |  | Stairwell B-EA 10 | A | DONE | 14 | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-10 | Z | 2024-08-07 | 80 | 0 | 250 | F | 0 | 440 |  |  |  | 156
2025-01-09 | 3909g |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-01-15 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 11th Fl. East unit plenums |  | 156
2025-01-09 | 3910g |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-15 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 11th Fl. East Taps |  | 156
2025-01-09 | 3911g |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-15 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 11th Fl. East sliders |  | 156
2025-01-09 | 3912g |  | 80149 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-01-15 | Z | 2024-08-12 | 30 | 0 | 0 |  | 0 | 40 |  | 11th Fl. East unit SA |  | 156
2025-01-09 | 3913g |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-01-15 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 11th Fl. East Corr. HP's |  | 156
2025-01-08 | 3915h | sp | 81902 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-10 | Z | 2024-08-12 | 20 | 90 | 0 |  | 0 | 90 |  | 12th Fl. OA |  | 151
2025-01-08 | 3916h |  | 81903 - 81904 | A | DONE | 34 | M |  | 121 E. WILSON 6230024 |  | 2025-01-10 | Z | 2024-08-12 | 830 | 0 | 0 |  | 0 | 890 |  | 12th Fl. East EA |  | 151
2025-01-06 | 787 |  | 63391,96-99 | A | DONE | 42 | L |  | BMH AHU9 6240001 |  | 2025-01-08 | Z | 2024-12-23 | 590 | 0 | 450 | F | 0 | 1860 |  | MECH RM |  | 17
2025-01-06 | 788 |  | 63392 | F | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-01-08 | Z | 2024-12-30 | 20 | 0 | 0 |  | 0 | 30 |  | TEMP HUMID |  | 10
2025-01-09 | 790 |  | 63401 , 63401A | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-01-16 | Z | 2024-12-31 | 50 | 0 | 0 |  | 0 | 60 |  | CS VAV 9.9R |  | 16
2025-01-09 | 791 | sp | 63402 - 63404 | A | DONE | 14 | S-M |  | BMH AHU9 6240001 |  | 2025-01-16 | Z | 2024-12-31 | 80 | 270 | 0 |  | 0 | 400 |  | VAV's |  | 16
2025-01-09 | 792 |  | 63405 , 63407 | A | DONE | 4 | S |  | BMH AHU9 6240001 |  | 2025-01-16 | Z | 2024-12-31 | 50 | 0 | 30 | F | 0 | 80 |  | VAV 9.2R , 9.2S HP |  | 16
2025-01-09 | 793 |  | 63409 , 63411 | A | DONE | 8 | S-M |  | BMH AHU9 6240001 |  | 2025-01-16 | Z | 2024-12-31 | 50 | 0 | 140 | F | 0 | 260 |  | CS SAHP |  | 16
2025-01-09 | 794 |  | 63414 - 63415 | A | DONE | 13 | S-M |  | BMH AHU9 6240001 |  | 2025-01-16 | Z | 2024-12-31 | 100 | 0 | 220 | F | 0 | 380 |  | SA SALP Hallway |  | 16
2025-01-09 | 795 |  | 67246 | A | DONE | 12 | S-M |  | BMH AHU9 6240001 |  | 2025-01-16 | Z | 2024-12-31 | 140 | 0 | 140 | F | 0 | 380 |  | CS RALP |  | 16
2025-01-07 | 2095 |  | 69725 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2025-01-10 | Z | 2025-01-03 | 30 | 0 | 0 |  | 40 | 60 |  | Grille box 1st |  | 7
2025-01-07 | 2096 |  | 81613 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2025-01-10 | Z | 2025-01-03 | 20 | 0 | 0 |  | 20 | 20 |  | 7th floor |  | 7
2025-01-07 | 2097 |  | 69726 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2025-01-10 | Z | 2025-01-06 | 30 | 0 | 0 |  | 30 | 60 |  | Grill TA |  | 4
2025-01-07 | 2098 |  | 69727 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2025-01-10 | Z | 2025-01-06 | 90 | 0 | 0 |  | 70 | 120 |  | Bathroom TA |  | 4
2025-01-10 | 2450 |  | 81526 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2025-01-13 | Z | 2025-01-10 | 20 | 0 | 0 |  | 0 | 20 |  | Vent / Drain covers |  | 3
2025-01-09 | 813 |  | 70708 - 70709 | A | DONE | 17 | S-M | pcd | DELLSHIRE 6240017 |  | 2025-01-13 | Z | 2024-11-27 | 310 | 0 | 110 | F | 0 | 730 |  | Pool RA |  | 47
2025-01-09 | 814 |  | 70710 - 70711 | A | DONE | 28 | S-M | pcd | DELLSHIRE 6240017 |  | 2025-01-13 | Z | 2024-11-27 | 520 | 0 | 160 | F | 0 | 1490 |  | Pool RA |  | 47
2025-01-09 | 815 |  | 70712 - 70713 | A | DONE | 14 | S-M | pcd | DELLSHIRE 6240017 |  | 2025-01-13 | Z | 2024-11-27 | 150 | 0 | 200 | F | 0 | 630 |  | Pool RA |  | 47
2025-01-08 | 160 | sp | 70236 | A | DONE | 2 | S |  | ENCAPSYS 10059905 |  | 2025-01-10 | Z | 2025-01-07 | 20 | 20 | 0 |  | 0 | 60 |  | Intake |  | 3
2025-01-08 | 161 |  | 70234 | A | DONE | 2 | S |  | ENCAPSYS 10059905 |  | 2025-01-10 | Z | 2025-01-07 | 20 | 0 | 0 |  | 0 | 20 |  | Filter rack |  | 3
2025-01-08 | 1135 |  | 56693 | A | DONE | 2 | S |  | EXACT QC LAB 2240070 | paint | 2025-01-13 | Z | 2025-01-06 | 30 | 0 | 0 |  | 20 | 40 |  | GRD |  | 7
2025-01-10 | 1137 |  | 56695 | A | DONE | 2 | S | ss | EXACT SCIENCE 8240020 |  | 2025-01-13 | Z | 2025-01-10 | 20 | 0 | 0 |  | 0 | 20 |  | Plate |  | 3
2025-01-09 | 1136 | sp | 56694 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2025-01-13 | Z | 2025-01-08 | 20 | 20 | 0 |  | 0 | 40 |  | Cabinet EA |  | 5
2025-01-06 | 2932 |  | 82564 | A | DONE | 7 | M |  | LABCORP 6240016 |  | 2025-01-08 | Z | 2024-12-31 | 160 | 0 | 0 |  | 0 | 330 |  | Roof tie ins |  | 8
2025-01-09 | 2934 |  | 82566 | A | DONE | 2 | S-M |  | LABCORP 6240016 |  | 2025-01-13 | Z | 2025-01-08 | 40 | 0 | 0 |  | 0 | 70 |  | Humidifier |  | 5
2025-01-09 | 156 |  | 68141 - 68142 | A | DONE | 2 | S | ss | MEMORIAL HS 6210024 |  | 2025-01-09 | Z | 2024-12-23 | 40 | 0 | 0 |  | 0 | 130 |  | DRAWBANDS |  | 16
2025-01-09 | 164 |  | EMAIL | A | DONE | 2 | S |  | OCTOPI 8240031 |  | 2025-01-09 | Z | 2025-01-09 | 20 | 0 | 0 |  | 0 | 20 |  | Cap |  | 0
2025-01-09 | 162 |  | 79432 | A | DONE | 2 | S |  | PLACON 10059987 |  | 2025-01-14 | Z | 2025-01-07 | 20 | 0 | 0 |  | 0 | 20 |  | Beauty ring |  | 7
2025-01-06 | 2529 |  | 81826 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-01-13 | Z | 2025-01-03 | 20 | 0 | 0 |  | 0 | 20 |  | Roof |  | 10
2025-01-08 | 2530 |  | 59838 | A | DONE | 13 | S-M |  | PROMEGA BTC 6230022 |  | 2025-01-13 | Z | 2025-01-03 | 320 | 0 | 0 |  | 0 | 860 |  | AHU-Louver |  | 10
2025-01-09 | 2531 | sp | 81828 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2025-01-10 | Z | 2025-01-08 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2025-01-08 | 159 | sp | 70237 | A | DONE | 2 | S |  | REYNOLDS 10059942 |  | 2025-01-09 | Z | 2025-01-07 | 20 | 20 | 0 |  | 0 | 40 |  | Misc |  | 2
2025-01-09 | 4786 |  | 61195 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2025-01-16 | Z | 2025-01-06 | 20 | 0 | 0 |  | 0 | 30 |  | Remodel |  | 10
2025-01-10 | 4787 |  | 61196 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2025-01-16 | Z | 2025-01-09 | 20 | 0 | 0 |  | 0 | 30 |  | Remodel |  | 7
2025-01-06 | 482 |  | L02_EAD_001 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 110 | 0 | 30 | F | 0 | 210 |  |  |  | 56
2025-01-06 | 483 | bth | L02_EAD_002 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 60 | 40 | 30 | F | 0 | 140 |  |  |  | 56
2025-01-06 | 484 | bth | L02_EAD_003 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 40 | 40 | 0 |  | 0 | 90 |  |  |  | 56
2025-01-06 | 485 |  | L02_EAD_004 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 50 | 0 | 50 | F | 0 | 130 |  |  |  | 56
2025-01-06 | 489 | bth | L02_SAMP_003 | A | DONE | 9 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 70 | 40 | 110 | F | 0 | 270 |  |  |  | 56
2025-01-07 | 490 | bth | L02_SAMP_005 | A | DONE | 10 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 180 | 20 | 40 | F | 0 | 330 |  |  |  | 56
2025-01-07 | 491 | bth | L02_SAMP_006 | A | DONE | 10 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 90 | 60 | 80 | F | 0 | 300 |  |  |  | 56
2025-01-07 | 492 | bth | L02_SAMP_007 | A | DONE | 11 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 30 | 20 | 220 | F | 0 | 330 |  |  |  | 56
2025-01-07 | 493 | bth | L02_SAMP_008 | A | DONE | 8 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 70 | 40 | 90 | F | 0 | 240 |  |  |  | 56
2025-01-07 | 494 | bth | L02_SAMP_009 | A | DONE | 7 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-11-14 | 50 | 30 | 80 | F | 0 | 200 |  |  |  | 56
2025-01-10 | 1159 | bth | L02_A_SALP-012 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 62
2025-01-10 | 1165 | sp | L02_A_SALP-018 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 80 | 0 |  | 0 | 100 |  |  |  | 62
2025-01-10 | 1177 |  | L02_A_TAD_006 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-16 | Z | 2024-11-15 | 100 | 0 | 0 |  | 70 | 160 |  |  |  | 62
2025-01-06 | 1178 |  | L02_A_TAD_007 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-09 | Z | 2024-11-15 | 150 | 0 | 0 |  | 120 | 210 |  |  |  | 55
2025-01-07 | 2802 |  | L02_A_EAD_008 | A | DONE | 3 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2024-12-11 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 29
2025-01-06 | 2808 |  | 83029 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | paint | 2025-01-09 | Z | 2024-12-31 | 80 | 0 | 0 |  | 40 | 140 |  | 2nd floor B finish |  | 9
2025-01-06 | 2809 | sp | 83030 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2025-01-02 | 20 | 20 | 0 |  | 0 | 30 |  | CAD fix |  | 7
2025-01-07 | 2811 |  | 82958 | A | DONE | 2 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-09 | Z | 2025-01-06 | 40 | 0 | 0 |  | 30 | 60 |  | 2nd floor A |  | 3
2025-01-07 | 2812 | sp | 83032 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-01-09 | Z | 2025-01-07 | 0 | 30 | 0 |  | 0 | 30 |  | Paint grip |  | 2
2025-01-10 | 2813 |  | 83033 | A | DONE | 12 | S-M | pt. alum | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2025-01-09 | 280 | 0 | 0 |  | 0 | 390 |  | 1st fl B |  | 7
2025-01-10 | 165 |  | 70238 | A | DONE | 2 | S |  | THERMO FISHER 6249999 |  | 2025-01-13 | Z | 2025-01-10 | 50 | 0 | 0 |  | 0 | 50 |  | Misc |  | 3
2025-01-08 | 4589 |  | 83910 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-01-20 | Z | 2024-12-23 | 20 | 0 | 0 |  | 0 | 80 |  | 5TH FL EX SLEEVE |  | 22
2025-01-07 | 3301 |  | 66885-86 | A | DONE | 2 | S-M |  | UWRF 6230010 |  | 2024-01-14 | Z | 2024-12-30 | 30 | 0 | 0 |  | 0 | 150 |  | OA BOX |  | 15
2025-01-09 | 3302 |  | 83531 | A | DONE | 22 | L |  | UWRF 6230010 |  | 2024-01-14 | Z | 2024-12-30 | 540 | 0 | 0 |  | 0 | 1500 |  | AH1-C |  | 15
2025-01-06 | 1391 |  | OA-04-03 | A | DONE | 38 | M |  | UWSP ALBERTSON 6230016 |  | 2024-01-07 | Z | 2024-12-24 | 860 | 0 | 90 | F | 0 | 2440 |  |  |  | 14
2025-01-06 | 1393 |  | OA-04-05 | A | DONE | 20 | M |  | UWSP ALBERTSON 6230016 |  | 2024-01-07 | Z | 2024-12-24 | 190 | 0 | 310 | F | 0 | 630 |  |  |  | 14
2025-01-08 | 1394 |  | 81167 | A | DONE | 9 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-01-14 | Z | 2024-12-30 | 210 | 0 | 0 |  | 0 | 300 |  | STRAPS |  | 15
2025-01-09 | 1395 |  | 81166,81556 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-01-14 | Z | 2024-12-30 | 20 | 20 | 0 |  | 0 | 30 |  | SAT 1-1-11/SA-04-07 |  | 15
2025-01-08 | 1399 |  | 81168 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-01-14 | Z | 2025-01-03 | 20 | 0 | 0 |  | 0 | 20 |  | LPSA 01-09 |  | 11
2025-01-08 | 2350 | sp | 81169 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-01-14 | Z | 2025-01-03 | 20 | 20 | 0 |  | 0 | 40 |  | 4th fl-SAT 1-4-6 |  | 11
2025-01-08 | 2351 |  | prefab hangers | A | DONE | 6 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-01-14 | Z | 2025-01-03 | 130 | 0 | 0 |  | 0 | 380 |  | Saddle hangers |  | 11
2025-01-09 | 2353 |  | 64710 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-01-21 | Z | 2025-01-06 | 20 | 0 | 0 |  | 0 | 20 |  | Roof rain cap flashing |  | 15
2025-01-08 | 2383 |  | RA-03-03 | delete |  |  | M-L |  | UWSP ALBERTSON 6230016 | VD | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2384 | bth | RA-03-04 | delete |  |  | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2385 | bth | RA-03-05 | delete |  |  | S-M |  | UWSP ALBERTSON 6230016 | VD's | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2386 | bth | RA-03-06 | delete |  |  | M |  | UWSP ALBERTSON 6230016 |  | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2387 |  | RA-03-07 | delete |  |  | M-L |  | UWSP ALBERTSON 6230016 | VD's | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2388 |  | RA-03-08 | delete |  |  | M |  | UWSP ALBERTSON 6230016 | VD's | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2389 |  | RA-03-10 | delete |  |  | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2390 |  | RA-03-11 | delete |  |  | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2391 |  | RA-03-12 | delete |  |  | S |  | UWSP ALBERTSON 6230016 | VD | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-08 | 2392 | bth | RA-03-13 | delete |  |  | S |  | UWSP ALBERTSON 6230016 |  | 2025-02-11 | Z | 2025-01-07 | [5 empty] | 0 |  |  |  | 35
2025-01-09 | 2743 |  | L1E_RA 1 | A | DONE | 18 | M | pt.neal | UWSP CHAMPION HALL 6240008 |  | 2025-01-14 | Z | 2025-01-02 | 270 | 0 | 160 | F | 0 | 770 |  |  |  | 12
2025-01-10 | 2756 |  | 70132 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-14 | Z | 2025-01-09 | 50 | 0 | 0 |  | 50 | 80 |  | TA |  | 5
2025-01-07 | 2103 | bth | L02_F_SALP_001 | A | DONE | 3 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 30 | 30 | 0 |  | 0 | 60 |  |  |  | 45
2025-01-07 | 2104 | bth | L02_F_SALP_002 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 80 | 40 | 0 |  | 0 | 150 |  |  |  | 45
2025-01-07 | 2105 | bth | L02_F_SALP_003 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 90 | 50 | 70 | F | 0 | 230 |  |  |  | 45
2025-01-07 | 2106 | bth | L02_F_SALP_004 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 70 | 70 | 70 | F | 0 | 240 |  |  |  | 45
2025-01-07 | 2107 | bth | L02_F_SALP_005 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 45
2025-01-07 | 2108 | bth | L02_F_SALP_006 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 50 | 40 | 90 | F | 0 | 210 |  |  |  | 45
2025-01-07 | 2109 | bth | L02_F_SALP_007 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 30 | 50 | 120 | F | 0 | 220 |  |  |  | 45
2025-01-07 | 2110 | bth | L02_F_SALP_008 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 30 | 50 | 120 | F | 0 | 220 |  |  |  | 45
2025-01-07 | 2111 | bth | L02_F_SALP_009 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 60 | 50 | 30 | F | 0 | 140 |  |  |  | 45
2025-01-07 | 2112 | bth | L02_F_SALP_010 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-10 | Z | 2024-11-26 | 30 | 70 | 70 | F | 0 | 190 |  |  |  | 45
2025-01-06 | 2113 | sp | L02_F_SALP_011 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-10 | Z | 2024-11-26 | 20 | 100 | 0 |  | 0 | 110 |  |  |  | 45
2025-01-07 | 2114 | bth | L02_F_SALP_012 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 70 | 50 | 70 | F | 0 | 230 |  |  |  | 45
2025-01-07 | 2115 | bth | L02_F_SALP_013 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 100 | 50 | 120 | F | 0 | 310 |  |  |  | 45
2025-01-07 | 2116 | bth | L02_F_SALP_014 | A | DONE | 3 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 20 | 50 | 0 |  | 0 | 50 |  |  |  | 45
2025-01-07 | 2117 | bth | L02_F_SALP_015 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 110 | 50 | 100 | F | 0 | 320 |  |  |  | 45
2025-01-07 | 2118 | bth | L02_F_SALP_016 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 40 | 50 | 0 |  | 0 | 90 |  |  |  | 45
2025-01-07 | 2119 | bth | L02_F_SALP_017 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 80 | 50 | 0 |  | 0 | 130 |  |  |  | 45
2025-01-07 | 2120 | bth | L02_F_RAD_001 | A | DONE | 3 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 40 | 20 | 0 |  | 0 | 60 |  |  |  | 45
2025-01-07 | 2121 |  | L02_F_RAD_002 | A | DONE | 2 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 45
2025-01-07 | 2122 |  | L02_F_RAD_003 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 80 | 0 | 40 | F | 100 | 170 |  |  |  | 45
2025-01-07 | 2123 |  | L02_F_RAD_004 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 100 | 0 | 70 | F | 130 | 210 |  |  |  | 45
2025-01-07 | 2124 | bth | L02_F_RAD_005 | A | DONE | 2 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-10 | Z | 2024-11-26 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 45
2025-01-08 | 2125 |  | L02_F_RAD_006 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 90 | 0 | 40 | F | 90 | 160 |  |  |  | 45
2025-01-08 | 2126 |  | L02_F_RAD_007 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 70 | 0 | 40 | F | 90 | 150 |  |  |  | 45
2025-01-08 | 2127 |  | L02_F_RAD_008 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 70 | 0 | 70 | F | 100 | 170 |  |  |  | 45
2025-01-08 | 2128 | bth | L02_F_RAD_009 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 50 | 70 | 0 |  | 40 | 150 |  |  |  | 45
2025-01-08 | 2129 |  | L02_F_RAD_010 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 90 | 0 | 40 | F | 90 | 150 |  |  |  | 45
2025-01-08 | 2130 |  | L02_F_RAD_011 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 80 | 0 | 0 |  | 70 | 120 |  |  |  | 45
2025-01-08 | 2131 | bth | L02_F_RAD_012 | A | DONE | 2 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-10 | Z | 2024-11-26 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 45
2025-01-08 | 2132 |  | L02_F_RAD_013 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 70 | 0 | 40 | F | 90 | 150 |  |  |  | 45
2025-01-08 | 2133 | bth | L02_F_RAD_014 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-10 | Z | 2024-11-26 | 60 | 80 | 0 |  | 20 | 140 |  |  |  | 45
2025-01-08 | 2191 |  | 79864 | A | DONE | 20 | M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2025-01-03 | 500 | 0 | 0 |  | 0 | 1080 |  | Wall backing |  | 14
2025-01-07 | 2192 |  | 79806 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-01-10 | Z | 2025-01-06 | 20 | 0 | 0 |  | 0 | 30 |  | Temp caps |  | 4
2025-01-08 | 1263 |  | 82478 | A | DONE | 14 | S-M |  | WINDSOR 6240012 | flex | 2025-01-13 | Z | 2024-12-31 | 150 | 0 | 190 | F | 0 | 320 |  | FCU-204 SA |  | 13
2025-01-08 | 1264 |  | 82479 | A | DONE | 4 | S |  | WINDSOR 6240012 | 1" liner | 2025-01-13 | Z | 2024-12-31 | 90 | 0 | 0 |  | 30 | 130 |  | FCU-204 SA |  | 13
2025-01-08 | 1265 |  | 82480 - 82481 | A | DONE | 3 | S |  | WINDSOR 6240012 | flex , VD's | 2025-01-13 | Z | 2024-12-31 | 60 | 0 | 0 |  | 0 | 80 |  | FCU-211 A,B |  | 13
2025-01-08 | 1266 |  | 82482 | A | DONE | 5 | S-M |  | WINDSOR 6240012 | bird s. , 1" liner | 2025-01-13 | Z | 2024-12-31 | 120 | 0 | 0 |  | 100 | 140 |  | 2nd floor TA |  | 13
2025-01-08 | 1267 |  | 82483 - 82484 | A | DONE | 28 | M |  | WINDSOR 6240012 | flex | 2025-01-13 | Z | 2025-01-02 | 410 | 0 | 270 | F | 0 | 690 |  | DOAS 2 SA |  | 11
2025-01-08 | 1268 |  | 82485 - 82486 | A | DONE | 11 | M |  | WINDSOR 6240012 | flex | 2025-01-13 | Z | 2025-01-02 | 230 | 0 | 40 | F | 0 | 360 |  | DOAS 2 EA |  | 11
2025-01-08 | 1272 |  | 84270 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2025-01-09 | Z | 2025-01-08 | 20 | 0 | 0 |  | 0 | 30 |  | Heto's |  | 1
2025-01-07 | 1974 |  | 71480 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-01-09 | Z | 2025-01-07 | 30 | 0 | 0 |  | 0 | 50 |  | Angle |  | 2
2025-01-09 | 1976 |  | 71483 | A | DONE | 2 | S | neal | WSCC 6240006 | 1" liner | 2025-01-16 | Z | 2025-01-08 | 40 | 0 | 0 |  | 40 | 120 |  | ERV-5 |  | 8
[6 empty] | 830 | [13 empty] | 29390 |  |  |  | 6880 | 23.41%
WEEK OF 1-13-2025
2025-01-16 | 1217 |  | 81948 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 | flex , VD's | 2025-01-20 | Z | 2025-01-06 | 100 | 0 | 260 | F | 0 | 360 |  | HP-102 |  | 14
2025-01-14 | 1218 | sp | 81949 | A | DONE | 16 | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-20 | Z | 2025-01-06 | 90 | 300 | 0 |  | 0 | 480 |  | HP-102 |  | 14
2025-01-15 | 3903h |  | 80139 | A | DONE | n/a | M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-01-20 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. West unit plenums |  | 161
2025-01-15 | 3904h |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-20 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. West unit Taps |  | 161
2025-01-15 | 3905h |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-20 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. West unit sliders |  | 161
2025-01-15 | 3906h |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-01-20 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. West Corr. HP's |  | 161
2025-01-17 | 796 | sp | 63400 | A | DONE | 3 | S |  | BMH AHU9 6240001 |  | 2025-01-23 | Z | 2024-12-31 | 20 | 50 | 0 |  | 0 | 80 |  | CS 9.3R |  | 23
2025-01-15 | 799 | sp | 63413A | A | DONE | 4 | S |  | BMH AHU9 6240001 |  | 2025-01-23 | Z | 2024-12-31 | 80 | 0 | 0 |  | 0 | 150 |  | CS VAV 9.7S |  | 23
2025-01-14 | 902 |  | 84951 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2025-01-16 | Z | 2025-01-14 | 20 | 0 | 0 |  | 0 | 40 |  | Mech Rm SAHP |  | 2
2025-01-16 | 904 |  | 84955 | A | DONE | 2 | S |  | BMH ULTRASOUND 2240011 |  | 2025-01-23 | Z | 2025-01-16 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2025-01-15 | 2090 |  | 61394 | A | DONE | 22 | S |  | CDIS 6220028 | paint | 2025-01-20 | Z | 2025-01-02 | 530 | 0 | 0 |  | 540 | 880 |  | Fin Tube |  | 18
2025-01-16 | 2451 |  | 69728 | A | DONE | 4 | S | pt.neal | CDIS 6220028 |  | 2025-01-24 | Z | 2025-01-15 | 80 | 0 | 0 |  | 0 | 100 |  | Flashing |  | 9
2025-01-16 | 2452 |  | 69732 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2025-01-24 | Z | 2025-01-15 | 70 | 0 | 0 |  | 0 | 100 |  | 3rd and 7th floor |  | 9
2025-01-16 | 2453 |  | 69730 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-01-24 | Z | 2025-01-16 | 20 | 0 | 0 |  | 0 | 60 |  | Flashing - AHU |  | 8
2025-01-17 | 2455 |  | 69733 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-01-20 | Z | 2025-01-16 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 4
2025-01-17 | 2891 |  | 56696 | A | DONE | 2 | S |  | EXACT 8240012 |  | 2025-01-23 | Z | 2025-01-16 | 20 | 0 | 0 |  | 0 | 20 |  | Angles |  | 7
2025-01-13 | 1138 | sp | 79138 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2025-01-15 | Z | 2025-01-10 | 20 | 0 | 0 |  | 0 | 20 |  | Dampers |  | 5
2025-01-15 | 2851 | sp | 79139 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2025-01-20 | Z | 2025-01-14 | 20 | 80 | 0 |  | 0 | 100 |  | CB-9 |  | 6
2025-01-17 | 166 | w | 84307 | A | DONE | 2 | S | ss | OAKWOOD 4240057 |  | 2025-01-22 | Z | 2025-01-15 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 7
2025-01-13 | 2532 |  | 59839 | A | DONE | 17 | S-M |  | PROMEGA BTC 6230022 |  | 2025-01-13 | Z | 2025-01-13 | 420 | 0 | 0 |  | 0 | 660 |  | AHU-Louver |  | 0
2025-01-14 | 2534 | sp | 81829 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2025-01-15 | Z | 2025-01-14 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2025-01-13 | 1160 | bth | L02_A_SALP-013 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 30 | 60 | 0 |  | 0 | 120 |  |  |  | 62
2025-01-13 | 1161 | bth | L02_A_SALP-014 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 62
2025-01-13 | 1162 | bth | L02_A_SALP-015 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 62
2025-01-13 | 1163 | bth | L02_A_SALP-016 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 62
2025-01-13 | 1164 | bth | L02_A_SALP-017 | A | DONE | 8 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 50 | 140 | 0 |  | 0 | 210 |  |  |  | 62
2025-01-13 | 1166 | bth | L02_A_SALP-019 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 62
2025-01-13 | 1167 | bth | L02_A_SALP-020 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 60 | 20 | 0 |  | 0 | 80 |  |  |  | 62
2025-01-13 | 1168 | bth | L02_A_SALP-021 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 40 | 20 | 20 | F | 0 | 80 |  |  |  | 62
2025-01-13 | 1169 | bth | L02_A_SALP-022 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 62
2025-01-13 | 1170 | bth | L02_A_SALP-023 | A | DONE | 6 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 40 | 100 | 0 |  | 0 | 170 |  |  |  | 62
2025-01-13 | 1171 | sp | L02_A_SALP-024 | A | DONE | 5 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 30 | 90 | 0 |  | 0 | 140 |  |  |  | 62
2025-01-13 | 1172 | sp | L02_A_SALP-025 | A | DONE | 4 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 30 | 60 | 0 |  | 0 | 100 |  |  |  | 62
2025-01-13 | 1173 | bth | L02_A_SALP-026 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 40 | 30 | 20 | F | 0 | 120 |  |  |  | 62
2025-01-13 | 1174 | bth | L02_A_SALP-027 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 62
2025-01-13 | 1175 | bth | L02_A_SALP-028 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 70 | 20 | 20 | F | 0 | 150 |  |  |  | 62
2025-01-13 | 1176 | bth | L02_A_SALP-029 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 62
2025-01-13 | 1179 |  | L02_A_TAD_008 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-16 | Z | 2024-11-15 | 90 | 0 | 0 |  | 50 | 140 |  |  |  | 62
2025-01-13 | 1180 |  | L02_A_TAD_009 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-16 | Z | 2024-11-15 | 70 | 0 | 0 |  | 50 | 110 |  |  |  | 62
2025-01-13 | 2814 |  | 83034 | A | DONE | 3 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2025-01-09 | 60 | 0 | 0 |  | 0 | 80 |  | 1st fl B |  | 7
2025-01-13 | 2815 |  | 83035 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2025-01-10 | 70 | 0 | 0 |  | 0 | 90 |  | Roof drops |  | 6
2025-01-15 | 2817 |  | 82959 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2025-01-14 | 20 | 0 | 0 |  | 0 | 30 |  | 2nd Floor |  | 2
2025-01-15 | 2820 | sp | 83039 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-16 | Z | 2025-01-15 | 20 | 20 | 0 |  | 0 | 20 |  | CEF-2 |  | 1
2025-01-16 | 2821 |  | 83040 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-22 | Z | 2025-01-16 | 90 | 0 | 0 |  | 0 | 100 |  | Flashing |  | 6
2025-01-17 | 3750 | sp | 69051 | A | DONE | 6 | S-M |  | UW-AVRL 5th FL 6240038 |  | 2025-01-22 | Z | 2025-01-16 | 0 | 150 | 0 |  | 0 | 180 |  | Sleeves |  | 6
2025-01-15 | 630 | w | 83256 | A | DONE | 2 | S-M |  | UW-BIO CHEM 6240036 | 2" DB | 2025-01-20 | Z | 2025-01-03 | 30 | 0 | 0 |  | 20 | 70 |  | Roof cap |  | 17
2025-01-15 | 631 | w | 83257 | A | DONE | 2 | S-M |  | UW-BIO CHEM 6240036 | 2" DB | 2025-01-20 | Z | 2025-01-03 | 30 | 0 | 0 |  | 20 | 80 |  | Roof curb |  | 17
2025-01-15 | 632 |  | 83258 | A | DONE | 6 | S |  | UW-BIO CHEM 6240036 |  | 2025-01-20 | Z | 2025-01-14 | 130 | 0 | 0 |  | 0 | 160 |  | EF-1 , AHU-1 |  | 6
2025-01-16 | 4569 |  | LL - SAT-3-L-7.1 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-01-20 | Z | 2024-12-17 | 210 | 0 | 0 |  | 160 | 290 |  |  |  | 34
2025-01-16 | 4570 |  | LL - SAT-3-L-7.2 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-20 | Z | 2024-12-17 | 80 | 0 | 80 | F | 130 | 230 |  |  |  | 34
2025-01-16 | 4571 |  | LL - SAT-3-L-7.3 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-20 | Z | 2024-12-17 | 250 | 0 | 40 | F | 190 | 360 |  |  |  | 34
2025-01-16 | 4572 | bth | LL - SAT-3-L-7.4 | A | DONE | 16 | S-M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-20 | Z | 2024-12-17 | 180 | 20 | 180 | F | 270 | 470 |  |  |  | 34
2025-01-16 | 4573 |  | LL - SAT-3-L-7.5 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-20 | Z | 2024-12-17 | 130 | 0 | 40 | F | 120 | 320 |  |  |  | 34
2025-01-16 | 4574 |  | LL - RAMP 3 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-01-20 | Z | 2024-12-17 | 320 | 0 | 150 | F | 20 | 720 |  |  |  | 34
2025-01-16 | 4575 |  | LL - RAMP 4 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-20 | Z | 2024-12-17 | 130 | 0 | 140 | F | 200 | 340 |  |  |  | 34
2025-01-16 | 4576 |  | LL - RAMP 5 | A | DONE | 13 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-20 | Z | 2024-12-17 | 110 | 0 | 60 | F | 140 | 240 |  |  |  | 34
2025-01-16 | 4577 |  | LL - RAMP 6 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-20 | Z | 2024-12-17 | 220 | 0 | 60 | F | 90 | 500 |  |  |  | 34
2025-01-16 | 4582 |  | LL - EAMP 4 | A | DONE | 11 | S-M | neal | UW-LEVY HALL 6230028 | VD , bird s. | 2025-01-20 | Z | 2024-12-17 | 70 | 0 | 200 | F | 10 | 350 |  |  |  | 34
2025-01-16 | 4583 |  | LL - EAMP 5 | A | DONE | 8 | S-M | neal | UW-LEVY HALL 6230028 | VD , MOD , bird s. | 2025-01-20 | Z | 2024-12-17 | 180 | 0 | 0 |  | 0 | 310 |  |  |  | 34
2025-01-16 | 4584 |  | LL - SAMP 9 | A | DONE | 20 | M |  | UW-LEVY HALL 6230028 | VD , bird s. | 2025-01-20 | Z | 2024-12-17 | 190 | 0 | 300 | F | 0 | 680 |  |  |  | 34
2025-01-16 | 4585 |  | LL - SAMP 10 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 | VD , MOD , bird s. | 2025-01-20 | Z | 2024-12-17 | 300 | 0 | 70 | F | 0 | 570 |  |  |  | 34
2025-01-13 | 3303 |  | 83534 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-01-21 | Z | 2025-01-09 | 20 | 0 | 0 |  | 0 | 60 |  | Duct hangers |  | 12
2025-01-16 | 3305 |  | 72934 - 72936 | A | DONE | 2 | S-M |  | UWRF 6230010 | 1" liner | 2025-01-21 | Z | 2025-01-10 | 50 | 0 | 0 |  | 30 | 70 |  | L2 TA |  | 11
2025-01-16 | 3306 |  | 72937 - 72938 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2025-01-21 | Z | 2025-01-10 | 30 | 0 | 0 |  | 20 | 30 |  | L2 TA |  | 11
2025-01-16 | 3307 | bth | 72940 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2025-01-21 | Z | 2025-01-10 | 40 | 20 | 0 |  | 0 | 50 |  | L2 PCD |  | 11
2025-01-17 | 1396 | sp | LPSA-02-17 | A | DONE | 28 | M |  | UWSP ALBERTSON 6230016 |  | 2025-01-21 | Z | 2025-01-02 | 70 | 610 | 0 |  | 0 | 720 |  |  |  | 19
2025-01-17 | 1397 | bth | LPSA-02-18 | A | DONE | 23 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-21 | Z | 2025-01-02 | 70 | 500 | 0 |  | 30 | 610 |  |  |  | 19
2025-01-16 | 1398 | bth | LPSA-02-19 | A | DONE | 24 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-21 | Z | 2025-01-02 | 90 | 500 | 0 |  | 20 | 680 |  |  |  | 19
2025-01-14 | 2352 | w | 64709 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | 1" DB | 2025-01-21 | Z | 2025-01-06 | 20 | 0 | 0 |  | 20 | 40 |  | Insulated curb cap |  | 15
2025-01-13 | 2395 |  | 81173 | A | DONE | 18 | M |  | UWSP ALBERTSON 6230016 |  | 2025-01-21 | Z | 2025-01-08 | 430 | 0 | 0 |  | 0 | 600 |  | Flashing |  | 13
2025-01-15 | r1318 |  | RA-02-06 | A | DONE | 16 | S-M | perf | UWSP ALBERTSON 6230016 | 2" DW | 2025-01-21 | Z | 2025-01-15 | 380 | 0 | 0 |  | 0 | 410 |  |  |  | 6
2025-01-17 | 2745 | bth | L1E_SAMP 1 | A | DONE | 11 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 180 | 30 | 60 | F | 0 | 410 |  |  |  | 14
2025-01-17 | 2746 | bth | L1E_SAMP 2 | A | DONE | 16 | M |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 210 | 20 | 160 | F | 0 | 800 |  |  |  | 14
2025-01-17 | 2747 | bth | L1E_SAMP 3 | A | DONE | 8 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 80 | 20 | 90 | F | 0 | 200 |  |  |  | 14
2025-01-17 | 2748 | bth | L1E_SAMP 4 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 50 | 40 | 0 |  | 0 | 140 |  |  |  | 14
2025-01-17 | 2749 |  | L1E_SAMP 5 | A | DONE | 12 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 110 | 0 | 190 | F | 0 | 480 |  |  |  | 14
2025-01-17 | 2750 | bth | L1E_SAMP 6 | A | DONE | 8 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 20 | 40 | 120 | F | 0 | 250 |  |  |  | 14
2025-01-17 | 2751 | bth | L1E_SAMP 7 | A | DONE | 11 | S-M | pt.neal | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 70 | 150 | 40 | F | 0 | 320 |  |  |  | 14
2025-01-17 | 2752 | sp | L1E_SAMP 8 | A | DONE | 7 | S | pt.neal | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 90 | 70 | 0 |  | 0 | 170 |  |  |  | 14
2025-01-17 | 2753 | sp | L1E_SAMP 9 | A | DONE | 5 | S | pt.neal | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 40 | 70 | 0 |  | 0 | 120 |  |  |  | 14
2025-01-16 | 2754 | sp | L1E_SAMP 10 | A | DONE | 5 | S | pt.neal | UWSP CHAMPION HALL 6240008 |  | 2025-01-21 | Z | 2025-01-07 | 30 | 90 | 0 |  | 0 | 140 |  |  |  | 14
2025-01-13 | 2134 | bth | L01_F_EAD_001 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 200 | 20 | 150 | F | 0 | 430 |  |  |  | 52
2025-01-13 | 2135 | bth | L01_F_EAD_002 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 50 | 20 | 170 | F | 0 | 380 |  |  |  | 52
2025-01-13 | 2136 | bth | L01_F_EAD_003 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 100 | 50 | 20 | F | 0 | 220 |  |  |  | 52
2025-01-13 | 2137 |  | L01_F_EAD_004 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 250 | 0 | 60 | F | 0 | 360 |  |  |  | 52
2025-01-13 | 2138 | bth | L01_F_EAD_005 | A | DONE | 16 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 170 | 50 | 160 | F | 0 | 460 |  |  |  | 52
2025-01-13 | 2139 | bth | L01_F_EAD_006 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 30 | 50 | 110 | F | 0 | 210 |  |  |  | 52
2025-01-13 | 2140 | sp | L01_F_EAD_007 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 220 | 120 | 0 |  | 0 | 500 |  |  |  | 52
2025-01-14 | 2141 |  | L01_F_EAD_008 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 130 | 0 | 200 | F | 0 | 460 |  |  |  | 52
2025-01-14 | 2142 | bth | L01_F_EAD_009 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 70 | 40 | 20 | F | 0 | 140 |  |  |  | 52
2025-01-14 | 2143 |  | L01_F_SOA_001 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 230 | 0 | 100 | F | 0 | 530 |  |  |  | 52
2025-01-14 | 2144 | bth | L01_F_SOA_002 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 40 | 40 | 220 | F | 0 | 360 |  |  |  | 52
2025-01-14 | 2145 | bth | L01_F_SOA_003 | A | DONE | 16 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 180 | 20 | 180 | F | 0 | 440 |  |  |  | 52
2025-01-14 | 2146 |  | L01_F_SOA_004 | A | DONE | 16 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 70 | 0 | 310 | F | 0 | 490 |  |  |  | 52
2025-01-14 | 2147 | bth | L01_F_SOA_005 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 70 | 110 | 110 | F | 0 | 310 |  |  |  | 52
2025-01-14 | 2148 | bth | L01_F_SOA_006 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 70 | 20 | 160 | F | 0 | 300 |  |  |  | 52
2025-01-14 | 2149 | bth | L01_F_SOA_007 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 70 | 40 | 130 | F | 0 | 270 |  |  |  | 52
2025-01-14 | 2150 | bth | L01_F_SOA_008 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 50 | 30 | 130 | F | 0 | 250 |  |  |  | 52
2025-01-14 | 2151 | bth | L01_F_SOA_009 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 40 | 20 | 140 | F | 0 | 250 |  |  |  | 52
2025-01-14 | 2152 | bth | L01_F_SOA_010 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 30 | 100 | 60 | F | 0 | 190 |  |  |  | 52
2025-01-14 | 2153 | bth | L01_F_SOA_011 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 50 | 20 | 160 | F | 0 | 290 |  |  |  | 52
2025-01-13 | 2154 | sp | L01_F_SOA_012 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 30 | 70 | 0 |  | 0 | 100 |  |  |  | 52
2025-01-13 | 2155 | sp | L01_F_SOA_013 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-17 | Z | 2024-11-26 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 52
2025-01-17 | 2235 |  | 69244 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-01-24 | Z | 2025-01-17 | 40 | 0 | 0 |  | 0 | 70 |  | Flat metal |  | 7
2025-01-17 | 2236 | sp | 79866 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-01-24 | Z | 2025-01-17 | 0 | 20 | 0 |  | 0 | 20 |  | Wall sleeves |  | 7
2025-01-15 | 1269 |  | 82487 - 82488 | A | DONE | 16 | M |  | WINDSOR 6240012 | flex | 2025-01-20 | Z | 2025-01-06 | 300 | 0 | 90 | F | 0 | 430 |  | DOAS #1 SA |  | 14
2025-01-15 | 1270 |  | 82489 - 82490 | A | DONE | 16 | M |  | WINDSOR 6240012 | flex | 2025-01-20 | Z | 2025-01-06 | 290 | 0 | 100 | F | 0 | 450 |  | DOAS #1 EA |  | 14
2025-01-15 | 1271 |  | 82491 | A | DONE | 3 | S |  | WINDSOR 6240012 |  | 2025-01-20 | Z | 2025-01-06 | 70 | 0 | 0 |  | 0 | 120 |  | L-3/4 |  | 14
2025-01-15 | 1273 |  | 82492 | A | DONE | 2 | S-M |  | WINDSOR 6240012 | flex | 2025-01-20 | Z | 2025-01-09 | 40 | 0 | 0 |  | 0 | 70 |  | Misc outs |  | 11
2025-01-15 | 1274 |  | 82493 | A | DONE | 2 | S |  | WINDSOR 6240012 | bird s. , 1" liner | 2025-01-20 | Z | 2025-01-09 | 20 | 0 | 0 |  | 20 | 30 |  | Rm 221 |  | 11
2025-01-14 | 1275 | sp | 82494 | A | DONE | 4 | S |  | WINDSOR 6240012 |  | 2025-01-20 | Z | 2025-01-09 | 20 | 60 | 0 |  | 0 | 60 |  | Misc outs |  | 11
2025-01-17 | 1977 |  | 71485 | A | DONE | 2 | S | neal | WSCC 6240006 | 1" liner | 2025-01-21 | Z | 2025-01-16 | 40 | 0 | 0 |  | 40 | 120 |  | ERV-5 |  | 5
[6 empty] | 837 | [13 empty] | 25640 |  |  |  | 3430 | 13.38%
WEEK OF 1-20-2025
2025-01-21 | 1211 |  | 81941 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-01-23 | Z | 2024-12-31 | 220 | 0 | 0 |  | 200 | 240 |  | 14th fl Unit Plenums |  | 23
2025-01-21 | 1212 |  | 81942 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-23 | Z | 2024-12-31 | 50 | 0 | 0 |  | 0 | 60 |  | 14th fl Unit Taps |  | 23
2025-01-21 | 1213 |  | 81943 | A | DONE | 3 | S |  | 121 E. WILSON 6230024 |  | 2025-01-23 | Z | 2024-12-31 | 70 | 0 | 0 |  | 0 | 80 |  | 14th fl Unit Sliders |  | 23
2025-01-21 | 1214 |  | 81944 | A | DONE | 6 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-01-23 | Z | 2024-12-31 | 130 | 0 | 0 |  | 90 | 120 |  | 14th fl Unit TA |  | 23
2025-01-21 | 1215 | w | 81945 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 | 1-1/2" DB | 2025-01-23 | Z | 2025-01-02 | 70 | 0 | 0 |  | 60 | 200 |  | Curb |  | 21
2025-01-21 | 2249 |  | 80075 | A | DONE | 29 | M |  | 121 E. WILSON 6230024 | paint | 2025-01-23 | Z | 2024-07-25 | 340 | 0 | 370 | F | 0 | 940 |  | DOAS-1 / OA-6 |  | 182
2025-01-21 | 3663 |  | 80088 , 80095 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-23 | Z | 2024-07-30 | 270 | 0 | 90 | F | 0 | 370 |  | EF-1,2 , EA-7 |  | 177
2025-01-21 | 3934 |  | EA-PH-01 | A | DONE | 16 | S-M |  | 121 E. WILSON 6230024 | flex | 2025-01-23 | Z | 2024-11-15 | 320 | 0 | 70 | F | 0 | 390 |  |  |  | 69
2025-01-21 | 3935 |  | EA-PH-02 | A | DONE | 3 | S |  | 121 E. WILSON 6230024 | bird s. , flex | 2025-01-23 | Z | 2024-11-15 | 60 | 0 | 0 |  | 0 | 110 |  | Welded curb cap |  | 69
2025-01-21 | 3936 |  | OA-PH-01 | A | DONE | 17 | S-M |  | 121 E. WILSON 6230024 | CD , flex | 2025-01-23 | Z | 2024-11-15 | 410 | 0 | 0 |  | 0 | 580 |  |  |  | 69
2025-01-21 | 3937 |  | OA-PH-02 | A | DONE | 8 | S |  | 121 E. WILSON 6230024 | flex | 2025-01-23 | Z | 2024-11-15 | 180 | 0 | 0 |  | 0 | 210 |  |  |  | 69
2025-01-22 | 3909h |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-01-28 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. East unit plenums | Design Air | 169
2025-01-22 | 3910h |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-28 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. East Taps | Design Air | 169
2025-01-22 | 3911h |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-28 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. East sliders | Design Air | 169
2025-01-22 | 3912h |  | 80149 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 |  | 2025-01-28 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. East unit SA | Design Air | 169
2025-01-22 | 3913h |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-01-28 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 12th Fl. East Corr. HP's | Design Air | 169
2025-01-20 | 797 |  | 63400A | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-01-23 | Z | 2024-12-31 | 20 | 0 | 0 |  | 0 | 20 |  | CS 9.3R |  | 23
2025-01-20 | 798 |  | 63412 - 63413 | A | DONE | 5 | S-M |  | BMH AHU9 6240001 |  | 2025-01-23 | Z | 2024-12-31 | 30 | 0 | 90 | F | 0 | 150 |  | CS VAV 9.6S , 9.7S |  | 23
2025-01-20 | 900 |  | 63406 , 63408 | A | DONE | 10 | S-M |  | BMH AHU9 6240001 |  | 2025-01-23 | Z | 2024-12-31 | 70 | 0 | 160 | F | 0 | 280 |  | CS VAV 9.2R LP |  | 23
2025-01-20 | 901 |  | 63410 | A | DONE | 4 | S |  | BMH AHU9 6240001 |  | 2025-01-23 | Z | 2024-12-31 | 50 | 0 | 30 | F | 0 | 90 |  | CS VAV 9.3S |  | 23
2025-01-20 | 907 |  | 84957 | A | DONE | 14 | S-M |  | BMH AHU9 6240001 |  | 2025-01-23 | Z | 2025-01-17 | 270 | 0 | 60 | F | 0 | 440 |  | Freezer |  | 6
2025-01-20 | 903 | bth | 84953 - 84954 | A | DONE | 6 | S-M |  | BMH ULTRASOUND 2240011 |  | 2025-01-23 | Z | 2025-01-16 | 50 | 100 | 0 |  | 0 | 170 |  | Misc |  | 7
2025-01-22 | 2454 |  | 69731 | A | DONE | 2 | S | ss | CDIS 6220028 |  | 2025-01-24 | Z | 2025-01-16 | 30 | 0 | 0 |  | 0 | 60 |  | Flashing - AHU |  | 8
2025-01-21 | 2456 |  | 61395 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-01-21 | Z | 2025-01-21 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2025-01-22 | 167 |  | 79433 | A | DONE | 2 | S |  | COMPASS PARK BANK 10060158 | paint | 2025-01-27 | Z | 2025-01-22 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 5
2025-01-23 | 622 |  | 70733 | A | DONE | 2 | S | ss | EGENESIS 6230002 |  | 2025-01-27 | Z | 2025-01-23 | 20 | 0 | 0 |  | 0 | 20 |  | TA Covers |  | 4
2025-01-22 | 1139 | bth | TL3_EAMP 1 | A | DONE | 6 | S |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 70 | 20 | 60 | F | 0 | 230 |  |  |  | 15
2025-01-22 | 1140 | bth | TL3_EAMP 2 | A | DONE | 9 | S |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 170 | 20 | 30 | F | 0 | 300 |  |  |  | 15
2025-01-22 | 1141 | bth | TL3_EAMP 3 | A | DONE | 10 | S |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 110 | 30 | 90 | F | 0 | 330 |  |  |  | 15
2025-01-22 | 1142 | bth | TL3_EAMP 4 | A | DONE | 33 | M |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 540 | 30 | 240 | F | 0 | 1150 |  |  |  | 15
2025-01-22 | 1143 | bth | TL3_EAT 1810-3 | A | DONE | 8 | S |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 140 | 20 | 40 | F | 0 | 270 |  |  |  | 15
2025-01-22 | 1144 | bth | TL3_EAT 1810-4 | A | DONE | 5 | S |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 100 | 20 | 0 |  | 0 | 130 |  |  |  | 15
2025-01-22 | 1145 | bth | TL3_EAT 1810-5 | A | DONE | 10 | S |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 80 | 20 | 40 | F | 0 | 170 |  |  |  | 15
2025-01-22 | 1146 | bth | TL3_EAT 1810-6 | A | DONE | 5 | S |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 30 | 20 | 60 | F | 0 | 110 |  |  |  | 15
2025-01-22 | 1147 | bth | TL3_EAT 1810-7 | A | DONE | 5 | S |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 40 | 40 | 30 | F | 0 | 140 |  |  |  | 15
2025-01-22 | 1148 | bth | TL3_SAMP 1 | A | DONE | 14 | S-M |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 190 | 50 | 110 | F | 0 | 510 |  |  |  | 15
2025-01-22 | 1149 | bth | TL3_SAMP 2 | A | DONE | 19 | M |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 180 | 40 | 240 | F | 0 | 720 |  |  |  | 15
2025-01-22 | 2850 | bth | TL3_SAMP 3 | A | DONE | 11 | S-M |  | EXACT TL-3 6240028 |  | 2025-01-28 | Z | 2025-01-13 | 180 | 30 | 60 | F | 0 | 370 |  |  |  | 15
2025-01-20 | 2935 |  | 82567 | A | DONE | 6 | S-M |  | LABCORP 6240016 |  | 2025-01-22 | Z | 2025-01-13 | 130 | 0 | 0 |  | 0 | 330 |  | EF-Tie in |  | 9
2025-01-20 | 3965 |  | 80162 | A | DONE | 2 | S |  | PECATONICA ES 6240005 |  | 2025-01-23 | Z | 2025-01-16 | 20 | 0 | 0 |  | 0 | 30 |  | Oval flashing |  | 7
2025-01-21 | 2528 |  | 59828 | A | DONE | 15 | S |  | PROMEGA BTC 6230022 |  | 2025-01-27 | Z | 2024-12-20 | 360 | 0 | 0 |  | 0 | 850 |  |  |  | 38
2025-01-20 | 2535 |  | 81830 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2025-01-22 | Z | 2025-01-20 | 90 | 0 | 0 |  | 0 | 290 |  | Misc |  | 2
2025-01-23 | 2536 |  | 81831 | A | DONE | 11 | S |  | PROMEGA BTC 6230022 |  | 2025-01-27 | Z | 2025-01-22 | 260 | 0 | 0 |  | 0 | 580 |  | Misc |  | 5
2025-01-24 | 2537 |  | 70843 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-01-27 | Z | 2025-01-23 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 4
2025-01-23 | 2538 |  | 70844 | A | DONE | 6 | S-M |  | PROMEGA BTC 6230022 |  | 2025-01-27 | Z | 2025-01-23 | 130 | 0 | 0 |  | 0 | 360 |  | Test Caps |  | 4
2025-01-21 | 3063 | bth | 70727 | A | DONE | 5 | S-M |  | RAMC 2240073 |  | 2025-01-27 | Z | 2025-01-13 | 30 | 20 | 70 | F | 0 | 120 |  | Post Partum 226/229 |  | 14
2025-01-21 | 1407 | w | 68452 | A | DONE | 2 | S-M |  | SPH SURGERY 6240039 |  | 2025-01-27 | Z | 2025-01-08 | 30 | 0 | 0 |  | 0 | 90 |  | Wall sleeves |  | 19
2025-01-20 | 498 | bth | L02_A_SALP-001 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 69 | 2024-01-23
2025-01-20 | 499 | bth | L02_A_SALP-002 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1150 | bth | L02_A_SALP-003 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 30 | 50 | 0 |  | 0 | 80 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1151 | bth | L02_A_SALP-004 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1152 | bth | L02_A_SALP-005 | A | DONE | 8 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 50 | 140 | 0 |  | 0 | 210 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1153 | sp | L02_A_SALP-006 | A | DONE | 4 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 30 | 70 | 0 |  | 0 | 100 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1154 | bth | L02_A_SALP-007 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 50 | 20 | 0 |  | 0 | 80 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1155 | bth | L02_A_SALP-008 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1156 | bth | L02_A_SALP-009 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1157 | bth | L02_A_SALP-010 | A | DONE | 8 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 60 | 130 | 0 |  | 0 | 230 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1158 | sp | L02_A_SALP-011 | A | DONE | 10 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 60 | 180 | 0 |  | 0 | 260 |  |  |  | 69 | 2024-01-23
2025-01-20 | 1181 | bth | L02_A_EAD_005 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 40 | 20 | 0 |  | 0 | 50 |  |  |  | 69
2025-01-20 | 1182 | bth | L02_A_EAD_006 | A | DONE | 3 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 20 | 30 | 20 | F | 0 | 80 |  |  |  | 69
2025-01-20 | 1183 | sp | L02_A_EAD_007 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2024-11-15 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 69
2025-01-20 | 1184 |  | L02_A_TAD_001 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 70 | 0 | 0 |  | 60 | 110 |  |  |  | 69
2025-01-20 | 1185 |  | L02_A_TAD_002 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 50 | 0 | 0 |  | 50 | 90 |  |  |  | 69
2025-01-20 | 1186 |  | L02_A_TAD_003 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 69
2025-01-20 | 1187 |  | L02_A_TAD_004 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 69
2025-01-20 | 1188 |  | L02_A_TAD_010 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 80 | 0 | 0 |  | 60 | 120 |  |  |  | 69
2025-01-20 | 1189 |  | L02_A_TAD_011 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 60 | 0 | 0 |  | 50 | 90 |  |  |  | 69
2025-01-20 | 1190 |  | L02_A_TAD_012 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 69
2025-01-20 | 1191 |  | L02_A_TAD_013 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 70 | 0 | 0 |  | 60 | 110 |  |  |  | 69
2025-01-20 | 1192 |  | L02_A_TAD_014 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2024-11-15 | 60 | 0 | 0 |  | 50 | 90 |  |  |  | 69
2025-01-20 | 2816 | sp | 83036 | A | DONE | 4 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-01-23 | Z | 2025-01-14 | 20 | 60 | 0 |  | 0 | 80 |  | 1st fl B |  | 9
2025-01-20 | 2818 | bth | 83037 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | paint | 2025-01-23 | Z | 2025-01-15 | 20 | 20 | 0 |  | 0 | 30 |  | CEF-2 |  | 8
2025-01-20 | 2819 |  | 83038 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-23 | Z | 2025-01-15 | 20 | 0 | 0 |  | 20 | 20 |  | Rm 141 |  | 8
2025-01-21 | 2822 |  | 82960 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-22 | Z | 2025-01-20 | 20 | 0 | 0 |  | 20 | 30 |  | Misc |  | 2
2025-01-21 | 1068 | w | 83912 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-01-27 | Z | 2025-01-10 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeves |  | 17
2025-01-23 | 1092 |  | 32500 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-01-23 | Z | 2025-01-23 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 0
2025-01-21 | 4594 | bth | LL - RAMP 1 | A | DONE | 11 | S-M | pt.neal | UW-LEVY HALL 6230028 | 1" liner | 2025-01-27 | Z | 2025-01-02 | 80 | 30 | 150 | F | 20 | 290 |  |  |  | 25
2025-01-21 | 4597 | bth | LL - EAMP 1 | A | DONE | 10 | S-M | pt.neal | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-27 | Z | 2025-01-02 | 70 | 100 | 60 | F | 20 | 270 |  |  |  | 25
2025-01-21 | 4598 |  | LL - EAMP 2 | A | DONE | 5 | S | neal | UW-LEVY HALL 6230028 | VD's | 2025-01-27 | Z | 2025-01-02 | 70 | 0 | 50 | F | 0 | 130 |  |  |  | 25
2025-01-22 | 3308 | bth | 72941 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2025-01-27 | Z | 2025-01-14 | 50 | 20 | 0 |  | 0 | 60 |  | L2 PCD |  | 13
2025-01-22 | 3309 |  | 72943 - 72944 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-01-27 | Z | 2025-01-14 | 20 | 0 | 0 |  | 20 | 30 |  | Rm 268 , 272 GE |  | 13
2025-01-22 | 3310 |  | 72945 - 72946 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-01-27 | Z | 2025-01-14 | 40 | 0 | 0 |  | 30 | 70 |  | Rm 250 , 252 GE |  | 13
2025-01-22 | 3311 |  | 72948 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-01-27 | Z | 2025-01-14 | 20 | 0 | 0 |  | 0 | 20 |  | Rm 250 GE |  | 13
2025-01-22 | 3312 |  | 72942 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-01-27 | Z | 2025-01-14 | 30 | 0 | 0 |  | 0 | 50 |  | PH OA Plenum |  | 13
2025-01-22 | 3313 |  | 83536 | A | DONE | 2 | S-M | pcd | UWRF 6230010 |  | 2025-01-27 | Z | 2025-01-15 | 40 | 0 | 0 |  | 0 | 100 |  | PH Outs |  | 12
2025-01-22 | 3314 |  | 83537 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-01-27 | Z | 2025-01-15 | 20 | 0 | 0 |  | 0 | 40 |  | PH Outs |  | 12
2025-01-23 | 2354 | bth | LPSA-03-3 | A | DONE | 6 | s | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-28 | Z | 2025-01-07 | 120 | 20 | 0 |  | 40 | 150 |  |  |  | 21
2025-01-23 | 2355 | bth | LPSA-03-4 | A | DONE | 10 | S-M | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-28 | Z | 2025-01-07 | 150 | 20 | 80 | F | 60 | 300 |  |  |  | 21
2025-01-23 | 2356 | bth | LPSA-03-5 | A | DONE | 8 | S | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 140 | 20 | 20 | F | 40 | 220 |  |  |  | 21
2025-01-23 | 2357 | bth | LPSA-03-6 | A | DONE | 10 | S | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 170 | 20 | 50 | F | 50 | 280 |  |  |  | 21
2025-01-23 | 2358 | bth | LPSA-03-7 | A | DONE | 8 | S | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-28 | Z | 2025-01-07 | 90 | 50 | 40 | F | 20 | 200 |  |  |  | 21
2025-01-23 | 2359 | bth | LPSA-03-8 | A | DONE | 11 | S-M | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 170 | 20 | 70 | F | 30 | 330 |  |  |  | 21
2025-01-23 | 2360 | bth | LPSA-03-9 | A | DONE | 21 | M | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 290 | 20 | 200 | F | 30 | 590 |  |  |  | 21
2025-01-23 | 2361 | bth | LPSA-03-10 | A | DONE | 12 | S-M | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-28 | Z | 2025-01-07 | 230 | 70 | 0 |  | 50 | 370 |  |  |  | 21
2025-01-22 | 3217 |  | 81171 - 81172 | A | DONE | 19 | M |  | UWSP ALBERTSON 6230016 | paint , 1" liner | 2025-01-28 | Z | 2025-01-16 | 460 | 0 | 0 |  | 40 | 450 |  | Misc |  | 12
2025-01-23 | 3218 |  | 81175 | A | DONE | 4 | M |  | UWSP ALBERTSON 6230016 | CD's | 2025-01-28 | Z | 2025-01-16 | 80 | 0 | 0 |  | 0 | 130 |  | 4th floor |  | 12
2025-01-22 | 3219 | sp | 81174 , 81180 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-01-28 | Z | 2025-01-16 | 20 | 20 | 0 |  | 0 | 20 |  | Misc |  | 12
2025-01-23 | 3220 |  | 81181 - 81184 | A | DONE | 4 | S-M |  | UWSP ALBERTSON 6230016 | VD's | 2025-01-28 | Z | 2025-01-16 | 100 | 0 | 0 |  | 0 | 140 |  | 2nd floor West and North |  | 12
2025-01-21 | 2234 | sp | 79865 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-24 | Z | 2025-01-16 | 20 | 70 | 0 |  | 0 | 80 |  | Extra duct |  | 8
2025-01-22 | 1276 |  | 82207 - 82208 | A | DONE | 14 | S-M |  | WINDSOR 6240012 |  | 2025-01-27 | Z | 2025-01-16 | 250 | 0 | 100 | F | 0 | 320 |  | DOAS #1 EA |  | 11
2025-01-22 | 1277 |  | 82209 | A | DONE | 3 | S |  | WINDSOR 6240012 |  | 2025-01-27 | Z | 2025-01-16 | 70 | 0 | 0 |  | 0 | 130 |  | DOAS #2 OA |  | 11
2025-01-22 | 1278 |  | 82495 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2025-01-27 | Z | 2025-01-16 | 20 | 0 | 0 |  | 0 | 20 |  | Grand Stair |  | 11
2025-01-22 | 1279 | bth | 82496 | A | DONE | 6 | S |  | WINDSOR 6240012 |  | 2025-01-27 | Z | 2025-01-20 | 80 | 60 | 0 |  | 0 | 140 |  | 2nd Fl outs |  | 7
2025-01-21 | 1975 |  | 71481 - 71482 | A | DONE | 6 | S-M | neal | WSCC 6240006 |  | 2025-01-23 | Z | 2025-01-07 | 150 | 0 | 0 |  | 0 | 250 |  | Wall trim |  | 16
2025-01-23 | 1978 | sp | 71486 | A | DONE | 4 | S | neal | WSCC 6240006 |  | 2025-01-30 | Z | 2025-01-20 | 20 | 60 | 0 |  | 0 | 90 |  | RTU-11 |  | 10
[6 empty] | 637 | [13 empty] | 19310 |  |  |  | 4430 | 22.94%
WEEK OF 1-27-2025
2025-01-30 | 3938 |  | EA-PH-03 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 | flex | 2025-01-30 | Z | 2024-11-15 | 250 | 0 | 90 | F | 0 | 480 |  |  |  | 76
2025-01-30 | 3940 |  | OA-PH-03 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 | flex | 2025-01-30 | Z | 2024-11-15 | 60 | 0 | 30 | F | 0 | 110 |  |  |  | 76
2025-01-30 | 3941 |  | OA-PH-04 | A | DONE | 5 | S |  | 121 E. WILSON 6230024 |  | 2025-01-30 | Z | 2024-11-15 | 120 | 0 | 0 |  | 0 | 150 |  |  |  | 76
2025-01-28 | 905 | bth | 84901 - 84902 | A | DONE | 4 | S-M |  | BMH AHU9 6240001 |  | 2025-01-30 | Z | 2025-01-16 | 70 | 20 | 0 |  | 0 | 90 |  | CS hallway SAHP |  | 14
2025-01-28 | 906 | bth | 84904 - 84905 | A | DONE | 5 | S-M |  | BMH AHU9 6240001 |  | 2025-01-30 | Z | 2025-01-16 | 50 | 50 | 20 | F | 0 | 130 |  | CS VAV 9.5R |  | 14
2025-01-28 | 908 |  | 84958 | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-01-30 | Z | 2025-01-27 | 20 | 0 | 0 |  | 0 | 20 |  | VAV-1056A |  | 3
2025-01-31 | 2852 | bth | TL3_SAT 1810-1 | A | DONE | 36 | M-L |  | EXACT TL-3 6240028 |  | 2025-02-03 | Z | 2025-01-14 | 320 | 120 | 440 | F | 0 | 1050 |  |  |  | 20
2025-01-31 | 2855 | bth | TL3_SAT 1810-3.2 | A | DONE | 21 | M |  | EXACT TL-3 6240028 |  | 2025-02-03 | Z | 2025-01-14 | 180 | 60 | 270 | F | 0 | 650 |  |  |  | 20
2025-01-31 | 2856 | bth | TL3_SAT 1810-3.3 | A | DONE | 12 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-03 | Z | 2025-01-14 | 130 | 70 | 100 | F | 0 | 360 |  |  |  | 20
2025-01-31 | 2857 | bth | TL3_SAT 1810-4 | A | DONE | 33 | M |  | EXACT TL-3 6240028 |  | 2025-02-03 | Z | 2025-01-14 | 480 | 40 | 290 | F | 0 | 1070 |  |  |  | 20
2025-01-31 | 2858 |  | TL3_SAT 1810-5.1 | A | DONE | 25 | M |  | EXACT TL-3 6240028 |  | 2025-02-03 | Z | 2025-01-14 | 310 | 0 | 300 | F | 0 | 730 |  |  |  | 20
2025-01-31 | 2859 | bth | TL3_SAT 1810-5.2 | A | DONE | 18 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-03 | Z | 2025-01-14 | 140 | 30 | 260 | F | 0 | 510 |  |  |  | 20
2025-01-31 | 2860 | bth | TL3_SAT 1810-6 | A | DONE | 17 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-03 | Z | 2025-01-14 | 200 | 110 | 110 | F | 0 | 540 |  |  |  | 20
2025-01-31 | 2861 |  | TL3_RAMP 1 | A | DONE | 34 | M |  | EXACT TL-3 6240028 | VD | 2025-02-03 | Z | 2025-01-14 | 700 | 0 | 130 | F | 0 | 1480 |  |  |  | 20
2025-01-31 | 2862 | bth | TL3_RAMP 2 | A | DONE | 33 | M-L |  | EXACT TL-3 6240028 |  | 2025-02-03 | Z | 2025-01-14 | 510 | 250 | 60 | F | 0 | 1530 |  |  |  | 20
2025-01-28 | 2655 |  | 78778 - 78779 | A | DONE | 18 | S-M |  | MONROE HS 6240018 | Foam gasket | 2025-01-29 | Z | 2025-01-10 | 440 | 0 | 0 |  | 0 | 510 |  | Roof drops |  | 19
2025-01-28 | 2656 |  | 78780 - 78781 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | Foam gasket | 2025-01-29 | Z | 2025-01-10 | 280 | 0 | 0 |  | 0 | 480 |  | Roof drops |  | 19
2025-01-28 | 2658 | w | 78783 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1-1/2 DB | 2025-01-29 | Z | 2025-01-16 | 30 | 0 | 0 |  | 30 | 110 |  | Curb / Cap |  | 13
2025-01-28 | 2675 |  | 78782 | A | DONE | 2 | S |  | MONROE HS 6240018 | Foam gasket | 2025-01-29 | Z | 2025-01-13 | 40 | 0 | 0 |  | 0 | 90 |  | Misc sleeves |  | 16
2025-01-29 | 2533 |  | 59840 - 59841 | A | DONE | 51 | M |  | PROMEGA BTC 6230022 |  | 2025-01-30 | Z | 2025-01-14 | 510 | 0 | 760 | F | 0 | 2300 |  | AHU-N SA |  | 16
2025-01-28 | 2539 |  | 59842 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-01-30 | Z | 2025-01-23 | 50 | 0 | 0 |  | 0 | 130 |  | Louvers |  | 7
2025-01-31 | 2541 |  | 59844 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 | paint | 2025-02-03 | Z | 2025-01-28 | 20 | 0 | 0 |  | 20 | 20 |  | Heto EA |  | 6
2025-01-28 | 4788 | w | 61197 | A | DONE | 2 | S-M |  | ROCK CO. JAIL 6220018 |  | 2025-01-29 | Z | 2025-01-23 | 30 | 0 | 0 |  | 0 | 60 |  | Temp curb cap |  | 6
2025-01-29 | 2823 |  | 82961 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-30 | Z | 2025-01-21 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor EA |  | 9
2025-01-30 | 2824 |  | 67735 - 67736 | A | DONE | 2 | S-M |  | STOUGHTON TRAILER 6240015 | paint | 2025-01-31 | Z | 2025-01-29 | 50 | 0 | 0 |  | 40 | 80 |  | Bathroom Sq/Round |  | 2
2025-01-29 | 3751 |  | 83259 | A | DONE | 5 | S |  | UW-BIO CHEM 6240036 | bird s. | 2025-01-30 | Z | 2025-01-24 | 110 | 0 | 0 |  | 0 | 170 |  | AHU-9 |  | 6
2025-01-31 | 1069 |  | 83913 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-04 | Z | 2025-01-13 | 40 | 0 | 0 |  | 0 | 100 |  | Sleeves |  | 22
2025-01-29 | 1097 |  | 2920 | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2025-02-04 | Z | 2025-01-29 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 6
2025-01-31 | 3315 |  | 72949 - 72950 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-02-03 | Z | 2025-01-16 | 30 | 0 | 0 |  | 20 | 50 |  | Rm 216,220 GE |  | 18
2025-01-31 | 3316 |  | 83551 - 83552 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-02-03 | Z | 2025-01-16 | 50 | 0 | 0 |  | 20 | 70 |  | Rm 222 , 236 GE |  | 18
2025-01-31 | 3317 | bth | 83553 - 83554 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2025-02-03 | Z | 2025-01-16 | 50 | 20 | 0 |  | 0 | 70 |  | Rm 216 Hood |  | 18
2025-01-31 | 3318 |  | 83555 - 83556 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-02-03 | Z | 2025-01-16 | 20 | 0 | 0 |  | 20 | 40 |  | Rm 287 , 291 GE |  | 18
2025-01-31 | 3319 |  | 83557 - 83558 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-02-03 | Z | 2025-01-20 | 20 | 0 | 0 |  | 0 | 30 |  | Rm 291,296 GE |  | 14
2025-01-31 | 3320 |  | 83559 - 83560 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-02-03 | Z | 2025-01-20 | 20 | 0 | 0 |  | 0 | 30 |  | Rm 296 GE |  | 14
2025-01-31 | 3321 | bth | 83561 - 83562 | A | DONE | 5 | S-M | pcd | UWRF 6230010 |  | 2025-02-03 | Z | 2025-01-22 | 90 | 20 | 0 |  | 0 | 120 |  | W. Loading / L2C Rm 289 |  | 12
2025-01-31 | 3322 |  | 83563 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-02-03 | Z | 2025-01-22 | 20 | 0 | 0 |  | 0 | 20 |  | L3 shaft |  | 12
2025-01-31 | 3323 |  | 83564 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2025-02-03 | Z | 2025-01-22 | 20 | 0 | 0 |  | 0 | 20 |  | L2-1A flashing |  | 12
2025-01-31 | 3326 |  | 83539 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-02-03 | Z | 2025-01-29 | 20 | 0 | 0 |  | 0 | 40 |  | PH OA Plenum |  | 5
2025-01-27 | 2362 | bth | LPSA-03-11 | A | DONE | 16 | S-M | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 280 | 70 | 30 | F | 80 | 490 |  |  |  | 21
2025-01-27 | 2363 |  | LPSA-03-12 | A | DONE | 10 | S | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 180 | 0 | 60 | F | 30 | 290 |  |  |  | 21
2025-01-27 | 2364 | bth | LPSA-03-13 | A | DONE | 20 | M | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 380 | 20 | 80 | F | 50 | 580 |  |  |  | 21
2025-01-27 | 2365 | bth | LPSA-03-14 | A | DONE | 4 | S | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-28 | Z | 2025-01-07 | 80 | 20 | 0 |  | 50 | 150 |  |  |  | 21
2025-01-27 | 2366 | bth | LPSA-03-15 | A | DONE | 11 | S-M | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 190 | 20 | 50 | F | 20 | 330 |  |  |  | 21
2025-01-27 | 2367 | bth | LPSA-03-16 | A | DONE | 13 | S-M | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 210 | 20 | 90 | F | 20 | 410 |  |  |  | 21
2025-01-28 | 2368 | bth | LPSA-03-17 | A | DONE | 14 | S-M | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-28 | Z | 2025-01-07 | 110 | 100 | 130 | F | 30 | 390 |  |  |  | 21
2025-01-28 | 2369 | bth | LPSA-03-17B | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | VD's | 2025-01-28 | Z | 2025-01-07 | 70 | 100 | 110 | F | 0 | 310 |  |  |  | 21
2025-01-27 | 2370 |  | LPSA-03-18 | A | DONE | 16 | M | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 240 | 0 | 150 | F | 30 | 540 |  |  |  | 21
2025-01-28 | 2371 | bth | LPSA-03-19 | A | DONE | 14 | S-M | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-28 | Z | 2025-01-07 | 160 | 150 | 30 | F | 80 | 400 |  |  |  | 21
2025-01-27 | 2372 | bth | LPSA-03-20 | A | DONE | 11 | S-M | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 180 | 30 | 50 | F | 30 | 340 |  |  |  | 21
2025-01-27 | 2373 |  | LPSA-03-21 | A | DONE | 30 | M-L | pt.neal | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2025-01-28 | Z | 2025-01-07 | 340 | 0 | 400 | F | 40 | 920 |  |  |  | 21
2025-01-27 | 2376 | sp | LPSA-03-24 | A | DONE | 10 | S |  | UWSP ALBERTSON 6230016 |  | 2025-02-11 | Z | 2025-01-07 | 20 | 210 | 0 |  | 0 | 220 |  |  |  | 35
2025-01-27 | 2377 | sp | LPSA-03-25 | A | DONE | 13 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-02-11 | Z | 2025-01-07 | 20 | 290 | 0 |  | 0 | 290 |  |  |  | 35
2025-01-28 | 2379 | bth | LPSA-03-27 | A | DONE | 22 | M | pt.neal | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-01-28 | Z | 2025-01-07 | 260 | 20 | 250 | F | 30 | 640 |  |  |  | 21
2025-01-28 | 2380 | bth | LPSA-03-28 | A | DONE | 6 | S | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-01-28 | Z | 2025-01-07 | 120 | 20 | 0 |  | 80 | 200 |  |  |  | 21
2025-01-28 | 2381 | bth | LPSA-03-29 | A | DONE | 8 | S | pt.neal | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-01-28 | Z | 2025-01-07 | 150 | 20 | 30 | F | 60 | 260 |  |  |  | 21
2025-01-28 | 2382 |  | LPSA-03-30 | A | DONE | 10 | S-M | pt.neal | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-01-28 | Z | 2025-01-07 | 140 | 0 | 100 | F | 30 | 330 |  |  |  | 21
2025-01-28 | 3222 |  | 81191 | A | DONE | 3 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-02-04 | Z | 2025-01-22 | 70 | 0 | 0 |  | 0 | 70 |  | Angles |  | 13
2025-01-29 | 2757 |  | 70133 | A | DONE | 2 | S | neal | UWSP CHAMPION HALL 6240008 | VD's | 2025-01-30 | Z | 2025-01-16 | 50 | 0 | 0 |  | 0 | 70 |  | L1E_SALP-15 |  | 14
2025-01-29 | 2758 |  | L1E_EA 2 | A | DONE | 3 | S |  | UWSP CHAMPION HALL 6240008 | VD's | 2025-01-30 | Z | 2025-01-16 | 40 | 0 | 20 | F | 0 | 80 |  |  |  | 14
2025-01-29 | 2759 |  | L1E_EA 3 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-16 | 40 | 0 | 50 | F | 0 | 100 |  |  |  | 14
2025-01-29 | 2760 |  | L1E_EA 4 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-16 | 40 | 0 | 70 | F | 0 | 140 |  |  |  | 14
2025-01-29 | 2761 |  | L1E_EA 5 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-16 | 90 | 0 | 30 | F | 0 | 130 |  |  |  | 14
2025-01-29 | 2762 |  | L1E_EA 6 | A | DONE | 11 | S | alum | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-16 | 140 | 0 | 130 | F | 0 | 170 |  |  |  | 14
2025-01-29 | 2763 |  | L1E_EA 7 | A | DONE | 8 | S | pt.alum | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-16 | 70 | 0 | 120 | F | 0 | 170 |  |  |  | 14
2025-01-29 | 2764 |  | L1E_EA 8 | A | DONE | 5 | S | alum | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-16 | 70 | 0 | 40 | F | 0 | 60 |  |  |  | 14
2025-01-29 | 2765 |  | L1E_EA 9 | A | DONE | 8 | S-M |  | UWSP CHAMPION HALL 6240008 | MOD | 2025-01-30 | Z | 2025-01-16 | 110 | 0 | 90 | F | 0 | 270 |  |  |  | 14
2025-01-29 | 2766 |  | L1E_EA 10 | A | DONE | 8 | S |  | UWSP CHAMPION HALL 6240008 | MOD , bird s. | 2025-01-30 | Z | 2025-01-16 | 130 | 0 | 50 | F | 0 | 210 |  |  |  | 14
2025-01-29 | 2767 | bth | L1E_SALP 1 | A | DONE | 8 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 100 | 20 | 60 | F | 30 | 240 |  |  |  | 9
2025-01-29 | 2768 | bth | L1E_SALP 2 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-21 | 60 | 20 | 70 | F | 0 | 180 |  |  |  | 9
2025-01-29 | 2769 | bth | L1E_SALP 3 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 50 | 50 | 30 | F | 30 | 120 |  |  |  | 9
2025-01-29 | 2770 |  | L1E_SALP 4 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 9
2025-01-29 | 2771 |  | L1E_SALP 5 | A | DONE | 4 | S | neal | UWSP CHAMPION HALL 6240008 | VD , 1" liner | 2025-01-30 | Z | 2025-01-21 | 70 | 0 | 20 | F | 30 | 130 |  |  |  | 9
2025-01-29 | 2772 | bth | L1E_SALP 6 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 60 | 20 | 0 |  | 40 | 90 |  |  |  | 9
2025-01-29 | 2773 | bth | L1E_SALP 7 | A | DONE | 10 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 130 | 30 | 80 | F | 40 | 270 |  |  |  | 9
2025-01-29 | 2774 |  | L1E_SALP 8 | A | DONE | 8 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-21 | 150 | 0 | 30 | F | 0 | 250 |  |  |  | 9
2025-01-29 | 2775 | bth | L1E_SALP 9 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 80 | 20 | 30 | F | 30 | 150 |  |  |  | 9
2025-01-29 | 2776 | bth | L1E_SALP 10 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-21 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 9
2025-01-29 | 2777 | bth | L1E_SALP 11 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 80 | 50 | 20 | F | 30 | 160 |  |  |  | 9
2025-01-29 | 2778 |  | L1E_SALP 12 | A | DONE | 16 | M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 130 | 0 | 260 | F | 50 | 510 |  |  |  | 9
2025-01-29 | 2779 |  | L1E_SALP 13 | A | DONE | 20 | M |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-21 | 200 | 0 | 290 | F | 0 | 590 |  |  |  | 9
2025-01-29 | 2780 | bth | L1E_SALP 14 | A | DONE | 8 | S-M | pt.neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-21 | 30 | 140 | 30 | F | 40 | 250 |  |  |  | 9
2025-01-29 | 2781 | sp | L1E_SALP 15 | A | DONE | 9 | S-M | neal | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-21 | 30 | 190 | 0 |  | 0 | 250 |  |  |  | 9
2025-01-29 | 2782 |  | 70134 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-01-30 | Z | 2025-01-27 | 20 | 0 | 0 |  | 20 | 30 |  | VAV-21-101 |  | 3
2025-01-29 | 2783 |  | 70135 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-30 | Z | 2025-01-29 | 20 | 0 | 0 |  | 0 | 20 |  | VAV -21-122 |  | 1
2025-01-30 | 2156 | bth | L01_F_SALP_001 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 30 | 30 | 0 |  | 0 | 70 |  |  |  | 66
2025-01-30 | 2157 | bth | L01_F_SALP_002 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 60 | 90 | 0 |  | 0 | 160 |  |  |  | 66
2025-01-30 | 2158 | bth | L01_F_SALP_003 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 70 | 50 | 70 | F | 0 | 230 |  |  |  | 66
2025-01-30 | 2159 | bth | L01_F_SALP_004 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 100 | 50 | 50 | F | 0 | 230 |  |  |  | 66
2025-01-30 | 2160 | sp | L01_F_SALP_005 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 20 | 80 | 0 |  | 0 | 90 |  |  |  | 66
2025-01-30 | 2161 | bth | L01_F_SALP_006 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 70 | 40 | 90 | F | 0 | 230 |  |  |  | 66
2025-01-30 | 2162 | bth | L01_F_SALP_007 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 20 | 50 | 120 | F | 0 | 230 |  |  |  | 66
2025-01-30 | 2163 | bth | L01_F_SALP_008 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 120 | 100 | 30 | F | 0 | 260 |  |  |  | 66
2025-01-30 | 2164 | bth | L01_F_SALP_009 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 60 | 20 | 80 | F | 0 | 200 |  |  |  | 66
2025-01-30 | 2165 | bth | L01_F_SALP_010 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 40 | 50 | 40 | F | 0 | 150 |  |  |  | 66
2025-01-30 | 2166 | sp | L01_F_SALP_011 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-01-31 | Z | 2024-11-26 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 66
2025-01-30 | 2167 | bth | L01_F_SALP_012 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 90 | 60 | 50 | F | 0 | 340 |  |  |  | 66
2025-01-30 | 2168 | bth | L01_F_SALP_013 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 130 | 60 | 90 | F | 0 | 340 |  |  |  | 66
2025-01-30 | 2169 | bth | L01_F_SALP_014 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 70 | 30 | 140 | F | 0 | 290 |  |  |  | 66
2025-01-30 | 2170 | sp | L01_F_SALP_015 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 20 | 60 | 0 |  | 0 | 90 |  |  |  | 66
2025-01-30 | 2171 | sp | L01_F_SALP_016 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 66
2025-01-30 | 2172 | sp | L01_F_SALP_017 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 66
2025-01-30 | 2173 | bth | L01_F_RAD_001 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 60 | 20 | 0 |  | 40 | 90 |  |  |  | 66
2025-01-30 | 2174 | sp | L01_F_RAD_002 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-01-31 | Z | 2024-11-26 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 66
2025-01-30 | 2175 |  | L01_F_RAD_003 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 80 | 0 | 40 | F | 100 | 170 |  |  |  | 66
2025-01-30 | 2176 |  | L01_F_RAD_004 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 90 | 0 | 40 | F | 110 | 180 |  |  |  | 66
2025-01-30 | 2177 | sp | L01_F_RAD_005 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" spiral acou. | 2025-01-31 | Z | 2024-11-26 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 66
2025-01-30 | 2178 |  | L01_F_RAD_006 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 70 | 0 | 40 | F | 90 | 150 |  |  |  | 66
2025-01-30 | 2179 |  | L01_F_RAD_007 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 90 | 0 | 40 | F | 90 | 160 |  |  |  | 66
2025-01-30 | 2180 | bth | L01_F_RAD_008 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 50 | 60 | 0 |  | 30 | 130 |  |  |  | 66
2025-01-30 | 2181 |  | L01_F_RAD_009 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 50 | 0 | 40 | F | 60 | 100 |  |  |  | 66
2025-01-30 | 2182 |  | L01_F_RAD_010 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 100 | 0 | 40 | F | 100 | 170 |  |  |  | 66
2025-01-30 | 2183 |  | L01_F_RAD_011 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 90 | 0 | 40 | F | 80 | 150 |  |  |  | 66
2025-01-30 | 2184 | sp | L01_F_RAD_012 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" spiral acou. | 2025-01-31 | Z | 2024-11-26 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 66
2025-01-30 | 2185 | bth | L01_F_RAD_013 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 40 | 60 | 0 |  | 20 | 100 |  |  |  | 66
2025-01-30 | 2186 |  | L01_F_RAD_014 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-01-31 | Z | 2024-11-26 | 90 | 0 | 40 | F | 90 | 160 |  |  |  | 66
2025-01-30 | 2187 | sp | L01_F_RAD_015 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" spiral acou. | 2025-01-31 | Z | 2024-11-26 | 20 | 20 | 0 |  | 20 | 30 |  |  |  | 66
2025-01-28 | 4111 |  | 69246 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-01-31 | Z | 2025-01-28 | 100 | 0 | 0 |  | 0 | 130 |  | Angles |  | 3
2025-01-28 | 1979 |  | 71487 | A | DONE | 3 | S | neal | WSCC 6240006 |  | 2025-01-30 | Z | 2025-01-23 | 20 | 0 | 40 | F | 0 | 60 |  | RTU-11 |  | 7
[6 empty] | 994 | [13 empty] | 30350 |  |  |  | 4460 | 14.7%
WEEK OF 2-3-2025
2025-02-03 | 1219 |  | 81950 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 | VD's , 1" liner | 2025-02-03 | Z | 2025-01-20 | 70 | 0 | 0 |  | 50 | 100 |  | 1st Fl lobby TA |  | 14
2025-02-03 | 1220 |  | 81951 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | VD's | 2025-02-03 | Z | 2025-01-20 | 20 | 0 | 0 |  | 0 | 30 |  | 1st Fl |  | 14
2025-02-03 | 1221 |  | 81952 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-03 | Z | 2025-01-20 | 80 | 0 | 20 | F | 60 | 90 |  | 1st Fl |  | 14
2025-02-03 | 1222 |  | 81953 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-02-03 | Z | 2025-01-21 | 20 | 0 | 0 |  | 0 | 20 |  | 1st Floor |  | 13
2025-02-03 | 1240 |  | 81954 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | flex | 2025-02-03 | Z | 2025-01-27 | 20 | 0 | 0 |  | 0 | 20 |  | 1st Floor |  | 7
2025-02-03 | 1241 |  | 81955 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | bird s. | 2025-02-03 | Z | 2025-01-27 | 20 | 0 | 0 |  | 0 | 30 |  | 1st Floor outs |  | 7
2025-02-07 | 1728 |  | 85151 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-11 | Z | 2025-01-29 | 190 | 0 | 0 |  | 0 | 200 |  | DOAS 1,2 FSD's |  | 13
2025-02-04 | 1729 |  | 81956 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | bird s. | 2025-02-05 | Z | 2025-02-04 | 20 | 0 | 0 |  | 20 | 30 |  | 1st Fl Misc |  | 1
2025-02-05 | 909 |  | 84906 | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-02-06 | Z | 2025-01-28 | 30 | 0 | 0 |  | 0 | 40 |  | VAV 9.9R |  | 9
2025-02-05 | 910 |  | 84959 | A | DONE | 3 | S |  | BMH AHU9 6240001 |  | 2025-02-06 | Z | 2025-01-28 | 20 | 40 | 0 |  | 0 | 90 |  | Mech Rm SAHP |  | 9
2025-02-05 | 911 | sp | 84909 | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-02-06 | Z | 2025-01-30 | 30 | 0 | 0 |  | 0 | 50 |  | Misc |  | 7
2025-02-05 | 912 |  | 84908 | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-02-06 | Z | 2025-01-30 | 30 | 0 | 0 |  | 0 | 40 |  | CS SAHP |  | 7
2025-02-05 | 913 |  | 84910 | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-02-06 | Z | 2025-01-30 | 20 | 0 | 0 |  | 0 | 20 |  | CS SAHP |  | 7
2025-02-07 | 2461 |  | 69734 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2025-02-11 | Z | 2025-02-06 | 130 | 20 | 0 |  | 0 | 160 |  | 1st B-Exh |  | 5
2025-02-07 | 2458 | bth | 81652 - 81653 | A | DONE | 6 | S-M | neal | CDIS 6220028 | paint | 2025-02-11 | Z | 2025-01-31 | 90 | 40 | 0 |  | 20 | 160 |  | 2nd Fl GET CB 1163 |  | 11
2025-02-07 | 2459 |  | 61386 , 61388 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2025-02-11 | Z | 2025-01-31 | 130 | 0 | 0 |  | 40 | 190 |  | CB 1163 |  | 11
2025-02-07 | 2460 | sp | 61387 | A | DONE | 4 | S-M | neal | CDIS 6220028 |  | 2025-02-11 | Z | 2025-01-31 | 40 | 40 | 0 |  | 0 | 90 |  | CB 1163 |  | 11
2025-02-07 | 820 |  | 1020 | A | DONE | 6 | S-M | Mix | DELLSHIRE 6240017 |  | 2025-02-10 | Z | 2025-01-28 | 150 | 0 | 0 |  | 0 | 440 |  | Hangers |  | 13
2025-02-07 | 824 | w | 854 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-02-10 | Z | 2025-02-04 | 30 | 0 | 0 |  | 0 | 60 |  | Sleeves |  | 6
2025-02-05 | 450 |  | 83041 | A | DONE | 4 | S |  | DOVE 6240041 |  | 2025-02-05 | Z | 2025-01-31 | 80 | 0 | 0 |  | 0 | 110 |  | Trays |  | 5
2025-02-07 | 2893 |  | 56697 , 56698 | A | DONE | 2 | S |  | EXACT SCIENCE 8240019 |  | 2025-02-12 | Z | 2025-01-31 | 20 | 0 | 0 |  | 0 | 50 |  | Fire stop , Water stop |  | 12
2025-02-03 | 2863 |  | TL3_RAMP 3 | A | DONE | 27 | M |  | EXACT TL-3 6240028 | VD's | 2025-02-03 | Z | 2025-01-14 | 560 | 0 | 110 | F | 0 | 920 |  |  |  | 20
2025-02-03 | 2864 | bth | TL3_RAMP 4 | A | DONE | 17 | S-M |  | EXACT TL-3 6240028 | VD | 2025-02-03 | Z | 2025-01-14 | 310 | 110 | 0 |  | 0 | 590 |  |  |  | 20
2025-02-03 | 2865 |  | TL3_RAMP 5 | A | DONE | 28 | M |  | EXACT TL-3 6240028 | VD's | 2025-02-03 | Z | 2025-01-14 | 340 | 0 | 360 | F | 0 | 960 |  |  |  | 20
2025-02-03 | 2866 | bth | TL3_RAMP 6 | A | DONE | 20 | S-M |  | EXACT TL-3 6240028 | VD | 2025-02-03 | Z | 2025-01-14 | 410 | 40 | 30 | F | 0 | 580 |  |  |  | 20
2025-02-06 | 2867 | bth | TL3_SAMP 4 | A | DONE | 44 | M-L |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 570 | 90 | 420 | F | 0 | 2400 |  |  |  | 22 | 2025-02-10
2025-02-06 | 2868 | bth | TL3_SAMP 5 | A | DONE | 27 | M |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 240 | 180 | 250 | F | 0 | 890 |  |  |  | 22 | 2025-02-10
2025-02-05 | 2869 | bth | TL3_SAMP 6 | A | DONE | 16 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 220 | 30 | 150 | F | 0 | 540 |  |  |  | 22 | 2025-02-10
2025-02-05 | 2870 |  | TL3_SAMP 7 | A | DONE | 9 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 160 | 0 | 60 | F | 0 | 300 |  |  |  | 22 | 2025-02-10
2025-02-05 | 2871 |  | TL3_SAMP 8 | A | DONE | 18 | M |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 180 | 0 | 270 | F | 0 | 670 |  |  |  | 22 | 2025-02-10
2025-02-06 | 2872 | bth | TL3_SAMP 9 | A | DONE | 16 | M |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 120 | 70 | 190 | F | 0 | 460 |  |  |  | 22 | 2025-02-10
2025-02-06 | 2873 | bth | TL3_SAMP 10 | A | DONE | 17 | M |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 120 | 210 | 90 | F | 0 | 530 |  |  |  | 22 | 2025-02-10
2025-02-06 | 2874 |  | TL3_RAMP 7 | A | DONE | 39 | M-L |  | EXACT TL-3 6240028 | VD | 2025-02-07 | Z | 2025-01-16 | 630 | 0 | 330 | F | 0 | 1800 |  |  |  | 22 | 2025-02-10
2025-02-06 | 2875 |  | TL3_RAMP 8 | A | DONE | 27 | M |  | EXACT TL-3 6240028 | VD's | 2025-02-07 | Z | 2025-01-16 | 370 | 0 | 290 | F | 0 | 740 |  |  |  | 22 | 2025-02-10
2025-02-06 | 2876 | bth | TL3_RAMP 9 | A | DONE | 43 | M-L |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 460 | 70 | 540 | F | 0 | 1970 |  |  |  | 22 | 2025-02-10
2025-02-06 | 2877 | bth | TL3_RAMP 10 | A | DONE | 35 | M |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 420 | 70 | 370 | F | 0 | 1210 |  |  |  | 22 | 2025-02-10
2025-02-06 | 2878 | bth | TL3_RAMP 11 | A | DONE | 17 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-07 | Z | 2025-01-16 | 130 | 80 | 200 | F | 0 | 600 |  |  |  | 22 | 2025-02-10
2025-02-03 | 2936 |  | 82568 | A | DONE | 4 | S-M |  | LABCORP 6240016 | VD's | 2025-02-03 | Z | 2025-01-24 | 90 | 0 | 0 |  | 0 | 180 |  | 1st floor B-Section |  | 10
2025-02-05 | 2937 | w | 82569 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2025-02-06 | Z | 2025-01-29 | 20 | 0 | 0 |  | 0 | 30 |  | Fluid Cooler Curb Cap |  | 8
2025-02-05 | 2659 |  | 78784 - 78785 | A | DONE | 4 | S-M |  | MONROE HS 6240018 |  | 2025-02-06 | Z | 2025-01-24 | 90 | 0 | 0 |  | 0 | 310 |  | Sleeves |  | 13
2025-02-03 | 2540 |  | 59843 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 | 1" liner | 2025-02-03 | Z | 2025-01-28 | 20 | 0 | 0 |  | 20 | 40 |  | TA |  | 6
2025-02-06 | 2542 |  | 59845 - 59847 | A | DONE | 49 | L |  | PROMEGA BTC 6230022 |  | 2025-02-07 | Z | 2025-01-29 | 1040 | 0 | 180 | F | 0 | 2530 |  | RA Fan |  | 9
2025-02-06 | 2543 |  | 59848 | A | DONE | 10 | M |  | PROMEGA BTC 6230022 |  | 2025-02-07 | Z | 2025-01-29 | 240 | 0 | 0 |  | 0 | 770 |  | AUH-M RA |  | 9
2025-02-06 | 2544 |  | 59849 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-02-07 | Z | 2025-01-29 | 40 | 0 | 0 |  | 0 | 100 |  | AHU-M SA |  | 9
2025-02-05 | 168 |  | 84272 | A | DONE | 2 | S |  | SCHUMANN PRINTERS 10060405 |  | 2025-02-05 | Z | 2025-01-29 | 40 | 0 | 0 |  | 0 | 50 |  | Flat Stock |  | 7
2025-02-07 | 3141 |  | 68456 | A | DONE | 5 | S |  | SPH BIRTH CENTER 6240022 |  | 2025-02-10 | Z | 2025-02-04 | 20 | 100 | 0 |  | 0 | 110 |  | EC |  | 6
2025-02-06 | 1408 |  | 68453 | A | DONE | 8 | S-M |  | SPH SURGERY 6240039 |  | 2025-02-10 | Z | 2025-01-24 | 200 | 0 | 0 |  | 0 | 290 |  | 1" wide straps |  | 17
2025-02-03 | 4296 |  | 79935 | A | DONE | 18 | S-M |  | ST.BERNARDS 6230023 | 1" liner | 2025-02-03 | Z | 2025-01-17 | 200 | 0 | 230 | F | 350 | 390 |  | Misc |  | 17
2025-02-03 | 4297 |  | 79936 | A | DONE | 2 | S |  | ST.BERNARDS 6230023 | paint | 2025-02-03 | Z | 2025-01-17 | 30 | 0 | 0 |  | 30 | 50 |  | Plenums |  | 17
2025-02-03 | 4298 |  | 79937 - 79938 | A | DONE | 15 | S-M |  | ST.BERNARDS 6230023 | 1" liner | 2025-02-03 | Z | 2025-01-17 | 270 | 0 | 90 | F | 280 | 330 |  | FCU 19,20 |  | 17
2025-02-03 | 4299 | bth | 79939 | A | DONE | 9 | S-M |  | ST.BERNARDS 6230023 | paint | 2025-02-03 | Z | 2025-01-17 | 100 | 120 | 0 |  | 50 | 190 |  | Loft |  | 17
2025-02-05 | 2825 |  | 67737 | A | DONE | 2 | S | alum | STOUGHTON TRAILER 6240015 |  | 2025-02-06 | Z | 2025-01-29 | 20 | 0 | 0 |  | 0 | 20 |  | Dryer vent |  | 8
2025-02-05 | 2826 | sp | 82963 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-02-06 | Z | 2025-01-31 | 0 | 20 | 0 |  | 0 | 20 |  | EA , SA |  | 6
2025-02-05 | 2828 |  | 84760 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-02-06 | Z | 2025-02-04 | 120 | 0 | 0 |  | 0 | 170 |  | Flashing |  | 2
2025-02-05 | 633 |  | 83260 | A | DONE | 8 | S |  | UW-BIO CHEM 6240036 |  | 2025-02-06 | Z | 2025-01-27 | 90 | 0 | 90 | F | 0 | 230 |  | Misc |  | 10
2025-02-03 | 1050 |  | LL - SAT-3-L-4 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-02-04 | Z | 2025-01-02 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 33
2025-02-03 | 1051 |  | LL - SAT-3-L-5 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-02-04 | Z | 2025-01-02 | 60 | 0 | 100 | F | 120 | 230 |  |  |  | 33
2025-02-03 | 1053 |  | LL - SAT-3-L-3.2 | A | DONE | 20 | M |  | UW-LEVY HALL 6230028 | VD's | 2025-02-04 | Z | 2025-01-02 | 140 | 0 | 360 | F | 0 | 640 |  |  |  | 33
2025-02-03 | 1054 | bth | LL - SAT-3-L-3.3 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-04 | Z | 2025-01-02 | 50 | 20 | 110 | F | 0 | 220 |  |  |  | 33
2025-02-04 | 1055 |  | LL - SAMP 3 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-04 | Z | 2025-01-02 | 120 | 40 | 0 |  | 0 | 220 |  |  |  | 33
2025-02-04 | 1056 |  | LL - RAMP 9 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-02-04 | Z | 2025-01-02 | 160 | 0 | 90 | F | 190 | 360 |  |  |  | 33
2025-02-04 | 1057 | bth | LL - RAMP 2 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-02-04 | Z | 2025-01-02 | 260 | 30 | 0 |  | 20 | 400 |  |  |  | 33
2025-02-03 | 1091 |  | 83915 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-04 | Z | 2025-01-22 | 40 | 0 | 0 |  | 0 | 50 |  | LL Utility EA |  | 13
2025-02-03 | 4599 |  | LL - FCU - 1 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-04 | Z | 2025-01-02 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 33
2025-02-07 | bins |  | Parts Tray Bins | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-07 | Z | 2025-02-06 | 80 | 0 | 0 |  | 0 | 80 |  | Tray Bins |  | 1
2025-02-07 | 3100 | bth | 82148 - 82150 | A | DONE | 9 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-10 | Z | 2025-01-14 | 120 | 70 | 30 | F | 70 | 230 |  | SAT-3-3-4,6,7 |  | 27
2025-02-07 | 3101 | bth | 82251 - 82252 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-10 | Z | 2025-01-14 | 40 | 50 | 80 | F | 0 | 180 |  | SAT-3-3-8 |  | 27
2025-02-07 | 3102 |  | 82253 - 82255 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-10 | Z | 2025-01-14 | 130 | 0 | 20 |  | 50 | 180 |  | SAT-3-3-10,11 |  | 27
2025-02-07 | 3103 | bth | 82256 - 82259 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 110 | 100 | 70 | F | 0 | 310 |  | SAT-3-3-1,2,11 |  | 27
2025-02-07 | 3104 |  | 82260 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 70 | 0 | 60 | F | 0 | 170 |  | SAT-3-3-3 |  | 27
2025-02-07 | 3105 | bth | 82264 - 82265 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-10 | Z | 2025-01-14 | 70 | 60 | 40 | F | 70 | 190 |  | SAT-3-3-5,9 |  | 27
2025-02-07 | 3106 | bth | 82268 - 82269 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 50 | 20 | 40 | F | 0 | 110 |  | SAT-1-3-3 |  | 27
2025-02-07 | 3107 | bth | 82270 - 82271 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 30 | 30 | 30 | F | 0 | 100 |  | SAT-1-3-1 |  | 27
2025-02-07 | 3108 | bth | 82272 - 82273 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 70 | 30 | 40 | F | 0 | 150 |  | SAT-1-3-4 |  | 27
2025-02-07 | 3109 |  | 82274 - 82277 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 150 | 0 | 80 | F | 0 | 320 |  | SAT-1-3-2 |  | 27
2025-02-07 | 3110 | bth | 82278 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 20 | 50 | 20 | F | 0 | 90 |  | SAT-1-3-2 |  | 27
2025-02-07 | 3111 |  | 82279 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-10 | Z | 2025-01-14 | 60 | 0 | 0 |  | 50 | 80 |  | 331.A TA |  | 27
2025-02-07 | 3112 | bth | 82280 - 82282 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 90 | 50 | 20 | F | 0 | 200 |  | SAT-1-3-5,6,7 |  | 27
2025-02-07 | 3899 | bth | 82139 - 82140 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-10 | Z | 2025-01-14 | 50 | 80 | 30 | F | 0 | 160 |  | SAT-1-3-17,21 |  | 27
2025-02-07 | 3324 |  | 83565 - 83566 | A | DONE | 2 | S-M |  | UWRF 6230010 | flex , paint , 1" liner | 2025-02-11 | Z | 2025-01-23 | 30 | 0 | 0 |  | 20 | 50 |  | L2 TA |  | 19
2025-02-07 | 3325 |  | 83567 - 83569 | A | DONE | 2 | S-M |  | UWRF 6230010 | flex , 1" liner | 2025-02-11 | Z | 2025-01-23 | 40 | 0 | 0 |  | 30 | 50 |  | L2 TA |  | 19
2025-02-04 | 2399 | bth | LPSA-04-2 | A | DONE | 9 | S | pt.neal | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-02-04 | Z | 2025-01-15 | 140 | 70 | 0 |  | 50 | 270 |  |  |  | 20
2025-02-04 | 3200 | bth | LPSA-04-3 | A | DONE | 6 | S | pt.neal | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-02-04 | Z | 2025-01-15 | 130 | 20 | 0 |  | 50 | 170 |  |  |  | 20
2025-02-04 | 3201 | bth | LPSA-04-4 | A | DONE | 11 | S-M | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-02-04 | Z | 2025-01-15 | 160 | 30 | 80 | F | 40 | 310 |  |  |  | 20
2025-02-04 | 3202 |  | LPSA-04-5 | A | DONE | 7 | S |  | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-02-04 | Z | 2025-01-15 | 110 | 0 | 50 | F | 50 | 220 |  |  |  | 20
2025-02-04 | 3203 | bth | LPSA-04-6 | A | DONE | 9 | S | pt.neal | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-02-04 | Z | 2025-01-15 | 120 | 70 | 20 | F | 40 | 220 |  |  |  | 20
2025-02-04 | 3204 | bth | LPSA-04-7 | A | DONE | 4 | S | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-02-04 | Z | 2025-01-15 | 40 | 60 | 0 |  | 20 | 110 |  |  |  | 20
2025-02-04 | 3205 | bth | LPSA-04-8 | A | DONE | 22 | M | pt.neal | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-02-04 | Z | 2025-01-15 | 380 | 20 | 130 | F | 30 | 630 |  |  |  | 20
2025-02-04 | 3206 |  | LPSA-04-9 | A | DONE | 10 | S-M | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-02-04 | Z | 2025-01-15 | 80 | 0 | 160 | F | 20 | 330 |  |  |  | 20
2025-02-04 | 3207 | bth | LPSA-04-10 | A | DONE | 8 | S | pt.neal | UWSP ALBERTSON 6230016 | VD , 1" liner | 2025-02-04 | Z | 2025-01-15 | 130 | 20 | 30 | F | 50 | 230 |  |  |  | 20
2025-02-04 | 3208 | bth | LPSA-04-11 | A | DONE | 13 | S-M | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-02-04 | Z | 2025-01-15 | 130 | 150 | 30 | F | 60 | 340 |  |  |  | 20
2025-02-04 | 3209 | bth | LPSA-04-12 | A | DONE | 7 | S | pt.neal | UWSP ALBERTSON 6230016 | 1" liner | 2025-02-04 | Z | 2025-01-15 | 150 | 20 | 0 |  | 70 | 190 |  |  |  | 20
2025-02-04 | 3210 | sp | LPSA-04-13 | A | DONE | 6 | S |  | UWSP ALBERTSON 6230016 |  | 2025-02-04 | Z | 2025-01-15 | 20 | 110 | 0 |  | 0 | 110 |  |  |  | 20
2025-02-04 | 3211 | sp | LPSA-04-14 | A | DONE | 16 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-02-04 | Z | 2025-01-15 | 40 | 360 | 0 |  | 0 | 450 |  |  |  | 20
2025-02-04 | 3212 | sp | LPSA-04-15 | A | DONE | 8 | S |  | UWSP ALBERTSON 6230016 |  | 2025-02-04 | Z | 2025-01-15 | 20 | 170 | 0 |  | 0 | 210 |  |  |  | 20
2025-02-04 | 3213 |  | LPSA-04-BCU-1 | A | DONE | 27 | M-L |  | UWSP ALBERTSON 6230016 | VD , flex | 2025-02-04 | Z | 2025-01-15 | 340 | 60 | 300 | F | 0 | 980 |  |  |  | 20
2025-02-04 | 3214 |  | RA-04-BCU-1 | A | DONE | 9 | S-M |  | UWSP ALBERTSON 6230016 | VD , flex | 2025-02-04 | Z | 2025-01-15 | 180 | 0 | 30 | F | 0 | 250 |  |  |  | 20
2025-02-04 | 3215 |  | RA-04-VRF-1-4-1 | A | DONE | 4 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-02-04 | Z | 2025-01-15 | 80 | 0 | 0 |  | 0 | 130 |  |  |  | 20
2025-02-04 | 3216 |  | LPSA-04-VRF-1-4-1 | A | DONE | 3 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-02-04 | Z | 2025-01-15 | 60 | 0 | 0 |  | 0 | 110 |  |  |  | 20
2025-02-04 | 3221 |  | 81190 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-02-04 | Z | 2025-01-22 | 40 | 0 | 0 |  | 0 | 100 |  | 2nd , 4th floor |  | 13
2025-02-07 | 3223 |  | 81194 | A | DONE | 6 | S-M | perf | UWSP ALBERTSON 6230016 | 2" DW | 2025-02-11 | Z | 2025-01-29 | 150 | 0 | 0 |  | 50 | 130 |  | 2nd Floor RA |  | 13
2025-02-07 | 3224 |  | 81195 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | VD's | 2025-02-11 | Z | 2025-01-29 | 20 | 0 | 0 |  | 0 | 30 |  | 2nd Floor LPSA 02-16 |  | 13
2025-02-05 | 2784 |  | 70136 | A | DONE | 5 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2025-02-06 | Z | 2025-01-31 | 120 | 0 | 0 |  | 0 | 310 |  | 1st Fl SA |  | 6
2025-02-05 | 2785 |  | 70137 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | bird s. | 2025-02-06 | Z | 2025-01-31 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 6
2025-02-04 | 2786 |  | 70138 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-02-06 | Z | 2025-02-03 | 30 | 0 | 0 |  | 0 | 60 |  | 1st Fl SA East |  | 3
2025-02-05 | 2011 | w | 79705 | A | DONE | 4 | S-M |  | UW-VET MED 6210014 |  | 2025-02-06 | Z | 2025-01-27 | 90 | 0 | 0 |  | 0 | 200 |  | Wall Sleeves |  | 10
2025-02-05 | 2441r | bth | SALP10-6 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 | partial , VAV | 2025-02-06 | Z | 2025-01-29 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 8
2025-02-07 | 2201 | sp | L02_G_EAD_008 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 20 | 130 | 0 |  | 0 | 130 |  |  |  | 35
2025-02-07 | 2210 | sp | L02_G_SOA_007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 20 | 100 | 0 |  | 0 | 100 |  |  |  | 35
2025-02-05 | 4147 |  | 83355 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-07 | Z | 2025-02-04 | 30 | 0 | 0 |  | 0 | 40 |  | 2nd F-Section |  | 3
2025-02-07 | 1280 |  | 82497 - 82498 | A | DONE | 6 | S-M |  | WINDSOR 6240012 | paint , flex | 2025-02-10 | Z | 2025-01-27 | 140 | 0 | 0 |  | 150 | 170 |  | Misc Finishes |  | 14
[6 empty] | 1015 | [13 empty] | 34530 |  |  |  | 7440 | 21.55%
WEEK OF 2-10-2025
2025-02-14 | 1731 | w | 81959 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-02-18 | Z | 2025-02-11 | 30 | 0 | 0 |  | 0 | 60 |  | PH Sleeves |  | 7
2025-02-14 | 3650 |  | 80081 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 | paint | 2025-02-18 | Z | 2024-07-25 | 40 | 0 | 150 | F | 20 | 210 |  | DOAS-2 / OA-6 |  | 208
2025-02-12 | 3939 |  | EA-PH-04 |  | delete |  | L |  | 121 E. WILSON 6230024 | CD | 2025-02-12 | Z | 2024-11-15 | [5 empty] | 0 |  | Welded curb cap |  | 89
2025-02-12 | 3942 |  | 81921 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-13 | Z | 2024-11-20 | 70 | 0 | 0 |  | 0 | 80 |  | 13th floor W. unit taps |  | 85
2025-02-12 | 3943 |  | 81922 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-13 | Z | 2024-11-20 | 90 | 0 | 0 |  | 0 | 100 |  | 13th floor W. unit sliders |  | 85
2025-02-12 | 3944 |  | 81923 | A | DONE | 10 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-02-13 | Z | 2024-11-20 | 250 | 0 | 0 |  | 230 | 280 |  | 13th floor W. unit plenums |  | 85
2025-02-12 | 3945 |  | 81924 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-13 | Z | 2024-11-20 | 40 | 0 | 0 |  | 0 | 50 |  | 13th floor W. unit SA duct |  | 85
2025-02-12 | 3946 |  | 81925 - 81926 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-02-13 | Z | 2024-11-20 | 60 | 0 | 0 |  | 40 | 60 |  | 13th floor W. unit TA |  | 85
2025-02-11 | 914 |  | 41836 | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2025-02-12 | Z | 2025-02-04 | 40 | 0 | 0 |  | 0 | 60 |  | VAV 9.7S |  | 8
2025-02-10 | 915 | sp | 41836A | A | DONE | 4 | S |  | BMH AHU9 6240001 |  | 2025-02-12 | Z | 2025-02-04 | 20 | 70 | 0 |  | 0 | 80 |  | VAV 9.7S |  | 8
2025-02-11 | 916 |  | 84960 | A | DONE | 3 | S |  | BMH AHU9 6240001 |  | 2025-02-12 | Z | 2025-02-04 | 60 | 0 | 0 |  | 0 | 140 |  | Mech Rm OA |  | 8
2025-02-14 | 2462 |  | 61396 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2025-02-17 | Z | 2025-02-13 | 50 | 0 | 0 |  | 0 | 150 |  | Misc |  | 4
2025-02-12 | 170 | sp | 70240 | A | DONE | 2 | S |  | COMPASS 10060746 |  | 2025-02-13 | Z | 2025-02-11 | 20 | 20 | 0 |  | 0 | 30 |  | VAV 1-07 |  | 2
2025-02-12 | 169 | bth | 70239 | A | DONE | 6 | S-M |  | DANE CO. AIRPORT 4250007 |  | 2025-02-14 | Z | 2025-01-31 | 40 | 100 | 0 |  | 0 | 140 |  | Misc |  | 14
2025-02-14 | 2897 |  | 79143 | A | DONE | 2 | S |  | EXACT 2240029 |  | 2025-02-18 | Z | 2025-02-12 | 20 | 0 | 0 |  | 0 | 20 |  | Snow hood - blank off |  | 6 | 2025-02-17
2025-02-14 | 1137 |  | 56695 | A | DONE | 2 | S |  | EXACT SCIENCE 8240020 |  | 2025-02-17 | Z | 2025-02-12 | 20 | 0 | 0 |  | 0 | 20 |  | Plates |  | 5 | 2025-02-17
2025-02-11 | 2853 | bth | TL3_SAT 1810-2 | A | DONE | 21 | M |  | EXACT TL-3 6240028 |  | 2025-02-12 | Z | 2025-01-14 | 170 | 230 | 120 |  | 0 | 650 |  |  |  | 29
2025-02-11 | 2854 |  | TL3_SAT 1810-3.1 | A | DONE | 24 | M |  | EXACT TL-3 6240028 |  | 2025-02-12 | Z | 2025-01-14 | 330 | 0 | 270 |  | 0 | 710 |  |  |  | 29
2025-02-14 | 2879 | bth | TL3_SAMP 11 | A | DONE | 64 | L |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 560 | 70 | 960 | F | 0 | 3560 |  |  |  | 29 | 2025-02-17
2025-02-12 | 2880 | bth | TL3_SAMP 12 | A | DONE | 23 | M-L |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 260 | 20 | 280 | F | 0 | 1030 |  |  |  | 29 | 2025-02-17
2025-02-12 | 2881 |  | TL3_SAMP 13 | A | DONE | 40 | M-L |  | EXACT TL-3 6240028 | VD's | 2025-02-14 | Z | 2025-01-16 | 750 | 0 | 240 | F | 0 | 1500 |  |  |  | 29 | 2025-02-17
2025-02-12 | 2882 | bth | TL3_SAMP 14 | A | DONE | 21 | M |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 210 | 190 | 120 | F | 0 | 610 |  |  |  | 29 | 2025-02-17
2025-02-12 | 2883 |  | TL3_EAT 1810.1 | A | DONE | 22 | M |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 150 | 0 | 380 | F | 0 | 750 |  |  |  | 29 | 2025-02-17
2025-02-12 | 2884 | bth | TL3_EAT 1810.2 | A | DONE | 14 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 140 | 20 | 190 | F | 0 | 420 |  |  |  | 29 | 2025-02-17
2025-02-12 | 2885 | bth | TL3_EAT 1810.3 | A | DONE | 16 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 130 | 110 | 150 | F | 0 | 500 |  |  |  | 29 | 2025-02-17
2025-02-14 | 2886 | bth | TL3_EAT 1810.4 | A | DONE | 17 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 150 | 200 | 60 | F | 0 | 480 |  |  |  | 29 | 2025-02-17
2025-02-14 | 2887 | sp | TL3_EAT 1810.5 | A | DONE | 7 | S |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 30 | 130 | 0 |  | 0 | 200 |  |  |  | 29 | 2025-02-17
2025-02-14 | 2888 | bth | TL3_EAT 1810.6 | A | DONE | 12 | S |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 100 | 200 | 0 |  | 0 | 360 |  |  |  | 29 | 2025-02-17
2025-02-14 | 2889 | bth | TL3_EAT 1810-1 | A | DONE | 25 | M |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 420 | 30 | 170 | F | 0 | 850 |  |  |  | 29
2025-02-14 | 2890 | bth | TL3_EAT 1810-2 | A | DONE | 19 | S-M |  | EXACT TL-3 6240028 |  | 2025-02-14 | Z | 2025-01-16 | 190 | 20 | 250 | F | 0 | 600 |  |  |  | 29
2025-02-14 | 2894 |  | 79142 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-02-18 | Z | 2025-02-07 | 20 | 0 | 0 |  | 0 | 40 |  | END CAPS |  | 11
2025-02-11 | 163 |  | 84267 | A | DONE | 8 | S |  | INSULATION TRAINING 3230014 |  | 2025-02-14 | Z | 2025-01-08 | 180 | 0 | 0 |  | 0 | 310 |  | Tanks |  | 37
2025-02-12 | 2660 |  | 021225 | A | DONE | 2 | S | BI | MONROE MS 6240018 |  | 2025-02-12 | Z | 2025-02-12 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 0
2025-02-11 | 2545 |  | 83952 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-02-12 | Z | 2025-02-11 | 20 | 0 | 0 |  | 0 | 50 |  | Misc |  | 1
2025-02-14 | 2895 |  | 83951 | A | DONE | 15 | M |  | PROMEGA BTC 6230022 | VD | 2025-02-14 | Z | 2025-02-10 | 240 | 0 | 120 | F | 0 | 800 |  | Misc |  | 4
2025-02-12 | 2896 |  | 83952 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-02-14 | Z | 2025-02-10 | 50 | 0 | 0 |  | 0 | 110 |  | AHU-N |  | 4
2025-02-12 | 2827 |  | 67738 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-02-13 | Z | 2025-02-03 | 20 | 0 | 0 |  | 0 | 30 |  | 2nd Floor |  | 10
2025-02-12 | 2829 | bth | 84761 | A | DONE | 5 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2025-02-13 | Z | 2025-02-05 | 100 | 20 | 0 |  | 0 | 180 |  | Flashing |  | 8
2025-02-14 | 2830 |  | 84762 - 84763 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-02-20 | Z | 2025-02-10 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 10
2025-02-14 | 2831 |  | 67739 | A | DONE | 2 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-02-17 | Z | 2025-02-12 | 50 | 0 | 0 |  | 40 | 80 |  | TAD 2A |  | 5
2025-02-14 | 3754 | sp | L5A-SAT 540-2 | A | DONE | 5 | S |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 40 | 80 | 0 |  | 0 | 130 |  |  |  | 16
2025-02-14 | 3755 | bth | L5A-SAT 540-3 | A | DONE | 11 | S-M |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 40 | 180 | 50 | F | 0 | 230 |  |  |  | 16
2025-02-14 | 3757 | bth | L5A-SAMP 1 | A | DONE | 33 | M-L |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 540 | 40 | 240 | F | 0 | 1340 |  |  |  | 16
2025-02-14 | 3758 | bth | L5A-SAMP 2 | A | DONE | 11 | S-M |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 120 | 110 | 30 | F | 0 | 300 |  |  |  | 16
2025-02-14 | 3759 | bth | L5A-EAT 540-1 | A | DONE | 5 | S |  | UW-AVRL 6240038 | VD's , oval | 2025-02-19 | Z | 2025-02-03 | 80 | 0 | 30 | F | 0 | 140 |  |  |  | 16
2025-02-14 | 3762 |  | L5A-TA 1 | A | DONE | 5 | S |  | UW-AVRL 6240038 | 1" liner | 2025-02-19 | Z | 2025-02-03 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 16
2025-02-14 | 3763 |  | L5A-TA 2 | A | DONE | 3 | S |  | UW-AVRL 6240038 | bird s. , 1" liner | 2025-02-19 | Z | 2025-02-03 | 10 | 0 | 20 | F | 20 | 40 |  |  |  | 16
2025-02-14 | 3764 |  | L5A-TA 3 | A | DONE | 3 | S |  | UW-AVRL 6240038 | bird s. , 1" liner | 2025-02-19 | Z | 2025-02-03 | 10 | 0 | 20 | F | 20 | 40 |  |  |  | 16
2025-02-14 | 3765 |  | L5A-TA 4 | A | DONE | 2 | S |  | UW-AVRL 6240038 | bird s. , 1" liner | 2025-02-19 | Z | 2025-02-03 | 20 | 0 | 20 | F | 30 | 50 |  |  |  | 16
2025-02-14 | 3767 | bth | L5A-EAMP 2 | A | DONE | 9 | S | pt.pcd | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-04 | 180 | 40 | 0 |  | 0 | 300 |  |  |  | 15
2025-02-11 | 365 |  | L1-SAMP 9 | A | DONE | 12 | M |  | UW-LEVY HALL 6230028 | partial , 1" liner | 2025-02-11 | Z | 2025-02-03 | 170 | 0 | 130 | F | 270 | 610 |  |  |  | 8
2025-02-10 | 366 |  | L1-OA 1 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | MOD | 2025-02-11 | Z | 2025-02-03 | 30 | 0 | 0 |  | 0 | 70 |  |  |  | 8
2025-02-10 | 367 |  | L1-RAMP 10 | A | DONE | 16 | M | neal | UW-LEVY HALL 6230028 | partial , MOD ,1" liner | 2025-02-11 | Z | 2025-02-03 | 250 | 0 | 130 | F | 150 | 580 |  |  |  | 8
2025-02-11 | 368 |  | L1-RAMP 8 | A | DONE | 4 | S | neal | UW-LEVY HALL 6230028 |  | 2025-02-11 | Z | 2025-02-03 | 40 | 0 | 40 | F | 0 | 100 |  |  |  | 8
2025-02-11 | 369 |  | L1-RAMP 9 | A | DONE | 2 | S | neal | UW-LEVY HALL 6230028 | MOD | 2025-02-11 | Z | 2025-02-03 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 8
2025-02-11 | 370 |  | L1-EAMP 10 | A | DONE | 7 | M |  | UW-LEVY HALL 6230028 | partial | 2025-02-11 | Z | 2025-02-03 | 120 | 0 | 50 | F | 130 | 290 |  |  |  | 8
2025-02-11 | 371 |  | L1-EAMP 11 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | partial , MOD | 2025-02-11 | Z | 2025-02-03 | 180 | 0 | 170 | F | 0 | 490 |  |  |  | 8
2025-02-14 | 372 |  | 83926 | A | DONE | 2 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-02-17 | Z | 2025-02-04 | 50 | 0 | 0 |  | 0 | 110 |  | LL / 1st Fl Wall sleeves |  | 13
2025-02-10 | 1058 |  | LL - SAT-3-L-8 | A | DONE | 6 | S-M | neal | UW-LEVY HALL 6230028 | VAV , VD's , 1" liner | 2025-02-11 | Z | 2025-01-07 | 100 | 0 | 30 | F | 30 | 170 |  |  |  | 35
2025-02-10 | 1059 | bth | LL - SAT-3-L-9 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-02-11 | Z | 2025-01-07 | 80 | 20 | 0 |  | 50 | 130 |  |  |  | 35
2025-02-10 | 1060 |  | LL - EAMP 3 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-02-11 | Z | 2025-01-07 | 230 | 20 | 90 | F | 20 | 450 |  |  |  | 35
2025-02-11 | 1061 | bth | LL - SAMP 4 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-11 | Z | 2025-01-07 | 130 | 30 | 30 | F | 0 | 250 |  |  |  | 35
2025-02-10 | 1062 | bth | LL - SAMP 5 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-11 | Z | 2025-01-07 | 50 | 20 | 30 | F | 0 | 180 |  |  |  | 35
2025-02-10 | 1063 |  | LL - TA 1 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-02-11 | Z | 2025-01-07 | 50 | 0 | 50 | F | 80 | 130 |  |  |  | 35
2025-02-11 | 1064 |  | LL - TA 2 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-02-11 | Z | 2025-01-07 | 60 | 0 | 50 | F | 80 | 130 |  |  |  | 35
2025-02-10 | 1065 |  | LL - TA 3 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-02-11 | Z | 2025-01-07 | 50 | 0 | 30 | F | 60 | 110 |  |  |  | 35
2025-02-11 | 1066 |  | LL - TA 4 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-02-11 | Z | 2025-01-07 | 40 | 0 | 30 | F | 60 | 100 |  |  |  | 35
2025-02-11 | 1093 |  | 83918 | A | DONE | 4 | S-M | pt.neal | UW-LEVY HALL 6230028 |  | 2025-02-11 | Z | 2025-01-29 | 80 | 0 | 0 |  | 0 | 130 |  | LL EAMP 4 |  | 13
2025-02-11 | 1094 |  | 83919 | A | DONE | 2 | S-M | neal | UW-LEVY HALL 6230028 |  | 2025-02-11 | Z | 2025-01-29 | 40 | 0 | 0 |  | 0 | 60 |  | LL Utility Rm |  | 13
2025-02-11 | 1095 |  | 83922 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-02-11 | Z | 2025-01-29 | 0 | 0 | 60 | F | 60 | 100 |  | 1st Floor Mock up |  | 13
2025-02-11 | 1096 |  | 83921 | A | DONE | 2 | S | neal | UW-LEVY HALL 6230028 |  | 2025-02-11 | Z | 2025-01-29 | 20 | 0 | 0 |  | 0 | 20 |  | LL EAMP 2 |  | 13
2025-02-14 | 1098 |  | 83923 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-18 | Z | 2025-01-30 | 90 | 0 | 0 |  | 0 | 100 |  | LL Classrooms |  | 19
2025-02-14 | 1099 |  | 83924 | A | DONE | 2 | S | neal | UW-LEVY HALL 6230028 |  | 2025-02-18 | Z | 2025-01-30 | 20 | 0 | 0 |  | 0 | 20 |  | LL EAMP 2 , RAMP 1 |  | 19
2025-02-14 | 3141 | bth | 82141 - 82142 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-17 | Z | 2025-02-03 | 70 | 20 | 0 |  | 30 | 90 |  | SAT 2-2-1 |  | 14
2025-02-14 | 3142 | bth | 82143 - 82144 | A | DONE | 8 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-17 | Z | 2025-02-03 | 40 | 10 | 60 | F | 80 | 130 |  | SAT 2-2-3 |  | 14
2025-02-14 | 3143 | bth | 82146 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-17 | Z | 2025-02-03 | 50 | 20 | 0 |  | 30 | 100 |  | SAT 2-2-2 |  | 14
2025-02-14 | 3153 |  | 84480 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 |  | 2025-02-17 | Z | 2025-02-11 | 120 | 0 | 0 |  | 0 | 230 |  | Drive |  | 6
2025-02-14 | 3327 |  | 83570 - 83571 | A | DONE | 6 | S |  | UWRF 6230010 | paint , flex | 2025-02-17 | Z | 2025-02-03 | 100 | 0 | 0 |  | 40 | 100 |  | Rm 396 GE S & N |  | 14
2025-02-14 | 3328 |  | 83572 - 83574 | A | DONE | 7 | S |  | UWRF 6230010 | paint , flex | 2025-02-17 | Z | 2025-02-03 | 110 | 0 | 0 |  | 70 | 150 |  | Rm 394 GE S & N , L3 GE |  | 14
2025-02-14 | 3329 | bth | 83575 - 83576 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2025-02-17 | Z | 2025-02-03 | 90 | 10 | 0 |  | 0 | 110 |  | Rm 352 #2 , 3 |  | 14
2025-02-14 | 3330 |  | 72939 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2025-02-17 | Z | 2025-02-03 | 20 | 0 | 0 |  | 0 | 20 |  | L2Z2 RA |  | 14
2025-02-14 | 3331 | bth | 83577 - 83580 | A | DONE | 6 | S-M | pcd | UWRF 6230010 |  | 2025-02-17 | Z | 2025-02-04 | 130 | 20 | 0 |  | 0 | 210 |  | Rm 352 #1,4,5,7 |  | 13
2025-02-14 | 3332 |  | 83540 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2025-02-17 | Z | 2025-02-05 | 120 | 0 | 0 |  | 0 | 270 |  | PH Outs |  | 12
2025-02-14 | 3333 |  | 83585 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-02-17 | Z | 2025-02-06 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 11
2025-02-10 | 2374 | bth | LPSA-03-22 | A | DONE | 15 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2025-02-11 | Z | 2025-01-07 | 80 | 280 | 0 |  | 40 | 420 |  |  |  | 35
2025-02-10 | 2375 | bth | LPSA-03-23 | A | DONE | 26 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2025-02-11 | Z | 2025-01-07 | 150 | 490 | 0 |  | 0 | 740 |  |  |  | 35
2025-02-10 | 2378 | sp | LPSA-03-26 | A | DONE | 15 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-02-11 | Z | 2025-01-07 | 40 | 320 | 0 |  | 0 | 420 |  |  |  | 35
2025-02-10 | 2393 |  | LPSA-03-CRU-1 | A | DONE | 11 | S-M |  | UWSP ALBERTSON 6230016 | VD's , flex | 2025-02-11 | Z | 2025-01-07 | 150 | 0 | 110 | F | 0 | 350 |  |  |  | 35
2025-02-10 | 2394 |  | LPSA-03-CRU-2 | A | DONE | 12 | M |  | UWSP ALBERTSON 6230016 | flex | 2025-02-11 | Z | 2025-01-07 | 210 | 0 | 80 | F | 0 | 390 |  |  |  | 35
2025-02-10 | 2396 |  | RA-03-VRF-1-3-1 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-02-11 | Z | 2025-01-08 | 50 | 0 | 0 |  | 0 | 90 |  |  |  | 34
2025-02-10 | 2397 |  | RA-03-09 | A | DONE | 67 | M-L |  | UWSP ALBERTSON 6230016 | VD's , 2" DW | 2025-02-11 | Z | 2025-01-08 | 1660 | 0 | 0 |  | 630 | 1400 |  |  |  | 34
2025-02-10 | 2398 |  | LPSA-03-VRF-1-3-1 | A | DONE | 3 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-02-11 | Z | 2025-01-08 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 34
2025-02-10 | 3225 |  | 81196 - 81197 | A | DONE | 29 | M |  | UWSP ALBERTSON 6230016 | paint | 2025-02-11 | Z | 2025-01-29 | 720 | 0 | 0 |  | 590 | 1030 |  | 1st Floor |  | 13
2025-02-14 | 3226 |  | 81135 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | paint , VD's | 2025-02-18 | Z | 2025-01-30 | 30 | 0 | 0 |  | 10 | 30 |  | LPSA 02 |  | 19
2025-02-14 | 3227 |  | 81185 - 81186 | A | DONE | 4 | S-M |  | UWSP ALBERTSON 6230016 | VD's | 2025-02-18 | Z | 2025-01-30 | 90 | 0 | 0 |  | 0 | 120 |  | 2nd Fl. East |  | 19
2025-02-14 | 3228 |  | 81198 - 81199 | A | DONE | 11 | S-M |  | UWSP ALBERTSON 6230016 | paint , flex | 2025-02-18 | Z | 2025-01-30 | 20 | 0 | 250 | F | 0 | 250 |  | 1st Fl. |  | 19
2025-02-14 | 3229 |  | 81200 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | paint , VD's | 2025-02-18 | Z | 2025-01-30 | 30 | 0 | 0 |  | 20 | 40 |  | 2nd Fl. |  | 19
2025-02-12 | 171 | w | 84308 | A | DONE | 2 | S | ss | VILLAGE OF DEOREST 4250001 |  | 2025-02-13 | Z | 2025-02-12 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 1
2025-02-11 | 2194 |  | L02_G_EAD_001 | A | DONE | 20 | M |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 350 | 0 | 150 | F | 0 | 700 |  |  |  | 35
2025-02-11 | 2195 |  | L02_G_EAD_002 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 50 | 0 | 320 | F | 0 | 450 |  |  |  | 35
2025-02-11 | 2196 | bth | L02_G_EAD_003 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 60 | 160 | 100 | F | 0 | 350 |  |  |  | 35
2025-02-11 | 2197 | bth | L02_G_EAD_004 | A | DONE | 5 | S | pt.neal | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 30 | 90 | 0 |  | 0 | 120 |  |  |  | 35
2025-02-11 | 2198 |  | L02_G_EAD_005 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 60 | 0 | 60 | F | 0 | 160 |  |  |  | 35
2025-02-11 | 2199 | bth | L02_G_EAD_006 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 40 | 30 | 150 | F | 0 | 250 |  |  |  | 35
2025-02-11 | 2200 | bth | L02_G_EAD_007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 30 | 30 | 60 | F | 0 | 140 |  |  |  | 35
2025-02-11 | 2202 | bth | L02_G_EAD_009 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 70 | 50 | 40 | F | 0 | 190 |  |  |  | 35
2025-02-11 | 2203 |  | L02_G_EAD_010 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 50 | 0 | 0 |  | 0 | 70 |  |  |  | 35
2025-02-11 | 2204 | bth | L02_G_SOA_001 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 90 | 40 | 60 | F | 0 | 230 |  |  |  | 35
2025-02-11 | 2205 |  | L02_G_SOA_002 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 180 | 0 | 130 | F | 0 | 370 |  |  |  | 35
2025-02-11 | 2206 | bth | L02_G_SOA_003 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 50 | 20 | 160 | F | 0 | 270 |  |  |  | 35
2025-02-11 | 2207 |  | L02_G_SOA_004 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 80 | 0 | 130 | F | 0 | 280 |  |  |  | 35
2025-02-11 | 2208 | bth | L02_G_SOA_005 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 30 | 40 | 130 | F | 0 | 230 |  |  |  | 35
2025-02-11 | 2209 | bth | L02_G_SOA_006 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-02-12 | Z | 2025-01-08 | 30 | 50 | 180 | F | 0 | 300 |  |  |  | 35
2025-02-14 | 2225 |  | L02_G_RAD_003 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 70 | 0 | 0 |  | 60 | 150 |  |  |  | 41
2025-02-12 | 4148 |  | 83353 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-02-14 | Z | 2025-02-11 | 20 | 0 | 0 |  | 20 | 20 |  | 2nd Floor F-RAD-11 |  | 3
2025-02-12 | 1980 |  | 71490 - 71491 | A | DONE | 3 | S-M |  | WSCC 6240006 | MOD | 2025-02-13 | Z | 2025-02-04 | 60 | 0 | 0 |  | 0 | 90 |  | Misc fittings |  | 9
2025-02-12 | 1982 | w | 71494-95 | A | DONE | 3 | S-M |  | WSCC 6240006 | pink foam | 2025-02-13 | Z | 2025-02-06 | 70 | 0 | 0 |  | 10 | 150 |  | E-Sleeves |  | 7
[6 empty] | 1043 | [13 empty] | 33730 |  |  |  | 6570 | 19.48%
WEEK OF 2-17-2025
2025-02-17 | 1200 |  | 81930 | A | DONE | 6 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-20 | Z | 2024-11-20 | 140 | 0 | 0 |  | 0 | 130 |  | 13th floor E. unit sliders |  | 92
2025-02-18 | 1201 |  | 81931 | A | DONE | 21 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-02-20 | Z | 2024-11-20 | 300 | 0 | 0 |  | 220 | 280 |  | 13th floor E. unit plenums |  | 92
2025-02-17 | 1202 |  | 81932 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-20 | Z | 2024-11-20 | 50 | 0 | 0 |  | 0 | 50 |  | 13th floor E. unit SA |  | 92
2025-02-18 | 1203 |  | 81933 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-20 | Z | 2024-11-20 | 40 | 0 | 80 | F | 100 | 110 |  | 13th floor E. unit TA |  | 92
2025-02-17 | 1730 |  | 81958 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-02-24 | Z | 2025-02-10 | 20 | 0 | 0 |  | 0 | 20 |  | 1st floor |  | 14
2025-02-18 | 1733 |  | 81962 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-24 | Z | 2025-02-17 | 30 | 0 | 0 |  | 0 | 40 |  | 12th EA |  | 7
2025-02-20 | 1734 |  | L13-EA-01 | A | DONE | 17 | S-M |  | 121 E. WILSON 6230024 | VD's | 2025-02-24 | Z | 2025-02-19 | 420 | 0 | 0 |  | 0 | 440 |  |  |  | 5
2025-02-20 | 1735 |  | L13-EA-02 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 | VD's | 2025-02-24 | Z | 2025-02-19 | 300 | 0 | 0 |  | 0 | 310 |  |  |  | 5
2025-02-20 | 1736 |  | L13-EA-03 | A | DONE | 16 | S-M |  | 121 E. WILSON 6230024 | VD's | 2025-02-24 | Z | 2025-02-19 | 390 | 0 | 0 |  | 0 | 410 |  |  |  | 5
2025-02-20 | 1737 |  | L13-EA-04 | A | DONE | 11 | S-M |  | 121 E. WILSON 6230024 | VD's | 2025-02-24 | Z | 2025-02-19 | 270 | 0 | 0 |  | 0 | 280 |  |  |  | 5
2025-02-18 | 3947 | bth | 81927 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-20 | Z | 2024-11-20 | 20 | 90 | 0 |  | 0 | 100 |  | 13th floor OA |  | 92
2025-02-18 | 3948 |  | 81928 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-20 | Z | 2024-11-20 | 40 | 0 | 0 |  | 30 | 40 |  | IDF 1360 TA |  | 92
2025-02-18 | 3949 |  | 81929 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-20 | Z | 2024-11-20 | 100 | 0 | 0 |  | 0 | 100 |  | 13th floor E. unit taps |  | 92
2025-02-17 | 917 | w | 84912 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2025-02-20 | Z | 2025-02-13 | 20 | 0 | 0 |  | 0 | 40 |  | Curb Cap |  | 7
2025-02-17 | 918 | sp | 84961 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2025-02-20 | Z | 2025-02-13 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2025-02-20 | 921 |  | 84964 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2025-02-21 | Z | 2025-02-20 | 20 | 0 | 0 |  | 0 | 20 |  | 9.2-Rheto |  | 1
2025-02-21 | 921 |  | 84964 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2025-02-21 | Z | 2025-02-21 | 20 | 0 | 0 |  | 0 | 20 |  | 12" HETO |  | 0
2025-02-20 | 2463 |  | 81617 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2025-02-21 | Z | 2025-02-20 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-CB-1163 |  | 1
2025-02-21 | 2464 |  | 61397 | A | DONE | 2 | S |  | CDIS 66220028 |  | 2025-02-24 | Z | 2025-02-21 | 20 | 0 | 0 |  | 0 | 20 |  | RINGS |  | 3
2025-02-19 | 173 | w | 95283 | A | DONE | 2 | S | ss | DANE CO. AIRPORT 6210011 |  | 2025-02-25 | Z | 2025-02-18 | 20 | 0 | 0 |  | 0 | 40 |  | Pipe |  | 7
2025-02-19 | 821 | sp | 70734 - 70735 | A | DONE | 28 | M | pcd | DELLSHIRE 6240017 |  | 2025-02-24 | Z | 2025-01-28 | 60 | 630 | 0 |  | 0 | 890 |  | AHU-1 SA |  | 27
2025-02-19 | 822 | sp | 70738 - 70739 | A | DONE | 28 | M | pcd | DELLSHIRE 6240017 |  | 2025-02-24 | Z | 2025-01-28 | 150 | 550 | 0 |  | 0 | 1000 |  | Pool Mech EA |  | 27
2025-02-18 | 823 | bth | 70740 - 70741 | A | DONE | 17 | S-M | pcd | DELLSHIRE 6240017 | VD | 2025-02-24 | Z | 2025-01-28 | 240 | 20 | 150 | F | 0 | 530 |  | EF-1 EA |  | 27
2025-02-18 | 828 |  | 29498 | A | DONE | 10 | S-M | pcd | DELLSHIRE 6240017 |  | 2025-02-24 | Z | 2025-02-12 | 60 | 30 | 140 | F | 0 | 290 |  | Basement RA |  | 12
2025-02-21 | 1200 |  | 79146 | A | DONE | 4 | S |  | EXACT TL-3 6240028 |  | 2025-02-25 | Z | 2025-02-20 | 80 | 0 | 0 |  | 0 | 80 |  | MISC |  | 5
2025-02-17 | 2898 | bth | 79144 | A | DONE | 4 | S |  | EXACT TL-3 6240028 |  | 2025-02-18 | Z | 2025-02-13 | 70 | 20 | 0 |  | 0 | 120 |  | RA |  | 5
2025-02-21 | 2899 |  | 79145 | A | DONE | 5 | S |  | EXACT TL-3 6240028 |  | 2025-02-25 | Z | 2025-02-19 | 110 | 0 | 0 |  | 0 | 140 |  | SA |  | 6
2025-02-17 | 2938 | w | 90076 | A | DONE | 2 | S | BI | LABCORP 6240016 |  | 2025-02-18 | Z | 2025-02-13 | 20 | 0 | 0 |  | 0 | 20 |  | Storm collar |  | 5
2025-02-21 | 2939 |  | 82570 | A | DONE | 2 | S | ss | LABCORP 6240016 |  | 2025-02-24 | Z | 2025-02-21 | 20 | 0 | 0 |  | 0 | 20 |  | 3375 Blood sample |  | 3
2025-02-19 | 174 | sp | 84309 | A | DONE | 2 | S | ss | OAKWOOD 4240059 |  | 2025-02-20 | Z | 2025-02-19 | 20 | 0 | 0 |  | 0 | 20 |  | Boiler EA |  | 1
2025-02-17 | 2546 |  | 83953 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2025-02-19 | Z | 2025-02-12 | 90 | 0 | 0 |  | 0 | 230 |  | RA |  | 7
2025-02-18 | 4789 |  | 85301 | A | DONE | 5 | S-M |  | ROCK CO. JAIL 6220018 | bird s. , security bar | 2025-02-20 | Z | 2025-02-14 | 110 | 0 | 0 |  | 0 | 210 |  | Remodel |  | 6
2025-02-17 | 1409 |  | 68457 | A | DONE | 2 | S |  | SPH BIRTH CENTER 6240022 |  | 2025-02-24 | Z | 2025-02-04 | 40 | 0 | 0 |  | 0 | 50 |  | Bathroom SA/EA |  | 20
2025-02-18 | 1410 |  | 68458 - 68459 | A | DONE | 5 | S |  | SPH BIRTH CENTER 6240022 | 1/2" liner | 2025-02-24 | Z | 2025-02-10 | 110 | 0 | 0 |  | 100 | 150 |  | R-7-19D , Bath Rm EA |  | 14
2025-02-18 | 2400 |  | 79940 - 79941 | A | DONE | 6 | S-M |  | ST.BERNARD 6230023 | paint , 1" liner | 2025-02-24 | Z | 2025-02-11 | 150 | 0 | 0 |  | 130 | 160 |  | FCU 15 , FCU 16 |  | 13
2025-02-18 | 2832 |  | 67740 - 67741 | A | DONE | 4 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-02-20 | Z | 2025-02-12 | 90 | 0 | 0 |  | 70 | 140 |  | TAD 2A |  | 8
2025-02-17 | 2833 |  | 67742 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-02-20 | Z | 2025-02-13 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd Floor |  | 7
2025-02-18 | 2834 |  | 67743 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | paint | 2025-02-20 | Z | 2025-02-14 | 70 | 0 | 0 |  | 20 | 120 |  | BG-1 |  | 6
2025-02-17 | 3752 | bth | L5A-SAT 539 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 16
2025-02-17 | 3753 | sp | L5A-SAT 540-1 | A | DONE | 11 | S-M |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 50 | 210 | 0 |  | 0 | 270 |  |  |  | 16
2025-02-17 | 3756 | sp | L5A-SAT 541 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 16
2025-02-17 | 3760 | sp | L5A-EAT 541 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 16
2025-02-17 | 3761 | bth | L5A-EAMP 1 | A | DONE | 14 | S-M |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-03 | 180 | 10 | 160 | F | 0 | 450 |  |  |  | 16
2025-02-17 | 3766 | sp | L5A-FAT 540 | A | DONE | 2 | S | pcd | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-04 | 20 | 30 | 0 |  | 0 | 70 |  |  |  | 15
2025-02-18 | 3768 | sp | 69127 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-02-19 | Z | 2025-02-18 | 0 | 20 | 0 |  | 0 | 20 |  | Invenra |  | 1
2025-02-20 | 3769 |  | 69128 | A | DONE | 6 | S-M |  | UW-AVRL 6240038 |  | 2025-02-24 | Z | 2025-02-18 | 140 | 0 | 0 |  | 0 | 350 |  | Sleeves |  | 6
2025-02-18 | 634 |  | 83262 | A | DONE | 2 | S | neal | UW-BIO CHEM 6240036 |  | 2025-02-20 | Z | 2025-02-18 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2025-02-21 | 373 |  | 83927 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-02-07 | 40 | 0 | 0 |  | 0 | 60 |  | LL-RAMP-2 |  | 18
2025-02-21 | 374 |  | 83928 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-02-13 | 20 | 0 | 0 |  | 0 | 30 |  | LL utility rm. |  | 12
2025-02-20 | 1072 | bth | L1-SAT-3-1-1 | A | DONE | 16 | M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-02-25 | Z | 2025-01-20 | 80 | 260 | 40 | F | 60 | 460 |  |  |  | 36 | 2025-02-11
2025-02-21 | 1073 |  | L1-SAT-3-1-2.1 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-02-25 | Z | 2025-01-20 | 160 | 0 | 210 | F | 80 | 450 |  |  |  | 36 | 2025-02-11
2025-02-18 | 1074 | sp | L1-SAT-3-1-2.2 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-01-20 | 20 | 100 | 0 |  | 0 | 130 |  |  |  | 36 | 2025-02-11
2025-02-21 | 1075 | bth | L1-SAT-3-1-2.3 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VD's | 2025-02-25 | Z | 2025-01-20 | 50 | 40 | 30 | F | 0 | 120 |  |  |  | 36 | 2025-02-11
2025-02-20 | 1083 | bth | L1-SAT-3-1-3 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-02-25 | Z | 2025-01-20 | 30 | 0 | 30 | F | 50 | 90 |  |  |  | 36
2025-02-21 | 1084 |  | L1-SAT-3-1-4 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-02-25 | Z | 2025-01-20 | 80 | 0 | 0 |  | 30 | 110 |  |  |  | 36
2025-02-20 | 3113 |  | 82301 - 82304 | A | DONE | 13 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-24 | Z | 2025-01-14 | 270 | 0 | 50 | F | 360 | 380 |  | 223A/B TA , 227 B/C TA |  | 41
2025-02-20 | 3114 |  | 82305 - 82308 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-24 | Z | 2025-01-14 | 250 | 0 | 0 |  | 230 | 330 |  | 227D,E,F,G TA |  | 41
2025-02-19 | 3115 | bth | 82309 - 82311 | A | DONE | 13 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 90 | 70 | 160 | F | 0 | 380 |  | SAT-3-2-1,2 |  | 41
2025-02-19 | 3116 | bth | 82312 - 82313 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 70 | 20 | 80 | F | 0 | 170 |  | SAT-3-2-4 |  | 41
2025-02-19 | 3117 |  | 82314 - 82315 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 50 | 0 | 50 | F | 0 | 120 |  | SAT-3-2-5 |  | 41
2025-02-19 | 3118 | bth | 82316 - 82318 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 110 | 30 | 40 | F | 0 | 200 |  | SAT-3-2-6,7 |  | 41
2025-02-19 | 3119 |  | 82319 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-24 | Z | 2025-01-14 | 50 | 0 | 0 |  | 40 | 60 |  | SAT-3-2-9 |  | 41
2025-02-19 | 3120 | bth | 82320 - 82321 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 60 | 50 | 60 | F | 0 | 180 |  | SAT-3-2-9 |  | 41
2025-02-19 | 3121 | bth | 82322 - 82324 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 90 | 50 | 60 | F | 0 | 220 |  | SAT-3-2-3 |  | 41
2025-02-19 | 3122 | bth | 82325 - 82326 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 100 | 30 | 20 | F | 0 | 180 |  | SAT-3-2-8 |  | 41
2025-02-19 | 3123 | bth | 82327 - 82330 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 120 | 90 | 20 | F | 0 | 230 |  | SAT-1-2-12 |  | 41
2025-02-19 | 3124 |  | 82331 - 82332 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 110 | 0 | 80 | F | 0 | 250 |  | SAT-1-2-14 |  | 41
2025-02-20 | 3125 | sp | 82333 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 0 | 30 | 0 |  | 0 | 30 |  | SAT-1-2-14 |  | 41
2025-02-20 | 3126 | bth | 82334 - 82335 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 60 | 30 | 0 |  | 0 | 110 |  | SAT-1-2-15 |  | 41
2025-02-19 | 3127 |  | 82336 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 20 | 0 | 0 |  | 20 | 40 |  | SAT-1-2-13 |  | 41
2025-02-19 | 3128 |  | 82337 - 82339 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 50 | 50 | 20 | F | 0 | 120 |  | SAT-1-2-8,9,13 |  | 41
2025-02-19 | 3129 |  | 82340 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-24 | Z | 2025-01-14 | 40 | 0 | 0 |  | 40 | 60 |  | SAT-1-2-16 |  | 41
2025-02-20 | 3130 | bth | 82341 - 82343 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 80 | 120 | 30 | F | 0 | 230 |  | SAT-1-2-6,7,10 |  | 41
2025-02-19 | 3131 | bth | 82344 - 82345 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 50 | 20 | 110 | F | 0 | 220 |  | SAT-1-2-5 |  | 41
2025-02-19 | 3132 |  | 82346 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 40 | 0 | 40 | F | 0 | 90 |  | SAT-1-2-11 |  | 41
2025-02-20 | 3133 | sp | 82347 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 20 | 50 | 0 |  | 0 | 50 |  | SAT-1-2-11 |  | 41
2025-02-20 | 3134 | bth | 82348 - 82349 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 70 | 20 | 30 | F | 0 | 120 |  | SAT-1-2-2 |  | 41
2025-02-19 | 3135 | sp | 82350 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 20 | 40 | 0 |  | 0 | 50 |  | SAT-1-2-4 |  | 41
2025-02-20 | 3136 | bth | 82351 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 40 | 40 | 0 |  | 0 | 80 |  | SAT-1-2-1 |  | 41
2025-02-19 | 3137 |  | 82352 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-24 | Z | 2025-01-14 | 50 | 0 | 0 |  | 40 | 80 |  | SAT-1-2-3 |  | 41
2025-02-19 | 3138 |  | 82353 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2025-02-24 | Z | 2025-01-14 | 20 | 20 | 20 | F | 0 | 60 |  | SAT-1-2-3 |  | 41
2025-02-20 | 3139 |  | 82355 - 82356 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-24 | Z | 2025-01-14 | 120 | 0 | 20 | F | 130 | 190 |  | 245C/D TA |  | 41
2025-02-20 | 3140 |  | 82357 - 82359 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-02-24 | Z | 2025-01-14 | 190 | 0 | 70 | F | 210 | 300 |  | 243,C,D TA |  | 41
2025-02-19 | 3151 | sp | 84457 | A | DONE | n/a | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-03 | Z | 2025-02-10 | 0 | 0 | 0 |  | 0 | 0 |  | 2nd / 3rd bought out 90's |  | 21
2025-02-18 | 3334 |  | 83581 - 83582 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-10 | 100 | 20 | 0 |  | 0 | 120 |  | Rm 318 #1 , 2 |  | 15
2025-02-20 | 3335 |  | 83584 , 83587 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-10 | 80 | 0 | 0 |  | 0 | 110 |  | Rm 318 #3 , 4 |  | 15
2025-02-20 | 3336 |  | 83589 - 83591 | A | DONE | 6 | S-M | pcd | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-10 | 130 | 20 | 0 |  | 0 | 160 |  | Rm 318 #5 , 6 ,7 |  | 15
2025-02-20 | 3337 |  | 83592 - 83593 | A | DONE | 5 | S-M | pcd | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-10 | 100 | 20 | 0 |  | 0 | 120 |  | Rm 318 #8 , Rm 324 FE |  | 15
2025-02-20 | 3338 | bth | 83541 | A | DONE | 3 | S |  | UWRF 6230010 | s.mates | 2025-02-25 | Z | 2025-02-11 | 70 | 0 | 0 |  | 0 | 130 |  | EF Roof outs |  | 14
2025-02-20 | 3339 | bth | 83594 - 83596 | A | DONE | 2 | S-M |  | UWRF 6230010 | paint , flex | 2025-02-25 | Z | 2025-02-11 | 50 | 0 | 0 |  | 40 | 90 |  | L2 GE , L3 GE |  | 14
2025-02-17 | 3340 |  | 83597 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-11 | 20 | 0 | 0 |  | 0 | 20 |  | L3 - Z2B |  | 14
2025-02-17 | 3341 |  | 83598 | A | DONE | 4 | S | neal | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-11 | 90 | 0 | 0 |  | 0 | 100 |  | Angles |  | 14
2025-02-18 | 3342 |  | 83599 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-02-25 | Z | 2025-02-11 | 20 | 0 | 0 |  | 20 | 20 |  | Rm 362 GE |  | 14
2025-02-19 | 3343 |  | 70403 - 70404 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-02-25 | Z | 2025-02-12 | 30 | 0 | 0 |  | 20 | 40 |  | L3 TA |  | 13
2025-02-20 | 3344 |  | 70405 | A | DONE | 2 | S |  | UWRF 6230010 | flex , 1" liner | 2025-02-25 | Z | 2025-02-12 | 20 | 0 | 0 |  | 20 | 30 |  | L3 TA |  | 13
2025-02-20 | 3345 |  | 70406 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-12 | 20 | 0 | 0 |  | 0 | 30 |  | L3 RA |  | 13
2025-02-20 | 3346 | bth | 70407 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-12 | 20 | 20 | 0 |  | 0 | 30 |  | L3 SA |  | 13
2025-02-18 | 3347 |  | 70408 - 70409 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-02-25 | Z | 2025-02-12 | 40 | 0 | 0 |  | 30 | 50 |  | L3 TA |  | 13
2025-02-20 | 3348 | sp | 70410 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-02-25 | Z | 2025-02-13 | 20 | 20 | 0 |  | 0 | 20 |  | 3rd Floor |  | 12
2025-02-17 | 3235 |  | 81146 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-02-18 | Z | 2025-02-17 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd Floor |  | 1
2025-02-17 | 2787 |  | 70139 | A | DONE | 5 | S-M | pt.neal | UWSP CHAMPION HALL 6240008 |  | 2025-02-20 | Z | 2025-02-13 | 120 | 0 | 0 |  | 0 | 220 |  | VAV-22-110 |  | 7
2025-02-18 | 2788 | w | 70141 | A | DONE | 4 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2025-02-20 | Z | 2025-02-13 | 80 | 0 | 0 |  | 0 | 200 |  | FSD Extension sleeves |  | 7
2025-02-18 | 1543 | sp | 73079 - 73082 | A | DONE | 14 | S-M |  | UW-VET MED 6210014 |  | 2025-02-21 | Z | 2025-01-30 | 60 | 280 | 0 |  | 0 | 340 |  | 10 A/B North |  | 22
2025-02-18 | 1544 |  | 73083 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-02-21 | Z | 2025-01-30 | 40 | 0 | 0 |  | 0 | 50 |  | 10 A/B North |  | 22
2025-02-18 | 1996 |  | SALP-0(7) | A | DONE | 10 | S-M |  | UW-VET MED 6210014 |  | 2025-02-21 | Z | 2025-01-30 | 180 | 0 | 50 | F | 0 | 330 |  |  |  | 22 | 2023-08-03 | 2024-07-01 | 2024-09-24 |  | 2024-09-25
2025-02-17 | 1997 |  | SALP-1(7) | A | DONE | 12 | S-M |  | UW-VET MED 6210014 | flex | 2025-02-21 | Z | 2025-01-30 | 60 | 0 | 240 | F | 0 | 380 |  |  |  | 22 | 2023-08-03 | 2024-07-01 | 2024-09-24 |  | 2024-09-25
2025-02-17 | 2012 |  | 79706 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2025-02-20 | Z | 2025-02-14 | 20 | 0 | 0 |  | 0 | 20 |  | CB-281 |  | 6
2025-02-17 | 2211 | sp | L02_G_SALP_001 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 41
2025-02-17 | 2212 | bth | L02_G_SALP_002 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 50 | 50 | 100 | F | 0 | 220 |  |  |  | 41
2025-02-17 | 2213 | bth | L02_G_SALP_003 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 130 | 80 | 30 | F | 0 | 260 |  |  |  | 41
2025-02-17 | 2214 | bth | L02_G_SALP_004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 30 | 30 | 20 | F | 0 | 90 |  |  |  | 41
2025-02-17 | 2215 | bth | L02_G_SALP_005 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 80 | 80 | 60 | F | 0 | 230 |  |  |  | 41
2025-02-17 | 2216 | bth | L02_G_SALP_006 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 30 | 50 | 0 |  | 0 | 90 |  |  |  | 41
2025-02-17 | 2217 | bth | L02_G_SALP_007 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 90 | 80 | 60 | F | 0 | 250 |  |  |  | 41
2025-02-17 | 2218 | bth | L02_G_SALP_008 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 80 | 20 | 0 |  | 0 | 120 |  |  |  | 41
2025-02-17 | 2219 | sp | L02_G_SALP_009 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-19 | Z | 2025-01-09 | 20 | 160 | 0 |  | 0 | 170 |  |  |  | 41
2025-02-17 | 2220 | sp | L02_G_SALP_010 | A | DONE | 10 | S |  | WAUNAKEE MS 6230013 |  | 2025-02-19 | Z | 2025-01-09 | 30 | 220 | 0 |  | 0 | 240 |  |  |  | 41
2025-02-17 | 2221 | sp | L02_G_SALP_011 | A | DONE | 7 | S | pt.neal | WAUNAKEE MS 6230013 |  | 2025-02-19 | Z | 2025-01-09 | 30 | 130 | 0 |  | 0 | 160 |  |  |  | 41
2025-02-17 | 2222 |  | L02_G_SALP_012 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-02-19 | Z | 2025-01-09 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 41
2025-02-17 | 2223 | bth | L02_G_RAD_001 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 30 | 20 | 0 |  | 20 | 60 |  |  |  | 41
2025-02-17 | 2224 |  | L02_G_RAD_002 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 70 | 0 | 40 | F | 90 | 160 |  |  |  | 41
2025-02-17 | 2226 |  | L02_G_RAD_004 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 41
2025-02-17 | 2227 |  | L02_G_RAD_005 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 70 | 0 | 0 |  | 60 | 130 |  |  |  | 41
2025-02-17 | 2228 | bth | L02_G_RAD_006 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 40 | 20 | 0 |  | 20 | 80 |  |  |  | 41
2025-02-17 | 2229 | bth | L02_G_RAD_007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 30 | 80 | 0 |  | 20 | 100 |  |  |  | 41
2025-02-17 | 2230 |  | L02_G_RAD_008 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 60 | 0 | 0 |  | 50 | 130 |  |  |  | 41
2025-02-17 | 2231 | bth | L02_G_RAD_009 | A | DONE | 10 | S-M | pt.neal | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 120 | 120 | 0 |  | 80 | 280 |  |  |  | 41
2025-02-17 | 2232 |  | L02_G_RAD_010 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-02-19 | Z | 2025-01-09 | 100 | 0 | 0 |  | 70 | 160 |  |  |  | 41
2025-02-17 | 2233 |  | L02_G_TAD_001 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-02-19 | Z | 2025-01-09 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 41
2025-02-17 | 4173 |  | 79809 | A | DONE | 3 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-02-21 | Z | 2025-02-12 | 60 | 0 | 0 |  | 0 | 140 |  | Fire angle |  | 9
2025-02-17 | 4174 |  | 79867 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-02-21 | Z | 2025-02-12 | 80 | 0 | 0 |  | 0 | 120 |  | Curb Cap |  | 9
2025-02-18 | 1981 |  | 71492 | A | DONE | 3 | S-M | pt.ss | WSCC 6240006 | thread nipple | 2025-02-20 | Z | 2025-02-05 | 10 | 60 | 0 |  | 0 | 70 |  | GFUH-1 |  | 15
2025-02-18 | 1983 | sp | 71496 | A | DONE | 6 | S | alum | WSCC 6240006 |  | 2025-02-20 | Z | 2025-02-07 | 20 | 130 | 0 |  | 0 | 80 |  | DRYER VENT |  | 13
[6 empty] | 758 | [13 empty] | 20100 |  |  |  | 4650 | 23.13%
WEEK OF 2-24-2025
2025-02-24 | 1223 |  | L14-RA-01 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 35
2025-02-24 | 1224 |  | L14-RA-02 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 35
2025-02-24 | 1225 |  | L14-RA-03 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 20 | 0 | 30 | F | 30 | 30 |  |  |  | 35
2025-02-24 | 1226 |  | L14-RA-04 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 35
2025-02-24 | 1227 |  | L14-RA-05 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 50 | 0 | 0 |  | 50 | 60 |  |  |  | 35
2025-02-24 | 1228 |  | L14-RA-06 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 35
2025-02-24 | 1229 |  | L14-RA-07 | A | DONE | 3 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 20 | 0 | 40 | F | 50 | 100 |  |  |  | 35
2025-02-24 | 1230 |  | L14-RA-08 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 35
2025-02-24 | 1231 |  | L14-RA-09 | A | DONE | 3 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 30 | 0 | 30 | F | 50 | 60 |  |  |  | 35
2025-02-24 | 1232 |  | L14-RA-10 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 35
2025-02-24 | 1233 |  | L14-RA-11 | A | DONE | 3 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-02-26 | Z | 2025-01-22 | 60 | 0 | 0 |  | 50 | 70 |  |  |  | 35
2025-02-25 | 1234 |  | L14-OA-01 | A | DONE | 17 | M |  | 121 E. WILSON 6230024 | VD's | 2025-02-26 | Z | 2025-01-22 | 350 | 0 | 60 | F | 0 | 440 |  |  |  | 35
2025-02-25 | 1235 |  | L14-OA-02 | A | DONE | 25 | M |  | 121 E. WILSON 6230024 |  | 2025-02-26 | Z | 2025-01-22 | 590 | 0 | 30 | F | 0 | 830 |  |  |  | 35
2025-02-25 | 1236 |  | L14-OA-03 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 |  | 2025-02-26 | Z | 2025-01-22 | 90 | 0 | 0 |  | 0 | 220 |  |  |  | 35
2025-02-25 | 1237 |  | L14-EA-01 | A | DONE | 6 | S |  | 121 E. WILSON 6230024 |  | 2025-02-26 | Z | 2025-01-22 | 130 | 0 | 0 |  | 0 | 150 |  |  |  | 35
2025-02-25 | 1238 |  | L14-EA-02 | A | DONE | 7 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-26 | Z | 2025-01-22 | 170 | 0 | 0 |  | 0 | 220 |  |  |  | 35
2025-02-25 | 1239 |  | L14-EA-03 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-02-26 | Z | 2025-01-22 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 35
2025-02-25 | 1732 |  | 81960 - 81961 | A | DONE | 6 | S-M |  | 121 E. WILSON 6230024 |  | 2025-02-27 | Z | 2025-02-14 | 140 | 0 | 0 |  | 0 | 440 |  | DOAS 1 , 2 |  | 13
2025-02-25 | 176 | bth | 70241 | A | DONE | 7 | S-M |  | ALDEVRON 4250005 |  | 2025-02-28 | Z | 2025-02-24 | 40 | 130 | 0 |  | 0 | 160 |  | Misc |  | 4
2025-02-25 | 922 |  | 84965 | N/A | DONE | 3 | S |  | BMH AHU-9 6240001 |  | 2025-03-06 | Z | 2025-02-24 | 0 | 0 | 80 | F | 0 | 110 |  | FLATSTOCK |  | 10
2025-02-25 | 2465 |  | 81618 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-02-25 | Z | 2025-02-25 | 30 | 0 | 0 |  | 0 | 80 |  | 1ST FLOOR |  | 0
2025-02-28 | 2467 |  | 61398 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-03-03 | Z | 2025-02-28 | 20 | 0 | 0 |  | 0 | 20 |  | AHU-3 |  | 3
2025-02-24 | 825 |  | 70751 - 70751.1 | A | DONE | 5 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-03 | Z | 2025-02-12 | 110 | 0 | 0 |  | 0 | 220 |  | 1st/2nd Fl hangers |  | 19
2025-02-25 | 829 | w | 70752 | A | DONE | 3 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-03 | Z | 2025-02-12 | 60 | 0 | 0 |  | 0 | 160 |  | VTAC Con. Sleeves 2/3rd |  | 19
2025-02-26 | 1202 | bth | 79021-22 | A | DONE | 14 | S-M |  | ES BIO-PHARMA 2250001 |  | 2025-03-04 | Z | 2025-02-25 | 100 | 240 | 0 |  | 0 | 410 |  | Exh & Spiral |  | 7
2025-02-26 | 1205 |  | 79023 - 79024 | A | DONE | 10 | S-M |  | ES BIO-PHARMA 2250001 |  | 2025-03-04 | Z | 2025-02-26 | 160 | 0 | 70 |  | 0 | 270 |  | RA / EA duct |  | 6
2025-02-26 | 1201 |  | 79149 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-03-04 | Z | 2025-02-24 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 8
2025-02-25 | 2892 |  | TL3_FCU 1871 | A | DONE | 13 | S-M |  | EXACT TL-3 6240028 |  | 2025-03-03 | Z | 2025-01-21 | 210 | 0 | 100 | F | 0 | 410 |  | Misc |  | 41
2025-02-25 | 2661 |  | 78786 | A | DONE | 2 | S-M |  | MONROE HS 6240018 |  | 2025-02-27 | Z | 2025-02-21 | 20 | 0 | 0 |  | 0 | 50 |  | Misc |  | 6
2025-02-25 | 172 |  | 85351 | A | DONE | 3 | S | ss | MOUNT VIEW HOSP. 2009365 |  | 2025-03-03 | Z | 2025-02-18 | 60 | 0 | 0 |  | 0 | 110 |  | Covers |  | 13
2025-02-28 | 3966 |  | 83143 | A | DONE | 5 | S-M |  | PECATONICA ES 6240005 |  | 2025-03-06 | Z | 2025-01-20 | 120 | 0 | 0 |  | 0 | 260 |  | Flashing | SEMI | 45 | 2025-06-09
2025-02-26 | 2547 |  | 59850 | A | DONE | 8 | M |  | PROMEGA BTC 6230022 |  | 2025-03-03 | Z | 2025-02-20 | 180 | 0 | 0 |  | 0 | 560 |  | AHU-N-RET |  | 11
2025-02-28 | 177 | w | 80764 - 80768 | A | DONE | 5 | S-M |  | SSM O'KEEFE 8240002 |  | 2025-03-04 | Z | 2025-02-27 | 110 | 0 | 0 |  | 0 | 310 |  | Drain pan |  | 5
2025-02-28 | 178 | w | 80769 , 80771 | A | DONE | 6 | S-M |  | SSM O'KEEFE 8240002 |  | 2025-03-04 | Z | 2025-02-27 | 150 | 0 | 0 |  | 0 | 320 |  | Drain pan |  | 5
2025-02-26 | 2401 |  | 79943 | A | DONE | 4 | S |  | ST.BERNARD 6230023 | 1" liner | 2025-02-27 | Z | 2025-02-14 | 100 | 0 | 0 |  | 90 | 140 |  | SA |  | 13
2025-02-25 | 2835 |  | 67744 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-02-27 | Z | 2025-02-18 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd Floor |  | 9
2025-02-25 | 2836 | sp | 84764 | A | DONE | 6 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-02-27 | Z | 2025-02-19 | 20 | 40 | 0 |  | 0 | 60 |  | Rm 182 |  | 8
2025-02-25 | 2837 |  | 67745 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | paint | 2025-02-27 | Z | 2025-02-19 | 20 | 0 | 0 |  | 20 | 20 |  | 2nd Floor |  | 8
2025-02-25 | 2838 |  | 67746 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | paint | 2025-02-27 | Z | 2025-02-20 | 20 | 0 | 0 |  | 20 | 20 |  | 2ND FLOOR |  | 7
2025-02-27 | 3798 |  | 69129 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-26 | 20 | 0 | 0 |  | 0 | 20 |  | 540-2 |  | 7
2025-02-24 | 350 |  | L1-SAT-3-1-6 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-02-25 | Z | 2025-01-31 | 90 | 0 | 170 | F | 220 | 370 |  |  |  | 25 | 2025-03-11
2025-02-27 | 351 |  | L1-FCU 2 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-31 | 60 | 0 | 0 |  | 40 | 90 |  |  |  | 32 | 2025-03-11
2025-02-28 | 353 | bth | L1-EAMP 9 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-31 | 140 | 20 | 0 |  | 100 | 170 |  |  |  | 32 | 2025-03-11
2025-02-24 | 354 |  | L1-EAMP 2 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-01-31 | 50 | 0 | 30 | F | 0 | 110 |  |  |  | 25
2025-02-24 | 355 |  | L1-EAMP 3 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-01-31 | 40 | 0 | 90 | F | 0 | 160 |  |  |  | 25
2025-02-24 | 356 |  | L1-EAMP 4 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-01-31 | 30 | 0 | 160 | F | 0 | 220 |  |  |  | 25
2025-02-24 | 357 |  | L1-EAMP 5 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-01-31 | 30 | 0 | 60 | F | 0 | 110 |  |  |  | 25
2025-02-24 | 358 | bth | L1-EAMP 6 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-02-25 | Z | 2025-01-31 | 50 | 0 | 0 |  | 20 | 80 |  |  |  | 25
2025-02-24 | 359 |  | L1-EAMP 7 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-02-25 | Z | 2025-01-31 | 30 | 0 | 60 | F | 0 | 110 |  |  |  | 25
2025-02-27 | 360 |  | L1-TA 1 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-31 | 50 | 0 | 50 | F | 80 | 130 |  |  |  | 32 | 2025-03-18
2025-02-27 | 361 |  | L1-TA 2 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-31 | 60 | 0 | 50 | F | 90 | 140 |  |  |  | 32 | 2025-03-18
2025-02-27 | 362 |  | L1-TA 3 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-31 | 50 | 0 | 30 | F | 60 | 100 |  |  |  | 32 | 2025-03-18
2025-02-28 | 363 |  | L1-TA 4 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-31 | 40 | 0 | 30 | F | 60 | 90 |  |  |  | 32 | 2025-03-18
2025-02-28 | 364 |  | L1-EAMP 1 | A | DONE | 14 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-03-04 | Z | 2025-01-31 | 260 | 0 | 70 | F | 20 | 450 |  |  |  | 32 | 2025-03-18
2025-02-26 | 375 |  | 83929 | A | DONE | 4 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-03-04 | Z | 2025-02-13 | 80 | 0 | 0 |  | 0 | 220 |  | Mech. Rm test caps |  | 19
2025-02-26 | 376 |  | 83930 - 83931 | A | DONE | 2 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-03-04 | Z | 2025-02-18 | 30 | 0 | 0 |  | 0 | 40 |  | LL utility EA , LL End caps |  | 14
2025-02-26 | 377 |  | 83933 | A | DONE | n/a | S-M |  | UW-LEVY HALL 6230028 | DM Frames | 2025-03-04 | Z | 2025-02-24 | 0 | 0 | 0 |  | 0 | 0 |  | DM Frames |  | 8
2025-02-27 | 378 |  | 83934 | A | DONE | 3 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-03-04 | Z | 2025-02-24 | 60 | 0 | 0 |  | 0 | 140 |  | 6TH FL SLEEVE |  | 8
2025-02-27 | 1052 |  | LL - SAT-3-L-3.1 | A | DONE | 17 | M |  | UW-LEVY HALL 6230028 | VAV , VD's , 1" liner | 2025-03-04 | Z | 2025-01-02 | 160 | 0 | 250 | F | 100 | 620 |  |  |  | 61 | 2025-02-03
2025-02-24 | 1071 | bth | L1-SAT-3-1-8 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | VAV , VD's , 1" liner | 2025-03-04 | Z | 2025-01-20 | 120 | 230 | 0 |  | 40 | 360 |  |  |  | 43 | 2025-02-11
2025-02-24 | 1076 |  | L1-RAMP 1 | A | DONE | 34 | M-L |  | UW-LEVY HALL 6230028 | VD , DW , 1" liner | 2025-02-25 | Z | 2025-01-20 | 340 | 0 | 510 | F | 150 | 1280 |  |  |  | 36
2025-02-24 | 1077 | bth | L1-RAMP 2 | A | DONE | 21 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-02-25 | Z | 2025-01-20 | 210 | 0 | 300 | F | 110 | 760 |  |  |  | 36
2025-02-24 | 1078 | bth | L1-RAMP 3 | A | DONE | 14 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-02-25 | Z | 2025-01-20 | 240 | 0 | 90 | F | 30 | 540 |  |  |  | 36
2025-02-24 | 1079 | bth | L1-RAMP 4 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-02-25 | Z | 2025-01-20 | 200 | 20 | 150 | F | 60 | 480 |  |  |  | 36
2025-02-27 | 1080 | bth | L1-SAMP 3 | A | DONE | 23 | M-L |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-20 | 490 | 20 | 60 | F | 220 | 1130 |  |  |  | 43 | 2025-02-25
2025-02-24 | 1081 | bth | L1-SAMP 4 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-01-20 | 160 | 20 | 30 | F | 0 | 280 |  |  |  | 36
2025-02-24 | 1082 | bth | L1-SAMP 5 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-02-25 | Z | 2025-01-20 | 120 | 30 | 80 | F | 0 | 400 |  |  |  | 36
2025-02-27 | 1085 |  | L1-RAMP 7 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-21 | 160 | 0 | 100 | F | 210 | 400 |  |  |  | 42
2025-02-27 | 1086 | bth | L1-SAMP 6 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-04 | Z | 2025-01-21 | 230 | 20 | 80 | F | 230 | 530 |  |  |  | 42
2025-02-27 | 1087 | bth | L1-SAMP 7 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-04 | Z | 2025-01-21 | 100 | 30 | 90 | F | 0 | 300 |  |  |  | 42
2025-02-27 | 1088 |  | L1-SAT-3-1-7.1 | A | DONE | 16 | M | pt.neal | UW-LEVY HALL 6230028 | VAV , VD's , 1" liner | 2025-03-04 | Z | 2025-01-21 | 290 | 0 | 100 | F | 210 | 550 |  |  |  | 42
2025-02-28 | 1089 | bth | L1-SAT-3-1-7.2 | A | DONE | 13 | S-M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-03-04 | Z | 2025-01-21 | 170 | 110 | 30 | F | 100 | 350 |  |  |  | 42
2025-02-27 | 1090 |  | L1-SAT-3-1-5 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , VD , 1" liner | 2025-03-04 | Z | 2025-01-21 | 50 | 20 | 0 |  | 50 | 70 |  |  |  | 42
2025-02-27 | 4591 | bth | LL - SAT-3-L-10 | A | DONE | 8 | S | pt.neal | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-03-04 | Z | 2025-01-02 | 90 | 90 | 0 |  | 40 | 230 |  |  |  | 61 | 2025-01-27
2025-02-27 | 4592 | bth | LL - SAT-3-L-1 | A | DONE | 3 | S | pt.neal | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-03-04 | Z | 2025-01-02 | 40 | 20 | 0 |  | 30 | 70 |  |  |  | 61 | 2025-01-27
2025-02-26 | 4593 |  | LL - SAT-3-L-2 | A | DONE | 10 | S-M | pt.neal | UW-LEVY HALL 6230028 | VAV , VD's , 1" liner | 2025-03-04 | Z | 2025-01-02 | 70 | 0 | 160 | F | 160 | 300 |  |  |  | 61 | 2025-01-27
2025-02-27 | 4595 | bth | LL - SAMP 1 | A | DONE | 32 | M-L |  | UW-LEVY HALL 6230028 |  | 2025-03-04 | Z | 2025-01-02 | 420 | 40 | 340 | F | 0 | 1280 |  |  |  | 61 | 2025-01-27
2025-02-27 | 4596 | sp | LL - SAMP 2 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-04 | Z | 2025-01-02 | 30 | 160 | 0 |  | 0 | 200 |  |  |  | 61 | 2025-01-27
2025-02-25 | 3144 |  | 84428 - 84430 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 | VD's | 2025-03-03 | Z | 2025-02-10 | 210 | 0 | 60 | F | 0 | 430 |  | 3rd Floor SO |  | 21
2025-02-25 | 3145 |  | 84431 - 84433 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 | VD | 2025-03-03 | Z | 2025-02-10 | 100 | 0 | 0 |  | 0 | 350 |  | 3rd Floor SO |  | 21
2025-02-25 | 3146 | sp | 84434 , 84436 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-03 | Z | 2025-02-10 | 20 | 280 | 0 |  | 0 | 280 |  | 3rd Floor SO |  | 21
2025-02-25 | 3147 |  | 84435 , 84437 | A | DONE | 13 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-03 | Z | 2025-02-10 | 220 | 0 | 100 | F | 0 | 490 |  | 3rd Floor SO |  | 21
2025-02-25 | 3148 |  | 84438 - 84439 | A | DONE | 16 | S-M |  | UWL-GRAFF 6230017 | VD | 2025-03-03 | Z | 2025-02-10 | 130 | 0 | 270 | F | 0 | 490 |  | 3rd Floor SO |  | 21
2025-02-26 | 3149 |  | 84440 - 84442 | A | DONE | 19 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-03 | Z | 2025-02-10 | 280 | 0 | 180 | F | 0 | 600 |  | 3rd Floor SO |  | 21
2025-02-26 | 3150 | sp | 84443 - 84444 | A | DONE | 9 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-03 | Z | 2025-02-10 | 20 | 190 | 0 |  | 0 | 190 |  | 3rd Floor SO |  | 21
2025-02-26 | 3152 |  | 84473 - 84474 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 | VD | 2025-03-03 | Z | 2025-02-10 | 60 | 0 | 50 | F | 0 | 140 |  | 2nd EA |  | 21
2025-02-26 | 3154 |  | 84493 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 |  | 2025-03-03 | Z | 2025-02-11 | 30 | 0 | 90 | F | 0 | 140 |  | SAT-3-3-5 |  | 20
2025-02-26 | 3155 |  | 84499 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-03-03 | Z | 2025-02-18 | 20 | 0 | 0 |  | 0 | 30 |  | SAT-3-3-3 |  | 13
2025-02-26 | 3156 |  | 84500 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-03-03 | Z | 2025-02-20 | 20 | 0 | 0 |  | 0 | 40 |  | SAT-1-3-4 |  | 11
2025-02-26 | 1100 | sp | 70414 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-03-04 | Z | 2025-02-18 | 20 | 0 | 0 |  | 0 | 20 |  | L3-SA |  | 14
2025-02-26 | 1101 |  | 70416 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-03-04 | Z | 2025-02-18 | 20 | 0 | 0 |  | 20 | 20 |  | L3-GE |  | 14
2025-02-26 | 1102 |  | 70417 - 70418 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2025-03-04 | Z | 2025-02-18 | 30 | 0 | 0 |  | 20 | 40 |  | L2-TA |  | 14
2025-02-26 | 3349 |  | 70411 - 70413 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-03-04 | Z | 2025-02-18 | 30 | 0 | 0 |  | 20 | 40 |  | L3-TA |  | 14
2025-02-24 | 3230 |  | 81136-39 | A | DONE | 4 | S |  | UWSP ALBERTSON 6230016 | paint | 2025-02-25 | Z | 2025-02-06 | 100 | 0 | 0 |  | 20 | 180 |  | MISC VRF |  | 19
2025-02-26 | 3231 |  | 81140 | A | DONE | 3 | S |  | UWSP ALBERTSON 6230016 |  | 2025-03-04 | Z | 2025-02-11 | 60 | 0 | 0 |  | 0 | 90 |  | 1st Fl RA |  | 21
2025-02-26 | 3232 |  | 81141 - 81142 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-03-04 | Z | 2025-02-11 | 40 | 0 | 0 |  | 0 | 60 |  | 3rd Floor |  | 21
2025-02-26 | 3233 |  | 81143 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-03-04 | Z | 2025-02-11 | 300 | 0 | 0 |  | 0 | 500 |  | 3rd Floor linear boxes |  | 21
2025-02-26 | 3234 |  | 81144 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | paint | 2025-03-04 | Z | 2025-02-11 | 20 | 0 | 0 |  | 20 | 30 |  | 4th Floor RA/EA |  | 21
2025-02-27 | 3236 |  | 81147 | A | DONE | 5 | S |  | UWSP ALBERTSON 6230016 | 2" DW | 2025-03-04 | Z | 2025-02-19 | 120 | 0 | 0 |  | 40 | 100 |  | 3rd Fl RA |  | 13
2025-02-26 | 3238 |  | 81149 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-03-04 | Z | 2025-02-25 | 50 | 0 | 0 |  | 0 | 80 |  | 3rd Floor-RA |  | 7
2025-02-24 | 2789 |  | 70142 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-02-25 | Z | 2025-02-19 | 30 | 0 | 0 |  | 20 | 50 |  | Misc |  | 6
2025-02-24 | 2013 | w | 79707 | A | DONE | 3 | S |  | UW-VET MED 6210014 |  | 2025-02-27 | Z | 2025-02-14 | 60 | 0 | 0 |  | 0 | 140 |  | Wall sleeves |  | 13
2025-02-26 | 2441 | bth | SALP10-6 | A | DONE | 11 | S-M | vav's | UW-VET MED 6210014 | partial , 1" liner | 2025-02-28 | Z | 2025-01-30 | 90 | 0 | 170 | F | 20 | 250 |  |  |  | 29 | 2023-08-03 | 2024-07-01 | 2024-09-24 |  | 2024-09-25
2025-02-26 | 2763 |  | 72640 - 72641 | A | DONE | 32 | M |  | UW-VET MED 6210014 | flex | 2025-02-28 | Z | 2025-01-30 | 160 | 0 | 620 | F | 0 | 1040 |  | CB 1456 |  | 29 | 2024-02-05 | 2024-07-01 | 2024-09-24 |  | 2024-09-25
2025-02-26 | 2764 |  | 72642 - 72644 | A | DONE | 18 | S-M |  | UW-VET MED 6210014 | flex | 2025-02-28 | Z | 2025-01-30 | 80 | 0 | 380 | F | 0 | 550 |  | CB 1456 |  | 29 | 2024-02-05 | 2024-07-01 | 2024-09-24 |  | 2024-09-25
2025-02-28 | 2237 |  | L01_G_SOA_001 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 140 | 0 | 170 | F | 0 | 420 |  |  |  | 43
2025-02-28 | 2238 |  | L01_G_SOA_002 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 30 | 0 | 270 | F | 0 | 370 |  |  |  | 43
2025-02-28 | 2240 | bth | L01_G_SOA_004 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 100 | 50 | 110 | F | 0 | 320 |  |  |  | 43
2025-02-28 | 2242 | bth | L01_G_SOA_006 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 20 | 120 | 0 |  | 0 | 130 |  |  |  | 43
2025-02-28 | 2244 | sp | L01_G_SOA_008 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 20 | 130 | 0 |  | 0 | 150 |  |  |  | 43
2025-02-25 | 1984 |  | 71497 | A | DONE | 12 | S-M | neal | WSCC 6240006 | paint | 2025-02-27 | Z | 2025-02-14 | 250 | 0 | 50 | F | 50 | 370 |  | RTU-1 RA |  | 13
2025-02-25 | 1985 |  | 71498 | A | DONE | 2 | S |  | WSCC 6240006 | 1"liner | 2025-02-27 | Z | 2025-02-24 | 30 | 0 | 0 |  | 30 | 50 |  | RTU-12-RA |  | 3
[6 empty] | 843 | [13 empty] | 27630 |  |  |  | 4140 | 14.98%
WEEK OF 3-3-2025
2025-03-03 | 1242 |  | L14-SA-01 | A | DONE | 7 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 170 | 0 | 0 |  | 60 | 190 |  |  |  | 36
2025-03-03 | 1243 |  | L14-SA-02 | A | DONE | 7 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 150 | 0 | 20 | F | 60 | 180 |  |  |  | 36
2025-03-03 | 1244 |  | L14-SA-03 | A | DONE | 7 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 150 | 0 | 20 | F | 70 | 180 |  |  |  | 36
2025-03-03 | 1245 |  | L14-SA-04 | A | DONE | 6 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 110 | 0 | 30 | F | 50 | 130 |  |  |  | 36
2025-03-03 | 1246 |  | L14-SA-05 | A | DONE | 6 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 150 | 0 | 0 |  | 60 | 170 |  |  |  | 36
2025-03-03 | 1247 |  | L14-SA-06 | A | DONE | 5 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 100 | 0 | 20 | F | 60 | 140 |  |  |  | 36
2025-03-04 | 1248 |  | L14-SA-07 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 180 | 0 | 120 | F | 80 | 300 |  |  |  | 36
2025-03-04 | 1249 |  | L14-SA-08 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 100 | 0 | 0 |  | 0 | 220 |  |  |  | 36
2025-03-04 | 1720 |  | L14-SA-09 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 90 | 0 | 0 |  | 30 | 100 |  |  |  | 36
2025-03-04 | 1721 |  | L14-SA-10 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 36
2025-03-04 | 1722 |  | L14-SA-11 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 36
2025-03-04 | 1723 |  | L14-SA-12 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 36
2025-03-04 | 1724 |  | L14-SA-13 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2025-03-05 | Z | 2025-01-28 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 36
2025-03-03 | 1725 | sp | L14-SA-14 | A | DONE | 3 | S | neal | 121 E. WILSON 6230024 |  | 2025-03-05 | Z | 2025-01-28 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 36
2025-03-03 | 1726 | sp | L14-SA-15 | A | DONE | 3 | S | neal | 121 E. WILSON 6230024 |  | 2025-03-05 | Z | 2025-01-28 | 20 | 50 | 0 |  | 0 | 80 |  |  |  | 36
2025-03-03 | 1727 | sp | L14-SA-16 | A | DONE | 7 | S | pt.neal | 121 E. WILSON 6230024 | flex | 2025-03-05 | Z | 2025-01-28 | 50 | 120 | 0 |  | 0 | 190 |  |  |  | 36
2025-03-03 | 1739 | w | 100426 | A | DONE | 2 | S | ss | 121 E. WILSON 6230024 |  | 2025-03-04 | Z | 2025-03-03 | 20 | 0 | 0 |  | 0 | 20 |  | Condensate pan |  | 1
2025-03-05 | 919 |  | 84962 | A | DONE | 5 | S-M |  | BMH AHU-9 6240001 |  | 2025-03-06 | Z | 2025-02-17 | 60 | 0 | 50 | F | 0 | 150 |  | Loading Dock SAHP |  | 17
2025-03-03 | 920 |  | 8463 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2025-03-06 | Z | 2025-02-18 | 20 | 0 | 0 |  | 0 | 30 |  | Loading Dock SAHP |  | 16
2025-03-05 | 923 | w | 84913 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2025-03-06 | Z | 2025-02-26 | 20 | 0 | 0 |  | 0 | 50 |  | Curb cap |  | 8
2025-03-04 | 924 |  | 84914 | A | DONE | 2 | S | neal | BMH AHU-9 6240001 | paint | 2025-03-06 | Z | 2025-02-26 | 20 | 0 | 0 |  | 20 | 30 |  | Loading dock |  | 8
2025-03-05 | 2466 |  | 69735 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-03-07 | Z | 2025-02-26 | 20 | 0 | 0 |  | 0 | 30 |  | RFI 1295 |  | 9
2025-03-04 | 2468 |  | 81619 | A | DONE | 2 | S | neal | CDIS 6220028 | 1" liner | 2025-03-05 | Z | 2025-03-03 | 30 | 0 | 0 |  | 20 | 40 |  | 7th floor |  | 2
2025-03-05 | 2469 |  | 61399 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2025-03-07 | Z | 2025-03-04 | 20 | 0 | 0 |  | 0 | 80 |  | CB1166 |  | 3
2025-03-04 | 182 |  | email | A | DONE | 2 | S |  | DANE CO. AIRPORT 6210011 |  | 2025-03-04 | Z | 2025-03-04 | 20 | 0 | 0 |  | 0 | 60 |  | C-Channel |  | 0
2025-03-06 | 832 | sp | 70754-55 | A | DONE | 21 | S-M | pt alum | DELLSHIRE 6240017 |  | 2025-03-10 | Z | 2025-02-24 | 60 | 450 | 0 |  | 0 | 450 |  | AHU-2-SA |  | 14
2025-03-07 | 833 | bth | 70761,64,67,68,70 | A | DONE | 19 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-10 | Z | 2025-02-24 | 90 | 390 | 0 |  | 20 | 470 |  | MISC VAV |  | 14
2025-03-07 | 834 |  | 70762 | A | DONE | 8 | S | pcd | DELLSHIRE 6240017 |  | 2025-03-10 | Z | 2025-02-24 | 180 | 0 | 0 |  | 0 | 450 |  | BATHROOM |  | 14
2025-03-05 | 838 |  | 70780 | A | DONE | 2 | S | neal | DELLSHIRE 6240017 |  | 2025-03-12 | Z | 2025-02-26 | 20 | 0 | 0 |  | 0 | 40 |  | VTAC trim ring |  | 14
2025-03-07 | 186 | sp | 73901 | A | delete | n/a | S |  | DEWITT 224064 |  | 2025-03-10 | Z | 2025-03-06 | 0 | 0 | 0 |  | 0 | 0 |  | 3-10-AM |  | 4
2025-03-06 | 1214 |  | 81542 | A | DONE | 11 | S-M |  | EXACT MRD 2250009 |  | 2025-03-07 | Z | 2025-03-05 | 160 | 0 | 100 | F | 0 | 370 |  | EC |  | 2
2025-03-07 | 1203 | ovl | 79147 | A | DONE | 10 | S-M | pcd | EXACT TL-2 2250003 | oval , accuflange | 2025-03-04 | Z | 2025-02-25 | 30 | 200 | 0 |  | 0 | 320 |  | CRAH-RA |  | 7
2025-03-03 | 1209 |  | 79025 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-03-04 | Z | 2025-02-28 | 20 | 0 | 0 |  | 0 | 30 |  | LPS |  | 4
2025-03-04 | 451 | w | 1000A | A | DONE | 2 | S |  | KIKKOMAN 6240041 |  | 2025-03-05 | Z | 2025-03-04 | 30 | 0 | 0 |  | 0 | 110 |  | Sleeves |  | 1
2025-03-07 | 2940 |  | 82572 | A | DONE | 3 | S-M |  | LABCORP 6220028 |  | 2025-03-10 | Z | 2025-02-28 | 70 | 0 | 0 |  | 0 | 230 |  | PH |  | 10
2025-03-07 | 2941 |  | 82573 | A | DONE | 6 | S-M |  | LABCORP 6220028 |  | 2025-03-10 | Z | 2025-02-28 | 130 | 0 | 0 |  | 0 | 510 |  | PH |  | 10
2025-03-07 | 2942 |  | 82574 - 82576 | A | DONE | 17 | M |  | LABCORP 6220028 |  | 2025-03-10 | Z | 2025-02-28 | 420 | 0 | 0 |  | 0 | 1050 |  | PH |  | 10
2025-03-05 | 175 |  | 66620 | A | DONE | 8 | S-M |  | MSN 2250007 |  | 2025-03-07 | Z | 2025-02-24 | 70 | 0 | 130 | F | 0 | 290 |  | DR-3 ROW-7 |  | 11
2025-03-07 | 3964 | w | 81062-64,83101 | A | DONE | 8 | S-M |  | PECATONICA ES 6240005 |  | 2025-03-10 | Z | 2024-12-26 | 140 | 0 | 20 | F | 0 | 380 |  | KILN HOOD |  | 66
2025-03-04 | 3967 |  | 0009 - 0010 | A | DONE | 2 | S |  | PECATONICA ES 6240005 |  | 2025-03-06 | Z | 2025-01-20 | 40 | 0 | 0 |  | 0 | 100 |  | Pre-fab hangers | SEMI | 45 | 2025-06-09
2025-03-06 | 3970 | sp | 83140 - 83141 | A | DONE | 23 | M |  | PECATONICA ES 6240005 |  | 2025-03-06 | Z | 2025-01-20 | 80 | 490 | 0 |  | 0 | 630 |  | B-Section SA | SEMI | 45 | 2025-06-16
2025-03-06 | 3972 | sp | 80164 - 80165 | A | DONE | 6 | S-M |  | PECATONICA ES 6240005 |  | 2025-03-06 | Z | 2025-01-20 | 20 | 120 | 0 |  | 0 | 170 |  | B-Section SA S | SEMI | 45 | 2025-06-16
2025-03-07 | 3973 | sp | 80166 - 80167 | A | DONE | 11 | S-M |  | PECATONICA ES 6240005 | oval | 2025-03-13 | Z | 2025-01-20 | 110 | 160 | 0 |  | 0 | 300 |  | B-Section SA S V-20 | SEMI | 52 | 2025-06-16
2025-03-06 | 3974 | sp | 80168 - 80169 | A | DONE | 14 | S-M |  | PECATONICA ES 6240005 | oval | 2025-03-06 | Z | 2025-01-20 | 60 | 270 | 0 |  | 0 | 440 |  | B-Section SA SE | SEMI | 45 | 2025-06-16
2025-03-05 | 3977 | sp | 80174 | A | DONE | 8 | S |  | PECATONICA ES 6240005 |  | 2025-03-06 | Z | 2025-01-21 | 30 | 160 | 0 |  | 0 | 170 |  | B-Section VAV | SEMI | 44 | 2025-06-23
2025-03-07 | 3989 |  | 0007 - 0008 | A | DONE | 2 | S-M | pt.neal | PECATONICA ES 6240005 |  | 2025-03-10 | Z | 2025-01-30 | 20 | 0 | 0 |  | 0 | 110 |  | Pre-fab hangers |  | 39
2025-03-06 | 4204 |  | 83124 - 83126 | A | DONE | 31 | M |  | PECATONICA ES 6240005 | flex , 1" liner | 2025-03-06 | Z | 2025-01-30 | 450 | 0 | 0 |  | 320 | 440 |  | RE-5 | SEMI | 35 | 2025-06-09
2025-03-05 | 2548 |  | 81861 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-03-06 | Z | 2025-03-03 | 30 | 0 | 0 |  | 0 | 50 |  | Misc |  | 3
2025-03-05 | 2549 |  | 70847 | A | DONE | 6 | S-M |  | PROMEGA BTC 6230022 | VD | 2025-03-06 | Z | 2025-03-03 | 100 | 30 | 0 |  | 0 | 250 |  | EA |  | 3
2025-03-05 | 4790 |  | 85302 | A | DONE | 8 | S | alum | ROCK CO. JAIL 6220018 | bird s. | 2025-03-06 | Z | 2025-02-28 | 90 | 110 | 0 |  | 0 | 100 |  | Dryer vent |  | 6
2025-03-05 | 4791 | bth | 85303 - 85304 | A | DONE | 7 | S-M |  | ROCK CO. JAIL 6220018 | bird s. , 1" liner | 2025-03-06 | Z | 2025-02-28 | 90 | 40 | 40 | F | 30 | 190 |  | Laundry RA |  | 6
2025-03-06 | 1411 |  | 68852 | A | DONE | 2 | S |  | SPH BIRTH CTR. 6240022 | 1/2"liner | 2025-03-10 | Z | 2025-02-24 | 20 | 0 | 0 |  | 0 | 40 |  | Exhaust |  | 14
2025-03-07 | 3142 |  | 68455 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-03-10 | Z | 2025-02-04 | 20 | 0 | 0 |  | 0 | 20 |  | DM Frames |  | 34
2025-03-03 | 2839 |  | 67747 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-03-03 | Z | 2025-03-03 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor |  | 0
2025-03-04 | 183 |  | 79439 , 79444 | A | DONE | 2 | S |  | TST COATING 4240060 | flex | 2025-03-05 | Z | 2025-03-04 | 20 | 0 | 0 |  | 20 | 40 |  | SA |  | 1
2025-03-04 | 3770 |  | L5B-TA 6 | A | DONE | 3 | S |  | UW-AVRL 6240038 | 1"liner | 2025-03-05 | Z | 2025-02-21 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 12
2025-03-04 | 3771 |  | L5B-TA 7 | A | DONE | 3 | S |  | UW-AVRL 6240038 | 1"liner | 2025-03-05 | Z | 2025-02-21 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 12
2025-03-04 | 3772 |  | L5B-TA 8 | A | DONE | 4 | S |  | UW-AVRL 6240038 | 1"liner | 2025-03-05 | Z | 2025-02-21 | 20 | 0 | 20 | F | 30 | 90 |  |  |  | 12
2025-03-04 | 3773 |  | L5B-TA 9 | A | DONE | 3 | S |  | UW-AVRL 6240038 | 1"liner | 2025-03-05 | Z | 2025-02-21 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 12
2025-03-04 | 3774 |  | L5B-TA 10 | A | DONE | 3 | S |  | UW-AVRL 6240038 | 1"liner | 2025-03-05 | Z | 2025-02-21 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 12
2025-03-04 | 3775 |  | L5B-SAT 521 | A | DONE | 7 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 50 | 60 | 0 |  | 0 | 160 |  |  |  | 12
2025-03-04 | 3776 |  | L5B-SAT 522 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 12
2025-03-04 | 3777 |  | L5B-SAT 524 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 30 | 30 | 0 |  | 0 | 70 |  |  |  | 12
2025-03-04 | 3778 |  | L5B-SAT 526 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 10 | 60 | 0 |  | 0 | 140 |  |  |  | 12
2025-03-04 | 3779 |  | L5B-SAT 570 | A | DONE | 10 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 210 | 40 | 0 |  | 0 | 300 |  |  |  | 12
2025-03-04 | 3780 |  | L5B-SAT 516 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 10 | 20 | 0 |  | 0 | 30 |  |  |  | 12
2025-03-04 | 3781 |  | L5B-SAT 512 | A | DONE | 10 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 120 | 130 | 0 |  | 0 | 280 |  |  |  | 12
2025-03-04 | 3782 |  | L5B-SAT 513 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 40 | 30 | 0 |  | 0 | 80 |  |  |  | 12
2025-03-04 | 3783 |  | L5B-SAMP 3 | A | DONE | 10 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 180 | 40 | 40 | F | 0 | 340 |  |  |  | 12
2025-03-04 | 3784 |  | L5B-SAMP 4 | A | DONE | 9 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 90 | 90 | 40 | F | 0 | 240 |  |  |  | 12
2025-03-04 | 3785 | bth | L5B-SAMP 5 | A | DONE | 11 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 100 | 70 | 90 | F | 0 | 290 |  |  |  | 12
2025-03-04 | 3786 | sp | L5B-SAMP 6 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 30 | 100 | 0 |  | 0 | 130 |  |  |  | 12
2025-03-04 | 3787 |  | L5B-Mech Room EA Fan 1 | A | DONE | 10 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 180 | 20 | 40 | F | 0 | 310 |  |  |  | 12
2025-03-04 | 3788 |  | L5B-Mech Room EAMP 1 | A | DONE | 9 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 180 | 0 | 40 | F | 0 | 250 |  |  |  | 12
2025-03-04 | 3789 |  | L5B-Mech Room SAMP 1 | A | DONE | 17 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 220 | 0 | 200 | F | 0 | 550 |  |  |  | 12
2025-03-04 | 3790 |  | L5B-EAT 515 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 12
2025-03-04 | 3791 |  | L5B-EAT 516 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 12
2025-03-04 | 3792 |  | L5B-EAT 509 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 12
2025-03-04 | 3793 |  | L5B-EAT 512 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 120 | 30 | 0 |  | 0 | 170 |  |  |  | 12
2025-03-04 | 3794 |  | L5B-EAMP 3 | A | DONE | 10 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 210 | 20 | 0 |  | 0 | 350 |  |  |  | 12
2025-03-04 | 3795 |  | L5B-EAMP 4 | A | DONE | 8 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 30 | 20 | 150 | F | 0 | 230 |  |  |  | 12
2025-03-04 | 3796 |  | L5B-EAMP 5 | A | DONE | 7 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 90 | 60 | 20 | F | 0 | 180 |  |  |  | 12
2025-03-04 | 3797 |  | L5B-EAMP 6 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-21 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 12
2025-03-04 | 4317 |  | L5B-EAMP 5.1 | A | DONE | 3 | S | neal | UW-AVRL 6240038 |  | 2025-03-05 | Z | 2025-02-28 | 30 | 30 | 0 |  | 0 | 70 |  |  |  | 5
2025-03-05 | 422 |  | 83941 | A | DONE | 2 | S | neal | UW-LEVY HALL 6230028 |  | 2025-03-05 | Z | 2025-03-05 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-3-L-8 |  | 0
2025-03-05 | 3239 |  | 81254 | A | DONE | 3 | S-M |  | UWSP ALBERTSON 6230016 | paint | 2025-03-06 | Z | 2025-02-28 | 60 | 0 | 0 |  | 20 | 110 |  | 1st Floor elec. Room |  | 6
2025-03-04 | 3243 |  | 81255 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-03-06 | Z | 2025-03-03 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2025-03-05 | 2790 |  | 70144 | A | DONE | 20 | M |  | UWSP CHAMPION HALL 6240008 |  | 2025-03-06 | Z | 2025-02-24 | 330 | 0 | 160 | F | 0 | 1090 |  | AHU-22-OA |  | 10
2025-03-05 | 2791 |  | 70147-48 | A | DONE | 8 | M |  | UWSP CHAMPION HALL 6240008 |  | 2025-03-06 | Z | 2025-02-24 | 130 | 0 | 60 | F | 0 | 220 |  | PRV-1 & 3 |  | 10
2025-03-05 | 2792 |  | 70145-46 | A | DONE | 18 | M |  | UWSP CHAMPION HALL 6240008 |  | 2025-03-06 | Z | 2025-02-24 | 370 | 0 | 80 | F | 0 | 1120 |  | AHU-21-OA / PRV-2 |  | 10
2025-03-05 | 2793 |  | 70149 | A | DONE | 4 | S-M | pt.alum | UWSP CHAMPION HALL 6240008 | 1" liner | 2025-03-06 | Z | 2025-02-28 | 80 | 0 | 0 |  | 20 | 90 |  | Shower EA |  | 6
2025-03-05 | 2014 |  | 79708 | A | DONE | 5 | S-M |  | UW-VET MED 6210014 |  | 2025-03-07 | Z | 2025-02-26 | 120 | 0 | 0 |  | 0 | 220 |  | 3rd floor |  | 9
2025-03-03 | 2015 | w | 79709 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-03-06 | Z | 2025-02-28 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 6
2025-03-06 | 1176 |  | PH_E_SOA_001 | A | DONE | 10 | M |  | WAUNAKEE MS 6230013 |  | 2025-03-07 | Z | 2025-02-26 | 250 | 0 | 0 |  | 0 | 620 |  |  |  | 9
2025-03-06 | 1177 |  | PH_E_SOA_002 | A | DONE | 12 | M |  | WAUNAKEE MS 6230013 | CD | 2025-03-07 | Z | 2025-02-26 | 280 | 0 | 0 |  | 0 | 590 |  |  |  | 9
2025-03-06 | 1178 |  | PH_E_SOA_003 | A | DONE | 12 | M |  | WAUNAKEE MS 6230013 | CD | 2025-03-07 | Z | 2025-02-26 | 290 | 0 | 0 |  | 0 | 610 |  |  |  | 9
2025-03-06 | 1179 |  | PH_E_SOA_004 | A | DONE | 12 | M |  | WAUNAKEE MS 6230013 |  | 2025-03-07 | Z | 2025-02-26 | 300 | 0 | 0 |  | 0 | 580 |  |  |  | 9
2025-03-06 | 1180 |  | PH_E_EAD_001 | A | DONE | 18 | M |  | WAUNAKEE MS 6230013 |  | 2025-03-07 | Z | 2025-02-26 | 380 | 0 | 60 | F | 0 | 930 |  |  |  | 9
2025-03-06 | 1181 |  | PH_E_EAD_002 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-07 | Z | 2025-02-26 | 250 | 0 | 60 | F | 0 | 470 |  |  |  | 9
2025-03-06 | 1182 |  | PH_E_EAD_003 | A | DONE | 17 | M |  | WAUNAKEE MS 6230013 | CD | 2025-03-07 | Z | 2025-02-26 | 350 | 0 | 60 | F | 0 | 700 |  |  |  | 9
2025-03-06 | 1183 |  | PH_E_EAD_004 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-07 | Z | 2025-02-26 | 210 | 0 | 60 | F | 0 | 530 |  |  |  | 9
2025-03-06 | 1184 |  | PH_E_EAD_005 | A | DONE | 16 | M |  | WAUNAKEE MS 6230013 | CD | 2025-03-07 | Z | 2025-02-26 | 320 | 0 | 60 | F | 0 | 850 |  |  |  | 9
2025-03-06 | 1185 |  | PH_E_EAD_006 | A | DONE | 17 | M |  | WAUNAKEE MS 6230013 |  | 2025-03-07 | Z | 2025-02-26 | 420 | 0 | 0 |  | 0 | 920 |  |  |  | 9
2025-03-04 | 1186 |  | 79808 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-07 | Z | 2025-03-03 | 80 | 0 | 0 |  | 0 | 80 |  |  |  | 4
2025-03-04 | 1187 |  | 79810 | A | DONE | 2 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-07 | Z | 2025-03-03 | 50 | 0 | 0 |  | 0 | 90 |  |  |  | 4
2025-03-03 | 2239 |  | L01_G_SOA_003 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 40 | 0 | 270 | F | 0 | 390 |  |  |  | 43
2025-03-03 | 2241 | bth | L01_G_SOA_005 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 60 | 70 | 60 | F | 0 | 220 |  |  |  | 43
2025-03-03 | 2243 | bth | L01_G_SOA_007 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 150 | 40 | 110 | F | 0 | 380 |  |  |  | 43
2025-03-03 | 2245 | bth | L01_G_SOA_009 | A | DONE | 6 | S | pt.neal | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 40 | 90 | 0 |  | 0 | 140 |  |  |  | 43
2025-03-03 | 2246 | bth | L01_G_SOA_010 | A | DONE | 6 | S | pt.neal | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 30 | 120 | 0 |  | 0 | 160 |  |  |  | 43
2025-03-03 | 2247 | bth | L01_G_SOA_011 | A | DONE | 10 | S-M | pt.neal | WAUNAKEE MS 6230013 | VD | 2025-03-05 | Z | 2025-01-21 | 70 | 150 | 30 | F | 0 | 300 |  |  |  | 43
2025-03-03 | 2248 |  | L01_G_EAD_001 | A | DONE | 18 | M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 170 | 0 | 270 | F | 0 | 670 |  |  |  | 43
2025-03-03 | 2249 |  | L01_G_EAD_002 | A | DONE | 19 | M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 70 | 0 | 400 | F | 0 | 700 |  |  |  | 43
2025-03-03 | 4100 | bth | L01_G_EAD_003 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 40 | 160 | 130 | F | 0 | 350 |  |  |  | 43
2025-03-03 | 4101 |  | L01_G_EAD_004 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 80 | 0 | 160 | F | 0 | 320 |  |  |  | 43
2025-03-03 | 4102 | bth | L01_G_EAD_005 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 110 | 20 | 30 | F | 0 | 220 |  |  |  | 43
2025-03-03 | 4103 | bth | L01_G_EAD_006 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | VD | 2025-03-05 | Z | 2025-01-21 | 60 | 20 | 100 | F | 0 | 250 |  |  |  | 43
2025-03-03 | 4104 | bth | L01_G_EAD_007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 20 | 90 | 0 |  | 0 | 110 |  |  |  | 43
2025-03-03 | 4105 |  | L01_G_EAD_008 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 70 | 0 | 130 | F | 0 | 260 |  |  |  | 43
2025-03-03 | 4106 | bth | L01_G_EAD_009 | A | DONE | 10 | S-M | pt.neal | WAUNAKEE MS 6230013 | VD | 2025-03-05 | Z | 2025-01-21 | 70 | 20 | 140 | F | 0 | 300 |  |  |  | 43
2025-03-03 | 4107 |  | L01_G_EAD_010 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-05 | Z | 2025-01-21 | 60 | 0 | 210 | F | 0 | 360 |  |  |  | 43
2025-03-03 | 4108 | bth | L01_G_EAD_011 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | VD | 2025-03-05 | Z | 2025-01-21 | 50 | 40 | 40 | F | 0 | 160 |  |  |  | 43
2025-03-03 | 4109 | sp | L01_G_EAD_012 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-05 | Z | 2025-01-21 | 30 | 110 | 0 |  | 0 | 140 |  |  |  | 43
2025-03-03 | 4110 | sp | L01_G_EAD_013 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-05 | Z | 2025-01-21 | 30 | 40 | 0 |  | 0 | 60 |  |  |  | 43
2025-03-07 | 1281 |  | 82212 | A | DONE | 3 | S-M |  | WINDSOR 6240012 |  | 2025-03-10 | Z | 2025-02-27 | 60 | 0 | 0 |  | 0 | 110 |  | East DOAS |  | 11
2025-03-07 | 1282 |  | 82214 | A | DONE | 4 | S-M |  | WINDSOR 6240012 |  | 2025-03-10 | Z | 2025-02-27 | 80 | 0 | 0 |  | 0 | 110 |  | East DOAS |  | 11
2025-03-05 | 1283 |  | 82215 | A | DONE | 4 | S-M |  | WINDSOR 6240012 | paint | 2025-03-06 | Z | 2025-02-27 | 100 | 0 | 0 |  | 110 | 110 |  | Finishes |  | 7
2025-03-07 | 1284 |  | 82216 - 82218 | A | DONE | 8 | S-M |  | WINDSOR 6240012 |  | 2025-03-10 | Z | 2025-03-05 | 180 | 0 | 0 |  | 0 | 330 |  | West DOAS |  | 5
2025-03-04 | 1986 |  | 01 | A | DONE | 2 | S | neal | WSCC 6240006 |  | 2025-03-06 | Z | 2025-02-26 | 20 | 0 | 0 |  | 0 | 60 |  | Pre-Fab Duct Hangers |  | 8
2025-03-05 | 1987 |  | 71499 | A | DONE | 3 | S | neal | WSCC 6240006 | 1" liner | 2025-03-06 | Z | 2025-02-26 | 60 | 0 | 0 |  | 50 | 120 |  | ERV-6 |  | 8
2025-03-07 | 1991 |  | 66184 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-03-13 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 20 |  | Fan -09 |  | 6
[6 empty] | 935 | [13 empty] | 31240 |  |  |  | 19300 | 61.78%
WEEK OF 3-10-2025
2025-03-13 | 1740 |  | 81970 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-03-13 | Z | 2025-03-05 | 20 | 0 | 0 |  | 0 | 20 |  | Funnel |  | 8
2025-03-12 | 1741 |  | 81971 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2025-03-13 | Z | 2025-03-05 | 70 | 0 | 0 |  | 0 | 100 |  | Flat stock |  | 8
2025-03-13 | 1743 |  | 81972 - 81973 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2025-03-17 | Z | 2025-03-10 | 120 | 0 | 0 |  | 0 | 320 |  | L14-OA-02 |  | 7
2025-03-13 | 925 |  | 84966 | A | DONE | 8 | S-M |  | BMH AHU-9 6240001 |  | 2025-03-17 | Z | 2025-03-12 | 180 | 0 | 0 |  | 0 | 350 |  | HPSA |  | 5
2025-03-13 | 926 | sp | 84967 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2025-03-17 | Z | 2025-03-12 | 0 | 30 | 0 |  | 0 | 30 |  | HPSA |  | 5
2025-03-14 | 927 |  | 84968 | A | DONE | 4 | S |  | BMH AHU-9 6240001 |  | 2025-03-17 | Z | 2025-03-12 | 0 | 0 | 90 | F | 0 | 120 |  | Shaft FSD's |  | 5
2025-03-11 | 2470 |  | 95248 | A | DONE | 2 | S-M | neal | CDIS 6220028 | paint | 2025-03-11 | Z | 2025-03-05 | 40 | 0 | 0 |  | 0 | 110 |  | Misc |  | 6
2025-03-13 | 835 | bth | 29499 | A | DONE | 14 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-17 | Z | 2025-02-24 | 190 | 20 | 130 | F | 0 | 510 |  | AHU-3-SA |  | 21
2025-03-13 | 836 |  | 70758-60 | A | DONE | 34 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-17 | Z | 2025-02-24 | 450 | 0 | 390 | F | 0 | 1110 |  | AHU-3-MISC |  | 21
2025-03-13 | 837 | bth | 70773,75-78 | A | DONE | 25 | S-M | pt pcd | DELLSHIRE 6240017 |  | 2025-03-17 | Z | 2025-02-24 | 230 | 90 | 290 | F | 0 | 770 |  | MISC |  | 21
2025-03-14 | 839 | w | 70753.1 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-03-17 | Z | 2025-02-26 | 30 | 0 | 0 |  | 0 | 70 |  | 2nd A/B EA sleeves |  | 19
2025-03-13 | 840 | bth | 70728 | A | DONE | 18 | M |  | DELLSHIRE 6240017 | flex | 2025-03-17 | Z | 2025-02-26 | 50 | 380 | 0 |  | 0 | 410 |  | 1st Fl. EG-12 |  | 19
2025-03-13 | 841 | bth | 70781 - 70783 | A | DONE | 23 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-17 | Z | 2025-03-04 | 310 | 40 | 210 | F | 0 | 520 |  | 1st Fl Main |  | 13
2025-03-14 | 842 | bth | 70784 - 70786 | A | DONE | 10 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-17 | Z | 2025-03-04 | 80 | 150 | 0 |  | 20 | 220 |  | VAV |  | 13
2025-03-13 | 843 | bth | 70787 - 70788 | A | DONE | 8 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-17 | Z | 2025-03-04 | 130 | 70 | 0 |  | 0 | 180 |  | VAV |  | 13
2025-03-11 | 847 |  | 70799 | A | DONE | 6 | S |  | DELLSHIRE 6240017 |  | 2025-03-12 | Z | 2025-03-07 | 160 | 0 | 0 |  | 0 | 190 |  | Angles |  | 5
2025-03-12 | 1213 |  | 56801 - 56802 | A | DONE | 3 | S |  | EXACT BIOPHARMA 2250001 | paint | 2025-03-13 | Z | 2025-03-05 | 70 | 0 | 0 |  | 50 | 100 |  | Ceiling finishes |  | 8
2025-03-13 | 1215 | bth | 81548 , 50 , 69623 | A | DONE | 24 | M |  | EXACT MRD 2250009 |  | 2025-03-14 | Z | 2025-03-11 | 290 | 160 | 150 | F | 0 | 740 |  | EAT EA |  | 3
2025-03-13 | 1217 |  | 69628 | A | DONE | 2 | S |  | EXACT MRD 2250009 |  | 2025-03-14 | Z | 2025-03-12 | 20 | 0 | 0 |  | 0 | 20 |  | EC |  | 2
2025-03-13 | 1216 |  | 95833 | A | DONE | 2 | S |  | EXACT MRD 8250009 |  | 2025-03-12 | Z | 2025-03-12 | 20 | 0 | 0 |  | 0 | 30 |  | Plate |  | 0
2025-03-11 | 1206 |  | 56699 | A | DONE | 2 | S-M |  | EXACT SCIENCE 8250004 |  | 2025-03-11 | Z | 2025-02-26 | 50 | 0 | 0 |  | 0 | 90 |  | Angle |  | 13
2025-03-11 | 1204 | ovl | 79148 | A | DONE | 9 | S-M | pcd | EXACT TL-2 2250003 | oval , accuflange | 2025-03-11 | Z | 2025-02-25 | 20 | 200 | 0 |  | 0 | 260 |  | CRAH-RA |  | 14
2025-03-12 | 1210 |  | 79026 | A | DONE | 4 | S-M | pcd | EXACT TL-2 2250003 | quick clamps | 2025-03-11 | Z | 2025-02-28 | 70 | 30 | 0 |  | 0 | 180 |  | CRAH RA |  | 11
2025-03-11 | 1211 |  | 79027 | A | DONE | 2 | S |  | EXACT TL-2 2250003 | paint | 2025-03-11 | Z | 2025-02-28 | 20 | 0 | 0 |  | 20 | 20 |  | CRAH RA |  | 11
2025-03-11 | 1212 |  | 79028 | A | DONE | 2 | S | pcd | EXACT TL-2 2250003 | oval , accuflange | 2025-03-11 | Z | 2025-02-28 | 40 | 0 | 0 |  | 0 | 70 |  | CRAH RA |  | 11
2025-03-11 | 1207 | bth | TL3_EAT 1810-6 | A | DONE | 4 | S | alum | EXACT TL-3 6240028 |  | 2025-03-11 | Z | 2025-02-26 | 30 | 50 | 0 |  | 0 | 50 |  |  |  | 13
2025-03-11 | 1208 | sp | TL3_EAT 1810-7 | A | DONE | 3 | S | alum | EXACT TL-3 6240028 |  | 2025-03-11 | Z | 2025-02-26 | 20 | 40 | 0 |  | 0 | 30 |  |  |  | 13
2025-03-13 | 2943 | sp | 82577 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2025-03-17 | Z | 2025-03-10 | 20 | 20 | 0 |  | 0 | 30 |  | 3rd Fl |  | 7
2025-03-13 | 2662 |  | 002 , 004 | A | DONE | 4 | S-M |  | MONROE HS 6240018 |  | 2025-03-13 | Z | 2025-03-05 | 100 | 0 | 0 |  | 0 | 330 |  | Sleeves |  | 8
2025-03-12 | 184 |  | 79435 | A | DONE | 2 | S |  | OAKWOOD PIONEER 10060765 | flex | 2025-03-12 | Z | 2025-03-04 | 20 | 0 | 0 |  | 0 | 30 |  | Apt. 123 |  | 8
2025-03-12 | 3968 | sp | 83136 - 83138 | A | DONE | 24 | M |  | PECATONICA ES 6240005 | oval , accuflange | 2025-03-13 | Z | 2025-01-20 | 110 | 490 | 0 |  | 0 | 720 |  | B-Section SA | SEMI | 52 | 2025-06-16
2025-03-12 | 3969 | sp | 83139 - 83139.5 | A | DONE | 10 | S-M |  | PECATONICA ES 6240005 | oval , accuflange | 2025-03-13 | Z | 2025-01-20 | 40 | 190 | 0 |  | 0 | 270 |  | B-Section SA | SEMI | 52 | 2025-06-16
2025-03-12 | 3971 | sp | 83142 , 80163 | A | DONE | 8 | M |  | PECATONICA ES 6240005 | oval | 2025-03-13 | Z | 2025-01-20 | 40 | 150 | 0 |  | 0 | 230 |  | B-Section SA NE | SEMI | 52 | 2025-06-16
2025-03-11 | 3975 |  | 80170 - 80171 | A | DONE | 22 | S-M |  | PECATONICA ES 6240005 | 2" liner | 2025-03-13 | Z | 2025-01-21 | 150 | 0 | 380 | F | 290 | 500 |  | B-Section VAV | SEMI | 51 | 2025-06-23
2025-03-11 | 3976 |  | 80172 - 80173 | A | DONE | 15 | S-M |  | PECATONICA ES 6240005 | 2" liner | 2025-03-13 | Z | 2025-01-21 | 110 | 0 | 250 | F | 280 | 450 |  | B-Section VAV | SEMI | 51 | 2025-06-23
2025-03-13 | 188 |  | 79445 | A | DONE | 2 | S |  | PROMEGA 4250008 |  | 2025-03-20 | Z | 2025-03-12 | 20 | 0 | 0 |  | 0 | 20 |  | Boiler intake |  | 8
2025-03-11 | 180 | sp | 79438 | A | DONE | 12 | S-M |  | PROMEGA BOILER 4250008 |  | 2025-03-11 | Z | 2025-03-03 | 70 | 210 | 0 |  | 0 | 270 |  | OA |  | 8
2025-03-12 | 4792 |  | 85305 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2025-03-13 | Z | 2025-03-10 | 40 | 0 | 0 |  | 0 | 50 |  | Jail |  | 3
2025-03-12 | 179 |  | 66178 - 66179 | A | DONE | 13 | S-M | neal | SCOTT W. 1000380 |  | 2025-03-13 | Z | 2025-02-28 | 120 | 0 | 200 | F | 0 | 370 |  | Furnace |  | 13
2025-03-11 | 181 |  | 80774 | A | DONE | 2 | S | ss | SSM O'KEEFE 8240002 |  | 2025-03-11 | Z | 2025-03-03 | 20 | 0 | 0 |  | 0 | 20 |  | Escutcheon |  | 8
2025-03-11 | 187 | w | 80775,80 | A | DONE | 2 | S |  | SSM O'KEEFE 8240002 |  | 2025-03-11 | Z | 2025-03-06 | 20 | 0 | 0 |  | 0 | 70 |  | PAN & V Channel |  | 5
2025-03-13 | 2402 |  | 80047 | A | DONE | 6 | S |  | ST.BERNARD 6230023 | paint , 1" liner | 2025-03-13 | Z | 2025-03-05 | 140 | 0 | 0 |  | 120 | 400 |  | SA |  | 8
2025-03-12 | 2840 |  | 67748 | A | DONE | 7 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2025-03-11 | Z | 2025-03-04 | 160 | 0 | 0 |  | 0 | 230 |  | 2nd B |  | 7
2025-03-13 | 2841 |  | 67749 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-03-13 | Z | 2025-03-05 | 20 | 0 | 0 |  | 0 | 20 |  | 2A |  | 8
2025-03-12 | 2842 |  | 67750 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-03-13 | Z | 2025-03-10 | 20 | 0 | 0 |  | 20 | 30 |  | 2nd Floor |  | 3
2025-03-13 | 2843 |  | 67752 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-03-17 | Z | 2025-03-11 | 20 | 0 | 0 |  | 20 | 40 |  | TA |  | 6
2025-03-12 | 3799 | bth | L5A-SAT 520-1 | A | DONE | 4 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 30 | 50 | 0 |  | 0 | 80 |  |  |  | 13
2025-03-13 | 4300 | bth | L5A-SAT 520-2 | A | DONE | 5 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 40 | 80 | 0 |  | 0 | 130 |  |  |  | 13
2025-03-12 | 4301 | bth | L5A-529 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 13
2025-03-13 | 4302 | bth | L5A-533 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 13
2025-03-12 | 4303 | bth | L5A-536 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 13
2025-03-12 | 4304 |  | L5A-537 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 13
2025-03-13 | 4305 | bth | L5A-EAT-520-1 | A | DONE | 10 | S-M |  | UW-AVRL 6240038 | VD's | 2025-03-12 | Z | 2025-02-27 | 140 | 20 | 90 | F | 0 | 320 |  |  |  | 13
2025-03-12 | 4306 | sp | L5A-EAT-537 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2025-03-12 | 4307 | sp | L5A-EAT-541 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2025-03-12 | 4308 |  | L5A-TA 5 | A | DONE | 2 | S |  | UW-AVRL 6240038 | 1" liner | 2025-03-12 | Z | 2025-02-27 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 13
2025-03-12 | 4309 |  | L5B-SAT 509 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 13
2025-03-13 | 4310 | bth | L5B-SAT 510 | A | DONE | 4 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 30 | 60 | 0 |  | 0 | 90 |  |  |  | 13
2025-03-13 | 4311 | bth | L5B-SAT 515 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2025-03-12 | 4312 | bth | L5B-SAT 520-3 | A | DONE | 8 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 90 | 80 | 20 | F | 0 | 200 |  |  |  | 13
2025-03-13 | 4313 | bth | L5B-SAT 520-4 | A | DONE | 8 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 40 | 150 | 0 |  | 0 | 200 |  |  |  | 13
2025-03-12 | 4314 |  | L5B-TA 11 | A | DONE | 2 | S |  | UW-AVRL 6240038 | 1" liner | 2025-03-12 | Z | 2025-02-27 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 13
2025-03-12 | 4315 | bth | L5B-EAT 520 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 80 | 50 | 20 | F | 0 | 180 |  |  |  | 13
2025-03-13 | 4316 | bth | L5B-EAT 513 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-02-27 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 13
2025-03-12 | 4318 |  | 69130 | A | DONE | 5 | S |  | UW-AVRL 6240038 | 1" liner | 2025-03-12 | Z | 2025-03-05 | 120 | 0 | 0 |  | 20 | 130 |  | TA-4 |  | 7
2025-03-12 | 4319 |  | 69131 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-03-12 | Z | 2025-03-06 | 60 | 0 | 0 |  | 0 | 110 |  | Duct Tester |  | 6
2025-03-11 | 352 |  | L1-RAMP 5 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-11 | Z | 2025-01-31 | 70 | 0 | 30 | F | 0 | 130 |  | Misc |  | 39
2025-03-14 | 446 |  | 83940 | A | DONE | 2 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-03-18 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 20 |  | 1st Floor |  | 11
2025-03-11 | 448 | w | 83943 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-11 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 30 |  | 6th Floor Sleeve |  | 4
2025-03-12 | 449 |  | EMAIL | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2025-03-11 | Z | 2025-03-11 | 20 | 0 | 0 |  | 0 | 20 |  | Cap |  | 0
2025-03-11 | 365p |  | L1-SAMP 9 | A | DONE | 9 | M |  | UW-LEVY HALL 6230028 | partial , 1" liner | 2025-03-11 | Z | 2025-02-03 | 220 | 0 | 0 |  | 150 | 480 |  |  |  | 36
2025-03-12 | 367p |  | L1-RAMP 10 | A | DONE | 17 | M |  | UW-LEVY HALL 6230028 | partial , 1" liner | 2025-03-11 | Z | 2025-02-03 | 420 | 0 | 0 |  | 320 | 1030 |  |  |  | 36
2025-03-12 | 369p |  | L1-RAMP 9 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-11 | Z | 2025-02-03 | 170 | 0 | 50 | F | 0 | 280 |  |  |  | 36
2025-03-12 | 370p |  | L1-EAMP 10 | A | DONE | 20 | M |  | UW-LEVY HALL 6230028 | partial , bird s. | 2025-03-11 | Z | 2025-02-03 | 410 | 0 | 70 | F | 370 | 1040 |  |  |  | 36
2025-03-12 | 371p |  | L1-EAMP 11 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 | partial | 2025-03-11 | Z | 2025-02-03 | 160 | 0 | 50 | F | 0 | 280 |  |  |  | 36
2025-03-13 | 3157 | sp | 82354 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | flex | 2025-03-17 | Z | 2025-02-26 | 20 | 30 | 0 |  | 0 | 40 |  | 2nd TF-2 |  | 19
2025-03-13 | 3158 |  | 84445 - 84448 | A | DONE | 23 | M |  | UWL-GRAFF 6230017 | VD's | 2025-03-17 | Z | 2025-02-26 | 330 | 0 | 240 | F | 0 | 870 |  | 2nd RA SO |  | 19
2025-03-13 | 3159 |  | 84449 - 84451 | A | DONE | 17 | S-M |  | UWL-GRAFF 6230017 | VD's | 2025-03-17 | Z | 2025-02-26 | 260 | 0 | 160 | F | 0 | 510 |  | 2nd RA SO |  | 19
2025-03-13 | 3160 | sp | 84452 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 0 | 50 | 0 |  | 0 | 40 |  | 2nd RA SO |  | 19
2025-03-13 | 3161 |  | 84453 - 84454 | A | DONE | 16 | M |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 210 | 0 | 170 | F | 0 | 580 |  | 2nd RA SO |  | 19
2025-03-13 | 3162 | sp | 84455 - 84456 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 20 | 180 | 0 |  | 0 | 220 |  | 2nd RA SO |  | 19
2025-03-13 | 3163 |  | 84468 , 84470 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 | VD | 2025-03-17 | Z | 2025-02-26 | 200 | 0 | 50 | F | 0 | 350 |  | 2nd RA NO |  | 19
2025-03-13 | 3164 | sp | 84471 - 72 , 84475 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 30 | 270 | 0 |  | 0 | 320 |  | 2nd RA NO |  | 19
2025-03-13 | 3165 |  | 84476 - 84477 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 150 | 0 | 100 | F | 0 | 330 |  | 2nd RA NO |  | 19
2025-03-13 | 3166 | sp | 84478 - 84479 | A | DONE | 9 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 20 | 190 | 0 |  | 0 | 230 |  | 2nd RA NO |  | 19
2025-03-13 | 3167 | sp | 84481 | A | DONE | 0 | n/a |  | UWL-GRAFF 6230017 | elbows | 2025-03-17 | Z | 2025-02-26 | 0 | 0 | 0 |  | 0 | 0 |  | 2nd fittings |  | 19
2025-03-13 | 3168 |  | 84504 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-1-3-4 |  | 19
2025-03-14 | 3169 | bth | 84508 - 84509 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 50 | 40 | 50 | F | 0 | 170 |  | SAT-3-2-2 |  | 19
2025-03-14 | 3170 |  | 84510 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 30 | 0 | 0 |  | 0 | 50 |  | SAT-3-2-1 |  | 19
2025-03-13 | 3171 |  | 84511 - 84514 | A | DONE | 18 | M |  | UWL-GRAFF 6230017 | VD's | 2025-03-17 | Z | 2025-02-26 | 180 | 0 | 250 | F | 0 | 550 |  | 2nd RA NO |  | 19
2025-03-13 | 3172 |  | 84515 - 84518 | A | DONE | 18 | M |  | UWL-GRAFF 6230017 | VD | 2025-03-17 | Z | 2025-02-26 | 250 | 0 | 200 | F | 0 | 690 |  | 2nd RA NO |  | 19
2025-03-14 | 3173 |  | 84519 - 84521 | A | DONE | 14 | M |  | UWL-GRAFF 6230017 | VD's | 2025-03-17 | Z | 2025-02-26 | 220 | 0 | 130 | F | 0 | 420 |  | 2nd RA NO |  | 19
2025-03-13 | 3174 | sp | 84522 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-02-26 | 0 | 30 | 0 |  | 0 | 30 |  | 2nd RA NO |  | 19
2025-03-13 | 3175 |  | 84631 - 84633 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-03-05 | 40 | 0 | 30 | F | 0 | 80 |  | SAT / RA |  | 12
2025-03-13 | 3176 |  | 84634 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-03-17 | Z | 2025-03-05 | 30 | 0 | 0 |  | 0 | 50 |  | 3rd RA so |  | 12
2025-03-11 | 1103 |  | 70420-21 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2025-03-11 | Z | 2025-02-25 | 70 | 0 | 0 |  | 0 | 100 |  | L2-FD |  | 14
2025-03-14 | 1105 |  | 70425 - 70426 | A | DONE | 2 | S |  | UWRF 6230010 | paint , flex | 2025-03-18 | Z | 2025-02-28 | 30 | 0 | 0 |  | 30 | 50 |  | L2-TA |  | 18
2025-03-14 | 1106 | sp | 70427 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2025-03-18 | Z | 2025-02-28 | 140 | 100 | 0 |  | 0 | 250 |  | Flex add on |  | 18
2025-03-14 | 1107 |  | 70428 - 70429 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-03-18 | Z | 2025-02-28 | 40 | 0 | 0 |  | 40 | 60 |  | L2/L3-TA |  | 18
2025-03-14 | 1110 |  | 66888 | A | DONE | 12 | M |  | UWRF 6230010 |  | 2025-03-18 | Z | 2025-03-06 | 300 | 0 | 0 |  | 0 | 710 |  | LOUVER |  | 12
2025-03-14 | 1111 |  | 66889 | A | DONE | 8 | M |  | UWRF 6230010 |  | 2025-03-18 | Z | 2025-03-06 | 180 | 0 | 0 |  | 0 | 530 |  | LOUVER |  | 12
2025-03-13 | 1115 |  | 66893 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2025-03-18 | Z | 2025-03-06 | 180 | 0 | 0 |  | 0 | 250 |  | TRIM |  | 12
2025-03-14 | 1116 |  | 70436 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-03-18 | Z | 2025-03-06 | 20 | 0 | 0 |  | 0 | 20 |  | CEILING TIE IN |  | 12
2025-03-11 | 1117 |  | 66894 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2025-03-11 | Z | 2025-03-06 | 90 | 0 | 0 |  | 0 | 280 |  | AHU-18-Remake |  | 5
2025-03-11 | 3237 |  | 81148 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-03-11 | Z | 2025-02-20 | 40 | 0 | 0 |  | 0 | 60 |  | 2ND FLOOR |  | 19
2025-03-11 | 3240 |  | 81150 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-03-11 | Z | 2025-02-28 | 20 | 0 | 0 |  | 0 | 30 |  | 4th Fl VRF |  | 11
2025-03-11 | 3241 |  | 81252 | A | DONE | 16 | M |  | UWSP ALBERTSON 6230016 |  | 2025-03-11 | Z | 2025-02-28 | 380 | 0 | 0 |  | 0 | 540 |  | 2nd Fl |  | 11
2025-03-11 | 3242 |  | 81253 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-03-11 | Z | 2025-02-28 | 40 | 0 | 0 |  | 0 | 60 |  | 2nd Fl RA |  | 11
2025-03-13 | 3244 |  | 81256 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-03-18 | Z | 2025-03-04 | 20 | 0 | 0 |  | 0 | 20 |  | 1st Fl |  | 14
2025-03-12 | 2794 |  | 70150 | A | DONE | 5 | S-M |  | UWSP CHAMPION 6240008 |  | 2025-03-13 | Z | 2025-03-06 | 120 | 0 | 0 |  | 0 | 400 |  | TEST CAPS |  | 7
2025-03-13 | 2795 |  | 58823-25 | A | DONE | 4 | S-M |  | UWSP CHAMPION 6240008 |  | 2025-03-13 | Z | 2025-03-06 | 100 | 0 | 0 |  | 30 | 130 |  | Misc |  | 7
2025-03-12 | 2796 |  | 70156 | A | DONE | 2 | S |  | UWSP CHAMPION 6240008 |  | 2025-03-13 | Z | 2025-03-10 | 50 | 0 | 0 |  | 0 | 80 |  | AHU-22 RA |  | 3
2025-03-13 | 2797 |  | 70157 | A | DONE | 2 | S |  | UWSP CHAMPION 6240008 |  | 2025-03-13 | Z | 2025-03-11 | 20 | 0 | 0 |  | 0 | 20 |  | PRV-1 EA |  | 2
2025-03-13 | 2016 |  | RA - 1(7) | A | DONE | 13 | S |  | UW-VET MED 6210014 | bird s. , flex | 2025-03-13 | Z | 2025-03-03 | 140 | 0 | 170 | F | 0 | 370 |  |  |  | 10
2025-03-13 | 1188 |  | 79811 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-14 | Z | 2025-03-10 | 60 | 0 | 0 |  | 0 | 90 |  | Misc |  | 4
2025-03-14 | 1285 |  | 82219 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2025-03-18 | Z | 2025-03-11 | 20 | 0 | 0 |  | 0 | 20 |  | W. DOAS |  | 7
2025-03-14 | 1286 |  | 82220 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2025-03-18 | Z | 2025-03-12 | 40 | 0 | 0 |  | 0 | 60 |  | DOAS outs |  | 6
2025-03-11 | 1990 | sp | 71500 | A | DONE | 7 | S |  | WSCC 6240006 |  | 2025-03-13 | Z | 2025-03-06 | 20 | 140 | 0 |  | 0 | 170 |  | FAN-09 |  | 7
2025-03-13 | 1992 |  | 84276 | A | DONE | 2 | S | ss | WSCC 6240006 |  | 2025-03-13 | Z | 2025-03-12 | 20 | 0 | 0 |  | 0 | 20 |  | Cover |  | 1
2025-03-13 | 1901r |  | 80866 | A | DONE | 3 | S-M | neal | WSCC 6240006 |  | 2025-03-13 | Z | 2025-03-12 | 70 | 0 | 0 |  | 60 | 220 |  | RTU-01 |  | 1
[6 empty] | 807 | [13 empty] | 25900 |  |  |  | 11400 | 44.02%
WEEK OF 3-17-2025
2025-03-19 | 1742 |  | 81967 - 81969 | A | DONE | 14 | M-L |  | 121 E. WILSON 6230024 | flex | 2025-03-20 | Z | 2025-03-06 | 350 | 0 | 0 |  | 0 | 1060 |  | FC-DROPS & Flex |  | 14
2025-03-18 | 1744 |  | 81974 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 |  | 2025-03-19 | Z | 2025-03-14 | 100 | 0 | 0 |  | 0 | 100 |  | EF DROPS |  | 5
2025-03-18 | 1745 |  | 81983-84 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-03-19 | Z | 2025-03-17 | 20 | 0 | 0 |  | 0 | 20 |  | L13 / Louver |  | 2
2025-03-17 | 2471 |  | 81622 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-03-19 | Z | 2025-03-14 | 20 | 0 | 0 |  | 0 | 20 |  | COVERS |  | 5
2025-03-21 | 844 | sp | 70789 | N/A | DONE | 22 | M |  | DELLSHIRE 6240017 | spiral & elbows only | 2025-03-24 | Z | 2025-03-05 | 0 | 550 | 0 |  | 0 | 500 |  | 1st Floor EA B |  | 19
2025-03-21 | 845 | bth | 70790 , 70792 - 93 | A | DONE | 21 | S-M |  | DELLSHIRE 6240017 | VD | 2025-03-24 | Z | 2025-03-05 | 290 | 60 | 190 | F | 0 | 490 |  | VAV 3-7 A |  | 19
2025-03-21 | 846 | bth | 70794 - 70796 | A | DONE | 19 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-24 | Z | 2025-03-05 | 250 | 190 | 20 | F | 0 | 440 |  | HP SA |  | 19
2025-03-21 | 848 |  | 73851 - 73852 | A | DONE | 5 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-24 | Z | 2025-03-10 | 30 | 90 | 0 |  | 0 | 110 |  | VAV 3-3 ,3-4 |  | 14
2025-03-20 | 849 |  | 70797 | A | DONE | 2 | S | pcd | DELLSHIRE 6240017 |  | 2025-03-24 | Z | 2025-03-10 | 20 | 0 | 0 |  | 0 | 30 |  | Basement |  | 14
2025-03-21 | 850 |  | 70798 | A | DONE | 3 | S |  | DELLSHIRE 6240017 |  | 2025-03-24 | Z | 2025-03-10 | 20 | 40 | 0 |  | 0 | 60 |  | VAV 3-3 1st floor |  | 14
2025-03-20 | 851 |  | 73854 | A | DONE | 10 | S |  | DELLSHIRE 6240017 | 1"liner | 2025-03-24 | Z | 2025-03-14 | 130 | 0 | 0 |  | 120 | 140 |  | SHAFT |  | 10
2025-03-17 | 857 | bth | 70777-78 | delete |  | 0 | M | pcd | DELLSHIRE 6240017 |  | 2025-03-31 | Z | 2025-03-14 | 0 | 0 | 0 |  | 0 | 0 |  | EF-2,3 |  | 17
2025-03-19 | 189 |  | 73653 | A | DONE | 2 | S |  | EGENESIS 2250004 |  | 2025-03-18 | Z | 2025-03-18 | 20 | 0 | 0 |  | 0 | 20 |  | PIPE CLAMPS |  | 0.5
2025-03-18 | 1219 |  | 56803 | A | DONE | 2 | S |  | ES BIO 2250001 |  | 2025-03-20 | Z | 2025-03-14 | 12 | 0 | 0 |  | 0 | 30 |  | CEILING FINISH |  | 6
2025-03-20 | 1220 |  | 83269 | A | DONE | 2 | S |  | ES CHARMANY 6240009 |  | 2025-03-21 | Z | 2025-03-14 | 30 | 0 | 0 |  | 0 | 30 |  | EXHAUST |  | 7
2025-03-20 | 1218 | sp | 79150 | A | DONE | 2 | S-M | pcd | EXACT TL-2 2250003 | s.mates , quick clamp | 2025-03-20 | Z | 2025-03-13 | 20 | 30 | 0 |  | 0 | 60 |  | CRAH |  | 7
2025-03-19 | 1221 | bth | 69624,27,30 | A | DONE | 19 | S-M |  | EXACT-MRD 2250009 |  | 2025-03-20 | Z | 2025-03-18 | 140 | 170 | 160 | F | 0 | 650 |  | MISC |  | 2
2025-03-17 | 452 |  | 55124 | A | DONE | 24 | M-L |  | KIKKOMAN 6240041 |  | 2025-03-19 | Z | 2025-03-07 | 600 | 0 | 0 |  | 0 | 1050 |  | Curb Caps |  | 12
2025-03-17 | 453 |  | 55123A | A | DONE | 70 | L |  | KIKKOMAN 6240041 |  | 2025-03-19 | Z | 2025-03-10 | 1740 | 0 | 0 |  | 0 | 2850 |  | Curb Caps |  | 9
2025-03-20 | 2944 |  | 82578 | A | DONE | 2 | S |  | LABCORP 6240016 | paint | 2025-03-24 | Z | 2025-03-20 | 20 | 0 | 0 |  | 10 | 20 |  | 3RD FL-EB |  | 4
2025-03-18 | 2663 | w | 78787 | A | DONE | 2 | S-M |  | MONROE HS 6240018 |  | 2025-03-20 | Z | 2025-03-05 | 30 | 0 | 0 |  | 0 | 50 |  | Sleeves |  | 15
2025-03-19 | 3990 |  | 83103 | A | DONE | 4 | S-M |  | PECATONICA ES 6240005 | 2" liner | 2025-03-20 | Z | 2025-01-30 | 90 | 0 | 0 |  | 80 | 170 |  | AHU-4 SA |  | 49
2025-03-18 | 3991 | sp | 83104 | A | DONE | 11 | S-M |  | PECATONICA ES 6240005 | oval , accuflange | 2025-03-20 | Z | 2025-01-30 | 50 | 220 | 0 |  | 0 | 320 |  | AHU-4 SA |  | 49
2025-03-19 | 3992 | sp | 83105 - 83107 | A | DONE | 11 | S-M |  | PECATONICA ES 6240005 |  | 2025-03-20 | Z | 2025-01-30 | 100 | 160 | 0 |  | 0 | 260 |  | AHU-4 SA VAV inlet |  | 49
2025-03-20 | 191 |  | 79947 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-03-24 | Z | 2025-03-20 | 20 | 0 | 0 |  | 0 | 20 |  | A-COLLARS |  | 4
2025-03-21 | 2590 |  | 37568 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-03-24 | Z | 2025-03-18 | 20 | 0 | 0 |  | 0 | 30 |  | MISC |  | 6
2025-03-21 | 4793 | sp | 85306 | A | DONE | 2 | S | alum | ROCK CO. JAIL 6220018 |  | 2025-03-24 | Z | 2025-03-17 | 10 | 40 | 0 |  | 0 | 20 |  | SHOWER |  | 7
2025-03-18 | 635 |  | 83263 - 83265 | A | DONE | 20 | M |  | UW-BIO CHEM 6240036 | flex , MOD's | 2025-03-20 | Z | 2025-03-07 | 400 | 0 | 80 | F | 0 | 570 |  | AHU 9 |  | 13
2025-03-21 | 636 |  | 83270 | A | DONE | 2 | S |  | UW-BIO CHEM 6240036 |  | 2025-03-21 | Z | 2025-03-20 | 20 | 0 | 0 |  | 0 | 20 |  | BSEC |  | 1
2025-03-20 | 2472 |  | 81623 | A | DONE | 2 | S | neal | UW-CDIS 6220028 |  | 2025-03-25 | Z | 2025-03-18 | 10 | 0 | 30 | F | 0 | 50 |  | 1ST |  | 7
2025-03-17 | 380 |  | 83936 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-18 | Z | 2025-02-28 | 20 | 0 | 0 |  | 0 | 30 |  | L1 EAMP 11 Mech Rm. |  | 18
2025-03-17 | 381 |  | 83938 - 83939 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-18 | Z | 2025-02-28 | 90 | 0 | 0 |  | 70 | 180 |  | L1 SAMP 9 Mech Rm. |  | 18
2025-03-17 | 382 | bth | L2-SAMP 1 | A | DONE | 27 | M-L |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-18 | Z | 2025-03-03 | 280 | 40 | 340 | F | 0 | 1210 |  |  |  | 15
2025-03-18 | 383 |  | L2-SAMP 3 | A | DONE | 60 | M-L |  | UW-LEVY HALL 6230028 | 1" DW | 2025-03-18 | Z | 2025-03-03 | 850 | 0 | 630 | F | 760 | 3100 |  |  |  | 15
2025-03-18 | 384 | bth | L2-SAMP 4 | A | DONE | 14 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-18 | Z | 2025-03-03 | 220 | 40 | 80 | F | 240 | 550 |  |  |  | 15
2025-03-17 | 385 | bth | L2-SAMP 5 | A | DONE | 30 | M |  | UW-LEVY HALL 6230028 |  | 2025-03-18 | Z | 2025-03-03 | 330 | 120 | 280 | F | 0 | 960 |  |  |  | 15
2025-03-18 | 386 | bth | L2-SAMP 6 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-18 | Z | 2025-03-03 | 260 | 20 | 160 | F | 330 | 740 |  |  |  | 15
2025-03-18 | 387 | bth | L2-SAMP 7 | A | DONE | 20 | M |  | UW-LEVY HALL 6230028 |  | 2025-03-18 | Z | 2025-03-03 | 320 | 30 | 150 | F | 0 | 670 |  |  |  | 15
2025-03-18 | 388 | bth | L2-SAMP 8 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-03-18 | Z | 2025-03-03 | 240 | 40 | 50 | F | 0 | 400 |  |  |  | 15
2025-03-18 | 389 | bth | L2-RAMP 10 | A | DONE | 20 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-18 | Z | 2025-03-03 | 280 | 60 | 140 | F | 90 | 740 |  |  |  | 15
2025-03-18 | 390 | bth | L2-RAMP 11 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-18 | Z | 2025-03-03 | 180 | 20 | 230 | F | 40 | 650 |  |  |  | 15
2025-03-18 | 391 | bth | L2-RAMP 12 | A | DONE | 21 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-20 | Z | 2025-03-03 | 130 | 20 | 360 | F | 80 | 810 |  |  |  | 17
2025-03-18 | 392 | bth | L2-RAMP 13 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-20 | Z | 2025-03-03 | 170 | 20 | 260 | F | 60 | 690 |  |  |  | 17
2025-03-19 | 393 | bth | L2-RAMP 14 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-20 | Z | 2025-03-03 | 110 | 30 | 40 | F | 60 | 250 |  |  |  | 17
2025-03-19 | 394 |  | L2-RAMP 15 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-03-20 | Z | 2025-03-03 | 320 | 0 | 150 | F | 370 | 710 |  |  |  | 17
2025-03-19 | 395 | bth | L2-RAMP 16 | A | DONE | 16 | M |  | UW-LEVY HALL 6230028 | s. mates , 1" liner | 2025-03-20 | Z | 2025-03-03 | 160 | 170 | 60 | F | 50 | 530 |  |  |  | 17
2025-03-21 | 397 |  | L2-RAMP 2 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-25 | Z | 2025-03-03 | 270 | 0 | 190 | F | 30 | 770 |  |  |  | 22
2025-03-21 | 401 |  | L2-RAMP 6 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | VD's | 2025-03-25 | Z | 2025-03-03 | 190 | 0 | 70 | F | 0 | 390 |  |  |  | 22
2025-03-17 | 447 |  | 83942 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | flex | 2025-03-18 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 20 |  | LL EF-1 |  | 11
2025-03-21 | 728 |  | 83944 | A | DONE | n/a | S |  | UW-LEVY HALL 6230028 |  | 2025-03-25 | Z | 2025-03-12 | 0 | 0 | 0 |  | 0 | 0 |  | DM Frames |  | 13
2025-03-21 | 729 | sp | 83945 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-25 | Z | 2025-03-12 | 10 | 40 | 0 |  | 0 | 50 |  | L1 Misc |  | 13
2025-03-20 | 3177 |  | 84635 - 84638 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 | VD | 2025-03-24 | Z | 2025-03-12 | 110 | 0 | 20 | F | 0 | 190 |  | 3rd RA SO |  | 12
2025-03-20 | 3178 | bth | 84639 - 84640 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2025-03-24 | Z | 2025-03-12 | 60 | 20 | 0 |  | 0 | 120 |  | 3rd RA SO |  | 12
2025-03-17 | 1104 |  | 70422 - 70424 | A | DONE | 3 | S-M |  | UWRF 6230010 | paint , flex , 1" liner | 2025-03-18 | Z | 2025-02-28 | 70 | 0 | 0 |  | 60 | 100 |  | L3-TA |  | 18
2025-03-17 | 1108 |  | 70433 | A | DONE | 2 | S |  | UWRF 6230010 | flex , 1" liner | 2025-03-18 | Z | 2025-03-05 | 30 | 0 | 0 |  | 20 | 50 |  | TA Finishes |  | 13
2025-03-17 | 1109 |  | 70434 | A | DONE | 2 | S |  | UWRF 6230010 | flex | 2025-03-18 | Z | 2025-03-05 | 20 | 0 | 0 |  | 0 | 20 |  | TA Finishes |  | 13
2025-03-17 | 1112 |  | 66890 | A | DONE | 6 | S-M |  | UWRF 6230010 |  | 2025-03-18 | Z | 2025-03-06 | 150 | 0 | 0 |  | 0 | 360 |  | LOUVER |  | 12
2025-03-17 | 1113 |  | 66891 | A | DONE | 6 | S-M |  | UWRF 6230010 |  | 2025-03-18 | Z | 2025-03-06 | 130 | 0 | 0 |  | 0 | 320 |  | LOUVER |  | 12
2025-03-17 | 1114 |  | 66892 | A | DONE | 12 | M |  | UWRF 6230010 |  | 2025-03-18 | Z | 2025-03-06 | 290 | 0 | 0 |  | 0 | 630 |  | LOUVER |  | 12
2025-03-20 | 1118 |  | 70437 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-03-25 | Z | 2025-03-11 | 20 | 0 | 0 |  | 10 | 20 |  | L3 GE |  | 14
2025-03-21 | 1119 |  | 70438 - 70440 | A | DONE | 4 | S-M | pcd | UWRF 6230010 |  | 2025-03-25 | Z | 2025-03-11 | 80 | 0 | 0 |  | 0 | 120 |  | L2 FE |  | 14
2025-03-21 | 1120 |  | 70441 - 70443 | A | DONE | 4 | S-M | pcd | UWRF 6230010 |  | 2025-03-25 | Z | 2025-03-11 | 100 | 0 | 0 |  | 0 | 160 |  | L2/L3 FE |  | 14
2025-03-20 | 1122 |  | 66895 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2025-03-25 | Z | 2025-03-12 | 200 | 0 | 0 |  | 0 | 330 |  | OA Trim |  | 13
2025-03-21 | 1123 |  | 66896 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2025-03-25 | Z | 2025-03-12 | 250 | 0 | 0 |  | 0 | 750 |  | RA out |  | 13
2025-03-20 | 1125 |  | 70449 - 70450 | A | DONE | 4 | S-M |  | UWRF 6230010 | paint , flex | 2025-03-25 | Z | 2025-03-13 | 80 | 0 | 0 |  | 10 | 100 |  | 2nd Floor Tie ins |  | 12
2025-03-21 | 1129 |  | 84808 | A | DONE | 2 | S | alum | UWRF 6230010 |  | 2025-03-25 | Z | 2025-03-18 | 20 | 0 | 0 |  | 0 | 20 |  | RM 324A |  | 7
2025-03-20 | 3245 |  | 81258 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-03-25 | Z | 2025-03-06 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd FL |  | 19
2025-03-19 | 2798 |  | 70158-59 | A | DONE | 3 | S |  | UWSP CHAMPION 6240008 |  | 2025-03-20 | Z | 2025-03-14 | 60 | 0 | 0 |  | 0 | 100 |  | PRV-5,7 |  | 6
2025-03-20 | 2799 |  | 70160-61 | A | DONE | 24 | S-M |  | UWSP CHAMPION 6240008 |  | 2025-03-25 | Z | 2025-03-14 | 530 | 0 | 60 | F | 0 | 990 |  | AHU-21 |  | 11
2025-03-19 | 4400 | sp | 58826 | A | DONE | 2 | S |  | UWSP CHAMPION 6240008 |  | 2025-03-20 | Z | 2025-03-17 | 20 | 0 | 0 |  | 0 | 30 |  | 1ST FL-OUT |  | 3
2025-03-20 | 1196 |  | 79814 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-21 | Z | 2025-03-12 | 60 | 0 | 0 |  | 0 | 90 |  | 2nd G EA |  | 9
2025-03-21 | 1197 | w | 79868 | A | DONE | 7 | M |  | WAUNAKEE MS 6230013 | 1"db | 2025-03-21 | Z | 2025-03-14 | 90 | 0 | 0 |  | 70 | 240 |  | Curb Ext |  | 7
2025-03-20 | 4113 | bth | L01_G_SALP-001 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 40 | 20 | 50 | F | 0 | 110 |  |  |  | 49
2025-03-19 | 4114 | sp | L01_G_SALP-002 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-21 | Z | 2025-01-31 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 49
2025-03-19 | 4115 | bth | L01_G_SALP-003 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 50 | 60 | 0 |  | 0 | 110 |  |  |  | 49
2025-03-19 | 4116 | bth | L01_G_SALP-004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 50 | 50 | 0 |  | 0 | 100 |  |  |  | 49
2025-03-19 | 4117 |  | L01_G_SALP-005 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 49
2025-03-20 | 4118 | bth | L01_G_SALP-006 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 40 | 80 | 0 |  | 0 | 120 |  |  |  | 49
2025-03-20 | 4119 | bth | L01_G_SALP-007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 30 | 60 | 30 | F | 0 | 110 |  |  |  | 49
2025-03-19 | 4120 | bth | L01_G_SALP-008 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 40 | 40 | 70 | F | 0 | 170 |  |  |  | 49
2025-03-19 | 4121 | bth | L01_G_SALP-009 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 30 | 140 | 0 |  | 0 | 180 |  |  |  | 49
2025-03-19 | 4122 |  | L01_G_SALP-010 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 70 | 0 | 0 |  | 0 | 120 |  |  |  | 49
2025-03-19 | 4123 | sp | L01_G_SALP-011 | A | DONE | 8 | S | neal | WAUNAKEE MS 6230013 | VD , flex | 2025-03-21 | Z | 2025-01-31 | 70 | 120 | 0 |  | 0 | 220 |  |  |  | 49
2025-03-19 | 4124 | sp | L01_G_SALP-012 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 49
2025-03-19 | 4125 | bth | L01_G_SALP-013 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 110 | 40 | 50 | F | 0 | 240 |  |  |  | 49
2025-03-20 | 4126 | sp | L01_G_SALP-014 | A | DONE | 9 | S-M | neal | WAUNAKEE MS 6230013 | VD , flex | 2025-03-21 | Z | 2025-01-31 | 70 | 140 | 0 |  | 0 | 270 |  |  |  | 49
2025-03-19 | 4127 |  | L01_G_SALP-015 | A | DONE | 5 | S | neal | WAUNAKEE MS 6230013 | VD , flex | 2025-03-21 | Z | 2025-01-31 | 60 | 0 | 50 | F | 0 | 150 |  |  |  | 49
2025-03-20 | 4128 | sp | L01_G_SALP-016 | A | DONE | 10 | S-M | neal | WAUNAKEE MS 6230013 | VD , flex | 2025-03-21 | Z | 2025-01-31 | 70 | 160 | 0 |  | 0 | 280 |  |  |  | 49
2025-03-20 | 4129 | sp | L01_G_SALP-017 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 49
2025-03-19 | 4130 |  | L01_G_RAD-001 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-03-21 | Z | 2025-01-31 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 49
2025-03-19 | 4131 |  | L01_G_RAD-002 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 49
2025-03-19 | 4132 |  | L01_G_RAD-003 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 49
2025-03-19 | 4133 |  | L01_G_RAD-004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 60 | 0 | 40 | F | 90 | 150 |  |  |  | 49
2025-03-19 | 4134 |  | L01_G_RAD-005 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 49
2025-03-19 | 4135 |  | L01_G_RAD-006 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 49
2025-03-19 | 4136 |  | L01_G_RAD-007 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 49
2025-03-19 | 4137 |  | L01_G_RAD-008 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 20 | 0 | 0 |  | 10 | 30 |  |  |  | 49
2025-03-19 | 4138 |  | L01_G_RAD-009 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 70 | 0 | 0 |  | 60 | 100 |  |  |  | 49
2025-03-20 | 4139 | bth | L01_G_RAD-010 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 10 | 20 | 0 |  | 30 | 40 |  |  |  | 49
2025-03-19 | 4140 |  | L01_G_RAD-011 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 49
2025-03-19 | 4141 |  | L01_G_RAD-012 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 60 | 0 | 0 |  | 50 | 70 |  |  |  | 49
2025-03-19 | 4142 |  | L01_G_RAD-013 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 49
2025-03-20 | 4143 |  | L01_G_RAD-014 | A | DONE | 15 | S-M | neal | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 130 | 0 | 80 | F | 160 | 300 |  |  |  | 49
2025-03-20 | 4144 |  | L01_G_RAD-015 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 49
2025-03-20 | 4145 | bth | L01_G_RAD-016 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-03-21 | Z | 2025-01-31 | 40 | 30 | 0 |  | 10 | 70 |  |  |  | 49
[6 empty] | 893 | [13 empty] | 31150 |  |  |  | 10200 | 32.74%
WEEK OF 3-24-2025
2025-03-24 | 250 |  | 81987 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-03-25 | Z | 2025-03-20 | 40 | 0 | 0 |  | 0 | 70 |  | EF DROP |  | 6
2025-03-27 | 1738 | sp | 81965 - 81966 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 | BDD , bird s. , 1" liner | 2025-03-25 | Z | 2025-02-27 | 250 | 120 | 0 |  | 60 | 510 |  | Fan curb cap / g. neck |  | 26 | 2025-03-11
2025-04-28 | 1746 | sp | 81976 | A | DONE | 7 | S |  | 121 E. WILSON 6230024 |  | 2025-03-31 | Z | 2025-03-17 | 20 | 150 | 0 |  | 0 | 150 |  | BOILER |  | 14
2025-03-27 | 1748 |  | 81982 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 |  | 2025-03-31 | Z | 2025-03-17 | 100 | 0 | 0 |  | 0 | 320 |  | FC INTAKE Plenum |  | 14
2025-03-24 | 3947 | m | 81927 | A | DONE | 5 | S |  | 121 E. WILSON 6230024 |  | 2025-03-25 | Z | 2025-03-19 | 20 | 90 | 0 |  | 0 | 100 |  | MISSING |  | 6
2025-03-24 | 190 |  | 31925 | A | DONE | 2 | S |  | AYERS 20009458 |  | 2025-03-25 | Z | 2025-03-20 | 30 | 0 | 0 |  | 20 | 30 |  | Filter Racks |  | 5
2025-04-28 | 193 | bth | 74003 | A | DONE | 2 | S |  | DANE CO. AIRPORT 4250007 | paint | 2025-03-31 | Z | 2025-03-25 | 20 | 20 | 0 |  | 20 | 40 |  | Misc |  | 6
2025-04-28 | 852 | sp | 70729 | A | DONE | 17 | S-M |  | DELLSHIRE 6240017 | flex | 2025-03-31 | Z | 2025-03-14 | 20 | 400 | 0 |  | 0 | 380 |  | 2ND FL-EG-12 |  | 17
2025-04-28 | 853 |  | 73853,55 | A | DONE | 12 | S-M |  | DELLSHIRE 6240017 | flex | 2025-03-31 | Z | 2025-03-14 | 160 | 0 | 130 | F | 0 | 360 |  | 1ST FL -RA |  | 17
2025-04-28 | 854 | w | 73652,73652.1 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-03-31 | Z | 2025-03-14 | 20 | 0 | 0 |  | 0 | 40 |  | MECH RM SLEEVES |  | 17
2025-04-28 | 858 |  | 70742 | A | DONE | 6 | S | pcd | DELLSHIRE 6240017 |  | 2025-03-31 | Z | 2025-03-17 | 70 | 0 | 80 | F | 0 | 170 |  | ACIID/CHEM RM |  | 14
2025-04-28 | 859 | sp | 70743 | A | DONE | 6 | S |  | DELLSHIRE 6240017 |  | 2025-03-31 | Z | 2025-03-17 | 20 | 110 | 0 |  | 0 | 140 |  | EF-2 |  | 14
2025-04-28 | 860 | sp | 73856 | A | DONE | 4 | S |  | DELLSHIRE 6240017 |  | 2025-03-31 | Z | 2025-03-18 | 20 | 60 | 0 |  | 0 | 60 |  | BASEMENT |  | 13
2025-04-28 | 861 | sp | 73858 | A | DONE | 8 | S-M |  | DELLSHIRE 6240017 |  | 2025-03-31 | Z | 2025-03-20 | 90 | 90 | 0 |  | 0 | 200 |  | BASEMENT |  | 11
2025-03-24 | 1225 |  | 69632 | A | DONE | 2 | S |  | EXACT MRD 2250009 |  | 2025-03-25 | Z | 2025-03-24 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 1
2025-03-26 | 1226 |  | 79033 | A | DONE | 2 | S |  | EXACT MRD 2250009 |  | 2025-03-27 | Z | 2025-03-25 | 20 | 0 | 0 |  | 0 | 20 |  | RA |  | 2
2025-03-26 | 1227 |  | 69637 - 69639 | A | DONE | 16 | S-M |  | EXACT MRD 2250009 |  | 2025-03-28 | Z | 2025-03-25 | 270 | 0 | 130 |  | 0 | 600 |  | BCU - 2826 |  | 3
2025-03-26 | 1223 | bth | 79030-31 | A | DONE | 7 | M | pcd | EXACT TL-2 2250003 |  | 2025-03-27 | Z | 2025-03-20 | 80 | 100 | 0 |  | 0 | 240 |  | CRAH EAST/WEST |  | 7
2025-02-25 | 1222 |  | 79029 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-03-27 | Z | 2025-03-20 | 20 | 0 | 0 |  | 0 | 30 |  | SA TIE INS |  | 7
2025-02-25 | 1224 |  | 79032 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-03-27 | Z | 2025-03-20 | 30 | 0 | 0 |  | 0 | 40 |  | EA-1810-2 |  | 7
2025-03-26 | 454 |  | 55125 - 55126 | A | DONE | 23 | L |  | KIKKOMAN 6240041 |  | 2025-03-28 | Z | 2025-03-10 | 580 | 0 | 0 |  | 0 | 1080 |  | Fan Caps |  | 18
2025-03-26 | 455 |  | 55127 | A | DONE | 10 | M |  | KIKKOMAN 6240041 |  | 2025-03-28 | Z | 2025-03-10 | 230 | 0 | 0 |  | 0 | 470 |  | Hood Caps |  | 18
2025-03-26 | 453A |  | 55123B | A | DONE | 69 | M |  | KIKKOMAN 6240041 |  | 2025-03-28 | Z | 2025-03-11 | 1720 | 0 | 0 |  | 0 | 3070 |  | Curb Caps |  | 17
2025-03-27 | 3993 |  | 83108 | A | DONE | 2 | S |  | PECATONICA ES 6240005 |  | 2025-03-31 | Z | 2025-01-30 | 50 | 0 | 0 |  | 0 | 50 |  | VAV Transitions |  | 60
2025-04-28 | 3994 |  | 83109 | A | DONE | 4 | S |  | PECATONICA ES 6240005 | 2" liner | 2025-03-31 | Z | 2025-01-30 | 50 | 0 | 40 | F | 70 | 100 |  | V-28 LPSA |  | 60
2025-04-28 | 3995 |  | 83110 | A | DONE | 3 | S |  | PECATONICA ES 6240005 | paint , VD's | 2025-03-31 | Z | 2025-01-30 | 70 | 0 | 0 |  | 20 | 100 |  | Lined to unlined transitions |  | 60
2025-04-28 | 3996 | sp | 83111 | A | DONE | 8 | S-M | neal | PECATONICA ES 6240005 |  | 2025-03-31 | Z | 2025-01-30 | 40 | 140 | 0 |  | 0 | 210 |  | V-28 Exposed SA |  | 60
2025-04-28 | 3997 |  | 83112 - 83113 | A | DONE | 12 | S-M |  | PECATONICA ES 6240005 | 2" liner | 2025-03-31 | Z | 2025-01-30 | 50 | 0 | 240 | F | 260 | 290 |  | V-29 LPSA |  | 60
2025-04-28 | 3998 | sp | 83114 - 83115 | A | DONE | 7 | S-M |  | PECATONICA ES 6240005 |  | 2025-03-31 | Z | 2025-01-30 | 20 | 150 | 0 |  | 0 | 150 |  | V-29 , 31 LPSA |  | 60
2025-03-26 | 2591 |  | 62722 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-03-27 | Z | 2025-03-25 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2025-03-27 | 4794 |  | 33245 | A | DONE | 2 | S | d.plate | ROCK CO. JAIL 8220022 |  | 2025-03-31 | Z | 2025-03-24 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2025-03-27 | 1412 |  | 68460 | A | DONE | 2 | S | ss | SPH SURGERY 6240039 |  | 2025-03-31 | Z | 2025-03-11 | 40 | 0 | 0 |  | 0 | 60 |  | EF Drops |  | 20
2025-03-27 | 2403 |  | 80049 | A | DONE | 6 | S |  | ST.BERNARD 6230023 | 1"liner | 2025-03-31 | Z | 2025-03-18 | 70 | 0 | 60 | F | 120 | 140 |  | TRANS-SA |  | 13
2025-03-27 | 2404 |  | 79949 - 79950 | A | DONE | 2 | S |  | ST.BERNARD 6230023 |  | 2025-03-31 | Z | 2025-03-24 | 30 | 0 | 0 |  | 20 | 40 |  | Misc |  | 7
2025-03-26 | 2844 |  | 67754 - 67755 | A | DONE | 47 | M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-03-27 | Z | 2025-03-13 | 600 | 0 | 0 |  | 590 | 700 |  | B-Section |  | 14
2025-03-26 | 2846 |  | 67759 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | 1"liner | 2025-03-27 | Z | 2025-03-21 | 20 | 0 | 0 |  | 0 | 20 |  | 2ND FLOOR |  | 6
2025-02-25 | 4320 | sp | L5C-SAT 501 | A | DONE | 10 | S-M |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 50 | 190 | 0 |  | 0 | 240 |  |  |  | 19
2025-02-25 | 4321 | bth | L5C-SAT 504-4 | A | DONE | 5 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 30 | 60 | 30 | F | 0 | 130 |  |  |  | 19
2025-02-25 | 4322 | bth | L5C-SAT 504-5 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 40 | 70 | 30 | F | 0 | 140 |  |  |  | 19
2025-02-25 | 4323 | bth | L5C-SAT 504-6 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 30 | 90 | 30 | F | 0 | 150 |  |  |  | 19
2025-03-26 | 4324 | sp | L5C-SAT 543 | A | DONE | 4 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 19
2025-02-25 | 4325 | bth | L5C-SAT 550.2 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 40 | 30 | 80 | F | 0 | 170 |  |  |  | 19
2025-02-25 | 4326 | bth | L5C-SAT 550.3 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 60 | 80 | 0 |  | 0 | 150 |  |  |  | 19
2025-03-26 | 4327 | sp | L5C-SAT 551-1 | A | DONE | 4 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 30 | 70 | 0 |  | 0 | 90 |  |  |  | 19
2025-02-25 | 4328 |  | L5C-SAT 551-2 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 19
2025-03-26 | 4329 | bth | L5C-SAT 553-1 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 50 | 90 | 0 |  | 0 | 140 |  |  |  | 19
2025-03-26 | 4330 | bth | L5C-SAT 553-2 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 50 | 40 | 50 | F | 0 | 160 |  |  |  | 19
2025-02-25 | 4331 |  | L5C-SAT 553A | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 19
2025-03-26 | 4332 | bth | L5C-SAT 553B | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 19
2025-03-26 | 4333 |  | L5C-SAT 555A | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 19
2025-03-26 | 4334 | bth | L5C-SAT 555B | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 19
2025-03-26 | 4335 | bth | L5C-SAMP 7 | A | DONE | 24 | M |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 430 | 20 | 130 | F | 0 | 990 |  |  |  | 19
2025-03-26 | 4336 | bth | L5C-SAMP 8 | A | DONE | 11 | S-M |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 50 | 80 | 140 | F | 0 | 300 |  |  |  | 19
2025-03-26 | 4337 | bth | L5C-SAMP 9 | A | DONE | 9 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 150 | 60 | 0 |  | 0 | 240 |  |  |  | 19
2025-03-26 | 4338 | bth | L5C-SAMP 10 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 110 | 20 | 0 |  | 0 | 140 |  |  |  | 19
2025-03-26 | 4339 | bth | L5C-SAMP 11 | A | DONE | 18 | M |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 40 | 120 | 270 | F | 0 | 480 |  |  |  | 19
2025-03-26 | 4340 | sp | L5C-EAT 540-2 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 120 | 0 |  | 0 | 170 |  |  |  | 19
2025-02-25 | 4341 | sp | L5C-EAT 540-3 | A | DONE | 9 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 70 | 150 | 0 |  | 0 | 250 |  |  |  | 19
2025-03-26 | 4342 | sp | L5C-EAT 543 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 19
2025-03-26 | 4343 | sp | L5C-EAT 551-1 | A | DONE | 2 | S | alum | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 19
2025-03-26 | 4344 | bth | L5C-EAT 551-2 | A | DONE | 4 | S | alum | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 30 | 20 | 40 | F | 0 | 50 |  |  |  | 19
2025-03-26 | 4345 | bth | L5C-EAT 553 | A | DONE | 5 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 70 | 20 | 30 | F | 0 | 150 |  |  |  | 19
2025-03-26 | 4346 | sp | L5C-EAT 553A | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 19
2025-03-26 | 4347 | sp | L5C-EAT 555A | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 19
2025-03-26 | 4348 | sp | L5C-EAT 555B | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 19
2025-02-25 | 4349 | sp | L5C-EAT 558 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 20 | 30 | 0 |  | 0 | 30 |  |  |  | 19
2025-03-26 | 4350 | bth | L5C-EAMP 7 | A | DONE | 26 | M |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 270 | 60 | 320 | F | 0 | 900 |  |  |  | 19
2025-02-25 | 4351 | bth | L5C-EAMP 8 | A | DONE | 7 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 50 | 80 | 30 | F | 0 | 160 |  |  |  | 19
2025-03-26 | 4352 | bth | L5C-EAMP 9 | A | DONE | 13 | S-M | pt.alum | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-07 | 130 | 40 | 140 | F | 0 | 310 |  |  |  | 19
2025-03-24 | 4353 |  | 69133 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-17 | 40 | 0 | 0 |  | 0 | 50 |  | SB-EAT-512 |  | 9
2025-02-25 | 4354 | bth | 69134 | A | DONE | 5 | S |  | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-17 | 90 | 30 | 0 |  | 0 | 160 |  | B-OUTS |  | 9
2025-03-26 | 4355 | w | L5B-MECH-EA FAN1 | A | DONE | 10 | S-M | ss | UW-AVRL 6240038 |  | 2025-03-26 | Z | 2025-03-19 | 240 | 10 | 0 |  | 0 | 630 |  |  |  | 7
2025-03-24 | 4356 |  | 69135 | A | DONE | 2 | S |  | UW-AVRL 6240038 | 1"liner | 2025-03-26 | Z | 2025-03-21 | 30 | 0 | 0 |  | 20 | 440 |  | B-TA-7 |  | 5
2025-03-26 | 637 |  | 83271 | A | DONE | 2 | S |  | UW-BIO CHEM 6240036 |  | 2025-03-27 | Z | 2025-03-25 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2025-03-26 | 2473 |  | 81624 | A | DONE | 3 | S |  | UW-CDIS 6220028 | 1"liner | 2025-03-27 | Z | 2025-03-21 | 40 | 20 | 0 |  | 30 | 60 |  | 1-B2-22 |  | 6
2025-03-24 | 379 |  | 83935 | A | DONE | 4 | S-M | neal | UW-LEVY HALL 6230028 | flex,angle ring,1" liner | 2025-03-18 | Z | 2025-02-28 | 80 | 20 | 0 |  | 30 | 150 |  | L1 RAMP 10 Mech Rm. |  | 18
2025-03-24 | 396 | bth | L2-RAMP 1 | A | DONE | 21 | M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-03-25 | Z | 2025-03-03 | 250 | 60 | 150 | F | 80 | 730 |  |  |  | 22
2025-03-24 | 398 | bth | L2-RAMP 3 | A | DONE | 25 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-25 | Z | 2025-03-03 | 120 | 10 | 420 | F | 90 | 790 |  |  |  | 22
2025-03-24 | 399 | bth | L2-RAMP 4 | A | DONE | 23 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-25 | Z | 2025-03-03 | 230 | 10 | 250 | F | 90 | 710 |  |  |  | 22
2025-03-24 | 400 | bth | L2-RAMP 5 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-25 | Z | 2025-03-03 | 210 | 10 | 180 | F | 90 | 550 |  |  |  | 22
2025-03-24 | 402 |  | L2-RAMP 7 | A | DONE | 33 | M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-03-25 | Z | 2025-03-03 | 300 | 0 | 220 | F | 340 | 900 |  |  |  | 22
2025-03-26 | 403 | sp | L2-SAMP 2 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-27 | Z | 2025-03-03 | 20 | 150 | 0 |  | 0 | 180 |  |  |  | 24
2025-03-26 | 404 | bth | L2-SAMP 12 | A | DONE | 13 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-27 | Z | 2025-03-03 | 160 | 70 | 80 | F | 0 | 340 |  |  |  | 24
2025-03-26 | 405 | sp | L2-SAMP 13 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-27 | Z | 2025-03-03 | 20 | 60 | 0 |  | 0 | 90 |  |  |  | 24
2025-03-26 | 406 | sp | L2-SAMP 14 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 |  | 2025-03-27 | Z | 2025-03-03 | 20 | 110 | 0 |  | 0 | 120 |  |  |  | 24
2025-03-27 | 407 |  | L2-SAMP 15 | A | DONE | 104 | L |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-27 | Z | 2025-03-03 | 410 | 0 | 1000 | F | 1190 | 2800 |  |  |  | 24
2025-03-27 | 408 |  | L2-RAMP 8 | A | DONE | 7 | S-M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-03-27 | Z | 2025-03-03 | 120 | 0 | 50 | F | 20 | 310 |  |  |  | 24
2025-03-26 | 409 | bth | L2-RAMP 9 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-27 | Z | 2025-03-03 | 200 | 10 | 50 | F | 40 | 460 |  |  |  | 24
2025-03-27 | 410 | bth | L2-EAMP 1 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-03-27 | Z | 2025-03-03 | 80 | 20 | 20 | F | 20 | 140 |  |  |  | 24
2025-03-24 | 1121 | bth | 70444 - 70447 | A | DONE | 11 | S-M | pcd | UWRF 6230010 |  | 2025-03-25 | Z | 2025-03-11 | 230 | 30 | 0 |  | 0 | 410 |  | L3 FE |  | 14
2025-03-24 | 1124 |  | 70448 | A | DONE | 2 | S-M |  | UWRF 6230010 | 1" liner | 2025-03-25 | Z | 2025-03-13 | 30 | 0 | 0 |  | 20 | 30 |  | 2nd Floor TA |  | 12
2025-03-24 | 3246 | w | 61477,95593 | A | DONE | 2 | M |  | UWSP ALBERTSON 6230016 | 1"DB | 2025-03-25 | Z | 2025-03-06 | 20 | 0 | 0 |  | 10 | 30 |  | ROOF CURB CAP |  | 19
2025-03-24 | 3247 |  | 81260 | A | DONE | 7 | S-M |  | UWSP ALBERTSON 6230016 | paint | 2025-03-25 | Z | 2025-03-10 | 130 | 0 | 0 |  | 30 | 270 |  | 1st Fl Boiler Rm. |  | 15
2025-03-24 | 4401 |  | 70163-64 | A | DONE | 43 | M |  | UWSP CHAMPION 6240008 |  | 2025-03-25 | Z | 2025-03-17 | 640 | 0 | 420 | F | 0 | 2480 |  | AHU-22 |  | 8
2025-03-27 | 4402 |  | 70165 | A | DONE | 8 | S-M |  | UWSP CHAMPION 6240008 |  | 2025-03-27 | Z | 2025-03-19 | 190 | 0 | 0 |  | 0 | 270 |  | AHU-21-OA |  | 8
2025-03-26 | 2021 | bth | 79722-23 | A | DONE | 3 | M |  | UW-VET MED 6210014 |  | 2025-03-27 | Z | 2025-03-14 | 40 | 20 | 0 |  | 0 | 80 |  | 3RD FL |  | 13
2025-03-27 | 952 |  | L01_E_SOA_012 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-02-17 | 70 | 0 | 120 | F | 0 | 250 |  |  |  | 39 | 2025-05-14
2025-03-27 | 953 |  | L01_E_SOA_013 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-02-17 | 90 | 0 | 150 | F | 0 | 420 |  |  |  | 39 | 2025-05-14
2025-03-27 | 1189 |  | PRE-FAB HANGERS | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-03-11 | 40 | 0 | 0 |  | 0 | 170 |  | Tear drops |  | 17
2025-03-27 | 1190 | sp | L01_G_SOA_012 | A | DONE | 13 | S-M | neal | WAUNAKEE MS 6230013 | spiral mate | 2025-03-28 | Z | 2025-03-12 | 0 | 320 | 0 |  | 0 | 450 |  |  |  | 16
2025-03-27 | 1191 | sp | L01_G_SOA_013 | A | DONE | 12 | S-M | neal | WAUNAKEE MS 6230013 | spiral mate | 2025-03-28 | Z | 2025-03-12 | 70 | 220 | 0 |  | 0 | 420 |  |  |  | 16
2025-03-27 | 1192 | sp | L01_G_SALP_018 | A | DONE | 17 | M | neal | WAUNAKEE MS 6230013 | spiral mate | 2025-03-28 | Z | 2025-03-12 | 70 | 350 | 0 |  | 0 | 670 |  |  |  | 16
2025-03-27 | 1193 | sp | L01_G_SALP_019 | A | DONE | 19 | M | neal | WAUNAKEE MS 6230013 | spiral mate | 2025-03-28 | Z | 2025-03-12 | 50 | 410 | 0 |  | 0 | 740 |  |  |  | 16
2025-03-27 | 1194 | sp | L01_G_SALP_020 | A | DONE | 19 | M | neal | WAUNAKEE MS 6230013 | spiral mate | 2025-03-28 | Z | 2025-03-12 | 30 | 430 | 0 |  | 0 | 690 |  |  |  | 16
2025-04-28 | 1195 | sp | L01_G_EAD_014 | A | DONE | 20 | M | neal | WAUNAKEE MS 6230013 | spiral mate | 2025-03-28 | Z | 2025-03-12 | 110 | 380 | 0 |  | 0 | 700 |  |  |  | 16
2025-03-27 | 1198 | w | 79869 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-03-14 | 20 | 0 | 0 |  | 0 | 40 |  | Rail Ext |  | 14
2025-03-24 | 4146 |  | L01_G_TAD-001 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-03-21 | Z | 2025-01-31 | 110 | 0 | 0 |  | 90 | 160 |  |  |  | 49
2025-03-27 | 4159 |  | L02_E_SOA_011 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-02-11 | 20 | 0 | 120 | F | 0 | 200 |  |  |  | 45 | 2025-04-09
2025-03-27 | 4160 |  | L02_E_SOA_012 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-02-11 | 40 | 0 | 120 | F | 0 | 230 |  |  |  | 45 | 2025-04-09
2025-03-27 | 4170 |  | L02_E_EAD_010 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-02-11 | 100 | 0 | 120 | F | 0 | 320 |  |  |  | 45 | 2025-04-09
2025-03-27 | 4171 |  | L02_E_EAD_011 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-02-11 | 50 | 0 | 170 | F | 0 | 350 |  |  |  | 45 | 2025-04-09
2025-03-27 | 4273 |  | L01_E_EAD_012 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-02-17 | 70 | 0 | 100 | F | 0 | 230 |  |  |  | 39 | 2025-05-07
2025-03-27 | 4274 |  | L01_E_EAD_013 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-03-28 | Z | 2025-02-17 | 100 | 0 | 100 | F | 0 | 270 |  |  |  | 39 | 2025-05-07
2025-04-28 | 1287 |  | 82222 | A | DONE | 2 | S |  | WINDSOR 6240012 | paint , flex | 2025-03-31 | Z | 2025-03-25 | 40 | 0 | 0 |  | 40 | 50 |  | Misc outs |  | 6
2025-03-26 | 1988 |  | 66180 - 66181 | A | DONE | 91 | L |  | WSCC 6240006 | S.mates , 2" DW | 2025-03-27 | Z | 2025-03-04 | 1430 | 0 | 0 |  | 830 | 2090 |  | DHU-1 SA / RA |  | 23
2025-03-26 | 1989 |  | 66182 - 66183 | A | DONE | 103 | L |  | WSCC 6240006 | S.mates , 2" DW | 2025-03-27 | Z | 2025-03-04 | 1630 | 0 | 0 |  | 960 | 2300 |  | DHU-2 SA / RA |  | 23
2025-03-26 | 1993 | sp | 66186 | A | DONE | 2 | S |  | WSCC 6240006 | spiral mate | 2025-03-27 | Z | 2025-03-13 | 30 | 20 | 0 |  | 0 | 70 |  | RTU-1 |  | 14
2025-03-26 | 1995 | sp | 66188 | A | DONE | 3 | S | neal | WSCC 6240006 | spiral mate | 2025-03-27 | Z | 2025-03-26 | 20 | 40 | 0 |  | 0 | 90 |  | RTU-1 SA |  | 1
2025-03-27 | 1996 |  | 66189 | A | DONE | 6 | S-M |  | WSCC 6240006 |  | 2025-03-28 | Z | 2025-03-27 | 150 | 0 | 0 |  | 0 | 220 |  | Angles |  | 1
[6 empty] | 1305 | [13 empty] | 40260 |  |  |  | 6270 | 15.57%
WEEK OF 3-31-2025
2025-03-31 | 251 |  | 81986 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 |  | 2025-04-02 | Z | 2025-03-20 | 100 | 0 | 0 |  | 0 | 170 |  | FC CURB CAPS |  | 13
2025-03-31 | 252 |  | 81988 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 |  | 2025-03-31 | Z | 2025-03-21 | 70 | 0 | 0 |  | 0 | 140 |  | ANGLES |  | 12
2025-04-02 | 253 | w | 81989 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-04-03 | Z | 2025-04-01 | 20 | 0 | 0 |  | 20 | 20 |  | Curb cap |  | 2
2025-04-05 | 257 |  | 81994 - 81995 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-04-07 | Z | 2025-04-01 | 50 | 0 | 0 |  | 0 | 80 |  | Saddle hangers / sleeves |  | 6
2025-04-05 | 259 |  | 81999 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-04-07 | Z | 2025-04-01 | 20 | 0 | 0 |  | 0 | 80 |  | Golf Rm |  | 6
2025-04-04 | 262 |  | 85202 | A | DONE | 6 | S |  | 121 E. WILSON 6230024 |  | 2025-04-04 | Z | 2025-04-04 | 50 | 0 | 100 |  | 0 | 210 |  | SF-1 Shaft |  | 0
2025-03-31 | 1747 |  | 81978 | A | DONE | 40 | L |  | 121 E. WILSON 6230024 | flex , 2" liner | 2025-03-31 | Z | 2025-03-17 | 980 | 0 | 0 |  | 440 | 2290 |  | FC INTAKE |  | 14
2025-03-31 | 1749 |  | 81985 | A | DONE | 7 | S-M | neal | 121 E. WILSON 6230024 | pipe shop to paint | 2025-04-02 | Z | 2025-03-19 | 170 | 0 | 0 |  | 0 | 410 |  | GAS SHROUD |  | 14
2025-03-31 | 194 |  | 70242 | A | DONE | 2 | S |  | DANE CO. AIRPORT 4250007 |  | 2025-04-01 | Z | 2025-03-31 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2025-04-04 | 830 | w | 70753 | A | DONE | 2 | S-M |  | DELLSHIRE 6240017 |  | 2025-04-07 | Z | 2025-02-12 | 50 | 0 | 0 |  | 0 | 110 |  | VTAC Con. Sleeve 4TH A/B |  | 54
2025-04-04 | 862 | bth | 73859 | A | DONE | 4 | S |  | DELLSHIRE 6240017 |  | 2025-04-07 | Z | 2025-03-27 | 20 | 60 | 0 |  | 0 | 80 |  | 1st floor |  | 11
2025-04-03 | 865 | w | 1128 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-04-07 | Z | 2025-04-01 | 20 | 0 | 0 |  | 0 | 30 |  | CMU sleeves |  | 6
2025-04-05 | 866 |  | 73864 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-04-07 | Z | 2025-04-04 | 40 | 0 | 0 |  | 0 | 60 |  | Misc |  | 3
2025-04-02 | 1233 |  | 69641 | A | DONE | 2 | S |  | EXACT MRD 2250009 |  | 2025-04-03 | Z | 2025-04-02 | 40 | 0 | 0 |  | 0 | 60 |  | BCU 2826 RA/SA |  | 1
2025-04-03 | 1236 |  | 69643 | A | DONE | 2 | S |  | EXACT MRD 2250009 |  | 2025-04-04 | Z | 2025-04-03 | 30 | 0 | 0 |  | 0 | 40 |  | Ceiling tie ins |  | 1
2025-04-01 | 1229 | w | 36527 | A | DONE | 2 | S | ss | EXACT SCIENCE 8250012 |  | 2025-04-02 | Z | 2025-03-28 | 20 | 0 | 0 |  | 0 | 20 |  | Water stop |  | 5
2025-04-01 | 1228 |  | 79034 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-04-02 | Z | 2025-03-26 | 20 | 0 | 0 |  | 0 | 20 |  | RAMP 8 |  | 7
2025-04-05 | 1232 |  | 60976 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-04-09 | Z | 2025-04-02 | 20 | 0 | 0 |  | 0 | 20 |  | Pump Shelf |  | 7
2025-04-02 | 2664 | bth | EA-L2B-01 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-04-03 | Z | 2025-03-10 | 170 | 100 | 0 |  | 50 | 300 |  |  |  | 24
2025-04-02 | 2665 |  | EA-L2B-02 | A | DONE | 4 | S |  | MONROE HS 6240018 | 1" liner | 2025-04-03 | Z | 2025-03-10 | 90 | 0 | 0 |  | 40 | 150 |  |  |  | 24
2025-04-02 | 2666 |  | RA-L2B-01 | A | DONE | 51 | M-L |  | MONROE HS 6240018 | 1" liner | 2025-04-03 | Z | 2025-03-10 | 690 | 0 | 570 | F | 980 | 2190 |  |  |  | 24
2025-04-02 | 2667 |  | RA-L2B-02 | A | DONE | 27 | M-L |  | MONROE HS 6240018 | 1" liner | 2025-04-03 | Z | 2025-03-10 | 90 | 0 | 580 | F | 600 | 1350 |  |  |  | 24
2025-04-02 | 2668 | bth | SALP-L2B-01 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 110 | 40 | 90 | F | 150 | 330 |  |  |  | 24
2025-04-02 | 2669 | bth | SALP-L2B-02 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 80 | 60 | 60 | F | 90 | 230 |  |  |  | 24
2025-04-02 | 2670 | bth | SALP-L2B-03 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 110 | 50 | 90 | F | 160 | 330 |  |  |  | 24
2025-04-02 | 2671 | bth | SALP-L2B-04 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 140 | 40 | 90 | F | 150 | 330 |  |  |  | 24
2025-04-03 | 2672 | bth | SALP-L2B-05 | A | DONE | 9 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 110 | 20 | 90 | F | 160 | 310 |  |  |  | 24
2025-04-03 | 2673 | bth | SALP-L2B-06 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 100 | 40 | 90 | F | 150 | 320 |  |  |  | 24
2025-04-03 | 2674 | bth | SALP-L2B-07 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 120 | 20 | 60 | F | 130 | 260 |  |  |  | 24
2025-04-03 | 2675 | bth | SALP-L2B-08 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 110 | 50 | 120 | F | 160 | 340 |  |  |  | 24
2025-04-03 | 2676 | bth | SALP-L2B-09 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 100 | 20 | 80 | F | 150 | 280 |  |  |  | 24
2025-04-03 | 2677 | bth | SALP-L2B-10 | A | DONE | 5 | S |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 40 | 70 | 0 |  | 20 | 110 |  |  |  | 24
2025-04-03 | 2678 | bth | SALP-L2B-11 | A | DONE | 5 | S |  | MONROE HS 6240018 | 2" liner | 2025-04-03 | Z | 2025-03-10 | 70 | 20 | 30 | F | 40 | 130 |  |  |  | 24
2025-04-03 | 2679 | bth | SAMP-L2B-01 | A | DONE | 9 | S-M |  | MONROE HS 6240018 | oval | 2025-04-03 | Z | 2025-03-10 | 130 | 60 | 20 | F | 0 | 250 |  |  |  | 24
2025-04-04 | 2680 | bth | SAMP-L2B-02 | A | DONE | 16 | S-M |  | MONROE HS 6240018 | oval , accuflange | 2025-04-03 | Z | 2025-03-10 | 200 | 190 | 0 |  | 0 | 460 |  |  |  | 24
2025-04-04 | 2681 | sp | SAMP-L2B-03 | A | DONE | 44 | L |  | MONROE HS 6240018 | oval , accuflange | 2025-04-03 | Z | 2025-03-10 | 280 | 810 | 0 |  | 0 | 1800 |  |  |  | 24
2025-04-03 | 2682 | bth | SAMP-L2B-04 | A | DONE | 29 | M-L |  | MONROE HS 6240018 | oval , accu. , 2" liner | 2025-04-03 | Z | 2025-03-10 | 290 | 420 | 0 |  | 120 | 1340 |  |  |  | 24
2025-04-03 | 2683 | bth | SAMP-L2B-05 | A | DONE | 22 | M |  | MONROE HS 6240018 | oval , accuflange | 2025-04-03 | Z | 2025-03-10 | 210 | 290 | 30 | F | 0 | 610 |  |  |  | 24
2025-04-03 | 2684 | bth | SAMP-L2B-06 | A | DONE | 16 | M |  | MONROE HS 6240018 | oval , accuflange | 2025-04-03 | Z | 2025-03-10 | 200 | 200 | 0 |  | 0 | 490 |  |  |  | 24
2025-03-31 | 3981 | sp | 80181 - 80182 | A | DONE | 8 | S-M | semi | PECATONICA ES 6240005 |  | 2025-04-11 | Z | 2025-01-22 | 30 | 170 | 0 |  | 0 | 180 |  | B-Section S. VAV LPSA | SEMI | 79 | 2025-06-30
2025-04-04 | 3999 |  | 83116 - 83117 | A | DONE | 14 | S-M |  | PECATONICA ES 6240005 | 1" liner | 2025-04-07 | Z | 2025-01-30 | 330 | 0 | 0 |  | 160 | 240 |  | C-Section TA |  | 67
2025-04-04 | 4200 |  | 83127 | A | DONE | 2 | S |  | PECATONICA ES 6240005 | flex | 2025-04-07 | Z | 2025-01-30 | 50 | 0 | 0 |  | 0 | 110 |  | UV 6 SA |  | 67
2025-03-31 | 4205 | sp | 83128 - 83129 | A | DONE | 7 | S-M | semi | PECATONICA ES 6240005 |  | 2025-04-11 | Z | 2025-01-30 | 20 | 140 | 0 |  | 0 | 190 |  | AHU-4 SA | SEMI | 71 | 2025-07-21
2025-03-31 | 4208 | sp | 83133 | A | DONE | 3 | S | semi | PECATONICA ES 6240005 |  | 2025-04-11 | Z | 2025-01-30 | 20 | 50 | 0 |  | 0 | 50 |  | VAV LPSA | SEMI | 71 | 2025-07-21
2025-04-03 | 4211 | bth | 80197 | A | DONE | 2 | S | pt.neal | PECATONICA ES 6240005 |  | 2025-04-07 | Z | 2025-04-01 | 20 | 20 | 0 |  | 0 | 40 |  | Misc |  | 6
2025-04-01 | 192 | w | 79946 | A | DONE | 2 | S-M |  | PEWAUKEE HS 6240030 |  | 2025-04-02 | Z | 2025-03-20 | 30 | 0 | 0 |  | 0 | 60 |  | SLEEVES |  | 13
2025-04-01 | 2592 |  | 62723 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 | flex | 2025-04-02 | Z | 2025-03-27 | 40 | 0 | 0 |  | 0 | 150 |  | RF-2 |  | 6
2025-04-04 | 1413 |  | 68461 | A | DONE | 2 | S-M |  | SPH SURGERY 6240039 |  | 2025-04-07 | Z | 2025-03-18 | 50 | 0 | 0 |  | 0 | 60 |  | Sleeves |  | 20
2025-04-01 | 2848 |  | 67761 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | paint | 2025-04-03 | Z | 2025-03-25 | 20 | 0 | 0 |  | 20 | 30 |  | 2nd floor |  | 9
2025-04-03 | 800 | w | 73551 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-04-04 | Z | 2025-03-13 | 20 | 0 | 0 |  | 0 | 20 |  | Roof jack |  | 22
2025-04-02 | 806 |  | PRE-FAB HANGERS | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 | Pipe Shop | 2025-04-04 | Z | 2025-03-26 | 20 | 0 | 0 |  | 0 | 40 |  | Saddle hangers / strut |  | 9
2025-04-01 | 4357 |  | 69261 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-02 | Z | 2025-03-31 | 40 | 0 | 0 |  | 0 | 50 |  | SAMP 3 |  | 2
2025-04-01 | 4358 |  | 59262 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-02 | Z | 2025-03-31 | 20 | 0 | 0 |  | 0 | 20 |  | L5B-EAT-512 |  | 2
2025-04-01 | 4359 |  | 59263 | A | DONE | 2 | S |  | UW-AVRL 6240038 | 1" liner | 2025-04-02 | Z | 2025-03-31 | 20 | 0 | 0 |  | 20 | 20 |  | L5B TA |  | 2
2025-04-01 | 4360 | sp | 59264 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-02 | Z | 2025-03-31 | 20 | 20 | 0 |  | 0 | 40 |  | L5B SAT |  | 2
2025-04-01 | 4361 |  | 69136 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-02 | Z | 2025-03-31 | 20 | 0 | 0 |  | 0 | 30 |  | Mech Rm EA |  | 2
2025-03-31 | 411 |  | L2-SAMP 9 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-04 | 30 | 0 | 120 | F | 0 | 190 |  |  |  | 28
2025-03-31 | 412 | sp | L2-SAMP 10 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-04 | 20 | 140 | 0 |  | 0 | 220 |  |  |  | 28
2025-03-31 | 413 |  | L2-SAMP 11 | A | DONE | 11 | S-M | pt.neal | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-04 | 120 | 0 | 140 | F | 0 | 350 |  |  |  | 28
2025-04-01 | 414 | bth | L2-SAMP 16 | A | DONE | 11 | S-M | pt.neal | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-04 | 150 | 30 | 90 | F | 0 | 360 |  |  |  | 28
2025-03-31 | 415 |  | L2-SAMP 17 | A | DONE | 6 | S | neal | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-04 | 30 | 0 | 110 | F | 0 | 180 |  |  |  | 28
2025-03-31 | 416 | bth | L2-RAMP 17 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-01 | Z | 2025-03-04 | 210 | 20 | 110 | F | 40 | 430 |  |  |  | 28
2025-03-31 | 417 | bth | L2-RAMP 18 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-01 | Z | 2025-03-04 | 100 | 120 | 0 |  | 60 | 260 |  |  |  | 28
2025-03-31 | 418 | bth | L2-RAMP 19 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-01 | Z | 2025-03-04 | 90 | 90 | 0 |  | 60 | 220 |  |  |  | 28
2025-03-31 | 419 |  | L2-RAMP 20 | A | DONE | 9 | S-M | pt.neal | UW-LEVY HALL 6230028 | 1" liner | 2025-04-01 | Z | 2025-03-04 | 120 | 0 | 90 | F | 30 | 270 |  |  |  | 28
2025-03-31 | 420 |  | L2-RAMP 21 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-01 | Z | 2025-03-04 | 90 | 0 | 60 | F | 130 | 330 |  |  |  | 28
2025-04-01 | 423 | bth | L2-SAT-3-2-1 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 40 | 20 | 90 | F | 30 | 180 |  |  |  | 27
2025-04-01 | 424 | bth | L2-SAT-3-2-16 | A | DONE | 16 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 170 | 90 | 130 | F | 230 | 490 |  |  |  | 27
2025-04-01 | 425 | bth | L2-SAT-3-2-17 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 100 | 20 | 160 | F | 210 | 370 |  |  |  | 27
2025-04-01 | 426 | bth | L2-SAT-3-2-2 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 40 | 20 | 0 |  | 30 | 70 |  |  |  | 27
2025-04-01 | 427 | bth | L2-SAT-3-2-3 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 60 | 30 | 20 | F | 30 | 130 |  |  |  | 27
2025-04-01 | 428 | bth | L2-SAT-3-2-4 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 80 | 30 | 20 | F | 30 | 170 |  |  |  | 27
2025-03-31 | 429 | bth | L2-SAT-3-2-5 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 70 | 20 | 60 | F | 30 | 180 |  |  |  | 27
2025-03-31 | 430 | bth | L2-SAT-3-2-6 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 30 | 20 | 0 |  | 20 | 60 |  |  |  | 27
2025-03-31 | 431 | bth | L2-SAT-3-2-7 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-01 | Z | 2025-03-05 | 130 | 40 | 60 | F | 20 | 300 |  |  |  | 27
2025-04-01 | 437 |  | L2-EAMP 2 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-05 | 80 | 0 | 40 | F | 0 | 170 |  |  |  | 27
2025-04-01 | 438 |  | L2-EAMP 3 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-05 | 370 | 0 | 0 |  | 0 | 460 |  |  |  | 27
2025-04-01 | 439 |  | L2-EAMP 4 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-05 | 150 | 0 | 0 |  | 0 | 210 |  |  |  | 27
2025-04-01 | 440 |  | L2-EAMP 5 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-05 | 80 | 0 | 0 |  | 0 | 110 |  |  |  | 27
2025-04-01 | 441 |  | L2-EAMP 6 | A | DONE | 4 | S | neal | UW-LEVY HALL 6230028 | VD | 2025-04-01 | Z | 2025-03-05 | 80 | 0 | 0 |  | 0 | 130 |  |  |  | 27
2025-04-01 | 442 |  | L2-EAMP 7 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-04-01 | Z | 2025-03-05 | 140 | 0 | 0 |  | 20 | 200 |  |  |  | 27
2025-03-31 | 443 |  | L2-EAMP 8 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-04-01 | Z | 2025-03-05 | 110 | 0 | 0 |  | 20 | 160 |  |  |  | 27
2025-03-31 | 444 |  | L2-EAMP 9 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-04-01 | Z | 2025-03-05 | 80 | 0 | 0 |  | 20 | 120 |  |  |  | 27
2025-04-01 | 445 |  | L2-EAMP 10 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-01 | Z | 2025-03-05 | 150 | 0 | 0 |  | 130 | 340 |  |  |  | 27
2025-04-01 | 700 | bth | L1-SAMP 8 | A | DONE | 35 | L |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-01 | Z | 2025-03-11 | 380 | 0 | 490 | F | 760 | 1830 |  |  |  | 21
2025-03-31 | 730 | sp | 83946 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-01 | Z | 2025-03-18 | 20 | 20 | 0 |  | 0 | 40 |  | L1-SAT-3-1-2.3 |  | 14
2025-04-01 | 731 |  | 83947-49 | A | DONE | 6 | M |  | UW-LEVY HALL 6230028 | 1"liner | 2025-04-01 | Z | 2025-03-21 | 150 | 0 | 0 |  | 40 | 250 |  | LL L1 L2 CAPS |  | 11
2025-04-02 | 734 |  | 83807 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-15 | Z | 2025-04-02 | 20 | 0 | 0 |  | 0 | 20 |  | LVL 2 misc |  | 13
2025-04-04 | 3180 | bth | 84523-29 | A | DONE | 56 | M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 430 | 280 | 680 | F | 0 | 1620 |  | 3RD RA |  | 20
2025-04-04 | 3181 |  | 84530-34 | A | DONE | 24 | M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 240 | 0 | 340 | F | 0 | 680 |  | 3RD RA |  | 20
2025-04-04 | 3182 | bth | 84535-40 | A | DONE | 8 | M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 140 | 40 | 20 | F | 0 | 210 |  | MISC-SAT |  | 20
2025-04-04 | 3183 | bth | 84601-03 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 50 | 90 | 60 | F | 0 | 210 |  | MISC-SAT |  | 20
2025-04-04 | 3184 | bth | 84604-07 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 50 | 70 | 20 | F | 0 | 130 |  | MISC-SAT |  | 20
2025-04-04 | 3185 | bth | 84609-15 | A | DONE | 17 | M |  | UWL-GRAFF 6230017 | 1"liner | 2025-04-07 | Z | 2025-03-18 | 180 | 90 | 140 | F | 30 | 440 |  | MISC-SAT |  | 20
2025-04-05 | 3186 | bth | 84616-20 | A | DONE | 30 | M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 400 | 230 | 120 | F | 0 | 920 |  | 3RD SA NO |  | 20
2025-04-05 | 3187 | bth | 84621-28 | A | DONE | 42 | M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 540 | 220 | 290 | F | 0 | 1200 |  | 3RD SA NO |  | 20
2025-04-05 | 3188 |  | 84629-30 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 50 | 0 | 0 |  | 0 | 70 |  | SAT-1-3-17 |  | 20
2025-04-05 | 3189 | bth | 84541-47 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 | 1"liner | 2025-04-07 | Z | 2025-03-18 | 100 | 50 | 110 | F | 30 | 290 |  | MISC-SAT |  | 20
2025-04-05 | 3190 |  | 84548-50 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 80 | 0 | 80 | F | 0 | 180 |  | SAT-1-3-11 |  | 20
2025-04-05 | 3191 |  | 84668 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 40 | 0 | 0 |  | 0 | 50 |  | TEST CAPS |  | 20
2025-04-05 | 3192 |  | 84669-71 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-19 | 60 | 0 | 0 |  | 0 | 70 |  | SAT - 3RD MISC |  | 19
2025-04-05 | 3193 |  | 84673 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-25 | 0 | 50 | 0 |  | 0 | 50 |  | SAT-3-2-2 |  | 13
2025-03-31 | 1126 |  | 83544 | A | DONE | 8 | S-M |  | UWRF 6230010 |  | 2025-04-01 | Z | 2025-03-13 | 190 | 0 | 0 |  | 0 | 410 |  | PH OA |  | 19
2025-03-31 | 1127 |  | 83545 | A | DONE | 2 | S |  | UWRF 6230010 | flex | 2025-04-01 | Z | 2025-03-13 | 20 | 0 | 0 |  | 0 | 30 |  | Roof outs |  | 19
2025-03-31 | 1128 |  | 84801 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-04-01 | Z | 2025-03-13 | 20 | 0 | 0 |  | 0 | 40 |  | GE tie in 2nd Floor |  | 19
2025-03-31 | 1130 | bth | 84802-07 | A | DONE | 13 | M | pcd | UWRF 6230010 |  | 2025-04-01 | Z | 2025-03-18 | 300 | 20 | 0 |  | 0 | 360 |  | MISC-RM |  | 14
2025-03-31 | 3248 |  | 81263 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | VD's | 2025-04-01 | Z | 2025-03-12 | 20 | 0 | 0 |  | 0 | 30 |  | 2nd Floor |  | 20
2025-03-31 | 3249 |  | 81267 | A | DONE | 2 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-04-01 | Z | 2025-03-20 | 30 | 0 | 0 |  | 0 | 50 |  | 3RD FL |  | 12
2025-03-31 | 4403 |  | 58827 | A | DONE | 2 | S |  | UWSP CHAMPION 6240008 | paint | 2025-04-01 | Z | 2025-03-21 | 30 | 0 | 0 |  | 20 | 40 |  | 2ND MISC |  | 11
2025-03-31 | 4404 | bth | 70166 | A | DONE | 5 | S-M | neal,al | UWSP CHAMPION 6240008 | MOD | 2025-04-01 | Z | 2025-03-24 | 100 | 20 | 0 |  | 0 | 80 |  | VAV-22-109 |  | 8
2025-04-02 | 2017 |  | 79710 - 79713 | A | DONE | 14 | S-M |  | UW-VET MED 6210014 |  | 2025-04-24 | Z | 2025-03-07 | 200 | 0 | 140 |  | 0 | 400 |  | 7B Chases |  | 48 | 2025-04-03
2025-04-03 | 2018 |  | 79714 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-04-24 | Z | 2025-03-07 | 20 | 0 | 0 |  | 0 | 30 |  | Gussets |  | 48 | 2025-04-03
2025-04-02 | 2019 |  | 79715-18 | A | DONE | 51 | M |  | UW-VET MED 6210014 |  | 2025-04-03 | Z | 2025-03-14 | 380 | 0 | 880 | F | 0 | 1500 |  | 10-D-EA |  | 19
2025-04-02 | 2020 | sp | 79719-21 | A | DONE | 16 | S-M |  | UW-VET MED 6210014 |  | 2025-04-03 | Z | 2025-03-14 | 60 | 320 | 0 |  | 0 | 380 |  | 10-D-EA |  | 19
2025-04-04 | 2030 |  | 79745 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-04-07 | Z | 2025-04-02 | 20 | 0 | 0 |  | 0 | 30 |  | 3rd Floor |  | 5
2025-04-03 | 1199 |  | 79815 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-04 | Z | 2025-03-25 | 30 | 0 | 0 |  | 20 | 40 |  | HP-322 RA |  | 10
2025-04-03 | 1650 | sp | 79816 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-03-25 | 20 | 80 | 0 |  | 0 | 80 |  | Misc |  | 10
2025-04-03 | 1651 |  | 79817 - 79818 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-04 | Z | 2025-03-25 | 20 | 0 | 0 |  | 0 | 40 |  | HP-322 SA |  | 10
2025-04-03 | 1652 |  | 79823 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-04 | Z | 2025-04-01 | 20 | 0 | 0 |  | 20 | 30 |  | 1st G-RA Electrical Rm |  | 3
2025-04-03 | 4149 |  | L02_E_SOA_001 | A | DONE | 19 | M |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 280 | 0 | 190 | F | 0 | 680 |  |  |  | 52
2025-04-03 | 4150 | bth | L02_E_SOA_002 | A | DONE | 16 | M |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 150 | 50 | 190 | F | 0 | 520 |  |  |  | 52
2025-04-04 | 4151 | bth | L02_E_SOA_003 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 150 | 80 | 140 | F | 0 | 440 |  |  |  | 52
2025-04-03 | 4152 | bth | L02_E_SOA_004 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 80 | 30 | 250 | F | 0 | 420 |  |  |  | 52
2025-04-04 | 4153 | sp | L02_E_SOA_005 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 30 | 190 | 0 |  | 0 | 230 |  |  |  | 52
2025-04-03 | 4154 | bth | L02_E_SOA_006 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 100 | 40 | 20 | F | 0 | 180 |  |  |  | 52
2025-04-03 | 4155 | bth | L02_E_SOA_007 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 90 | 20 | 40 | F | 0 | 170 |  |  |  | 52
2025-04-04 | 4156 | sp | L02_E_SOA_008 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 20 | 150 | 0 |  | 0 | 170 |  |  |  | 52
2025-04-04 | 4157 | sp | L02_E_SOA_009 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 30 | 90 | 0 |  | 0 | 130 |  |  |  | 52
2025-04-03 | 4158 |  | L02_E_SOA_010 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 80 | 0 | 0 |  | 0 | 130 |  |  |  | 52
2025-04-03 | 4161 | bth | L02_E_EAD_001 | A | DONE | 20 | M |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 170 | 30 | 300 | F | 0 | 590 |  |  |  | 52
2025-04-03 | 4162 | bth | L02_E_EAD_002 | A | DONE | 19 | M |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 120 | 20 | 330 | F | 0 | 560 |  |  |  | 52
2025-04-04 | 4163 | bth | L02_E_EAD_003 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 140 | 40 | 90 | F | 0 | 300 |  |  |  | 52
2025-04-03 | 4164 | bth | L02_E_EAD_004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 60 | 20 | 0 |  | 0 | 80 |  |  |  | 52
2025-04-04 | 4165 | bth | L02_E_EAD_005 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 30 | 20 | 50 | F | 0 | 120 |  |  |  | 52
2025-04-03 | 4166 | bth | L02_E_EAD_006 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 70 | 20 | 40 | F | 0 | 140 |  |  |  | 52
2025-04-04 | 4167 | bth | L02_E_EAD_007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 40 | 20 | 60 | F | 0 | 130 |  |  |  | 52
2025-04-04 | 4168 | bth | L02_E_EAD_008 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 40 | 40 | 50 | F | 0 | 140 |  |  |  | 52
2025-04-04 | 4169 | bth | L02_E_EAD_009 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 80 | 0 | 0 |  | 0 | 120 |  |  |  | 52
2025-04-03 | 4172 |  | L02_E_EAD_012 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-04 | Z | 2025-02-11 | 0 | 0 | 80 | F | 0 | 100 |  |  |  | 52
2025-04-01 | 1994 |  | 66187 | A | DONE | 4 | S |  | WSCC 6240006 |  | 2025-04-03 | Z | 2025-03-20 | 40 | 0 | 0 |  | 30 | 60 |  | Misc Fittings |  | 14
2025-04-01 | 1997 |  | 66190 | A | DONE | 2 | S | neal | WSCC 6240006 |  | 2025-04-03 | Z | 2025-03-31 | 20 | 0 | 0 |  | 0 | 20 |  | VAV-1-7 |  | 3
2025-04-04 | 1998 |  | 66191 | A | DONE | 2 | S | neal | WSCC 6240006 |  | 2025-04-04 | Z | 2025-04-04 | 20 | 0 | 0 |  | 0 | 20 |  | VAV 1-11 |  | 0
[6 empty] | 1273 | [13 empty] | 41040 |  |  |  | 2280 | 5.556%
WEEK OF 4-7-2025
2025-04-07 | 254 |  | 81990 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-04-07 | Z | 2025-04-01 | 40 | 0 | 0 |  | 0 | 40 |  | Dog wash room |  | 6
2025-04-07 | 255 |  | 81991 - 81992 | A | DONE | 6 | S |  | 121 E. WILSON 6230024 |  | 2025-04-07 | Z | 2025-04-01 | 150 | 0 | 0 |  | 0 | 160 |  | OA tie ins |  | 6
2025-04-07 | 256 |  | 81993 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | flex | 2025-04-07 | Z | 2025-04-01 | 20 | 0 | 0 |  | 20 | 20 |  | HP SA |  | 6
2025-04-07 | 258 |  | 81996 - 81998 | A | DONE | 16 | S-M |  | 121 E. WILSON 6230024 | bird s. , flex | 2025-04-07 | Z | 2025-04-01 | 350 | 0 | 40 | A | 0 | 540 |  | SF-2 , PH OUTS |  | 6
2025-04-07 | 260 |  | 82000 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-04-07 | Z | 2025-04-01 | 30 | 0 | 0 |  | 0 | 50 |  | Stairs A sleeve |  | 6
2025-04-07 | 261 |  | 85201 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-04-09 | Z | 2025-04-03 | 40 | 0 | 0 |  | 30 | 40 |  | L14 RA-02 |  | 6
2025-04-09 | 263 |  | 85203 - 85205 | A | DONE | 22 | S-M |  | 121 E. WILSON 6230024 | bird s. , flex , 1" liner | 2025-04-10 | Z | 2025-04-07 | 450 | 0 | 100 | A | 0 | 820 |  | SF-1 , ERU-PH |  | 3
2025-04-11 | 264 |  | 85208 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | paint | 2025-04-14 | Z | 2025-04-10 | 30 | 0 | 0 |  | 20 | 60 |  | RA Grille box |  | 4
2025-04-08 | 928 |  | 482025 | A | DONE | 2 | S | ss | BMH AHU-9 6240001 |  | 2025-04-08 | Z | 2025-04-08 | 20 | 0 | 0 |  | 0 | 20 |  | Cover |  | 0
2025-04-07 | 2474 |  | 81625 - 81628 | A | DONE | 4 | S-M | neal | CDIS 6220028 |  | 2025-04-08 | Z | 2025-03-31 | 100 | 0 | 0 |  | 0 | 160 |  | GET 1-7-1 thru 4 |  | 8
2025-04-07 | 2475 |  | 81629 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2025-04-08 | Z | 2025-03-31 | 50 | 0 | 0 |  | 20 | 90 |  | All GET's 1 thru 4 |  | 8
2025-04-10 | 2476 |  | 81630 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-04-11 | Z | 2025-04-09 | 20 | 0 | 0 |  | 0 | 20 |  | #10 |  | 2
2025-04-09 | 863 | sp | 73860 - 73862 | A | DONE | 13 | S-M |  | DELLSHIRE 6240017 |  | 2025-04-14 | Z | 2025-03-27 | 100 | 220 | 0 |  | 0 | 320 |  | 1st floor C EA |  | 18
2025-04-08 | 864 | sp | 73654 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-04-14 | Z | 2025-04-01 | 50 | 0 | 0 |  | 0 | 70 |  | Misc coupling |  | 13
2025-04-09 | 1600 |  | 84766 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-04-15 | Z | 2025-04-08 | 20 | 0 | 0 |  | 0 | 80 |  | Trailer |  | 7
2025-04-11 | 1235 |  | 69642 | A | DONE | 2 | S |  | EXACT 501 6240025 | To Pipe Shop - paint | 2025-04-16 | Z | 2025-04-03 | 40 | 0 | 0 |  | 40 | 140 |  | Drip ledge |  | 13
2025-04-07 | 1237 |  | 69644 | A | DONE | 2 | S |  | EXACT MRD 2250009 |  | 2025-04-08 | Z | 2025-04-07 | 20 | 0 | 0 |  | 0 | 50 |  | SAT 2826 |  | 1
2025-04-11 | 1240 |  | 79045 | A | DONE | 2 | S | pcd | EXACT TL-2 2250003 |  | 2025-04-16 | Z | 2025-04-11 | 20 | 0 | 0 |  | 0 | 20 |  | Gauge panel |  | 5
2025-04-08 | 1230 |  | 79035 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-04-09 | Z | 2025-03-31 | 20 | 0 | 0 |  | 0 | 40 |  | Out |  | 9
2025-04-08 | 1231 |  | 79036 - 79038 | A | DONE | 25 | S-M |  | EXACT TL-3 6240028 |  | 2025-04-09 | Z | 2025-03-31 | 340 | 0 | 280 | A | 0 | 850 |  | Shell EA |  | 9
2025-04-08 | 1234 |  | 79040 - 79041 | A | DONE | 6 | S-M |  | EXACT TL-3 6240028 | paint , flex | 2025-04-09 | Z | 2025-04-02 | 130 | 0 | 0 |  | 20 | 210 |  | SA / RA |  | 7
2025-04-08 | 1238 |  | 79042 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-04-14 | Z | 2025-04-07 | 30 | 0 | 0 |  | 0 | 30 |  | Flashing |  | 7
2025-04-10 | 456 | w | 84277 | A | DONE | 2 | S |  | KIKKOMAN 6240041 |  | 2025-04-10 | Z | 2025-04-10 | 20 | 0 | 0 |  | 0 | 40 |  | Sleeve |  | 0
2025-04-08 | 2945 |  | 82579 | A | DONE | 4 | S |  | LABCORP 6240016 | paint | 2025-04-11 | Z | 2025-04-04 | 80 | 0 | 0 |  | 60 | 180 |  | 1st Floor B-Section |  | 7
2025-04-11 | 2946 |  | 82580 | A | DONE | 11 | M |  | LABCORP 6240016 |  | 2025-04-16 | Z | 2025-04-07 | 260 | 0 | 0 |  | 0 | 660 |  | PH |  | 9
2025-04-08 | 2947 |  | 82581 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2025-04-11 | Z | 2025-04-08 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd Floor eb 3311 |  | 3
2025-04-11 | 2948 |  | 82582 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2025-04-16 | Z | 2025-04-10 | 20 | 0 | 0 |  | 0 | 20 |  | R-Angle |  | 6
2025-04-07 | 1700 |  | 74253 | A | DONE | 7 | S |  | MADISON CO. 6250005 |  | 2025-04-08 | Z | 2025-03-27 | 40 | 0 | 120 | A | 0 | 180 |  | Phase 2 |  | 12
2025-04-07 | 1701 | sp | 74254 | A | DONE | 10 | S-M |  | MADISON CO. 6250005 |  | 2025-04-08 | Z | 2025-03-27 | 50 | 200 | 0 |  | 0 | 240 |  | Phase 2 |  | 12
2025-04-07 | 1702 |  | 74256 | A | DONE | 2 | S |  | MADISON CO. 6250005 |  | 2025-04-08 | Z | 2025-03-28 | 30 | 0 | 0 |  | 0 | 40 |  | Phase 2 |  | 11
2025-04-09 | 1703 |  | 74257 | A | DONE | 2 | S |  | MADISON COUNTRY 6250005 | bird s. | 2025-04-21 | Z | 2025-04-08 | 20 | 0 | 0 |  | 0 | 30 |  | Phase 2 |  | 13
2025-04-11 | 1500 | sp | EA-L1B-07 | A | DONE | 8 | S |  | MONROE HS 6240018 |  | 2025-04-16 | Z | 2025-03-24 | 20 | 160 | 0 |  | 0 | 180 |  |  |  | 23
2025-04-07 | 2665 |  | 78788 | A | DONE | 6 | S-M |  | MONROE HS 6240018 |  | 2025-04-09 | Z | 2025-03-17 | 130 | 0 | 0 |  | 0 | 190 |  | Drywall Sleeves |  | 22
2025-04-11 | 2689 | sp | SAMP-L1B-05 | A | DONE | 21 | M |  | MONROE HS 6240018 | oval , accuflange | 2025-04-16 | Z | 2025-03-24 | 130 | 380 | 0 |  | 0 | 720 |  |  |  | 23
2025-04-11 | 2694 | sp | EA-L1B-01 | A | DONE | 10 | S |  | MONROE HS 6240018 |  | 2025-04-16 | Z | 2025-03-24 | 20 | 210 | 0 |  | 0 | 220 |  |  |  | 23
2025-04-09 | 3978 |  | 80175 - 80176 | A | DONE | 13 | S-M | semi | PECATONICA ES 6240005 | 2" liner | 2025-04-11 | Z | 2025-01-22 | 120 | 0 | 190 | A | 220 | 290 |  | B-Section S. VAV LPSA | SEMI | 79 | 2025-06-30
2025-04-09 | 3979 |  | 80177 - 80178 | A | DONE | 6 | S-M | semi | PECATONICA ES 6240005 | 2" liner | 2025-04-11 | Z | 2025-01-22 | 80 | 0 | 70 | A | 120 | 180 |  | B-Section S. VAV LPSA | SEMI | 79 | 2025-06-30
2025-04-09 | 3980 |  | 80179 - 80180 | A | DONE | 12 | S-M | semi | PECATONICA ES 6240005 | 2" liner | 2025-04-11 | Z | 2025-01-22 | 130 | 0 | 170 | A | 210 | 280 |  | B-Section S. VAV LPSA | SEMI | 79 | 2025-06-30
2025-04-09 | 3982 |  | 80183 | A | DONE | 9 | S | semi | PECATONICA ES 6240005 | 1" liner | 2025-04-11 | Z | 2025-01-27 | 80 | 0 | 140 | A | 180 | 220 |  | CE EA Attic | SEMI | 74 | 2025-07-07
2025-04-09 | 3983 | bth | 80184 - 80186 | A | DONE | 4 | S-M | semi | PECATONICA ES 6240005 | flex | 2025-04-11 | Z | 2025-01-27 | 60 | 20 | 0 |  | 0 | 70 |  | CE EA Ceiling | SEMI | 74 | 2025-07-07
2025-04-09 | 3984 |  | 80187 - 80188 | A | DONE | 7 | S-M | semi | PECATONICA ES 6240005 | flex , 1" liner | 2025-04-11 | Z | 2025-01-27 | 170 | 0 | 0 |  | 140 | 220 |  | B-Section TA | SEMI | 74 | 2025-07-07
2025-04-09 | 3985 |  | 80189 - 80190 | A | DONE | 10 | S-M | semi | PECATONICA ES 6240005 | 1" liner | 2025-04-11 | Z | 2025-01-27 | 250 | 0 | 0 |  | 210 | 450 |  | B-Section TA | SEMI | 74 | 2025-07-07
2025-04-09 | 3986 |  | 80191 | A | DONE | 10 | S-M | semi | PECATONICA ES 6240005 |  | 2025-04-11 | Z | 2025-01-29 | 190 | 0 | 60 | A | 0 | 470 |  | AHU-3 OA | SEMI | 72 | 2025-07-14
2025-04-09 | 3987 |  | 80192 - 80193 | A | DONE | 10 | S-M | semi | PECATONICA ES 6240005 | VD , 1" liner | 2025-04-11 | Z | 2025-01-29 | 230 | 0 | 0 |  | 170 | 470 |  | AHU-3 RA | SEMI | 72 | 2025-07-14
2025-04-09 | 3988 | bth | 80194 - 80195 | A | DONE | 8 | S-M | semi | PECATONICA ES 6240005 | accuflange , 2" liner | 2025-04-11 | Z | 2025-01-29 | 190 | 0 | 0 |  | 130 | 550 |  | AHU-3 SA | SEMI | 72 | 2025-07-14
2025-04-09 | 4206 |  | 83130 | A | DONE | 2 | S | semi | PECATONICA ES 6240005 |  | 2025-04-11 | Z | 2025-01-30 | 50 | 0 | 0 |  | 0 | 60 |  | VAV LPSA | SEMI | 71 | 2025-07-21
2025-04-09 | 4207 |  | 83131 - 83132 | A | DONE | 8 | S-M | semi | PECATONICA ES 6240005 | 2" liner | 2025-04-11 | Z | 2025-01-30 | 70 | 0 | 120 | A | 170 | 230 |  | VAV LPSA | SEMI | 71 | 2025-07-21
2025-04-09 | 4209 |  | 83134 | A | DONE | 4 | S | semi | PECATONICA ES 6240005 | 1" liner | 2025-04-11 | Z | 2025-01-30 | 60 | 0 | 40 | A | 90 | 150 |  | Special ED TA | SEMI | 71 | 2025-07-21
2025-04-09 | 4210 | w | 83135 | A | DONE | 2 | S-M | semi | PECATONICA ES 6240005 | 1" DB | 2025-04-11 | Z | 2025-01-30 | 30 | 0 | 0 |  | 30 | 110 |  | C-Section Curb Adapt. | SEMI | 71 | 2025-06-23
2025-04-07 | 1800 |  | 79974 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | 1" liner | 2025-04-08 | Z | 2025-04-01 | 30 | 0 | 0 |  | 20 | 100 |  | EC |  | 7
2025-04-08 | 2593 | bth | 70846 | A | DONE | 7 | S-M |  | PROMEGA BTC 6230022 |  | 2025-04-09 | Z | 2025-03-27 | 100 | 20 | 50 | A | 0 | 190 |  | EAT 6-2 |  | 13
2025-04-08 | 2594 |  | 70850 | A | DONE | 31 | M |  | PROMEGA BTC 6230022 | VD | 2025-04-09 | Z | 2025-03-27 | 290 | 0 | 480 | A | 0 | 1580 |  | AHU-13 |  | 13
2025-04-08 | 2595 |  | 62724 | A | DONE | 15 | S-M |  | PROMEGA BTC 6230022 |  | 2025-04-09 | Z | 2025-03-31 | 190 | 0 | 180 | A | 0 | 800 |  | AHU M SA |  | 9
2025-04-10 | 2597 |  | 62725 | A | DONE | 8 | S |  | PROMEGA BTC 6230022 |  | 2025-04-16 | Z | 2025-04-04 | 190 | 0 | 0 |  | 0 | 520 |  | AHU M SA |  | 12
2025-04-10 | 2598 |  | 62728 | A | DONE | 22 | M |  | PROMEGA BTC 6230022 |  | 2025-04-16 | Z | 2025-04-04 | 80 | 0 | 470 | A | 0 | 800 |  | RA |  | 12
2025-04-10 | 2599 |  | 62726 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-04-14 | Z | 2025-04-04 | 30 | 0 | 0 |  | 0 | 60 |  | Misc |  | 10
2025-04-10 | 2596 |  | 62727 | A | DONE | 4 | S |  | PROMEGA CULINARY 2240009 | paint | 2025-04-14 | Z | 2025-04-04 | 60 | 0 | 30 | A | 20 | 100 |  | Misc |  | 10
2025-04-10 | 3020 |  | 62730 | A | DONE | 2 | S |  | PROMEGA CULINARY 2240009 |  | 2025-04-14 | Z | 2025-04-08 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2025-04-08 | 4795 |  | 83604 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2025-04-10 | Z | 2025-04-04 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2025-04-10 | 2405 | bth | 80041 - 43 , 79960 | A | DONE | 28 | S-M |  | ST.BERNARD 2230056 |  | 2025-04-14 | Z | 2025-03-31 | 310 | 100 | 280 | A | 0 | 700 |  | RA |  | 14
2025-04-10 | 2406 |  | 79975 | A | DONE | 2 | S |  | ST.BERNARD 6230023 | paint | 2025-04-14 | Z | 2025-04-07 | 40 | 0 | 0 |  | 20 | 60 |  | Misc |  | 7
2025-04-08 | 2845 |  | 67757 | A | DONE | 27 | S-M |  | STOUGHTON TRAILER 6240015 | 1"liner | 2025-04-08 | Z | 2025-03-19 | 660 | 0 | 0 |  | 720 | 860 |  | A-SEC |  | 22
2025-04-08 | 2847 |  | 67760 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-04-08 | Z | 2025-03-21 | 30 | 0 | 0 |  | 0 | 50 |  | 2A |  | 20
2025-04-08 | 2849 |  | 67762 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-04-08 | Z | 2025-03-31 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd Floor |  | 8
2025-04-11 | 4050 |  | 67763 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-04-15 | Z | 2025-04-07 | 30 | 0 | 0 |  | 30 | 40 |  | TA |  | 8
2025-04-10 | 4051 |  | 67767 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | 1" liner | 2025-04-15 | Z | 2025-04-07 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 8
2025-04-11 | 4052 | w | 83043 | A | DONE | 2 | S-M |  | STOUGHTON TRAILER 6240015 | nipple | 1900-01-14 | Z | 2025-04-08 | 20 | 0 | 0 |  | 0 | 110 |  | Drain pan |  | -45740
2025-04-08 | 2022 |  | 79724-25 | A | DONE | 39 | M |  | UW VET MED 6210014 |  | 2025-04-10 | Z | 2025-03-14 | 200 | 0 | 770 | A | 0 | 1160 |  | 10-D-SA |  | 27
2025-04-08 | 2023 | sp | 79726-27 | A | DONE | 7 | S |  | UW VET MED 6210014 |  | 2025-04-10 | Z | 2025-03-14 | 40 | 130 | 0 |  | 0 | 160 |  | 10-D-SA |  | 27
2025-04-11 | 4362 | bth | L5D-SAT 550 | A | DONE | 12 | S-M |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 80 | 110 | 110 | A | 0 | 330 |  |  |  | 14
2025-04-11 | 4363 | bth | L5D-SAT 555-1 | A | DONE | 6 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 30 | 70 | 50 | A | 0 | 170 |  |  |  | 14
2025-04-11 | 4364 | bth | L5D-SAT 555-2 | A | DONE | 9 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 80 | 100 | 30 | A | 0 | 210 |  |  |  | 14
2025-04-10 | 4365 | sp | L5D-SAT 555C | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 30 | 20 | 0 |  | 0 | 60 |  |  |  | 14
2025-04-09 | 4366 | sp | L5D-SAT 559 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 14
2025-04-11 | 4367 | sp | L5D-SAT 560 | A | DONE | 4 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 30 | 70 | 0 |  | 0 | 100 |  |  |  | 14
2025-04-11 | 4368 | sp | L5D-SAT 590 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 14
2025-04-10 | 4369 | bth | L5D-SAMP 12 | A | DONE | 14 | S-M |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 50 | 140 | 160 | A | 0 | 370 |  |  |  | 14
2025-04-11 | 4370 | bth | L5D-SAMP 13 | A | DONE | 11 | S-M |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 160 | 40 | 70 | A | 0 | 330 |  |  |  | 14
2025-04-08 | 4371 | sp | L5D-EAT 550 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 14
2025-04-11 | 4372 | sp | L5D-EAT 555 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 14
2025-04-10 | 4373 | sp | L5D-EAT 559 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 14
2025-04-11 | 4374 | sp | L5D-EAT 560 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 14
2025-04-11 | 4375 | bth | L5D-EAT 570 | A | DONE | 9 | S | alum | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 80 | 130 | 0 |  | 0 | 130 |  |  |  | 14
2025-04-10 | 4376 | sp | L5D-EAT 577 | A | DONE | 8 | S | alum | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 60 | 130 | 0 |  | 0 | 100 |  |  |  | 14
2025-04-11 | 4377 | sp | L5D-FAT 585 | A | DONE | 10 | S | pcd | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 60 | 190 | 0 |  | 0 | 300 |  |  |  | 14
2025-04-11 | 4378 | bth | L5D-EAMP 10 | A | DONE | 14 | S | pt.alum | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 220 | 30 | 90 | A | 0 | 240 |  |  |  | 14
2025-04-11 | 4379 | bth | L5D-EAMP 11 | A | DONE | 10 | S | pt.alum | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 80 | 90 | 60 | A | 0 | 140 |  |  |  | 14
2025-04-10 | 4380 | w | L5D-EAMP SS 1 | A | DONE | 12 | M | ss | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-02 | 290 | 0 | 0 |  | 0 | 750 |  |  |  | 14
2025-04-08 | 4381 | bth | 59265 - 59267 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-04-09 | Z | 2025-04-03 | 30 | 30 | 0 |  | 0 | 60 |  | A-Section EA / SAT 510 |  | 6
2025-04-07 | 4382 |  | 69137 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-09 | Z | 2025-04-03 | 20 | 0 | 0 |  | 0 | 30 |  | Outs |  | 6
2025-04-07 | 4383 |  | 69138 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-09 | Z | 2025-04-03 | 50 | 0 | 0 |  | 0 | 60 |  | Flashing |  | 6
2025-04-11 | 4385 |  | 59274 - 59275 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-08 | 60 | 0 | 0 |  | 0 | 90 |  | Misc |  | 8
2025-04-11 | 4386 | sp | 59276 | A | DONE | 4 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-08 | 20 | 80 | 0 |  | 0 | 100 |  | SAT SA |  | 8
2025-04-10 | 4387 |  | 59277 | A | DONE | 5 | S |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-10 | 110 | 0 | 0 |  | 0 | 160 |  | D-Sleeves |  | 6
2025-04-07 | 432 |  | L2-TA 1 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-08 | Z | 2025-03-05 | 90 | 0 | 0 |  | 80 | 120 |  |  |  | 34
2025-04-07 | 433 |  | L2-TA 2 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-08 | Z | 2025-03-05 | 90 | 0 | 0 |  | 80 | 130 |  |  |  | 34
2025-04-07 | 434 |  | L2-TA 3 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-08 | Z | 2025-03-05 | 70 | 0 | 0 |  | 60 | 110 |  |  |  | 34
2025-04-07 | 435 |  | L2-TA 4 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-08 | Z | 2025-03-05 | 70 | 0 | 0 |  | 60 | 110 |  |  |  | 34
2025-04-07 | 436 |  | L2-TA 5 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-08 | Z | 2025-03-05 | 60 | 0 | 0 |  | 50 | 90 |  |  |  | 34
2025-04-07 | 712 | bth | L2-SAT-3-2-22 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 30 | 0 | 40 | A | 30 | 80 |  |  |  | 28
2025-04-07 | 713 | bth | L2-SAT-3-2-23 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 80 | 20 | 0 |  | 20 | 100 |  |  |  | 28
2025-04-07 | 714 | bth | L2-SAT-3-2-24 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 50 | 20 | 40 | A | 30 | 120 |  |  |  | 28
2025-04-07 | 715 | bth | L2-SAT-3-2-25 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 80 | 20 | 40 | A | 20 | 150 |  |  |  | 28
2025-04-07 | 716 | bth | L2-SAT-3-2-26 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 80 | 0 | 0 |  | 30 | 100 |  |  |  | 28
2025-04-07 | 717 |  | L2-SAT-3-2-27 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-08 | Z | 2025-03-11 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 28
2025-04-07 | 718 | bth | L2-SAT-3-2-28 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 40 | 20 | 0 |  | 30 | 50 |  |  |  | 28
2025-04-08 | 719 |  | L2-SAT-3-2-29 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 28
2025-04-08 | 720 | bth | L2-SAT-3-2-30 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VD , VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 50 | 0 | 20 | A | 20 | 100 |  |  |  | 28
2025-04-08 | 722 | bth | L2-SAT-3-2-32 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-08 | Z | 2025-03-11 | 60 | 20 | 0 |  | 40 | 90 |  |  |  | 28
2025-04-08 | 726 |  | L2-TA 6 | A | DONE | 47 | M-L |  | UW-LEVY HALL 6230028 | bird s. , 1" liner | 2025-04-08 | Z | 2025-03-11 | 1170 | 0 | 0 |  | 860 | 1380 |  |  |  | 28
2025-04-08 | 727 |  | L2-TA 7 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | bird s. , 1" liner | 2025-04-08 | Z | 2025-03-11 | 120 | 0 | 0 |  | 90 | 150 |  |  |  | 28
2025-04-07 | 732 |  | 83803 | A | DONE | 2 | S | alum,nl | UW-LEVY HALL 6230028 | VD | 2025-04-08 | Z | 2025-03-25 | 20 | 0 | 0 |  | 0 | 20 |  | LL Utility Rm. |  | 14
2025-04-10 | 733 |  | 83804 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-15 | Z | 2025-04-01 | 20 | 0 | 0 |  | 20 | 30 |  | L1-RAMP 4 |  | 14
2025-04-10 | 783 |  | MER-RAMP 1 | A | DONE | 17 | M-L |  | UW-LEVY HALL 6230028 | partial | 2025-04-15 | Z | 2025-04-07 | 420 | 0 | 0 |  | 0 | 1520 |  | 90 degree elbow |  | 8
2025-04-07 | 3179 |  | 84501-03,05,07 | A | DONE | 34 | M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-18 | 510 | 0 | 320 | F | 0 | 1270 |  | 3RD RA |  | 20
2025-04-07 | 3194 |  | 84674 - 84676 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-04-07 | Z | 2025-03-25 | 70 | 0 | 30 | F | 0 | 110 |  | 2nd RA |  | 13
2025-04-10 | 3943 |  | 84679 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 |  | 2025-04-14 | Z | 2025-03-27 | 260 | 0 | 0 |  | 0 | 590 |  | AHU 2 RA PH |  | 18
2025-04-10 | 3944 |  | 84687 - 84689 | A | DONE | 33 | M |  | UWL-GRAFF 6230017 |  | 2025-04-14 | Z | 2025-03-27 | 650 | 0 | 160 | F | 0 | 1360 |  | AHU 2,3 RA/SA PH |  | 18
2025-04-10 | 3945 |  | 84690 - 84692 | A | DONE | 23 | M |  | UWL-GRAFF 6230017 |  | 2025-04-14 | Z | 2025-03-27 | 560 | 0 | 0 |  | 0 | 1270 |  | AHU 3 SA PH |  | 18
2025-04-07 | 1131 |  | 66897 | A | DONE | 26 | S-M |  | UWRF 6230010 |  | 2025-04-08 | Z | 2025-03-25 | 650 | 0 | 0 |  | 0 | 1200 |  | OA Tie in |  | 14
2025-04-07 | 1132 |  | 84809 , 84812 | A | DONE | 2 | S |  | UWRF 6230010 | flex | 2025-04-08 | Z | 2025-03-25 | 30 | 0 | 0 |  | 30 | 50 |  | L3 TA |  | 14
2025-04-07 | 1133 |  | 84813 , 84815 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-04-08 | Z | 2025-03-25 | 50 | 0 | 0 |  | 0 | 80 |  | L3 FE |  | 14
2025-04-07 | 1134 |  | 84814 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2025-04-08 | Z | 2025-03-25 | 50 | 0 | 0 |  | 30 | 80 |  | L3 TA |  | 14
2025-04-07 | 1135 | bth | 84816 - 84817 , 84819 | A | DONE | 9 | S-M | pcd | UWRF 6230010 |  | 2025-04-08 | Z | 2025-03-26 | 190 | 20 | 0 |  | 0 | 240 |  | Rm 389 , 362 |  | 13
2025-04-07 | 1136 |  | 84818 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2025-04-08 | Z | 2025-03-26 | 30 | 0 | 0 |  | 20 | 40 |  | Rm 391 TA |  | 13
2025-04-07 | 1137 |  | 84820 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-04-08 | Z | 2025-03-26 | 20 | 0 | 0 |  | 0 | 30 |  | L1-SA |  | 13
2025-04-07 | 1138 |  | 66898 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-04-08 | Z | 2025-03-27 | 30 | 0 | 0 |  | 0 | 90 |  | OA |  | 12
2025-04-10 | 1139 |  | 66899 | A | DONE | 2 | S |  | UWRF 6230010 | paint , 1" liner | 2025-04-15 | Z | 2025-04-01 | 30 | 0 | 0 |  | 20 | 40 |  | 1st floor TA |  | 14
2025-04-10 | 1140 |  | 84821 - 84822 | A | DONE | 6 | S | pcd | UWRF 6230010 |  | 2025-04-15 | Z | 2025-04-01 | 110 | 20 | 0 |  | 0 | 140 |  | L3-FE , Rm 320 FE |  | 14
2025-04-07 | 3250 |  | 81269 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-04-08 | Z | 2025-03-28 | 20 | 0 | 0 |  | 0 | 20 |  | 4th flat stock |  | 11
2025-04-07 | 3251 |  | 81271 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-04-08 | Z | 2025-04-02 | 20 | 0 | 0 |  | 0 | 30 |  | 4th Floor ceiling tie in |  | 6
2025-04-10 | 3252 | w | 81273 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | nailer , 1-1/2" DB | 2025-04-14 | Z | 2025-04-04 | 20 | 0 | 0 |  | 20 | 60 |  | Roof curb |  | 10
2025-04-10 | 3253 |  | 81274 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-04-14 | Z | 2025-04-04 | 20 | 0 | 0 |  | 0 | 30 |  | RA |  | 10
2025-04-07 | 4405 |  | 70167 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-04-08 | Z | 2025-04-01 | 80 | 0 | 0 |  | 0 | 120 |  | AHU-22 SA |  | 7
2025-04-07 | 4406 |  | 70168 | A | DONE | 4 | S-M | neal | UWSP CHAMPION HALL 6240008 | bird s. , nipple , MOD | 2025-04-08 | Z | 2025-04-03 | 90 | 0 | 0 |  | 0 | 130 |  | PRV- 6 EA |  | 5
2025-04-07 | 4407 |  | 70169 | A | DONE | 5 | S-M |  | UWSP CHAMPION HALL 6240008 | nipple | 2025-04-08 | Z | 2025-04-03 | 120 | 0 | 0 |  | 0 | 250 |  | RH-3 OA |  | 5
2025-04-10 | 4408 |  | 70170 | A | DONE | 3 | S-M |  | UWSP CHAMPION HALL 6240008 | bird s. , flex | 2025-04-15 | Z | 2025-04-04 | 70 | 0 | 0 |  | 0 | 110 |  | SF-1 |  | 11
2025-04-10 | 4409 |  | 70172 - 70174 | A | DONE | 6 | S-M |  | UWSP CHAMPION HALL 6240008 | paint | 2025-04-15 | Z | 2025-04-04 | 140 | 0 | 0 |  | 130 | 190 |  | EA Plenums |  | 11
2025-04-10 | 4410 |  | 70175 | A | DONE | 2 | S | pt.neal | UWSP CHAMPION HALL 6240008 |  | 2025-04-15 | Z | 2025-04-04 | 30 | 0 | 0 |  | 0 | 40 |  | Rm 149 |  | 11
2025-04-08 | 2029 |  | 79744 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-04-10 | Z | 2025-04-01 | 40 | 0 | 0 |  | 0 | 90 |  | EF-38 |  | 9
2025-04-09 | 1653 |  | PRE-FAB HANGERS | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-09 | Z | 2025-04-09 | 40 | 0 | 0 |  | 0 | 90 |  | Hangers |  | 0
2025-04-10 | 4193 | w | L02_E_GEA_001 | A | DONE | 2 | S | BI | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-02-13 | 50 | 0 | 0 |  | 0 | 160 |  |  |  | 64
2025-04-09 | 1999 | sp | 66192 | A | DONE | 2 | S | neal | WSCC 6240006 | spiral mate | 2025-04-10 | Z | 2025-04-08 | 0 | 20 | 0 |  | 0 | 20 |  | RTU-1 RA |  | 2
2025-04-09 | 2700 | sp | 66193 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-04-10 | Z | 2025-04-09 | 30 | 0 | 0 |  | 0 | 40 |  | RTU-1 RA |  | 1
[6 empty] | 1003 | [13 empty] | 34140
WEEK OF 4-14-2025
2025-04-16 | 265 |  | 85209 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-04-18 | Z | 2025-04-15 | 30 | 0 | 0 |  | 0 | 40 |  | SF-1 |  | 3
2025-04-16 | 266 |  | 85153 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | paint | 2025-04-18 | Z | 2025-04-15 | 20 | 0 | 0 |  | 20 | 20 |  | ERV-2 EA |  | 3
2025-04-16 | 267 |  | 85210 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-04-18 | Z | 2025-04-15 | 40 | 0 | 0 |  | 0 | 100 |  | Sleeve Ext. |  | 3
2025-04-15 | 2477 |  | 69973 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2025-04-22 | Z | 2025-04-10 | 20 | 0 | 0 |  | 0 | 20 |  | Angles |  | 12
2025-04-17 | 868 | sp | 70743 | A | DONE | 6 | S | pcd | DELLSHIRE 6240017 |  | 2025-04-21 | Z | 2025-04-08 | 20 | 120 | 0 |  | 0 | 140 |  | EF-2 |  | 13
2025-04-18 | 869 | w | 73659 | A | DONE | 6 | M |  | DELLSHIRE 6240017 |  | 2025-04-21 | Z | 2025-04-08 | 130 | 0 | 0 |  | 0 | 390 |  | 3rd/4th EA sleeves |  | 13
2025-04-16 | 870 |  | 73863 | A | DONE | 4 | S-M |  | DELLSHIRE 6240017 |  | 2025-04-21 | Z | 2025-04-08 | 100 | 0 | 0 |  | 0 | 120 |  | EF-6 |  | 13
2025-04-17 | 871 | bth | 73866 | A | DONE | 4 | S |  | DELLSHIRE 6240017 | nipple | 2025-04-21 | Z | 2025-04-08 | 70 | 20 | 0 |  | 0 | 90 |  | EF-5 Drop |  | 13
2025-04-16 | 875 | sp | 73872 | A | DONE | 5 | S |  | DELLSHIRE 6240017 |  | 2025-04-21 | Z | 2025-04-09 | 40 | 70 | 0 |  | 0 | 110 |  | VAV reducers |  | 12
2025-04-16 | 1241 |  | 79043 | A | DONE | 2 | S |  | EXACT B6 - 4B 8250004 |  | 2025-04-21 | Z | 2025-04-11 | 20 | 0 | 0 |  | 0 | 20 |  | Waste EA |  | 10
2025-04-16 | 1242 | sp | 79046 | A | DONE | 3 | S |  | EXACT B6 - 4B 8250004 |  | 2025-04-21 | Z | 2025-04-15 | 20 | 50 | 0 |  | 0 | 60 |  | Misc |  | 6
2025-04-14 | 1239 |  | 79044 | A | DONE | 3 | S |  | EXACT TL-3 6240028 |  | 2025-04-16 | Z | 2025-04-11 | 30 | 0 | 0 |  | 0 | 80 |  | Outs |  | 5
2025-04-15 | 3380 | w | 74258 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2025-04-21 | Z | 2025-04-08 | 20 | 0 | 0 |  | 0 | 80 |  | Cond. Pan |  | 13
2025-04-14 | 2949 |  | 82583 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2025-04-16 | Z | 2025-04-14 | 20 | 0 | 0 |  | 0 | 20 |  | B-Section roof |  | 2
2025-04-14 | 1704 | bth | 74259 | A | DONE | 2 | S |  | MADISON COUNTRY 6250005 |  | 2025-04-15 | Z | 2025-04-14 | 20 | 20 | 0 |  | 0 | 30 |  | Misc |  | 1
2025-04-14 | 2685 | bth | SAMP-L1B-01 | A | DONE | 28 | M |  | MONROE HS 6240018 | oval , accuflange | 2025-04-16 | Z | 2025-03-24 | 140 | 540 | 20 | F | 0 | 930 |  |  |  | 23
2025-04-14 | 2686 | sp | SAMP-L1B-02 | A | DONE | 9 | S-M |  | MONROE HS 6240018 |  | 2025-04-16 | Z | 2025-03-24 | 20 | 200 | 0 |  | 0 | 220 |  |  |  | 23
2025-04-14 | 2688 | bth | SAMP-L1B-04 | A | DONE | 25 | M |  | MONROE HS 6240018 | oval , accuflange | 2025-04-16 | Z | 2025-03-24 | 170 | 350 | 100 | F | 0 | 800 |  |  |  | 23
2025-04-14 | 2690 |  | RA-L1B-01 | A | DONE | 47 | L |  | MONROE HS 6240018 | 1" liner | 2025-04-16 | Z | 2025-03-24 | 710 | 0 | 450 | F | 1020 | 2410 |  |  |  | 23
2025-04-14 | 2691 |  | RA-L1B-02 | A | DONE | 18 | M |  | MONROE HS 6240018 | 1" liner | 2025-04-16 | Z | 2025-03-24 | 440 | 0 | 0 |  | 400 | 860 |  |  |  | 23
2025-04-14 | 2692 | bth | RA-L1B-03 | A | DONE | 4 | S |  | MONROE HS 6240018 | flex | 2025-04-16 | Z | 2025-03-24 | 70 | 20 | 0 |  | 0 | 110 |  |  |  | 23
2025-04-14 | 2693 |  | RA-L1B-04 | A | DONE | 8 | S |  | MONROE HS 6240018 | 1" liner | 2025-04-16 | Z | 2025-03-24 | 130 | 0 | 50 | F | 150 | 270 |  |  |  | 23
2025-04-15 | 2695 |  | EA-L1B-02 | A | DONE | 8 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-04-16 | Z | 2025-03-24 | 200 | 0 | 0 |  | 50 | 330 |  |  |  | 23
2025-04-14 | 2696 |  | EA-L1B-03 | A | DONE | 10 | S-M | pt.neal | MONROE HS 6240018 | 1" liner | 2025-04-16 | Z | 2025-03-24 | 150 | 0 | 90 | F | 130 | 350 |  |  |  | 23
2025-04-14 | 2697 | bth | EA-L1B-04 | A | DONE | 14 | S-M |  | MONROE HS 6240018 |  | 2025-04-16 | Z | 2025-03-24 | 160 | 180 | 0 |  | 0 | 390 |  |  |  | 23
2025-04-14 | 2698 |  | EA-L1B-05 | A | DONE | 14 | S-M |  | MONROE HS 6240018 | VD , 1" liner | 2025-04-16 | Z | 2025-03-24 | 130 | 130 | 80 | F | 130 | 410 |  |  |  | 23
2025-04-14 | 2699 | sp | EA-L1B-06 | A | DONE | 4 | S |  | MONROE HS 6240018 |  | 2025-04-16 | Z | 2025-03-24 | 20 | 70 | 0 |  | 0 | 70 |  |  |  | 23
2025-04-16 | 4201 |  | 83118 - 83119 | A | DONE | 5 | S-M |  | PECATONICA ES 6240005 | VD's , 1" liner | 2025-04-21 | Z | 2025-01-30 | 120 | 0 | 0 |  | 100 | 130 |  | AHU-4 RA |  | 81
2025-04-16 | 4202 |  | 83120 - 83121 | A | DONE | 9 | S-M |  | PECATONICA ES 6240005 |  | 2025-04-21 | Z | 2025-01-30 | 210 | 0 | 0 |  | 0 | 370 |  | AHU-4 RA / OA |  | 81
2025-04-16 | 4203 |  | 83122 - 83123 | A | DONE | 14 | S-M |  | PECATONICA ES 6240005 | flex , 1" liner | 2025-04-21 | Z | 2025-01-30 | 240 | 0 | 100 | F | 270 | 510 |  | RE-6 |  | 81
2025-04-16 | 4212 |  | 80198 | A | DONE | 2 | S |  | PECATONICA ES 6240005 | 1" liner | 2025-04-21 | Z | 2025-04-03 | 40 | 0 | 0 |  | 30 | 40 |  | LMC TA |  | 18
2025-04-16 | 4213 |  | 80199 | A | DONE | 2 | S |  | PECATONICA ES 6240005 |  | 2025-04-21 | Z | 2025-04-03 | 20 | 20 | 0 |  | 0 | 20 |  | LMC SA |  | 18
2025-04-16 | 3022 |  | 62733 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-04-21 | Z | 2025-04-15 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2025-04-16 | 940 | bth | 62734 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 |  | 2025-04-21 | Z | 2025-04-15 | 50 | 0 | 0 |  | 0 | 80 |  | Misc |  | 6
2025-04-15 | 4796 |  | 85307 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 | paint | 2025-04-16 | Z | 2025-04-14 | 20 | 0 | 0 |  | 20 | 20 |  | Grille box |  | 2
2025-04-16 | 1414 |  | PTH-OA-001 | A | DONE | 45 | L |  | SPH SURGERY 6240039 |  | 2025-04-18 | Z | 2025-03-26 | 610 | 0 | 510 | F | 0 | 2540 |  |  |  | 23
2025-04-15 | 1415 |  | PTH-OA-002 | A | DONE | 11 | S-M |  | SPH SURGERY 6240039 |  | 2025-04-18 | Z | 2025-03-26 | 80 | 0 | 180 | F | 0 | 380 |  |  |  | 23
2025-04-15 | 1416 |  | PTH-OA-003 | A | DONE | 10 | S-M |  | SPH SURGERY 6240039 | flex | 2025-04-18 | Z | 2025-03-26 | 230 | 0 | 0 |  | 0 | 420 |  |  |  | 23
2025-04-15 | 1417 |  | PTH-OA-004 | A | DONE | 10 | S-M |  | SPH SURGERY 6240039 | flex | 2025-04-18 | Z | 2025-03-26 | 150 | 0 | 90 | F | 0 | 360 |  |  |  | 23
2025-04-15 | 1426 |  | 68854 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-04-18 | Z | 2025-04-08 | 20 | 0 | 0 |  | 0 | 20 |  | FD ext. |  | 10
2025-04-16 | 4053 | sp | 67769 | A | delete | 2 | S | neal | STOUGHTON TRAILERS 6240015 |  | 2025-04-23 | Z | 2025-04-14 | 20 | 20 | 0 |  | 0 | 40 |  | 1st floor |  | 9
2025-04-16 | 195 | sp | 71488 - 71489 | A | DONE | 11 | S-M |  | TIM ABNEY 1000381 |  | 2025-04-18 | Z | 2025-04-10 | 50 | 220 | 0 |  | 0 | 240 |  | Misc |  | 8
2025-04-14 | 4384 |  | 59268 - 59273 | A | DONE | 5 | S-M |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-08 | 120 | 0 | 0 |  | 0 | 270 |  | Cone flashing |  | 8
2025-04-14 | 4388 |  | 59278 | A | DONE | 4 | S-M |  | UW-AVRL 6240038 |  | 2025-04-16 | Z | 2025-04-10 | 80 | 0 | 0 |  | 0 | 210 |  | L5C-EAMP 7 |  | 6
2025-04-17 | 638 |  | 83272 | A | DONE | 2 | S |  | UW-BIO CHEM 6240036 |  | 2025-04-18 | Z | 2025-04-16 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 2
2025-04-16 | 701 | bth | L2-SALP 1 | A | DONE | 14 | S-M | pt.neal | UW-LEVY HALL 6230028 |  | 2025-04-22 | Z | 2025-03-11 | 160 | 90 | 90 | F | 0 | 400 |  |  |  | 42
2025-04-17 | 706 |  | L2-SAT-3-2-14 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 42
2025-04-17 | 707 |  | L2-SAT-3-2-15 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD's , VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 130 | 0 | 40 | F | 110 | 230 |  |  |  | 42
2025-04-18 | 709 |  | L2-SAT-3-2-19 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 | VD's , VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 70 | 0 | 130 | F | 140 | 270 |  |  |  | 42
2025-04-18 | 710 |  | L2-SAT-3-2-20 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD's , VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 120 | 0 | 50 | F | 30 | 230 |  |  |  | 42
2025-04-18 | 725 |  | L2-FCU 3 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-22 | Z | 2025-03-11 | 80 | 0 | 0 |  | 0 | 120 |  |  |  | 42
2025-04-17 | 3195 |  | 82287 - 82290 | A | DONE | 24 | M |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 270 | 120 | 200 | F | 0 | 820 |  | AHU-3 SA |  | 27
2025-04-18 | 3196 | bth | 82291 - 82292 | A | DONE | 24 | S-M |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 180 | 30 | 380 | F | 0 | 800 |  | AHU-3 SA |  | 27
2025-04-18 | 3197 | sp | 82293 - 94 , 82296 | A | DONE | 27 | M |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 60 | 500 | 0 |  | 0 | 570 |  | AHU-3 SA |  | 27
2025-04-18 | 3198 |  | 82378 , 82386 - 87 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-04-21 | Z | 2025-03-25 | 180 | 0 | 0 |  | 170 | 240 |  | TA |  | 27
2025-04-18 | 3199 |  | 82389 - 90 , 82394 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2025-04-21 | Z | 2025-03-25 | 190 | 0 | 0 |  | 170 | 260 |  | TA |  | 27
2025-04-17 | 3900 |  | 84416 - 84418 | A | DONE | 31 | M |  | UWL-GRAFF 6230017 | VD | 2025-04-21 | Z | 2025-03-25 | 230 | 0 | 530 | F | 0 | 1270 |  | AHU-3 RA |  | 27
2025-04-17 | 3901 | bth | 84419 - 84421 | A | DONE | 15 | S-M |  | UWL-GRAFF 6230017 | VD's | 2025-04-21 | Z | 2025-03-25 | 140 | 30 | 200 | F | 0 | 420 |  | AHU-3 RA |  | 27
2025-04-18 | 3902 | bth | 84422 - 84424 | A | DONE | 20 | M |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 180 | 120 | 180 | F | 0 | 630 |  | AHU-1 SA |  | 27
2025-04-17 | 3903 |  | 84482 - 84484 | A | DONE | 22 | S-M |  | UWL-GRAFF 6230017 | VD's | 2025-04-21 | Z | 2025-03-25 | 270 | 0 | 260 | F | 0 | 630 |  | 1st RA |  | 27
2025-04-17 | 3904 |  | 84487 - 84489 | A | DONE | 21 | M |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 370 | 0 | 140 | F | 0 | 720 |  | AHU-1 SA |  | 27
2025-04-17 | 3905 | sp | 84491 - 84492 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 20 | 120 | 0 |  | 0 | 120 |  | AHU-1 SA |  | 27
2025-04-18 | 3906 |  | 84494 - 84498 | A | DONE | 40 | M |  | UWL-GRAFF 6230017 | VD's | 2025-04-21 | Z | 2025-03-25 | 350 | 0 | 650 | F | 0 | 1390 |  | AHU-1 RA |  | 27
2025-04-16 | 3907 |  | 84642 - 84644 | A | DONE | 21 | S-M |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 290 | 0 | 230 | F | 0 | 710 |  | AHU-1 SA |  | 27
2025-04-18 | 3908 | sp | 84645 | A | DONE | 7 | S |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 40 | 130 | 0 |  | 0 | 150 |  | AHU SA |  | 27
2025-04-18 | 3909 |  | 84649 - 84650 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-04-21 | Z | 2025-03-25 | 130 | 0 | 0 |  | 0 | 180 |  | 135 B , C |  | 27
2025-04-18 | 3910 |  | 84659 - 84662 | A | DONE | 22 | S-M |  | UWL-GRAFF 6230017 | VD's | 2025-04-21 | Z | 2025-03-25 | 240 | 0 | 290 | F | 0 | 640 |  | AHU-1 RA |  | 27
2025-04-18 | 3911 |  | 84663 - 84665 | A | DONE | 14 | S-M |  | UWL-GRAFF 6230017 | VD's | 2025-04-21 | Z | 2025-03-25 | 80 | 0 | 250 | F | 0 | 420 |  | AHU-1 RA |  | 27
2025-04-17 | 3912 | sp | 84666 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-25 | 20 | 20 | 0 |  | 0 | 40 |  | AHU-1 RA |  | 27
2025-04-16 | 3940 |  | 84677 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-26 | 20 | 0 | 0 |  | 0 | 30 |  | 2nd RA |  | 26
2025-04-16 | 3942 |  | 84682 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-04-21 | Z | 2025-03-26 | 30 | 0 | 0 |  | 0 | 40 |  | RA Rm 233C |  | 26
2025-04-17 | 3947 |  | 84696 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | VD | 2025-04-21 | Z | 2025-04-09 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd RA SO |  | 12
2025-04-16 | 1851 |  | 69534 | A | DONE | 2 | S |  | UWP-FH 6240021 |  | 2025-04-17 | Z | 2025-04-15 | 50 | 0 | 0 |  | 0 | 130 |  | 2nd floor |  | 2
2025-04-14 | 1850 |  | 69532 | A | DONE | 3 | S |  | UWP-WFH 6240021 |  | 2025-04-17 | Z | 2025-04-04 | 70 | 0 | 0 |  | 0 | 170 |  | Gym |  | 13
2025-04-18 | 1141 |  | 84823 - 84824 | A | DONE | 2 | S |  | UWRF 6230010 | paint , 1" liner | 2025-04-22 | Z | 2025-04-08 | 50 | 0 | 0 |  | 40 | 80 |  | L2-TA |  | 14
2025-04-17 | 1142 |  | 84825 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-04-22 | Z | 2025-04-08 | 30 | 0 | 0 |  | 30 | 50 |  | L2-TA |  | 14
2025-04-17 | 3257 |  | 81282 | A | DONE | 4 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-04-22 | Z | 2025-04-15 | 100 | 0 | 0 |  | 0 | 120 |  | Flashing |  | 7
2025-04-16 | 4411 | bth | 70176 | A | DONE | 4 | S-M |  | UWSP CHAMPIONS 6240008 | paint | 2025-04-22 | Z | 2025-04-15 | 80 | 20 | 0 |  | 60 | 110 |  | EA Plenums |  | 7
2025-04-15 | 2024 |  | 79728 - 79730 | A | DONE | 4 | S-M |  | UW-VET MED 6210014 | coils | 2025-04-17 | Z | 2025-03-28 | 90 | 0 | 0 |  | 0 | 130 |  | 10 D SA |  | 20
2025-04-14 | 2025 |  | 79731 - 79734 | A | DONE | 4 | S-M |  | UW-VET MED 6210014 | coils | 2025-04-17 | Z | 2025-03-28 | 90 | 0 | 0 |  | 0 | 140 |  | 10 D SA |  | 20
2025-04-15 | 2026 | sp | 79735 - 79738 | A | DONE | 9 | S-M |  | UW-VET MED 6210014 |  | 2025-04-17 | Z | 2025-03-28 | 30 | 180 | 0 |  | 0 | 230 |  | 10 D SA 2 |  | 20
2025-04-15 | 2027 | sp | 79739 - 79742 | A | DONE | 9 | S-M |  | UW-VET MED 6210014 |  | 2025-04-17 | Z | 2025-03-28 | 20 | 190 | 0 |  | 0 | 220 |  | 10 D SA 2 |  | 20
2025-04-14 | 2028 |  | 79743 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 |  | 2025-04-17 | Z | 2025-03-28 | 20 | 0 | 0 |  | 0 | 20 |  | 10 D SA 2 |  | 20
2025-04-15 | 2031 |  | 79747 | A | DONE | 3 | S |  | UW-VET MED 6210014 |  | 2025-04-17 | Z | 2025-04-11 | 70 | 0 | 0 |  | 0 | 100 |  | 10 D outs |  | 6
2025-04-15 | 1654 |  | 79826 | A | DONE | 2 | S | pt.neal | WAUNAKEE MS 6230013 | 1" liner | 2025-04-18 | Z | 2025-04-10 | 40 | 0 | 0 |  | 30 | 50 |  | HP 3-127 RA |  | 8
2025-04-15 | 1655 |  | 79825 | A | DONE | 3 | S | neal | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-04-10 | 60 | 0 | 0 |  | 0 | 70 |  | 1st G HP 3-127 SA |  | 8
2025-04-17 | 1657 |  | 79828 | A | DONE | 3 | S | neal | WAUNAKEE MS 6230013 |  | 2025-04-24 | Z | 2025-04-11 | 60 | 0 | 0 |  | 0 | 110 |  | G-Section flashing |  | 13
2025-04-16 | 1658 |  | 79829 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-24 | Z | 2025-04-11 | 20 | 0 | 0 |  | 0 | 30 |  | 1st G-Section flashing |  | 13
2025-04-16 | 1659 |  | 79874 | A | DONE | 4 | S-M | alum | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-04-11 | 20 | 70 | 0 |  | 0 | 50 |  | Dryer vent |  | 7
2025-04-14 | 4175 |  | L02_E_RAD_001 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 120 | 0 | 40 | F | 130 | 230 |  |  |  | 64
2025-04-15 | 4176 |  | L02_E_RAD_002 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 100 | 0 | 0 |  | 90 | 150 |  |  |  | 64
2025-04-16 | 4177 | bth | L02_E_RAD_003 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 60 | 70 | 0 |  | 30 | 130 |  |  |  | 64
2025-04-16 | 4178 | sp | L02_E_RAD_004 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-02-13 | 20 | 120 | 0 |  | 0 | 130 |  |  |  | 64
2025-04-15 | 4179 |  | L02_E_RAD_005 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 64
2025-04-15 | 4180 |  | L02_E_RAD_006 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 60 | 0 | 0 |  | 50 | 100 |  |  |  | 64
2025-04-15 | 4181 |  | L02_E_RAD_007 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 40 | 0 | 0 |  | 40 | 70 |  |  |  | 64
2025-04-15 | 4182 |  | L02_E_RAD_008 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 70 | 0 | 0 |  | 50 | 120 |  |  |  | 64
2025-04-15 | 4183 |  | L02_E_RAD_009 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 70 | 0 | 0 |  | 50 | 120 |  |  |  | 64
2025-04-15 | 4184 |  | L02_E_RAD_010 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 80 | 0 | 0 |  | 60 | 130 |  |  |  | 64
2025-04-15 | 4185 |  | L02_E_RAD_011 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 110 | 0 | 0 |  | 90 | 160 |  |  |  | 64
2025-04-15 | 4186 |  | L02_E_RAD_012 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 64
2025-04-16 | 4187 | bth | L02_E_RAD_013 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 100 | 30 | 0 |  | 60 | 170 |  |  |  | 64
2025-04-16 | 4188 | sp | L02_E_RAD_014 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-02-13 | 30 | 140 | 0 |  | 0 | 160 |  |  |  | 64
2025-04-16 | 4189 | bth | L02_E_RAD_015 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 40 | 40 | 0 |  | 30 | 90 |  |  |  | 64
2025-04-15 | 4190 | bth | L02_E_RAD_016 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 40 | 20 | 0 |  | 30 | 60 |  |  |  | 64
2025-04-15 | 4191 |  | L02_E_RAD_017 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 50 | 20 | 0 |  | 30 | 60 |  |  |  | 64
2025-04-15 | 4192 |  | L02_E_RAD_018 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-04-18 | Z | 2025-02-13 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 64
2025-04-16 | 4194 | bth | L02_E_SALP_001 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 60 | 40 | 80 | F | 0 | 210 |  |  |  | 64
2025-04-15 | 4195 | bth | L02_E_SALP_002 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 100 | 40 | 120 | F | 0 | 290 |  |  |  | 64
2025-04-16 | 4196 | bth | L02_E_SALP_003 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 50 | 110 | 0 |  | 0 | 160 |  |  |  | 64
2025-04-16 | 4197 | sp | L02_E_SALP_004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-02-13 | 20 | 60 | 0 |  | 0 | 70 |  |  |  | 64
2025-04-16 | 4198 | bth | L02_E_SALP_005 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 60 | 50 | 0 |  | 0 | 130 |  |  |  | 64
2025-04-15 | 4199 |  | L02_E_SALP_006 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 64
2025-04-16 | 4250 | bth | L02_E_SALP_007 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 140 | 70 | 0 |  | 0 | 260 |  |  |  | 64
2025-04-16 | 4251 | bth | L02_E_SALP_008 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 130 | 80 | 140 | F | 0 | 390 |  |  |  | 64
2025-04-16 | 4252 | bth | L02_E_SALP_009 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 110 | 70 | 140 | F | 0 | 390 |  |  |  | 64
2025-04-15 | 4253 | bth | L02_E_SALP_010 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 150 | 40 | 80 | F | 0 | 330 |  |  |  | 64
2025-04-15 | 4254 | bth | L02_E_SALP_011 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 110 | 40 | 50 | F | 0 | 240 |  |  |  | 64
2025-04-15 | 4255 | bth | L02_E_SALP_012 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 60 | 160 | 0 |  | 0 | 210 |  |  |  | 64
2025-04-16 | 4256 | sp | L02_E_SALP_013 | A | DONE | 10 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-02-13 | 40 | 190 | 0 |  | 0 | 220 |  |  |  | 64
2025-04-15 | 4257 | bth | L02_E_SALP_014 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 50 | 20 | 0 |  | 0 | 70 |  |  |  | 64
2025-04-16 | 4258 | sp | L02_E_SALP_015 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-02-13 | 30 | 160 | 0 |  | 0 | 190 |  |  |  | 64
2025-04-16 | 4259 | bth | L02_E_SALP_016 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 30 | 70 | 0 |  | 0 | 100 |  |  |  | 64
2025-04-16 | 4260 | bth | L02_E_SALP_017 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 30 | 40 | 0 |  | 0 | 80 |  |  |  | 64
2025-04-15 | 4261 | bth | L02_E_SALP_018 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-04-18 | Z | 2025-02-13 | 50 | 80 | 0 |  | 0 | 130 |  |  |  | 64
2025-04-16 | 1198r | w | 79869 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-18 | Z | 2025-04-08 | 110 | 0 | 0 |  | 0 | 270 |  | Rail ext. |  | 10
2025-04-15 | 2701 |  | 66194 | A | DONE | 2 | S | neal | WSCC 6240006 | 1" liner | 2025-04-17 | Z | 2025-04-14 | 30 | 0 | 0 |  | 20 | 40 |  | VAV -1-6 |  | 3
2025-04-18 | 2702 | w | 66195 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-04-21 | Z | 2025-04-17 | 20 | 0 | 0 |  | 0 | 60 |  | Cap JPC |  | 4
[6 empty] | 1022 | [13 empty] | 33330 |  |  |  | 3590 | 10.77%
WEEK OF 4-21-2025
2025-04-21 | 268 |  | 85155 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-04-24 | Z | 2025-04-21 | 20 | 0 | 0 |  | 0 | 20 |  | TA Fan outs |  | 3
2025-04-23 | 269 | sp | 85211 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 |  | 2025-04-24 | Z | 2025-04-21 | 20 | 160 | 0 |  | 0 | 150 |  | DOAS-2 OA |  | 3
2025-04-23 | 270 |  | 85213 - 85214 | A | DONE | 6 | S-M |  | 121 E. WILSON 6230024 |  | 2025-04-24 | Z | 2025-04-21 | 140 | 0 | 0 |  | 0 | 150 |  | DOAS-1,2 outs |  | 3
2025-04-23 | 271 |  | 85215 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-04-24 | Z | 2025-04-22 | 20 | 0 | 0 |  | 0 | 50 |  | Spiral hangers |  | 2
2025-04-21 | 198 |  | 83273 | A | DONE | 2 | S |  | 441 CHARMANY 6240009 |  | 2025-04-24 | Z | 2025-04-16 | 30 | 0 | 0 |  | 0 | 40 |  | Misc |  | 8
2025-04-21 | 197 |  | 84703 | A | DONE | 2 | S-M |  | ACS 10061682 |  | 2025-04-22 | Z | 2025-04-15 | 40 | 0 | 0 |  | 0 | 100 |  | RTU-3 |  | 7
2025-04-25 | 2252 |  | 86381 | A | DONE | 2 | S | BI | BARTILLION 6240024 |  | 2025-04-28 | Z | 2025-04-25 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 3
2025-04-23 | 2481 |  | 69976 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-04-25 | Z | 2025-04-23 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 2
2025-04-24 | 826 |  | 70751.2 | A | DONE | 2 | S-M |  | DELLSHIRE 6240017 |  | 2025-04-28 | Z | 2025-02-12 | 30 | 0 | 0 |  | 0 | 40 |  | 3rd Floor hangers |  | 75
2025-04-25 | 855 | sp | 70730 | A | DONE | 53 | L |  | DELLSHIRE 6240017 |  | 2025-04-28 | Z | 2025-03-14 | 50 | 1260 | 0 |  | 0 | 1180 |  | 3RD FL-EG-12 |  | 45
2025-04-21 | 867 | w | NO 1. | A | DONE | 24 | S-M | neal | DELLSHIRE 6240017 | bird s. | 2025-04-21 | Z | 2025-04-08 | 440 | 160 | 0 |  | 0 | 1110 |  | EA roof caps |  | 13
2025-04-24 | 872 | w | 73660 | A | DONE | 3 | S-M |  | DELLSHIRE 6240017 |  | 2025-04-28 | Z | 2025-04-08 | 60 | 0 | 0 |  | 0 | 190 |  | 4th Floor C/D EA sleeves |  | 20
2025-04-25 | 873 | bth | 73868 - 73869 | A | DONE | 7 | S |  | DELLSHIRE 6240017 |  | 2025-04-28 | Z | 2025-04-09 | 140 | 20 | 0 |  | 0 | 260 |  | EF-7 |  | 19
2025-04-24 | 874 | sp | 73871 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-04-28 | Z | 2025-04-09 | 0 | 40 | 0 |  | 0 | 40 |  | EF-7 |  | 19
2025-04-24 | 876 | bth | 73875 - 73876 | A | DONE | 4 | S-M |  | DELLSHIRE 6240017 |  | 2025-04-28 | Z | 2025-04-16 | 30 | 40 | 30 | F | 0 | 110 |  | Basement |  | 12
2025-04-25 | 1243 |  | 56699A | A | DONE | 2 | S |  | EXACT SCIENCE 8250004 |  | 2025-04-30 | Z | 2025-04-16 | 30 | 0 | 0 |  | 0 | 50 |  | Stool Buffer |  | 14
2025-04-22 | 2551 |  | 82584 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2025-04-23 | Z | 2025-04-21 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor |  | 2
2025-04-24 | 2552 |  | 82585 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2025-04-28 | Z | 2025-04-24 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd Floor |  | 4
2025-04-25 | 2553 |  | 82586 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2025-04-28 | Z | 2025-04-25 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor |  | 3
2025-04-22 | 1501 | sp | FE-L1B-01 | A | DONE | 5 | S |  | MONROE HS 6240018 |  | 2025-04-23 | Z | 2025-03-24 | 20 | 100 | 0 |  | 0 | 110 |  |  |  | 30
2025-04-22 | 1502 | w | KE-L1B-01 | A | DONE | 7 | S-M | ss | MONROE HS 6240018 |  | 2025-04-23 | Z | 2025-03-24 | 160 | 0 | 0 |  | 0 | 460 |  |  |  | 30
2025-04-23 | 1503 | w | KE-L1B-02 | A | DONE | 3 | S | ss | MONROE HS 6240018 |  | 2025-04-23 | Z | 2025-03-24 | 60 | 0 | 0 |  | 0 | 150 |  |  |  | 30
2025-04-22 | 1504 |  | OA-L1B-01 | A | DONE | 4 | S |  | MONROE HS 6240018 | flex , CD | 2025-04-23 | Z | 2025-03-24 | 80 | 0 | 0 |  | 0 | 110 |  |  |  | 30
2025-04-22 | 1505 |  | OA-L1B-02 | A | DONE | 6 | S |  | MONROE HS 6240018 | flex , CD | 2025-04-23 | Z | 2025-03-24 | 150 | 0 | 0 |  | 30 | 230 |  |  |  | 30
2025-04-22 | 1506 | bth | SALP-L1B-01 | A | DONE | 14 | S-M |  | MONROE HS 6240018 | VD's , 2" liner | 2025-04-23 | Z | 2025-03-24 | 200 | 30 | 110 | F | 230 | 480 |  |  |  | 30
2025-04-22 | 1507 | bth | SALP-L1B-02 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 170 | 60 | 30 | F | 120 | 300 |  |  |  | 30
2025-04-22 | 1508 | bth | SALP-L1B-03 | A | DONE | 15 | S-M |  | MONROE HS 6240018 | VD's , 2" liner | 2025-04-23 | Z | 2025-03-24 | 240 | 20 | 100 | F | 240 | 470 |  |  |  | 30
2025-04-22 | 1509 | bth | SALP-L1B-04 | A | DONE | 13 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 150 | 20 | 150 | F | 250 | 460 |  |  |  | 30
2025-04-22 | 1510 | bth | SALP-L1B-05 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 90 | 60 | 30 | F | 80 | 200 |  |  |  | 30
2025-04-22 | 1511 | bth | SALP-L1B-06 | A | DONE | 14 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 130 | 50 | 150 | F | 260 | 450 |  |  |  | 30
2025-04-22 | 1512 | bth | SALP-L1B-07 | A | DONE | 22 | M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 250 | 200 | 80 | F | 230 | 600 |  |  |  | 30
2025-04-23 | 1513 | bth | SALP-L1B-08 | A | DONE | 25 | M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 190 | 270 | 150 | F | 240 | 740 |  |  |  | 30
2025-04-23 | 1514 | bth | SALP-L1B-09 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 90 | 50 | 60 | F | 100 | 240 |  |  |  | 30
2025-04-23 | 1515 | bth | SALP-L1B-10 | A | DONE | 20 | M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 260 | 150 | 70 | F | 220 | 610 |  |  |  | 30
2025-04-23 | 1516 | bth | SALP-L1B-11 | A | DONE | 21 | M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 130 | 120 | 260 | F | 300 | 640 |  |  |  | 30
2025-04-23 | 1517 | bth | SALP-L1B-12 | A | DONE | 20 | M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 210 | 60 | 210 | F | 330 | 670 |  |  |  | 30
2025-04-23 | 1518 | bth | SALP-L1B-13 | A | DONE | 38 | M-L | pt.neal | MONROE HS 6240018 | VD's , 2" liner | 2025-04-23 | Z | 2025-03-24 | 590 | 20 | 330 | F | 610 | 1340 |  |  |  | 30
2025-04-23 | 1519 |  | SALP-L1B-14 | A | DONE | 38 | M-L |  | MONROE HS 6240018 | VD's , 2" liner | 2025-04-23 | Z | 2025-03-24 | 620 | 0 | 330 | F | 680 | 1570 |  |  |  | 30
2025-04-23 | 1520 |  | SALP-L1B-15 | A | DONE | 49 | M-L |  | MONROE HS 6240018 | flex | 2025-04-23 | Z | 2025-03-24 | 740 | 0 | 480 | F | 0 | 2020 |  |  |  | 30
2025-04-23 | 1521 |  | SALP-L1B-16 | A | DONE | 17 | M |  | MONROE HS 6240018 | VD's | 2025-04-23 | Z | 2025-03-24 | 340 | 0 | 80 | F | 0 | 570 |  |  |  | 30
2025-04-23 | 1522 | sp | SALP-L1B-17 | A | DONE | 9 | S-M |  | MONROE HS 6240018 | flex | 2025-04-23 | Z | 2025-03-24 | 80 | 140 | 0 |  | 0 | 280 |  |  |  | 30
2025-04-23 | 1523 | bth | SALP-L1B-18 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-04-23 | Z | 2025-03-24 | 190 | 70 | 40 | F | 130 | 390 |  |  |  | 30
2025-04-23 | 1524 |  | TA-L1B-01 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-04-23 | Z | 2025-03-24 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 30
2025-04-22 | 1552 | sp | 83603 | A | DONE | 10 | S-M | pcd | MONROE HS 6240018 | accuflange , 2" DW | 2025-04-23 | Z | 2025-04-02 | 40 | 190 | 0 |  | 100 | 380 |  | Orchestra Underground |  | 21
2025-04-22 | 1586 | sp | 83607 | A | DONE | 8 | S-M | pcd | MONROE HS 6240018 | accuflange , 2" DW | 2025-04-23 | Z | 2025-04-14 | 20 | 170 | 0 |  | 100 | 320 |  | Orchestra Underground |  | 9
2025-04-21 | 2687 | sp | SAMP-L1B-03 | A | DONE | 33 | M-L |  | MONROE HS 6240018 | oval , accuflange | 2025-04-23 | Z | 2025-03-24 | 200 | 620 | 0 |  | 0 | 1060 |  |  |  | 30
2025-04-23 | 196 |  | 84702 | A | DONE | 2 | S |  | OAKWOOD TABOR 4240059 |  | 2025-04-29 | Z | 2025-04-15 | 20 | 0 | 0 |  | 20 | 30 |  | AHU-1 |  | 14
2025-04-21 | 199 | w | 84278 | A | DONE | 2 | S |  | PAN 10061541 |  | 2025-04-21 | Z | 2025-04-21 | 20 | 0 | 0 |  | 0 | 50 |  | Pan |  | 0
2025-04-24 | 4214 |  | 79683 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2025-04-28 | Z | 2025-04-22 | 20 | 0 | 0 |  | 0 | 40 |  | OA |  | 6
2025-04-24 | 3023 |  | 62732 - 62735 | A | DONE | 30 | M |  | PROMEGA BTC 6230022 |  | 2025-04-28 | Z | 2025-04-17 | 100 | 0 | 630 | F | 0 | 1030 |  | RA |  | 11
2025-04-22 | 941 |  | 84279 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 | VD's | 2025-04-22 | Z | 2025-04-22 | 20 | 0 | 0 |  | 0 | 20 |  | Dampers |  | 0
2025-04-24 | 1427 |  | 68462 - 68463 | A | DONE | 9 | S |  | SPH SURGERY 6240039 |  | 2025-04-28 | Z | 2025-04-14 | 20 | 0 | 200 | F | 0 | 250 |  | Phase 1C |  | 14
2025-04-24 | 1428 | bth | 68464 - 68466 | A | DONE | 15 | S-M |  | SPH SURGERY 6240039 |  | 2025-04-28 | Z | 2025-04-14 | 50 | 30 | 290 | F | 0 | 510 |  | Phase 1C |  | 14
2025-04-24 | 1429 | sp | 68467 | A | DONE | 7 | S-M |  | SPH SURGERY 6240039 |  | 2025-04-28 | Z | 2025-04-14 | 50 | 120 | 0 |  | 0 | 190 |  | VAV 5-14 |  | 14
2025-04-24 | 1430 |  | 68855 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-04-28 | Z | 2025-04-14 | 20 | 0 | 0 |  | 0 | 20 |  | Silencer Frames |  | 14
2025-04-21 | 2407 |  | 79976 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2025-04-23 | Z | 2025-04-16 | 40 | 0 | 0 |  | 0 | 40 |  | RA outs |  | 7
2025-04-23 | 2408 | bth | 79977 | A | DONE | 6 | S-M |  | ST.BERNARD 6230023 |  | 2025-04-25 | Z | 2025-04-21 | 90 | 50 | 0 |  | 0 | 120 |  | TF-1 |  | 4
2025-04-22 | 4055 |  | 83045 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-04-23 | Z | 2025-04-21 | 70 | 0 | 0 |  | 0 | 90 |  | Lobby ceiling |  | 2
2025-04-24 | 807 |  | 73563 | A | DONE | 4 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-04-28 | Z | 2025-04-22 | 100 | 0 | 0 |  | 0 | 140 |  | Caps / patches |  | 6
2025-04-24 | 201 |  | 84714 | A | DONE | 2 | S |  | THERMO FISHER 10062095 |  | 2025-04-28 | Z | 2025-04-22 | 20 | 0 | 0 |  | 0 | 50 |  | AHU 4115 |  | 6
2025-04-22 | 4389 |  | 59279 - 59281 | A | DONE | 5 | S-M |  | UW-AVRL 6240038 |  | 2025-04-23 | Z | 2025-04-17 | 180 | 0 | 0 |  | 0 | 240 |  | Outs |  | 6
2025-04-22 | 4390 | bth | 59282 - 59284 | A | DONE | 5 | S-M |  | UW-AVRL 6240038 | paint | 2025-04-23 | Z | 2025-04-17 | 100 | 20 | 0 |  | 90 | 220 |  | Outs |  | 6
2025-04-25 | 4392 |  | 69139 | A | DONE | 10 | S |  | UW-AVRL 6240038 |  | 2025-04-30 | Z | 2025-04-23 | 230 | 0 | 0 |  | 0 | 260 |  | Flashing |  | 7
2025-04-21 | 702 | bth | L2-SAT-3-2-10 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 40 | 20 | 30 | F | 30 | 90 |  |  |  | 42
2025-04-21 | 703 | bth | L2-SAT-3-2-11 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 20 | 20 | 30 | F | 20 | 70 |  |  |  | 42
2025-04-21 | 704 | bth | L2-SAT-3-2-12 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 80 | 40 | 40 | F | 30 | 190 |  |  |  | 42
2025-04-21 | 705 | bth | L2-SAT-3-2-13 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 30 | 20 | 40 | F | 30 | 100 |  |  |  | 42
2025-04-21 | 708 | bth | L2-SAT-3-2-18 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 100 | 130 | 110 | F | 150 | 410 |  |  |  | 42
2025-04-21 | 711 | bth | L2-SAT-3-2-21 | A | DONE | 8 | S-M | pt.neal | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 110 | 80 | 0 |  | 30 | 230 |  |  |  | 42
2025-04-21 | 721 | bth | L2-SAT-3-2-31 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 40 | 20 | 0 |  | 30 | 70 |  |  |  | 42
2025-04-21 | 723 | bth | L2-SAT-3-2-8 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 42
2025-04-21 | 724 |  | L2-SAT-3-2-9 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-04-22 | Z | 2025-03-11 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 42
2025-04-25 | 741 | bth | L3-SAMP 15 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-29 | Z | 2025-04-02 | 80 | 80 | 50 | F | 0 | 230 |  |  |  | 27
2025-04-21 | 4047 |  | L1-SAMP 1 | A | DONE | 22 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-22 | Z | 2025-04-15 | 480 | 0 | 50 | F | 160 | 940 |  |  |  | 7
2025-04-21 | 4048 |  | L1-SAMP 2 | A | DONE | 63 | M-L |  | UW-LEVY HALL 6230028 | 1" DW | 2025-04-22 | Z | 2025-04-15 | 1380 | 0 | 190 | F | 940 | 2230 |  |  |  | 7
2025-04-21 | 4049 |  | L1-TA 5 | A | DONE | 20 | S |  | UW-LEVY HALL 6230028 | bird s. , 1" liner | 2025-04-22 | Z | 2025-04-15 | 490 | 0 | 0 |  | 410 | 730 |  |  |  | 7
2025-04-24 | 3948 |  | 84697 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | VD | 2025-04-28 | Z | 2025-04-15 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd RA |  | 13
2025-04-24 | 3949 |  | 84698 - 84700 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 | VD | 2025-04-28 | Z | 2025-04-16 | 60 | 0 | 0 |  | 0 | 90 |  | 3rd RA |  | 12
2025-04-24 | 1143 |  | 84827 - 84829 | A | DONE | 5 | S-M | pcd | UWRF 6230010 |  | 2025-04-29 | Z | 2025-04-16 | 110 | 0 | 0 |  | 0 | 180 |  | 1st floor fume |  | 13
2025-04-24 | 1144 |  | 84830 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-04-29 | Z | 2025-04-16 | 20 | 0 | 0 |  | 20 | 30 |  | Rm 115 GE |  | 13
2025-04-24 | 1145 | bth | 84831 - 84833 | A | DONE | 10 | S-M | pcd | UWRF 6230010 |  | 2025-04-29 | Z | 2025-04-16 | 220 | 30 | 0 |  | 0 | 290 |  | Rm 111 fume , L1 fume |  | 13
2025-04-24 | 1146 | sp | 84834 , 84851 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-04-29 | Z | 2025-04-16 | 20 | 20 | 0 |  | 0 | 40 |  | L1 SA |  | 13
2025-04-24 | 1147 |  | 84853 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-04-29 | Z | 2025-04-16 | 20 | 0 | 0 |  | 0 | 20 |  | Rm 296 GE |  | 13
2025-04-23 | 1148 |  | 84835 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-04-29 | Z | 2025-04-17 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 12
2025-04-25 | 3254 |  | 81277 - 81278 | A | DONE | 16 | M-L |  | UWSP ALBERTSON 6230016 | paint | 2025-04-29 | Z | 2025-04-15 | 380 | 0 | 0 |  | 270 | 1200 |  | Louver East |  | 14
2025-04-25 | 3255 |  | 81279 - 81280 | A | DONE | 16 | M-L |  | UWSP ALBERTSON 6230016 | paint | 2025-04-29 | Z | 2025-04-15 | 380 | 0 | 0 |  | 270 | 1200 |  | Louver West |  | 14
2025-04-24 | 3256 |  | 81281 | A | DONE | 5 | M |  | UWSP ALBERTSON 6230016 | paint | 2025-04-29 | Z | 2025-04-15 | 120 | 0 | 0 |  | 120 | 360 |  | Blank off Louver |  | 14
2025-04-25 | 4412 |  | 70177 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | paint | 2025-04-29 | Z | 2025-04-24 | 30 | 0 | 0 |  | 30 | 50 |  | TA |  | 5
2025-04-23 | 2032 |  | 79748 | A | DONE | 4 | S |  | UW-VET MED 6210014 |  | 2025-04-24 | Z | 2025-04-16 | 50 | 0 | 30 | F | 0 | 90 |  | 10-D misc |  | 8
2025-04-23 | 2033 |  | 57607 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-04-24 | Z | 2025-04-22 | 20 | 0 | 0 |  | 0 | 30 |  | Flashing |  | 2
2025-04-24 | 950 | bth | L01_E_SOA_010 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 40 | 60 | 120 | F | 0 | 240 |  |  |  | 67
2025-04-24 | 951 | bth | L01_E_SOA_011 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 40 | 100 | 50 | F | 0 | 190 |  |  |  | 67
2025-04-24 | 1656 | sp | 79827 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 | flex , spiralmate | 2025-04-25 | Z | 2025-04-11 | 20 | 0 | 0 |  | 0 | 50 |  | EF-1 |  | 14
2025-04-23 | 1660 |  | 79830 - 79831 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 120 | 0 | 0 |  | 0 | 220 |  | 1st E EA |  | 4
2025-04-24 | 1661 |  | 79833 - 79834 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 30 | 0 | 0 |  | 0 | 40 |  | SOA N Shaft |  | 4
2025-04-23 | 1662 |  | PRE-FAB HANGERS | A | DONE | 3 | S | neal | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 70 | 0 | 0 |  | 0 | 190 |  | Hangers |  | 4
2025-04-25 | 1663 | sp | L01_G_DCA_002 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 60 | 160 | 0 |  | 0 | 380 |  |  |  | 4
2025-04-25 | 1665 | sp | L01_G_DCA_004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 40 | 60 | 0 |  | 0 | 170 |  |  |  | 4
2025-04-25 | 1666 | sp | L01_G_DCA_005 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 4
2025-04-25 | 1667 | sp | L01_G_DCA_006 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 40 | 30 | 0 |  | 0 | 130 |  |  |  | 4
2025-04-25 | 1681 | w | 79876 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-22 | 20 | 0 | 0 |  | 0 | 20 |  | Baseboard mock up |  | 3
2025-04-24 | 4262 | sp | L01_E_EAD_001 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 80 | 20 | 140 | F | 0 | 300 |  |  |  | 67
2025-04-24 | 4263 | bth | L01_E_EAD_002 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 50 | 30 | 200 | F | 0 | 320 |  |  |  | 67
2025-04-23 | 4264 | sp | L01_E_EAD_003 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 67
2025-04-24 | 4265 |  | L01_E_EAD_004 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 190 | 0 | 50 | F | 0 | 410 |  |  |  | 67
2025-04-24 | 4266 |  | L01_E_EAD_005 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 140 | 50 | 170 | F | 0 | 420 |  |  |  | 67
2025-04-24 | 4267 | bth | L01_E_EAD_006 | A | DONE | 19 | M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 110 | 20 | 340 | F | 0 | 570 |  |  |  | 67
2025-04-23 | 4268 | sp | L01_E_EAD_007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 67
2025-04-24 | 4269 | bth | L01_E_EAD_008 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 50 | 100 | 100 | F | 0 | 280 |  |  |  | 67
2025-04-24 | 4270 |  | L01_E_EAD_009 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 50 | 0 | 130 | F | 0 | 230 |  |  |  | 67
2025-04-23 | 4271 | sp | L01_E_EAD_010 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 20 | 100 | 0 |  | 0 | 110 |  |  |  | 67
2025-04-23 | 4272 | sp | L01_E_EAD_011 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 20 | 50 | 0 |  | 0 | 50 |  |  |  | 67
2025-04-24 | 4291 | bth | L01_E_SOA_001 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 220 | 30 | 100 | F | 0 | 400 |  |  |  | 67
2025-04-24 | 4292 |  | L01_E_SOA_002 | A | DONE | 15 | M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 0 | 0 | 360 | F | 0 | 450 |  |  |  | 67
2025-04-24 | 4293 | sp | L01_E_SOA_003 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 30 | 60 | 0 |  | 0 | 90 |  |  |  | 67
2025-04-24 | 4294 |  | L01_E_SOA_004 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 90 | 0 | 150 | F | 0 | 320 |  |  |  | 67
2025-04-24 | 4295 | bth | L01_E_SOA_005 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 40 | 20 | 220 | F | 0 | 320 |  |  |  | 67
2025-04-24 | 4296 |  | L01_E_SOA_006 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 70 | 0 | 60 | F | 0 | 150 |  |  |  | 67
2025-04-23 | 4297 | sp | L01_E_SOA_007 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 20 | 40 | 0 |  | 0 | 40 |  |  |  | 67
2025-04-23 | 4298 | sp | L01_E_SOA_008 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 67
2025-04-24 | 4299 | bth | L01_E_SOA_009 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-02-17 | 20 | 40 | 220 | F | 0 | 320 |  |  |  | 67
2025-04-23 | 2703 | sp | 66196 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-04-24 | Z | 2025-04-21 | 20 | 0 | 0 |  | 0 | 20 |  | Fan 03 EA |  | 3
[6 empty] | 1134 | [13 empty] | 37520 |  |  |  | 10440 | 27.83%
WEEK OF 4-28-2025
2025-04-29 | 272 |  | 85216 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | paint | 2025-05-01 | Z | 2025-04-25 | 30 | 0 | 0 |  | 30 | 40 |  | IDF TA |  | 6
2025-04-29 | 273 |  | 85217 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2025-05-01 | Z | 2025-04-25 | 20 | 0 | 0 |  | 20 | 40 |  | 1311 TA |  | 6
2025-04-30 | 274 |  | 85162 | A | DONE | 6 | S-M |  | 121 E. WILSON 6230024 | MOD | 2025-05-01 | Z | 2025-04-25 | 110 | 0 | 20 | F | 0 | 230 |  | PL-1 |  | 6
2025-04-30 | 275 |  | 85156 - 85158 | A | DONE | 42 | L |  | 121 E. WILSON 6230024 | exp. metal , VD's | 2025-05-01 | Z | 2025-04-25 | 670 | 0 | 360 | F | 0 | 2490 |  | PL-1 - 3 |  | 6
2025-04-30 | 276 |  | 85159 - 85161 | A | DONE | 13 | M |  | 121 E. WILSON 6230024 | bird s. | 2025-05-01 | Z | 2025-04-25 | 310 | 0 | 0 |  | 0 | 730 |  | Gen. - Boiler |  | 6
2025-04-30 | 277 | bth | 85219 - 85223 | A | DONE | 6 | S-M | pt. ss | 121 E. WILSON 6230024 |  | 2025-05-01 | Z | 2025-04-25 | 110 | 40 | 0 |  | 0 | 170 |  | Pool heater intake |  | 6
2025-04-30 | 278 |  | 85224 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-05-01 | Z | 2025-04-25 | 30 | 0 | 0 |  | 0 | 30 |  | PL-1 |  | 6
2025-04-30 | 279 |  | 85225 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-05-01 | Z | 2025-04-25 | 20 | 0 | 0 |  | 0 | 20 |  | HP-102 |  | 6
2025-04-28 | 2251 | w | 84353 | A | DONE | 2 | S-M |  | BARTILLION 6240024 | 2" FB | 2025-04-30 | Z | 2025-04-24 | 40 | 0 | 0 |  | 30 | 100 |  | Louver sleeves |  | 6
2025-05-02 | 2479 |  | 69971 , 69974 | A | DONE | 11 | S-M | neal | CDIS 6220028 |  | 2025-05-06 | Z | 2025-04-22 | 260 | 0 | 0 |  | 0 | 760 |  | VIV EA |  | 14
2025-05-02 | 2480 |  | 69972 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2025-05-06 | Z | 2025-04-22 | 210 | 0 | 0 |  | 0 | 690 |  | VIV OA |  | 14
2025-05-01 | 206 | sp | 84715 | A | DONE | 8 | S-M | neal | COMPASS 4250018 |  | 2025-05-05 | Z | 2025-04-25 | 60 | 120 | 0 |  | 0 | 210 |  | 2nd floor RA |  | 10
2025-05-02 | 210 |  | 70243 | A | DONE | 2 | S | neal | COMPASS 7447 4250018 |  | 2025-05-05 | Z | 2025-05-02 | 20 | 0 | 0 |  | 0 | 20 |  | VAV |  | 3
2025-05-01 | 877 | bth | 73877 - 73880 | A | DONE | 15 | M |  | DELLSHIRE 6240017 |  | 2025-05-05 | Z | 2025-04-17 | 180 | 160 | 30 | F | 0 | 430 |  | VAV LP |  | 18
2025-05-01 | 878 | bth | 73882 - 73886 | A | DONE | 26 | M |  | DELLSHIRE 6240017 | bird s. | 2025-05-05 | Z | 2025-04-17 | 300 | 350 | 0 |  | 0 | 700 |  | VAV LP |  | 18
2025-04-28 | 879 |  | 73661 | A | DONE | 20 | M | neal | DELLSHIRE 6240017 |  | 2025-04-30 | Z | 2025-04-17 | 490 | 0 | 0 |  | 0 | 840 |  | VTAC Trim ring |  | 13
2025-04-29 | 880 |  | 73662 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-05-05 | Z | 2025-04-21 | 20 | 0 | 0 |  | 0 | 40 |  | Flashing |  | 14
2025-04-30 | 207 |  | 89732 - 89734 | A | DONE | 2 | S | BI | EDGERTON GEAR 4240036 |  | 2025-05-02 | Z | 2025-04-25 | 30 | 0 | 0 |  | 0 | 80 |  | Hangers |  | 7
2025-05-02 | 1244 |  | 79047 | A | DONE | 7 | S-M |  | EXACT 501 6240025 |  | 2025-05-05 | Z | 2025-05-01 | 160 | 0 | 0 |  | 0 | 280 |  | Wall Blocking |  | 4
2025-04-30 | 1750 | w | 69426 | A | DONE | 20 | M | BI | ONE 09 6240037 |  | 2025-05-01 | Z | 2025-04-11 | 500 | 0 | 0 |  | 0 | 1200 |  | Chop House |  | 20
2025-05-01 | 1801 |  | PRE-FAB HANGERS | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-05-05 | Z | 2025-04-21 | 50 | 0 | 0 |  | 0 | 140 |  | Hangers |  | 14
2025-04-28 | 3021 |  | 62731 | A | DONE | 7 | S-M |  | PROMEGA BTC 6230022 |  | 2025-04-30 | Z | 2025-04-15 | 130 | 0 | 40 | F | 0 | 320 |  | EA |  | 15
2025-04-28 | 3024 |  | 62736 | A | DONE | 14 | S-M |  | PROMEGA BTC 6230022 |  | 2025-04-30 | Z | 2025-04-21 | 240 | 0 | 110 | F | 0 | 510 |  | SA |  | 9
2025-05-01 | 3027 |  | 62742 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-05-02 | Z | 2025-04-30 | 50 | 0 | 0 |  | 0 | 70 |  | EA |  | 2
2025-05-01 | 3028 |  | 81832 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-05-02 | Z | 2025-04-30 | 40 | 0 | 0 |  | 0 | 50 |  | Misc |  | 2
2025-04-29 | 943 |  | 62741 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 |  | 2025-04-30 | Z | 2025-04-29 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2025-04-28 | 942 |  | 62737 | A | DONE | 2 | S |  | PROMEGA RDC 6210033 |  | 2025-05-02 | Z | 2025-04-23 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 9
2025-04-29 | 1422 |  | PTH-MPRA-001 | A | DONE | 14 | M |  | SPH SURGERY 6240039 | flex | 2025-05-02 | Z | 2025-03-26 | 350 | 0 | 0 |  | 0 | 860 |  |  |  | 37
2025-04-29 | 1423 | bth | PTH-MPRA-002 | A | DONE | 31 | M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-03-26 | 300 | 20 | 450 | F | 0 | 1030 |  |  |  | 37
2025-04-29 | 1431 | bth | SAMP-001 | A | DONE | 7 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 140 | 20 | 0 |  | 0 | 190 |  |  |  | 17
2025-04-29 | 1432 | bth | SAMP-002 | A | DONE | 21 | M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 190 | 80 | 250 | F | 0 | 650 |  |  |  | 17
2025-04-29 | 1433 | bth | L1-A-VAV 12-1 | A | DONE | 14 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 180 | 20 | 140 | F | 0 | 400 |  |  |  | 17
2025-04-29 | 1434 |  | L1-A-VAV 12-2 | A | DONE | 7 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 80 | 0 | 80 | F | 0 | 200 |  |  |  | 17
2025-04-29 | 1435 | bth | L1-A-VAV 12-8 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 30 | 20 | 40 | F | 0 | 90 |  |  |  | 17
2025-04-29 | 1436 | bth | L1-A-VAV 12-12 | A | DONE | 20 | M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 170 | 50 | 260 | F | 0 | 610 |  |  |  | 17
2025-04-29 | 1437 | bth | L1-A-VAV 12-16 | A | DONE | 6 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 30 | 90 | 20 | F | 0 | 140 |  |  |  | 17
2025-04-29 | 1438 | bth | SALP-001 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 70 | 20 | 0 |  | 0 | 80 |  |  |  | 17
2025-04-29 | 1439 | bth | SALP-002 | A | DONE | 7 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 80 | 20 | 60 | F | 0 | 130 |  |  |  | 17
2025-04-29 | 1440 | bth | SALP-003 | A | DONE | 14 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 140 | 60 | 150 | F | 0 | 400 |  |  |  | 17
2025-04-29 | 1441 |  | SALP-004 | A | DONE | 10 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 190 | 0 | 40 | F | 0 | 310 |  |  |  | 17
2025-04-29 | 1442 |  | SALP-005 | A | DONE | 11 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 90 | 90 | 80 | F | 0 | 280 |  |  |  | 17
2025-04-29 | 1443 |  | SALP-006 | A | DONE | 17 | M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 170 | 0 | 250 | F | 0 | 560 |  |  |  | 17
2025-04-29 | 1444 |  | SALP-007 | A | DONE | 11 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 190 | 0 | 70 | F | 0 | 310 |  |  |  | 17
2025-04-29 | 1445 | bth | SALP-008 | A | DONE | 8 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 60 | 120 | 0 |  | 0 | 190 |  |  |  | 17
2025-04-29 | 1446 | bth | SALP-009 | A | DONE | 8 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 90 | 60 | 40 | F | 0 | 240 |  |  |  | 17
2025-04-29 | 1447 | bth | SALP-010 | A | DONE | 24 | M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 240 | 120 | 240 | F | 0 | 730 |  |  |  | 17
2025-04-29 | 1448 | bth | SALP-011 | A | DONE | 7 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 50 | 120 | 0 |  | 0 | 170 |  |  |  | 17
2025-04-29 | 1449 |  | SALP-012 | A | DONE | 17 | M |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-15 | 170 | 0 | 250 | F | 0 | 550 |  |  |  | 17
2025-04-29 | 2832 | bth | 68468 - 68469 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-24 | 20 | 20 | 60 | F | 0 | 100 |  | Phase 1C |  | 8
2025-04-29 | 2833 |  | 68470 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-25 | 40 | 0 | 0 |  | 0 | 80 |  | Phase 1C OR 5 |  | 7
2025-04-29 | 2834 |  | 68471 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-02 | Z | 2025-04-25 | 50 | 0 | 0 |  | 0 | 180 |  | Test caps |  | 7
2025-05-01 | 2409 |  | 79979 | A | DONE | 2 | S |  | ST.BERNARD 6230023 | 1" liner | 2025-05-06 | Z | 2025-04-29 | 20 | 0 | 0 |  | 20 | 20 |  | RF-3 |  | 7
2025-04-29 | 4056 | sp | 83047 | A | DONE | 3 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-05-05 | Z | 2025-04-23 | 20 | 50 | 0 |  | 0 | 70 |  | Café |  | 12
2025-04-30 | 4057 |  | 83048 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-05-05 | Z | 2025-04-23 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 12
2025-04-30 | 4058 |  | 67758 | A | DONE | 6 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-05-05 | Z | 2025-04-25 | 130 | 0 | 0 |  | 140 | 180 |  | A-Section |  | 10
2025-05-01 | 4059 | sp | 67770 | A | DONE | 2 | S-M | neal | STOUGHTON TRAILER 6240015 |  | 2025-05-05 | Z | 2025-04-25 | 30 | 20 | 0 |  | 0 | 40 |  | Outs |  | 10
2025-04-30 | 4060 |  | 67771 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | paint | 2025-05-05 | Z | 2025-04-25 | 20 | 0 | 0 |  | 20 | 30 |  | 1st A |  | 10
2025-05-01 | 3752 |  | 59295 | A | DONE | 2 | S-M |  | UW-AVRL 6240038 |  | 2025-05-07 | Z | 2025-04-30 | 20 | 0 | 0 |  | 0 | 20 |  | D-Section Flashing |  | 7
2025-04-29 | 4391 |  | 59285 | A | DONE | 2 | S | neal | UW-AVRL 6240038 |  | 2025-04-30 | Z | 2025-04-22 | 30 | 0 | 0 |  | 0 | 60 |  | Flashing |  | 8
2025-04-28 | 4393 | bth | 69286 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-30 | Z | 2025-04-24 | 30 | 20 | 0 |  | 0 | 50 |  | Misc |  | 6
2025-04-28 | 4394 |  | 59287 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-30 | Z | 2025-04-25 | 30 | 0 | 0 |  | 0 | 40 |  | Flashing |  | 5
2025-04-29 | 4398 | sp | 69140 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-04-30 | Z | 2025-04-28 | 20 | 20 | 0 |  | 0 | 40 |  | SAT 581 |  | 2
2025-05-02 | 4399 |  | 1234 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-05-07 | Z | 2025-04-30 | 20 | 0 | 0 |  | 0 | 20 |  | Hangers |  | 7
2025-04-28 | 735 | bth | L3-SAMP 9 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 |  | 2025-04-29 | Z | 2025-04-02 | 140 | 60 | 270 | F | 0 | 700 |  |  |  | 27
2025-04-28 | 736 | bth | L3-SAMP 10 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-04-29 | Z | 2025-04-02 | 120 | 20 | 90 | F | 0 | 290 |  |  |  | 27
2025-04-28 | 737 | sp | L3-SAMP 11 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 |  | 2025-04-29 | Z | 2025-04-02 | 20 | 120 | 0 |  | 0 | 130 |  |  |  | 27
2025-04-28 | 738 | bth | L3-SAMP 12 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-04-29 | Z | 2025-04-02 | 60 | 60 | 150 | F | 0 | 360 |  |  |  | 27
2025-04-28 | 739 | bth | L3-SAMP 13 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-04-29 | Z | 2025-04-02 | 180 | 60 | 120 | F | 0 | 440 |  |  |  | 27
2025-04-28 | 740 | bth | L3-SAMP 14 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-04-29 | Z | 2025-04-02 | 150 | 70 | 70 | F | 0 | 370 |  |  |  | 27
2025-04-28 | 742 | bth | L3-SAMP 16 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-04-29 | Z | 2025-04-02 | 100 | 40 | 70 | F | 0 | 250 |  |  |  | 27
2025-04-28 | 743 |  | L3-RAMP 18 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-04-29 | Z | 2025-04-02 | 220 | 0 | 250 | F | 30 | 660 |  |  |  | 27
2025-04-28 | 744 | bth | L3-RAMP 19 | A | DONE | 17 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-02 | 270 | 20 | 120 | F | 80 | 480 |  |  |  | 27
2025-04-28 | 745 | bth | L3-RAMP 20 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-02 | 140 | 20 | 170 | F | 50 | 410 |  |  |  | 27
2025-04-28 | 746 | bth | L3-RAMP 21 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-02 | 150 | 20 | 220 | F | 80 | 470 |  |  |  | 27
2025-04-28 | 747 | bth | L3-RAMP 22 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-02 | 110 | 20 | 200 | F | 60 | 400 |  |  |  | 27
2025-04-28 | 748 | bth | L3-RAMP 23 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-02 | 130 | 20 | 120 | F | 40 | 300 |  |  |  | 27
2025-04-28 | 749 | bth | L3-RAMP 24 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-02 | 120 | 20 | 160 | F | 60 | 380 |  |  |  | 27
2025-04-28 | 750 | bth | L3-RAMP 25 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-02 | 180 | 20 | 140 | F | 40 | 420 |  |  |  | 27
2025-04-28 | 751 | bth | L3-RAMP 26 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-02 | 220 | 80 | 40 | F | 50 | 420 |  |  |  | 27
2025-04-28 | 752 | bth | L3-RAMP 27 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD | 2025-04-29 | Z | 2025-04-02 | 30 | 0 | 140 | F | 0 | 210 |  |  |  | 27
2025-05-02 | 772 | bth | L3-SAMP 1 | A | DONE | 17 | M |  | UW-LEVY HALL 6230028 |  | 2025-05-06 | Z | 2025-04-03 | 220 | 30 | 170 | F | 0 | 650 |  |  |  | 33
2025-05-01 | 773 | bth | L3-SAMP 2 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-06 | Z | 2025-04-03 | 60 | 20 | 120 | F | 0 | 240 |  |  |  | 33
2025-05-01 | 774 | bth | L3-SAMP 7 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 |  | 2025-05-06 | Z | 2025-04-03 | 280 | 60 | 100 | F | 0 | 730 |  |  |  | 33
2025-05-02 | 777 | bth | L3-RAMP 7 | A | DONE | 22 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-06 | Z | 2025-04-03 | 390 | 20 | 120 | F | 70 | 1030 |  |  |  | 33
2025-05-02 | 778 | bth | L3-RAMP 8 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-06 | Z | 2025-04-03 | 160 | 20 | 120 | F | 20 | 600 |  |  |  | 33
2025-05-02 | 779 | bth | L3-RAMP 9 | A | DONE | 24 | M-L |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-06 | Z | 2025-04-03 | 120 | 20 | 440 | F | 80 | 970 |  |  |  | 33
2025-05-02 | 781 | bth | L3-RAMP 11 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-06 | Z | 2025-04-03 | 170 | 40 | 250 | F | 70 | 690 |  |  |  | 33
2025-05-02 | 782 | bth | L3-RAMP 12 | A | DONE | 13 | S-M |  | UW-LEVY HALL 6230028 | Sp. Acou ,VD, 1" liner | 2025-05-06 | Z | 2025-04-03 | 220 | 20 | 70 | F | 220 | 470 |  |  |  | 33
2025-04-28 | 3700 |  | L1-SAMP 10 | A | DONE | 41 | L |  | UW-LEVY HALL 6230028 | 1" liner | 2025-04-29 | Z | 2025-04-22 | 500 | 0 | 520 | F | 830 | 1980 |  |  |  | 7
2025-05-02 | 3701 |  | 83814 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-06 | Z | 2025-04-23 | 20 | 20 | 0 |  | 0 | 40 |  | L2-SAT-3-2-1 |  | 13
2025-05-02 | 3702 |  | 83816 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-06 | Z | 2025-04-24 | 100 | 0 | 0 |  | 0 | 130 |  | L2-EAMP 2 |  | 12
2025-05-02 | 3704 | bth | L1-RAMP 6 | A | DONE | 106 | L |  | UW-LEVY HALL 6230028 | 1" liner , 1" DW | 2025-05-06 | Z | 2025-04-28 | 2060 | 20 | 570 | F | 1250 | 2690 |  |  |  | 8
2025-04-30 | 3913 | bth | 82283 - 82286 | A | DONE | 18 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 270 | 80 | 90 | F | 0 | 490 |  | SAT 3-1-5 |  | 41
2025-04-30 | 3914 |  | 82297 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 50 | 0 | 30 | F | 0 | 90 |  | SAT 3-1-12 |  | 41
2025-04-30 | 3915 | sp | 82298 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 20 | 30 | 0 |  | 0 | 50 |  | SAT 3-1-12 |  | 41
2025-05-01 | 3916 | bth | 82361 - 82366 | A | DONE | 16 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 170 | 90 | 140 | F | 0 | 440 |  | SAT 1-1-12 - 14 |  | 41
2025-04-30 | 3917 | bth | 82367 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 20 | 80 | 40 | F | 0 | 140 |  | SAT 3-1-15 |  | 41
2025-04-30 | 3918 |  | 82368 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-05-05 | Z | 2025-03-25 | 40 | 0 | 0 |  | 30 | 50 |  | SAT 1-1-16 |  | 41
2025-04-30 | 3919 | bth | 82369 , 82371 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 50 | 40 | 0 |  | 0 | 80 |  | SAT 1-1-16 |  | 41
2025-05-01 | 3920 | bth | 82370 , 82372 - 73 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 70 | 130 | 30 | F | 0 | 250 |  | SAT 3-1-13 - 14 |  | 41
2025-04-30 | 3921 | bth | 82374 - 82375 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 50 | 60 | 40 | F | 0 | 150 |  | SAT 3-1-1 |  | 41
2025-05-01 | 3922 | bth | 82376 - 82377 | A | DONE | 7 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-05-05 | Z | 2025-03-25 | 60 | 20 | 80 | F | 30 | 190 |  | SAT 3-1-2 |  | 41
2025-05-01 | 3923 | bth | 82379 - 72380 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 60 | 100 | 80 | F | 0 | 250 |  | SAT 3-1-3 |  | 41
2025-05-01 | 3924 | bth | 82381 - 82383 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 40 | 40 | 30 | F | 0 | 120 |  | SAT 3-1-15,16,17 |  | 41
2025-05-01 | 3925 | bth | 82384 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 50 | 20 | 0 |  | 0 | 70 |  | SAT 1-1-2 |  | 41
2025-05-01 | 3926 | bth | 82385 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-05-05 | Z | 2025-03-25 | 50 | 30 | 0 |  | 30 | 80 |  | SAT 3-1-6 |  | 41
2025-05-01 | 3927 | bth | 82388 , 82391 - 93 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 90 | 100 | 80 | F | 0 | 310 |  | SAT 3-1-7,8,9,10 |  | 41
2025-05-01 | 3928 | bth | 82395 , 82397 - 98 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 60 | 40 | 100 | F | 0 | 230 |  | SAT 3-1-4 , 19/11 |  | 41
2025-05-01 | 3929 |  | 84401 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-05-05 | Z | 2025-03-25 | 30 | 0 | 0 |  | 30 | 50 |  | SAT 3-1-18 |  | 41
2025-05-01 | 3930 | bth | 84405 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 50 | 40 | 40 | F | 0 | 120 |  | SAT 3-1-18 |  | 41
2025-05-01 | 3931 | bth | 84413 - 84415 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 80 | 70 | 20 | F | 0 | 190 |  | SAT 1-1-9,10,11 |  | 41
2025-05-01 | 3932 |  | 84485 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 50 | 0 | 60 | F | 0 | 120 |  | SAT 1-1-7 |  | 41
2025-05-01 | 3933 | sp | 84486 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 20 | 140 | 0 |  | 0 | 140 |  | SAT 1-1-7 |  | 41
2025-05-01 | 3934 |  | 84646 - 84647 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 50 | 0 | 70 | F | 0 | 150 |  | SAT 1-1-17 |  | 41
2025-05-01 | 3935 | sp | 84648 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 0 | 20 | 0 |  | 0 | 20 |  | SAT 1-1-1/6 |  | 41
2025-05-01 | 3936 |  | 84651 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | 1" liner | 2025-05-05 | Z | 2025-03-25 | 40 | 0 | 0 |  | 40 | 60 |  | SAT 1-1-3 |  | 41
2025-05-01 | 3937 |  | 84652 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 40 | 0 | 50 | F | 0 | 90 |  | SAT 1-1-3 |  | 41
2025-05-01 | 3938 | sp | 84653 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 0 | 90 | 0 |  | 0 | 80 |  | SAT 1-1-3/4/5 |  | 41
2025-05-01 | 3939 |  | 84657 - 84658 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-25 | 50 | 0 | 70 | F | 0 | 150 |  | SAT 1-1-5 |  | 41
2025-04-28 | 3941 |  | 84680 - 84681 | A | DONE | 8 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-03-26 | 80 | 0 | 100 | F | 0 | 210 |  | SAT-1-1-4 |  | 40
2025-05-01 | 3946 | bth | 84693 - 84695 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 | VD | 2025-05-05 | Z | 2025-04-08 | 90 | 40 | 70 | F | 0 | 230 |  | 2nd RA SO |  | 27
2025-04-30 | 3951 |  | 74504 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-05-05 | Z | 2025-04-28 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd RA |  | 7
2025-04-29 | 1852 |  | 69535 - 69536 | A | DONE | 40 | M |  | UWP-FH 6240021 |  | 2025-05-01 | Z | 2025-04-21 | 1000 | 0 | 0 |  | 0 | 1820 |  | Roof Caps |  | 10
2025-05-01 | 1149 |  | 66900 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2025-05-06 | Z | 2025-04-22 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor change |  | 14
2025-05-02 | 2850 | bth | 84836 - 84837 | A | DONE | 8 | S-M | pcd | UWRF 6230010 |  | 2025-05-06 | Z | 2025-04-22 | 150 | 30 | 0 |  | 0 | 210 |  | Rm. 111#2 / L1-FE |  | 14
2025-04-29 | 2853 |  | 84854 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2025-05-02 | Z | 2025-04-28 | 20 | 0 | 0 |  | 0 | 20 |  | Flat stock |  | 4
2025-04-28 | 4413 |  | 70178 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-04-29 | Z | 2025-04-25 | 80 | 0 | 0 |  | 0 | 150 |  | Flashing |  | 4
2025-04-28 | 2034 |  | 57608 | A | DONE | 2 | S | neal | UW-VET MED 6210014 |  | 2025-04-30 | Z | 2025-04-23 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2025-04-28 | 2035 |  | 57609 | A | DONE | 4 | S-M | neal | UW-VET MED 6210014 |  | 2025-04-30 | Z | 2025-04-23 | 80 | 0 | 0 |  | 0 | 100 |  | 2nd floor |  | 7
2025-04-30 | 2038 | sp | 57612 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-05-01 | Z | 2025-04-29 | 20 | 30 | 0 |  | 0 | 40 |  | Misc |  | 2
2025-04-28 | 1664 | sp | L01_G_DCA_003 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 40 | 80 | 0 |  | 0 | 240 |  |  |  | 4
2025-04-28 | 1668 | sp | L01_G_DCA_007 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 20 | 50 | 0 |  | 0 | 140 |  |  |  | 4
2025-04-28 | 1669 | sp | L01_G_DCA_008 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 20 | 40 | 0 |  | 0 | 110 |  |  |  | 4
2025-04-28 | 1670 | sp | L01_G_DCA_009 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-04-25 | Z | 2025-04-21 | 20 | 30 | 0 |  | 0 | 140 |  |  |  | 4
2025-05-02 | 1671 | sp | L01_G_DCA_011 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 30 | 170 | 0 |  | 0 | 340 |  |  |  | 16
2025-05-02 | 1672 | sp | L01_G_DCA_012 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 40 | 140 | 0 |  | 0 | 310 |  |  |  | 16
2025-04-29 | 1680 | w | 79875 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | 2" nailer , 1" DB | 2025-05-02 | Z | 2025-04-21 | 20 | 0 | 0 |  | 90 | 150 |  | PRV - 1 |  | 11
2025-05-01 | 1682 |  | 79836 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-02 | Z | 2025-04-30 | 20 | 0 | 0 |  | 0 | 30 |  | 2nd E-South Shaft |  | 2
2025-04-28 | 1288 |  | 82223 | A | DONE | 2 | S |  | WINDSOR 6240012 | paint , flex | 2025-04-30 | Z | 2025-04-22 | 20 | 0 | 0 |  | 20 | 20 |  | Elev. Lobby TA |  | 8
2025-04-30 | 2704 |  | 66197 | A | DONE | 2 | S | neal | WSCC 6240006 | 1" liner | 2025-05-01 | Z | 2025-04-29 | 20 | 0 | 0 |  | 20 | 40 |  | VAV 1-4 |  | 2
2025-04-30 | 2705 | sp | 66198 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-05-01 | Z | 2025-04-30 | 20 | 0 | 0 |  | 0 | 20 |  | Fan-03 |  | 1
[6 empty] | 1317 | [13 empty] | 44750 |  |  |  | 14800 | 33.07%
WEEK OF 5-5-2025
2025-05-09 | 2482 | sp | 582025 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-05-09 | Z | 2025-05-08 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2025-05-05 | 214 |  | 70245 | A | DONE | 2 | S | neal | COMPASS 7447 4250018 |  | 2025-05-06 | Z | 2025-05-05 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2025-05-09 | 884 |  | 73666 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-05-12 | Z | 2025-04-25 | 20 | 0 | 0 |  | 0 | 20 |  | EF-6 |  | 17
2025-05-09 | 885 |  | 73887 - 73889 | A | DONE | 8 | S-M |  | DELLSHIRE 6240017 |  | 2025-05-12 | Z | 2025-04-25 | 370 | 0 | 200 | F | 0 | 830 |  | AHU-8 RA , 7 SA |  | 17
2025-05-09 | 886 |  | 73890 - 73892 | A | DONE | 20 | S-M |  | DELLSHIRE 6240017 |  | 2025-05-12 | Z | 2025-04-25 | 330 | 0 | 160 | F | 0 | 760 |  | AHU-6 SA , MUH-2 SA |  | 17
2025-05-09 | 887 |  | 73893 - 73894 | A | DONE | 14 | S-M |  | DELLSHIRE 6240017 |  | 2025-05-12 | Z | 2025-04-25 | 260 | 0 | 90 | F | 0 | 580 |  | MAU-1 SA , AU-8 SA |  | 17
2025-05-09 | 888 | sp | 73895 | A | DONE | 3 | S |  | DELLSHIRE 6240017 |  | 2025-05-12 | Z | 2025-04-25 | 20 | 40 | 0 |  | 0 | 50 |  | AHU-8 SA |  | 17
2025-05-09 | 889 |  | 73896 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-05-12 | Z | 2025-04-25 | 0 | 0 | 20 | F | 20 | 30 |  | VAV 3-2 |  | 17
2025-05-06 | 890 |  | 73661 | A | DONE | 6 | S-M | neal | DELLSHIRE 6240017 |  | 2025-05-08 | Z | 2025-05-01 | 140 | 0 | 0 |  | 0 | 260 |  | VTAC Trim Rings |  | 7
2025-05-09 | 1601 | w | 74301 | A | DONE | 2 | S |  | DOC JDC 6240023 | 2" FB | 2025-05-09 | Z | 2025-05-01 | 20 | 0 | 0 |  | 20 | 30 |  | Zone 1 Sleeves |  | 8
2025-05-08 | 202 | bth | 84712 - 84713 | A | DONE | 74 | L |  | EDGERTON GEAR 4240036 | accuflange | 2025-05-08 | Z | 2025-04-22 | 760 | 1070 | 0 |  | 0 | 2480 |  | RTU SA |  | 16
2025-05-06 | 203 |  | 84706 - 84708 | A | DONE | 68 | M |  | EDGERTON GEAR 4240036 | accuflange | 2025-05-08 | Z | 2025-04-22 | 1410 | 0 | 290 | F | 480 | 4030 |  | RTU SA |  | 16
2025-05-08 | 204 | w | 84710 | A | DONE | 6 | M |  | EDGERTON GEAR 4240036 |  | 2025-05-08 | Z | 2025-04-22 | 150 | 0 | 0 |  | 0 | 450 |  | RTU 3 ,4 curbs |  | 16
2025-05-08 | 205 | w | 84711 | A | DONE | 6 | M |  | EDGERTON GEAR 4240036 |  | 2025-05-08 | Z | 2025-04-22 | 150 | 0 | 0 |  | 0 | 460 |  | RTU 1, 2 curbs |  | 16
2025-05-09 | 208 |  | 84717 | A | DONE | 2 | S |  | EDGERTON GEAR 4240036 |  | 2025-05-13 | Z | 2025-04-29 | 40 | 0 | 0 |  | 0 | 90 |  | RTU-4 |  | 14
2025-05-09 | 209 | sp | 84716 | A | DONE | 45 | M |  | EDGERTON GEAR 4240036 | accuflange | 2025-05-13 | Z | 2025-04-29 | 290 | 830 | 0 |  | 0 | 1330 |  | RTU-4 |  | 14
2025-05-06 | 212 |  | 84720 | A | DONE | 8 | S-M |  | EDGERTON GEAR 4240036 |  | 2025-05-09 | Z | 2025-05-05 | 180 | 0 | 0 |  | 0 | 340 |  | RTU 1-4 |  | 4
2025-05-08 | 213 |  | 84721 | A | DONE | 5 | S-M |  | EDGERTON GEAR 4240036 |  | 2025-05-09 | Z | 2025-05-05 | 120 | 0 | 0 |  | 0 | 210 |  | RTU 1-3 |  | 4
2025-05-05 | 211 |  | 70244 | A | DONE | 2 | S | alum | MCFARLAND HS 6259999 |  | 2025-05-07 | Z | 2025-05-02 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 5
2025-05-05 | 1587 |  | EA-L2C-01 | A | DONE | 9 | S-M |  | MONROE HS 6240018 | flex , 1" liner | 2025-05-07 | Z | 2025-04-22 | 210 | 0 | 0 |  | 60 | 300 |  |  |  | 15
2025-05-05 | 1588 |  | OA-L2C-01 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | flex | 2025-05-07 | Z | 2025-04-22 | 190 | 0 | 40 | F | 0 | 300 |  |  |  | 15
2025-05-06 | 1589 |  | OA-L2C-02 | A | DONE | 36 | L |  | MONROE HS 6240018 | CD's | 2025-05-07 | Z | 2025-04-22 | 620 | 0 | 260 | F | 0 | 1980 |  |  |  | 15
2025-05-05 | 1590 |  | RA-L2C-01 | A | DONE | 25 | M |  | MONROE HS 6240018 | 1" liner | 2025-05-07 | Z | 2025-04-22 | 470 | 0 | 150 | F | 470 | 1180 |  |  |  | 15
2025-05-05 | 1591 |  | RA-L2C-02 | A | DONE | 36 | L |  | MONROE HS 6240018 | 1" liner | 2025-05-07 | Z | 2025-04-22 | 680 | 0 | 220 | F | 750 | 1640 |  |  |  | 15
2025-05-05 | 1592 | bth | SALP-L2C-01 | A | DONE | 5 | S |  | MONROE HS 6240018 | 2" liner | 2025-05-07 | Z | 2025-04-22 | 60 | 20 | 30 | F | 60 | 130 |  |  |  | 15
2025-05-06 | 1593 |  | SALP-L2C-02 | A | DONE | 9 | S |  | MONROE HS 6240018 | flex | 2025-05-07 | Z | 2025-04-22 | 170 | 0 | 40 | F | 0 | 240 |  |  |  | 15
2025-05-06 | 1594 | bth | SAMP-L2C-01 | A | DONE | 21 | M-L |  | MONROE HS 6240018 | accuflange , oval | 2025-05-07 | Z | 2025-04-22 | 460 | 50 | 0 |  | 0 | 1160 |  |  |  | 15
2025-05-06 | 3805 |  | PIPE SLEEVES | A | DONE | 2 | S | BI | MONROE HS 6240018 |  | 2025-05-12 | Z | 2025-05-06 | 20 | 0 | 0 |  | 0 | 30 |  | Caps |  | 6
2025-05-06 | 1752 |  | SALP-L1-09 | A | DONE | 7 | S |  | ONE 09 6240037 | flex | 2025-05-07 | Z | 2025-04-30 | 50 | 30 | 90 | F | 0 | 180 |  |  |  | 7
2025-05-06 | 1753 |  | SALP-L1-08 | A | DONE | 8 | S |  | ONE 09 6240037 | flex | 2025-05-07 | Z | 2025-04-30 | 80 | 30 | 90 | F | 0 | 200 |  |  |  | 7
2025-05-06 | 1754 |  | SALP-L1-05 | A | DONE | 9 | S |  | ONE 09 6240037 | flex | 2025-05-07 | Z | 2025-04-30 | 100 | 20 | 100 | F | 0 | 220 |  |  |  | 7
2025-05-08 | 1750a | w | 69427 - 69428 | A | DONE | 34 | M-L | BI | ONE 09 6240037 |  | 2025-05-07 | Z | 2025-04-11 | 840 | 0 | 0 |  | 0 | 2610 |  | Chop House |  | 26
2025-05-05 | 1751 | w | 69429 | A | DONE | 4 | S |  | ONE 09 6240038 |  | 2025-05-08 | Z | 2025-04-29 | 80 | 0 | 0 |  | 0 | 180 |  | Rails |  | 9
2025-05-06 | 3026 | sp | 62739 - 62740 | A | DONE | 30 | S-M |  | PROMEGA BTC 6230022 |  | 2025-05-13 | Z | 2025-04-25 | 170 | 580 | 0 |  | 0 | 760 |  | EA |  | 18
2025-05-09 | 3029 |  | 62743 | A | DONE | 13 | S-M |  | PROMEGA BTC 6230022 |  | 2025-05-13 | Z | 2025-05-02 | 60 | 0 | 250 | F | 0 | 490 |  | North RA |  | 11
2025-05-09 | 3030 |  | 62744 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-05-09 | Z | 2025-05-08 | 40 | 0 | 0 |  | 0 | 80 |  | Misc |  | 1
2025-05-06 | 2800 | sp | L1-A-RAV 12-7 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 21
2025-05-06 | 2801 | sp | L1-A-RAV 12-8 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 20 | 60 | 0 |  | 0 | 60 |  |  |  | 21
2025-05-06 | 2802 | sp | L1-A-RAV 12-13 | A | DONE | 3 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 30 | 40 | 0 |  | 0 | 80 |  |  |  | 21
2025-05-06 | 2803 | sp | L1-A-RAV 12-14 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 21
2025-05-08 | 2804 | bth | L1-A-RAV 12-15 | A | DONE | 3 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 50 | 20 | 0 |  | 0 | 100 |  |  |  | 21
2025-05-08 | 2805 | sp | L1-A-RAV 12-17 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 21
2025-05-08 | 2813 | bth | L1-A-RAMP-001 | A | DONE | 20 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 280 | 100 | 110 | F | 0 | 550 |  |  |  | 21
2025-05-06 | 2814 | sp | L1-A-RAMP-002 | A | DONE | 5 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 20 | 90 | 0 |  | 0 | 110 |  |  |  | 21
2025-05-08 | 2815 |  | L1-A-RAMP-003 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 90 | 0 | 0 |  | 0 | 210 |  |  |  | 21
2025-05-08 | 2816 |  | L1-A-RAMP-004 | A | DONE | 9 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 220 | 0 | 0 |  | 0 | 340 |  |  |  | 21
2025-05-08 | 2817 | bth | L1-A-RAMP-005 | A | DONE | 17 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 140 | 20 | 260 | F | 0 | 530 |  |  |  | 21
2025-05-08 | 2818 |  | L1-A-RAMP-006 | A | DONE | 21 | M |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 410 | 0 | 100 | F | 0 | 690 |  |  |  | 21
2025-05-08 | 2819 | bth | L1-A-RAMP-007 | A | DONE | 12 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 120 | 30 | 140 | F | 0 | 380 |  |  |  | 21
2025-05-08 | 2820 | bth | L1-A-RAMP-008 | A | DONE | 13 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 140 | 20 | 160 | F | 0 | 380 |  |  |  | 21
2025-05-08 | 2821 | bth | L1-A-RAMP-009 | A | DONE | 10 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-17 | 90 | 20 | 140 | F | 0 | 300 |  |  |  | 21
2025-05-08 | 2835 | sp | 68857 | A | DONE | 5 | S |  | SPH SURGERY 6240039 |  | 2025-05-08 | Z | 2025-04-29 | 70 | 50 | 0 |  | 0 | 130 |  | OR RA |  | 9
2025-05-06 | 2836 |  | 68472 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-06 | Z | 2025-05-06 | 20 | 0 | 0 |  | 0 | 20 |  | EF |  | 0
2025-05-06 | 2411 |  | 74106 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2025-05-09 | Z | 2025-05-06 | 20 | 0 | 0 |  | 0 | 20 |  | Dining SA rework |  | 3
2025-05-09 | 2410 | sp | 74104 | A | DONE | 9 | S-M |  | ST.BERNARD 6230023 |  | 2025-05-12 | Z | 2025-05-02 | 70 | 150 | 0 |  | 0 | 260 |  | Misc |  | 10
2025-05-05 | 4061 |  | 83049 - 83050 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-05-07 | Z | 2025-05-05 | 50 | 70 | 0 |  | 0 | 140 |  | Lobby |  | 2
2025-05-09 | 808 | w | 73566 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-05-12 | Z | 2025-05-05 | 30 | 0 | 0 |  | 0 | 80 |  | Curb Adapt. |  | 7
2025-05-09 | 809 |  | 73567 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-05-12 | Z | 2025-05-05 | 20 | 0 | 0 |  | 0 | 20 |  | Roof EA Reducer |  | 7
2025-05-09 | 810 | w | 73568 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 | 1" DB | 2025-05-12 | Z | 2025-05-05 | 20 | 0 | 0 |  | 20 | 40 |  | PRV H1-8 Curb adaptor |  | 7
2025-05-09 | 811 | sp | 73569 | A | DONE | 8 | S |  | SW HEALTH OR 5 6250004 |  | 2025-05-12 | Z | 2025-05-05 | 60 | 120 | 0 |  | 0 | 210 |  | 2nd floor EA |  | 7
2025-05-06 | 3750 |  | 59288 - 59291 | A | DONE | 3 | S-M |  | UW-AVRL 6240038 |  | 2025-05-07 | Z | 2025-04-30 | 70 | 0 | 0 |  | 20 | 160 |  | C-Section Flashing |  | 7
2025-05-05 | 3751 |  | 59292 - 59294 | A | DONE | 3 | S-M |  | UW-AVRL 6240038 |  | 2025-05-07 | Z | 2025-04-30 | 60 | 0 | 0 |  | 0 | 120 |  | C-Section Flashing |  | 7
2025-05-06 | 3753 |  | 59296 - 59298 | A | DONE | 5 | S-M |  | UW-AVRL 6240038 |  | 2025-05-07 | Z | 2025-04-30 | 50 | 0 | 0 |  | 0 | 110 |  | D-Section Flashing |  | 7
2025-05-06 | 3754 | bth | 59299 | A | DONE | 2 | S | pt.alum | UW-AVRL 6240038 |  | 2025-05-07 | Z | 2025-05-01 | 20 | 20 | 0 |  | 0 | 40 |  | C,D outs |  | 6
2025-05-09 | 3755 | w | 69141 | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-05-08 | Z | 2025-05-08 | 20 | 0 | 0 |  | 0 | 20 |  | Slip Flanges |  | 0
2025-05-05 | 639 |  | 66716 | A | DONE | 2 | S |  | UW-BIO CHEM 6240036 | VD | 2025-05-06 | Z | 2025-05-05 | 50 | 0 | 0 |  | 0 | 90 |  | EA outs |  | 1
2025-05-09 | 753 |  | L3-TA 1 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 60 | 0 | 0 |  | 50 | 90 |  |  |  | 40
2025-05-09 | 754 |  | L3-TA 2 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 70 | 0 | 0 |  | 60 | 100 |  |  |  | 40
2025-05-09 | 755 |  | L3-TA 3 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 120 | 0 | 0 |  | 50 | 190 |  |  |  | 40
2025-05-09 | 756 |  | L3-TA 4 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 40
2025-05-09 | 757 |  | L3-TA 5 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 40
2025-05-09 | 761 | bth | L3-RAMP 28 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 140 | 20 | 170 | F | 50 | 410 |  |  |  | 40
2025-05-09 | 762 | bth | L3-RAMP 29 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 90 | 50 | 40 | F | 50 | 220 |  |  |  | 40
2025-05-09 | 764 | bth | L3-RAMP 31 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 150 | 20 | 80 | F | 70 | 310 |  |  |  | 40
2025-05-09 | 765 | bth | L3-RAMP 32 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 120 | 20 | 70 | F | 50 | 280 |  |  |  | 40
2025-05-09 | 766 |  | L3-EAMP 1 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-13 | Z | 2025-04-03 | 90 | 0 | 0 |  | 0 | 140 |  |  |  | 40
2025-05-09 | 767 |  | L3-EAMP 2 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-05-13 | Z | 2025-04-03 | 130 | 0 | 40 | F | 20 | 200 |  |  |  | 40
2025-05-09 | 770 |  | L3-EAMP 5 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-13 | Z | 2025-04-03 | 100 | 0 | 0 |  | 0 | 140 |  |  |  | 40
2025-05-05 | 775 | bth | L3-SAMP 8 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-06 | Z | 2025-04-03 | 30 | 20 | 50 | F | 0 | 110 |  |  |  | 33
2025-05-05 | 776 |  | L3-RAMP 6 | A | DONE | 14 | M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-05-06 | Z | 2025-04-03 | 230 | 0 | 120 | F | 20 | 710 |  |  |  | 33
2025-05-05 | 780 | bth | L3-RAMP 10 | A | DONE | 22 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-06 | Z | 2025-04-03 | 200 | 20 | 330 | F | 90 | 920 |  |  |  | 33
2025-05-05 | 3703 |  | L1-EAMP 8 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-06 | Z | 2025-04-28 | 40 | 0 | 120 | F | 0 | 190 |  |  |  | 8
2025-05-09 | 4007 |  | L3-SAMP 3 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-13 | Z | 2025-04-07 | 100 | 40 | 60 | F | 0 | 240 |  |  |  | 36
2025-05-09 | 4008 |  | L3-SAMP 5 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-05-13 | Z | 2025-04-07 | 70 | 40 | 170 | F | 0 | 310 |  |  |  | 36
2025-05-09 | 4009 |  | L3-SAMP 6 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-13 | Z | 2025-04-07 | 50 | 60 | 0 |  | 0 | 130 |  |  |  | 36
2025-05-09 | 4037 | bth | L3-RAMP 5 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 80 | 20 | 60 | F | 50 | 180 |  |  |  | 35
2025-05-09 | 4038 | bth | L3-RAMP 13 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 180 | 40 | 80 | F | 60 | 350 |  |  |  | 35
2025-05-09 | 4041 | bth | L3-RAMP 16 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 110 | 20 | 110 | F | 30 | 300 |  |  |  | 35
2025-05-09 | 4042 | bth | L3-RAMP 17 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 110 | 20 | 40 | F | 40 | 200 |  |  |  | 35
2025-05-09 | 4044 |  | L3-EAMP 6 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-05-13 | Z | 2025-04-08 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 35
2025-05-09 | 4045 |  | L3-EAMP 7 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-13 | Z | 2025-04-08 | 20 | 0 | 90 | F | 0 | 120 |  |  |  | 35
2025-05-09 | 4046 |  | L3-EAMP 8 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-13 | Z | 2025-04-08 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 35
2025-05-09 | 3950 |  | 74501 - 74503 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-12 | Z | 2025-04-22 | 60 | 0 | 0 |  | 0 | 90 |  | 3rd AHU-1 test / SAT's |  | 20
2025-05-09 | 3952 |  | 74505 - 74506 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-12 | Z | 2025-04-30 | 20 | 0 | 20 | F | 0 | 40 |  | 2nd RA/NO |  | 12
2025-05-09 | 3953 |  | 74507 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | shut down | 2025-05-12 | Z | 2025-05-01 | 40 | 0 | 0 |  | 0 | 50 |  | EA Shut down |  | 11
2025-05-09 | 3954 |  | 74508 - 74509 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2025-05-12 | Z | 2025-05-06 | 190 | 0 | 0 |  | 0 | 460 |  | AHU test caps |  | 6
2025-05-05 | 1853 | sp | 69537 | A | DONE | 21 | S-M |  | UWP-FH 6240021 |  | 2025-05-08 | Z | 2025-04-25 | 180 | 340 | 0 |  | 0 | 520 |  | 2nd floor |  | 13
2025-05-08 | 1854 |  | 69538 - 69539 | A | DONE | 39 | S-M |  | UWP-FH 6240021 |  | 2025-05-08 | Z | 2025-04-25 | 90 | 0 | 870 | F | 0 | 1160 |  | 2nd floor EA , SA |  | 13
2025-05-09 | 2851 |  | 84838 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-05-13 | Z | 2025-04-28 | 30 | 20 | 0 |  | 0 | 50 |  | L1-FE |  | 15
2025-05-09 | 2852 |  | 84839 - 84840 | A | DONE | 4 | S |  | UWRF 6230010 | paint , 1" liner | 2025-05-13 | Z | 2025-04-28 | 80 | 0 | 0 |  | 60 | 120 |  | L2 TA |  | 15
2025-05-08 | 3258 |  | 81283 | A | DONE | 5 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-05-09 | Z | 2025-04-23 | 120 | 0 | 0 |  | 0 | 170 |  | 1st floor |  | 16
2025-05-09 | 3259 |  | 81284 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-05-12 | Z | 2025-04-25 | 20 | 0 | 0 |  | 0 | 20 |  | 1st floor |  | 17
2025-05-05 | 2039 | w | 57614 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 |  | 2025-05-08 | Z | 2025-04-30 | 30 | 0 | 0 |  | 0 | 80 |  | Caps |  | 8
2025-05-08 | 2040 |  | 57615 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 |  | 2025-05-08 | Z | 2025-05-01 | 40 | 0 | 0 |  | 0 | 60 |  | DM Frames |  | 7
2025-05-09 | 3854 |  | 85308 | A | DONE | 8 | S-M | neal | UW-WITTE HALL 6250003 |  | 2025-05-15 | Z | 2025-04-30 | 200 | 0 | 0 |  | 0 | 250 |  | Flashing |  | 15
2025-05-09 | 954 |  | L01_E_RAD_001 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 81
2025-05-09 | 955 |  | L01_E_RAD_002 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 100 | 0 | 0 |  | 80 | 150 |  |  |  | 81
2025-05-09 | 956 | bth | L01_E_RAD_003 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 80 | 80 | 30 | F | 60 | 200 |  |  |  | 81
2025-05-09 | 957 | bth | L01_E_RAD_004 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-05-09 | Z | 2025-02-17 | 30 | 20 | 0 |  | 20 | 50 |  |  |  | 81
2025-05-09 | 958 |  | L01_E_RAD_005 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 60 | 0 | 30 | F | 80 | 140 |  |  |  | 81
2025-05-09 | 959 |  | L01_E_RAD_006 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 60 | 0 | 30 | F | 70 | 130 |  |  |  | 81
2025-05-09 | 960 | bth | L01_E_RAD_007 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 81
2025-05-09 | 961 | bth | L01_E_RAD_008 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 81
2025-05-09 | 962 | bth | L01_E_RAD_009 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 40 | 60 | 0 |  | 20 | 110 |  |  |  | 81
2025-05-09 | 963 |  | L01_E_RAD_010 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 81
2025-05-09 | 964 | bth | L01_E_RAD_011 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 50 | 30 | 0 |  | 30 | 80 |  |  |  | 81
2025-05-09 | 965 |  | L01_E_RAD_012 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-09 | Z | 2025-02-17 | 20 | 0 | 0 |  | 20 | 50 |  |  |  | 81
2025-05-09 | 966 |  | L01_E_TAD_001 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-05-09 | Z | 2025-02-17 | 80 | 0 | 0 |  | 70 | 150 |  |  |  | 81
2025-05-09 | 967 |  | L01_E_TAD_002 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-05-09 | Z | 2025-02-17 | 80 | 0 | 0 |  | 70 | 120 |  |  |  | 81
2025-05-09 | 968 | w | L01_E_GEA_001 | A | DONE | 4 | S-M | BI | WAUNAKEE MS 6230013 |  | 2025-05-09 | Z | 2025-02-17 | 100 | 0 | 0 |  | 0 | 270 |  |  |  | 81
2025-05-05 | 1673 | sp | L01_G_DCA_013 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 30 | 160 | 0 |  | 0 | 350 |  |  |  | 16
2025-05-06 | 1674 | sp | L01_G_DCA_014 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 50 | 70 | 0 |  | 0 | 130 |  |  |  | 16
2025-05-06 | 1675 | sp | L01_G_DCA_015 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 40 | 60 | 0 |  | 0 | 170 |  |  |  | 16
2025-05-06 | 1676 | sp | L01_G_DCA_016 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 20 | 70 | 0 |  | 0 | 180 |  |  |  | 16
2025-05-06 | 1677 | sp | L01_G_DCA_017 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 20 | 30 | 0 |  | 0 | 90 |  |  |  | 16
2025-05-06 | 1678 | sp | L01_G_DCA_018 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 30 | 30 | 0 |  | 0 | 100 |  |  |  | 16
2025-05-06 | 1679 | sp | L01_G_DCA_019 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-07 | Z | 2025-04-21 | 20 | 40 | 0 |  | 0 | 100 |  |  |  | 16
2025-05-08 | 1683 |  | 79835 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-09 | Z | 2025-04-30 | 40 | 0 | 0 |  | 0 | 50 |  | 2-E-EA |  | 9
2025-05-08 | 1684 |  | 79837 - 79838 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-04-30 | 20 | 0 | 0 |  | 0 | 40 |  | HP-3-223 RA / SA |  | 9
2025-05-09 | 1685 | w | 79841 | A | DONE | 2 | S | BI | WAUNAKEE MS 6230013 |  | 2025-05-14 | Z | 2025-05-05 | 20 | 0 | 0 |  | 0 | 60 |  | E-Section EA |  | 9
2025-05-09 | 1687 | w | 79843 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-14 | Z | 2025-05-05 | 30 | 0 | 0 |  | 20 | 60 |  | E-Section roof curb |  | 9
2025-05-09 | 1691 |  | 79848 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-09 | Z | 2025-05-08 | 20 | 0 | 0 |  | 0 | 40 |  | FD Angle |  | 1
2025-05-09 | 1695 |  | 83342 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-05-12 | Z | 2025-05-09 | 20 | 0 | 0 |  | 0 | 20 |  | 1st -G |  | 3
2025-05-08 | 4275 | bth | L01_E_SALP_001 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 50 | 80 | 0 |  | 0 | 140 |  |  |  | 81
2025-05-08 | 4276 | sp | L01_E_SALP_002 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-09 | Z | 2025-02-17 | 20 | 110 | 0 |  | 0 | 130 |  |  |  | 81
2025-05-08 | 4277 | bth | L01_E_SALP_003 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 50 | 80 | 30 | F | 0 | 170 |  |  |  | 81
2025-05-08 | 4278 | sp | L01_E_SALP_004 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-09 | Z | 2025-02-17 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 81
2025-05-08 | 4279 | bth | L01_E_SALP_005 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 40 | 70 | 0 |  | 0 | 120 |  |  |  | 81
2025-05-08 | 4280 | bth | L01_E_SALP_006 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 81
2025-05-09 | 4281 | bth | L01_E_SALP_007 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 40 | 60 | 0 |  | 0 | 100 |  |  |  | 81
2025-05-08 | 4282 | bth | L01_E_SALP_008 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 40 | 40 | 0 |  | 0 | 80 |  |  |  | 81
2025-05-08 | 4283 | bth | L01_E_SALP_009 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 81
2025-05-08 | 4284 | bth | L01_E_SALP_010 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 81
2025-05-09 | 4285 | bth | L01_E_SALP_011 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 40 | 20 | 0 |  | 0 | 60 |  |  |  | 81
2025-05-08 | 4286 | sp | L01_E_SALP_012 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-09 | Z | 2025-02-17 | 0 | 50 | 0 |  | 0 | 50 |  |  |  | 81
2025-05-08 | 4287 | bth | L01_E_SALP_013 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 40 | 70 | 0 |  | 0 | 100 |  |  |  | 81
2025-05-08 | 4288 | sp | L01_E_SALP_014 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-09 | Z | 2025-02-17 | 20 | 120 | 0 |  | 0 | 110 |  |  |  | 81
2025-05-09 | 4289 | bth | L01_E_SALP_015 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 30 | 30 | 0 |  | 0 | 60 |  |  |  | 81
2025-05-08 | 4290 | bth | L01_E_SALP_016 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-09 | Z | 2025-02-17 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 81
2025-05-06 | 2706 |  | 66199 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-05-08 | Z | 2025-05-02 | 50 | 0 | 0 |  | 0 | 70 |  | Misc |  | 6
[6 empty] | 1165 | [13 empty] | 42610 |  |  |  | 6640 | 15.58%
WEEK OF 5-12-2025
2025-05-12 | 280 |  | 85226 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 | paint , bird.s | 2025-05-14 | Z | 2025-04-30 | 210 | 0 | 0 |  | 160 | 690 |  | EF-7 |  | 14
2025-05-12 | 281 |  | 85227 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 | flex | 2025-05-14 | Z | 2025-04-30 | 200 | 0 | 0 |  | 0 | 570 |  | EF-7 |  | 14
2025-05-14 | 2257 | w | 84355 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2025-05-21 | Z | 2025-05-08 | 20 | 0 | 0 |  | 0 | 60 |  | Sleeves |  | 13
2025-05-15 | 2274 | w | 84356 | A | DONE | 2 | S |  | BARTILLION 6240024 | 2" FB | 2025-05-20 | Z | 2025-05-14 | 40 | 0 | 0 |  | 20 | 80 |  | Misc |  | 6
2025-05-13 | 2483 |  | 69977 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2025-05-15 | Z | 2025-05-08 | 20 | 0 | 0 |  | 0 | 60 |  | Vivarium |  | 7
2025-05-16 | 827 |  | 70751.3 - 70751.4 | A | DONE | 3 | S-M |  | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-02-12 | 60 | 0 | 0 |  | 0 | 80 |  | 4th Floor hangers |  | 96
2025-05-13 | 831 | w | 70754 | A | DONE | 2 | S-M |  | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-02-12 | 50 | 0 | 0 |  | 0 | 140 |  | VTAC Con. Sleeve 4TH C/D |  | 96
2025-05-14 | 856 | sp | 70731 | A | DONE | 52 | L |  | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-03-14 | 40 | 1260 | 0 |  | 0 | 1190 |  | 4TH FL-EG-12 |  | 66
2025-05-16 | 891 |  | 73898 | A | DONE | 3 | S | pt.pcd | DELLSHIRE 6240017 | 1" liner | 2025-05-19 | Z | 2025-05-02 | 20 | 40 | 0 |  | 20 | 60 |  | Misc |  | 17
2025-05-16 | 892 | sp | 73667 - 73668 | A | DONE | 58 | M |  | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-05-02 | 70 | 1370 | 0 |  | 0 | 1300 |  | 1,2nd EA Riser |  | 17
2025-05-16 | 895 |  | 73701 - 73702 | A | DONE | 22 | M |  | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-05-05 | 370 | 0 | 170 | F | 0 | 730 |  | AHU-6 RA |  | 14
2025-05-16 | 896 | bth | 73703 - 73704 | A | DONE | 15 | S-M |  | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-05-05 | 110 | 260 | 0 |  | 0 | 350 |  | EA-1st floor D |  | 14
2025-05-16 | 897 |  | 73705 - 73706 , 73708 | A | DONE | 30 | M |  | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-05-05 | 710 | 0 | 40 | F | 0 | 1030 |  | AHU-7 RA |  | 14
2025-05-16 | 3500 |  | 73751 | A | DONE | 2 | S | neal | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-05-15 | 30 | 0 | 0 |  | 0 | 70 |  | Misc Flashing |  | 4
2025-05-15 | 3501 | w | 73752 - 73753 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-05-19 | Z | 2025-05-15 | 20 | 0 | 0 |  | 0 | 70 |  | CW stone sleeves |  | 4
2025-05-15 | 1602 |  | 97709 | A | DONE | 2 | S | BI | DOC JDC 6240023 |  | 2025-05-19 | Z | 2025-05-15 | 20 | 0 | 0 |  | 0 | 30 |  | Plate |  | 4
2025-05-12 | 215 |  | 74553 | A | DONE | 2 | S |  | DON S. |  | 2025-05-16 | Z | 2025-05-08 | 20 | 0 | 0 |  | 0 | 20 |  | Adaptor |  | 8
2025-05-13 | 217 | bth | 84722 | A | DONE | 3 | S |  | EDGERTON GEAR 4240036 | accuflange | 2025-05-13 | Z | 2025-05-13 | 70 | 0 | 0 |  | 0 | 190 |  |  |  | 0
2025-05-15 | 219 |  | 83194 | A | DONE | 2 | S |  | EDGERTON GEAR 4240036 |  | 2025-05-15 | Z | 2025-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | RTU-2 |  | 0
2025-05-16 | 221 |  | 83195 | A | DONE | 11 | S-M |  | EDGERTON GEAR 4240036 |  | 2025-05-19 | Z | 2025-05-16 | 150 | 0 | 120 | F | 0 | 380 |  | RTU-4 |  | 3
2025-05-16 | 1246 | sp | 79049 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2025-05-20 | Z | 2025-05-12 | 40 | 20 | 0 |  | 0 | 60 |  | Silencer Add |  | 8
2025-05-14 | 218 |  | 74009 | A | DONE | 2 | S |  | JP CULLEN 4250016 |  | 2025-05-14 | Z | 2025-05-14 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2025-05-12 | 1705 |  | 74201 | A | DONE | 2 | S |  | MADISON COUNTRY 6250005 |  | 2025-05-16 | Z | 2025-05-12 | 20 | 0 | 0 |  | 0 | 20 |  | Bathroom EA |  | 4
2025-05-12 | 3801 |  | 83609 | A | DONE | 3 | S-M |  | MONROE HS 6240018 |  | 2025-05-14 | Z | 2025-05-01 | 70 | 0 | 0 |  | 0 | 100 |  | MUA Drops |  | 13
2025-05-12 | 3802 |  | 85309 | A | DONE | 14 | S-M | neal | MONROE HS 6240018 |  | 2025-05-14 | Z | 2025-05-05 | 350 | 0 | 0 |  | 0 | 960 |  | Hangers |  | 9
2025-05-12 | 3803 |  | 85311 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-05-14 | Z | 2025-05-06 | 20 | 0 | 0 |  | 20 | 30 |  | 2nd B RA |  | 8
2025-05-16 | 3804 | w | DUCT SLEEVES | A | DONE | 2 | S-M |  | MONROE HS 6240018 |  | 2025-05-21 | Z | 2025-05-06 | 50 | 0 | 0 |  | 0 | 170 |  |  |  | 15
2025-05-12 | 3806 |  | TA-L2B-01 | A | DONE | 4 | S |  | MONROE HS 6240018 | 1" liner | 2025-05-14 | Z | 2025-05-06 | 80 | 0 | 0 |  | 80 | 100 |  |  |  | 8
2025-05-12 | 1767 | bth | EA-L1-02 | A | DONE | 22 | M |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 310 | 110 | 120 | F | 0 | 690 |  |  |  | 9
2025-05-12 | 1768 |  | OA-L1-03 | A | DONE | 5 | S |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 110 | 0 | 0 |  | 0 | 180 |  |  |  | 9
2025-05-13 | 1769 | bth | SALP-L1-01 | A | DONE | 10 | S |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 150 | 50 | 30 | F | 0 | 250 |  |  |  | 9
2025-05-13 | 1770 | bth | SALP-L1-02 | A | DONE | 14 | S-M |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 180 | 50 | 110 | F | 0 | 380 |  |  |  | 9
2025-05-13 | 1771 | bth | SALP-L1-03 | A | DONE | 20 | M |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 210 | 50 | 240 | F | 0 | 590 |  |  |  | 9
2025-05-12 | 1772 | bth | SALP-L1-04 | A | DONE | 18 | S-M |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 250 | 60 | 140 | F | 0 | 550 |  |  |  | 9
2025-05-13 | 1773 | bth | SALP-L1-06 | A | DONE | 11 | S-M |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 180 | 40 | 40 | F | 0 | 300 |  |  |  | 9
2025-05-13 | 1774 | bth | SALP-L1-07 | A | DONE | 7 | S |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 100 | 20 | 50 | F | 0 | 200 |  |  |  | 9
2025-05-13 | 1775 | bth | SALP-L1-10 | A | DONE | 8 | S |  | ONE 09 6240037 | flex | 2025-05-14 | Z | 2025-05-05 | 100 | 20 | 80 | F | 0 | 220 |  |  |  | 9
2025-05-13 | 1776 |  | RA-L1-01 | A | DONE | 7 | S-M |  | ONE 09 6240037 | flex , 1" liner | 2025-05-28 | Z | 2025-05-05 | 170 | 0 | 0 |  | 160 | 270 |  |  |  | 23
2025-05-13 | 1777 |  | RA-L1-02 | A | DONE | 4 | S |  | ONE 09 6240037 | flex , 1" liner | 2025-05-28 | Z | 2025-05-05 | 100 | 0 | 0 |  | 90 | 150 |  |  |  | 23
2025-05-12 | 485 |  | 55129 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-05-15 | Z | 2025-05-08 | 40 | 0 | 0 |  | 0 | 160 |  | C.O. 156 |  | 7
2025-05-12 | 3031 |  | 81833 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-05-13 | Z | 2025-05-12 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2025-05-14 | 3032 |  | 62746 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-05-15 | Z | 2025-05-14 | 60 | 0 | 0 |  | 0 | 100 |  | Misc |  | 1
2025-05-16 | 3033 |  | 62747 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2025-05-20 | Z | 2025-05-15 | 100 | 0 | 0 |  | 0 | 170 |  | RA |  | 5
2025-05-15 | 1418 | bth | PTH-MPSA-001 | A | DONE | 32 | M-L |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-03-26 | 460 | 50 | 280 | F | 0 | 1540 |  |  |  | 51
2025-05-15 | 1419 | bth | PTH-MPSA-002 | A | DONE | 28 | L |  | SPH SURGERY 6240039 | flex | 2025-05-16 | Z | 2025-03-26 | 540 | 20 | 130 | F | 0 | 1590 |  |  |  | 51
2025-05-13 | 1420 | bth | PTH-MPSA-003 | A | DONE | 10 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-03-26 | 70 | 160 | 0 |  | 0 | 270 |  |  |  | 51
2025-05-13 | 1421 | bth | PTH-MPSA-004 | A | DONE | 9 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-03-26 | 90 | 120 | 0 |  | 0 | 240 |  |  |  | 51
2025-05-15 | 1424 |  | PTH-EA-001 | A | DONE | 20 | M |  | SPH SURGERY 6240039 | flex | 2025-05-16 | Z | 2025-03-26 | 500 | 0 | 0 |  | 0 | 1230 |  |  |  | 51
2025-05-15 | 1425 |  | PTH-EA-002 | A | DONE | 24 | M |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-03-26 | 390 | 0 | 190 | F | 0 | 870 |  |  |  | 51
2025-05-15 | 2806 | bth | L1-A G1031A SS EA | A | DONE | 9 | S | ss | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 120 | 90 | 0 |  | 0 | 220 |  |  |  | 29
2025-05-15 | 2807 | bth | L1-A-EAV 12-9.1 | A | DONE | 6 | S | ss | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 50 | 70 | 30 | F | 0 | 150 |  |  |  | 29
2025-05-15 | 2808 | bth | L1-A-EAV 12-9 | A | DONE | 18 | S-M | pt.ss | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 280 | 20 | 150 | F | 0 | 470 |  |  |  | 29
2025-05-15 | 2809 | sp | L1-A-EAV 12-10 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 29
2025-05-15 | 2810 | bth | L1-A-EAV 12-18 | A | DONE | 6 | S | ss | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 80 | 20 | 30 | F | 0 | 230 |  |  |  | 29
2025-05-15 | 2811 | bth | PRV-12-1 SS | A | DONE | 14 | S-M | pt.ss | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 130 | 30 | 170 | F | 0 | 360 |  |  |  | 29
2025-05-13 | 2812 | sp | PRV-12-1.1 | A | DONE | 9 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 20 | 200 | 0 |  | 0 | 200 |  |  |  | 29
2025-05-14 | 2822 | sp | L1-A-RAV 12-1 | A | DONE | 6 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 60 | 80 | 0 |  | 0 | 260 |  |  |  | 29
2025-05-14 | 2823 | bth | L1-A-RAV 12-2 | A | DONE | 22 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 350 | 20 | 170 | F | 0 | 620 |  |  |  | 29
2025-05-14 | 2824 | bth | L1-A-RAV 12-3 | A | DONE | 23 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 330 | 20 | 220 | F | 0 | 660 |  |  |  | 29
2025-05-15 | 2825 | bth | L1-A-RAV 12-4 | A | DONE | 21 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 290 | 20 | 200 | F | 0 | 640 |  |  |  | 29
2025-05-15 | 2826 |  | L1-A-RAV 12-5.1 | A | DONE | 10 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 110 | 0 | 140 | F | 0 | 320 |  |  |  | 29
2025-05-15 | 2827 | bth | L1-A-RAV 12-5 | A | DONE | 17 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 230 | 20 | 170 | F | 0 | 560 |  |  |  | 29
2025-05-15 | 2828 | bth | L1-A-RAV 12-6 | A | DONE | 22 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 230 | 20 | 280 | F | 0 | 620 |  |  |  | 29
2025-05-15 | 2829 | bth | L1-A-RAV 12-11 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 70 | 20 | 0 |  | 0 | 120 |  |  |  | 29
2025-05-15 | 2830 | bth | L1-A-RAV 12-12 | A | DONE | 9 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 70 | 80 | 60 | F | 0 | 240 |  |  |  | 29
2025-05-14 | 2831 | sp | L1-A-RAV 12-16 | A | DONE | 6 | S |  | SPH SURGERY 6240039 |  | 2025-05-16 | Z | 2025-04-17 | 20 | 120 | 0 |  | 0 | 130 |  |  |  | 29
2025-05-13 | 2841 | bth | 68860 - 68862 | A | DONE | 9 | S-M |  | SPH SURGERY 6240039 |  | 2025-05-14 | Z | 2025-05-08 | 140 | 80 | 0 |  | 0 | 240 |  | Phase 1C |  | 6
2025-05-16 | 4062 |  | 84767 - 84768 | A | DONE | 2 | S | pt.neal | STOUGHTON TRAILER 6240015 | bird s. , 1" liner | 2025-05-19 | Z | 2025-05-08 | 50 | 0 | 0 |  | 20 | 70 |  | Café |  | 11
2025-05-16 | 4064 | bth | 73954 - 73955 | A | DONE | 9 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2025-05-19 | Z | 2025-05-16 | 60 | 160 | 0 |  | 0 | 210 |  | Misc |  | 3
2025-05-14 | 812 |  | 73570 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-05-19 | Z | 2025-05-08 | 20 | 0 | 0 |  | 0 | 20 |  | Piping storm collars |  | 11
2025-05-13 | 3756 |  | UW3565 | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-05-13 | Z | 2025-05-13 | 20 | 0 | 0 |  | 0 | 20 |  | EA duct collar |  | 0
2025-05-12 | 4395 |  | L6-SAMP 1 | A | DONE | 25 | M |  | UW-AVRL 6240038 |  | 2025-05-14 | Z | 2025-04-28 | 360 | 0 | 250 | F | 0 | 820 |  |  |  | 16
2025-05-12 | 4396 |  | L6-SAMP 2 | A | DONE | 15 | M |  | UW-AVRL 6240038 |  | 2025-05-14 | Z | 2025-04-28 | 110 | 0 | 250 | F | 0 | 480 |  |  |  | 16
2025-05-12 | 4397 |  | L6-OA 1 | A | DONE | 14 | S-M |  | UW-AVRL 6240038 |  | 2025-05-14 | Z | 2025-04-28 | 200 | 0 | 140 | F | 0 | 400 |  |  |  | 16
2025-05-12 | 758 |  | L3-TA 6 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 140 | 0 | 0 |  | 60 | 180 |  |  |  | 40
2025-05-12 | 763 | bth | L3-RAMP 30 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 90 | 30 | 60 | F | 60 | 220 |  |  |  | 40
2025-05-12 | 768 |  | L3-EAMP 3 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-05-13 | Z | 2025-04-03 | 130 | 0 | 40 | F | 20 | 220 |  |  |  | 40
2025-05-12 | 769 |  | L3-EAMP 4 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-03 | 60 | 0 | 0 |  | 20 | 90 |  |  |  | 40
2025-05-16 | 771 |  | L3-SAT 3-3-37.3 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-05-20 | Z | 2025-04-03 | 170 | 0 | 80 | F | 0 | 310 |  |  |  | 47
2025-05-13 | 3705 |  | 83817 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-20 | Z | 2025-05-06 | 20 | 0 | 0 |  | 0 | 20 |  | LVL 3 fire damper DM |  | 14
2025-05-12 | 4033 | bth | L3-RAMP 1 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | VD | 2025-05-13 | Z | 2025-04-08 | 130 | 20 | 120 | F | 20 | 330 |  |  |  | 35
2025-05-12 | 4034 | bth | L3-RAMP 2 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 150 | 30 | 160 | F | 90 | 410 |  |  |  | 35
2025-05-12 | 4035 | bth | L3-RAMP 3 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 90 | 50 | 70 | F | 60 | 260 |  |  |  | 35
2025-05-12 | 4036 | bth | L3-RAMP 4 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 80 | 60 | 30 | F | 40 | 180 |  |  |  | 35
2025-05-12 | 4039 | bth | L3-RAMP 14 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 100 | 60 | 50 | F | 50 | 250 |  |  |  | 35
2025-05-12 | 4040 | bth | L3-RAMP 15 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-13 | Z | 2025-04-08 | 80 | 20 | 30 | F | 50 | 140 |  |  |  | 35
2025-05-12 | 1857 |  | 66625 | A | DONE | 2 | S-M |  | UWP-FH 6240021 |  | 2025-05-15 | Z | 2025-05-08 | 50 | 0 | 0 |  | 0 | 140 |  | Flat stock |  | 7
2025-05-16 | 2854 |  | 84842 - 84843 | A | DONE | 4 | S-M | pcd | UWRF 6230010 |  | 2025-05-19 | Z | 2025-05-01 | 80 | 0 | 0 |  | 0 | 120 |  | L1-FE , L3-FE |  | 18
2025-05-15 | 2855 |  | 84844 | A | DONE | 6 | S | ss | UWRF 6230010 |  | 2025-05-19 | Z | 2025-05-01 | 20 | 120 | 0 |  | 0 | 140 |  | 111 Hood |  | 18
2025-05-13 | 2859 |  | 84849 | delete | DONE | 0 | S |  | UWRF 6230010 | paint , 1" liner | 2025-05-27 | Z | 2025-05-12 | 0 | 0 | 0 |  | 0 | 0 |  | 1st Floor TA |  | 15
2025-05-16 | 2860 | sp | 84841 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-05-19 | Z | 2025-05-13 | 0 | 30 | 0 |  | 0 | 30 |  | L1-GE |  | 6
2025-05-13 | 4414 |  | 70181 - 70182 | A | DONE | 22 | S-M | alum | UWSP CHAMPION HALL 6240008 |  | 2025-05-16 | Z | 2025-05-01 | 550 | 0 | 0 |  | 0 | 520 |  | Intake Hood Panels |  | 15
2025-05-13 | 2041 |  | 57616 , 57618 | A | DONE | 4 | S-M |  | UW-VET MED 6210014 | coils | 2025-05-15 | Z | 2025-05-01 | 100 | 0 | 0 |  | 0 | 150 |  | Misc |  | 14
2025-05-13 | 2042 | sp | 57617 , 57622 | A | DONE | 7 | S-M |  | UW-VET MED 6210014 |  | 2025-05-15 | Z | 2025-05-01 | 40 | 120 | 0 |  | 0 | 150 |  | Misc |  | 14
2025-05-13 | 2043 |  | 57619 - 57621 | A | DONE | 31 | S-M |  | UW-VET MED 6210014 | VD | 2025-05-15 | Z | 2025-05-01 | 140 | 0 | 630 | F | 0 | 920 |  | Misc |  | 14
2025-05-14 | 3850 |  | 74761 | A | DONE | 178 | L | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-05-15 | Z | 2025-04-29 | 930 | 0 | 3500 | F | 3950 | 5270 |  | EA Reducers |  | 16
2025-05-14 | 3851 |  | 74762 | A | DONE | 186 | L | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-05-15 | Z | 2025-04-29 | 720 | 0 | 3930 | F | 4080 | 5540 |  | EA Straight |  | 16
2025-05-14 | 3852 |  | 74763 | A | DONE | 43 | L | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-05-15 | Z | 2025-04-29 | 1060 | 0 | 0 |  | 930 | 1590 |  | EA Elbows |  | 16
2025-05-12 | 3853 |  | 74765 | A | DONE | 3 | L | neal | UW-WITTE HALL 6250003 |  | 2025-05-15 | Z | 2025-04-29 | 60 | 0 | 0 |  | 0 | 90 |  | Hangers |  | 16
2025-05-12 | 1686 |  | 79842 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-14 | Z | 2025-05-05 | 40 | 0 | 0 |  | 0 | 110 |  | E-Roof |  | 9
2025-05-12 | 1688 | w | 79839 | A | DONE | 2 | S-M | ss | WAUNAKEE MS 6230013 |  | 2025-05-14 | Z | 2025-05-05 | 20 | 0 | 0 |  | 0 | 60 |  | E-Section EA |  | 9
2025-05-12 | 1689 |  | 79877 | A | DONE | 5 | S | pt.neal | WAUNAKEE MS 6230013 |  | 2025-05-14 | Z | 2025-05-08 | 120 | 0 | 0 |  | 0 | 170 |  | Louver Section G |  | 6
2025-05-13 | 1690 |  | 79846 - 79847 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-05-16 | Z | 2025-05-08 | 20 | 0 | 0 |  | 20 | 40 |  | HP - 2-227 RA |  | 8
2025-05-16 | 1693 | w | 83402 - 83403 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | 1" DB | 2025-05-21 | Z | 2025-05-09 | 40 | 0 | 0 |  | 30 | 100 |  | Curb extension |  | 12
2025-05-12 | 1696 |  | 84282 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-12 | Z | 2025-05-12 | 20 | 0 | 0 |  | 0 | 20 |  | Coupling |  | 0
2025-05-15 | 1697 |  | 83304 | A | DONE | 4 | S-M | pt.neal | WAUNAKEE MS 6230013 |  | 2025-05-16 | Z | 2025-05-15 | 100 | 0 | 0 |  | 0 | 140 |  | Flashing |  | 1
2025-05-16 | 1698 |  | 83305 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-05-20 | Z | 2025-05-15 | 20 | 0 | 0 |  | 0 | 30 |  | G-Section out / flashing |  | 5
2025-05-12 | 1289 |  | 82224 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2025-05-16 | Z | 2025-05-12 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 4
[6 empty] | 1408 | [13 empty] | 44610 |  |  |  | 7500 | 16.81%
WEEK OF 5-19-2025
2025-05-20 | 283 |  | 69435 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-05-21 | Z | 2025-05-12 | 30 | 0 | 0 |  | 0 | 40 |  | ERV-1 OAS |  | 9
2025-05-19 | 284 | w | 85229 | A | DONE | 3 | S-M | ss | 121 E. WILSON 6230024 |  | 2025-05-20 | Z | 2025-05-13 | 70 | 0 | 0 |  | 0 | 280 |  | Snow melt boxes |  | 7
2025-05-20 | 285 |  | 85230 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | flex | 2025-05-21 | Z | 2025-05-19 | 20 | 0 | 0 |  | 0 | 20 |  | EF-12 |  | 2
2025-05-20 | 2254 |  | 69738 , 69746 | A | DONE | 12 | S-M |  | BARTILLION 6240024 | 1" liner | 2025-05-21 | Z | 2025-05-05 | 150 | 0 | 140 | F | 230 | 380 |  | Kitchen / Dishwasher |  | 16
2025-05-20 | 2255 |  | 69739 - 69743 | A | DONE | 47 | M-L |  | BARTILLION 6240024 | VD's | 2025-05-21 | Z | 2025-05-05 | 700 | 0 | 470 | F | 0 | 1520 |  | Kitchen / Dishwasher |  | 16
2025-05-20 | 2256 |  | 69744 - 69745 | A | DONE | 13 | M |  | BARTILLION 6240024 |  | 2025-05-21 | Z | 2025-05-05 | 240 | 0 | 70 | F | 0 | 380 |  | Kitchen / Dishwasher |  | 16
2025-05-19 | 2258 | w | 69737 , 69749 | A | DONE | 12 | M | BI | BARTILLION 6240024 |  | 2025-05-21 | Z | 2025-05-08 | 280 | 0 | 0 |  | 0 | 790 |  | Kitchen Hood |  | 13
2025-05-19 | 2259 |  | PRE-FAB TEAR DROP | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2025-05-21 | Z | 2025-05-09 | 20 | 0 | 0 |  | 0 | 20 |  | Hangers |  | 12
2025-05-22 | 898 |  | 73709 - 73710 | A | DONE | 8 | S |  | DELLSHIRE 6240017 | flex | 2025-05-26 | Z | 2025-05-08 | 150 | 40 | 0 |  | 0 | 320 |  | AHU Outs |  | 18
2025-05-22 | 899 | bth | 73899 | A | DONE | 5 | S |  | DELLSHIRE 6240017 |  | 2025-05-26 | Z | 2025-05-08 | 70 | 50 | 0 |  | 0 | 120 |  | Misc |  | 18
2025-05-20 | 1245 |  | 79048 | A | DONE | 2 | S-M |  | EXACT 501 6240025 |  | 2025-05-21 | Z | 2025-05-09 | 30 | 0 | 0 |  | 0 | 40 |  | Screen protectors |  | 12
2025-05-20 | 1247 |  | 56804 - 56807 | A | DONE | 8 | M |  | EXACT TL-3 6240028 | paint , flex | 2025-05-21 | Z | 2025-05-15 | 190 | 0 | 0 |  | 80 | 270 |  | GRD finshes |  | 6
2025-05-20 | 1248 |  | 56808 - 56811 | A | DONE | 5 | M |  | EXACT TL-3 6240028 | paint , flex | 2025-05-21 | Z | 2025-05-15 | 120 | 0 | 0 |  | 80 | 180 |  | GRD finshes |  | 6
2025-05-20 | 1249 |  | 56812 - 56814 | A | DONE | 3 | S-M |  | EXACT TL-3 6240028 | paint , flex | 2025-05-21 | Z | 2025-05-15 | 70 | 0 | 0 |  | 40 | 90 |  | GRD finshes |  | 6
2025-05-19 | 220 |  | 74051 | A | DONE | 2 | S |  | JP CULLEN 4250016 | 1/2" liner | 2025-05-21 | Z | 2025-05-15 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 6
2025-05-22 | 222 |  | 74052 | A | DONE | 2 | S |  | LAKE RIDGE BANK 4250028 | 1" liner | 2025-05-27 | Z | 2025-05-20 | 40 | 0 | 0 |  | 30 | 50 |  | TA boxes |  | 7
2025-05-21 | 3825 |  | 85312 | A | DONE | 4 | S |  | MONROE HS 6240018 |  | 2025-05-23 | Z | 2025-05-16 | 80 | 0 | 0 |  | 0 | 120 |  | B2 |  | 7
2025-05-21 | 1758 |  | EA-L1-01 | A | DONE | 5 | S |  | ONE 09 6240037 | flex , CD | 2025-05-21 | Z | 2025-05-05 | 40 | 0 | 70 | F | 0 | 110 |  |  |  | 16
2025-05-21 | 1760 |  | OA-L1-01 | A | DONE | 2 | S |  | ONE 09 6240037 | flex | 2025-05-21 | Z | 2025-05-05 | 50 | 0 | 0 |  | 0 | 100 |  |  |  | 16
2025-05-21 | 1761 |  | OA-L1-02 | A | DONE | 3 | S |  | ONE 09 6240037 | flex | 2025-05-21 | Z | 2025-05-05 | 40 | 0 | 30 | F | 0 | 80 |  |  |  | 16
2025-05-20 | 1762 |  | RA-L1-04 | A | DONE | 10 | S-M |  | ONE 09 6240037 | flex , 1" liner | 2025-05-21 | Z | 2025-05-05 | 190 | 0 | 40 | F | 170 | 290 |  |  |  | 16
2025-05-21 | 1763 | sp | SALP-L1-11 | A | DONE | 5 | S |  | ONE 09 6240037 | flex | 2025-05-21 | Z | 2025-05-05 | 40 | 80 | 0 |  | 0 | 120 |  |  |  | 16
2025-05-21 | 1764 | bth | SALP-L1-12 | A | DONE | 21 | M |  | ONE 09 6240037 | flex | 2025-05-21 | Z | 2025-05-05 | 330 | 60 | 130 | F | 0 | 730 |  |  |  | 16
2025-05-20 | 1765 | bth | SALP-L1-13 | A | DONE | 24 | M |  | ONE 09 6240037 | flex | 2025-05-21 | Z | 2025-05-05 | 320 | 40 | 240 | F | 0 | 580 |  |  |  | 16
2025-05-20 | 1766 | sp | SALP-L1-14 | A | DONE | 8 | S |  | ONE 09 6240037 |  | 2025-05-21 | Z | 2025-05-05 | 20 | 170 | 0 |  | 0 | 170 |  |  |  | 16
2025-05-23 | 1778 | w | 69430 - 69431 | A | DONE | 34 | L | BI | ONE 09 6240037 | drain | 2025-05-26 | Z | 2025-05-09 | 830 | 0 | 0 |  | 0 | 2360 |  | FH Grease duct |  | 17
2025-05-23 | 1821 |  | L1A-RAMP 5 | A | DONE | 19 | M |  | PEWAUKEE HS 6240030 | nipple , 1" liner | 2025-06-09 | Z | 2025-05-06 | 220 | 0 | 240 | F | 410 | 720 |  |  |  | 34
2025-05-23 | 1823 | bth | L1A-EA 2 | A | DONE | 7 | S |  | PEWAUKEE HS 6240030 | 1" liner | 2025-06-09 | Z | 2025-05-06 | 50 | 120 | 0 |  | 20 | 160 |  |  |  | 34
2025-05-20 | 1824 |  | 74109 | A | DONE | 5 | S |  | PEWAUKEE HS 6240030 |  | 2025-05-21 | Z | 2025-05-06 | 30 | 0 | 90 | F | 0 | 140 |  | Existing locker Rm |  | 15
2025-05-20 | 1825 |  | 74151 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-05-21 | Z | 2025-05-12 | 20 | 0 | 0 |  | 0 | 40 |  | Stairwell EC's |  | 9
2025-05-21 | 466 | bth | L02_NC_SALP_002 | A | DONE | 14 | S-M |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 40 | 20 | 290 | F | 0 | 420 |  |  |  | 29
2025-05-21 | 467 | bth | L02_NC_SALP_003 | A | DONE | 18 | M |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 20 | 20 | 400 | F | 0 | 530 |  |  |  | 29
2025-05-21 | 468 | bth | L02_NC_SALP_004 | A | DONE | 14 | S-M |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 50 | 20 | 260 | F | 0 | 390 |  |  |  | 29
2025-05-21 | 469 | bth | L02_NC_SALP_005 | A | DONE | 16 | S-M |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 20 | 20 | 350 | F | 0 | 470 |  |  |  | 29
2025-05-21 | 470 | sp | L02_NC_SALP_006 | A | DONE | 17 | S-M |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 30 | 380 | 0 |  | 0 | 480 |  |  |  | 29
2025-05-20 | 471 | sp | L02_NC_SALP_007 | A | DONE | 9 | S |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 20 | 190 | 0 |  | 0 | 200 |  |  |  | 29
2025-05-20 | 472 | sp | L02_NC_SALP_008 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 20 | 100 | 0 |  | 0 | 120 |  |  |  | 29
2025-05-20 | 473 | bth | L02_NC_SALP_009 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 40 | 100 | 0 |  | 0 | 140 |  |  |  | 29
2025-05-20 | 474 | sp | L02_NC_SALP_010 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 20 | 140 | 0 |  | 0 | 140 |  |  |  | 29
2025-05-20 | 475 | sp | L02_NC_SALP_011 | A | DONE | 9 | S |  | PROJECT DOVE 6240041 |  | 2025-05-22 | Z | 2025-04-23 | 20 | 190 | 0 |  | 0 | 190 |  |  |  | 29
2025-05-20 | 3025 |  | 62738 | A | DONE | 34 | S-M |  | PROMEGA BTC 6230022 |  | 2025-05-21 | Z | 2025-04-25 | 30 | 0 | 810 | F | 0 | 1510 |  | SA |  | 26
2025-05-19 | 3034 | sp | 81834 | A | DONE | 6 | S |  | PROMEGA BTC 6230022 |  | 2025-05-20 | Z | 2025-05-15 | 20 | 120 | 0 |  | 0 | 120 |  | OA |  | 5
2025-05-22 | 2837 |  | 68473 | A | DONE | 9 | S |  | SPH SURGERY 6240039 | paint | 2025-05-23 | Z | 2025-05-08 | 210 | 0 | 0 |  | 190 | 550 |  | OA Louver pc 5 |  | 15
2025-05-22 | 2838 |  | 68482 | A | DONE | 22 | M-L |  | SPH SURGERY 6240039 | paint | 2025-05-23 | Z | 2025-05-08 | 550 | 0 | 0 |  | 520 | 1840 |  | Misc |  | 15
2025-05-21 | 2839 |  | 68483 | A | DONE | 2 | S |  | SPH SURGERY 6240039 | paint | 2025-05-23 | Z | 2025-05-08 | 50 | 0 | 0 |  | 50 | 70 |  | Misc louver trim |  | 15
2025-05-21 | 2840 |  | 68858 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-23 | Z | 2025-05-08 | 40 | 0 | 0 |  | 0 | 50 |  | SAMP 2 |  | 15
2025-05-22 | 2842 |  | 68485 - 68486 | A | DONE | 8 | S-M |  | SPH SURGERY 6240039 | paint | 2025-05-23 | Z | 2025-05-13 | 180 | 0 | 0 |  | 170 | 500 |  | PH EA Louvers |  | 10
2025-05-22 | 2843 |  | 68482 - 1 | A | DONE | 18 | S-M |  | SPH SURGERY 6240039 | paint | 2025-05-23 | Z | 2025-05-13 | 440 | 0 | 0 |  | 430 | 1490 |  | PH EA Louvers |  | 10
2025-05-21 | 2844 |  | 68487 , 68863 | A | DONE | 3 | S |  | SPH SURGERY 6240039 |  | 2025-05-23 | Z | 2025-05-13 | 30 | 0 | 30 | F | 0 | 60 |  | VAV 1st , VAV 12-12 |  | 10
2025-05-20 | 2845 |  | 68864 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-23 | Z | 2025-05-15 | 20 | 0 | 0 |  | 0 | 30 |  | SALP-001 |  | 8
2025-05-19 | 4063 | bth | 73952 - 73953 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-05-19 | Z | 2025-05-16 | 30 | 20 | 0 |  | 0 | 60 |  | 1A , 1B |  | 3
2025-05-22 | 801 |  | 73552 - 73555 | delete |  |  | M-L |  | SW HEALTH OR 5 6250004 | flex | 2025-05-23 | Z | 2025-03-24 | 0 | 0 | 0 |  | 0 | 0 |  | RTU-1 RA |  | 60
2025-05-22 | 802 |  | 73556 | delete |  |  | M |  | SW HEALTH OR 5 6250004 | 2" DB , 1-1/2" wrap | 2025-05-23 | Z | 2025-03-24 | 0 | 0 | 0 |  | 0 | 0 |  | RTU-1 drop cap |  | 60
2025-05-22 | 803 |  | 73557 - 73559 | delete |  |  | M |  | SW HEALTH OR 5 6250004 | flex | 2025-05-23 | Z | 2025-03-24 | 0 | 0 | 0 |  | 0 | 0 |  | RTU-1 SA |  | 60
2025-05-22 | 804 |  | 73560 | delete |  |  | S-M |  | SW HEALTH OR 5 6250004 | flex | 2025-05-23 | Z | 2025-03-24 | 0 | 0 | 0 |  | 0 | 0 |  | RTU-1 OA |  | 60
2025-05-22 | 805 | sp | 73561 | delete |  |  | M |  | SW HEALTH OR 5 6250004 |  | 2025-05-23 | Z | 2025-03-26 | 0 | 0 | 0 |  | 0 | 0 |  | Roof EA duct |  | 58
2025-05-20 | 3757 |  | 69142 | A | DONE | 2 | S | neal | UW-AVRL 6240038 |  | 2025-05-21 | Z | 2025-05-15 | 30 | 0 | 0 |  | 0 | 60 |  | B/D Flashing |  | 6
2025-05-19 | 3758 |  | 69143 - 69144 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-05-21 | Z | 2025-05-15 | 30 | 0 | 0 |  | 0 | 50 |  | D Flashing |  | 6
2025-05-19 | 759 |  | L3-SAT 3-3-37.1 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 | 1" liner , VAV | 2025-05-20 | Z | 2025-04-03 | 180 | 0 | 270 | F | 70 | 560 |  |  |  | 47
2025-05-19 | 760 | bth | L3-SAT 3-3-37.2 | A | DONE | 13 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-05-20 | Z | 2025-04-03 | 200 | 20 | 90 | F | 0 | 350 |  |  |  | 47
2025-05-19 | 792 | bth | L3-SAT 3-3-19 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 80 | 20 | 0 |  | 40 | 120 |  |  |  | 43
2025-05-19 | 793 | bth | L3-SAT 3-3-20 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 70 | 20 | 20 | F | 30 | 110 |  |  |  | 43
2025-05-19 | 794 | bth | L3-SAT 3-3-21 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 50 | 20 | 0 |  | 30 | 80 |  |  |  | 43
2025-05-19 | 795 | bth | L3-SAT 3-3-22 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 70 | 40 | 0 |  | 40 | 140 |  |  |  | 43
2025-05-19 | 796 | bth | L3-SAT 3-3-23 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 60 | 40 | 60 | F | 30 | 170 |  |  |  | 43
2025-05-19 | 797 | bth | L3-SAT 3-3-24 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 70 | 20 | 40 | F | 30 | 140 |  |  |  | 43
2025-05-19 | 798 | bth | L3-SAT 3-3-25 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 50 | 0 | 20 | F | 30 | 90 |  |  |  | 43
2025-05-19 | 799 | bth | L3-SAT 3-3-26 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 30 | 0 | 30 | F | 40 | 80 |  |  |  | 43
2025-05-19 | 3706 |  | L5-RAMP 17 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-05-20 | Z | 2025-05-08 | 160 | 0 | 40 | F | 20 | 240 |  |  |  | 12
2025-05-19 | 3707 | bth | L5-RAMP 18 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-20 | Z | 2025-05-08 | 160 | 40 | 130 | F | 70 | 420 |  |  |  | 12
2025-05-19 | 3708 | bth | L5-RAMP 19 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-20 | Z | 2025-05-08 | 150 | 20 | 170 | F | 50 | 400 |  |  |  | 12
2025-05-19 | 3709 | bth | L5-RAMP 20 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-20 | Z | 2025-05-08 | 40 | 50 | 150 | F | 30 | 280 |  |  |  | 12
2025-05-19 | 3710 | bth | L5-RAMP 21 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-20 | Z | 2025-05-08 | 220 | 120 | 120 | F | 130 | 560 |  |  |  | 12
2025-05-19 | 3711 | bth | L5-RAMP 22 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-20 | Z | 2025-05-08 | 170 | 80 | 80 | F | 80 | 370 |  |  |  | 12
2025-05-19 | 3712 | bth | L5-RAMP 23 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-20 | Z | 2025-05-08 | 130 | 80 | 150 | F | 60 | 400 |  |  |  | 12
2025-05-19 | 3713 |  | L5-RAMP 24 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 | VD's | 2025-05-20 | Z | 2025-05-08 | 120 | 0 | 70 | F | 50 | 260 |  |  |  | 12
2025-05-19 | 3714 | bth | L5-RAMP 25 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-20 | Z | 2025-05-08 | 120 | 20 | 120 | F | 70 | 330 |  |  |  | 12
2025-05-19 | 3715 |  | L5-RAMP 26 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-05-20 | Z | 2025-05-08 | 120 | 0 | 80 | F | 0 | 230 |  |  |  | 12
2025-05-19 | 3716 | bth | L5-RAMP 27 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-20 | Z | 2025-05-08 | 90 | 60 | 30 | F | 20 | 200 |  |  |  | 12
2025-05-19 | 3717 | bth | L5-RAMP 28 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-05-20 | Z | 2025-05-08 | 130 | 40 | 120 | F | 30 | 330 |  |  |  | 12
2025-05-19 | 3718 |  | L5-EAMP 2 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-05-20 | Z | 2025-05-08 | 190 | 0 | 90 | F | 20 | 380 |  |  |  | 12
2025-05-19 | 3719 | sp | 83819 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-20 | Z | 2025-05-08 | 20 | 20 | 0 |  | 0 | 20 |  | LL-3-L-10 , L2-3-2-11 |  | 12
2025-05-19 | 4000 | bth | L3-SAT 3-3-27 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 60 | 20 | 0 |  | 30 | 120 |  |  |  | 43
2025-05-19 | 4001 | bth | L3-SAT 3-3-28 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 40 | 60 | 0 |  | 30 | 110 |  |  |  | 43
2025-05-19 | 4002 | bth | L3-SAT 3-3-29 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 40 | 20 | 30 | F | 40 | 100 |  |  |  | 43
2025-05-19 | 4003 | bth | L3-SAT 3-3-30 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 20 | 20 | 30 | F | 30 | 80 |  |  |  | 43
2025-05-19 | 4004 |  | L3-SAT 3-3-31 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 43
2025-05-19 | 4005 | bth | L3-SAT 3-3-32 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 20 | 60 | 30 | F | 30 | 120 |  |  |  | 43
2025-05-19 | 4006 | bth | L3-SAT 3-3-33 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-05-20 | Z | 2025-04-07 | 20 | 20 | 40 | F | 30 | 80 |  |  |  | 43
2025-05-19 | 4032 | bth | L3-SAMP 4 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-20 | Z | 2025-04-08 | 70 | 40 | 70 | F | 0 | 200 |  |  |  | 42
2025-05-23 | 3955 |  | 74510 - 74513 | A | DONE | 21 | M |  | UWL-GRAFF 6230017 |  | 2025-05-26 | Z | 2025-05-08 | 510 | 0 | 0 |  | 0 | 1100 |  | AHU Outs |  | 18
2025-05-22 | 3956 |  | 74514 - 74518 | A | DONE | 45 | M |  | UWL-GRAFF 6230017 |  | 2025-05-26 | Z | 2025-05-08 | 1060 | 0 | 60 | F | 0 | 1980 |  | AHU Outs |  | 18
2025-05-22 | 3957 |  | 74519 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 | VD | 2025-05-26 | Z | 2025-05-08 | 100 | 0 | 20 | F | 0 | 230 |  | RA AHU / SAT-1-2-11 |  | 18
2025-05-23 | 3958 |  | 74521 - 74524 | A | DONE | 31 | M |  | UWL-GRAFF 6230017 |  | 2025-05-26 | Z | 2025-05-13 | 490 | 0 | 270 | F | 0 | 1310 |  | AHU Outs |  | 13
2025-05-22 | 3959 |  | 74525 - 74528 | A | DONE | 28 | M |  | UWL-GRAFF 6230017 |  | 2025-05-26 | Z | 2025-05-13 | 410 | 0 | 280 | F | 0 | 1200 |  | AHU Outs |  | 13
2025-05-22 | 3960 |  | 74529 - 74533 | A | DONE | 32 | M |  | UWL-GRAFF 6230017 |  | 2025-05-26 | Z | 2025-05-13 | 530 | 0 | 260 | F | 0 | 1370 |  | AHU Outs |  | 13
2025-05-22 | 3961 | sp | 74535 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-05-26 | Z | 2025-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd duct test |  | 11
2025-05-21 | 1855 |  | 66621 - 66622 | A | DONE | 11 | S-M |  | UWP-FH 6240021 | VD's | 2025-05-22 | Z | 2025-05-08 | 100 | 0 | 160 | F | 0 | 310 |  | LL SA |  | 14
2025-05-20 | 1856 | sp | 66623 - 66624 | A | DONE | 3 | S |  | UWP-FH 6240021 |  | 2025-05-22 | Z | 2025-05-08 | 30 | 50 | 0 |  | 0 | 80 |  | LL SA |  | 14
2025-05-20 | 1861 | bth | 66626 | A | DONE | 2 | S-M |  | UWP-FH 6240021 |  | 2025-05-22 | Z | 2025-05-15 | 20 | 20 | 0 |  | 0 | 50 |  | 2nd fl EA |  | 7
2025-05-23 | 3260 |  | 81286 , 81288 - 81291 | A | DONE | 4 | S-M |  | UWSP ALBERTSON 6230016 | bird s. , flex | 2025-05-27 | Z | 2025-05-20 | 90 | 0 | 0 |  | 0 | 140 |  | Misc |  | 7
2025-05-21 | 2036 |  | 57604 - 57606 | A | DONE | 5 | S-M |  | UW-VET MED 6210014 | coil | 2025-05-22 | Z | 2025-04-25 | 110 | 0 | 0 |  | 0 | 160 |  | 7B SA |  | 27
2025-05-21 | 2037 | bth | 57610 - 57611 | A | DONE | 7 | S-M |  | UW-VET MED 6210014 |  | 2025-05-22 | Z | 2025-04-25 | 70 | 100 | 0 |  | 0 | 170 |  | 7B SA |  | 27
2025-05-21 | 2044 |  | 57623 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-05-22 | Z | 2025-05-12 | 20 | 0 | 0 |  | 0 | 30 |  | 7B 2-1-1 |  | 10
2025-05-20 | 2045 | sp | 57624 | A | DONE | 5 | S |  | UW-VET MED 6210014 |  | 2025-05-22 | Z | 2025-05-12 | 20 | 90 | 0 |  | 0 | 100 |  | 7B 2-1-1 |  | 10
2025-05-21 | 3071 | bth | 57637 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-05-22 | Z | 2025-05-13 | 30 | 20 | 0 |  | 0 | 50 |  | 10-D outs |  | 9
2025-05-20 | 3072 |  | 57638 | A | DONE | 3 | S |  | UW-VET MED 6210014 |  | 2025-05-22 | Z | 2025-05-19 | 70 | 0 | 0 |  | 0 | 80 |  | Flashing |  | 3
2025-05-22 | 223 |  | 84994 | A | DONE | 2 | S |  | UWW METALS LAB 6250001 | 1" liner | 2025-05-23 | Z | 2025-05-21 | 20 | 0 | 0 |  | 20 | 50 |  | Misc EC's |  | 2
2025-05-19 | 216 |  | 85355 | A | DONE | 2 | S-M |  | VERNON HOSPITAL 4259999 | filter rack | 2025-05-20 | Z | 2025-05-13 | 40 | 0 | 0 |  | 0 | 60 |  | Filter rack |  | 7
2025-05-21 | 969 | bth | L02_D_SOA_001 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 150 | 20 | 150 | F | 0 | 490 |  |  |  | 93
2025-05-21 | 970 | bth | L02_D_SOA_002 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 90 | 30 | 170 | F | 0 | 360 |  |  |  | 93
2025-05-21 | 971 | bth | L02_D_SOA_003 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 50 | 50 | 140 | F | 0 | 270 |  |  |  | 93
2025-05-21 | 972 | bth | L02_D_SOA_004 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 60 | 30 | 130 | F | 0 | 270 |  |  |  | 93
2025-05-21 | 973 | bth | L02_D_SOA_005 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 30 | 90 | 60 | F | 0 | 180 |  |  |  | 93
2025-05-21 | 974 | sp | L02_D_SOA_006 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 20 | 160 | 0 |  | 0 | 170 |  |  |  | 93
2025-05-21 | 975 | bth | L02_D_SOA_007 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 110 | 40 | 0 |  | 0 | 160 |  |  |  | 93
2025-05-21 | 976 |  | L02_D_SOA_008 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 110 | 0 | 170 | F | 0 | 370 |  |  |  | 93
2025-05-21 | 977 |  | L02_D_SOA_009 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 50 | 0 | 250 | F | 0 | 400 |  |  |  | 93
2025-05-21 | 978 |  | L02_D_SOA_010 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 80 | 0 | 180 | F | 0 | 340 |  |  |  | 93
2025-05-21 | 979 | bth | L02_D_SOA_011 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 70 | 170 | 130 | F | 0 | 410 |  |  |  | 93
2025-05-21 | 980 | bth | L02_D_SOA_012 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 70 | 130 | 70 | F | 0 | 310 |  |  |  | 93
2025-05-21 | 981 | bth | L02_D_SOA_013 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 50 | 40 | 40 | F | 0 | 150 |  |  |  | 93
2025-05-21 | 982 | sp | L02_D_SOA_014 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 20 | 100 | 0 |  | 0 | 110 |  |  |  | 93
2025-05-21 | 983 |  | L02_D_EAD_001 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 200 | 0 | 70 | F | 0 | 370 |  |  |  | 93
2025-05-21 | 984 |  | L02_D_EAD_002 | A | DONE | 18 | M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 60 | 0 | 380 | F | 0 | 580 |  |  |  | 93
2025-05-21 | 985 | bth | L02_D_EAD_003 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 70 | 30 | 130 | F | 0 | 280 |  |  |  | 93
2025-05-22 | 986 | bth | L02_D_EAD_004 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 50 | 20 | 130 | F | 0 | 240 |  |  |  | 93
2025-05-22 | 987 | bth | L02_D_EAD_005 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 40 | 30 | 180 | F | 0 | 310 |  |  |  | 93
2025-05-22 | 988 |  | L02_D_EAD_006 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 50 | 0 | 160 | F | 0 | 280 |  |  |  | 93
2025-05-22 | 989 | bth | L02_D_EAD_007 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 40 | 40 | 200 | F | 0 | 340 |  |  |  | 93
2025-05-22 | 990 | bth | L02_D_EAD_008 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 100 | 50 | 100 | F | 0 | 310 |  |  |  | 93
2025-05-21 | 991 | sp | L02_D_EAD_009 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-02-19 | 20 | 130 | 0 |  | 0 | 140 |  |  |  | 93
2025-05-20 | 1419 |  | 83307 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-05-20 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing G |  | 3
2025-05-21 | 1420 | w | 83344 | A | DONE | 2 | S | BI | WAUNAKEE MS 6230013 |  | 2025-05-23 | Z | 2025-05-20 | 20 | 0 | 0 |  | 0 | 20 |  | 1st E-Section grease duct |  | 3
2025-05-20 | 1692 |  | 83401 , 83405 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | CD's | 2025-05-21 | Z | 2025-05-09 | 80 | 0 | 0 |  | 0 | 110 |  | PRV-4,6,7 |  | 12
2025-05-20 | 1694 | sp | 83404 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | bird s. | 2025-05-21 | Z | 2025-05-09 | 20 | 40 | 0 |  | 0 | 60 |  | Kiln vent |  | 12
2025-05-20 | 2707 |  | 66200 | A | DONE | 2 | S |  | WSCC 6240006 | paint | 2025-05-23 | Z | 2025-05-20 | 20 | 0 | 0 |  | 20 | 20 |  | Grille boxes |  | 3
2025-05-21 | 2708 |  | 76101 | A | DONE | 2 | S |  | WSCC 6240006 | paint | 2025-05-23 | Z | 2025-05-20 | 30 | 0 | 0 |  | 30 | 50 |  | Misc |  | 3
[6 empty] | 1215 | [13 empty] | 42440 |  |  |  | 13490 | 31.79%
WEEK OF 5-27-2025
2025-05-28 | 227 |  | 74019 | A | DONE | 2 | S | neal | 7447 UNIVERSITY 4250018 |  | 2025-05-29 | Z | 2025-05-27 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2025-05-27 | 2253 | w | 69748 , 69736 | A | DONE | 11 | S-M | ss | BARTILLION 6240024 | angle rings | 2025-05-21 | Z | 2025-05-05 | 270 | 0 | 0 |  | 0 | 680 |  | Kitchen / Dishwasher |  | 16
2025-05-27 | 2260 |  | 69747 | A | DONE | 8 | S |  | BARTILLION 6240024 | 1" liner | 2025-06-10 | Z | 2025-05-12 | 130 | 0 | 60 | F | 130 | 280 |  | RET-Mech Over AHU |  | 29
2025-05-30 | 2261 |  | 83205 - 83208 | A | DONE | 54 | M |  | BARTILLION 6240024 | flex | 2025-05-30 | Z | 2025-05-12 | 900 | 0 | 450 | F | 0 | 1680 |  | Mech Room |  | 18
2025-05-27 | 2262 | sp | 83209 | A | DONE | 3 | S |  | BARTILLION 6240024 |  | 2025-06-10 | Z | 2025-05-12 | 0 | 70 | 0 |  | 0 | 90 |  | Spiral |  | 29
2025-05-31 | 2263 |  | 83210 - 83212 | A | DONE | 36 | M |  | BARTILLION 6240024 |  | 2025-05-30 | Z | 2025-05-12 | 770 | 0 | 130 | F | 0 | 1170 |  | EA , REF 1 , CC AHU |  | 18
2025-05-31 | 2275 |  | 83235 - 83237 | A | DONE | 7 | S-M |  | BARTILLION 6240024 |  | 2025-05-30 | Z | 2025-05-15 | 160 | 0 | 0 |  | 0 | 250 |  | AV to RC tie in |  | 15
2025-05-31 | 893 | sp | 73669 | A | DONE | 65 | M-L |  | DELLSHIRE 6240017 |  | 2025-06-02 | Z | 2025-05-02 | 90 | 1530 | 0 |  | 0 | 1470 |  | 3rd EA Riser |  | 31
2025-05-27 | 3502 | bth | 73711 | A | DONE | 5 | S |  | DELLSHIRE 6240017 |  | 2025-05-27 | Z | 2025-05-15 | 50 | 60 | 0 |  | 0 | 100 |  | 3rd fl SA 305 |  | 12
2025-05-27 | 3503 |  | 73712 - 73713 | A | DONE | 8 | S-M |  | DELLSHIRE 6240017 |  | 2025-05-27 | Z | 2025-05-15 | 180 | 0 | 20 | F | 0 | 210 |  | 3rd fl SA 305 |  | 12
2025-05-27 | 3504 | bth | 73714 - 73715 | A | DONE | 10 | S-M |  | DELLSHIRE 6240017 | flex | 2025-05-27 | Z | 2025-05-15 | 70 | 100 | 60 | F | 0 | 250 |  | 3rd fl EF-14 |  | 12
2025-05-31 | 3505 | sp | 73716 | A | DONE | 6 | S-M |  | DELLSHIRE 6240017 |  | 2025-06-02 | Z | 2025-05-15 | 40 | 110 | 0 |  | 0 | 140 |  | 2nd floor misc |  | 18
2025-05-29 | 1603 |  | 97709 | A | DONE | 2 | S | BI | DOC JDC 6240023 |  | 2025-06-06 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 30 |  | Caps |  | 8
2025-05-31 | 1605 |  | EMAIL | A | DONE | 42 | L |  | DOC JDC 6240023 |  | 2025-06-05 | Z | 2025-05-30 | 1030 | 0 | 0 |  | 0 | 3080 |  | Angles |  | 6
2025-05-29 | 229 |  | 73757 | A | DONE | 2 | S |  | EGENESIS 2250004 |  | 2025-05-29 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | Reducers |  | 0
2025-05-30 | 1010 |  | 56815 | A | DONE | 2 | S |  | EXACT TL-3 6240028 | VD | 2025-06-03 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | EA Damper |  | 5
2025-05-29 | 1712 |  | 95835 | A | DONE | 2 | S |  | MCDS 8250007 |  | 2025-06-02 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 60 |  | Plates |  | 4
2025-05-29 | 1525 |  | EA-L1D-01 | A | DONE | 11 | S-M | neal | MONROE HS 6240018 | CD's | 2025-05-28 | Z | 2025-03-25 | 220 | 0 | 50 | F | 0 | 310 |  |  |  | 64
2025-05-29 | 1526 |  | EA-L1D-02 | A | DONE | 12 | S-M | neal | MONROE HS 6240018 | CD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 230 | 0 | 50 | F | 150 | 410 |  |  |  | 64
2025-05-29 | 1527 | bth | EA-L1D-03 | A | DONE | 8 | S | pt.neal | MONROE HS 6240018 | bird s. , CD | 2025-05-28 | Z | 2025-03-25 | 90 | 100 | 0 |  | 0 | 210 |  |  |  | 64
2025-05-29 | 1528 | bth | EA-L1D-04 | A | DONE | 20 | M | pt.neal | MONROE HS 6240018 | 1" liner | 2025-05-28 | Z | 2025-03-25 | 170 | 160 | 160 | F | 250 | 620 |  |  |  | 64
2025-05-29 | 1529 |  | EA-L1D-05 | A | DONE | 2 | S |  | MONROE HS 6240018 | VD , CD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 50 | 0 | 0 |  | 20 | 80 |  |  |  | 64
2025-05-29 | 1530 |  | OA-L1D-01 | A | DONE | 7 | S-M | neal | MONROE HS 6240018 | flex , CD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 170 | 0 | 0 |  | 30 | 250 |  |  |  | 64
2025-05-29 | 1531 |  | OA-L1D-02 | A | DONE | 10 | S-M | neal | MONROE HS 6240018 | flex , CD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 190 | 0 | 40 | F | 20 | 330 |  |  |  | 64
2025-05-29 | 1532 |  | OA-L1D-03 | A | DONE | 6 | S |  | MONROE HS 6240018 | flex , CD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 120 | 0 | 30 | F | 30 | 220 |  |  |  | 64
2025-05-29 | 1533 |  | OA-L1D-04 | A | DONE | 5 | S |  | MONROE HS 6240018 | flex , CD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 110 | 0 | 0 |  | 20 | 150 |  |  |  | 64
2025-05-28 | 1534 |  | RA-L1D-01 | A | DONE | 40 | M-L | pt.neal | MONROE HS 6240018 | VD , CD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 670 | 0 | 310 | F | 790 | 2000 |  |  |  | 64
2025-05-29 | 1535 |  | RA-L1D-02 | A | DONE | 31 | M-L |  | MONROE HS 6240018 | VD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 530 | 0 | 230 | F | 560 | 1110 |  |  |  | 64
2025-05-29 | 1536 |  | RA-L1D-03 | A | DONE | 62 | L | neal | MONROE HS 6240018 | CD , 1" liner | 2025-05-28 | Z | 2025-03-25 | 1040 | 0 | 500 | F | 1320 | 3360 |  |  |  | 64
2025-05-29 | 1537 | bth | RA-L1D-04 | A | DONE | 4 | S |  | MONROE HS 6240018 | flex | 2025-05-28 | Z | 2025-03-25 | 50 | 30 | 0 |  | 30 | 100 |  |  |  | 64
2025-05-28 | 3807 | sp | 78789 | A | DONE | 7 | S-M |  | MONROE HS 6240018 |  | 2025-05-28 | Z | 2025-05-15 | 170 | 0 | 0 |  | 0 | 280 |  | Wall sleeves |  | 13
2025-05-28 | 226 |  | EMAIL | A | DONE | 2 | S |  | OAKWOOD VILLAGE 6210004 |  | 2025-05-28 | Z | 2025-05-22 | 20 | 0 | 0 |  | 0 | 20 |  | Pan |  | 6
2025-05-27 | 1759 |  | KE-L1-01 | A | DONE | 14 | S-M | alum | ONE 09 6240037 | flex | 2025-05-21 | Z | 2025-05-05 | 220 | 0 | 120 | F | 0 | 260 |  |  |  | 16
2025-05-30 | 1779 | w | 69432 , 69434 | A | DONE | 13 | M | BI | ONE 09 6240037 |  | 2025-06-03 | Z | 2025-05-12 | 320 | 0 | 0 |  | 0 | 900 |  | FH Grease duct |  | 22
2025-05-29 | 4215 |  | 88791 | A | DONE | 2 | S | neal | PECATONICA 6240005 |  | 2025-06-02 | Z | 2025-05-21 | 30 | 0 | 0 |  | 20 | 90 |  | Hat channel |  | 12
2025-05-28 | 4216 |  | 79684 | A | DONE | 2 | S | neal | PECATONICA 6240005 |  | 2025-05-27 | Z | 2025-05-21 | 20 | 20 | 0 |  | 0 | 20 |  | Ext. |  | 6
2025-05-30 | 4217 |  | 79687 | A | DONE | 2 | S |  | PECATONICA 6240005 | paint | 2025-06-02 | Z | 2025-05-29 | 20 | 0 | 0 |  | 20 | 30 |  | RA |  | 4
2025-05-27 | 1802 |  | L1A-TA 1 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | 1" liner | 2025-06-09 | Z | 2025-05-06 | 50 | 0 | 0 |  | 50 | 80 |  |  |  | 34
2025-05-27 | 1803 |  | L1A-TA 2 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | 1" liner | 2025-06-09 | Z | 2025-05-06 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 34
2025-05-29 | 1807 | bth | L1A-SAT V-1 | A | DONE | 30 | S |  | PEWAUKEE HS 6240030 | 2" liner | 2025-06-09 | Z | 2025-05-06 | 710 | 30 | 0 |  | 30 | 110 |  |  |  | 34
2025-05-28 | 1809 | sp | L1A-SAT V-3 | A | DONE | 24 | M | neal | PEWAUKEE HS 6240030 | VD's | 2025-06-02 | Z | 2025-05-06 | 160 | 440 | 0 |  | 0 | 710 |  |  |  | 27
2025-05-28 | 1810 | sp | L1A-SAT V-4 | A | DONE | 18 | S-M | neal | PEWAUKEE HS 6240030 | VD's | 2025-06-02 | Z | 2025-05-06 | 140 | 310 | 0 |  | 0 | 540 |  |  |  | 27
2025-05-27 | 1811 |  | L1A-SAT V-5 | A | DONE | 5 | S |  | PEWAUKEE HS 6240030 |  | 2025-06-09 | Z | 2025-05-06 | 40 | 20 | 50 | F | 80 | 150 |  |  |  | 34
2025-05-28 | 1813 | bth | L1A-SAT V-7 | A | DONE | 4 | S |  | PEWAUKEE HS 6240030 | 2" liner | 2025-06-09 | Z | 2025-05-06 | 30 | 20 | 40 | F | 40 | 100 |  |  |  | 34
2025-05-28 | 1814 | bth | L1A-SAT V-8 | A | DONE | 10 | S-M |  | PEWAUKEE HS 6240030 | 2" liner | 2025-06-09 | Z | 2025-05-06 | 50 | 160 | 40 | F | 50 | 280 |  |  |  | 34
2025-05-27 | 1815 | sp | L1A-SAT V-9 | A | DONE | 20 | M | neal | PEWAUKEE HS 6240030 | VD's | 2025-06-02 | Z | 2025-05-06 | 150 | 350 | 0 |  | 0 | 590 |  |  |  | 27
2025-05-28 | 1816 | bth | L1A-SAT V-10 | A | DONE | 27 | M | neal | PEWAUKEE HS 6240030 | VD's , 2" sp. , 2" liner | 2025-06-02 | Z | 2025-05-06 | 200 | 400 | 60 | F | 140 | 950 |  |  |  | 27
2025-05-27 | 1817 |  | L1A-RAMP 1 | A | DONE | 40 | M-L |  | PEWAUKEE HS 6240030 | VD , 1" liner | 2025-06-09 | Z | 2025-05-06 | 710 | 0 | 290 | F | 770 | 2010 |  |  |  | 34
2025-05-28 | 1828 |  | 74112 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-05-29 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | S/D |  | 0
2025-05-30 | 486 |  | L02_SC_SALP_001 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 80 | 20 | 30 | F | 0 | 160 |  |  |  | 16
2025-05-30 | 487 | sp | L02_SC_SALP_002 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 0 | 100 | 0 |  | 0 | 120 |  |  |  | 16
2025-05-29 | 488 | sp | L02_SC_SALP_003 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 20 | 80 | 0 |  | 0 | 120 |  |  |  | 16
2025-05-29 | 489 | sp | L02_SC_SALP_004 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 16
2025-05-29 | 490 | sp | L02_SC_SALP_005 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 16
2025-05-30 | 491 | bth | L02_SC_SALP_006 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 16
2025-05-31 | 492 | bth | L02_SC_SALP_007 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 16
2025-05-30 | 493 | bth | L02_SC_SALP_008 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | VD's | 2025-05-29 | Z | 2025-05-13 | 50 | 130 | 0 |  | 0 | 190 |  |  |  | 16
2025-05-30 | 494 | bth | L02_SC_SAMP_001 | A | DONE | 12 | S-M |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 200 | 30 | 50 | F | 0 | 390 |  |  |  | 16
2025-05-30 | 495 | sp | L02_SC_SAMP_002 | A | DONE | 13 | S-M |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 40 | 280 | 0 |  | 0 | 360 |  |  |  | 16
2025-05-30 | 496 | sp | L02_SC_SAMP_003 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 40 | 230 | 0 |  | 0 | 300 |  |  |  | 16
2025-05-30 | 497 | sp | L02_SC_SAMP_004 | A | DONE | 9 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 30 | 180 | 0 |  | 0 | 230 |  |  |  | 16
2025-05-30 | 498 | sp | L02_SC_RA_001 | A | DONE | 10 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 40 | 200 | 0 |  | 0 | 290 |  |  |  | 16
2025-05-30 | 499 | sp | L02_SC_RA_002 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-13 | 30 | 70 | 0 |  | 0 | 110 |  |  |  | 16
2025-05-29 | 1317 |  | 55130 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-05-29 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 60 |  | Louver angle |  | 0
2025-05-28 | 3035 | sp | 62748 | A | DONE | 8 | S-M |  | PROMEGA BTC 6230022 |  | 2025-05-28 | Z | 2025-05-21 | 30 | 160 | 0 |  | 0 | 200 |  | Misc |  | 7
2025-05-30 | 3036 |  | 62749 | A | DONE | 21 | S-M |  | PROMEGA BTC 6230022 |  | 2025-06-02 | Z | 2025-05-21 | 0 | 0 | 520 | F | 0 | 750 |  | RA |  | 12
2025-05-27 | 2846 |  | 68488 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-05-27 | Z | 2025-05-19 | 20 | 0 | 0 |  | 0 | 20 |  | SA 1st |  | 8
2025-05-28 | 2412 |  | 74152 | A | DONE | 2 | S |  | ST.BERNARD 6230023 | paint | 2025-05-28 | Z | 2025-05-15 | 20 | 0 | 0 |  | 20 | 30 |  | Confession Grille boxes |  | 13
2025-05-31 | 224 |  | 74017 | A | DONE | 2 | S |  | UPPERHOUSE 4250019 | 1" liner | 2025-06-02 | Z | 2025-05-22 | 50 | 0 | 0 |  | 40 | 50 |  | TA |  | 11
2025-05-30 | 225 | sp | 74018 | A | DONE | 6 | S-M |  | UPPERHOUSE 4250019 |  | 2025-06-02 | Z | 2025-05-22 | 50 | 90 | 0 |  | 0 | 130 |  | Misc |  | 11
2025-05-27 | 3759 | bth | 69145 | A | DONE | 2 | S-M |  | UW-AVRL 6240038 | 1" liner | 2025-05-28 | Z | 2025-05-21 | 30 | 20 | 0 |  | 20 | 60 |  | C/D Hallway |  | 7
2025-05-27 | 3720 | bth | L5-RAMP 2 | A | DONE | 17 | M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-05-27 | Z | 2025-05-13 | 250 | 20 | 140 | F | 40 | 650 |  |  |  | 14
2025-05-27 | 3721 | bth | L5-RAMP 3 | A | DONE | 17 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-27 | Z | 2025-05-13 | 220 | 20 | 170 | F | 60 | 690 |  |  |  | 14
2025-05-27 | 3722 | bth | L5-RAMP 4 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-27 | Z | 2025-05-13 | 120 | 20 | 120 | F | 50 | 360 |  |  |  | 14
2025-05-27 | 3723 | bth | L5-RAMP 5 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-27 | Z | 2025-05-13 | 70 | 80 | 40 | F | 50 | 230 |  |  |  | 14
2025-05-27 | 3724 | bth | L5-RAMP 6 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-27 | Z | 2025-05-13 | 180 | 20 | 140 | F | 70 | 460 |  |  |  | 14
2025-05-27 | 3725 | bth | L5-RAMP 7 | A | DONE | 17 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-27 | Z | 2025-05-13 | 210 | 50 | 150 | F | 90 | 520 |  |  |  | 14
2025-05-27 | 3726 | bth | L5-RAMP 8 | A | DONE | 16 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-27 | Z | 2025-05-13 | 220 | 20 | 160 | F | 60 | 540 |  |  |  | 14
2025-05-27 | 3727 |  | L5-RAMP 9 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-27 | Z | 2025-05-13 | 260 | 0 | 90 | F | 110 | 480 |  |  |  | 14
2025-05-27 | 3728 | bth | L5-RAMP 10 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-05-27 | Z | 2025-05-13 | 40 | 60 | 0 |  | 20 | 110 |  |  |  | 14
2025-05-27 | 3729 |  | 82964 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-05-27 | Z | 2025-05-15 | 50 | 0 | 0 |  | 0 | 70 |  | EAMP |  | 12
2025-05-27 | 3730 |  | 82965 | A | DONE | 2 | S | neal | UW-LEVY HALL 6230028 |  | 2025-05-27 | Z | 2025-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | SALP |  | 12
2025-05-30 | 3743 |  | LL-SAMP 6 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | partial , 1" liner | 2025-05-29 | Z | 2025-05-22 | 80 | 0 | 0 |  | 70 | 150 |  |  |  | 7
2025-05-30 | 3744 |  | 96958 | A | DONE | 2 | S |  | UW-LEVY HALL 8230028 |  | 2025-06-02 | Z | 2025-05-23 | 30 | 0 | 0 |  | 0 | 70 |  | Flat stock |  | 10
2025-05-31 | 3962 |  | 74536 - 74543 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-02 | Z | 2025-05-15 | 260 | 0 | 30 | F | 0 | 340 |  | Misc |  | 18
2025-05-31 | 3963 |  | 74544 - 74546 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-02 | Z | 2025-05-16 | 80 | 0 | 0 |  | 0 | 180 |  | 2nd AHU-3 |  | 17
2025-05-31 | 3964 |  | 74547 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-02 | Z | 2025-05-19 | 30 | 0 | 0 |  | 0 | 50 |  | AHU-1 RA C185 |  | 14
2025-05-31 | 3965 |  | 74548 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-02 | Z | 2025-05-20 | 30 | 0 | 0 |  | 0 | 50 |  | AHU-1 RA 1st |  | 13
2025-05-30 | 1858 | bth | 69540 | A | DONE | 33 | M-L |  | UWP-FH 6240021 | VD's | 2025-05-29 | Z | 2025-05-13 | 360 | 380 | 80 | F | 0 | 1190 |  |  |  | 16
2025-05-30 | 1859 |  | 69541 - 69543 | A | DONE | 32 | S-M |  | UWP-FH 6240021 |  | 2025-05-29 | Z | 2025-05-13 | 500 | 0 | 280 | F | 0 | 1060 |  |  |  | 16
2025-05-30 | 1860 |  | 69544 - 69545 | A | DONE | 19 | S-M |  | UWP-FH 6240021 |  | 2025-05-29 | Z | 2025-05-13 | 300 | 0 | 160 | F | 0 | 620 |  |  |  | 16
2025-05-30 | 1862 |  | 66627 | A | DONE | 6 | S |  | UWP-FH 6240021 |  | 2025-05-29 | Z | 2025-05-16 | 130 | 0 | 0 |  | 0 | 320 |  | Test caps |  | 13
2025-05-27 | 2856 |  | 84845 | A | DONE | 2 | S |  | UWRF 6230010 | paint , 1" liner | 2025-05-27 | Z | 2025-05-08 | 30 | 0 | 0 |  | 30 | 50 |  | 1st floor TA |  | 19
2025-05-27 | 2857 | sp | 84846 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-05-27 | Z | 2025-05-08 | 20 | 20 | 0 |  | 0 | 20 |  | 195B pcd drop |  | 19
2025-05-27 | 2858 |  | 84848 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-05-27 | Z | 2025-05-08 | 20 | 0 | 0 |  | 0 | 20 |  | 195B |  | 19
2025-05-27 | 2861 |  | 84855 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-05-27 | Z | 2025-05-15 | 40 | 0 | 0 |  | 0 | 60 |  | Rm 112 Hood tie in |  | 12
2025-05-31 | 3264 |  | 81287 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | flex | 2025-06-03 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 5
2025-05-27 | 4417 |  | 58828 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-05-28 | Z | 2025-05-27 | 20 | 0 | 0 |  | 0 | 50 |  | Caps |  | 1
2025-05-28 | 4415 |  | 70183 | A | DONE | 4 | S-M | alum | UWSP CHAMPIONS 6240008 |  | 2025-05-28 | Z | 2025-05-21 | 80 | 0 | 0 |  | 0 | 100 |  | Intake hood |  | 7
2025-05-28 | 3073 |  | 57639 | A | DONE | 2 | S |  | UW-VET MED 6210014 | VD's | 2025-05-29 | Z | 2025-05-21 | 40 | 0 | 0 |  | 0 | 60 |  | 1256 EA |  | 8
2025-05-28 | 3855 |  | 74766 | A | DONE | 12 | S-M | neal | UW-WITTE HALL 6250003 | AB damper , 1" liner | 2025-05-27 | Z | 2025-05-16 | 20 | 0 | 280 | F | 250 | 350 |  | EA |  | 11
2025-05-28 | 1421 |  | 83345 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-28 | Z | 2025-05-20 | 60 | 0 | 0 |  | 0 | 90 |  | 1st E-SOA |  | 8
2025-05-30 | 1422 | sp | 83346 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-05-30 | Z | 2025-05-20 | 30 | 0 | 0 |  | 0 | 40 |  | Misc |  | 10
2025-05-31 | 1473 |  | 79880 , 79882 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-05-30 | Z | 2025-05-23 | 20 | 0 | 0 |  | 0 | 30 |  | Replacements |  | 7
2025-05-29 | 2709 | bth | 76102 | A | DONE | 4 | S-M | pt.neal | WSCC 6240006 | paint | 2025-05-30 | Z | 2025-05-20 | 50 | 30 | 0 |  | 20 | 80 |  | TA / RA |  | 10
2025-05-28 | 2710 |  | 76103 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-05-30 | Z | 2025-05-23 | 40 | 0 | 0 |  | 0 | 60 |  | FAN-6 |  | 7
[6 empty] | 1130 | [13 empty] | 38940 |  |  |  | 7180 | 18.44%
WEEK OF 6-2-2025
2025-06-04 | 287a |  | 85232 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2025-06-06 | Z | 2025-06-04 | 20 | 0 | 0 |  | 0 | 20 |  | TA Sleeves |  | 2
2025-06-06 | 2266 | sp | 83216 - 83219 | A | DONE | 36 | M |  | BARTILLION 6240024 |  | 2025-06-10 | Z | 2025-05-13 | 90 | 800 | 0 |  | 0 | 880 |  | EA |  | 28
2025-06-06 | 2286 | w | 75153 | A | DONE | 2 | S | BI | BARTILLION 6240024 |  | 2025-06-10 | Z | 2025-05-27 | 30 | 0 | 0 |  | 0 | 80 |  | Grease duct |  | 14
2025-06-03 | 1137 |  | 56695 | A | DONE | 2 | S | ss | CHENERY BROS 1848 8240009 |  | 2025-06-06 | Z | 2025-05-23 | 20 | 0 | 0 |  | 0 | 20 |  | Plates |  | 14
2025-06-02 | 3507 | bth | 73720 - 73722 | A | DONE | 19 | S-M |  | DELLSHIRE 6240017 |  | 2025-06-02 | Z | 2025-05-15 | 260 | 90 | 120 | F | 30 | 550 |  | 2nd floor misc |  | 18
2025-06-03 | 3508 |  | 73723 | A | DONE | 4 | S |  | DELLSHIRE 6240017 | VD's | 2025-06-02 | Z | 2025-05-15 | 50 | 0 | 40 | F | 20 | 100 |  | House keep 204 LP |  | 18
2025-06-06 | 1606 |  | EMAIL | A | DONE | 18 | S-M |  | DOC-JCF 6240023 |  | 2025-06-06 | Z | 2025-06-03 | 440 | 0 | 0 |  | 0 | 1130 |  | Angles |  | 3
2025-06-02 | 1011 | w | 56816 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2025-06-03 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | FCU N100 |  | 5
2025-06-03 | 2554 |  | 82589 | A | DONE | 6 | S-M |  | LABCORP 6240016 |  | 2025-06-04 | Z | 2025-05-13 | 130 | 0 | 0 |  | 0 | 190 |  | 1st Floor MRI |  | 22
2025-06-03 | 2555 | sp | 82590 | A | DONE | 5 | S |  | LABCORP 6240016 |  | 2025-06-04 | Z | 2025-05-13 | 20 | 90 | 0 |  | 0 | 100 |  | 1st Floor MRI |  | 22
2025-06-03 | 2556 |  | 82591 - 82592 | A | DONE | 8 | S-M |  | LABCORP 6240016 |  | 2025-06-04 | Z | 2025-05-13 | 160 | 0 | 20 | F | 0 | 210 |  | 1st Floor MRI |  | 22
2025-06-03 | 2557 | bth | 82593 - 82595 | A | DONE | 9 | S-M |  | LABCORP 6240016 | bird s. | 2025-06-04 | Z | 2025-05-13 | 130 | 90 | 0 |  | 0 | 240 |  | 1st Floor MRI |  | 22
2025-06-04 | 1538 |  | SALP-L1D-01 | A | DONE | 66 | L |  | MONROE HS 6240018 | 2" liner | 2025-06-04 | Z | 2025-03-25 | 680 | 0 | 960 | F | 750 | 2860 |  |  |  | 71
2025-06-03 | 1539 |  | SALP-L1D-02 | A | DONE | 45 | M-L |  | MONROE HS 6240018 | VD , CD , 2" liner | 2025-06-04 | Z | 2025-03-25 | 610 | 0 | 510 | F | 370 | 1480 |  |  |  | 71
2025-06-04 | 1540 | bth | SALP-L1D-03 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | flex , 2" liner | 2025-06-04 | Z | 2025-03-25 | 90 | 100 | 90 | F | 130 | 350 |  |  |  | 71
2025-06-04 | 1541 | bth | SALP-L1D-04 | A | DONE | 17 | M |  | MONROE HS 6240018 | flex , 2" liner | 2025-06-04 | Z | 2025-03-25 | 270 | 20 | 130 | F | 330 | 650 |  |  |  | 71
2025-06-04 | 1542 | bth | SALP-L1D-05 | A | DONE | 13 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-04 | Z | 2025-03-25 | 150 | 20 | 150 | F | 240 | 480 |  |  |  | 71
2025-06-04 | 1543 | bth | SALP-L1D-06 | A | DONE | 7 | S |  | MONROE HS 6240018 |  | 2025-06-04 | Z | 2025-03-25 | 30 | 140 | 0 |  | 0 | 260 |  |  |  | 71
2025-06-04 | 1544 |  | SALP-L1D-07 | A | DONE | 23 | M |  | MONROE HS 6240018 | VD | 2025-06-04 | Z | 2025-03-25 | 440 | 0 | 120 | F | 0 | 830 |  |  |  | 71
2025-06-05 | 1545 |  | SALP-L1D-08 | A | DONE | 18 | M |  | MONROE HS 6240018 |  | 2025-06-04 | Z | 2025-03-25 | 320 | 0 | 120 | F | 0 | 510 |  |  |  | 71
2025-06-04 | 1546 |  | SALP-L1D-09 | A | DONE | 32 | M-L |  | MONROE HS 6240018 | VD , 2" liner | 2025-06-04 | Z | 2025-03-25 | 520 | 0 | 260 | F | 250 | 1500 |  |  |  | 71
2025-06-05 | 1547 |  | SALP-L1D-10 | A | DONE | 53 | L |  | MONROE HS 6240018 | 2" liner | 2025-06-04 | Z | 2025-03-25 | 670 | 0 | 640 | F | 330 | 2370 |  |  |  | 71
2025-06-04 | 1548 | sp | SALP-L1D-11 | A | DONE | 18 | M | neal | MONROE HS 6240018 | flex , VD | 2025-06-04 | Z | 2025-03-25 | 130 | 300 | 0 |  | 0 | 540 |  |  |  | 71
2025-06-04 | 1549 | sp | SALP-L1D-12 | A | DONE | 11 | S-M | neal | MONROE HS 6240018 | flex , VD | 2025-06-04 | Z | 2025-03-25 | 90 | 180 | 0 |  | 0 | 340 |  |  |  | 71
2025-06-05 | 1550 | bth | SALP-L1D-13 | A | DONE | 17 | S-M |  | MONROE HS 6240018 | flex , VD , 2" liner | 2025-06-04 | Z | 2025-03-25 | 290 | 50 | 70 | F | 100 | 490 |  |  |  | 71
2025-06-05 | 1551 |  | TA-L1D-14 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-06-04 | Z | 2025-03-25 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 71
2025-06-05 | 3822 |  | RA-LL-03 | A | DONE | 36 | S-M |  | MONROE HS 6240018 | VD , partial , 1" liner | 2025-06-04 | Z | 2025-05-28 | 380 | 0 | 500 | F | 400 | 980 |  |  |  | 7
2025-06-03 | 3826 |  | 85313 | A | DONE | 2 | S-M |  | MONROE HS 6240018 |  | 2025-06-04 | Z | 2025-05-29 | 40 | 0 | 0 |  | 0 | 70 |  | 1st B |  | 6
2025-06-03 | 228 |  | 66629 | A | DONE | 2 | S |  | MSN 2250019 |  | 2025-06-05 | Z | 2025-05-27 | 20 | 0 | 0 |  | 0 | 40 |  | DR-4 Row 3 Cab 11 |  | 9
2025-06-07 | 1780 | w | 69437 | A | DONE | 4 | S-M | BI | ONE 09 6240037 |  | 2025-06-11 | Z | 2025-05-22 | 80 | 0 | 0 |  | 0 | 230 |  | CH-Grease duct outs |  | 20
2025-06-07 | 1804 | bth | L1A-SAMP 1 | A | DONE | 26 | M-L |  | PEWAUKEE HS 6240030 | oval , accu. , 2" liner | 2025-09-06 | Z | 2025-05-06 | 360 | 290 | 0 |  | 220 | 1880 |  |  |  | 123
2025-06-03 | 1805 | sp | L1A-SAMP 2 | A | DONE | 23 | M |  | PEWAUKEE HS 6240030 | oval , accuflange | 2025-06-02 | Z | 2025-05-06 | 180 | 380 | 0 |  | 0 | 1320 |  |  |  | 27
2025-06-02 | 1806 | bth | L1A-SAMP 3 | A | DONE | 28 | S | neal | PEWAUKEE HS 6240030 | oval , accuflange | 2025-06-02 | Z | 2025-05-06 | 320 | 360 | 0 |  | 0 | 1620 |  |  |  | 27
2025-06-07 | 1808 | bth | L1A-SAT V-2 | A | DONE | 3 | S |  | PEWAUKEE HS 6240030 | 2" liner | 2025-09-06 | Z | 2025-05-06 | 40 | 20 | 0 |  | 30 | 60 |  |  |  | 123
2025-06-05 | 1812 |  | L1A-SAT V-6 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-09-06 | Z | 2025-05-06 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 123
2025-06-05 | 1818 |  | L1A-RAMP 2 | A | DONE | 24 | M |  | PEWAUKEE HS 6240030 | 1" liner | 2025-09-06 | Z | 2025-05-06 | 270 | 0 | 310 | F | 520 | 950 |  |  |  | 123
2025-06-05 | 1819 |  | L1A-RAMP 3 | A | DONE | 17 | M | neal | PEWAUKEE HS 6240030 | 1" liner | 2025-09-06 | Z | 2025-05-06 | 360 | 0 | 60 | F | 300 | 760 |  |  |  | 123
2025-06-07 | 1820 |  | L1A-RAMP 4 | A | DONE | 56 | L | neal | PEWAUKEE HS 6240030 | bird s. , VD , 1" liner | 2025-09-06 | Z | 2025-05-06 | 680 | 0 | 700 | F | 1230 | 2660 |  |  |  | 123
2025-06-05 | 1822 | bth | L1A-EA 1 | A | DONE | 10 | S |  | PEWAUKEE HS 6240030 | 1" liner | 2025-09-06 | Z | 2025-05-06 | 130 | 100 | 0 |  | 70 | 240 |  |  |  | 123
2025-06-07 | 1826 |  | 74153 - 74154 | A | DONE | 8 | S-M |  | PEWAUKEE HS 6240030 | 1" liner , 2" liner | 2025-09-06 | Z | 2025-05-27 | 180 | 0 | 0 |  | 180 | 470 |  | AHU-1 |  | 102
2025-06-07 | 1827 | sp/w | 74155 | A | DONE | 2 | S-M |  | PEWAUKEE HS 6240030 |  | 2025-09-06 | Z | 2025-05-27 | 20 | 30 | 0 |  | 0 | 60 |  | Dryer vent |  | 102
2025-06-03 | 3037 |  | 62750 | A | DONE | 3 | S |  | PROMEGA BTC 6230022 |  | 2025-06-04 | Z | 2025-05-30 | 70 | 0 | 0 |  | 0 | 150 |  | SA |  | 5
2025-06-05 | 3038 |  | 81835 - 81836 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2025-06-06 | Z | 2025-05-30 | 80 | 0 | 0 |  | 0 | 130 |  | Misc |  | 7
2025-06-05 | 3663 |  | 68489 | A | DONE | 2 | S |  | SPH SURGERY 6240039 | DM frames | 2025-06-06 | Z | 2025-05-22 | 40 | 0 | 0 |  | 0 | 50 |  | DM frames |  | 15
2025-06-06 | 3666 | sp | 68901 | A | DONE | 3 | S |  | SPH SURGERY 6240039 |  | 2025-06-06 | Z | 2025-06-03 | 20 | 40 | 0 |  | 0 | 60 |  | Phase 1C |  | 3
2025-06-05 | 3667 |  | 68902 | A | DONE | 2 | S | ss | SPH SURGERY 6240039 |  | 2025-06-06 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 20 |  | Patch |  | 3
2025-06-03 | 4065 |  | 73956 | A | DONE | 16 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-06-04 | Z | 2025-05-19 | 390 | 0 | 0 |  | 420 | 510 |  | SI-17 |  | 16
2025-06-03 | 4066 |  | 73957 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-06-04 | Z | 2025-05-22 | 20 | 0 | 0 |  | 0 | 30 |  | 214 |  | 13
2025-06-04 | 4067 |  | 73958 - 73961 | A | DONE | 8 | S-M | neal | STOUGHTON TRAILER 6240015 | paint , 1" liner | 2025-06-04 | Z | 2025-05-22 | 180 | 0 | 0 |  | 150 | 330 |  | 217 , 271 , 2nd , 2B E. |  | 13
2025-06-02 | 4068 |  | 73962 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | paint | 2025-06-04 | Z | 2025-05-23 | 20 | 0 | 0 |  | 20 | 20 |  | 250 L-Channel |  | 12
2025-06-04 | 4069 |  | 73963 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-06-06 | Z | 2025-05-27 | 20 | 0 | 0 |  | 0 | 20 |  | Kitchen |  | 10
2025-06-06 | 230 |  | 74020 | A | DONE | 2 | S |  | UPPERHOUSE 4250004 |  | 2025-06-10 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 40 |  | MUA Temp caps |  | 7
2025-06-06 | 232 |  | 74021 | A | DONE | 2 | S |  | UPPERHOUSE 4250004 |  | 2025-06-09 | Z | 2025-06-06 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 3
2025-06-04 | 640 |  | 66718 | A | DONE | 2 | S |  | UW-BIO CHEM 6240036 |  | 2025-06-05 | Z | 2025-06-04 | 30 | 0 | 0 |  | 0 | 40 |  | Misc |  | 1
2025-06-02 | 784 |  | L3-TA 7 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-06-03 | Z | 2025-04-07 | 90 | 0 | 0 |  | 70 | 120 |  |  |  | 57 | 2025-05-27 | 2025-06-09
2025-06-02 | 785 |  | L3-SAT 3-3-12 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-07 | 90 | 0 | 60 | F | 40 | 180 |  |  |  | 57 | 2025-05-27 | 2025-06-09
2025-06-02 | 786 | bth | L3-SAT 3-3-13 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-07 | 40 | 30 | 60 | F | 30 | 140 |  |  |  | 57 | 2025-05-27 | 2025-06-09
2025-06-02 | 787 | bth | L3-SAT 3-3-14 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-07 | 40 | 40 | 30 | F | 40 | 100 |  |  |  | 57 | 2025-05-27 | 2025-06-09
2025-06-02 | 788 | bth | L3-SAT 3-3-15 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-07 | 20 | 20 | 30 | F | 30 | 70 |  |  |  | 57 | 2025-05-27 | 2025-06-09
2025-06-02 | 789 | bth | L3-SAT 3-3-16 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-07 | 70 | 20 | 20 | F | 20 | 130 |  |  |  | 57 | 2025-05-27 | 2025-06-09
2025-06-02 | 790 | bth | L3-SAT 3-3-17 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-07 | 30 | 0 | 30 | F | 40 | 70 |  |  |  | 57 | 2025-05-27 | 2025-06-09
2025-06-02 | 791 |  | L3-SAT 3-3-18 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-07 | 90 | 0 | 20 | F | 20 | 120 |  |  |  | 57 | 2025-05-27 | 2025-06-09
2025-06-02 | 4010 | bth | L3-SAT 3-3-1 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 70 | 30 | 0 |  | 30 | 120 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-03 | 4011 | bth | L3-SAT 3-3-2 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 50 | 20 | 40 | F | 30 | 110 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4012 | bth | L3-SAT 3-3-3 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 60 | 20 | 0 |  | 40 | 90 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4013 | bth | L3-SAT 3-3-4 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 70 | 20 | 0 |  | 40 | 80 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4014 | bth | L3-SAT 3-3-5 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 60 | 30 | 0 |  | 40 | 90 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4015 | bth | L3-SAT 3-3-6 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 20 | 30 | 30 | F | 30 | 70 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4016 | bth | L3-SAT 3-3-7 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 30 | 30 | 0 |  | 20 | 60 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4017 | bth | L3-SAT 3-3-8 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 80 | 30 | 60 | F | 40 | 190 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4018 | bth | L3-SAT 3-3-9 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 40 | 50 | 0 |  | 30 | 100 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4019 | bth | L3-SAT 3-3-10 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 110 | 20 | 20 | F | 40 | 170 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4020 | bth | L3-SAT 3-3-11 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 110 | 30 | 0 |  | 30 | 190 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-03 | 4021 |  | L3-SAT 3-3-34.1 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 180 | 0 | 190 | F | 20 | 570 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-03 | 4022 |  | L3-SAT 3-3-34.2 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-06-03 | Z | 2025-04-08 | 80 | 0 | 110 | F | 0 | 260 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4023 | bth | L3-SAT 3-3-35 | A | DONE | 20 | M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 170 | 80 | 240 | F | 50 | 570 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4024 | bth | L3-SAT 3-3-36 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 50 | 30 | 0 |  | 20 | 100 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-03 | 4025 | bth | L3-SAT 3-3-38 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 40 | 30 | 0 |  | 20 | 70 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4026 |  | L3-SAT 3-3-39 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-06-03 | Z | 2025-04-08 | 20 | 0 | 30 | F | 30 | 60 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4027 | bth | L3-SAT 3-3-40 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 70 | 20 | 40 | F | 30 | 130 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4028 | bth | L3-SAT 3-3-41 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 30 | 50 | 30 | F | 40 | 120 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-02 | 4029 | bth | L3-SAT 3-3-42 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 60 | 20 | 70 | F | 30 | 190 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-03 | 4030 |  | L3-SAT 3-3-43 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 60 | 0 | 0 |  | 30 | 90 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-03 | 4031 | bth | L3-SAT 3-3-44 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-06-03 | Z | 2025-04-08 | 20 | 20 | 30 | F | 30 | 60 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-03 | 4043 |  | L3-FCU 4 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 |  | 2025-06-03 | Z | 2025-04-08 | 110 | 0 | 0 |  | 0 | 150 |  |  |  | 56 | 2025-05-27 | 2025-06-09
2025-06-06 | 2863 |  | 84857 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-06-10 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | 112 FEMP tie in |  | 12
2025-06-04 | 4416 | w | 70185 | A | DONE | 4 | S-M | ss. Perf | UWSP CHAMPIONS 6240008 | ss angle | 2025-06-03 | Z | 2025-05-21 | 100 | 0 | 0 |  | 0 | 100 |  | Intake hood baffle |  | 13
2025-06-05 | 2046 | bth | 57625 - 57627 | A | DONE | 8 | S-M |  | UW-VET MED 6210014 |  | 2025-06-05 | Z | 2025-05-12 | 90 | 80 | 0 |  | 0 | 180 |  | 7B SA |  | 24
2025-06-04 | 2047 | sp | 57628 - 57630 | A | DONE | 9 | S-M |  | UW-VET MED 6210014 |  | 2025-06-05 | Z | 2025-05-12 | 20 | 190 | 0 |  | 0 | 190 |  | 7B SA |  | 24
2025-06-05 | 2048 |  | 57631 - 57632 | A | DONE | 9 | S-M |  | UW-VET MED 6210014 | VD | 2025-06-05 | Z | 2025-05-12 | 90 | 0 | 120 | F | 0 | 260 |  | 7B SA |  | 24
2025-06-04 | 2049 | sp | 57633 - 57634 | A | DONE | 11 | S-M |  | UW-VET MED 6210014 |  | 2025-06-05 | Z | 2025-05-12 | 80 | 190 | 0 |  | 0 | 260 |  | 7B EA - HP |  | 24
2025-06-05 | 3070 |  | 57635 - 57636 | A | DONE | 10 | S-M |  | UW-VET MED 6210014 | VD | 2025-06-05 | Z | 2025-05-12 | 50 | 0 | 200 | F | 0 | 290 |  | 7B EA |  | 24
2025-06-04 | 3074 | sp | 57640 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-06-05 | Z | 2025-05-27 | 20 | 20 | 0 |  | 0 | 30 |  | Outs |  | 9
2025-06-04 | 3075 | sp | 57641 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2025-06-05 | Z | 2025-05-29 | 20 | 20 | 0 |  | 0 | 40 |  | CB 343 |  | 7
2025-06-05 | 3550 |  | PRE-FAB HANGERS | A | DONE | 2 | S | neal | UWW METALS LAB 6250001 |  | 2025-06-06 | Z | 2025-05-22 | 40 | 0 | 0 |  | 0 | 90 |  | Tear drop hangers |  | 15
2025-06-05 | 3551 | sp | 84970 | A | DONE | 13 | S-M | perf | UWW METALS LAB 6250001 |  | 2025-06-06 | Z | 2025-05-23 | 30 | 290 | 0 |  | 0 | 220 |  | Perforated duct |  | 14
2025-06-05 | 3553 | sp | 84977 , 84980 | A | DONE | 20 | S-M | neal | UWW METALS LAB 6250001 |  | 2025-06-06 | Z | 2025-05-23 | 120 | 360 | 0 |  | 0 | 480 |  | RHC 2054A , 1st EA |  | 14
2025-06-05 | 3556 | sp | 84984 | A | DONE | 7 | S-M | neal | UWW METALS LAB 6250001 |  | 2025-06-06 | Z | 2025-05-23 | 70 | 100 | 0 |  | 0 | 200 |  | EF-14 |  | 14
2025-06-04 | 3851a |  | 74762 | A | DONE | 8 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-06-04 | Z | 2025-06-02 | 160 | 0 | 30 | F | 140 | 230 |  | Misc |  | 2
2025-06-05 | 3855a |  | 74766 | A | DONE | 7 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner , AB damper | 2025-06-04 | Z | 2025-05-30 | 160 | 0 | 0 |  | 110 | 240 |  | Damper piece |  | 5
2025-06-05 | 992 | bth | L02_D_SALP_001 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 107
2025-06-05 | 993 | sp | L02_D_SALP_002 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-06 | Z | 2025-02-19 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 107
2025-06-05 | 994 | sp | L02_D_SALP_003 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-06 | Z | 2025-02-19 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 107
2025-06-06 | 1155 | sp | L02_D_SALP_014 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-06 | Z | 2025-02-19 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 107
2025-06-05 | 1163 | bth | L02_D_RAD_003 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 107
2025-06-04 | 1470 |  | 79878 | A | DONE | 5 | S | neal | WAUNAKEE MS 6230013 |  | 2025-06-06 | Z | 2025-05-21 | 120 | 0 | 0 |  | 0 | 140 |  | Flashing |  | 16
2025-06-04 | 1471 |  | 83347 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-06 | Z | 2025-05-21 | 120 | 0 | 0 |  | 0 | 120 |  | Flashing |  | 16
2025-06-04 | 1474 |  | 83349 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-06 | Z | 2025-05-20 | 170 | 0 | 0 |  | 0 | 250 |  | Temp caps |  | 17
2025-06-05 | 2711 |  | 76104 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-06-06 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 60 |  | FAN-6 |  | 3
[6 empty] | 1056 | [13 empty] | 37300 |  |  |  | 3950 | 10.59%
WEEK OF 6-9-2025
2025-06-11 | 2264 |  | 83213 | A | DONE | 26 | M |  | BARTILLION 6240024 |  | 2025-06-10 | Z | 2025-05-13 | 130 | 0 | 500 | F | 0 | 840 |  | B-Section RA , A Section |  | 28
2025-06-11 | 2265 |  | 83214 - 83215 | A | DONE | 54 | M |  | BARTILLION 6240024 | 1" liner | 2025-06-10 | Z | 2025-05-13 | 390 | 0 | 960 | F | 1120 | 1970 |  | SA Main A,B |  | 28
2025-06-11 | 2267 |  | 83220 - 83222 | A | DONE | 29 | S-M |  | BARTILLION 6240024 |  | 2025-06-10 | Z | 2025-05-13 | 300 | 0 | 410 | F | 0 | 830 |  | 1st EA |  | 28
2025-06-11 | 2268 |  | 83223 | A | DONE | 6 | S |  | BARTILLION 6240024 | s.mates , 1" liner | 2025-06-10 | Z | 2025-05-13 | 90 | 0 | 40 | F | 90 | 140 |  | SA B-Section 1st |  | 28
2025-06-11 | 2271 |  | 83230 | A | DONE | 6 | S-M |  | BARTILLION 6240024 | s.mates , 1" liner | 2025-06-10 | Z | 2025-05-13 | 70 | 0 | 70 | F | 110 | 160 |  | Dorm 6 SA |  | 28
2025-06-11 | 2272 |  | 83231 | A | DONE | 4 | S |  | BARTILLION 6240024 |  | 2025-06-10 | Z | 2025-05-13 | 40 | 0 | 50 | F | 0 | 90 |  | MP run outs offices 1st |  | 28
2025-06-09 | 2273 | sp | 83232 , 69750 | A | DONE | 9 | S |  | BARTILLION 6240024 |  | 2025-06-10 | Z | 2025-05-13 | 20 | 190 | 0 |  | 0 | 190 |  | MP SA run outs |  | 28
2025-06-10 | 882 |  | 73664 | A | DONE | 5 | S-M |  | DELLSHIRE 6240017 | paint , 1" liner | 2025-06-09 | Z | 2025-04-21 | 110 | 0 | 0 |  | 100 | 180 |  | VTAC Plenum/slider V.2 |  | 49
2025-06-10 | 1607 |  | 97709 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-06-11 | Z | 2025-06-10 | 20 | 0 | 0 |  | 0 | 30 |  | Plate |  | 1
2025-06-12 | 1608 |  | EMAIL | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-06-16 | Z | 2025-06-10 | 440 | 0 | 0 |  | 0 | 1360 |  | Angles |  | 6
2025-06-11 | 1706 |  | 74202 - 74204 | A | DONE | 24 | M |  | MCDS 6250005 | bird s. | 2025-06-10 | Z | 2025-05-27 | 210 | 0 | 390 | F | 0 | 820 |  | RA Riser |  | 14
2025-06-11 | 1707 | bth | 74205 - 74207 | A | DONE | 22 | M |  | MCDS 6250005 |  | 2025-06-10 | Z | 2025-05-27 | 110 | 230 | 190 | F | 0 | 640 |  | VAV 1,2,3 |  | 14
2025-06-11 | 1708 | sp | 74208 - 74209 | A | DONE | 10 | S-M |  | MCDS 6250005 |  | 2025-06-10 | Z | 2025-05-27 | 70 | 180 | 0 |  | 0 | 240 |  | VAV 4,5 |  | 14
2025-06-11 | 1709 |  | 74210 | A | DONE | 9 | S-M |  | MCDS 6250005 |  | 2025-06-10 | Z | 2025-05-27 | 20 | 0 | 190 | F | 0 | 240 |  | VAV 4,5 |  | 14
2025-06-11 | 1710 | bth | 74211 - 74215 | A | DONE | 16 | S-M |  | MCDS 6250005 |  | 2025-06-10 | Z | 2025-05-27 | 180 | 190 | 30 | F | 0 | 420 |  | VAV 6,7 |  | 14
2025-06-11 | 1711 |  | 74217 - 74218 | A | DONE | 4 | S-M |  | MCDS 6250005 | 1" liner | 2025-06-17 | Z | 2025-05-27 | 100 | 0 | 0 |  | 90 | 310 |  | AHU SA / RA |  | 21
2025-06-11 | 1715 |  | 74261 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-06-10 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 20 |  | Shaft |  | 7
2025-06-13 | 1563 | bth | SALP-L2A-01 | A | DONE | 15 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-10 | Z | 2025-04-10 | 190 | 40 | 140 | F | 230 | 460 |  |  |  | 61
2025-06-13 | 1564 | bth | SALP-L2A-02 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-10 | Z | 2025-04-10 | 100 | 40 | 100 | F | 150 | 310 |  |  |  | 61
2025-06-13 | 1565 | bth | SALP-L2A-03 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-10 | Z | 2025-04-10 | 90 | 40 | 130 | F | 170 | 340 |  |  |  | 61
2025-06-13 | 1566 | bth | SALP-L2A-04 | A | DONE | 22 | M |  | MONROE HS 6240018 | 2" liner | 2025-06-10 | Z | 2025-04-10 | 210 | 70 | 260 | F | 350 | 690 |  |  |  | 61
2025-06-13 | 1567 | bth | SALP-L2A-05 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-10 | Z | 2025-04-10 | 160 | 50 | 70 | F | 150 | 340 |  |  |  | 61
2025-06-13 | 1568 | bth | SALP-L2A-06 | A | DONE | 20 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-10 | Z | 2025-04-10 | 200 | 40 | 250 | F | 290 | 680 |  |  |  | 61
2025-06-13 | 1577 | sp | SAMP-L2A-01 | A | DONE | 18 | M |  | MONROE HS 6240018 | accuflange , oval | 2025-06-10 | Z | 2025-04-10 | 80 | 360 | 0 |  | 0 | 750 |  |  |  | 61
2025-06-13 | 1578 | bth | SAMP-L2A-02 | A | DONE | 16 | M |  | MONROE HS 6240018 | accuflange , oval | 2025-06-10 | Z | 2025-04-10 | 60 | 340 | 0 |  | 0 | 800 |  |  |  | 61
2025-06-13 | 1579 | bth | SAMP-L2A-03 | A | DONE | 22 | M |  | MONROE HS 6240018 | accuflange , oval | 2025-06-10 | Z | 2025-04-10 | 140 | 390 | 0 |  | 0 | 1240 |  |  |  | 61
2025-06-13 | 1580 | sp | SAMP-L2A-04 | A | DONE | 21 | M |  | MONROE HS 6240018 | accuflange , oval | 2025-06-10 | Z | 2025-04-10 | 60 | 460 | 0 |  | 0 | 910 |  |  |  | 61
2025-06-13 | 1581 | bth | SAMP-L2A-05 | A | DONE | 33 | M-L |  | MONROE HS 6240018 | accuflange , 2" liner | 2025-06-10 | Z | 2025-04-10 | 700 | 120 | 0 |  | 430 | 1610 |  |  |  | 61
2025-06-13 | 1582 | bth | SAMP-L2A-06 | A | DONE | 22 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-10 | Z | 2025-04-10 | 300 | 20 | 210 | F | 200 | 900 |  |  |  | 61
2025-06-12 | 1583 | bth | SAMP-L2A-07 | A | DONE | 16 | S-M |  | MONROE HS 6240018 |  | 2025-06-10 | Z | 2025-04-10 | 140 | 20 | 240 | F | 0 | 550 |  |  |  | 61
2025-06-13 | 1584 | bth | SAMP-L2A-08 | A | DONE | 10 | S-M |  | MONROE HS 6240018 |  | 2025-06-10 | Z | 2025-04-10 | 30 | 190 | 30 | F | 0 | 300 |  |  |  | 61
2025-06-13 | 1585 | sp | SAMP-L2A-09 | A | DONE | 9 | S |  | MONROE HS 6240018 |  | 2025-06-10 | Z | 2025-04-10 | 60 | 150 | 0 |  | 0 | 250 |  |  |  | 61
2025-06-13 | 3827 |  | TA-L1B-02 | A | DONE | 5 | S |  | MONROE HS 6240018 | 1" liner | 2025-06-10 | Z | 2025-05-29 | 120 | 0 | 0 |  | 120 | 160 |  |  |  | 12 | 2025-06-12
2025-06-13 | 3828 |  | TA-L1B-03 | A | DONE | 5 | S |  | MONROE HS 6240018 | 1" liner | 2025-06-10 | Z | 2025-05-29 | 120 | 0 | 0 |  | 110 | 160 |  |  |  | 12 | 2025-06-12
2025-06-12 | 1781 |  | FH-SALP-L1-16 | A | DONE | 49 | M-L |  | ONE 09 6240037 |  | 2025-06-11 | Z | 2025-05-27 | 400 | 80 | 730 | F | 0 | 1420 |  |  |  | 15
2025-06-12 | 1782 |  | FH-SALP-L1-17 | A | DONE | 25 | M |  | ONE 09 6240037 | VD's | 2025-06-11 | Z | 2025-05-27 | 370 | 0 | 240 | F | 0 | 710 |  |  |  | 15
2025-06-12 | 1832 |  | call in | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-06-12 | Z | 2025-06-12 | 20 | 0 | 0 |  | 0 | 60 |  | oval coupling |  | 0
2025-06-09 | 1318 |  | MAU_12_MA_001 | A | DONE | 12 | M |  | PROJECT DOVE 6240041 |  | 2025-06-05 | Z | 2025-05-29 | 80 | 0 | 200 | F | 0 | 710 |  |  |  | 7
2025-06-09 | 1319 |  | MAU_12_RAMP_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 |  | 2025-06-05 | Z | 2025-05-29 | 200 | 0 | 0 | F | 0 | 480 |  |  |  | 7
2025-06-09 | 1320 |  | MAU_13_MA_001 | A | DONE | 12 | M |  | PROJECT DOVE 6240041 |  | 2025-06-05 | Z | 2025-05-29 | 280 | 0 | 0 |  | 0 | 680 |  |  |  | 7
2025-06-09 | 1321 |  | MAU_13_RAMP_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 |  | 2025-06-05 | Z | 2025-05-29 | 190 | 0 | 0 |  | 0 | 470 |  |  |  | 7
2025-06-09 | 1326 |  | MAU_11_MA_001 | A | DONE | 12 | M |  | PROJECT DOVE 6240041 |  | 2025-06-05 | Z | 2025-05-29 | 80 | 0 | 200 | F | 0 | 700 |  |  |  | 7
2025-06-09 | 1327 |  | MAU_11_RAMP_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 |  | 2025-06-05 | Z | 2025-05-29 | 180 | 0 | 0 |  | 0 | 430 |  |  |  | 7
2025-06-10 | 1347 |  | 55135 | A | delete | n/a | S | ss/nl | PROJECT DOVE 6240041 |  | 2025-06-11 | Z | 2025-06-06 | 0 | 0 | 0 |  | 0 | 0 |  | Exposed |  | 5
2025-06-11 | 1365 |  | 61125 | A | DONE | 2 | S | neal | PROJECT DOVE 6240041 |  | 2025-06-11 | Z | 2025-06-11 | 20 | 0 | 0 |  | 0 | 20 |  | Angles |  | 0
2025-06-10 | 231 |  | 75751 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-06-11 | Z | 2025-06-04 | 50 | 0 | 0 |  | 0 | 90 |  | Flat Stock |  | 7
2025-06-12 | 1950 |  | 75778 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 | DM Frames | 2025-06-11 | Z | 2025-06-09 | 50 | 0 | 0 |  | 0 | 90 |  | DM / Angles |  | 2
2025-06-12 | 1951 | bth | 75779 | A | DONE | 4 | S |  | REEDSBURG HS 6250010 |  | 2025-06-11 | Z | 2025-06-09 | 70 | 20 | 0 |  | 0 | 90 |  | 1st Floor LP |  | 2
2025-06-11 | 1160 | bth | J2F-EAD-090 |  | delete | 0 | S-M |  | ROCK CO. JAIL 6220018 |  | 2025-06-11 | Z | 2023-11-28 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 561
2025-06-11 | 1161 | bth | J2F-EAD-091 |  | delete | 0 | S-M | pt.alum | ROCK CO. JAIL 6220018 |  | 2025-06-11 | Z | 2023-11-28 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 561
2025-06-11 | 1162 |  | J2F-EAD-110 |  | delete | 0 | S-M |  | ROCK CO. JAIL 6220018 |  | 2025-06-11 | Z | 2023-11-28 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 561
2025-06-11 | 1163 |  | J2F-EAD-111 |  | delete | 0 | S-M |  | ROCK CO. JAIL 6220018 |  | 2025-06-11 | Z | 2023-11-28 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 561
2025-06-11 | 1164 |  | J2F-EAD-112 |  | delete | 0 | S-M |  | ROCK CO. JAIL 6220018 |  | 2025-06-11 | Z | 2023-11-28 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 561
2025-06-11 | 1165 |  | J2F-EAD-113 |  | delete | 0 | S-M |  | ROCK CO. JAIL 6220018 |  | 2025-06-11 | Z | 2023-11-28 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 561
2025-06-12 | 3671 |  | HAND | A | DONE | 3 | S |  | SPH SURGERY 6240039 |  | 2025-06-13 | Z | 2025-06-12 | 60 | 0 | 0 |  | 0 | 150 |  | Leave Apart |  | 1
2025-06-10 | 2413 |  | 74110 - 74111 | A | DONE | 9 | S-M |  | ST.BERNARD 6230023 | flex , CD | 2025-06-10 | Z | 2025-05-29 | 120 | 0 | 90 | F | 0 | 290 |  | RF-1,2 |  | 12
2025-06-12 | 816 |  | DH-0002 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-06-13 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 60 |  | Pre-fab hangers |  | 15
2025-06-13 | 817 | sp | 73608 - 73609 | A | DONE | 16 | S-M |  | SW HEALTH OR 5 6250004 | flex | 2025-06-13 | Z | 2025-05-29 | 70 | 320 | 0 |  | 0 | 400 |  | H2-2 , H1-3 |  | 15
2025-06-13 | 818 | sp | 73610 - 73611 | A | DONE | 16 | S-M |  | SW HEALTH OR 5 6250004 | flex | 2025-06-13 | Z | 2025-05-29 | 70 | 330 | 0 |  | 0 | 410 |  | H2-1 , H1-4 |  | 15
2025-06-13 | 820 | sp | 73613 | A | DONE | 4 | S-M |  | SW HEALTH OR 5 6250004 | flex | 2025-06-13 | Z | 2025-05-29 | 20 | 60 | 0 |  | 0 | 80 |  | H2-3 |  | 15
2025-06-13 | 821 | sp | 73614 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-06-13 | Z | 2025-05-29 | 20 | 30 | 0 |  | 0 | 60 |  | H2-3 2nd floor |  | 15
2025-06-13 | 822 |  | 73616 , 73618 - 73619 | A | DONE | 8 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-06-13 | Z | 2025-06-02 | 200 | 0 | 0 |  | 0 | 300 |  | Misc |  | 11
2025-06-13 | 823 |  | 73620 - 73621 | A | DONE | 6 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-06-13 | Z | 2025-06-02 | 140 | 0 | 0 |  | 0 | 200 |  | Misc |  | 11
2025-06-10 | 3745 |  | W.SHAFT-SAMP 1 | A | DONE | 6 | S-M |  | UW-LEVY HALL 6230028 | partial | 2025-06-09 | Z | 2025-05-30 | 40 | 0 | 100 | F | 0 | 200 |  |  |  | 10
2025-06-10 | 3746 |  | W.SHAFT-SAMP 2 | A | DONE | 52 | M-L |  | UW-LEVY HALL 6230028 | 1" liner,1" DW,partial | 2025-06-09 | Z | 2025-05-30 | 680 | 0 | 620 | F | 370 | 2060 |  |  |  | 10
2025-06-10 | 3747 |  | W.SHAFT-RAMP 1 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | partial | 2025-06-09 | Z | 2025-05-30 | 80 | 0 | 160 | F | 0 | 410 |  |  |  | 10
2025-06-10 | 3748 |  | W.SHAFT-RAMP 2 | A | DONE | 24 | M |  | UW-LEVY HALL 6230028 | partial | 2025-06-09 | Z | 2025-05-30 | 160 | 0 | 440 | F | 20 | 1060 |  |  |  | 10
2025-06-10 | 3749 |  | W.SHAFT-EAMP 1 | A | DONE | 7 | S-M |  | UW-LEVY HALL 6230028 | partial | 2025-06-09 | Z | 2025-05-30 | 50 | 0 | 110 | F | 0 | 190 |  |  |  | 10
2025-06-10 | 3966 |  | 74549 - 74550 , 74603 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-09 | Z | 2025-05-21 | 70 | 0 | 30 | F | 0 | 170 |  | AHU's |  | 19
2025-06-10 | 3967 |  | 74556 | A | DONE | 19 | M-L | ss | UWL-GRAFF 6230017 | nipple | 2025-06-09 | Z | 2025-05-22 | 460 | 0 | 0 |  | 0 | 1160 |  | OA IH-1 , AHU-1 |  | 18
2025-06-10 | 3968 | bth | 74604 - 74607 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-09 | Z | 2025-05-23 | 150 | 20 | 70 | F | 0 | 320 |  | AHU-3 |  | 17
2025-06-12 | 3969 |  | 74609 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-16 | Z | 2025-05-29 | 30 | 0 | 0 |  | 0 | 50 |  | AHU-3 RA 1sT |  | 18
2025-06-12 | 3970 |  | 74610 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 | 2" FB | 2025-06-16 | Z | 2025-05-29 | 80 | 0 | 0 |  | 0 | 190 |  | AHU-3 PH |  | 18
2025-06-12 | 3971 |  | 74611 - 74612 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-16 | Z | 2025-05-30 | 120 | 0 | 0 |  | 0 | 230 |  | AHU-3 RA |  | 17
2025-06-12 | 3972 |  | 74613 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-16 | Z | 2025-05-30 | 20 | 0 | 0 |  | 0 | 20 |  | Rm 144 M |  | 17
2025-06-12 | 3973 |  | 74614 , 74616 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-16 | Z | 2025-06-04 | 40 | 0 | 0 |  | 0 | 60 |  | Outs |  | 12
2025-06-13 | 1863 |  | 66630 | A | DONE | 3 | S-M |  | UWP-FH 6240021 |  | 2025-06-12 | Z | 2025-05-29 | 70 | 0 | 0 |  | 0 | 100 |  | 2nd Floor |  | 14
2025-06-13 | 1865 |  | 66634 - 66636 | A | DONE | 8 | S-M |  | UWP-FH 6240021 | VD's | 2025-06-12 | Z | 2025-05-29 | 180 | 0 | 0 |  | 0 | 340 |  | AHU's |  | 14
2025-06-09 | 2862 |  | 84856 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-06-10 | Z | 2025-05-29 | 20 | 0 | 0 |  | 0 | 30 |  | 116 FEMP Hood tie in |  | 12
2025-06-12 | 3262 |  | 81294 | A | DONE | 2 | S | ss | UWSP ALBERTSON 6230016 |  | 2025-06-13 | Z | 2025-05-22 | 20 | 0 | 0 |  | 0 | 20 |  | Steam pit gussets |  | 22
2025-06-09 | 4418 |  | 70186 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-06-10 | Z | 2025-06-04 | 20 | 0 | 0 |  | 0 | 40 |  | Intake Hood |  | 6
2025-06-09 | 4419 |  | 70187 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2025-06-10 | Z | 2025-06-04 | 20 | 0 | 0 |  | 0 | 50 |  | Louver Sleeve |  | 6
2025-06-13 | 3076 |  | 57643 | A | DONE | 3 | S |  | UW-VET MED 6210014 |  | 2025-06-12 | Z | 2025-06-03 | 70 | 0 | 0 |  | 0 | 100 |  | 10-O South |  | 9
2025-06-13 | 3077 |  | 57644 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 |  | 2025-06-12 | Z | 2025-06-03 | 30 | 0 | 0 |  | 0 | 50 |  | CB 357 |  | 9
2025-06-13 | 3078 |  | 57645 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-06-12 | Z | 2025-06-09 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 3
2025-06-09 | 3552 |  | 84972 - 84976 | A | DONE | 43 | M | neal | UW-WHITEWATER ML 6250001 | reheat coil | 2025-06-06 | Z | 2025-05-23 | 620 | 0 | 440 | F | 0 | 1250 |  | RHC 2054 |  | 14
2025-06-09 | 3554 |  | 84978 - 84979 | A | DONE | 11 | S-M | neal | UW-WHITEWATER ML 6250001 | paint | 2025-06-06 | Z | 2025-05-23 | 160 | 0 | 110 | F | 60 | 310 |  | Flex studio EA , TA |  | 14
2025-06-09 | 3555 |  | 84981 - 84983 | A | DONE | 40 | M | neal | UW-WHITEWATER ML 6250001 | VD's , CD | 2025-06-06 | Z | 2025-05-23 | 530 | 0 | 450 | F | 0 | 1570 |  | EF-14 |  | 14
2025-06-13 | 3561 |  | 84995 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-06-13 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 50 |  | Sleeves |  | 10
2025-06-12 | 3573 |  | EMAIL | A | DONE | 2 | S | neal | UW-WHITEWATER ML 6250001 |  | 2025-06-13 | Z | 2025-06-11 | 20 | 0 | 0 |  | 0 | 20 |  | Couplings |  | 2
2025-06-09 | 223r |  | 84994 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 | 1" liner | 2025-06-06 | Z | 2025-06-02 | 20 | 0 | 0 |  | 20 | 20 |  | EC"s |  | 4
2025-06-12 | 3856 |  | 74767 | A | DONE | 3 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-06-11 | Z | 2025-05-29 | 60 | 0 | 0 |  | 50 | 80 |  | Misc |  | 13
2025-06-10 | 3855b |  | 74766 | A | DONE | 7 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner , AB damper | 2025-06-11 | Z | 2025-05-31 | 160 | 0 | 0 |  | 110 | 240 |  | Damper piece |  | 11
2025-06-09 | 995 | bth | L02_D_SALP_004 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 40 | 20 | 0 |  | 0 | 70 |  |  |  | 107
2025-06-09 | 996 | bth | L02_D_SALP_005 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 60 | 70 | 0 |  | 0 | 140 |  |  |  | 107
2025-06-09 | 997 | bth | L02_D_SALP_006 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 80 | 50 | 140 | F | 0 | 360 |  |  |  | 107
2025-06-09 | 998 | bth | L02_D_SALP_007 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 10 | 40 | 0 |  | 0 | 50 |  |  |  | 107
2025-06-09 | 999 | bth | L02_D_SALP_008 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 80 | 40 | 140 | F | 0 | 340 |  |  |  | 107
2025-06-09 | 1150 | bth | L02_D_SALP_009 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 80 | 40 | 70 | F | 0 | 230 |  |  |  | 107
2025-06-09 | 1151 | bth | L02_D_SALP_010 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 40 | 50 | 90 | F | 0 | 210 |  |  |  | 107
2025-06-09 | 1152 | bth | L02_D_SALP_011 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 60 | 30 | 70 | F | 0 | 220 |  |  |  | 107
2025-06-09 | 1153 | bth | L02_D_SALP_012 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 80 | 30 | 80 | F | 0 | 230 |  |  |  | 107
2025-06-09 | 1154 | bth | L02_D_SALP_013 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-06 | Z | 2025-02-19 | 40 | 60 | 40 | F | 0 | 170 |  |  |  | 107
2025-06-09 | 1156 | bth | L02_D_SALP_015 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 40 | 40 | 90 | F | 0 | 210 |  |  |  | 107
2025-06-10 | 1157 | bth | L02_D_SALP_016 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 20 | 80 | 0 |  | 0 | 90 |  |  |  | 107
2025-06-09 | 1158 | bth | L02_D_SALP_017 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 30 | 40 | 90 | F | 0 | 200 |  |  |  | 107
2025-06-10 | 1159 | bth | L02_D_SALP_018 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 40 | 50 | 0 |  | 0 | 90 |  |  |  | 107
2025-06-10 | 1160 | bth | L02_D_SALP_019 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-06-06 | Z | 2025-02-19 | 40 | 40 | 90 | F | 0 | 210 |  |  |  | 107
2025-06-10 | 1161 |  | L02_D_RAD_001 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 60 | 0 | 0 |  | 60 | 100 |  |  |  | 107
2025-06-10 | 1162 | bth | L02_D_RAD_002 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 40 | 20 | 0 |  | 30 | 60 |  |  |  | 107
2025-06-10 | 1164 |  | L02_D_RAD_004 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 70 | 0 | 40 | F | 90 | 140 |  |  |  | 107
2025-06-10 | 1165 | bth | L02_D_RAD_005 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 30 | 20 | 0 |  | 20 | 60 |  |  |  | 107
2025-06-10 | 1166 |  | L02_D_RAD_006 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 80 | 0 | 40 | F | 100 | 160 |  |  |  | 107
2025-06-10 | 1167 |  | L02_D_RAD_007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 70 | 0 | 40 | F | 90 | 150 |  |  |  | 107
2025-06-10 | 1168 |  | L02_D_RAD_008 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 90 | 0 | 40 | F | 100 | 160 |  |  |  | 107
2025-06-10 | 1169 |  | L02_D_RAD_009 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 80 | 0 | 40 | F | 80 | 140 |  |  |  | 107
2025-06-10 | 1170 | bth | L02_D_RAD_010 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 40 | 30 | 0 |  | 30 | 90 |  |  |  | 107
2025-06-10 | 1171 |  | L02_D_RAD_011 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 60 | 0 | 70 | F | 100 | 160 |  |  |  | 107
2025-06-10 | 1172 |  | L02_D_RAD_012 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 40 | 0 | 60 | F | 80 | 130 |  |  |  | 107
2025-06-10 | 1173 |  | L02_D_RAD_013 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 60 | 0 | 70 | F | 100 | 160 |  |  |  | 107
2025-06-10 | 1174 | bth | L02_D_RAD_014 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 50 | 80 | 0 |  | 20 | 130 |  |  |  | 107
2025-06-10 | 1175 |  | L02_D_RAD_015 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-02-19 | 100 | 0 | 40 | F | 100 | 160 |  |  |  | 107
2025-06-09 | 1472 |  | 83348 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-06-06 | Z | 2025-05-21 | 30 | 0 | 0 |  | 20 | 40 |  | 1st E HP 2224 SA |  | 16
2025-06-09 | 1906 |  | 83311 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-06 | Z | 2025-05-29 | 30 | 0 | 20 | F | 0 | 60 |  | PRV |  | 8
2025-06-12 | 1908 |  | 83312 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-11 | Z | 2025-06-05 | 20 | 0 | 0 |  | 0 | 30 |  | D OA outs |  | 6
[6 empty] | 1178 | [13 empty] | 41990 |  |  |  | 17500 | 41.68%
WEEK OF 6-16-2025
2025-06-16 | 286 |  | 85231 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2025-06-13 | Z | 2025-05-30 | 100 | 0 | 0 |  | 0 | 380 |  | G-Generator Rm |  | 14
2025-06-19 | 299 |  | 85246 - 85247 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2025-06-16 | Z | 2025-06-16 | 90 | 0 | 0 |  | 0 | 290 |  | Gen. Intake |  | 0
2025-06-19 | 235 |  | 84724 | A | DONE | 2 | S |  | 8020 B-2 4250030 |  | 2025-06-19 | Z | 2025-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | Boiler 2 |  | 2
2025-06-19 | 234 |  | 84723 | A | DONE | 2 | S |  | 8020 HP 4250031 | flex | 2025-06-19 | Z | 2025-06-17 | 30 | 0 | 0 |  | 0 | 40 |  | Heat Pump |  | 2
2025-06-16 | 2269 | sp | 83224 - 83226 | A | DONE | 200 | M-L |  | BARTILLION 6240024 | s.mates , 1" DW | 2025-06-10 | Z | 2025-05-13 | 760 | 4220 | 0 |  | 1360 | 4490 |  | SA Dining Rm |  | 28
2025-06-17 | 2270 | sp | 83227 - 83229 | A | DONE | 108 | M-L |  | BARTILLION 6240024 | s.mates , 1" DW | 2025-06-10 | Z | 2025-05-13 | 120 | 2560 | 0 |  | 670 | 2310 |  | Dinning south run outs |  | 28
2025-06-16 | 2276 | bth | 83233 - 83234 | A | DONE | 21 | S-M |  | BARTILLION 6240024 | 1" liner | 2025-06-12 | Z | 2025-05-21 | 150 | 120 | 240 | F | 320 | 550 |  | MD 1-12 - 1-16 |  | 22
2025-06-16 | 2277 | sp | 83238 - 83239 | A | DONE | 8 | S-M |  | BARTILLION 6240024 |  | 2025-06-12 | Z | 2025-05-21 | 40 | 160 | 0 |  | 0 | 190 |  | AV 1-10 , 11 , 13 |  | 22
2025-06-16 | 2278 |  | 83240 | A | DONE | 3 | S-M |  | BARTILLION 6240024 | 1" liner | 2025-06-12 | Z | 2025-05-21 | 70 | 0 | 0 |  | 50 | 90 |  | LP 1-10 , 1-11 |  | 22
2025-06-16 | 2279 | sp | 83241 - 83242 | A | DONE | 16 | S-M |  | BARTILLION 6240024 | 1" spiral acoustic | 2025-06-12 | Z | 2025-05-21 | 90 | 290 | 0 |  | 70 | 400 |  | MP Main |  | 22
2025-06-16 | 2280 |  | 83243 | A | DONE | 3 | S |  | BARTILLION 6240024 | 1" liner | 2025-06-12 | Z | 2025-05-21 | 70 | 0 | 0 |  | 40 | 100 |  | AV 1-9 |  | 22
2025-06-16 | 2281 | sp | 83244 | A | DONE | 5 | S-M |  | BARTILLION 6240024 |  | 2025-06-12 | Z | 2025-05-21 | 0 | 110 | 0 |  | 0 | 110 |  | AV |  | 22
2025-06-16 | 2282 |  | 83245 - 83246 | A | DONE | 6 | S-M |  | BARTILLION 6240024 | 1" liner | 2025-06-12 | Z | 2025-05-21 | 150 | 0 | 0 |  | 110 | 210 |  | AV 1-1 , 2 , 3 |  | 22
2025-06-17 | 2284 |  | 83250 | A | DONE | 5 | S |  | BARTILLION 6240024 | 1" liner | 2025-06-12 | Z | 2025-05-21 | 120 | 0 | 0 |  | 80 | 160 |  | AV 1-8 , 14 , 15 |  | 22
2025-06-16 | 2285 |  | 75151 - 75152 | A | DONE | 12 | S-M |  | BARTILLION 6240024 | 1" liner | 2025-06-12 | Z | 2025-05-21 | 290 | 0 | 0 |  | 260 | 390 |  | TA 1st |  | 22
2025-06-16 | 2291 |  | 75154 | A | DONE | 8 | S-M |  | BARTILLION 6240024 |  | 2025-06-12 | Z | 2025-05-29 | 80 | 0 | 110 | F | 0 | 220 |  | MAU SA |  | 14
2025-06-16 | 2292 |  | 75167 - 75168 | A | DONE | 14 | S-M |  | BARTILLION 6240024 | paint | 2025-06-12 | Z | 2025-05-29 | 330 | 0 | 0 |  | 30 | 560 |  | MAU RA , Kitchen RA |  | 14
2025-06-19 | 2293 | w | 75176 | A | DONE | 2 | S | ss | BARTILLION 6240024 |  | 2025-06-18 | Z | 2025-06-04 | 30 | 0 | 0 |  | 0 | 70 |  | Dishwasher out |  | 14
2025-06-19 | 2900 | w | 80909 | A | DONE | 2 | S |  | BROOM ST. 6240033 | paint | 2025-06-18 | Z | 2025-06-17 | 40 | 0 | 0 |  | 0 | 80 |  | Gen. EA Sleeve |  | 1
2025-06-19 | 894 | sp | 73670 | A | DONE | 55 | M-L |  | DELLSHIRE 6240017 |  | 2025-06-16 | Z | 2025-05-02 | 70 | 1290 | 0 |  | 0 | 1560 |  | 4th EA Riser |  | 45
2025-06-16 | 1604 | w | 74301-B | A | DONE | 7 | S-M |  | DOC JDC 6240023 | 2" FB | 2025-06-11 | Z | 2025-05-29 | 170 | 0 | 0 |  | 110 | 440 |  | Zone 1 sleeves |  | 13
2025-06-19 | 1609 | w | 73903 | A | DONE | 2 | S-M |  | DOC JDC 6240023 | 2" FB | 2025-06-18 | Z | 2025-06-17 | 40 | 0 | 0 |  | 20 | 100 |  | Sleeves for Mezz |  | 1
2025-06-20 | 1716 |  | 74219 , 74221 - 74222 | A | DONE | 10 | M |  | MCDS 6250005 | 1" liner | 2025-06-17 | Z | 2025-06-03 | 190 | 0 | 50 | F | 180 | 480 |  | RTU-1 SA / RA |  | 14
2025-06-20 | 1717 |  | 74220 | A | DONE | 2 | S-M |  | MCDS 6250005 |  | 2025-06-17 | Z | 2025-06-03 | 50 | 0 | 0 |  | 0 | 110 |  | RTU-1 SA |  | 14
2025-06-16 | 1713 |  | 74262 | A | DONE | 2 | S |  | MCDS 625005 | 1" liner | 2025-06-13 | Z | 2025-05-30 | 50 | 0 | 0 |  | 50 | 70 |  | Misc |  | 14
2025-06-16 | 1714 |  | 74263 | A | DONE | 9 | S |  | MCDS 625005 |  | 2025-06-13 | Z | 2025-05-30 | 30 | 190 | 0 |  | 0 | 200 |  | Misc |  | 14
2025-06-20 | 3829 |  | 83610 | A | DONE | 3 | S |  | MONROE HS 6240018 |  | 2025-06-17 | Z | 2025-06-03 | 60 | 0 | 0 |  | 0 | 80 |  | RHRU Drops |  | 14
2025-06-19 | 1783 |  | 69439 - 69440 | A | DONE | 8 | S-M |  | ONE 09 6240037 | flex | 2025-06-16 | Z | 2025-06-06 | 180 | 0 | 0 |  | 0 | 200 |  | CH 105 soffit |  | 10
2025-06-20 | 1830 | sp | 74114 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-06-18 | Z | 2025-06-06 | 20 | 20 | 0 |  | 0 | 40 |  | Coach office SA |  | 12
2025-06-20 | 1831 |  | 74156 | A | DONE | 2 | S-M |  | PEWAUKEE HS 6240030 |  | 2025-06-18 | Z | 2025-06-06 | 40 | 0 | 0 |  | 0 | 100 |  | RTU-1 damper sleeve |  | 12
2025-06-17 | 1322 |  | AHU_002_RAMP_001 | A | DONE | 6 | S-M | ss | PROJECT DOVE 6240041 |  | 2025-06-13 | Z | 2025-06-04 | 130 | 0 | 0 |  | 0 | 360 |  |  |  | 9 | 2025-06-05
2025-06-19 | 1323 |  | AHU_002_SAMP_001 | A | DONE | 11 | M | ss | PROJECT DOVE 6240041 |  | 2025-06-13 | Z | 2025-06-04 | 260 | 0 | 0 |  | 0 | 700 |  |  |  | 9 | 2025-06-05
2025-06-19 | 1324 |  | AHU_003_RAMP_001 | A | DONE | 9 | S-M | ss | PROJECT DOVE 6240041 |  | 2025-06-13 | Z | 2025-06-04 | 220 | 0 | 0 |  | 0 | 560 |  |  |  | 9 | 2025-06-05
2025-06-19 | 1325 |  | AHU_003_SAMP_001 | A | DONE | 11 | M | ss | PROJECT DOVE 6240041 |  | 2025-06-13 | Z | 2025-06-04 | 270 | 0 | 0 |  | 0 | 760 |  |  |  | 9 | 2025-06-05
2025-06-17 | 3039 | sp | 81837 | A | DONE | 10 | S-M |  | PROMEGA BTC 6230022 |  | 2025-06-16 | Z | 2025-06-03 | 40 | 200 | 0 |  | 0 | 250 |  | RA |  | 13
2025-06-17 | 3040 |  | 81838 | A | DONE | 26 | M |  | PROMEGA BTC 6230022 |  | 2025-06-16 | Z | 2025-06-03 | 390 | 0 | 240 | F | 0 | 1290 |  | SA |  | 13
2025-06-17 | 3041 |  | 81839 | A | DONE | 12 | M |  | PROMEGA BTC 6230022 |  | 2025-06-16 | Z | 2025-06-03 | 80 | 0 | 220 | F | 0 | 580 |  | RA |  | 13
2025-06-19 | 3042 | bth | 81840 | F | DONE | 3 | S |  | PROMEGA BTC 6230022 |  | 2025-06-18 | Z | 2025-06-09 | 20 | 40 | 0 |  | 0 | 60 |  | Misc |  | 9
2025-06-20 | 3043 |  | 81841 | F | DONE | 4 | S-M |  | PROMEGA BTC 6230022 | bird s. | 2025-06-18 | Z | 2025-06-09 | 100 | 0 | 0 |  | 0 | 180 |  | Misc |  | 9
2025-06-16 | 1952 |  | 75780 | A | DONE | 3 | S |  | REEDSBURG HS 6250010 | 1" liner | 2025-06-11 | Z | 2025-06-09 | 60 | 0 | 0 |  | 50 | 90 |  | 1st Floor TA |  | 2
2025-06-20 | 1953 |  | 75752 | A | DONE | 8 | S-M | neal | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 50 | 140 | 0 |  | 0 | 240 |  | HP |  | 9
2025-06-20 | 1955 | bth | 75758 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 30 | 20 | 0 |  | 0 | 50 |  | V-204 LP SA |  | 9
2025-06-20 | 1956 | bth | 75759 - 75760 | A | DONE | 7 | S |  | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 100 | 70 | 0 |  | 0 | 180 |  | V-206 LP SA |  | 9
2025-06-20 | 1957 | sp | 75761 - 75764 | A | DONE | 13 | M | neal | REEDSBURG HS 6250010 | VD's | 2025-06-18 | Z | 2025-06-09 | 90 | 220 | 0 |  | 0 | 390 |  | V-208 LP SA |  | 9
2025-06-20 | 1958 | bth | 75765 - 75767 | A | DONE | 8 | S-M |  | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 120 | 70 | 0 |  | 0 | 200 |  | V-210,12,13 LP SA |  | 9
2025-06-20 | 1959 | bth | 75768 - 75770 | A | DONE | 8 | S-M |  | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 90 | 90 | 20 | F | 0 | 250 |  | V-214,5,11 LP SA |  | 9
2025-06-20 | 1960 |  | 75771 | A | DONE | 2 | S | neal | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 30 | 0 | 0 |  | 0 | 70 |  | Tear drop hangers |  | 9
2025-06-20 | 1961 |  | 75772 | A | DONE | 3 | S | neal | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 70 | 0 | 0 |  | 0 | 100 |  | EF-1,2,3 |  | 9
2025-06-20 | 1962 |  | 75773 - 75774 | A | DONE | 6 | S-M | neal | REEDSBURG HS 6250010 | paint | 2025-06-18 | Z | 2025-06-09 | 130 | 0 | 0 |  | 50 | 200 |  | EF-1,2 |  | 9
2025-06-20 | 1963 |  | 75775 | A | DONE | 2 | S | neal | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 30 | 0 | 0 |  | 0 | 50 |  | EF-3 |  | 9
2025-06-20 | 1964 |  | 75776 - 75777 | A | DONE | 4 | S-M | neal | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 20 | 80 | 0 |  | 0 | 110 |  | EF-3 |  | 9
2025-06-20 | 1965 |  | 75781 | A | DONE | 2 | S | neal | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 50 | 0 | 0 |  | 0 | 80 |  | EF-4,5,6 drops |  | 9
2025-06-20 | 1966 |  | 75782 | A | DONE | 5 | S | neal | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 70 | 50 | 0 |  | 0 | 130 |  | EF-4,5 |  | 9
2025-06-20 | 1967 |  | 75783 - 75784 | A | DONE | 4 | S-M |  | REEDSBURG HS 6250010 |  | 2025-06-18 | Z | 2025-06-09 | 80 | 0 | 0 |  | 0 | 110 |  | EF-6 |  | 9
2025-06-17 | 3664 |  | 68865 - 68867 | A | DONE | 7 | S-M | pt.ss | SPH SURGERY 6240039 |  | 2025-06-16 | Z | 2025-06-02 | 170 | 0 | 0 |  | 0 | 280 |  | PRV 12-1 |  | 14
2025-06-17 | 3665 | sp | 68868 | A | DONE | 3 | S | ss | SPH SURGERY 6240039 |  | 2025-06-16 | Z | 2025-06-02 | 20 | 40 | 0 |  | 0 | 60 |  | Misc |  | 14
2025-06-20 | 3674 |  | 68145 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-06-23 | Z | 2025-06-16 | 30 | 0 | 0 |  | 0 | 50 |  | VAV-5-15 |  | 7
2025-06-20 | 3675 | sp | 68146 | A | DONE | 5 | S |  | SPH SURGERY 6240039 |  | 2025-06-23 | Z | 2025-06-16 | 20 | 100 | 0 |  | 0 | 100 |  | VAV-5-15 |  | 7
2025-06-19 | 2414 | w | 74113 | A | DONE | 2 | S |  | ST.BERNARD 2230037 |  | 2025-06-18 | Z | 2025-06-04 | 20 | 0 | 0 |  | 0 | 20 |  | Test caps |  | 14
2025-06-17 | 815 |  | 73607 | A | DONE | 42 | M-L | neal | SW HEALTH OR 5 6250004 | 3" DW | 2025-06-16 | Z | 2025-05-22 | 1050 | 0 | 0 |  | 400 | 1050 |  | OA |  | 25
2025-06-17 | 819 | w | 73612 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 | 1-1/2 DB | 2025-06-13 | Z | 2025-05-29 | 30 | 0 | 0 |  | 20 | 80 |  | H1-4 |  | 15
2025-06-19 | 824 | sp | 73571 , 73573 | A | DONE | 7 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-06-16 | Z | 2025-06-04 | 50 | 120 | 0 |  | 0 | 180 |  | VAV E1-08,09 , LPSA |  | 12
2025-06-16 | 825 |  | 73572 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-06-16 | Z | 2025-06-04 | 40 | 0 | 0 |  | 0 | 60 |  | VAV LPSA |  | 12
2025-06-17 | 826 |  | 73622 - 73623 | A | DONE | 11 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-06-16 | Z | 2025-06-05 | 210 | 0 | 60 | F | 0 | 360 |  | OR SA |  | 11
2025-06-19 | 827 |  | 73624 | A | DONE | 7 | S |  | SW HEALTH OR 5 6250004 |  | 2025-06-16 | Z | 2025-06-05 | 20 | 50 | 0 |  | 0 | 80 |  | OR SA |  | 11
2025-06-19 | 828 |  | 73625 , 73627 - 73628 | A | DONE | 18 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-06-16 | Z | 2025-06-05 | 210 | 0 | 220 | F | 0 | 550 |  | OA E/W RA |  | 11
2025-06-20 | 829 |  | 73574 - 73576 | A | DONE | 102 | M-L | neal | SW HEALTH OR 5 6250004 | 3" DW | 2025-06-16 | Z | 2025-06-05 | 2120 | 0 | 410 | F | 1310 | 5030 |  | Lower roof exterior duct |  | 11
2025-06-19 | 641 |  | 66719 - 66720 | A | DONE | 5 | S |  | UW-BIO CHEM 6240036 |  | 2025-06-16 | Z | 2025-06-16 | 110 | 0 | 0 |  | 0 | 160 |  | AHU-7 Flashing |  | 0
2025-06-19 | 642 |  | 66721 | A | DONE | 3 | S |  | UW-BIO CHEM 6240036 |  | 2025-06-16 | Z | 2025-06-16 | 70 | 0 | 0 |  | 0 | 90 |  | AHU-7 Flashing |  | 0
2025-06-19 | 643 |  | 66722 | A | DONE | 2 | S | ss | UW-BIO CHEM 6240036 |  | 2025-06-19 | Z | 2025-06-18 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 1
2025-06-19 | 2007 |  | 83823 | A | DONE | 2 | S | ss | UW-LEVY HALL 6230028 |  | 2025-06-16 | Z | 2025-06-06 | 20 | 0 | 0 |  | 0 | 30 |  | Generator Breaching |  | 10
2025-06-20 | 726r |  | L2-TA 6 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | bird s. , 1" liner | 2025-06-16 | Z | 2025-06-02 | 70 | 0 | 0 |  | 60 | 100 |  |  |  | 14
2025-06-20 | 3974 |  | 74617 - 74619 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-18 | Z | 2025-06-05 | 20 | 0 | 0 |  | 0 | 30 |  | RM 135 outs |  | 13
2025-06-20 | 3975 | sp | 74620 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-18 | Z | 2025-06-06 | 20 | 20 | 0 |  | 0 | 20 |  | Chanc EA |  | 12
2025-06-20 | 3976 |  | 74621 - 74622 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-18 | Z | 2025-06-06 | 160 | 0 | 0 |  | 0 | 360 |  | AHU-1 Chase |  | 12
2025-06-16 | 1864 | sp | 66631 | A | DONE | 4 | S-M |  | UWP-FH 6240021 |  | 2025-06-12 | Z | 2025-05-29 | 40 | 40 | 0 |  | 0 | 80 |  | 2nd Floor |  | 14
2025-06-16 | 1866 |  | 66637 | A | DONE | 21 | M |  | UWP-FH 6240021 |  | 2025-06-12 | Z | 2025-05-29 | 510 | 0 | 0 |  | 0 | 1190 |  | AHU's |  | 14
2025-06-16 | 1867 |  | 66639 , 66641 | A | DONE | 8 | S-M |  | UWP-FH 6240021 | 1" liner | 2025-06-12 | Z | 2025-06-05 | 190 | 0 | 0 |  | 20 | 420 |  | DOAS 2nd Floor |  | 7
2025-06-20 | 2864 |  | 84858 | A | DONE | 2 | S | ss | UWRF 6230010 | flex | 2025-06-24 | Z | 2025-06-10 | 60 | 0 | 0 |  | 0 | 80 |  | Roof |  | 14
2025-06-16 | 3261 |  | 81293 | A | DONE | 4 | S-M | ss | UWSP ALBERTSON 6230016 |  | 2025-06-13 | Z | 2025-05-22 | 80 | 0 | 0 |  | 0 | 100 |  | Steam pit |  | 22
2025-06-16 | 3263 |  | 81296 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | filter rack | 2025-06-13 | Z | 2025-05-22 | 20 | 0 | 0 |  | 0 | 30 |  | 1st Floor VRF 1-1-1 |  | 22
2025-06-16 | 3265 |  | 61481 - 61483 | A | DONE | 4 | S-M |  | UWSP ALBERTSON 6230016 |  | 2025-06-13 | Z | 2025-05-29 | 80 | 0 | 0 |  | 0 | 120 |  | 3rd Floor , Rm 450 |  | 15
2025-06-16 | 3266 | sp | 61484 - 61485 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-06-13 | Z | 2025-06-05 | 20 | 30 | 0 |  | 0 | 40 |  | 3rd Floor RA |  | 8
2025-06-16 | 3267 |  | 61486 - 61489 | A | DONE | 5 | S-M |  | UWSP ALBERTSON 6230016 | paint , flex | 2025-06-13 | Z | 2025-06-05 | 120 | 0 | 0 |  | 60 | 180 |  | Misc |  | 8
2025-06-20 | 3268 |  | 61490 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 | paint | 2025-06-17 | Z | 2025-06-11 | 30 | 0 | 0 |  | 20 | 50 |  | Misc |  | 6
2025-06-20 | 3080 |  | DH-7B | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-06-19 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 40 |  | Pre-fab hangers |  | 3
2025-06-20 | 3081 |  | 57648 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-06-19 | Z | 2025-06-17 | 30 | 0 | 0 |  | 0 | 50 |  | Flatstock |  | 2
2025-06-17 | 3557 |  | 84985 - 84987 | A | DONE | 12 | M | neal | UW-WHITEWATER ML 6250001 | VD's | 2025-06-13 | Z | 2025-05-23 | 140 | 0 | 140 | F | 0 | 390 |  | Advanced studio , EF-12 |  | 21
2025-06-17 | 3558 |  | 84989 | A | DONE | 4 | S | neal | UW-WHITEWATER ML 6250001 |  | 2025-06-13 | Z | 2025-05-23 | 90 | 0 | 0 |  | 0 | 120 |  | EF Stacks |  | 21
2025-06-17 | 3559 | sp | 84990 - 84992 | A | DONE | 15 | M | neal | UW-WHITEWATER ML 6250001 |  | 2025-06-13 | Z | 2025-05-23 | 100 | 270 | 0 |  | 0 | 450 |  | 3D printer , Chem buffer |  | 21
2025-06-16 | 3560 |  | 84993 | A | DONE | 2 | S | neal | UW-WHITEWATER ML 6250001 | bird s. | 2025-06-13 | Z | 2025-05-23 | 20 | 0 | 0 |  | 0 | 20 |  | Chem / Buffering EA M-21 |  | 21
2025-06-16 | 3568 |  | 85005 | A | DONE | 4 | S-M |  | UW-WHITEWATER ML 6250001 |  | 2025-06-13 | Z | 2025-06-09 | 80 | 0 | 0 |  | 0 | 100 |  | Drops |  | 4
2025-06-17 | 3569 | sp | 85006 | A | DONE | 2 | S-M | neal | UW-WHITEWATER ML 6250001 |  | 2025-06-13 | Z | 2025-06-09 | 20 | 30 | 0 |  | 0 | 60 |  | Drops |  | 4
2025-06-17 | 3570 | w | 85007 | A | DONE | 2 | S | ss | UW-WHITEWATER ML 6250001 |  | 2025-06-13 | Z | 2025-06-09 | 20 | 0 | 0 |  | 0 | 60 |  | Fume hood |  | 4
2025-06-19 | 3857 |  | 74768 | A | DONE | 8 | S-M | neal | UW-WITTE HALL 6250003 |  | 2025-06-18 | Z | 2025-06-06 | 200 | 0 | 0 |  | 0 | 240 |  | Flashing |  | 12
2025-06-19 | 3855c |  | 74766 | A | DONE | 7 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner , AB damper | 2025-06-18 | Z | 2025-05-31 | 160 | 0 | 0 |  | 110 | 240 |  | Damper piece |  | 18
[6 empty] | 1046 | [13 empty] | 33800 |  |  |  | 20620 | 61.01%
WEEK OF 6-23-2025
2025-06-26 | 287 |  | 85232 | A | DONE | 21 | S-M |  | 121 E. WILSON 6230024 |  | 2025-06-19 | Z | 2025-06-04 | 520 | 0 | 0 |  | 0 | 560 |  | TA Sleeves |  | 15
2025-06-23 | 288 |  | 85233 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 | bird s. | 2025-06-17 | Z | 2025-06-04 | 20 | 0 | 0 |  | 0 | 30 |  | EF-8 |  | 13
2025-06-25 | 289 | sp | 85234 | A | DONE | 6 | S-M |  | 121 E. WILSON 6230024 | bird s. | 2025-06-19 | Z | 2025-06-09 | 20 | 130 | 0 |  | 0 | 160 |  | Snowmelt boiler intake |  | 10
2025-06-24 | 291 | bth | 69443 | A | DONE | 12 | S |  | 121 E. WILSON 6230024 |  | 2025-06-17 | Z | 2025-06-09 | 110 | 180 | 0 |  | 0 | 560 |  | ERV-1 |  | 8
2025-06-24 | 292 |  | 69444 - 69446 | A | DONE | 24 | S-M |  | 121 E. WILSON 6230024 | VD , flex | 2025-06-17 | Z | 2025-06-09 | 280 | 0 | 300 | F | 0 | 590 |  | ERV-1 |  | 8
2025-06-25 | 293 |  | 85235 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2025-06-19 | Z | 2025-06-10 | 60 | 0 | 0 |  | 0 | 80 |  | Vent gooseneck |  | 9
2025-06-25 | 294 |  | 85236 - 85238 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 | flex | 2025-06-19 | Z | 2025-06-10 | 100 | 0 | 0 |  | 0 | 140 |  | EF-13 , PH-1, EF-1 |  | 9
2025-06-25 | 295 |  | 85240 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-06-19 | Z | 2025-06-16 | 40 | 0 | 0 |  | 0 | 50 |  | EF-1 |  | 3
2025-06-23 | 298 |  | 85245 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-06-17 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 70 |  |  |  | 1
2025-06-23 | 1032 |  | 79506 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-06-24 | Z | 2025-06-23 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 1
2025-06-24 | 1033 |  | 85164 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-06-30 | Z | 2025-06-24 | 30 | 0 | 0 |  | 0 | 80 |  | Golf Rm RA |  | 6
2025-06-26 | 290a |  | 69448 - 69449 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 | VD , paint , flex | 2025-06-19 | Z | 2025-06-09 | 240 | 0 | 60 | F | 40 | 450 |  | ERV-1 RA /SA |  | 10
2025-06-24 | 2283 | sp | 83247 - 83249 | A | DONE | 115 | M | perf | BARTILLION 6240024 | s.mates , 1" DW | 2025-06-12 | Z | 2025-05-21 | 310 | 2560 | 0 |  | 740 | 2430 |  | AV 1-1 , 5 , 15 |  | 22
2025-06-24 | 2287 |  | 75155 , 75158 | A | DONE | 16 | S-M |  | BARTILLION 6240024 | 1" liner | 2025-06-18 | Z | 2025-05-29 | 60 | 0 | 330 | F | 330 | 590 |  | 2nd Floor RET Mech |  | 20
2025-06-24 | 2288 |  | 75156 - 75157 | A | DONE | 42 | S-M |  | BARTILLION 6240024 | flex | 2025-06-18 | Z | 2025-05-29 | 720 | 50 | 260 | F | 0 | 710 |  | RET 2nd Mech Corridor |  | 20
2025-06-24 | 2289 |  | 75159 - 75162 | A | DONE | 24 | M |  | BARTILLION 6240024 |  | 2025-06-18 | Z | 2025-05-29 | 550 | 0 | 50 | F | 0 | 900 |  | 2nd Mech SA to Corridor |  | 20
2025-06-25 | 2290 |  | 75163 - 75166 | A | DONE | 27 | M |  | BARTILLION 6240024 |  | 2025-06-18 | Z | 2025-05-29 | 490 | 0 | 170 | F | 0 | 810 |  | 2nd Mech OA to Corridor |  | 20
2025-06-27 | 2294 |  | 75169 - 75171 | A | DONE | 60 | M |  | BARTILLION 6240024 |  | 2025-06-24 | Z | 2025-06-04 | 380 | 0 | 1120 | F | 0 | 1950 |  | 2nd SA Main B-Section |  | 20
2025-06-27 | 2295 |  | 75172 - 75175 | A | DONE | 84 | M |  | BARTILLION 6240024 |  | 2025-06-24 | Z | 2025-06-04 | 730 | 0 | 1350 | F | 0 | 3020 |  | 2nd RA Main B-Section |  | 20
2025-06-25 | 2901 | w | 84284 | A | DONE | 2 | S |  | BROOM ST. 6240033 | paint | 2025-06-27 | Z | 2025-06-25 | 20 | 0 | 0 |  | 0 | 40 |  | Sleeve |  | 2
2025-06-26 | 2902 | w | 80911 | A | DONE | 2 | S |  | BROOM ST. 6240033 | paint | 2025-06-27 | Z | 2025-06-26 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeve |  | 1
2025-06-23 | 3506 | bth | 73717 - 73719 | A | DONE | 22 | S-M |  | DELLSHIRE 6240017 |  | 2025-06-16 | Z | 2025-05-15 | 170 | 90 | 270 | F | 0 | 600 |  | 2nd floor misc |  | 32
2025-06-23 | 3509 |  | 73724 - 73725 | A | DONE | 14 | S |  | DELLSHIRE 6240017 | 1" liner | 2025-06-16 | Z | 2025-06-02 | 210 | 0 | 130 | F | 20 | 400 |  | 1st, 2nd outs |  | 14
2025-06-23 | 3510 |  | 73726 - 73728 | A | DONE | 17 | S |  | DELLSHIRE 6240017 |  | 2025-06-16 | Z | 2025-06-02 | 300 | 0 | 110 | F | 0 | 530 |  | 2nd Floor VAV 3-14 LP |  | 14
2025-06-23 | 3511 |  | 73729 - 73730 | A | DONE | 6 | S |  | DELLSHIRE 6240017 |  | 2025-06-16 | Z | 2025-06-02 | 90 | 0 | 40 | F | 0 | 160 |  | 2nd Floor VAV 3-14 LP |  | 14
2025-06-23 | 3512 |  | 73731 - 73732 | A | DONE | 16 | S-M |  | DELLSHIRE 6240017 |  | 2025-06-16 | Z | 2025-06-02 | 230 | 0 | 170 | F | 0 | 510 |  | AHU 3 RA LL |  | 14
2025-06-24 | 3513 |  | 73733 - 73734 | A | DONE | 8 | S-M | pcd | DELLSHIRE 6240017 |  | 2025-06-16 | Z | 2025-06-02 | 130 | 0 | 50 | F | 0 | 300 |  | Pool storage RA |  | 14
2025-06-24 | 3514 |  | 73735 | A | DONE | 30 | S-M |  | DELLSHIRE 6240017 | 1" liner | 2025-06-16 | Z | 2025-06-02 | 730 | 0 | 0 |  | 650 | 740 |  | SA risers |  | 14
2025-06-23 | 3516 |  | E287037 | A | DONE | 2 | S-M |  | DELLSHIRE 6240017 |  | 2025-06-23 | Z | 2025-06-20 | 80 | 0 | 0 |  | 0 | 90 |  | 2X2X60 angles |  | 3
2025-06-25 | 1137 |  | 56695 | A | DONE | 2 | S | ss | EXACT BIO 8240004 |  | 2025-06-23 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 30 |  | Plates |  | 7
2025-06-23 | 2558 | bth | 82596 | A | DONE | 4 | S |  | LABCORP 6240016 |  | 2025-06-23 | Z | 2025-06-20 | 70 | 30 | 0 |  | 0 | 120 |  | MRI Tie In |  | 3
2025-06-24 | 2077 | w | 85321 | A | DONE | 2 | S | ss | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 40 |  | Dishwasher |  | 8
2025-06-26 | 2078 |  | 85322 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | 1st B |  | 7
2025-06-26 | 2079 |  | TA-L1E-01 | A | DONE | 8 | S |  | MONROE HS 6240018 | 1" liner | 2025-06-19 | Z | 2025-06-17 | 110 | 0 | 90 | F | 170 | 280 |  |  |  | 2
2025-06-26 | 2080 |  | TA-L1E-02 | A | DONE | 10 | S-M |  | MONROE HS 6240018 |  | 2025-06-19 | Z | 2025-06-17 | 110 | 0 | 120 | F | 200 | 360 |  |  |  | 2
2025-06-27 | 3833 |  | 85314 | A | DONE | 3 | S |  | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-06-10 | 70 | 0 | 0 |  | 0 | 120 |  | 1st D |  | 14
2025-06-27 | 3834 |  | 85315 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-06-24 | Z | 2025-06-10 | 30 | 0 | 0 |  | 30 | 40 |  | 1st D |  | 14
2025-06-27 | 3835 |  | 85316 - 85317 | A | DONE | 7 | S-M | neal | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-06-10 | 170 | 0 | 0 |  | 0 | 270 |  | 1st D |  | 14
2025-06-27 | 3836 |  | 85318 | A | DONE | 2 | S |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-06-10 | 20 | 0 | 0 |  | 20 | 30 |  | 1st B |  | 14
2025-06-27 | 3837 |  | 85319 | A | DONE | 5 | S-M |  | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-06-10 | 20 | 100 | 0 |  | 0 | 120 |  | 1st B |  | 14
2025-06-24 | 3838 | w | 85320 | A | DONE | 2 | S | ss | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-06-10 | 20 | 0 | 0 |  | 0 | 50 |  | KE 1st B |  | 14
2025-06-24 | 233 |  | 75703 | A | DONE | 4 | S | alum | MSN 2250024 |  | 2025-06-19 | Z | 2025-06-10 | 40 | 0 | 0 |  | 0 | 60 |  | DR-5 306.04.07 |  | 9
2025-06-25 | 1784 | bth | FH-ERV-EA-L1-24 | A | DONE | 18 | S-M | pt.neal | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 140 | 290 | 0 |  | 0 | 500 |  |  |  | 10
2025-06-25 | 1785 |  | FH-ERV-EA-L1-26 | A | DONE | 3 | S |  | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 60 | 0 | 0 |  | 0 | 70 |  |  |  | 10
2025-06-25 | 1786 |  | FH-ERV-OA-L1-25 | A | DONE | 5 | S |  | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 110 | 0 | 0 |  | 0 | 130 |  |  |  | 10
2025-06-25 | 1787 | bth | FH-ERV-SALP-L1-23 | A | DONE | 17 | S-M | pt.neal | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 120 | 290 | 0 |  | 0 | 450 |  |  |  | 10
2025-06-25 | 1788 | sp | FH-SALP-L1-18 | A | DONE | 12 | S-M | neal | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 60 | 230 | 0 |  | 0 | 330 |  |  |  | 10
2025-06-25 | 1789 | sp | FH-SALP-L1-19 | A | DONE | 12 | S-M | neal | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 70 | 230 | 0 |  | 0 | 360 |  |  |  | 10
2025-06-25 | 1790 | sp | FH-SALP-L1-20 | A | DONE | 17 | S-M | neal | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 100 | 320 | 0 |  | 0 | 480 |  |  |  | 10
2025-06-25 | 1791 | sp | FH-SALP-L1-21 | A | DONE | 12 | S-M |  | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 60 | 230 | 0 |  | 0 | 340 |  |  |  | 10
2025-06-25 | 1792 | sp | FH-SALP-L1-22 | A | DONE | 8 | S |  | ONE 09 6240037 | flex | 2025-06-19 | Z | 2025-06-09 | 30 | 150 | 0 |  | 0 | 160 |  |  |  | 10
2025-06-25 | 1793 |  | FH-TA-L1-30 | A | DONE | 3 | S |  | ONE 09 6240037 | 1" liner | 2025-06-19 | Z | 2025-06-09 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 10
2025-06-25 | 4218 | sp | 79686 | A | DONE | 12 | S |  | PECATONICA 6240005 |  | 2025-06-23 | Z | 2025-06-05 | 80 | 200 | 0 |  | 0 | 340 |  | RE-4 |  | 18
2025-06-26 | 4219 |  | 79685 | A | DONE | 9 | S-M |  | PECATONICA 6240005 | paint , 1" liner | 2025-06-23 | Z | 2025-06-05 | 130 | 0 | 90 | F | 160 | 250 |  | RE-4 |  | 18
2025-06-26 | 4220 |  | 79688 | A | DONE | 3 | S-M |  | PECATONICA 6240005 |  | 2025-06-23 | Z | 2025-06-05 | 70 | 0 | 0 |  | 0 | 190 |  | AHU-3 OA |  | 18
2025-06-25 | 4221 | sp | 81631 | A | DONE | 3 | S |  | PECATONICA 6240005 |  | 2025-06-23 | Z | 2025-06-12 | 40 | 20 | 0 |  | 0 | 60 |  | B-SA-MAIN-NE |  | 11
2025-06-23 | 1829 |  | 74101 | A | DONE | 23 | S-M |  | PEWAUKEE HS 6240030 | 1" liner | 2025-06-18 | Z | 2025-06-04 | 60 | 40 | 470 | F | 230 | 780 |  | Culinary SA |  | 14
2025-06-24 | 1838 |  | 74116 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | bird s. | 2025-06-25 | Z | 2025-06-23 | 30 | 0 | 0 |  | 20 | 110 |  | Birdscreen |  | 2
2025-06-24 | 1301 |  | L01_AREA_900_EA_001 | A | DONE | 19 | M |  | PROJECT DOVE 6240041 |  | 2025-06-19 | Z | 2025-05-19 | 400 | 0 | 70 | F | 0 | 720 |  |  |  | 31 | 2025-06-05
2025-06-25 | 1302 |  | L01_AREA_900_EA_002 | A | DONE | 18 | M |  | PROJECT DOVE 6240041 | VD | 2025-06-19 | Z | 2025-05-19 | 210 | 0 | 240 | F | 0 | 690 |  |  |  | 31
2025-06-25 | 1303 |  | L01_AREA_900_EA_003 | A | DONE | 12 | S-M |  | PROJECT DOVE 6240041 | VD . bird s. | 2025-06-19 | Z | 2025-05-19 | 80 | 0 | 220 | F | 0 | 420 |  |  |  | 31
2025-06-25 | 1304 |  | L01_AREA_900_EA_004 | A | DONE | 14 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-06-19 | Z | 2025-05-19 | 50 | 0 | 300 | F | 0 | 530 |  |  |  | 31
2025-06-25 | 1305 |  | L01_AREA_900_EA_005 | A | DONE | 2 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-06-19 | Z | 2025-05-19 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 31
2025-06-25 | 1306 |  | L01_AREA_900_EA_006 | A | DONE | 14 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-06-19 | Z | 2025-05-19 | 270 | 0 | 60 | F | 0 | 510 |  |  |  | 31
2025-06-25 | 1307 |  | L01_AREA_900_EA_007 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-06-19 | Z | 2025-05-19 | 80 | 0 | 0 |  | 0 | 200 |  |  |  | 31
2025-06-26 | 1329 | sp | L01_AREA_300_EA_002 | delete |  |  | S |  | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-06-03 | [5 empty] | 0 |  | BADGER |  | 100 | 2025-06-26
2025-06-26 | 1330 | bth | L01_AREA_300_EA_003 | delete |  |  | S |  | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-06-03 | [5 empty] | 0 |  | BADGER |  | 100 | 2025-06-26
2025-06-23 | 1374 |  | 55136 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-06-26 | Z | 2025-06-16 | 70 | 0 | 0 |  | 0 | 100 |  | Flashing |  | 10
2025-06-26 | 1378 |  | 62625 | A | DONE | 2 | S | neal | PROJECT DOVE 6240041 |  | 2025-06-26 | Z | 2025-06-19 | 20 | 0 | 0 |  | 0 | 20 |  | Angles |  | 7
2025-06-24 | 1379 |  | 55139 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-06-26 | Z | 2025-06-24 | 60 | 0 | 0 |  | 0 | 80 |  | Test caps |  | 2
2025-06-23 | 3044 |  | 81842 - 81844 | A | DONE | 10 | S-M |  | PROMEGA BTC 6230022 |  | 2025-06-26 | Z | 2025-06-19 | 230 | 0 | 0 |  | 0 | 510 |  | EF-L , SA , RA |  | 7
2025-06-27 | 944 |  | EMAIL | A | DONE | 2 | S | pcd | PROMEGA FEYNMAN 6220014 |  | 2025-06-30 | Z | 2025-06-27 | 20 | 0 | 0 |  | 0 | 20 |  | Draw band |  | 3
2025-06-23 | 1954 | sp | 75754 - 75757 | A | DONE | 11 | M | neal | REEDSBURG HS 6250010 | VD's | 2025-06-18 | Z | 2025-06-09 | 110 | 160 | 0 |  | 0 | 380 |  | V-201 LP SA |  | 9
2025-06-23 | 1971 |  | 75794 | A | DONE | 6 | S-M |  | REEDSBURG HS 6250010 |  | 2025-06-25 | Z | 2025-06-10 | 150 | 0 | 0 |  | 0 | 210 |  | Flashing |  | 15
2025-06-23 | 1973 |  | 98247 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-06-25 | Z | 2025-06-23 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2025-06-26 | 1974 | w | 75802 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-07-02 | Z | 2025-06-24 | 20 | 0 | 0 |  | 0 | 60 |  | FD Extensions |  | 8
2025-06-26 | 3668 |  | 68143 | A | DONE | 5 | S |  | SPH SURGERY 6240039 |  | 2025-06-23 | Z | 2025-06-09 | 120 | 0 | 0 |  | 0 | 210 |  | RAMP 1 RA |  | 14
2025-06-25 | 3669 | sp | 68144 | F | DONE | 2 | S | ss | SPH SURGERY 6240039 |  | 2025-06-23 | Z | 2025-06-09 | 20 | 20 | 0 |  | 0 | 40 |  | EA |  | 14
2025-06-26 | 3670 |  | 68903 | A | DONE | 3 | S-M |  | SPH SURGERY 6240039 | flex | 2025-06-23 | Z | 2025-06-10 | 60 | 0 | 0 |  | 0 | 80 |  | OR outs |  | 13
2025-06-27 | 3672 |  | 68904 - 68905 | A | DONE | 11 | S-M |  | SPH SURGERY 6240039 | flex | 2025-06-24 | Z | 2025-06-16 | 260 | 0 | 0 |  | 0 | 630 |  | DDU OA |  | 8
2025-06-27 | 3673 |  | 68907 | A | DONE | 3 | S-M |  | SPH SURGERY 6240039 | flex | 2025-06-24 | Z | 2025-06-16 | 60 | 0 | 0 |  | 0 | 160 |  | OA outs |  | 8
2025-06-27 | 3676 |  | 68147 | A | DONE | 3 | S |  | SPH SURGERY 6240039 |  | 2025-06-24 | Z | 2025-06-17 | 40 | 0 | 30 | F | 0 | 100 |  | RA drops OR 10 |  | 7
2025-06-27 | 3681 |  | 68148 | A | DONE | 2 | S |  | SPH SURGERY 6240039 | flex | 2025-06-24 | Z | 2025-06-18 | 30 | 0 | 0 |  | 0 | 50 |  | OR 10 SA outs |  | 6
2025-06-24 | 4070 | sp | 73964 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | paint | 2025-06-17 | Z | 2025-06-10 | 20 | 20 | 0 |  | 0 | 30 |  | Kitchenette |  | 7
2025-06-27 | 4071 |  | 73965 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | paint | 2025-06-24 | Z | 2025-06-11 | 20 | 0 | 0 |  | 0 | 20 |  | 145 Pipe cover |  | 13
2025-06-25 | 4072 |  | 73968 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | bird s. | 2025-06-24 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 8
2025-06-25 | 4073 |  | 73969 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-06-24 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 20 |  | 103 |  | 8
2025-06-27 | 4074 |  | 73970 - 73972 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | paint | 2025-06-24 | Z | 2025-06-16 | 20 | 0 | 0 |  | 10 | 30 |  | Pipe Cover |  | 8
2025-06-23 | 813 |  | 73602 - 73603 | A | DONE | 168 | L | neal | SW HEALTH OR 5 6250004 | 3" DW | 2025-06-16 | Z | 2025-05-22 | 3290 | 0 | 900 | F | 2070 | 8620 |  | RA |  | 25
2025-06-23 | 814 |  | 73604 - 73605 | A | DONE | 133 | L | neal | SW HEALTH OR 5 6250004 | 3" DW | 2025-06-16 | Z | 2025-05-22 | 2830 | 0 | 490 | F | 1390 | 6000 |  | SA |  | 25
2025-06-24 | 3760 |  | L5DL-SAT 571 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-06-18 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 15
2025-06-24 | 3761 |  | L5DL-SAT 575 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-06-18 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 15
2025-06-24 | 3762 |  | L5DL-SAT 580 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-06-18 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 15
2025-06-24 | 3763 |  | L5DL-SAT 581 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-06-18 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 15
2025-06-24 | 3764 |  | L5DL-SAT 583 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-06-18 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 15
2025-06-24 | 3765 |  | L5DL-SAT 585 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-06-18 | Z | 2025-06-03 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 15
2025-06-24 | 3768 |  | L6-OA LOUVER CONN. | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-06-25 | Z | 2025-06-23 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 2
2025-06-24 | 2000 |  | EL.SHAFT-SAMP 1 | A | DONE | 12 | M |  | UW-LEVY HALL 6230028 | 1" liner , partial | 2025-06-16 | Z | 2025-05-30 | 70 | 0 | 230 | F | 270 | 590 |  |  |  | 17
2025-06-23 | 2001 |  | EL.SHAFT-SAMP 2 | A | DONE | 21 | M |  | UW-LEVY HALL 6230028 | partial | 2025-06-16 | Z | 2025-05-30 | 120 | 0 | 390 | F | 0 | 760 |  |  |  | 17
2025-06-24 | 2002 |  | EL.SHAFT-RAMP 1 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 | partial | 2025-06-16 | Z | 2025-05-30 | 90 | 0 | 350 | F | 0 | 620 |  |  |  | 17
2025-06-24 | 2003 |  | EL.SHAFT-RAMP 2 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 | 1" liner , partial | 2025-06-16 | Z | 2025-05-30 | 70 | 0 | 150 | F | 200 | 440 |  |  |  | 17
2025-06-23 | 2004 |  | EL.SHAFT-EAMP 1 | A | DONE | 13 | S-M |  | UW-LEVY HALL 6230028 | partial | 2025-06-16 | Z | 2025-05-30 | 120 | 0 | 200 | F | 0 | 400 |  |  |  | 17
2025-06-24 | 2005 |  | EL.SHAFT-EAMP 2 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | 1" liner , partial | 2025-06-16 | Z | 2025-05-30 | 70 | 0 | 200 | F | 240 | 510 |  |  |  | 17
2025-06-26 | 2006 |  | 83821 - 83822 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-06-23 | Z | 2025-06-04 | 90 | 70 | 60 | F | 20 | 250 |  | L1-SAMP 3 , RAMP 7 |  | 19
2025-06-26 | 2008 | sp | 83824 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-06-09 | 0 | 20 | 0 |  | 0 | 20 |  | SAT-3-3-13 |  | 14
2025-06-26 | 2009 | sp | 83825 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-06-10 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-3-3-14 |  | 13
2025-06-26 | 2010 |  | 83826 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-06-10 | 50 | 0 | 0 |  | 0 | 140 |  | L1-RAMP |  | 13
2025-06-27 | 2011 |  | 83827 | A | DONE | 17 | S-M |  | UW-LEVY HALL 6230028 | 1" DW | 2025-06-23 | Z | 2025-06-10 | 310 | 0 | 0 |  | 130 | 310 |  | L1-RAMP 6 |  | 13
2025-06-27 | 3731 | bth | L5-SAMP 1 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-05-15 | 260 | 100 | 80 | F | 0 | 850 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-26 | 3732 | bth | L5-SAMP 2 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-05-15 | 70 | 180 | 80 | F | 0 | 380 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-26 | 3733 | sp | L5-SAMP 3 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-05-15 | 30 | 190 | 0 |  | 0 | 230 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-26 | 3734 | bth | L5-SAMP 4 | A | DONE | 22 | M |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-05-15 | 270 | 150 | 120 | F | 0 | 650 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-26 | 3735 | bth | L5-SAMP 5 | A | DONE | 16 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-05-15 | 140 | 50 | 190 | F | 0 | 480 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-27 | 3736 | bth | L5-RAMP 11 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-06-23 | Z | 2025-05-15 | 260 | 40 | 70 | F | 50 | 440 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-26 | 3737 | bth | L5-RAMP 12 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-06-23 | Z | 2025-05-15 | 70 | 20 | 100 | F | 30 | 240 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-26 | 3738 | bth | L5-RAMP 13 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-06-23 | Z | 2025-05-15 | 120 | 80 | 70 | F | 70 | 300 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-26 | 3739 | bth | L5-RAMP 14 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-06-23 | Z | 2025-05-15 | 130 | 20 | 90 | F | 60 | 300 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-27 | 3740 | bth | L5-RAMP 15 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-06-23 | Z | 2025-05-15 | 60 | 90 | 0 |  | 40 | 170 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-27 | 3741 | bth | L5-RAMP 16 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-06-23 | Z | 2025-05-15 | 60 | 50 | 0 |  | 40 | 130 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-26 | 3742 | bth | L5-RAMP 1 | A | DONE | 26 | M |  | UW-LEVY HALL 6230028 |  | 2025-06-23 | Z | 2025-05-15 | 270 | 20 | 340 | F | 20 | 920 |  |  |  | 39 | 2025-06-03 | 2025-06-16
2025-06-27 | 3981 |  | 74630 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-25 | Z | 2025-06-16 | 50 | 0 | 0 |  | 0 | 100 |  | AHU-2 |  | 9
2025-06-23 | 1868 |  | 69547 - 69549 | A | DONE | 13 | S-M |  | UWP-FH 6240021 |  | 2025-06-26 | Z | 2025-06-05 | 220 | 0 | 90 | F | 0 | 390 |  | 1st Floor SA |  | 21
2025-06-27 | 1869 | sp | 69550 , 75701 | A | DONE | 14 | S-M |  | UWP-FH 6240021 |  | 2025-06-26 | Z | 2025-06-06 | 110 | 220 | 0 |  | 0 | 330 |  | 1st floor SA |  | 20
2025-06-23 | 1870 |  | 75702 | A | DONE | 2 | S |  | UWP-FH 6240021 | VD | 2025-06-26 | Z | 2025-06-06 | 20 | 0 | 0 |  | 0 | 30 |  | 1st floor SA |  | 20
2025-06-24 | 1871 |  | 75704 - 75706 | A | DONE | 7 | S-M |  | UWP-FH 6240021 | flex , coil | 2025-06-19 | Z | 2025-06-16 | 170 | 0 | 0 |  | 0 | 230 |  | LL |  | 3
2025-06-23 | 1872 | sp | 75707 | A | DONE | 4 | S |  | UWP-FH 6240021 |  | 2025-06-19 | Z | 2025-06-16 | 20 | 60 | 0 |  | 0 | 60 |  | LL |  | 3
2025-06-24 | 1873 |  | 75708 | A | DONE | 4 | S |  | UWP-FH 6240021 |  | 2025-06-19 | Z | 2025-06-16 | 20 | 0 | 60 | F | 0 | 120 |  | Gym SA |  | 3
2025-06-27 | 2865 | bth | 84859 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2025-06-24 | Z | 2025-06-12 | 40 | 20 | 0 |  | 0 | 50 |  | 3RD FL FUME HOOD |  | 12
2025-06-27 | 2866 |  | 84860 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-06-24 | Z | 2025-06-12 | 30 | 0 | 0 |  | 20 | 40 |  | 3rd FL Transfer |  | 12
2025-06-24 | 4420 |  | 70188 | A | DONE | n/a | S-M |  | UWSP CHAMPION HALL 6240008 | bird s. | 2025-06-17 | Z | 2025-06-04 | 0 | 0 | 0 |  | 0 | 0 |  | Intake Hood / Birdscreen |  | 13
2025-06-24 | 4421 |  | 58831 | A | DONE | 2 | S | ss | UWSP CHAMPION HALL 6240008 |  | 2025-06-24 | Z | 2025-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2025-06-25 | 3079 | sp | 57646 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-06-19 | Z | 2025-06-11 | 30 | 20 | 0 |  | 0 | 50 |  | 7B Misc |  | 8
2025-06-25 | 3562 |  | 84996 | A | DONE | 34 | M |  | UW-WHITEWATER ML 6250001 |  | 2025-06-20 | Z | 2025-06-09 | 190 | 0 | 640 | F | 0 | 1380 |  | SA Main |  | 11
2025-06-26 | 3563 |  | 84997 - 84999 | A | DONE | 18 | S-M |  | UW-WHITEWATER ML 6250001 | reheat coil's | 2025-06-20 | Z | 2025-06-09 | 250 | 0 | 200 | F | 0 | 570 |  | RHC-2054B , 2054-2 , 3 |  | 11
2025-06-24 | 3564 |  | 85000 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-06-20 | Z | 2025-06-09 | 20 | 0 | 0 |  | 20 | 20 |  | RHC-37 |  | 11
2025-06-26 | 3565 |  | 85001 | A | DONE | 6 | S-M |  | UW-WHITEWATER ML 6250001 | reheat coil | 2025-06-20 | Z | 2025-06-09 | 90 | 0 | 40 | F | 0 | 190 |  | RHC-2054A |  | 11
2025-06-25 | 3566 | sp | 85002 | A | DONE | 6 | S-M |  | UW-WHITEWATER ML 6250001 | reheat coil | 2025-06-20 | Z | 2025-06-09 | 20 | 130 | 0 |  | 0 | 180 |  | Hallway spiral |  | 11
2025-06-24 | 3567 |  | 85003 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-06-20 | Z | 2025-06-09 | 20 | 0 | 0 |  | 0 | 30 |  | RHC-2054-1 |  | 11
2025-06-26 | 3571 |  | 85008 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 | reheat coil | 2025-06-20 | Z | 2025-06-09 | 20 | 0 | 20 | F | 0 | 60 |  | RHC-H2059 |  | 11
2025-06-25 | 3572 |  | 85009 | A | DONE | 6 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-06-20 | Z | 2025-06-09 | 100 | 0 | 50 | F | 0 | 250 |  | Hallway RA |  | 11
2025-06-26 | 3574 |  | 85012 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-06-20 | Z | 2025-06-16 | 30 | 0 | 0 |  | 0 | 50 |  | RHC-2054-1 |  | 4
2025-06-23 | 3859 |  | 74774 | A | DONE | 2 | S-M | neal | UW-WITTE HALL 6250003 |  | 2025-06-25 | Z | 2025-06-20 | 30 | 0 | 0 |  | 0 | 30 |  | Hangers |  | 5
2025-06-23 | 3855d |  | 74766 | A | DONE | 7 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner , AB damper | 2025-06-25 | Z | 2025-05-31 | 160 | 0 | 0 |  | 110 | 240 |  | Damper piece |  | 25
2025-06-25 | 1907 |  | 83451 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex, 1" liner | 2025-06-20 | Z | 2025-06-05 | 50 | 0 | 0 |  | 40 | 70 |  | 1st E-HP-2-123 RA |  | 15
2025-06-26 | 2712 |  | 76105 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-06-19 | Z | 2025-06-12 | 40 | 0 | 0 |  | 0 | 60 |  | SOFFIT |  | 7
[6 empty] | 1690 | [13 empty] | 57190 |  |  |  | 17020 | 29.76%
WEEK OF 6-30-2025
2025-07-01 | 296 |  | 85241 - 85242 | A | DONE | 18 | M-L |  | 121 E. WILSON 6230024 | exp. Metal | 2025-06-30 | Z | 2025-06-16 | 430 | 0 | 0 |  | 0 | 1250 |  |  |  | 14
2025-07-01 | 297 |  | 85243 - 85244 | A | DONE | 12 | S |  | 121 E. WILSON 6230024 | exp. Metal | 2025-06-30 | Z | 2025-06-16 | 290 | 0 | 0 |  | 0 | 900 |  |  |  | 14
2025-07-02 | 1030 |  | 85248 | A | DONE | 8 | S |  | 121 E. WILSON 6230024 | bird s. | 2025-06-30 | Z | 2025-06-23 | 190 | 0 | 0 |  | 0 | 670 |  | PL-1 Intake |  | 7
2025-07-02 | 1031 |  | 85249 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | bird s. | 2025-06-30 | Z | 2025-06-23 | 20 | 0 | 0 |  | 0 | 20 |  | PH Boiler Intake |  | 7
2025-07-01 | 3515 | w | NO.1 | A | DONE | 4 | S |  | DELLSHIRE 6240017 | bird s. | 2025-06-30 | Z | 2025-06-17 | 60 | 30 | 0 |  | 0 | 140 |  | EA Roof Caps |  | 13
2025-07-01 | 1610 |  | 73904 | A | DONE | 3 | S-M |  | DOC JDC 6240023 |  | 2025-06-25 | Z | 2025-06-18 | 70 | 0 | 0 |  | 0 | 150 |  | Sec. Sleeves PH |  | 7
2025-07-02 | 1611 |  | 73902 , 73905 | A | DONE | 10 | S-M |  | DOC JDC 6240023 |  | 2025-06-25 | Z | 2025-06-18 | 240 | 0 | 0 |  | 0 | 390 |  | Sec. Bar Sleeves |  | 7
2025-06-30 | 1613 | w | 97713 | A | DONE | 4 | S |  | DOC JDC 6240023 | 1" DB | 2025-06-25 | Z | 2025-06-19 | 70 | 0 | 0 |  | 30 | 170 |  | Curb ext. |  | 6
2025-06-30 | 2559 | bth | 84725 - 84727 | A | DONE | 6 | S-M |  | LABCORP 4259999 |  | 2025-06-26 | Z | 2025-06-23 | 100 | 20 | 20 | F | 0 | 140 |  | EB3370 |  | 3
2025-06-30 | 1718 |  | 74224 - 74225 | A | DONE | 4 | S |  | MCDS 6250005 |  | 2025-06-27 | Z | 2025-06-17 | 50 | 0 | 50 | F | 0 | 110 |  | Misc |  | 10
2025-06-30 | 1723 |  | 74236 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-06-27 | Z | 2025-06-27 | 20 | 0 | 0 |  | 0 | 20 |  | Furnace |  | 0
2025-07-01 | 1557 |  | EA-L2A-05 | A | DONE | 8 | S |  | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-04-10 | 180 | 20 | 0 |  | 0 | 280 |  |  |  | 75 | 2025-06-12
2025-07-01 | 1559 | bth | EA-L2A-07 | A | DONE | 3 | S |  | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-04-10 | 30 | 40 | 0 |  | 0 | 70 |  |  |  | 75 | 2025-06-12
2025-06-30 | 1560 |  | OA-L2A-01 | A | DONE | 45 | M-L |  | MONROE HS 6240018 | CD's | 2025-06-24 | Z | 2025-04-10 | 1010 | 0 | 110 | F | 0 | 1870 |  |  |  | 75 | 2025-06-12
2025-07-01 | 1561 |  | RA-L2A-01 | A | DONE | 54 | L |  | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-04-10 | 1150 | 0 | 190 | F | 1130 | 3100 |  |  |  | 75 | 2025-06-12
2025-07-01 | 1562 |  | RA-L2A-02 | A | DONE | 24 | M |  | MONROE HS 6240018 | VD , CD's , 1" liner | 2025-06-24 | Z | 2025-04-10 | 530 | 0 | 50 | F | 310 | 760 |  |  |  | 75 | 2025-06-12
2025-07-01 | 1573 | bth | SALP-L2A-11 | A | DONE | 7 | S |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-04-10 | 40 | 0 | 120 | F | 120 | 220 |  |  |  | 75 | 2025-06-12
2025-06-30 | 3003 |  | 83612 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-06-19 | 50 | 0 | 0 |  | 0 | 130 |  | Temp air |  | 5
2025-07-02 | 3832 |  | TA-L2A-01 | A | DONE | 6 | S |  | MONROE HS 6240018 | 1" liner | 2025-06-24 | Z | 2025-06-06 | 130 | 0 | 0 |  | 130 | 170 |  |  |  | 18 | 2025-06-17
2025-07-01 | 4222 |  | 73577 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2025-06-30 | Z | 2025-06-18 | 20 | 0 | 0 |  | 0 | 30 |  | V-8 HP |  | 12
2025-07-01 | 4223 | sp | 81633 | A | DONE | 6 | S-M |  | PECATONICA HS 6240005 |  | 2025-06-30 | Z | 2025-06-25 | 0 | 140 | 0 |  | 0 | 120 |  | Attic -C |  | 5
2025-06-30 | 1833 |  | 70869 | A | DONE | 3 | S-M |  | PEWAUKEE HS 6240030 | 2" liner | 2025-06-25 | Z | 2025-06-16 | 40 | 0 | 0 |  | 30 | 110 |  | Misc |  | 9
2025-07-03 | 1834 |  | DH-1 THRU 3 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-07-01 | Z | 2025-06-17 | 40 | 0 | 0 |  | 0 | 110 |  | Hangers |  | 14 | 2025-07-02
2025-07-01 | 1835 |  | 74115 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | CD , 1" liner | 2025-06-25 | Z | 2025-06-19 | 30 | 0 | 0 |  | 10 | 80 |  | Outs |  | 6
2025-06-30 | 1836 |  | 70872-73 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | 1", 2" liner | 2025-06-25 | Z | 2025-06-20 | 50 | 0 | 0 |  | 40 | 170 |  | RAMP/SAMP-1 |  | 5
2025-07-02 | 1839 |  | 70874 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | CD | 2025-07-01 | Z | 2025-06-24 | 20 | 0 | 0 |  | 20 | 30 |  | RE 1-B Out |  | 7 | 2025-07-02
2025-07-03 | 1841 |  | 74157 | A | DONE | 3 | S |  | PEWAUKEE HS 6240030 |  | 2025-07-01 | Z | 2025-06-27 | 60 | 0 | 0 |  | 0 | 80 |  | Existing RTU tie in |  | 4 | 2025-07-02
2025-07-01 | 1375 |  | 23000 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-06-26 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 30 |  | Cap |  | 10
2025-07-03 | 4554 | sp | 76159 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-03 | 20 | 20 | 0 |  | 0 | 40 |  | Testing Reducers |  | 7
2025-07-03 | 4555 |  | 76160 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-03 | 20 | 0 | 0 |  | 0 | 20 |  | Roof Cap |  | 7
2025-07-01 | 1968 |  | 75785 - 75788 | A | DONE | 11 | S-M |  | REEDSBURG HS 6250010 | 1" liner | 2025-06-25 | Z | 2025-06-10 | 230 | 0 | 40 | F | 190 | 310 |  | TA |  | 15
2025-07-01 | 1969 |  | 75789 - 75791 | A | DONE | 16 | S-M | pt.neal | REEDSBURG HS 6250010 | paint , 1" liner | 2025-06-25 | Z | 2025-06-10 | 400 | 0 | 0 |  | 350 | 590 |  | TA |  | 15
2025-07-01 | 1970 |  | 75792 - 75793 | A | DONE | 13 | S-M |  | REEDSBURG HS 6250010 | 1" liner | 2025-06-25 | Z | 2025-06-10 | 220 | 0 | 90 | F | 270 | 470 |  | TA |  | 15
2025-06-30 | 1972 | sp | 75795 - 75796 | A | DONE | 4 | S-M |  | REEDSBURG HS 6250010 |  | 2025-06-25 | Z | 2025-06-16 | 40 | 40 | 0 |  | 0 | 80 |  | HP SA |  | 9
2025-07-02 | 1975 | bth | 75798 | A | DONE | 7 | S-M | pt.neal | REEDSBURG HS 6250010 |  | 2025-07-01 | Z | 2025-06-24 | 20 | 150 | 0 |  | 0 | 160 |  | V-208 , 209 LPSA |  | 7 | 2025-07-02
2025-07-02 | 1976 |  | 75799 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-07-01 | Z | 2025-06-24 | 30 | 0 | 0 |  | 0 | 50 |  | FD-6 relief |  | 7 | 2025-07-02
2025-07-02 | 1978 | sp | 75803 | A | DONE | 2 | S | pt.neal | REEDSBURG HS 6250010 |  | 2025-07-01 | Z | 2025-06-25 | 20 | 0 | 0 |  | 0 | 30 |  | V-202 LPSA |  | 6 | 2025-07-02
2025-07-02 | 1979 |  | 75805 - 75806 | A | DONE | 2 | S-M |  | REEDSBURG HS 6250010 |  | 2025-07-01 | Z | 2025-06-26 | 40 | 0 | 0 |  | 0 | 60 |  | EA Adapters |  | 5 | 2025-07-02
2025-07-02 | 1980 |  | 75808 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-07-01 | Z | 2025-06-26 | 20 | 0 | 0 |  | 0 | 20 |  | LPS V-205 |  | 5 | 2025-07-02
2025-07-01 | 1981 |  | 75809 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-07-02 | Z | 2025-07-01 | 20 | 0 | 0 |  | 0 | 30 |  | V-212 LPS |  | 1
2025-07-01 | 3678 | sp | 68911 | A | DONE | 3 | S |  | SPH SURGERY 6240039 |  | 2025-07-01 | Z | 2025-06-18 | 0 | 60 | 0 |  | 0 | 50 |  | PH-RAV 12-11 |  | 13 | 2025-07-07
2025-07-03 | 3679 |  | 68912 - 68913 | A | DONE | 7 | S |  | SPH SURGERY 6240039 |  | 2025-07-01 | Z | 2025-06-18 | 160 | 0 | 0 |  | 0 | 330 |  | OA / EA EC's |  | 13 | 2025-07-07
2025-06-30 | 3682 |  | 68149 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-07-01 | Z | 2025-06-30 | 20 | 0 | 0 |  | 0 | 30 |  | L1-A-RAV-12-4 |  | 1
2025-07-02 | 4075 |  | 73974 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-07-02 | Z | 2025-06-19 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 13
2025-07-02 | 830 | bth | 73629 - 73632 | A | DONE | 12 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-06-30 | Z | 2025-06-06 | 270 | 30 | 0 |  | 0 | 440 |  | SA Sterile |  | 24
2025-07-01 | 831 |  | 73633 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 | VD | 2025-06-30 | Z | 2025-06-06 | 20 | 0 | 0 |  | 0 | 20 |  | RA Sanitary |  | 24
2025-07-03 | 832 |  | 73634 | A | DONE | 9 | S |  | SW HEALTH OR 5 6250004 |  | 2025-07-01 | Z | 2025-06-16 | 140 | 0 | 70 | F | 0 | 430 |  | 1st Floor SA |  | 15 | 2025-07-07
2025-07-03 | 835 |  | 73642 | A | DONE | 9 | S |  | SW HEALTH OR 5 6250004 |  | 2025-07-01 | Z | 2025-06-16 | 140 | 0 | 70 | F | 0 | 440 |  | 1st Floor RA |  | 15 | 2025-07-07
2025-07-03 | 836 |  | 73643 | A | DONE | 13 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-07-08 | Z | 2025-06-16 | 250 | 0 | 60 | F | 0 | 510 |  | 1st Floor RA |  | 22
2025-07-03 | 837 |  | 73644 - 73646 | A | DONE | 22 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-07-08 | Z | 2025-06-16 | 220 | 0 | 310 | F | 0 | 1060 |  | 1st Floor RA |  | 22
2025-07-03 | 838 |  | 73647 | A | DONE | 3 | S |  | SW HEALTH OR 5 6250004 |  | 2025-07-08 | Z | 2025-06-16 | 70 | 0 | 0 |  | 0 | 90 |  | VAV RA-02 HP |  | 22
2025-07-02 | 839 | sp | 73648 | A | DONE | 3 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-07-08 | Z | 2025-06-16 | 20 | 50 | 0 |  | 0 | 60 |  | Misc |  | 22
2025-07-02 | 840 |  | 73649 | A | DONE | 4 | S | neal | SW HEALTH OR 5 6250004 |  | 2025-06-30 | Z | 2025-06-16 | 30 | 0 | 60 | F | 0 | 100 |  | Stack |  | 14
2025-07-01 | 841 |  | 73650 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 | VD's | 2025-06-30 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 20 |  | EF |  | 14
2025-07-03 | 842 | w | 73578 | A | DONE | 10 | S-M |  | SW HEALTH OR 5 6250004 | 3" DW | 2025-06-30 | Z | 2025-06-18 | 240 | 0 | 0 |  | 120 | 520 |  | OR Drop curb cap |  | 12
2025-06-30 | 3766 | w | 69146 | A | DONE | 3 | S | ss | UW-AVRL 6240038 |  | 2025-06-25 | Z | 2025-06-16 | 70 | 0 | 0 |  | 0 | 150 |  | Flashing |  | 9
2025-07-01 | 3767 |  | 69147 , DH-UW123, 124 | A | DONE | 2 | S-M |  | UW-AVRL 6240038 |  | 2025-06-25 | Z | 2025-06-16 | 40 | 0 | 0 |  | 0 | 100 |  | Riser Clamps |  | 9
2025-07-01 | 3769 | w | 69053 | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-06-26 | Z | 2025-06-24 | 30 | 0 | 0 |  | 0 | 60 |  | EA Fan |  | 2
2025-07-02 | 2014 |  | 96963 | A | DONE | 2 | S |  | UW-LEVY HALL 8230028 |  | 2025-07-01 | Z | 2025-06-17 | 20 | 0 | 0 |  | 0 | 60 |  | Flat stock |  | 14
2025-07-01 | 3977 |  | 74623 - 74624 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2025-06-25 | Z | 2025-06-10 | 70 | 0 | 0 |  | 0 | 100 |  | Basement RA |  | 15
2025-07-01 | 3978 |  | 74625 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-25 | Z | 2025-06-10 | 130 | 0 | 0 |  | 0 | 290 |  | AHU-2 Relief |  | 15
2025-06-30 | 3979 | w | 38268 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 | 1"DB | 2025-06-25 | Z | 2025-06-12 | 60 | 0 | 0 |  | 60 | 170 |  | CURB CAP |  | 13
2025-07-01 | 3980 | bth | 74626-29 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2025-06-25 | Z | 2025-06-12 | 70 | 20 | 0 |  | 0 | 90 |  | MISC |  | 13
2025-07-01 | 3982 |  | 74631 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-25 | Z | 2025-06-16 | 30 | 0 | 0 |  | 0 | 40 |  | 3rd SA |  | 9
2025-07-03 | 3983 |  | 74632 - 74633 | A | DONE | 28 | M |  | UWL-GRAFF 6230017 |  | 2025-07-01 | Z | 2025-06-18 | 550 | 0 | 150 | F | 0 | 1170 |  | AHU-1,3 OA |  | 13 | 2025-07-07
2025-07-02 | 3984 |  | 74634 - 74635 | A | DONE | 10 | M |  | UWL-GRAFF 6230017 |  | 2025-07-01 | Z | 2025-06-18 | 160 | 0 | 70 | F | 0 | 370 |  | AHU-2 OA |  | 13 | 2025-07-07
2025-06-30 | 3985 | sp | 74644 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-06-25 | Z | 2025-06-19 | 20 | 20 | 0 |  | 0 | 40 |  | SAT-3-3-2 |  | 6
2025-07-03 | 3986 |  | 74641-43 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-07-01 | Z | 2025-06-19 | 50 | 0 | 0 |  | 0 | 120 |  |  |  | 12 | 2025-07-07
2025-07-02 | 3987 |  | 74645 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-07-01 | Z | 2025-06-24 | 20 | 0 | 0 |  | 0 | 30 |  | Rm 118 |  | 7 | 2025-07-07
2025-07-02 | 3988 |  | 82164 - 82165 | A | DONE | 15 | S-M |  | UWL-GRAFF 6230017 |  | 2025-07-01 | Z | 2025-06-24 | 370 | 0 | 0 |  | 0 | 830 |  | AHU-1 |  | 7 | 2025-07-07
2025-07-02 | 3989 |  | 82168 - 82170 | A | DONE | 21 | S-M |  | UWL-GRAFF 6230017 |  | 2025-07-01 | Z | 2025-06-24 | 520 | 0 | 0 |  | 0 | 1230 |  | AHU-1 |  | 7 | 2025-07-07
2025-07-01 | 3990 | sp | 82171 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-07-01 | Z | 2025-06-25 | 0 | 40 | 0 |  | 0 | 50 |  | 1st SA |  | 6
2025-07-02 | 3991 |  | 82172 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-07-01 | Z | 2025-06-25 | 20 | 0 | 0 |  | 0 | 40 |  | 2nd RA |  | 6
2025-07-02 | 1874 |  | 75709 | A | DONE | 3 | S |  | UWP-FH 6240021 | flex | 2025-06-26 | Z | 2025-06-17 | 70 | 0 | 0 |  | 0 | 100 |  | FCU-13 LL |  | 9
2025-07-02 | 1875 |  | 75710 | A | DONE | 4 | S-M |  | UWP-FH 6240021 | flex | 2025-06-26 | Z | 2025-06-18 | 90 | 0 | 0 |  | 0 | 120 |  | 2nd Floor DOAS-2 SA |  | 8
2025-07-02 | 1878 |  | 75713 | A | DONE | 2 | S |  | UWP-FH 6240021 |  | 2025-07-01 | Z | 2025-06-25 | 50 | 0 | 0 |  | 0 | 170 |  | AHU-1 |  | 6 | 2025-07-03
2025-07-01 | 2867 |  | 84861 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2025-07-01 | Z | 2025-06-17 | 20 | 0 | 0 |  | 20 | 30 |  | 2nd Floor TA |  | 14
2025-07-03 | 2868 |  | 84863 - 84864 | A | DONE | 6 | S-M |  | UWRF 6230010 |  | 2025-07-01 | Z | 2025-06-18 | 130 | 0 | 0 |  | 0 | 340 |  | PRV Station Louver tie in |  | 13
2025-07-02 | 3082 |  | 57649 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-07-03 | Z | 2025-06-26 | 20 | 0 | 0 |  | 0 | 20 |  | ERG Rm |  | 7
2025-07-01 | 3575 |  | 85013 | A | DONE | 4 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-06-27 | Z | 2025-06-16 | 80 | 0 | 0 |  | 0 | 100 |  | Flashing |  | 11
2025-06-30 | 3576 |  | 85014 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-06-27 | Z | 2025-06-20 | 20 | 0 | 0 |  | 0 | 20 |  | Curb Inserts |  | 7
2025-06-30 | 3577 |  | 85015 | A | DONE | 2 | S |  | UW-WHITEWATER MP 6250001 |  | 2025-06-27 | Z | 2025-06-27 | 20 | 0 | 0 |  | 0 | 20 |  | Hallway RA |  | 0
2025-07-02 | 3858 |  | 74769 , 76772 - 74773 | A | DONE | 20 | S-M | neal | UW-WITTE HALL 6250003 | VD's | 2025-07-01 | Z | 2025-06-17 | 500 | 0 | 0 |  | 460 | 650 |  | Existing tie in |  | 14
2025-07-02 | 3860 |  | 74775 | A | DONE | 3 | S | neal | UW-WITTE HALL 6250003 |  | 2025-07-01 | Z | 2025-06-23 | 70 | 0 | 0 |  | 70 | 100 |  | Outs |  | 8
2025-07-02 | 3862 |  | 74777 | A | DONE | 2 | S | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-07-01 | Z | 2025-06-25 | 20 | 0 | 0 |  | 20 | 20 |  | Outs |  | 6
2025-07-02 | 3863 |  | 74778 | A | DONE | 2 | S | neal | UW-WITTE HALL 6250003 |  | 2025-07-01 | Z | 2025-06-26 | 20 | 0 | 0 |  | 20 | 30 |  | 7th and 8th Floor |  | 5
2025-07-02 | 3855e |  | 74766 | A | DONE | 7 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner , AB damper | 2025-07-01 | Z | 2025-05-31 | 160 | 0 | 0 |  | 110 | 240 |  | Damper piece |  | 31
2025-07-01 | 1409 | sp | L01_D_SOA_011 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 20 | 160 | 0 |  | 0 | 200 |  |  |  | 37
2025-07-01 | 1410 | sp | L01_D_SOA_012 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 20 | 100 | 0 |  | 0 | 110 |  |  |  | 37
2025-07-01 | 1418 | sp | L01_D_EAD_008 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 20 | 130 | 0 |  | 0 | 140 |  |  |  | 37
2025-07-03 | 1423 |  | L02_C_SOA_001 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1424 |  | L02_C_SOA_002 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1425 |  | L02_C_SOA_003 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1426 |  | L02_C_SOA_004 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1427 |  | L02_C_SOA_005 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1428 |  | L02_C_SOA_006 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1429 |  | L02_C_SOA_007 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1430 |  | L02_C_SOA_008 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1431 |  | L02_C_SOA_009 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1432 |  | L02_C_SAMP_001 | delete |  | n/a | M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1433 |  | L02_C_SAMP_002 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1434 |  | L02_C_SAMP_003 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1435 |  | L02_C_SAMP_004 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1436 |  | L02_C_SAMP_005 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1437 |  | L02_C_SAMP_006 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1438 |  | L02_C_SAMP_007 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1439 |  | L02_C_SAMP_008 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1440 |  | L02_C_SAMP_009 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1441 |  | L02_C_SAMP_010 | delete |  | n/a | M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1442 |  | L02_C_SAMP_011 | delete |  | n/a | M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1443 |  | L02_C_SAMP_012 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1444 |  | L02_C_SALP_001 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1445 |  | L02_C_SALP_002 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1446 |  | L02_C_SALP_003 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1447 |  | L02_C_SALP_004 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1448 |  | L02_C_SALP_005 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1449 |  | L02_C_SALP_006 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1450 |  | L02_C_SALP_007 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1451 |  | L02_C_SALP_008 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1452 |  | L02_C_SALP_009 | delete |  | n/a | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1453 |  | L02_C_EAD_001 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1454 |  | L02_C_EAD_002 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1455 |  | L02_C_EAD_003 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1456 |  | L02_C_EAD_004 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1457 |  | L02_C_EAD_005 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1458 |  | L02_C_EAD_006 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1459 |  | L02_C_EAD_007 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1460 |  | L02_C_EAD_008 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1461 |  | L02_C_RAD_001 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1462 |  | L02_C_RAD_002 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1463 |  | L02_C_RAD_003 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1464 |  | L02_C_RAD_004 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1465 |  | L02_C_RAD_005 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1466 |  | L02_C_RAD_006 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1467 |  | L02_C_RAD_007 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1468 |  | L02_C_RAD_008 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-03 | 1469 |  | L02_C_RAD_009 | delete |  | n/a | S |  | WAUNAKEE MS 6230013 |  | 2025-07-16 | Z | 2025-05-21 | 0 | 0 | 0 |  | 0 | 0 |  | Greater WI |  | 56
2025-07-01 | 1912 | sp | 79883 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-06-16 | 20 | 70 | 0 |  | 0 | 90 |  | PRV-7 |  | 9
2025-07-01 | 1920 |  | 79888 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-27 | 120 | 0 | 0 |  | 0 | 200 |  | Flashing |  | 6
2025-06-30 | 2713 |  | LOUVER CONNECTION | A | DONE | 2 | S-M |  | WSCC 6240006 |  | 2025-07-01 | Z | 2025-06-24 | 30 | 0 | 0 |  | 0 | 100 |  | AHU-1 |  | 7
2025-06-30 | 2714 |  | 76110 | A | DONE | 3 | S-M |  | WSCC 6240006 | bird s. | 2025-07-01 | Z | 2025-06-24 | 70 | 0 | 0 |  | 0 | 200 |  | Damper / Louver |  | 7
[6 empty] | 619 | [13 empty] | 25240 |  |  |  | 13270 | 52.58%
WEEK OF 7-7-2025
2025-07-10 | 2730 | bth | 75189-91 | A | DONE | 16 | M |  | BARTILLION 6240024 |  | 2025-07-03 | Z | 2025-06-20 | 190 | 150 | 50 | F | 50 | 540 |  | MISC |  | 13
2025-07-10 | 2731 |  | 75192 | A | DONE | 9 | S |  | BARTILLION 6240024 |  | 2025-07-03 | Z | 2025-06-23 | 0 | 0 | 220 | F | 0 | 260 |  | 1st RA Mains |  | 10
2025-07-11 | 2732 |  | 75193 | A | DONE | 6 | S-M |  | BARTILLION 6240024 | 1" liner | 2025-07-03 | Z | 2025-06-23 | 140 | 0 | 0 |  | 90 | 200 |  | 1st FD TA |  | 10
2025-07-10 | 2903 | w | 80913 | A | DONE | 2 | S |  | BROOM ST. 6240033 | paint | 2025-07-02 | Z | 2025-06-26 | 40 | 0 | 0 |  | 0 | 100 |  | Sleeves |  | 6
2025-07-07 | 238 |  | 83196 | A | DONE | 4 | S |  | COMPASS PROP. 10062536 |  | 2025-07-10 | Z | 2025-06-26 | 40 | 0 | 0 |  | 0 | 90 |  | AHU Coil |  | 14
2025-07-11 | 881 |  | 73663 | A | DONE | 24 | L |  | DELLSHIRE 6240017 | paint , 1" liner | 2025-07-07 | Z | 2025-04-21 | 600 | 0 | 0 |  | 630 | 700 |  | VTAC Plenum/slider V.1 |  | 77
2025-07-09 | 3517 |  | 73801 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-07-02 | Z | 2025-06-27 | 20 | 0 | 0 |  | 0 | 30 |  | Coor. SA Dampers |  | 5
2025-07-07 | 1612 |  | 73906 - 73907 | A | DONE | 8 | S-M |  | DOC JDC 6240023 |  | 2025-07-09 | Z | 2025-06-18 | 190 | 0 | 0 |  | 0 | 260 |  | Sec. Grille Sleeves |  | 21
2025-07-09 | 1012 |  | L2_EX MOD-1 | A | DONE | 20 | M |  | EXACT TL-5 6240014 |  | 2025-07-01 | Z | 2025-06-17 | 330 | 0 | 150 | F | 0 | 970 |  |  |  | 14
2025-07-09 | 1013 |  | L2_EX MOD-2 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2025-07-01 | Z | 2025-06-17 | 60 | 0 | 40 | F | 0 | 140 |  |  |  | 14
2025-07-08 | 1014 |  | 79050 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2025-07-01 | Z | 2025-07-01 | 20 | 0 | 20 | F | 0 | 40 |  | Spool adds |  | 0
2025-07-09 | 243 |  | 84729 | A | DONE | 2 | S |  | GLACIER CREEK 4250014 |  | 2025-07-09 | Z | 2025-07-09 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 0
2025-07-10 | 242 |  | 84728 | A | DONE | 4 | S |  | LAB CORP 10062916 |  | 2025-07-14 | Z | 2025-07-09 | 20 | 0 | 0 |  | 0 | 80 |  | Misc |  | 5
2025-07-08 | 1719 | sp | 74228 , 74231 | A | DONE | 24 | S-M |  | MCDS 6250005 |  | 2025-07-03 | Z | 2025-06-19 | 140 | 450 | 0 |  | 0 | 710 |  | F-1 SA |  | 14
2025-07-09 | 1720 |  | 74230 | A | DONE | 10 | S |  | MCDS 6250005 |  | 2025-07-03 | Z | 2025-06-19 | 30 | 0 | 70 | F | 0 | 110 |  | F-1 |  | 14
2025-07-09 | 1721 | bth | 74267-69 | A | DONE | 14 | S-M |  | MCDS 6250005 |  | 2025-07-03 | Z | 2025-06-19 | 110 | 220 | 0 |  | 0 | 350 |  | FAN 1&2 |  | 14
2025-07-09 | 1722 |  | 74232 - 74234 | A | DONE | 2 | S-M |  | MCDS 6250005 |  | 2025-07-10 | Z | 2025-06-26 | 50 | 0 | 0 |  | 0 | 80 |  | VAV-1,2 |  | 14
2025-07-08 | 1724 |  | 74235 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-07-08 | Z | 2025-07-08 | 20 | 0 | 0 |  | 20 | 30 |  | Misc |  | 0
2025-07-10 | 4500 |  | 76106 - 76108 | A | DONE | 26 | S-M |  | MONONA GROVE HS 6250016 | 1" liner | 2025-07-01 | Z | 2025-06-24 | 630 | 0 | 0 |  | 540 | 980 |  | VAV's |  | 7
2025-07-08 | 4501 | sp | 76109 | A | DONE | 3 | S |  | MONONA GROVE HS 6250016 |  | 2025-07-01 | Z | 2025-06-24 | 40 | 20 | 0 |  | 0 | 70 |  | VAV 65 |  | 7
2025-07-08 | 1553 |  | EA-L2A-01 | A | DONE | 5 | S |  | MONROE HS 6240018 | 1" liner | 2025-06-24 | Z | 2025-04-10 | 120 | 0 | 0 |  | 70 | 160 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1554 | bth | EA-L2A-02 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-06-24 | Z | 2025-04-10 | 210 | 80 | 0 |  | 50 | 380 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1555 | bth | EA-L2A-03 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-06-24 | Z | 2025-04-10 | 180 | 30 | 30 | F | 20 | 270 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1556 | bth | EA-L2A-04 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-06-24 | Z | 2025-04-10 | 150 | 60 | 60 | F | 100 | 350 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1558 | bth | EA-L2A-06 | A | DONE | 7 | S |  | MONROE HS 6240018 |  | 2025-06-24 | Z | 2025-04-10 | 100 | 30 | 30 | F | 60 | 180 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1569 | bth | SALP-L2A-07 | A | DONE | 14 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-04-10 | 130 | 60 | 160 | F | 230 | 470 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1570 | bth | SALP-L2A-08 | A | DONE | 13 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-04-10 | 60 | 100 | 150 | F | 160 | 380 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1571 | bth | SALP-L2A-09 | A | DONE | 23 | M |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-04-10 | 200 | 140 | 220 | F | 340 | 740 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1572 | bth | SALP-L2A-10 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-04-10 | 50 | 70 | 70 | F | 80 | 210 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1574 | bth | SALP-L2A-12 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-04-10 | 150 | 90 | 30 | F | 130 | 340 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1575 | bth | SALP-L2A-13 | A | DONE | 12 | M |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-04-10 | 140 | 90 | 60 | F | 130 | 340 |  |  |  | 75 | 2025-06-12
2025-07-08 | 1576 | bth | SALP-L2A-14 | A | DONE | 18 | M |  | MONROE HS 6240018 | 2" liner | 2025-06-24 | Z | 2025-04-10 | 170 | 90 | 190 | F | 280 | 590 |  |  |  | 75 | 2025-06-12
2025-07-11 | 2052 | sp | EA-L1A-05 | A | DONE | 2 | S | alum | MONROE HS 6240018 |  | 2025-07-15 | Z | 2025-06-11 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 34
2025-07-08 | 3004 | w | 85323 | A | DONE | 5 | S-M | ss | MONROE HS 6240018 |  | 2025-07-02 | Z | 2025-06-23 | 110 | 0 | 0 |  | 0 | 280 |  | Kitchen |  | 9
2025-07-09 | 3005 |  | 85324 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-07-02 | Z | 2025-06-23 | 20 | 0 | 0 |  | 0 | 20 |  | Mech Room |  | 9
2025-07-10 | 3006 |  | 85325 | A | DONE | 6 | S | neal | MONROE HS 6240018 |  | 2025-07-02 | Z | 2025-06-23 | 130 | 0 | 0 |  | 0 | 190 |  | Loading Dock |  | 9
2025-07-10 | 3007 | bth | 85326 | A | DONE | 6 | S | pt.alum | MONROE HS 6240018 | bird s. | 2025-07-02 | Z | 2025-06-23 | 50 | 80 | 0 |  | 0 | 100 |  | Misc |  | 9
2025-07-08 | 3010 |  | 85329 | A | DONE | 6 | S-M |  | MONROE HS 6240018 |  | 2025-07-08 | Z | 2025-06-26 | 150 | 0 | 0 |  | 0 | 290 |  | Flashing |  | 12
2025-07-08 | 3019 |  | RA-L1E-06 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-06-24 | Z | 2025-06-23 | 160 | 0 | 130 |  | 180 | 440 |  |  |  | 1
2025-07-11 | 3840 | sp | SAMP-L1A-02 | A | DONE | 30 | M-L |  | MONROE HS 6240018 | oval , accuflange | 2025-07-08 | Z | 2025-06-11 | 40 | 700 | 0 |  | 0 | 1320 |  |  |  | 27
2025-07-11 | 3842 | sp | SAMP-L1A-04 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | oval | 2025-07-08 | Z | 2025-06-11 | 80 | 180 | 0 |  | 0 | 290 |  |  |  | 27
2025-07-10 | 3843 | sp | SAMP-L1A-05 | A | DONE | 8 | S |  | MONROE HS 6240018 |  | 2025-07-08 | Z | 2025-06-11 | 30 | 150 | 0 |  | 0 | 200 |  |  |  | 27
2025-07-10 | 3845 | sp | SAMP-L1A-07 | A | DONE | 9 | S |  | MONROE HS 6240018 |  | 2025-07-08 | Z | 2025-06-11 | 20 | 200 | 0 |  | 0 | 200 |  |  |  | 27
2025-07-11 | 1794 |  | 69450,69504-05 | A | DONE | 19 | S-M | pt alum | ONE 09 6240037 |  | 2025-07-07 | Z | 2025-06-19 | 350 | 0 | 120 | A | 100 | 530 |  | CH-Misc |  | 18
2025-07-11 | 1795 |  | RA-L1-03 | A | DONE | 10 | S |  | ONE 09 6240037 | flex , 1" liner | 2025-07-07 | Z | 2025-06-24 | 250 | 0 | 0 |  | 0 | 350 |  |  |  | 13
2025-07-11 | 1797 |  | 79509 | A | DONE | 2 | S |  | ONE 09 6240037 |  | 2025-07-07 | Z | 2025-06-25 | 30 | 0 | 0 |  | 0 | 100 |  | MAU-1 DX COIL |  | 12
2025-07-09 | 1798 | w | 79510 | A | DONE | 2 | S | BI | ONE 09 6240037 |  | 2025-07-11 | Z | 2025-07-07 | 30 | 0 | 0 |  | 0 | 90 |  | CH PRV-1 Grease duct |  | 4
2025-07-08 | 4224 |  | 79689 | A | DONE | 6 | S-M |  | PECATONICA 6240005 | VD's | 2025-07-08 | Z | 2025-07-01 | 140 | 0 | 0 |  | 90 | 200 |  | V-27 LP |  | 7
2025-07-10 | 4227 | sp | 81638 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2025-07-21 | Z | 2025-07-03 | 20 | 20 | 0 |  | 0 | 40 |  | CE-4 |  | 18
2025-07-08 | 1837 |  | R-0,01 | A | DONE | 2 | S-M | neal | PEWAUKEE HS 6240030 |  | 2025-07-08 | Z | 2025-06-20 | 30 | 0 | 0 |  | 0 | 80 |  | HANGERS |  | 18
2025-07-08 | 1840 |  | 74117 - 74120 | A | DONE | 17 | S-M | pt.neal | PEWAUKEE HS 6240030 |  | 2025-07-08 | Z | 2025-06-26 | 410 | 0 | 0 |  | 0 | 430 |  | A-Section |  | 12
2025-07-10 | 1842 | sp | 76703 | A | DONE | 4 | S |  | PEWAUKEE HS 6240030 |  | 2025-07-16 | Z | 2025-07-03 | 20 | 80 | 0 |  | 0 | 120 |  | Dryer vent |  | 13
2025-07-09 | 1369 | sp | L02_AREA_200_RA_001 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 |  | 2025-07-01 | Z | 2025-06-11 | 20 | 140 | 0 |  | 0 | 170 |  |  |  | 20 | 2025-07-03
2025-07-09 | 1370 | sp | L02_AREA_200_RA_002 | A | DONE | 10 | S |  | PROJECT DOVE 6240041 |  | 2025-07-01 | Z | 2025-06-11 | 20 | 220 | 0 |  | 0 | 220 |  |  |  | 20 | 2025-07-03
2025-07-09 | 1372 | bth | L02_AREA_200_SALP_001 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 |  | 2025-07-01 | Z | 2025-06-11 | 20 | 20 | 140 | A | 0 | 200 |  |  |  | 20 | 2025-07-03
2025-07-09 | 1373 | sp | L02_AREA_200_SALP_002 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 |  | 2025-07-01 | Z | 2025-06-11 | 20 | 170 | 0 |  | 0 | 180 |  |  |  | 20 | 2025-07-03
2025-07-08 | 1380 |  | 55140 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-06-24 | 60 | 0 | 0 |  | 0 | 120 |  | Curb Angles |  | 16
2025-07-09 | 1392 |  | AHU_001_RAMP_001 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-07-01 | Z | 2025-07-01 | 60 | 0 | 0 |  | 0 | 90 |  |  |  | 0
2025-07-09 | 1393 |  | AHU_001_SAMP_001 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-07-01 | Z | 2025-07-01 | 80 | 0 | 0 |  | 0 | 130 |  |  |  | 0
2025-07-07 | 3045 | bth | 81845 - 81846 | A | DONE | 3 | S |  | PROMEGA BTC 6230022 |  | 2025-07-03 | Z | 2025-06-19 | 30 | 40 | 0 |  | 0 | 70 |  | VAV 9-15 , BCU D |  | 14
2025-07-07 | 3046 |  | 84286 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2025-07-08 | Z | 2025-07-07 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2025-07-07 | 945 |  | 81848 | A | DONE | 2 | S | pcd | PROMEGA FEYNMAN 6220014 |  | 2025-07-03 | Z | 2025-06-30 | 20 | 0 | 0 |  | 0 | 30 |  | EA |  | 3
2025-07-07 | 1977 |  | 75800 - 75801 | A | DONE | 8 | S-M |  | REEDSBURG HS 6250010 | 1" liner | 2025-07-01 | Z | 2025-06-24 | 200 | 0 | 0 |  | 160 | 280 |  | TA |  | 7 | 2025-07-02
2025-07-07 | 3677 |  | 68908 - 68910 | A | DONE | 15 | M |  | SPH SURGERY 6240039 |  | 2025-07-01 | Z | 2025-06-18 | 360 | 0 | 0 |  | 0 | 940 |  | AHU-12 SA |  | 13 | 2025-07-07
2025-07-07 | 3680 |  | 68914 - 68920 | A | DONE | 7 | S-M |  | SPH SURGERY 6240039 | flex | 2025-07-01 | Z | 2025-06-18 | 160 | 0 | 0 |  | 0 | 260 |  | VAV outs |  | 13 | 2025-07-07
2025-07-11 | 3684 |  | 68872 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-07-14 | Z | 2025-07-10 | 80 | 0 | 0 |  | 0 | 110 |  | 12-5.1 RAV |  | 4
2025-07-10 | 3685 | sp | 68873 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-07-14 | Z | 2025-07-10 | 0 | 50 | 0 |  | 0 | 60 |  | L1-A RAV |  | 4
2025-07-11 | 3687 |  | 84287 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-07-11 | Z | 2025-07-11 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2025-07-07 | 4076 |  | 73975 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | paint | 2025-07-02 | Z | 2025-07-02 | 20 | 0 | 0 |  | 20 | 20 |  | 1900-04-29 |  | 0
2025-07-09 | 4077 |  | 73976 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-07-10 | Z | 2025-07-09 | 20 | 0 | 0 |  | 0 | 20 |  | Kitchenette |  | 1
2025-07-08 | 236 | sp | 74273 | A | DONE | 10 | S |  | SUNSET RIDGE 2250022 |  | 2025-07-08 | Z | 2025-06-26 | 30 | 200 | 0 |  | 0 | 230 |  | SA |  | 12
2025-07-08 | 237 | w | 74274 | A | DONE | 2 | S |  | SUNSET RIDGE 2250022 | paint , 2" DB | 2025-07-08 | Z | 2025-06-26 | 30 | 0 | 0 |  | 40 | 90 |  | RA |  | 12
2025-07-09 | 500 |  | 73579 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-07-14 | Z | 2025-07-09 | 20 | 0 | 0 |  | 0 | 30 |  | Roof flat patch |  | 5
2025-07-11 | 501 |  | DH0005 - DH0006 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-07-21 | Z | 2025-07-09 | 30 | 0 | 0 |  | 0 | 90 |  | Hangers |  | 12
2025-07-10 | 502 |  | 95836 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-07-10 | Z | 2025-07-10 | 20 | 0 | 0 |  | 0 | 20 |  | Cap |  | 0
2025-07-07 | 833 |  | 73636 - 73638 | A | DONE | 31 | M |  | SW HEALTH OR 5 6250004 |  | 2025-07-08 | Z | 2025-06-16 | 320 | 0 | 440 | A | 0 | 1450 |  | 1st Floor SA |  | 22
2025-07-08 | 834 | sp | 73639 - 73641 | A | DONE | 14 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-07-08 | Z | 2025-06-16 | 160 | 170 | 0 |  | 0 | 340 |  | Misc |  | 22
2025-07-11 | 843 | sp | 75505 | A | DONE | 3 | S |  | SW HEALTH OR 5 6250004 |  | 2025-07-21 | Z | 2025-06-30 | 20 | 50 | 0 |  | 0 | 80 |  | Existing RA |  | 21
2025-07-11 | 846 | sp | 75511 - 75512 | A | DONE | 3 | S |  | SW HEALTH OR 5 6250004 |  | 2025-07-28 | Z | 2025-06-30 | 20 | 50 | 0 |  | 0 | 70 |  | Misc |  | 28 | 2025-07-21
2025-07-08 | 849 | sp | 75517 | A | DONE | 7 | S-M |  | SW HEALTH OR 5 6250004 | oval | 2025-07-08 | Z | 2025-07-02 | 50 | 120 | 0 |  | 0 | 180 |  | OR 5 RA |  | 6
2025-07-07 | 3775 | w | 61926 | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-07-08 | Z | 2025-07-02 | 20 | 0 | 0 |  | 0 | 60 |  | Roof Exh |  | 6
2025-07-10 | 3776 |  | 61930 | A | DONE | 2 | S | ss | UW-AVRL 6240038 | Foam Tape | 2025-07-16 | Z | 2025-07-07 | 20 | 0 | 0 |  | 0 | 20 |  | 5th Floor tie ins |  | 9
2025-07-10 | 2012 |  | W.SHAFT-SAMP 3 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-01 | Z | 2025-06-17 | 60 | 0 | 0 |  | 0 | 140 |  |  |  | 14
2025-07-10 | 2013 |  | W.SHAFT-RAMP 4 | A | DONE | 6 | S-M |  | UW-LEVY HALL 6230028 | VD | 2025-07-01 | Z | 2025-06-17 | 130 | 0 | 0 |  | 0 | 250 |  |  |  | 14
2025-07-07 | 2015 |  | 83829 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-01 | Z | 2025-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | Cap |  | 14
2025-07-10 | 2016 |  | 83828 | A | DONE | 4 | S-M |  | UW-LEVY HALL 6230028 | 1" DW | 2025-07-01 | Z | 2025-06-19 | 80 | 0 | 0 |  | 20 | 180 |  | Shaft -West |  | 12
2025-07-11 | 2043 |  | 83830 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-07 | Z | 2025-06-24 | 40 | 0 | 0 |  | 0 | 60 |  | L5 RAMP 9 |  | 13
2025-07-09 | 2044 |  | 83831 | A | DONE | 36 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-07 | Z | 2025-06-24 | 880 | 0 | 0 |  | 0 | 1160 |  | Misc |  | 13
2025-07-10 | 2052 |  | 83832 | A | DONE | 6 | S | pt.neal | UW-LEVY HALL 6230028 |  | 2025-07-07 | Z | 2025-06-24 | 140 | 0 | 0 |  | 0 | 140 |  | Misc |  | 13
2025-07-11 | 2000a |  | EL.SHAFT-SAMP 1 | A | DONE | 27 | M |  | UW-LEVY HALL 6230028 | 1" liner , partial | 2025-07-07 | Z | 2025-06-19 | 120 | 0 | 550 | A | 590 | 1250 |  |  |  | 18
2025-07-11 | 2001a |  | EL.SHAFT-SAMP 2 | A | DONE | 23 | M |  | UW-LEVY HALL 6230028 | partial | 2025-07-07 | Z | 2025-06-19 | 150 | 0 | 420 | A | 0 | 1040 |  |  |  | 18
2025-07-11 | 2002a |  | EL.SHAFT-RAMP 1 | A | DONE | 20 | M |  | UW-LEVY HALL 6230028 | partial | 2025-07-07 | Z | 2025-06-19 | 120 | 0 | 370 | A | 0 | 730 |  |  |  | 18
2025-07-11 | 2003a |  | EL.SHAFT-RAMP 2 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | 1" liner , partial | 2025-07-07 | Z | 2025-06-19 | 120 | 0 | 350 | A | 410 | 840 |  |  |  | 18
2025-07-11 | 2004a |  | EL.SHAFT-EAMP 1 | A | DONE | 21 | M |  | UW-LEVY HALL 6230028 | partial | 2025-07-07 | Z | 2025-06-19 | 230 | 0 | 290 | A | 0 | 660 |  |  |  | 18
2025-07-10 | 3745a |  | W.SHAFT-SAMP 1 | A | DONE | 26 | M |  | UW-LEVY HALL 6230028 | partial | 2025-07-01 | Z | 2025-06-17 | 180 | 0 | 460 | A | 0 | 1470 |  |  |  | 14
2025-07-10 | 3746a |  | W.SHAFT-SAMP 2 | A | DONE | 36 | M-L |  | UW-LEVY HALL 6230028 | 1" liner , partial | 2025-07-01 | Z | 2025-06-17 | 290 | 0 | 590 | A | 0 | 1610 |  |  |  | 14
2025-07-10 | 3747a |  | W.SHAFT-RAMP 1 | A | DONE | 26 | M |  | UW-LEVY HALL 6230028 | partial | 2025-07-01 | Z | 2025-06-17 | 250 | 0 | 380 | A | 0 | 1270 |  |  |  | 14
2025-07-10 | 3748a |  | W.SHAFT-RAMP 2 | A | DONE | 38 | M |  | UW-LEVY HALL 6230028 | partial | 2025-07-01 | Z | 2025-06-17 | 310 | 0 | 620 | A | 0 | 1650 |  |  |  | 14
2025-07-10 | 3749a |  | W.SHAFT-EAMP 1 | A | DONE | 11 | M |  | UW-LEVY HALL 6230028 | partial | 2025-07-01 | Z | 2025-06-17 | 100 | 0 | 170 | A | 0 | 340 |  |  |  | 14
2025-07-07 | 1876 |  | 75711 - 75712 | A | DONE | 4 | S-M |  | UWP-FH 6240021 | flex | 2025-07-08 | Z | 2025-06-24 | 100 | 0 | 0 |  | 0 | 130 |  | DOAS - 2 EA |  | 14
2025-07-07 | 1877 |  | 66644 | A | DONE | 2 | S |  | UWP-FH 6240021 |  | 2025-07-08 | Z | 2025-06-24 | 20 | 0 | 0 |  | 0 | 30 |  | DOAS - 2 EA |  | 14
2025-07-07 | 2869 |  | 84865 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-07-08 | Z | 2025-06-26 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd Floor tie in |  | 12
2025-07-07 | 2870 | sp | 84866 - 84867 | A | DONE | 3 | S-M | ss | UWRF 6230010 |  | 2025-07-08 | Z | 2025-06-26 | 60 | 0 | 0 |  | 0 | 120 |  | FEMP drops |  | 12
2025-07-07 | 2871 | sp | 84868 | A | DONE | 2 | S-M | pcd | UWRF 6230010 |  | 2025-07-08 | Z | 2025-06-26 | 20 | 30 | 0 |  | 0 | 50 |  | 318 FEMP drops |  | 12
2025-07-10 | 3269 |  | 61491 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-07-15 | Z | 2025-06-26 | 20 | 0 | 0 |  | 0 | 20 |  | 4th Floor |  | 19
2025-07-07 | 4422 | w | 58832 | A | DONE | 2 | S-M |  | UWSP CHAMPION HALL 6240008 | expanded metal | 2025-07-10 | Z | 2025-06-30 | 20 | 0 | 0 |  | 0 | 20 |  | Intake Hood |  | 10
2025-07-11 | 3578 |  | 85016 | A | DONE | 4 | S | neal | UW-WHITEWATER ML 6250001 |  | 2025-07-18 | Z | 2025-07-07 | 80 | 0 | 0 |  | 0 | 120 |  | Misc |  | 11
2025-07-11 | 3580 |  | 85018 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-07-18 | Z | 2025-07-07 | 30 | 0 | 0 |  | 0 | 40 |  | TA |  | 11
2025-07-09 | 3581 | sp | 85019 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-07-10 | Z | 2025-07-09 | 20 | 0 | 0 |  | 0 | 30 |  | Damper |  | 1
2025-07-07 | 3861 |  | 74776 | A | DONE | 2 | S |  | UW-WITTE HALL 6250003 |  | 2025-07-08 | Z | 2025-06-24 | 20 | 0 | 0 |  | 0 | 20 |  | DM Frames |  | 14
2025-07-07 | 3864 |  | 74780 | A | DONE | 2 | S | neal | UW-WITTE HALL 6250003 |  | 2025-07-08 | Z | 2025-07-03 | 20 | 0 | 0 |  | 0 | 40 |  | EX outs |  | 5
2025-07-07 | 3866 |  | 74781 | A | DONE | 4 | S-M | neal | UW-WITTE HALL 6250003 |  | 2025-07-08 | Z | 2025-07-03 | 100 | 0 | 0 |  | 0 | 150 |  | Flashing |  | 5
2025-07-11 | 3867 |  | 74782 | A | DONE | 8 | S-M | neal | UW-WITTE HALL 6250003 |  | 2025-07-16 | Z | 2025-07-03 | 200 | 0 | 0 |  | 0 | 240 |  | Flashing |  | 13
2025-07-08 | 3855f |  | 74766 | A | DONE | 4 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner , AB damper | 2025-07-08 | Z | 2025-05-31 | 100 | 0 | 0 |  | 70 | 160 |  | Damper piece |  | 38
2025-07-09 | 1400 |  | L01_D_SOA_002 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 160 | 0 | 90 | A | 0 | 290 |  |  |  | 37
2025-07-09 | 1401 | bth | L01_D_SOA_003 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 60 | 30 | 280 | A | 0 | 460 |  |  |  | 37
2025-07-09 | 1402 | bth | L01_D_SOA_004 | A | DONE | 17 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 170 | 20 | 230 | A | 0 | 500 |  |  |  | 37
2025-07-09 | 1403 | bth | L01_D_SOA_005 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 50 | 40 | 210 | A | 0 | 360 |  |  |  | 37
2025-07-09 | 1404 | bth | L01_D_SOA_006 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 60 | 180 | 40 | A | 0 | 300 |  |  |  | 37
2025-07-09 | 1405 | bth | L01_D_SOA_007 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 210 | 40 | 60 | A | 0 | 390 |  |  |  | 37
2025-07-09 | 1406 | bth | L01_D_SOA_008 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 60 | 60 | 210 | A | 0 | 380 |  |  |  | 37
2025-07-09 | 1407 | bth | L01_D_SOA_009 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 90 | 40 | 60 | A | 0 | 240 |  |  |  | 37
2025-07-09 | 1408 | bth | L01_D_SOA_010 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 20 | 40 | 150 | A | 0 | 210 |  |  |  | 37
2025-07-09 | 1411 | bth | L01_D_EAD_001 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 150 | 30 | 190 | A | 0 | 490 |  |  |  | 37
2025-07-09 | 1412 | bth | L01_D_EAD_002 | A | DONE | 17 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 210 | 30 | 180 | A | 0 | 520 |  |  |  | 37
2025-07-09 | 1413 | bth | L01_D_EAD_003 | A | DONE | 11 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 40 | 100 | 120 | A | 0 | 280 |  |  |  | 37
2025-07-09 | 1414 | bth | L01_D_EAD_004 | A | DONE | 10 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 100 | 20 | 110 | A | 0 | 280 |  |  |  | 37
2025-07-09 | 1415 | bth | L01_D_EAD_005 | A | DONE | 10 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 120 | 20 | 110 | A | 0 | 290 |  |  |  | 37
2025-07-09 | 1416 | bth | L01_D_EAD_006 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 20 | 20 | 140 | A | 0 | 210 |  |  |  | 37
2025-07-09 | 1417 | bth | L01_D_EAD_007 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 40 | 50 | 60 | A | 0 | 160 |  |  |  | 37
2025-07-09 | 1699 |  | L01_D_SOA_001 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-05-19 | 190 | 0 | 90 | A | 0 | 420 |  |  |  | 37
2025-07-08 | 1909 |  | 83314 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-07-09 | Z | 2025-06-10 | 40 | 0 | 0 |  | 0 | 100 |  | Gym Hangers |  | 29
2025-07-09 | 1910 | w | 83454 | A | DONE | 2 | S-M | ss | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-06-12 | 20 | 0 | 0 |  | 0 | 50 |  | EF-2-ROOF |  | 13
2025-07-09 | 1911 | bth | 83455 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-06-12 | 60 | 40 | 0 |  | 0 | 110 |  | EF-3-ROOF |  | 13
2025-07-09 | 1913 | sp/w | 79884 | A | DONE | 4 | S-M | neal | WAUNAKEE MS 6230013 |  | 2025-06-25 | Z | 2025-06-16 | 30 | 60 | 0 |  | 0 | 150 |  | Dust collection |  | 9
2025-07-08 | 1914 |  | 79885 - 79886 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | paint | 2025-06-25 | Z | 2025-06-16 | 200 | 0 | 0 |  | 50 | 290 |  | Flashing |  | 9
2025-07-09 | 1915 |  | 79887 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | paint | 2025-06-25 | Z | 2025-06-16 | 180 | 0 | 0 |  | 190 | 260 |  | Grille Boxes EG , RG |  | 9
2025-07-09 | 1916 |  | 83456 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-23 | 20 | 20 | 0 |  | 0 | 40 |  | 1st G-EA |  | 10
2025-07-09 | 1917 |  | 83457 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-07-03 | Z | 2025-06-23 | 20 | 0 | 0 |  | 20 | 40 |  | 1st G-TA |  | 10
2025-07-07 | 1918 |  | 83459 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-23 | 20 | 0 | 0 |  | 0 | 40 |  | 1st G-Flashing |  | 10
2025-07-11 | 1919 |  | 83359 - 83360 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-26 | 320 | 0 | 0 |  | 0 | 910 |  | A-PH Roof |  | 7
2025-07-11 | 1921 |  | L02_A_EAD_001 | A | DONE | 13 | M |  | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-30 | 90 | 0 | 230 | A | 0 | 580 |  |  |  | 3
2025-07-11 | 1922 | w | L02_A_GEA_001 | A | DONE | 9 | M | BI | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-30 | 220 | 0 | 0 |  | 0 | 680 |  |  |  | 3
2025-07-11 | 1923 | w | L02_A_KEA_001 | A | DONE | 4 | S | ss | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-30 | 90 | 0 | 0 |  | 0 | 210 |  |  |  | 3
2025-07-11 | 1925 |  | L02_A_OA_001 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-30 | 60 | 0 | 170 | A | 0 | 360 |  |  |  | 3
2025-07-11 | 1926 |  | L02_A_OA_002 | A | DONE | 10 | M |  | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-30 | 180 | 0 | 60 | A | 0 | 380 |  |  |  | 3
2025-07-11 | 1927 |  | L02_A_SOA_003 | A | DONE | 14 | M |  | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-30 | 40 | 0 | 290 | A | 0 | 470 |  |  |  | 3
[6 empty] | 1318 | [13 empty] | 45550 |  |  |  | 24070 | 52.84%
WEEK OF 7-14-2025
2025-07-14 | 1034 |  | 85165 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 | bird s. , paint | 2025-07-16 | Z | 2025-07-02 | 50 | 0 | 0 |  | 20 | 120 |  | ERV-1 EA |  | 14
2025-07-14 | 1035 |  | 85166 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2025-07-16 | Z | 2025-07-14 | 40 | 0 | 0 |  | 0 | 90 |  | PL-1 SW Louver |  | 2
2025-07-18 | r287 |  | 85232 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-07-22 | Z | 2025-07-18 | 20 | 0 | 0 |  | 0 | 20 |  | TA Sleeves |  | 4
2025-07-16 | 2296 |  | 75178 - 75180 | A | DONE | 12 | S-M |  | BARTILLION 6240024 |  | 2025-07-10 | Z | 2025-06-16 | 250 | 0 | 50 | A | 0 | 420 |  | EA to ERV , 1st Mech |  | 24
2025-07-14 | 2297 |  | 75181 - 75182 | A | DONE | 26 | S-M |  | BARTILLION 6240024 |  | 2025-07-10 | Z | 2025-06-16 | 230 | 0 | 420 | A | 0 | 770 |  | 2nd B-EA |  | 24
2025-07-16 | 2298 | bth | 75183 - 75187 | A | DONE | 51 | M |  | BARTILLION 6240024 | paint | 2025-07-10 | Z | 2025-06-16 | 230 | 1040 | 0 |  | 0 | 1430 |  | 2nd EA |  | 24
2025-07-16 | 2299 |  | 75188 | A | DONE | 14 | S |  | BARTILLION 6240024 |  | 2025-07-10 | Z | 2025-06-16 | 40 | 0 | 290 | A | 0 | 400 |  | 2nd EA |  | 24
2025-07-18 | 2733 |  | 84357 | A | DONE | 3 | S-M |  | BARTILLION 6240024 | paint | 2025-07-16 | Z | 2025-06-30 | 70 | 0 | 0 |  | 70 | 150 |  | EA boxes |  | 16
2025-07-14 | 2740 | w | 84358 | A | DONE | 2 | S | BI | BARTILLION 6240024 |  | 2025-07-18 | Z | 2025-07-10 | 30 | 0 | 0 |  | 0 | 90 |  | Grease duct |  | 8
2025-07-18 | 2741 |  | 84359 | A | DONE | 3 | S-M | neal | BARTILLION 6240024 |  | 2025-07-22 | Z | 2025-07-15 | 60 | 0 | 0 |  | 0 | 90 |  | Flashing |  | 7
2025-07-18 | 2484 | sp | 69978 - 69980 | A | DONE | 4 | S-M | neal | CDIS 6220028 |  | 2025-07-16 | Z | 2025-06-26 | 50 | 50 | 0 |  | 0 | 120 |  | CB 1168 Rm 3564 , 3570 |  | 20
2025-07-18 | 2485 |  | 69981 - 69982 | A | DONE | 2 | S-M | neal | CDIS 6220028 |  | 2025-07-16 | Z | 2025-06-26 | 40 | 0 | 0 |  | 0 | 60 |  | CB 1168 Rm |  | 20
2025-07-18 | 2486 | sp | 69983 - 69986 | A | DONE | 7 | S-M | neal | CDIS 6220028 |  | 2025-07-16 | Z | 2025-06-26 | 50 | 120 | 0 |  | 0 | 190 |  | CB 1168 Rm 3574 , 3594 |  | 20
2025-07-17 | 2487 |  | PRE-FAB HANGERS | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2025-07-16 | Z | 2025-06-26 | 20 | 0 | 0 |  | 0 | 60 |  | Tear Drop Hangers |  | 20
2025-07-15 | 2488 |  | 65657 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2025-07-16 | Z | 2025-07-16 | 80 | 0 | 0 |  | 0 | 120 |  | Flat Stock |  | 0
2025-07-14 | 883 |  | 73665 | A | DONE | 2 | S |  | DELLSHIRE 6240017 | paint , 1" liner | 2025-07-07 | Z | 2025-04-21 | 40 | 0 | 0 |  | 40 | 60 |  | VTAC Plenum/slider V.3 |  | 77
2025-07-14 | 3518 |  | 73802 | A | DONE | 23 | S-M |  | DELLSHIRE 6240017 |  | 2025-07-11 | Z | 2025-06-30 | 570 | 0 | 0 |  | 360 | 710 |  | C/D SA Risers |  | 11
2025-07-16 | 3519 |  | 73673 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-07-11 | Z | 2025-07-03 | 40 | 0 | 0 |  | 0 | 90 |  | Louver EIFS Mock up |  | 8
2025-07-16 | 881a |  | 73663 | A | DONE | 56 | M-L |  | DELLSHIRE 6240017 | paint , 1" liner | 2025-07-11 | Z | 2025-07-01 | 1400 | 0 | 0 |  | 1410 | 1610 |  |  |  | 10
2025-07-14 | 247 |  | 84288 | A | DONE | 2 | S |  | DEWITT 2250018 |  | 2025-07-14 | Z | 2025-07-14 | 20 | 0 | 0 |  | 0 | 20 |  | Chilled Beam |  | 0
2025-07-15 | 249 |  | 80343 - 80344 | A | DONE | 3 | S |  | DEWITT 2250018 |  | 2025-07-15 | Z | 2025-07-15 | 40 | 20 | 0 |  | 0 | 70 |  | Chilled Beam |  | 0
2025-07-18 | 1614 | w | 74302 - 74303 | A | DONE | 2 | S-M |  | DOC JDC 6240023 | 2" DB | 2025-07-25 | Z | 2025-06-25 | 50 | 0 | 0 |  | 50 | 150 |  | ACCU-1 thru 3 |  | 30
2025-07-17 | 1015 |  | 56817 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2025-07-22 | Z | 2025-07-16 | 60 | 0 | 0 |  | 0 | 110 |  | Shut down |  | 6
2025-07-18 | 251 |  | 65670 , 65672 | A | DONE | 4 | S-M |  | HISTOSONICS 6250009 |  | 2025-07-21 | Z | 2025-07-18 | 80 | 0 | 0 |  | 0 | 130 |  | RTU-7 RA |  | 3
2025-07-17 | 248 |  | 84732 | A | DONE | 5 | S |  | KEVIN M. 1000382 |  | 2025-07-16 | Z | 2025-07-14 | 120 | 0 | 0 |  | 0 | 130 |  | Misc |  | 2
2025-07-14 | 246 |  | 84730 - 84731 | A | DONE | 2 | S |  | LAB CORP 10062916 |  | 2025-07-14 | Z | 2025-07-14 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2025-07-14 | 1725 |  | 74238 | A | DONE | 2 | S |  | MCDS 6250005 | paint | 2025-07-17 | Z | 2025-07-11 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 6
2025-07-15 | 1726 |  | 84289 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-07-15 | Z | 2025-07-15 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 0
2025-07-18 | 1728 |  | 74242 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-07-21 | Z | 2025-07-18 | 40 | 0 | 0 |  | 0 | 40 |  | Misc angle |  | 3
2025-07-15 | 4502 |  | 84290 | A | DONE | 7 | S-M |  | MONONA GROVE HS 6250016 |  | 2025-07-15 | Z | 2025-07-15 | 160 | 0 | 0 |  | 0 | 280 |  | Flat Stock |  | 0
2025-07-18 | 2050 |  | EA-L1A-03 | A | DONE | 8 | S |  | MONROE HS 6240018 | VD | 2025-07-15 | Z | 2025-06-11 | 90 | 0 | 90 | A | 0 | 220 |  |  |  | 34
2025-07-17 | 2051 |  | EA-L1A-04 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-07-15 | Z | 2025-06-11 | 90 | 0 | 180 | A | 240 | 350 |  |  |  | 34
2025-07-17 | 2053 |  | RA-L1A-01 | A | DONE | 16 | M |  | MONROE HS 6240018 | 1" liner | 2025-07-15 | Z | 2025-06-11 | 260 | 0 | 140 | A | 360 | 620 |  |  |  | 34
2025-07-18 | 2054 |  | RA-L1A-02 | A | DONE | 24 | M-L |  | MONROE HS 6240018 | 1" liner | 2025-07-15 | Z | 2025-06-11 | 270 | 0 | 310 | A | 520 | 1260 |  |  |  | 34
2025-07-17 | 2056 | bth | SALP-L1A-02 | A | DONE | 9 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 90 | 40 | 90 | A | 150 | 300 |  |  |  | 34
2025-07-18 | 2057 | bth | SALP-L1A-03 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 100 | 40 | 90 | A | 150 | 310 |  |  |  | 34
2025-07-17 | 2058 | bth | SALP-L1A-04 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 90 | 40 | 120 | A | 170 | 350 |  |  |  | 34
2025-07-17 | 2059 | bth | SALP-L1A-05 | A | DONE | 13 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 100 | 100 | 120 | A | 170 | 440 |  |  |  | 34
2025-07-17 | 2060 |  | SALP-L1A-06 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 140 | 0 | 110 | A | 180 | 320 |  |  |  | 34
2025-07-17 | 2061 | bth | SALP-L1A-07 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 80 | 40 | 120 | A | 160 | 330 |  |  |  | 34
2025-07-17 | 2062 | bth | SALP-L1A-08 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 90 | 40 | 120 | A | 170 | 340 |  |  |  | 34
2025-07-18 | 2063 | bth | SALP-L1A-09 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 130 | 40 | 100 | A | 160 | 330 |  |  |  | 34
2025-07-18 | 2064 | bth | SALP-L1A-10 | A | DONE | 14 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 120 | 40 | 170 | A | 230 | 450 |  |  |  | 34
2025-07-18 | 2065 | bth | SALP-L1A-11 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 130 | 20 | 120 | A | 180 | 340 |  |  |  | 34
2025-07-18 | 2066 | bth | SALP-L1A-12 | A | DONE | 5 | S |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 50 | 60 | 0 |  | 30 | 120 |  |  |  | 34
2025-07-18 | 2067 | bth | SALP-L1A-13 | A | DONE | 7 | S |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 110 | 60 | 0 |  | 90 | 230 |  |  |  | 34
2025-07-18 | 2068 | bth | SALP-L1A-14 | A | DONE | 13 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 160 | 20 | 130 | A | 220 | 400 |  |  |  | 34
2025-07-18 | 2069 | bth | SALP-L1A-15 | A | DONE | 9 | S |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 20 | 80 | 120 | A | 110 | 260 |  |  |  | 34
2025-07-18 | 2070 | bth | SALP-L1A-16 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 130 | 20 | 50 | A | 150 | 280 |  |  |  | 34
2025-07-18 | 2071 |  | SALP-L1A-17 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 190 | 0 | 110 | A | 210 | 380 |  |  |  | 34
2025-07-18 | 2074 |  | SALP-L1A-20 | A | DONE | 18 | M |  | MONROE HS 6240018 | VD , 2" liner | 2025-07-15 | Z | 2025-06-11 | 210 | 0 | 240 | A | 370 | 710 |  |  |  | 34
2025-07-18 | 2075 | bth | SALP-L1A-21 | A | DONE | 15 | S-M |  | MONROE HS 6240018 | VD , 2" liner | 2025-07-15 | Z | 2025-06-11 | 80 | 30 | 250 | A | 260 | 490 |  |  |  | 34
2025-07-14 | 3008 |  | 85327 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-07-08 | Z | 2025-06-25 | 40 | 0 | 0 |  | 0 | 80 |  | 2nd A |  | 13
2025-07-15 | 3009 |  | 85328 | A | DONE | 4 | S-M |  | MONROE HS 6240018 | oval accuflange | 2025-07-08 | Z | 2025-06-25 | 90 | 0 | 0 |  | 0 | 200 |  | 2nd A |  | 13
2025-07-17 | 3016 |  | 85330 | A | DONE | 4 | S-M |  | MONROE HS 6240018 |  | 2025-07-15 | Z | 2025-07-01 | 80 | 0 | 0 |  | 0 | 190 |  | Mech Rooom |  | 14
2025-07-17 | 3017 |  | 85331 | A | DONE | 2 | S-M |  | MONROE HS 6240018 | flex , paint | 2025-07-15 | Z | 2025-07-01 | 50 | 0 | 0 |  | 20 | 140 |  | 2nd B |  | 14
2025-07-17 | 3018 |  | 85332 | A | DONE | 2 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-07-01 | 20 | 0 | 0 |  | 20 | 40 |  | 1st C VAV |  | 14
2025-07-15 | 3830 |  | TA-L1A-01 | A | DONE | 4 | S |  | MONROE HS 6240018 | 1" liner | 2025-07-08 | Z | 2025-06-06 | 100 | 0 | 0 |  | 100 | 130 |  |  |  | 32 | 2025-06-17
2025-07-15 | 3831 |  | TA-L1A-02 | A | DONE | 3 | S |  | MONROE HS 6240018 | 1" liner | 2025-07-08 | Z | 2025-06-06 | 70 | 0 | 0 |  | 70 | 90 |  |  |  | 32 | 2025-06-17
2025-07-14 | 3839 | sp | SAMP-L1A-01 | A | DONE | 21 | M |  | MONROE HS 6240018 | oval , accuflange | 2025-07-08 | Z | 2025-06-11 | 40 | 470 | 0 |  | 0 | 780 |  |  |  | 27
2025-07-14 | 3841 | bth | SAMP-L1A-03 | A | DONE | 42 | L |  | MONROE HS 6240018 | oval , accu. , 2" liner | 2025-07-08 | Z | 2025-06-11 | 380 | 580 | 80 | A | 340 | 2270 |  |  |  | 27
2025-07-15 | 3844 | bth | SAMP-L1A-06 | A | DONE | 16 | M |  | MONROE HS 6240018 | 2" liner | 2025-07-08 | Z | 2025-06-11 | 250 | 140 | 0 |  | 60 | 650 |  |  |  | 27
2025-07-15 | 3846 | sp | SAMP-L1A-08 | A | DONE | 12 | S-M |  | MONROE HS 6240018 |  | 2025-07-08 | Z | 2025-06-11 | 20 | 280 | 0 |  | 0 | 290 |  |  |  | 27
2025-07-17 | 3848 | bth | EA-L1A-01 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | VD , 1" liner | 2025-07-15 | Z | 2025-06-11 | 150 | 40 | 60 | A | 130 | 330 |  |  |  | 34
2025-07-17 | 3849 | bth | EA-L1A-02 | A | DONE | 5 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-07-15 | Z | 2025-06-11 | 30 | 90 | 0 |  | 20 | 120 |  |  |  | 34
2025-07-14 | 1796 |  | 79508 | A | DONE | 4 | S-M | pt.ss | ONE 09 6240037 | nipple | 2025-07-07 | Z | 2025-06-25 | 80 | 0 | 0 |  | 0 | 220 |  | MAU-1 DX COIL |  | 12
2025-07-16 | 1799 |  | 79511 | A | DONE | 2 | S |  | ONE 09 6240037 |  | 2025-07-11 | Z | 2025-07-07 | 20 | 0 | 0 |  | 0 | 30 |  | HP 140 RA |  | 4
2025-07-14 | 4225 |  | 81634 - 81635 | A | DONE | 6 | S-M |  | PECATONICA 6240005 |  | 2025-07-21 | Z | 2025-07-03 | 130 | 0 | 0 |  | 0 | 310 |  | B-Section Main |  | 18
2025-07-14 | 4226 |  | 91636 - 81637 | A | DONE | 5 | S-M |  | PECATONICA 6240005 | 2" liner | 2025-07-21 | Z | 2025-07-03 | 70 | 20 | 30 | A | 70 | 130 |  | B-Section |  | 18
2025-07-14 | 4228 |  | 79690 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2025-07-21 | Z | 2025-07-07 | 20 | 0 | 0 |  | 0 | 20 |  | AHU-3 OA |  | 14
2025-07-18 | 1849 | sp | L1B-CE 1 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-07-30 | Z | 2025-07-08 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 22 | 2025-07-23
2025-07-14 | 4611 |  | 76706 | A | DONE | 3 | S-M | neal | PEWAUKEE HS 6240030 |  | 2025-07-16 | Z | 2025-07-08 | 60 | 0 | 0 |  | 0 | 110 |  | Misc |  | 8
2025-07-15 | 4612 |  | 74121 | A | DONE | 3 | S |  | PEWAUKEE HS 6240030 | 1" liner | 2025-07-16 | Z | 2025-07-08 | 60 | 0 | 0 |  | 20 | 80 |  | RE-1-A |  | 8
2025-07-15 | 239 | w | 70246 | A | DONE | 2 | S-M | ss | PLACON 10063039 |  | 2025-07-16 | Z | 2025-07-03 | 50 | 0 | 0 |  | 0 | 150 |  | Hood |  | 13
2025-07-14 | 240 | w | 70247 | A | DONE | 2 | S |  | PLACON 10063039 | 1-1/2 DB | 2025-07-16 | Z | 2025-07-03 | 20 | 0 | 0 |  | 20 | 60 |  | Curb |  | 13
2025-07-14 | 241 | bth | 70248 | A | DONE | 7 | S-M |  | PLACON 10063039 |  | 2025-07-16 | Z | 2025-07-03 | 50 | 120 | 0 |  | 0 | 180 |  | EA |  | 13
2025-07-17 | 1328 | sp | L01_AREA_300_EA_001 | delete |  |  | S |  | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-06-03 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 100 | 2025-06-26
2025-07-16 | 1348 |  | L01_AREA_400_EA_001 | A | DONE | 7 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-06-06 | 170 | 0 | 0 |  | 0 | 320 |  |  |  | 34
2025-07-16 | 1349 |  | L01_AREA_400_MA_001 | A | DONE | 15 | M |  | PROJECT DOVE 6240041 | VD's | 2025-07-10 | Z | 2025-06-06 | 370 | 0 | 0 |  | 0 | 930 |  |  |  | 34
2025-07-16 | 1350 | bth | L01_AREA_400_MA_002 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-06-06 | 30 | 50 | 0 |  | 0 | 100 |  |  |  | 34
2025-07-16 | 1351 |  | L01_AREA_400_RAMP_001 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-06-06 | 30 | 0 | 180 | A | 0 | 360 |  |  |  | 34
2025-07-15 | 1376 |  | 55137 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-17 | Z | 2025-06-16 | 50 | 0 | 0 |  | 0 | 250 |  | Area 500 L2 hangers |  | 31
2025-07-15 | 1377 |  | 55138 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-07-17 | Z | 2025-06-16 | 20 | 0 | 0 |  | 0 | 60 |  | Area 200 L2 hangers |  | 31
2025-07-15 | 4556 |  | 76151 - 76153 | A | DONE | 6 | M | ss | PROJECT DOVE 6240041 |  | 2025-07-17 | Z | 2025-07-03 | 150 | 0 | 0 |  | 0 | 420 |  | AHU-3 Filter rack |  | 14
2025-07-15 | 4557 |  | 76154 - 76158 | A | DONE | 7 | M | ss | PROJECT DOVE 6240041 |  | 2025-07-17 | Z | 2025-07-03 | 160 | 0 | 0 |  | 0 | 450 |  | AHU-2 Filter rack |  | 14
2025-07-14 | 4558 |  | MAU_07_MA_001 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-08 | 210 | 0 | 0 |  | 0 | 570 |  |  |  | 2
2025-07-15 | 4559 |  | MAU_07_RAMP_001 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-08 | 210 | 0 | 0 |  | 0 | 570 |  |  |  | 2
2025-07-16 | 4576 |  | MAU_03_MA_001 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-09 | 50 | 0 | 60 | A | 0 | 180 |  |  |  | 1
2025-07-15 | 4577 |  | MAU_03_RAMP_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-09 | 50 | 0 | 0 |  | 0 | 80 |  |  |  | 1
2025-07-15 | 4578 |  | L02_AREA_400_EA_001 | A | DONE | 12 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-09 | 90 | 0 | 190 | A | 0 | 470 |  |  |  | 1
2025-07-15 | 4579 |  | L02_AREA_400_RAMP_001 | A | DONE | 12 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-09 | 250 | 0 | 50 | A | 0 | 410 |  |  |  | 1
2025-07-16 | 4580 |  | L02_AREA_400_MA_001 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-10 | Z | 2025-07-09 | 100 | 0 | 170 | A | 0 | 560 |  |  |  | 1
2025-07-14 | 4581 | sp | 76161 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-17 | Z | 2025-07-10 | 20 | 20 | 0 |  | 0 | 40 |  | 2nd S. Corridor |  | 7
2025-07-18 | 244 | bth | 70249 | A | DONE | 6 | S-M |  | SCHUMANN PRINTER 10063207 |  | 2025-07-25 | Z | 2025-07-11 | 40 | 110 | 0 |  | 20 | 150 |  | Misc |  | 14
2025-07-14 | 3683 |  | 68150 | A | DONE | 3 | S |  | SPH SURGERY 6240039 |  | 2025-07-21 | Z | 2025-07-07 | 60 | 0 | 0 |  | 0 | 180 |  | Misc |  | 14
2025-07-15 | 3686 |  | 68874 - 68875 | A | DONE | 3 | S-M |  | SPH SURGERY 6240039 |  | 2025-07-21 | Z | 2025-07-11 | 60 | 0 | 0 |  | 0 | 90 |  | PH Outs |  | 10
2025-07-14 | 3688 |  | 68490 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-07-21 | Z | 2025-07-14 | 40 | 0 | 0 |  | 0 | 70 |  | Flat Stock |  | 7
2025-07-18 | 3689 |  | 68494 | A | DONE | 2 | S-M |  | SPH SURGERY 6240039 |  | 2025-07-28 | Z | 2025-07-14 | 30 | 0 | 0 |  | 0 | 40 |  | Steam Roof Flashing |  | 14
2025-07-17 | 4079 |  | 73978 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | bird s. | 2025-07-25 | Z | 2025-07-15 | 20 | 0 | 0 |  | 0 | 20 |  | Closet |  | 10
2025-07-14 | 4078 | w | 73977 | A | DONE | 2 | S |  | STOUGTON TRAILER 6240015 | nipple | 2025-07-17 | Z | 2025-07-10 | 20 | 0 | 0 |  | 0 | 20 |  | Drain pan |  | 7
2025-07-18 | 504 |  | 75520 | A | DONE | 2 | S | neal | SW HEALTH OR 5 6250004 |  | 2025-07-28 | Z | 2025-07-16 | 40 | 0 | 0 |  | 0 | 60 |  | Misc |  | 12
2025-07-17 | 505 |  | 75521 | A | DONE | 2 | S | neal | SW HEALTH OR 5 6250004 | bird s. | 2025-07-21 | Z | 2025-07-16 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 5
2025-07-14 | 3770 | bth | L5D-WSHP-1 | A | DONE | 8 | S-M |  | UW-AVRL 6240038 |  | 2025-07-16 | Z | 2025-06-24 | 70 | 40 | 80 | A | 0 | 250 |  |  |  | 22
2025-07-14 | 3771 | bth | L5D-WSHP-2 | A | DONE | 13 | S-M |  | UW-AVRL 6240038 |  | 2025-07-16 | Z | 2025-06-24 | 120 | 50 | 140 | A | 0 | 380 |  |  |  | 22
2025-07-14 | 3772 |  | 61925 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-07-16 | Z | 2025-07-02 | 30 | 0 | 0 |  | 0 | 50 |  | Misc tie ins |  | 14
2025-07-14 | 3773 |  | 61927 | A | DONE | 2 | S | ss/pcd | UW-AVRL 6240038 | paint | 2025-07-16 | Z | 2025-07-02 | 30 | 20 | 0 |  | 0 | 60 |  | 5th Floor tie ins |  | 14
2025-07-14 | 3774 |  | 61928 - 61929 | A | DONE | 2 | S |  | UW-AVRL 6240038 | paint | 2025-07-16 | Z | 2025-07-02 | 50 | 0 | 0 |  | 20 | 80 |  | 5th Floor tie ins |  | 14
2025-07-14 | 3777 |  | 61933 | A | DONE | 2 | S |  | UW-AVRL 6240038 | paint | 2025-07-16 | Z | 2025-07-09 | 30 | 0 | 0 |  | 30 | 40 |  | 5th Floor Misc |  | 7
2025-07-14 | 3778 | bth | 61934 | A | DONE | 2 | S |  | UW-AVRL 6240038 | paint | 2025-07-16 | Z | 2025-07-10 | 30 | 20 | 0 |  | 20 | 50 |  | 5th Floor tie in |  | 6
2025-07-16 | 3786 |  | 61931 - 61932 | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-07-16 | Z | 2025-07-14 | 20 | 0 | 0 |  | 0 | 20 |  | 5th Floor BSL |  | 2
2025-07-14 | 2017 |  | EL.SHAFT-SAMP 3 | A | DONE | 24 | M |  | UW-LEVY HALL 6230028 |  | 2025-07-07 | Z | 2025-06-19 | 340 | 0 | 240 | A | 0 | 950 |  |  |  | 18
2025-07-14 | 2018 |  | EL.SHAFT-RAMP 3 | A | DONE | 21 | M |  | UW-LEVY HALL 6230028 |  | 2025-07-07 | Z | 2025-06-19 | 320 | 0 | 190 | A | 0 | 960 |  |  |  | 18
2025-07-16 | 2019 | bth | L5-SAMP 6 | A | DONE | 12 | M |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 100 | 30 | 170 | A | 0 | 370 |  |  |  | 21
2025-07-16 | 2020 | bth | L5-SAMP 7 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 90 | 70 | 50 | A | 0 | 230 |  |  |  | 21
2025-07-16 | 2021 | bth | L5-SAMP 8 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 20 | 20 | 180 | A | 0 | 260 |  |  |  | 21
2025-07-16 | 2022 | bth | L5-SAMP 9 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 40 | 70 | 70 | A | 0 | 190 |  |  |  | 21
2025-07-16 | 2023 | bth | L5-SAMP 10 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 70 | 50 | 120 | A | 0 | 290 |  |  |  | 21
2025-07-16 | 2024 | bth | L5-SAMP 11 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 110 | 20 | 80 | A | 0 | 250 |  |  |  | 21
2025-07-16 | 2025 | bth | L5-SAMP 12 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 90 | 60 | 70 | A | 0 | 260 |  |  |  | 21
2025-07-16 | 2026 | bth | L5-EAMP 1 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 21
2025-07-16 | 2027 | bth | L5-EAMP 3 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-14 | Z | 2025-06-23 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2025-07-16 | 2028 | bth | L5-EAMP 4 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 70 | 0 | 0 |  | 0 | 120 |  |  |  | 21
2025-07-16 | 2029 | bth | L5-EAMP 5 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 40 | 0 | 80 | A | 0 | 140 |  |  |  | 21
2025-07-16 | 2030 | bth | L5-EAMP 6 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-23 | 110 | 0 | 0 |  | 0 | 160 |  |  |  | 21
2025-07-17 | 2074 |  | 82966 - 82967 | A | DONE | 2 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-14 | Z | 2025-06-27 | 50 | 0 | 0 |  | 30 | 80 |  | SAMP, RAMP |  | 17
2025-07-16 | 2078 |  | 82975 - 82976 | A | DONE | 6 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-22 | Z | 2025-07-15 | 130 | 0 | 0 |  | 100 | 180 |  | L1 Bathroom TA |  | 7
2025-07-14 | 2005a |  | EL.SHAFT-EAMP 2 | A | DONE | 17 | M |  | UW-LEVY HALL 6230028 | 1" liner , partial | 2025-07-07 | Z | 2025-06-19 | 120 | 0 | 300 | A | 380 | 760 |  |  |  | 18
2025-07-14 | 3992 |  | 82174 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | paint | 2025-07-21 | Z | 2025-07-09 | 50 | 0 | 0 |  | 50 | 100 |  | Grille outs |  | 12
2025-07-14 | 1880 |  | 66645 | A | DONE | 2 | S |  | UWP-FH 6240021 |  | 2025-07-17 | Z | 2025-07-10 | 20 | 0 | 0 |  | 0 | 30 |  | LL |  | 7
2025-07-18 | 1881 |  | 66648 | A | DONE | 4 | S |  | UWP-FH 6240021 |  | 2025-07-24 | Z | 2025-07-16 | 90 | 0 | 0 |  | 0 | 120 |  | 2nd Floor |  | 8
2025-07-17 | 1882 |  | 75716 | A | DONE | 2 | S |  | UWP-FH 6240021 |  | 2025-07-24 | Z | 2025-07-17 | 30 | 0 | 0 |  | 0 | 70 |  | 1st Fl Chase |  | 7
2025-07-14 | 3083 |  | 57650 | delete | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-07-15 | Z | 2025-07-08 | 40 | 0 | 0 |  | 0 | 70 |  | Misc |  | 7
2025-07-17 | 3084 |  | 54525 , 73100 | A | DONE | 2 | S |  | UW-VET MED 6210014 | paint | 2025-07-15 | Z | 2025-07-09 | 30 | 0 | 0 |  | 30 | 60 |  | 2nd Floor |  | 6
2025-07-15 | 3085 |  | 54526 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-07-15 | Z | 2025-07-09 | 20 | 0 | 0 |  | 0 | 30 |  | 7B |  | 6
2025-07-14 | 3579 |  | 85017 | A | DONE | 6 | S-M | neal | UW-WHITEWATER ML 6250001 |  | 2025-07-18 | Z | 2025-07-07 | 80 | 0 | 50 | A | 0 | 200 |  | Misc |  | 11
2025-07-16 | 3868 |  | 74783 - 74784 | A | DONE | 4 | S-M | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-07-23 | Z | 2025-07-14 | 100 | 0 | 0 |  | 90 | 140 |  | Floor outs |  | 9
2025-07-18 | 3869 | sp | 74785 | A | DONE | 2 | S |  | UW-WITTE HALL 6250003 |  | 2025-07-23 | Z | 2025-07-15 | 20 | 0 | 0 |  | 0 | 20 |  | 11th Floor |  | 8
2025-07-18 | 3870 |  | 74786 | A | DONE | 2 | S |  | UW-WITTE HALL 6250003 | 1" liner | 2025-07-23 | Z | 2025-07-15 | 30 | 0 | 0 |  | 30 | 40 |  | 11th Floor |  | 8
2025-07-16 | 3871 |  | 74788 | A | DONE | 2 | S | neal | UW-WITTE HALL 6250003 |  | 2025-07-17 | Z | 2025-07-16 | 40 | 0 | 0 |  | 0 | 50 |  | Misc |  | 1
2025-07-15 | 1475 | bth | L01_D_SALP_001 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 70 | 40 | 120 | A | 0 | 290 |  |  |  | 43
2025-07-15 | 1476 | bth | L01_D_SALP_002 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 43
2025-07-15 | 1477 | bth | L01_D_SALP_003 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 60 | 40 | 140 | A | 0 | 290 |  |  |  | 43
2025-07-15 | 1478 | bth | L01_D_SALP_004 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 50 | 40 | 90 | A | 0 | 240 |  |  |  | 43
2025-07-15 | 1479 | bth | L01_D_SALP_005 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 70 | 80 | 70 | A | 0 | 570 |  |  |  | 43
2025-07-15 | 1480 | bth | L01_D_SALP_006 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 60 | 60 | 90 | A | 0 | 240 |  |  |  | 43
2025-07-15 | 1481 | bth | L01_D_SALP_007 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 60 | 50 | 90 | A | 0 | 240 |  |  |  | 43
2025-07-15 | 1482 | bth | L01_D_SALP_008 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 43
2025-07-15 | 1483 | bth | L01_D_SALP_009 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 50 | 60 | 90 | A | 0 | 230 |  |  |  | 43
2025-07-15 | 1484 | bth | L01_D_SALP_010 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 40 | 60 | 90 | A | 0 | 220 |  |  |  | 43
2025-07-15 | 1485 | bth | L01_D_SALP_011 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 43
2025-07-15 | 1486 | bth | L01_D_SALP_012 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 70 | 60 | 30 | A | 0 | 170 |  |  |  | 43
2025-07-15 | 1487 | bth | L01_D_SALP_013 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 50 | 110 | 0 |  | 0 | 200 |  |  |  | 43
2025-07-15 | 1488 | bth | L01_D_SALP_014 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 40 | 50 | 0 |  | 0 | 90 |  |  |  | 43
2025-07-15 | 1489 | bth | L01_D_SALP_015 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 60 | 30 | 60 | A | 0 | 180 |  |  |  | 43
2025-07-15 | 1490 | bth | L01_D_SALP_016 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-07-09 | Z | 2025-05-27 | 50 | 60 | 40 | A | 0 | 160 |  |  |  | 43
2025-07-15 | 1491 |  | L01_D_RAD_001 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-07-09 | Z | 2025-05-27 | 80 | 0 | 0 |  | 70 | 130 |  |  |  | 43
2025-07-15 | 1492 | bth | L01_D_RAD_002 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 43
2025-07-15 | 1493 |  | L01_D_RAD_003 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 80 | 0 | 0 |  | 70 | 120 |  |  |  | 43
2025-07-15 | 1494 |  | L01_D_RAD_004 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 90 | 0 | 40 | A | 90 | 160 |  |  |  | 43
2025-07-15 | 1495 |  | L01_D_RAD_005 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 80 | 0 | 40 | A | 90 | 150 |  |  |  | 43
2025-07-15 | 1496 |  | L01_D_RAD_006 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 70 | 0 | 40 | A | 80 | 140 |  |  |  | 43
2025-07-15 | 1497 |  | L01_D_RAD_007 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 90 | 0 | 40 | A | 90 | 160 |  |  |  | 43
2025-07-15 | 1498 | bth | L01_D_RAD_008 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 43
2025-07-15 | 1499 |  | L01_D_RAD_009 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 100 | 0 | 40 | A | 100 | 180 |  |  |  | 43
2025-07-15 | 1900 |  | L01_D_RAD_010 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 60 | 0 | 40 | A | 80 | 160 |  |  |  | 43
2025-07-15 | 1901 | bth | L01_D_RAD_011 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 43
2025-07-15 | 1902 | bth | L01_D_RAD_012 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 40 | 20 | 0 |  | 30 | 60 |  |  |  | 43
2025-07-15 | 1903 | bth | L01_D_RAD_013 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-07-09 | Z | 2025-05-27 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 43
2025-07-15 | 1904 | bth | L01_D_RAD_014 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 40 | 60 | 0 |  | 20 | 100 |  |  |  | 43
2025-07-15 | 1905 | bth | L01_D_RAD_015 | A | DONE | 13 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-07-09 | Z | 2025-05-27 | 320 | 0 | 0 |  | 0 | 910 |  |  |  | 43
2025-07-14 | 1924 | w | L02_A_KEA_002 | A | DONE | 10 | S | ss | WAUNAKEE MS 6230013 |  | 2025-07-03 | Z | 2025-06-30 | 90 | 0 | 0 |  | 0 | 230 |  |  |  | 3
[6 empty] | 1215 | [13 empty] | 42650 |  |  |  | 20430 | 47.9%
WEEK OF 7-21-2025
2025-07-21 | 2734 |  | 75194 | A | DONE | 8 | S-M |  | BARTILLION 6240024 | spiralmate | 2025-07-16 | Z | 2025-07-03 | 110 | 0 | 80 | A | 0 | 220 |  | AV 1-17 |  | 13
2025-07-21 | 2735 |  | 75195 | A | DONE | 4 | S |  | BARTILLION 6240024 | 1" liner | 2025-07-16 | Z | 2025-07-03 | 90 | 0 | 0 |  | 80 | 170 |  | Misc |  | 13
2025-07-23 | 2736 |  | 75196 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2025-07-16 | Z | 2025-07-03 | 40 | 0 | 0 |  | 0 | 60 |  | 1st Floor Grille Outs |  | 13
2025-07-25 | 2743 | sp | 75206 | A | DONE | 2 | S |  | BARTILLION 6240024 | spiralmates | 2025-07-29 | Z | 2025-07-16 | 30 | 0 | 0 |  | 0 | 40 |  | Intake outs |  | 13
2025-07-21 | 245 |  | 85362 | A | DONE | 2 | S |  | CUMMINS 30004604 | flex | 2025-07-25 | Z | 2025-07-11 | 40 | 0 | 0 |  | 0 | 70 |  | Air Comp. |  | 14
2025-07-25 | 255 |  | 72425 | A | DONE | 2 | S |  | DEFOREST MS 4250020 |  | 2025-07-24 | Z | 2025-07-24 | 20 | 0 | 0 |  | 0 | 20 |  | Disc |  | 0
2025-07-25 | 3520 | sp | 73674 | A | DONE | 80 | M |  | DELLSHIRE 6240017 |  | 2025-07-28 | Z | 2025-07-11 | 100 | 1890 | 0 |  | 0 | 2270 |  | Area B Attic EA |  | 17
2025-07-23 | 1616 | w | 73911 | A | DONE | 2 | S | ss | DOC JDC 6240023 |  | 2025-07-31 | Z | 2025-07-10 | 20 | 0 | 0 |  | 0 | 50 |  | Dishwasher Drop |  | 21
2025-07-23 | 1618 | w | 73913 | A | DONE | 2 | S | BI | DOC JDC 6240023 |  | 2025-07-31 | Z | 2025-07-10 | 40 | 0 | 0 |  | 0 | 130 |  | Kitchen EA Drop |  | 21
2025-07-22 | 1016 |  | 56819 - 56822 | A | DONE | 24 | M |  | EXACT TL-3 6240028 | flex | 2025-07-28 | Z | 2025-07-17 | 580 | 0 | 0 |  | 0 | 1680 |  | CRAH-2 |  | 11
2025-07-25 | 256 |  | 69988 | A | DONE | 2 | S |  | HISTOSONICS 6250007 |  | 2025-07-30 | Z | 2025-07-25 | 20 | 0 | 0 |  | 0 | 30 |  | Sleeves |  | 5
2025-07-23 | 253 |  | 65690 , 65693 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-07-24 | Z | 2025-07-22 | 40 | 0 | 0 |  | 0 | 60 |  | RTU-2 RA , RTU-1 SA |  | 2
2025-07-22 | 254 |  | 69987 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-07-24 | Z | 2025-07-22 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeves |  | 2
2025-07-25 | 250 | w | 84292 | A | DONE | 2 | S | ss | KEVIN M. 1000382 |  | 2025-07-31 | Z | 2025-07-16 | 20 | 0 | 0 |  | 0 | 60 |  | Misc |  | 15
2025-07-22 | 1727 |  | 74239 - 74240 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-07-23 | Z | 2025-07-17 | 80 | 0 | 0 |  | 0 | 150 |  | RTU-1 SA |  | 6
2025-07-21 | 1730 |  | 74246 | A | DONE | 2 | S |  | MCDS 6250005 | paint | 2025-07-23 | Z | 2025-07-21 | 20 | 0 | 0 |  | 20 | 30 |  | TA Box |  | 2
2025-07-21 | 4503 |  | 76112 | A | DONE | 4 | S-M |  | MONONA GROVE HS 6250016 |  | 2025-07-22 | Z | 2025-07-21 | 100 | 0 | 0 |  | 60 | 120 |  | VAV |  | 1
2025-07-21 | 2055 | bth | SALP-L1A-01 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 90 | 50 | 60 | A | 120 | 270 |  |  |  | 34
2025-07-21 | 2072 |  | SALP-L1A-18 | A | DONE | 9 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 50 | 0 | 160 | A | 180 | 300 |  |  |  | 34
2025-07-21 | 2073 | bth | SALP-L1A-19 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 30 | 20 | 140 | A | 130 | 250 |  |  |  | 34
2025-07-21 | 2076 | bth | SALP-L1A-22 | A | DONE | 9 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-15 | Z | 2025-06-11 | 150 | 70 | 0 |  | 120 | 270 |  |  |  | 34
2025-07-23 | 3814 | bth | SA-LL-01 | A | DONE | 26 | M |  | MONROE HS 6240018 | 2" liner | 2025-07-22 | Z | 2025-05-15 | 290 | 80 | 260 | A | 400 | 890 |  |  |  | 68 | 2025-06-19
2025-07-22 | 3815 | bth | TA-LL-01 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-07-22 | Z | 2025-05-15 | 30 | 20 | 0 |  | 20 | 50 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3816 | bth | SA-LL-02 | A | DONE | 16 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-22 | Z | 2025-05-15 | 150 | 120 | 110 | A | 200 | 480 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3817 |  | SA-LL-03 | A | DONE | 20 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-22 | Z | 2025-05-15 | 320 | 0 | 170 | A | 360 | 620 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3818 | bth | SA-LL-04 | A | DONE | 7 | S |  | MONROE HS 6240018 | flex , 2" liner | 2025-07-22 | Z | 2025-05-15 | 110 | 20 | 30 | A | 100 | 200 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3819 |  | SA-LL-05 | A | DONE | 17 | M |  | MONROE HS 6240018 | 2" liner | 2025-07-22 | Z | 2025-05-15 | 420 | 0 | 0 |  | 370 | 690 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3820 | bth | SA-LL-06 | A | DONE | 19 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-22 | Z | 2025-05-15 | 180 | 140 | 150 | A | 210 | 580 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3821 | bth | SA-LL-07 | A | DONE | 18 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-07-22 | Z | 2025-05-15 | 110 | 230 | 90 | A | 150 | 530 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3822 |  | RA-LL-03 | A | DONE | 88 | L |  | MONROE HS 6240018 | VD , partial , 1" liner | 2025-07-22 | Z | 2025-05-15 | 850 | 0 | 1350 | A | 1810 | 4110 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3823 | bth | RA-LL-04 | A | DONE | 5 | S | neal | MONROE HS 6240018 | flex , 1" liner | 2025-07-22 | Z | 2025-05-15 | 100 | 20 | 0 |  | 60 | 140 |  |  |  | 68 | 2025-06-19
2025-07-23 | 3824 |  | RA-LL-05 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-07-22 | Z | 2025-05-15 | 50 | 0 | 0 |  | 20 | 80 |  |  |  | 68 | 2025-06-19
2025-07-21 | 3835d |  | 85316 - 85317 | A | DONE | 3 | S | neal | MONROE HS 6240018 |  | 2025-07-22 | Z | 2025-07-21 | 60 | 0 | 0 |  | 0 | 80 |  | Missing duct |  | 1
2025-07-23 | 3252 |  | 79514 | A | DONE | 2 | S | BI | ONE 09 6240037 |  | 2025-07-25 | Z | 2025-07-23 | 20 | 0 | 0 |  | 0 | 20 |  | Grease Flange |  | 2
2025-07-22 | 4229 |  | 79691 | A | DONE | 3 | S |  | PECATONICA 6240005 | 1" liner | 2025-07-28 | Z | 2025-07-18 | 70 | 0 | 0 |  | 50 | 100 |  | Corridor 125 |  | 10
2025-07-25 | 1845 | bth | L1B-TA 2 | A | DONE | 4 | S |  | PEWAUKEE HS 6240030 | bird s. , 1" liner | 2025-07-30 | Z | 2025-07-08 | 60 | 20 | 0 |  | 30 | 80 |  |  |  | 22 | 2025-07-23
2025-07-25 | 1846 | sp | L1B-SAMP 3 | A | DONE | 16 | M |  | PEWAUKEE HS 6240030 | oval | 2025-07-30 | Z | 2025-07-08 | 90 | 310 | 0 |  | 0 | 600 |  |  |  | 22 | 2025-07-23
2025-07-25 | 4643 |  | 74122 - 74123 | A | DONE | 4 | S |  | PEWAUKEE HS 6240030 | 1" liner | 2025-07-30 | Z | 2025-07-17 | 80 | 0 | 0 |  | 20 | 110 |  | V-120 |  | 13
2025-07-23 | 4645 | bth | 76708 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-07-30 | Z | 2025-07-22 | 20 | 30 | 0 |  | 0 | 60 |  | Old Culinary |  | 8
2025-07-25 | 4647 | sp | 74125 | A | DONE | 10 | S |  | PEWAUKEE HS 6240030 |  | 2025-07-30 | Z | 2025-07-23 | 20 | 210 | 0 |  | 0 | 220 |  | VAV 120 |  | 7
2025-07-25 | 1366 |  | L02_AREA_200_EA_001 | delete |  |  | S |  | PROJECT DOVE 6240041 | bird s. | 2025-08-07 | Z | 2025-06-11 | 0 | 0 | 0 |  | 0 | 0 |  | BADGER |  | 57 | 2025-07-03
2025-07-25 | 1367 |  | L02_AREA_200_MA_003 | delete |  |  | S |  | PROJECT DOVE 6240041 | VD's | 2025-08-07 | Z | 2025-06-11 | 0 | 0 | 0 |  | 0 | 0 |  | BADGER |  | 57 | 2025-07-03
2025-07-25 | 1368 |  | L02_AREA_200_MA_006 | delete |  |  | S |  | PROJECT DOVE 6240041 | VD's | 2025-08-07 | Z | 2025-06-11 | 0 | 0 | 0 |  | 0 | 0 |  | BADGER |  | 57 | 2025-07-03
2025-07-25 | 1371 |  | L02_AREA_200_RAMP_002 | delete |  |  | S |  | PROJECT DOVE 6240041 |  | 2025-08-07 | Z | 2025-06-11 | 0 | 0 | 0 |  | 0 | 0 |  | BADGER |  | 57 | 2025-07-03
2025-07-21 | 1381 |  | L2_AREA_500_EA_001 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-17 | Z | 2025-06-26 | 170 | 0 | 0 |  | 0 | 220 |  |  |  | 21
2025-07-21 | 1382 |  | L2_AREA_500_EA_002 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-17 | Z | 2025-06-26 | 110 | 0 | 0 |  | 0 | 180 |  |  |  | 21
2025-07-21 | 1383 |  | L2_AREA_500_EA_003 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-17 | Z | 2025-06-26 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 21
2025-07-21 | 1384 | bth | L2_AREA_500_MA_001 | A | DONE | 63 | L |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-07-17 | Z | 2025-06-26 | 540 | 1030 | 0 |  | 0 | 3290 |  |  |  | 21
2025-07-25 | 1385 | sp | L2_AREA_500_MA_002 | A | DONE | 46 | L |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-07-23 | Z | 2025-06-26 | 290 | 860 | 0 |  | 0 | 2310 |  |  |  | 27
2025-07-21 | 1388 |  | L2_AREA_500_OA_001 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | VD , bird s. | 2025-07-17 | Z | 2025-06-26 | 70 | 0 | 0 |  | 0 | 130 |  |  |  | 21
2025-07-21 | 1389 |  | L2_AREA_500_RAMP_001 | A | DONE | 12 | M |  | PROJECT DOVE 6240041 | bird s. | 2025-07-17 | Z | 2025-06-26 | 300 | 0 | 0 |  | 0 | 870 |  |  |  | 21
2025-07-21 | 1390 |  | L2_AREA_500_RAMP_002 | A | DONE | 13 | M |  | PROJECT DOVE 6240041 | bird s. | 2025-07-17 | Z | 2025-06-26 | 310 | 0 | 0 |  | 0 | 870 |  |  |  | 21
2025-07-25 | 4560 |  | L02_AREA_700_EAST EA_001 | A | DONE | 4 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-07-23 | Z | 2025-07-08 | 80 | 0 | 0 |  | 0 | 210 |  |  |  | 15
2025-07-25 | 4561 |  | L02_AREA_700_EAST EA_002 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-23 | Z | 2025-07-08 | 80 | 0 | 0 |  | 0 | 210 |  |  |  | 15
2025-07-22 | 4562 | sp | L02_AREA_700_EAST MA_001 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | spiral mate | 2025-07-23 | Z | 2025-07-08 | 30 | 60 | 0 |  | 0 | 180 |  |  |  | 15
2025-07-22 | 4563 | sp | L02_AREA_700_EAST MA_002 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-08 | 30 | 90 | 0 |  | 0 | 130 |  |  |  | 15
2025-07-23 | 4564 | sp | L02_AREA_700_EAST MA_003 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-08 | 20 | 140 | 0 |  | 0 | 140 |  |  |  | 15
2025-07-25 | 4565 |  | L02_AREA_700_EAST MA_004 | A | DONE | 9 | M |  | PROJECT DOVE 6240041 | VD | 2025-07-23 | Z | 2025-07-08 | 210 | 0 | 0 |  | 0 | 610 |  |  |  | 15
2025-07-25 | 4566 |  | L02_AREA_700_EAST MA_005 | A | DONE | 9 | M |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-07-23 | Z | 2025-07-08 | 210 | 0 | 0 |  | 0 | 650 |  |  |  | 15
2025-07-25 | 4567 |  | L02_AREA_700_EAST MA_006 | A | DONE | 9 | M |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-07-23 | Z | 2025-07-08 | 210 | 0 | 0 |  | 0 | 590 |  |  |  | 15
2025-07-25 | 4568 |  | L02_AREA_700_EAST MA_007 | A | DONE | 10 | M |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-07-23 | Z | 2025-07-08 | 220 | 0 | 0 |  | 0 | 640 |  |  |  | 15
2025-07-22 | 4569 | sp | L02_AREA_700_EAST MA_008 | A | DONE | 10 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-08 | 40 | 210 | 0 |  | 0 | 370 |  |  |  | 15
2025-07-23 | 4570 | sp | L02_AREA_700_EAST MA_009 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-08 | 60 | 140 | 0 |  | 0 | 220 |  |  |  | 15
2025-07-22 | 4571 | sp | L02_AREA_700_EAST MA_010 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | spiral mates | 2025-07-23 | Z | 2025-07-08 | 20 | 40 | 0 |  | 0 | 160 |  |  |  | 15
2025-07-25 | 4572 |  | L02_AREA_700_EAST RAMP_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-07-23 | Z | 2025-07-08 | 120 | 0 | 70 | A | 0 | 330 |  |  |  | 15
2025-07-25 | 4573 |  | L02_AREA_700_EAST RAMP_002 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-07-23 | Z | 2025-07-08 | 100 | 0 | 80 | A | 0 | 400 |  |  |  | 15
2025-07-25 | 4574 |  | L02_AREA_700_EAST RAMP_003 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-23 | Z | 2025-07-08 | 140 | 0 | 0 |  | 0 | 320 |  |  |  | 15
2025-07-25 | 4575 |  | L02_AREA_700_EAST RAMP_004 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-23 | Z | 2025-07-08 | 110 | 0 | 0 |  | 0 | 320 |  |  |  | 15
2025-07-25 | 4582 | bth | L01_AREA_052_SAMP_001 | A | DONE | 16 | M |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 300 | 20 | 70 | A | 0 | 750 |  |  |  | 13
2025-07-25 | 4583 | bth | L01_AREA_052_SAMP_002 | A | DONE | 13 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 120 | 60 | 130 | A | 0 | 500 |  |  |  | 13
2025-07-23 | 4584 | sp | L01_AREA_052_SAMP_003 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 20 | 100 | 0 |  | 0 | 140 |  |  |  | 13
2025-07-23 | 4585 | sp | L01_AREA_052_SAMP_004 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 13
2025-07-23 | 4586 | sp | L01_AREA_052_SAMP_005 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 40 | 80 | 0 |  | 0 | 140 |  |  |  | 13
2025-07-23 | 4587 | sp | L01_AREA_052_SAMP_006 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 20 | 100 | 0 |  | 0 | 120 |  |  |  | 13
2025-07-23 | 4588 | sp | L01_AREA_052_SAMP_007 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 30 | 80 | 0 |  | 0 | 120 |  |  |  | 13
2025-07-23 | 4589 | sp | L01_AREA_052_SAMP_008 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 20 | 60 | 0 |  | 0 | 60 |  |  |  | 13
2025-07-23 | 4590 | sp | L01_AREA_052_SAMP_009 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 13
2025-07-23 | 4591 |  | L01_AREA_052_SAMP_010 | A | DONE | 12 | M |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 210 | 0 | 80 | A | 0 | 480 |  |  |  | 13
2025-07-22 | 4592 | sp | L01_AREA_052_SAMP_011 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 20 | 100 | 0 |  | 0 | 130 |  |  |  | 13
2025-07-22 | 4593 | sp | L01_AREA_052_SAMP_012 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 20 | 70 | 0 |  | 0 | 100 |  |  |  | 13
2025-07-23 | 4594 | sp | L01_AREA_052_SAMP_013 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-10 | 20 | 100 | 0 |  | 0 | 100 |  |  |  | 13
2025-07-25 | 4595 |  | L01_AREA_052_TA_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-07-23 | Z | 2025-07-10 | 40 | 0 | 0 |  | 30 | 70 |  |  |  | 13
2025-07-25 | 4596 |  | L01_AREA_052_TA_002 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-07-23 | Z | 2025-07-10 | 30 | 0 | 0 |  | 30 | 60 |  |  |  | 13
2025-07-25 | 4597 |  | L01_AREA_052_TA_003 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-07-23 | Z | 2025-07-10 | 80 | 0 | 0 |  | 70 | 130 |  |  |  | 13
2025-07-25 | 4598 |  | L01_AREA_052_TA_004 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-07-23 | Z | 2025-07-10 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 13
2025-07-25 | 4599 |  | L01_AREA_052_TA_005 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-07-23 | Z | 2025-07-10 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 13
2025-07-22 | 4713 |  | L02_AREA_052_RAMP_001 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-07-17 | Z | 2025-07-14 | 90 | 0 | 0 |  | 0 | 200 |  |  |  | 3
2025-07-21 | 4714 |  | L02_AREA_052_SAMP_011 | A | DONE | 10 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-07-17 | Z | 2025-07-14 | 200 | 0 | 40 | A | 0 | 340 |  |  |  | 3
2025-07-22 | 4761 |  | 76163 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-24 | Z | 2025-07-18 | 20 | 0 | 0 |  | 0 | 50 |  | Roof curb |  | 6
2025-07-22 | 4762 |  | 76164 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-23 | Z | 2025-07-21 | 20 | 0 | 0 |  | 0 | 20 |  | EF-11 |  | 2
2025-07-23 | 4763 |  | 76201 | A | DONE | 4 | S-M | neal | PROJECT DOVE 6240041 |  | 2025-07-24 | Z | 2025-07-22 | 100 | 0 | 0 |  | 0 | 140 |  | Flashing |  | 2
2025-07-25 | 3047 |  | 81849 | A | DONE | 5 | S-M |  | PROMEGA BTC 6230022 |  | 2025-07-28 | Z | 2025-07-14 | 120 | 0 | 0 |  | 0 | 310 |  | Misc |  | 14
2025-07-21 | 1982 |  | 98250 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-07-23 | Z | 2025-07-21 | 20 | 0 | 0 |  | 0 | 20 |  | Gussets |  | 2
2025-07-22 | 1983 | sp | 45811 | A | DONE | 2 | S-M | neal | REEDSBURG HS 6250010 |  | 2025-07-23 | Z | 2025-07-21 | 60 | 30 | 0 |  | 0 | 120 |  | EA outs |  | 2
2025-07-21 | 1984 |  | 75812 | A | DONE | 2 | S |  | REEDSBURG HS 6250010 |  | 2025-07-24 | Z | 2025-07-21 | 20 | 0 | 0 |  | 0 | 20 |  | Riser Clamps |  | 3
2025-07-21 | 3691 |  | 68496 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-07-27 | Z | 2025-07-17 | 20 | 0 | 0 |  | 0 | 30 |  | OR-7 |  | 10
2025-07-22 | 3692 |  | 68497 | A | DONE | 2 | S |  | SPH SURGERY 6240039 | paint | 2025-07-27 | Z | 2025-07-18 | 20 | 0 | 0 |  | 20 | 20 |  | GRD |  | 9
2025-07-23 | 3693 |  | 68877 , 68498 | A | DONE | 6 | S-M |  | SPH SURGERY 6240039 | flex | 2025-07-28 | Z | 2025-07-22 | 140 | 0 | 0 |  | 0 | 340 |  | OA-7 , PH |  | 6
2025-07-21 | 844 | pt/w | 75507 | A | DONE | 2 | S-M | pt.ss | SW HEALTH OR 5 6250004 | nipple | 2025-07-28 | Z | 2025-06-30 | 30 | 0 | 0 |  | 0 | 70 |  | Misc |  | 28 | 2025-07-21
2025-07-21 | 845 | bth | 75508 - 75510 | A | DONE | 5 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-07-28 | Z | 2025-06-30 | 60 | 30 | 30 | A | 0 | 160 |  | Misc |  | 28 | 2025-07-21
2025-07-25 | 4654 |  | 82226 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-07-28 | Z | 2025-07-15 | 20 | 0 | 0 |  | 0 | 20 |  | Rm 2170 |  | 13
2025-07-25 | 4655 |  | 82227 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-08-04 | Z | 2025-07-23 | 20 | 0 | 0 |  | 0 | 20 |  | RTU Patch |  | 12
2025-07-25 | 3783 | w | L5-EAT 583 SS | A | DONE | 2 | S | pt.ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-11 | 30 | 0 | 0 |  | 0 | 70 |  |  |  | 19
2025-07-23 | 3789 |  | 61936 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-18 | 20 | 0 | 0 |  | 0 | 20 |  | 5th Floor tie in |  | 12
2025-07-25 | 3791 | sp | L5B-BCU SA 1 | A | DONE | 4 | S |  | UW-AVRL 6240038 |  | 2025-07-30 | 49700+M3765T3749:T3784 | 2025-07-22 | 40 | 40 | 0 |  | 0 | 120 |  |  |  | 8
2025-07-23 | 3793 | w | 61937 | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-22 | 20 | 0 | 0 |  | 0 | 20 |  | Roof Tie in |  | 8
2025-07-25 | 3767r |  | DH-VW123 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-07-28 | Z | 2025-07-25 | 20 | 0 | 0 |  | 0 | 60 |  | Tear drop hangers |  | 3
2025-07-23 | 2031 | bth | L4-RAMP 10 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-07-17 | Z | 2025-06-23 | 190 | 20 | 130 | A | 50 | 450 |  |  |  | 24
2025-07-21 | 2032 | bth | L4-RAMP 11 | A | DONE | 16 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 210 | 30 | 160 | A | 80 | 480 |  |  |  | 24
2025-07-22 | 2033 | bth | L4-RAMP 12 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 90 | 70 | 80 | A | 50 | 280 |  |  |  | 24
2025-07-23 | 2034 | bth | L4-RAMP 13 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 160 | 20 | 120 | A | 80 | 350 |  |  |  | 24
2025-07-22 | 2035 | bth | L4-RAMP 14 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 100 | 40 | 200 | A | 70 | 420 |  |  |  | 24
2025-07-22 | 2036 | bth | L4-RAMP 15 | A | DONE | 9 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 140 | 50 | 30 | A | 70 | 240 |  |  |  | 24
2025-07-23 | 2037 | bth | L4-RAMP 16 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 110 | 40 | 150 | A | 70 | 380 |  |  |  | 24
2025-07-23 | 2038 | bth | L4-RAMP 17 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 120 | 20 | 100 | A | 40 | 280 |  |  |  | 24
2025-07-23 | 2039 | bth | L4-RAMP 18 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 90 | 0 | 70 | A | 40 | 220 |  |  |  | 24
2025-07-23 | 2040 | bth | L4-RAMP 19 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 120 | 20 | 120 | A | 60 | 330 |  |  |  | 24
2025-07-22 | 2041 | bth | L4-RAMP 20 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 160 | 60 | 30 | A | 20 | 300 |  |  |  | 24
2025-07-23 | 2042 | bth | L4-RAMP 21 | A | DONE | 25 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-23 | 280 | 100 | 230 | A | 70 | 690 |  |  |  | 24
2025-07-22 | 2045 | bth | L4-RAMP 4 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-07-17 | Z | 2025-06-24 | 290 | 20 | 130 | A | 30 | 710 |  |  |  | 23
2025-07-22 | 2046 | bth | L4-RAMP 5.1 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-24 | 210 | 20 | 50 | A | 60 | 400 |  |  |  | 23
2025-07-21 | 2047 | bth | L4-RAMP 5.2 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-24 | 40 | 150 | 0 |  | 30 | 190 |  |  |  | 23
2025-07-21 | 2048 | bth | L4-RAMP 6 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-24 | 120 | 40 | 170 | A | 50 | 420 |  |  |  | 23
2025-07-21 | 2049 | bth | L4-RAMP 7 | A | DONE | 14 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-24 | 140 | 20 | 170 | A | 80 | 390 |  |  |  | 23
2025-07-22 | 2050 | bth | L4-RAMP 8 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-17 | Z | 2025-06-24 | 150 | 30 | 190 | A | 50 | 460 |  |  |  | 23
2025-07-23 | 2051 |  | L4-RAMP 9 | A | DONE | 23 | M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-07-17 | Z | 2025-06-24 | 280 | 0 | 290 | A | 310 | 700 |  |  |  | 23
2025-07-25 | 2053 | bth | L4-SAMP 7 | A | DONE | 13 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-24 | Z | 2025-06-25 | 100 | 60 | 150 | A | 0 | 390 |  |  |  | 29
2025-07-25 | 2054 | bth | L4-SAMP 8 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-24 | Z | 2025-06-25 | 30 | 40 | 170 | A | 0 | 280 |  |  |  | 29
2025-07-25 | 2055 | bth | L4-SAMP 9 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-24 | Z | 2025-06-25 | 50 | 40 | 150 | A | 0 | 290 |  |  |  | 29
2025-07-25 | 2056 | bth | L4-SAMP 10 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-24 | Z | 2025-06-25 | 120 | 20 | 150 | A | 0 | 340 |  |  |  | 29
2025-07-25 | 2057 | bth | L4-SAMP 11 | A | DONE | 18 | M |  | UW-LEVY HALL 6230028 |  | 2025-07-24 | Z | 2025-06-25 | 230 | 50 | 150 | A | 0 | 600 |  |  |  | 29
2025-07-25 | 2058 |  | L4-EAMP 1 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-07-24 | Z | 2025-06-25 | 50 | 0 | 0 |  | 20 | 70 |  |  |  | 29
2025-07-23 | 2059 | sp | L4-EAMP 2 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-24 | Z | 2025-06-25 | 20 | 120 | 0 |  | 0 | 130 |  |  |  | 29
2025-07-25 | 2060 |  | L4-EAMP 3 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-24 | Z | 2025-06-25 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 29
2025-07-25 | 2061 | bth | L4-EAMP 4 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-24 | Z | 2025-06-25 | 20 | 50 | 0 |  | 20 | 80 |  |  |  | 29
2025-07-25 | 2062 |  | L4-EAMP 5 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-24 | Z | 2025-06-25 | 140 | 0 | 20 | A | 20 | 180 |  |  |  | 29
2025-07-25 | 2063 |  | L4-EAMP 6 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-07-24 | Z | 2025-06-25 | 130 | 0 | 80 | A | 20 | 280 |  |  |  | 29
2025-07-25 | 2064 |  | L4-EAMP 7 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD's , 1" liner | 2025-07-24 | Z | 2025-06-25 | 120 | 0 | 50 | A | 20 | 210 |  |  |  | 29
2025-07-25 | 2065 | bth | L4-RAMP 1 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-07-28 | Z | 2025-06-26 | 120 | 20 | 100 | A | 0 | 290 |  |  |  | 32
2025-07-25 | 2066 | bth | L4-RAMP 2 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-28 | Z | 2025-06-26 | 150 | 20 | 120 | A | 100 | 370 |  |  |  | 32
2025-07-25 | 2067 | bth | L4-RAMP 3 | A | DONE | 15 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-28 | Z | 2025-06-26 | 190 | 110 | 60 | A | 110 | 410 |  |  |  | 32
2025-07-25 | 2068 | bth | L4-SAMP 1 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-28 | Z | 2025-06-26 | 60 | 110 | 120 | A | 0 | 380 |  |  |  | 32
2025-07-25 | 2069 | bth | L4-SAMP 2 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-28 | Z | 2025-06-26 | 50 | 40 | 90 | A | 0 | 230 |  |  |  | 32
2025-07-25 | 2070 | bth | L4-SAMP 3 | A | DONE | 18 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-28 | Z | 2025-06-26 | 260 | 70 | 100 | A | 0 | 490 |  |  |  | 32
2025-07-25 | 2073 | bth | L4-SAMP 6 | A | DONE | 16 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-28 | Z | 2025-06-26 | 100 | 30 | 260 | A | 0 | 260 |  |  |  | 32
2025-07-22 | 2075 |  | 82969 | A | DONE | 11 | S |  | UW-LEVY HALL 6230028 | 1" DW | 2025-07-17 | Z | 2025-07-07 | 260 | 0 | 0 |  | 80 | 260 |  | LL-RAMP 6 |  | 10
2025-07-23 | 2077 |  | 82973 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-07-28 | Z | 2025-07-15 | 20 | 0 | 0 |  | 0 | 20 |  | L5 , L3 Misc |  | 13
2025-07-22 | 2079 |  | 82977 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-07-22 | Z | 2025-07-17 | 30 | 0 | 0 |  | 0 | 50 |  | L4 W. Shaft RAMP 2 |  | 5
2025-07-25 | 3993 |  | 82175 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-08-04 | Z | 2025-07-16 | 20 | 0 | 0 |  | 0 | 60 |  | Louver Att. |  | 19
2025-07-23 | 3995 |  | 82177 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2025-07-28 | Z | 2025-07-22 | 20 | 0 | 0 |  | 0 | 20 |  | 1st |  | 6
2025-07-25 | 3996 |  | 82178 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | VD's | 2025-07-28 | Z | 2025-07-23 | 20 | 0 | 0 |  | 0 | 20 |  | RA Chase |  | 5
2025-07-21 | 1879 |  | 75714 - 75715 , 66646 | A | DONE | 6 | S-M |  | UWP-FH 6240021 | paint , flex | 2025-07-24 | Z | 2025-07-10 | 150 | 0 | 0 |  | 20 | 260 |  | Gym , 1st,2nd floor |  | 14
2025-07-25 | 1883 |  | 75717 | A | DONE | 2 | S |  | UWP-FH 6240021 |  | 2025-07-31 | Z | 2025-07-24 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor |  | 7
2025-07-21 | 2872 |  | 84869 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-07-22 | Z | 2025-07-02 | 40 | 0 | 0 |  | 30 | 50 |  | 1st floor TA |  | 20
2025-07-25 | 3584 |  | 85024 | A | DONE | 2 | S |  | UW-WHITEWATER 6250001 |  | 2025-08-01 | Z | 2025-07-17 | 20 | 0 | 0 |  | 0 | 20 |  | TA |  | 15
2025-07-22 | 3582 |  | 85021 - 85023 | A | DONE | 5 | S-M | neal | UW-WHITEWATER ML 6250001 |  | 2025-07-25 | Z | 2025-07-17 | 120 | 0 | 0 |  | 0 | 180 |  | RHC-2054-3 |  | 8
2025-07-22 | 3586 |  | 85033 | A | DONE | 2 | S | neal | UW-WHITEWATER ML 6250001 |  | 2025-07-25 | Z | 2025-07-21 | 20 | 0 | 0 |  | 0 | 20 |  | RHC-2054-2 |  | 4
2025-07-22 | 3587 |  | 85034 | A | DONE | 2 | S | neal | UW-WHITEWATER ML 6250001 |  | 2025-07-25 | Z | 2025-07-22 | 40 | 0 | 0 |  | 0 | 50 |  | EF-12 |  | 3
2025-07-23 | 3872 | w | 74789 | A | DONE | 2 | S |  | UW-WITTE HALL 6250003 |  | 2025-07-30 | Z | 2025-07-21 | 30 | 0 | 0 |  | 0 | 90 |  | Curb Cap |  | 9
2025-07-25 | 3875 |  | 74792 | A | DONE | 2 | S-M | neal | UW-WITTE HALL 6250003 |  | 2025-07-25 | Z | 2025-07-23 | 50 | 0 | 0 |  | 0 | 60 |  | Flashing |  | 2
2025-07-25 | 3878 |  | 74796 | A | DONE | 8 | S | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-07-25 | Z | 2025-07-25 | 0 | 0 | 200 | A | 190 | 190 |  | 10th floor |  | 0
2025-07-21 | 601 |  | 83361 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-07-25 | Z | 2025-07-10 | 50 | 0 | 0 |  | 0 | 80 |  | Reducers |  | 15
2025-07-25 | 602 |  | 83362 , 64 , 66 | A | DONE | 3 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-07-25 | Z | 2025-07-10 | 70 | 0 | 0 |  | 0 | 100 |  | 2nd Floor RA , Rm 2313 |  | 15
2025-07-25 | 609 |  | 83367 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-07-25 | Z | 2025-07-14 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd Floor Corr RA |  | 11
2025-07-25 | 610 |  | 83368 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-01 | Z | 2025-07-22 | 250 | 0 | 0 |  | 0 | 290 |  | Misc |  | 10
2025-07-25 | 1928 |  | 83462 - 83463 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-07-25 | Z | 2025-07-09 | 80 | 0 | 0 |  | 0 | 130 |  | DOAS 2 SOA |  | 16
2025-07-21 | 2715 |  | 76111 | A | DONE | 2 | S |  | WSCC 6240006 | 2" DW, s.mates | 2025-07-22 | Z | 2025-07-18 | 40 | 0 | 0 |  | 20 | 110 |  | DHU-2 |  | 4
2025-07-23 | 2716 |  | 76113 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2025-07-25 | Z | 2025-07-23 | 20 | 0 | 0 |  | 0 | 20 |  | TA |  | 2
[6 empty] | 1387 | [13 empty] | 49700 |  |  |  | 9850 | 19.82%
WEEK OF 7-28-2025
2025-07-28 | 1036 |  | 85167 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-07-28 | Z | 2025-07-28 | 30 | 0 | 0 |  | 0 | 90 |  | ERU-1 |  | 0
2025-07-30 | 1037 |  | 85168 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-07-31 | Z | 2025-07-30 | 20 | 0 | 0 |  | 0 | 20 |  | HP sleeve |  | 1
2025-07-30 | 551 |  | 75223 | A | DONE | 2 | S |  | BARTILLION 6240024 | VD | 2025-07-29 | Z | 2025-07-24 | 50 | 0 | 0 |  | 30 | 110 |  | Rm 143 |  | 5
2025-08-01 | 2737 | sp | 75197 - 75198 | A | DONE | 257 | L | perf | BARTILLION 6240024 | s.mates , 1" DW | 2025-07-29 | Z | 2025-07-09 | 850 | 5560 | 0 |  | 2930 | 5190 |  | SA 2nd Dorm 3,4 |  | 20
2025-07-28 | 2742 | bth | 75203 - 75205 | A | DONE | 8 | S-M |  | BARTILLION 6240024 | 1" sp.acoustic,1" liner | 2025-07-29 | Z | 2025-07-16 | 160 | 0 | 30 | A | 100 | 250 |  | SA Main Out / TA |  | 13
2025-07-28 | 2744 |  | 75207 | A | DONE | 6 | S |  | BARTILLION 6240024 | paint | 2025-07-29 | Z | 2025-07-16 | 130 | 0 | 0 |  | 30 | 190 |  | Kitchen RA |  | 13
2025-07-29 | 2747 |  | 75218 - 75219 | A | DONE | 9 | S-M |  | BARTILLION 6240024 |  | 2025-07-29 | Z | 2025-07-24 | 70 | 0 | 140 | A | 0 | 310 |  | SA 2nd Bath / RA Main |  | 5
2025-08-01 | 2749 |  | 75217 | A | DONE | 2 | S |  | BARTILLION 6240024 | 1" liner | 2025-08-07 | Z | 2025-07-24 | 50 | 0 | 0 |  | 0 | 100 |  | SA Main off AHU |  | 14
2025-07-29 | 257 |  | 84733 | A | DONE | 2 | S |  | DEFOREST MS 4250020 |  | 2025-08-01 | Z | 2025-07-28 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 4
2025-07-29 | 1615 |  | 73908 - 73910 | A | DONE | 17 | M |  | DOC JDC 6240023 |  | 2025-07-31 | Z | 2025-07-10 | 420 | 0 | 0 |  | 0 | 620 |  | EA Drops |  | 21
2025-07-28 | 1617 |  | 73912 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-07-31 | Z | 2025-07-10 | 40 | 0 | 0 |  | 0 | 60 |  | EA Drop |  | 21
2025-08-01 | 1017 |  | 56824 | A | DONE | 2 | S | alum | EXACT TL-3 6240028 |  | 2025-08-05 | Z | 2025-07-31 | 20 | 0 | 0 |  | 0 | 20 |  | Glass wash |  | 5
2025-08-01 | 3223 |  | 56699A | A | DONE | 4 | S-M |  | HISTOSONICS 8250016 |  | 2025-08-06 | Z | 2025-07-29 | 100 | 0 | 0 |  | 0 | 220 |  | DI Channel |  | 8
2025-07-28 | 1729 |  | 74243 - 74245 | A | DONE | 6 | S |  | MCDS 6250005 | filter rack | 2025-07-29 | Z | 2025-07-21 | 90 | 0 | 40 | A | 0 | 140 |  | F-1 |  | 8
2025-07-28 | 1731 |  | 74247 | A | DONE | 2 | S |  | MCDS 6250005 | paint | 2025-07-30 | Z | 2025-07-28 | 50 | 0 | 0 |  | 20 | 60 |  | RA box |  | 2
2025-07-29 | 1733 |  | 74248 - 74249 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-07-30 | Z | 2025-07-28 | 40 | 0 | 0 |  | 0 | 60 |  | VAV-4 |  | 2
2025-07-28 | 1732 |  | 74250 | A | DONE | 2 | S |  | MCDS 8250007 |  | 2025-07-28 | Z | 2025-07-28 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2025-07-30 | 2775 | bth | EA-L1F-01 | A | DONE | 6 | S | neal | MONROE HS 6240018 | CD | 2025-08-05 | Z | 2025-04-29 | 40 | 100 | 0 |  | 0 | 150 |  |  |  | 98 | 2025-06-24
2025-07-30 | 2776 |  | EA-L1F-02 | A | DONE | 6 | S |  | MONROE HS 6240018 |  | 2025-08-05 | Z | 2025-04-29 | 0 | 0 | 150 | A | 140 | 280 |  |  |  | 98 | 2025-06-24
2025-07-30 | 2777 |  | EA-L1F-03 | A | DONE | 12 | M | neal | MONROE HS 6240018 | 1" liner | 2025-08-05 | Z | 2025-04-29 | 220 | 0 | 80 | A | 160 | 500 |  |  |  | 98
2025-07-30 | 2778 |  | EA-L1F-04 | A | DONE | 4 | S | neal | MONROE HS 6240018 | 1" liner | 2025-08-05 | Z | 2025-04-29 | 90 | 0 | 0 |  | 80 | 160 |  |  |  | 98 | 2025-06-24
2025-07-30 | 2779 |  | EA-L1F-05 | A | DONE | 4 | S | neal | MONROE HS 6240018 | 1" liner | 2025-08-05 | Z | 2025-04-29 | 90 | 0 | 0 |  | 80 | 180 |  |  |  | 98 | 2025-06-24
2025-08-01 | 2780 |  | RA-L1F-01 | A | DONE | 8 | S-M | neal | MONROE HS 6240018 | CD , 1" liner | 2025-08-05 | Z | 2025-04-29 | 180 | 0 | 0 |  | 120 | 280 |  |  |  | 98 | 2025-06-24
2025-08-01 | 2781 |  | RA-L1F-02 | A | DONE | 31 | M-L |  | MONROE HS 6240018 | CD , 1" liner | 2025-08-05 | Z | 2025-04-29 | 350 | 0 | 420 | A | 590 | 1430 |  |  |  | 98 | 2025-06-24
2025-08-01 | 2782 | sp | SALP-L1F-01 | A | DONE | 21 | M | neal | MONROE HS 6240018 | VD , spiral mates | 2025-08-05 | Z | 2025-04-29 | 150 | 360 | 0 |  | 0 | 680 |  |  |  | 98
2025-08-01 | 2783 | sp | SALP-L1F-02 | A | DONE | 21 | M | neal | MONROE HS 6240018 | VD , spiral mates | 2025-08-05 | Z | 2025-04-29 | 150 | 360 | 0 |  | 0 | 690 |  |  |  | 98
2025-08-01 | 2784 | sp | SALP-L1F-03 | A | DONE | 22 | M | neal | MONROE HS 6240018 | VD , spiral mates | 2025-08-05 | Z | 2025-04-29 | 200 | 350 | 0 |  | 0 | 640 |  |  |  | 98
2025-08-01 | 2786 | bth | SALP-L1F-05 | A | DONE | 62 | L | neal | MONROE HS 6240018 | VD, s. mates , 2" liner | 2025-08-05 | Z | 2025-04-29 | 760 | 790 | 0 |  | 240 | 2570 |  |  |  | 98
2025-08-01 | 2787 | bth | SALP-L1F-06 | A | DONE | 9 | S | neal | MONROE HS 6240018 |  | 2025-08-05 | Z | 2025-04-29 | 60 | 160 | 0 |  | 0 | 270 |  |  |  | 98 | 2025-06-24
2025-08-01 | 2788 | sp | SALP-L1F-07 | A | DONE | 12 | S-M | neal | MONROE HS 6240018 |  | 2025-08-05 | Z | 2025-04-29 | 40 | 240 | 0 |  | 0 | 330 |  |  |  | 98
2025-08-01 | 3028 |  | 85333 | A | DONE | 5 | S |  | MONROE HS 6240018 |  | 2025-08-05 | Z | 2025-07-28 | 120 | 0 | 0 |  | 0 | 280 |  | A2 Mech |  | 8
2025-08-01 | 3030 |  | 85335 | A | DONE | 3 | S | neal | MONROE HS 6240018 |  | 2025-08-05 | Z | 2025-07-28 | 70 | 0 | 0 |  | 0 | 190 |  | Saddle hangers |  | 8
2025-07-30 | 3250 |  | 79512 | A | DONE | 9 | S | neal | ONE 09 6240037 | bird s. | 2025-08-04 | Z | 2025-07-21 | 220 | 0 | 0 |  | 0 | 430 |  | FH-HP RA |  | 14
2025-07-30 | 3251 |  | 79513 | A | DONE | 4 | S |  | ONE 09 6240037 | paint | 2025-08-04 | Z | 2025-07-21 | 90 | 0 | 0 |  | 60 | 140 |  | FH-LV tie in |  | 14
2025-07-28 | 3253 |  | 79515 | A | DONE | 2 | S |  | ONE 09 6240037 |  | 2025-07-30 | Z | 2025-07-23 | 40 | 0 | 0 |  | 0 | 40 |  | HP / RA |  | 7
2025-07-28 | 4230 | w | 81639 | A | DONE | 2 | S | BI | PECATONICA 6240005 |  | 2025-08-04 | Z | 2025-07-25 | 30 | 0 | 0 |  | 0 | 70 |  | RE-8 |  | 10
2025-07-29 | 4231 |  | 81640 - 81642 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2025-08-04 | Z | 2025-07-28 | 40 | 0 | 0 |  | 0 | 50 |  | RE-11 , 12 |  | 7
2025-07-29 | 4232 |  | 81643 | A | DONE | 2 | S |  | PECATONICA 6240005 | 1" liner | 2025-08-04 | Z | 2025-07-28 | 20 | 0 | 0 |  | 20 | 30 |  | RE-5 |  | 7
2025-08-01 | 4233 |  | 81645 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2025-08-04 | Z | 2025-07-30 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 5
2025-08-01 | 800 |  | 76712 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-06 | Z | 2025-07-28 | 50 | 0 | 0 |  | 0 | 80 |  | Pipe flashing |  | 9
2025-07-28 | 1843 |  | L1B-RA-7 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 | bird s. | 2025-07-30 | Z | 2025-07-08 | 50 | 0 | 0 |  | 0 | 80 |  |  |  | 22 | 2025-07-23
2025-07-28 | 1844 |  | L1B-TA 5 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | bird s. , 1" liner | 2025-07-30 | Z | 2025-07-08 | 40 | 0 | 0 |  | 40 | 100 |  |  |  | 22 | 2025-07-23
2025-07-28 | 1847 |  | L1B-TA 1 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | bird s. , 1" liner | 2025-07-30 | Z | 2025-07-08 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 22 | 2025-07-23
2025-07-28 | 1848 |  | L1B-RE-11 | A | DONE | 16 | M | pt.neal | PEWAUKEE HS 6240030 | 1" liner | 2025-07-30 | Z | 2025-07-08 | 320 | 0 | 70 | A | 70 | 490 |  |  |  | 22 | 2025-07-23
2025-07-28 | 4600 | bth | L1B-SAT V-18 | A | DONE | 3 | S |  | PEWAUKEE HS 6240030 | 2" liner | 2025-07-30 | Z | 2025-07-08 | 40 | 20 | 0 |  | 20 | 80 |  |  |  | 22 | 2025-07-23
2025-07-28 | 4601 | bth | L1B-SAT V-19 | A | DONE | 27 | M | pt.neal | PEWAUKEE HS 6240030 | 2" liner | 2025-07-30 | Z | 2025-07-08 | 230 | 350 | 80 | A | 140 | 780 |  |  |  | 22 | 2025-07-23
2025-07-28 | 4602 | bth | L1B-B COIL SA 1 | A | DONE | 8 | S-M | neal | PEWAUKEE HS 6240030 | VD's | 2025-07-30 | Z | 2025-07-08 | 80 | 120 | 0 |  | 0 | 270 |  |  |  | 22 | 2025-07-23
2025-08-01 | 4603 |  | L1B-TA 4 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | bird s. , 1" liner | 2025-08-06 | Z | 2025-07-08 | 50 | 0 | 0 |  | 50 | 80 |  |  |  | 29
2025-08-01 | 4604 |  | L1B-SAT V-15 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | 2" liner | 2025-08-06 | Z | 2025-07-08 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 29
2025-08-01 | 4606 | bth | L1B-SAT V-17 | A | DONE | 27 | M |  | PEWAUKEE HS 6240030 | 2" liner | 2025-08-06 | Z | 2025-07-08 | 300 | 150 | 210 | A | 400 | 930 |  |  |  | 29
2025-08-01 | 4607 | bth | L1B-SAT V-20 | A | DONE | 13 | S-M |  | PEWAUKEE HS 6240030 | 2" liner | 2025-08-06 | Z | 2025-07-08 | 120 | 20 | 170 | A | 150 | 440 |  |  |  | 29
2025-08-01 | 4608 |  | L1B-RE-10 | A | DONE | 14 | S-M |  | PEWAUKEE HS 6240030 | 1" liner | 2025-08-06 | Z | 2025-07-08 | 220 | 0 | 120 | A | 60 | 430 |  |  |  | 29
2025-08-01 | 4644 |  | 74156 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-08-06 | Z | 2025-07-17 | 30 | 0 | 0 |  | 0 | 90 |  | RTU-2 Damper Sleeve |  | 20
2025-07-28 | 4646 |  | 74124 | A | DONE | 5 | S |  | PEWAUKEE HS 6240030 |  | 2025-07-30 | Z | 2025-07-23 | 110 | 0 | 0 |  | 0 | 160 |  | VAV 120 |  | 7
2025-08-01 | 4648 | bth | 74126 | A | DONE | 6 | S |  | PEWAUKEE HS 6240030 |  | 2025-08-06 | Z | 2025-07-24 | 80 | 50 | 0 |  | 30 | 130 |  | V-130 |  | 13
2025-07-29 | 1391 |  | L01_AREA_300_MA_003 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 |  | 2025-07-31 | Z | 2025-07-01 | 100 | 0 | 0 |  | 0 | 160 |  |  |  | 30
2025-07-29 | 4715 |  | L01_AREA_052_EA_001 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 120 | 0 | 0 |  | 0 | 180 |  |  |  | 17
2025-07-29 | 4716 | bth | L01_AREA_052_EA_002 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 100 | 90 | 0 |  | 0 | 270 |  |  |  | 17
2025-07-30 | 4717 | bth | L01_AREA_052_EA_003 | A | DONE | 11 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 120 | 20 | 120 | A | 0 | 290 |  |  |  | 17
2025-07-28 | 4718 | bth | L01_AREA_052_EA_004 | A | DONE | 11 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 80 | 20 | 160 | A | 0 | 300 |  |  |  | 17
2025-07-30 | 4719 | sp | L01_AREA_052_EA_005 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 17
2025-07-28 | 4720 |  | L01_AREA_052_EA_006 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 17
2025-07-30 | 4721 | sp | L01_AREA_052_EA_007 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 17
2025-07-30 | 4722 | sp | L01_AREA_052_EA_008 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 0 | 50 | 0 |  | 0 | 50 |  |  |  | 17
2025-07-30 | 4723 | sp | L01_AREA_052_EA_009 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 17
2025-07-30 | 4724 | bth | L01_AREA_052_EA_010 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 170 | 20 | 0 |  | 0 | 210 |  |  |  | 17
2025-07-30 | 4725 | bth | L01_AREA_052_EA_011 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 90 | 40 | 30 | A | 0 | 220 |  |  |  | 17
2025-07-30 | 4726 | sp | L01_AREA_052_EA_012 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 17
2025-07-30 | 4727 | sp | L01_AREA_052_EA_013 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-01 | Z | 2025-07-15 | 20 | 80 | 0 |  | 0 | 90 |  |  |  | 17
2025-07-29 | 4746 |  | 76162 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-07-31 | Z | 2025-07-17 | 20 | 0 | 0 |  | 0 | 20 |  | L2/1 AREA 300 Stainless |  | 14
2025-07-29 | 4764 |  | L02_AREA_700_WEST_EA_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-31 | Z | 2025-07-23 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 8
2025-07-30 | 4765 |  | L02_AREA_700_WEST_EA_002 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-31 | Z | 2025-07-23 | 130 | 0 | 0 |  | 0 | 310 |  |  |  | 8
2025-07-29 | 4766 |  | L02_AREA_700_WEST_EA_003 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-31 | Z | 2025-07-23 | 140 | 0 | 0 |  | 0 | 310 |  |  |  | 8
2025-07-29 | 4767 |  | L02_AREA_700_WEST_EA_004 | A | DONE | 12 | S |  | PROJECT DOVE 6240041 |  | 2025-07-31 | Z | 2025-07-23 | 200 | 0 | 100 | A | 0 | 520 |  |  |  | 8
2025-07-30 | 4768 | bth | L02_AREA_700_WEST_EA_005 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | spiral mates | 2025-07-31 | Z | 2025-07-23 | 60 | 60 | 0 |  | 0 | 180 |  |  |  | 8
2025-07-29 | 4769 |  | L02_AREA_700_WEST_EA_006 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-31 | Z | 2025-07-23 | 130 | 0 | 0 |  | 0 | 290 |  |  |  | 8
2025-07-29 | 4770 | bth | L02_AREA_700_WEST_MA_001 | A | DONE | 12 | S |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-07-31 | Z | 2025-07-23 | 160 | 90 | 40 | A | 0 | 510 |  |  |  | 8
2025-07-29 | 4771 |  | L02_AREA_700_WEST_MA_002 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | VD | 2025-07-31 | Z | 2025-07-23 | 200 | 0 | 0 |  | 0 | 830 |  |  |  | 8
2025-07-30 | 4774 | sp | L02_AREA_700_WEST_MA_005 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-07-31 | Z | 2025-07-23 | 30 | 60 | 0 |  | 0 | 100 |  |  |  | 8
2025-07-30 | 4776 |  | L02_AREA_700_WEST_OA_002 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | bird s. , VD | 2025-07-31 | Z | 2025-07-23 | 200 | 0 | 0 |  | 0 | 440 |  |  |  | 8
2025-07-29 | 4777 |  | L02_AREA_700_WEST_RAMP_007 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-31 | Z | 2025-07-23 | 160 | 0 | 0 |  | 0 | 380 |  |  |  | 8
2025-07-30 | 4778 |  | L02_AREA_700_WEST_RAMP_008 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-31 | Z | 2025-07-23 | 150 | 0 | 0 |  | 0 | 330 |  |  |  | 8
2025-07-28 | 4779 |  | 76165 | A | DONE | 4 | S-M | neal | PROJECT DOVE 6240041 |  | 2025-08-07 | Z | 2025-07-24 | 90 | 0 | 0 |  | 0 | 120 |  | Flashing |  | 14
2025-07-28 | 4787 |  | L02_AREA_900_EA_001 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-30 | Z | 2025-07-25 | 140 | 0 | 0 |  | 0 | 230 |  |  |  | 5
2025-07-28 | 4788 |  | L02_AREA_900_OA_001 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-07-30 | Z | 2025-07-25 | 70 | 0 | 0 |  | 0 | 150 |  |  |  | 5
2025-07-28 | 4789 |  | L02_AREA_900_OA_002 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-07-30 | Z | 2025-07-25 | 200 | 0 | 0 |  | 0 | 440 |  |  |  | 5
2025-07-30 | 4790 |  | 76166 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 |  | 2025-07-31 | Z | 2025-07-28 | 260 | 0 | 0 |  | 0 | 480 |  | Curb caps |  | 3
2025-07-29 | 1985 |  | 75814 | A | DONE | 4 | S |  | REEDSBURG HS 6250010 | paint , 1" liner | 2025-07-31 | Z | 2025-07-28 | 80 | 0 | 0 |  | 0 | 120 |  | TA grille adapters |  | 3
2025-07-29 | 3690 | bth | 68491 - 68493 | A | DONE | 13 | S-M |  | SPH SURGERY 6240039 |  | 2025-08-04 | Z | 2025-07-14 | 70 | 220 | 30 | A | 0 | 310 |  | Pink Phase |  | 21
2025-07-30 | 3694 | w | 68499 | A | DONE | 3 | S |  | SPH SURGERY 6240039 | 1" DB | 2025-08-01 | Z | 2025-07-29 | 70 | 0 | 0 |  | 20 | 140 |  | Roof curb |  | 3
2025-07-29 | 503 |  | 75518 - 75519 | A | DONE | 71 | L | neal | SW HEALTH OR 5 6250004 | 3" DW | 2025-08-04 | Z | 2025-07-16 | 1760 | 0 | 0 |  | 710 | 3720 |  | Roof SA , RA |  | 19
2025-08-01 | 4653 |  | 74658 - 74660 | A | DONE | 4 | S-M |  | TOMAH HEALTH 2250033 | VD's , bird s. | 2025-08-04 | Z | 2025-07-15 | 90 | 0 | 0 |  | 0 | 140 |  |  |  | 20
2025-07-28 | 4650 |  | 74661 | A | DONE | 3 | S |  | TOMAH HEALTH 6250006 |  | 2025-07-28 | Z | 2025-07-07 | 30 | 0 | 40 | A | 0 | 80 |  | Rm 2170 |  | 21
2025-07-28 | 4651 |  | 74662 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 | 1" elastomeric | 2025-07-28 | Z | 2025-07-07 | 30 | 0 | 0 |  | 20 | 40 |  | Rm 3061 |  | 21
2025-07-28 | 4652 | sp | 74663 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-07-28 | Z | 2025-07-07 | 20 | 20 | 0 |  | 0 | 40 |  | Rm 3061 |  | 21
2025-07-29 | 3779 | w | L5-EAT 571 SS | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-11 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 19
2025-07-29 | 3781 | w | L5-EAT 580 SS | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-11 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 19
2025-07-30 | 3782 | w | L5-EAT 581 SS | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-11 | 20 | 0 | 0 |  | 0 | 80 |  |  |  | 19
2025-07-29 | 3784 | w | L5-EAT 585 SS | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-11 | 20 | 0 | 0 |  | 0 | 90 |  |  |  | 19
2025-07-30 | 3785 | w | L5-FAT 585 SS | A | DONE | 2 | S | pt.ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-11 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 19
2025-07-28 | 3787 | sp | L5D-EAT 558 | A | DONE | 2 | S |  | UW-AVRL 6240038 | VD | 2025-07-30 | Z | 2025-07-14 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 16
2025-07-28 | 3788 |  | 61935 | A | DONE | 5 | S |  | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-16 | 120 | 0 | 0 |  | 0 | 210 |  | PH |  | 14
2025-07-28 | 3790 |  | L5B-BCU EA 1 | A | DONE | 7 | S |  | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-22 | 160 | 0 | 0 |  | 0 | 250 |  |  |  | 8
2025-07-28 | 3792 | w | L5B-BL3E EA 1 | A | DONE | 7 | S-M | ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-22 | 160 | 0 | 0 |  | 0 | 450 |  |  |  | 8
2025-07-29 | 3794 |  | 61939 | A | DONE | 2 | S | alum | UW-AVRL 6240038 |  | 2025-08-04 | Z | 2025-07-28 | 20 | 0 | 0 |  | 0 | 20 |  | 5th floor tie ins |  | 7
2025-07-30 | 3795 |  | 69148 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-08-04 | Z | 2025-07-29 | 20 | 0 | 0 |  | 0 | 40 |  | 5th Floor HP |  | 6
2025-07-28 | 2071 | bth | L4-SAMP 4 | A | DONE | 11 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-28 | Z | 2025-06-26 | 40 | 50 | 180 | A | 0 | 320 |  |  |  | 32
2025-07-28 | 2072 | bth | L4-SAMP 5 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-07-28 | Z | 2025-06-26 | 130 | 40 | 30 | A | 0 | 250 |  |  |  | 32
2025-07-28 | 2076 |  | 82970 , 82970 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | paint , 1" liner | 2025-07-28 | Z | 2025-07-14 | 240 | 0 | 0 |  | 220 | 330 |  | L2 Restoom |  | 14
2025-07-28 | 3994 |  | 82176 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | paint | 2025-08-04 | Z | 2025-07-17 | 50 | 0 | 0 |  | 50 | 110 |  | 1st RA |  | 18
2025-08-01 | 1884 |  | 75719 | A | DONE | 2 | S |  | UWP-FH 6240021 |  | 2025-08-07 | Z | 2025-07-29 | 20 | 0 | 0 |  | 0 | 30 |  | 1st floor TA |  | 9
2025-07-29 | 3086 |  | 54527 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-08-06 | Z | 2025-07-28 | 20 | 0 | 0 |  | 0 | 20 |  | CB 401 |  | 9
2025-07-30 | 3583 | w | 85020 | A | DONE | 7 | S-M |  | UW-WHITEWATER 6250001 |  | 2025-08-01 | Z | 2025-07-17 | 160 | 0 | 0 |  | 0 | 210 |  | Curb cap |  | 15
2025-07-28 | 3585 | bth | 85025 - 85030 | A | DONE | 17 | M |  | UW-WHITEWATER 6250001 | flex | 2025-08-01 | Z | 2025-07-17 | 210 | 200 | 0 |  | 0 | 710 |  | EF Roof |  | 15
2025-08-01 | 3586 | w | 85031 - 85032 | A | DONE | 3 | S-M | ss | UW-WHITEWATER 6250001 | flex | 2025-08-01 | Z | 2025-07-17 | 60 | 0 | 0 |  | 0 | 180 |  | EF-13 / Fume Hood |  | 15
2025-07-28 | 3873 |  | 74790 | A | DONE | 2 | S |  | UW-WITTE HALL 6250003 | 1" liner | 2025-07-30 | Z | 2025-07-21 | 40 | 0 | 0 |  | 40 | 60 |  | Roof drop |  | 9
2025-07-28 | 3874 |  | 74791 | A | DONE | 2 | S |  | UW-WITTE HALL 6250003 |  | 2025-07-30 | Z | 2025-07-23 | 40 | 0 | 0 |  | 0 | 70 |  | Roof |  | 7
2025-07-28 | 3879 |  | 74797 | A | DONE | 2 | S | neal | UW-WITTE HALL 6250003 |  | 2025-07-29 | Z | 2025-07-28 | 50 | 0 | 0 |  | 0 | 60 |  | Flashing |  | 1
2025-08-01 | 3880 |  | 74798 | A | DONE | 2 | S | neal | UW-WITTE HALL 6250003 | 1" liner | 2025-08-06 | Z | 2025-07-31 | 30 | 0 | 0 |  | 20 | 50 |  | EC |  | 6
2025-08-01 | 3881 |  | 74799 - 74800 | A | DONE | 11 | S-M |  | UW-WITTE HALL 6250003 | 1" liner | 2025-08-06 | Z | 2025-07-31 | 170 | 0 | 100 | A | 190 | 360 |  | EA West , Ease |  | 6
[6 empty] | 1115 | [13 empty] | 37600 |  |  |  | 11130 | 29.6%
WEEK OF 8-4-2025
2025-08-06 | 1038 |  | 85169 - 85170 | A | DONE | 2 | S | neal | 121 E. WILSON 6230024 | paint | 2025-08-07 | Z | 2025-08-05 | 20 | 0 | 0 |  | 0 | 20 |  | Shroud , Escutcheon |  | 2
2025-08-04 | 550 |  | 75221 - 75222 | A | DONE | 52 | M-L |  | BARTILLION 6240024 | 1" liner | 2025-08-07 | Z | 2025-07-24 | 590 | 0 | 690 | A | 850 | 1590 |  | LP SA |  | 14
2025-08-04 | 553 | sp | 84361 - 84362 | A | DONE | 8 | S-M | al,ss | BARTILLION 6240024 | bird s. | 2025-08-07 | Z | 2025-07-31 | 70 | 110 | 0 |  | 0 | 170 |  | Venting |  | 7
2025-08-06 | 555 |  | 84364 | A | DONE | 2 | S | BI | BARTILLION 6240024 |  | 2025-08-15 | Z | 2025-07-31 | 20 | 0 | 0 |  | 0 | 20 |  | BI blank off |  | 15
2025-08-04 | 556 |  | 84365 | A | DONE | 2 | S-M |  | BARTILLION 6240024 |  | 2025-08-07 | Z | 2025-07-31 | 30 | 0 | 0 |  | 0 | 50 |  | Flashing |  | 7
2025-08-08 | 557 |  | 75224 , 75226 | A | DONE | 3 | S-M |  | BARTILLION 6240024 | flex , 1" liner | 2025-08-12 | Z | 2025-08-04 | 70 | 0 | 0 |  | 40 | 100 |  | TA fan outs |  | 8
2025-08-07 | 558 |  | 75225 , 75227 | A | DONE | 4 | S-M |  | BARTILLION 6240024 |  | 2025-08-12 | Z | 2025-08-04 | 80 | 0 | 0 |  | 0 | 100 |  | RA |  | 8
2025-08-08 | 559 |  | 84366 | A | DONE | 2 | S |  | BARTILLION 6240024 | paint | 2025-08-12 | Z | 2025-08-06 | 20 | 0 | 0 |  | 20 | 40 |  | Grille box |  | 6
2025-08-04 | 2738 | sp | 75199 - 75200 | A | DONE | 86 | L | perf | BARTILLION 6240024 | s.mates , 1" DW | 2025-08-05 | Z | 2025-07-09 | 210 | 1930 | 0 |  | 1000 | 1810 |  | SA Dorm 5 |  | 27 | 2025-07-29
2025-08-06 | 2739 | sp | 75201 - 75202 | A | DONE | 159 | L | perf | BARTILLION 6240024 | s.mates , 1" DW | 2025-08-12 | Z | 2025-07-09 | 340 | 3630 | 0 |  | 1010 | 3440 |  | Dorm 4 SA |  | 34 | 2025-07-29
2025-08-04 | 2748 |  | 75213 - 75216 | A | DONE | 21 | M |  | BARTILLION 6240024 |  | 2025-08-07 | Z | 2025-07-24 | 430 | 30 | 60 | A | 0 | 660 |  | Misc |  | 14
2025-08-07 | 2489 |  | EMAIL | A | DONE | 2 | S |  | CDIS 6220011 | bird s. | 2025-08-07 | Z | 2025-08-07 | 20 | 0 | 0 |  | 0 | 20 |  | Bird screen |  | 0
2025-08-05 | 3521 |  | 73762 - 73764 | A | DONE | 12 | S-M |  | DELLSHIRE 6240017 |  | 2025-08-11 | Z | 2025-07-24 | 50 | 0 | 240 | A | 0 | 340 |  | Mech Chase |  | 18
2025-08-05 | 3522 |  | 73765 - 73766 | A | DONE | 19 | S-M |  | DELLSHIRE 6240017 |  | 2025-08-11 | Z | 2025-07-24 | 180 | 0 | 290 | A | 0 | 600 |  | SA Chase |  | 18
2025-08-05 | 3523 |  | 73767 | A | DONE | 10 | S |  | DELLSHIRE 6240017 |  | 2025-08-11 | Z | 2025-07-24 | 160 | 0 | 70 | A | 0 | 280 |  | RA Mech Chase |  | 18
2025-08-06 | 3524 |  | 73768 | A | DONE | 24 | M |  | DELLSHIRE 6240017 | paint | 2025-08-11 | Z | 2025-07-29 | 380 | 210 | 0 |  | 90 | 640 |  | VTAC tie ins |  | 13
2025-08-08 | 3525 |  | 73769 | A | DONE | 6 | S-M | pcd | DELLSHIRE 6240017 |  | 2025-08-11 | Z | 2025-07-29 | 150 | 0 | 0 |  | 0 | 290 |  | Laundry Room |  | 13
2025-08-06 | 3526 |  | 73675 | A | DONE | 19 | S-M |  | DELLSHIRE 6240017 | paint | 2025-08-11 | Z | 2025-07-31 | 340 | 0 | 120 | A | 20 | 860 |  | Misc SM |  | 11
2025-08-04 | 692 |  | 73914 - 73915 | A | DONE | 5 | S-M |  | DOC JDC 6240023 |  | 2025-08-07 | Z | 2025-07-23 | 120 | 0 | 0 |  | 0 | 170 |  | Zone 2 EA Drops |  | 15
2025-08-05 | 1018 |  | 56825 | A | DONE | 2 | S |  | EXACT TL-3 6240028 |  | 2025-08-06 | Z | 2025-08-05 | 20 | 0 | 0 |  | 0 | 20 |  | Damper |  | 1
2025-08-06 | 3200 |  | 65658 - 65659 | A | DONE | 23 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 180 | 0 | 390 | A | 0 | 670 |  | RTU-4 RA |  | 14
2025-08-06 | 3201 | sp | 65660 | A | DONE | 4 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 0 | 90 | 0 |  | 0 | 80 |  | RTU-4 SA |  | 14
2025-08-05 | 3202 |  | 65682 - 65683 | A | DONE | 4 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 100 | 0 | 0 |  | 0 | 140 |  | RTU-4 RA |  | 14
2025-08-06 | 3203 |  | 65681 | A | DONE | 4 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 90 | 0 | 0 |  | 0 | 150 |  | RTU-6 SA |  | 14
2025-08-06 | 3204 |  | 65667 - 65668 | A | DONE | 20 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 200 | 0 | 280 | A | 0 | 620 |  | RTU-6 RA / SA |  | 14
2025-08-06 | 3205 | sp | 65669 | A | DONE | 3 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 20 | 50 | 0 |  | 0 | 60 |  | RTU-6 SA |  | 14
2025-08-05 | 3206 |  | 65671 | A | DONE | 6 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 40 | 0 | 110 | A | 0 | 170 |  | RTU-7 RA |  | 14
2025-08-06 | 3207 |  | 65673 | A | DONE | 8 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 70 | 0 | 110 | A | 0 | 210 |  | RTU-7 SA |  | 14
2025-08-06 | 3208 | sp | 65674 | A | DONE | 8 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 20 | 170 | 0 |  | 0 | 160 |  | RTU-7 SA / RA |  | 14
2025-08-06 | 3209 |  | 65700 | A | DONE | 6 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 100 | 0 | 40 | A | 0 | 150 |  | RTU-5 RA |  | 14
2025-08-06 | 3210 |  | 65675 - 65677 | A | DONE | 29 | M |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 310 | 0 | 400 | A | 0 | 830 |  | RTU-5 SA |  | 14
2025-08-06 | 3211 | sp | 65678 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 0 | 40 | 0 |  | 0 | 40 |  | RTU-5 |  | 14
2025-08-06 | 3212 |  | 65679 - 65680 | A | DONE | 15 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 220 | 0 | 140 | A | 0 | 430 |  | RTU-5 RA |  | 14
2025-08-04 | 3213 |  | 65689 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 20 | 0 | 0 |  | 0 | 20 |  | RTU-8 |  | 14
2025-08-06 | 3214 |  | 65688 | A | DONE | 4 | S |  | HISTOSONICS 6250009 | 1/2" liner | 2025-08-11 | Z | 2025-07-28 | 60 | 0 | 30 | A | 70 | 110 |  | TA |  | 14
2025-08-06 | 3215 | sp | 65687 | A | DONE | 4 | S |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-07-28 | 20 | 60 | 0 |  | 0 | 80 |  | EA |  | 14
2025-08-04 | 3224 |  | 69990 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-08-05 | Z | 2025-08-04 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeves |  | 1
2025-08-07 | 3228 |  | 77254 - 77255 | A | DONE | 7 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-11 | Z | 2025-08-06 | 90 | 0 | 70 |  | 0 | 180 |  | RTU-6 SA |  | 5
2025-08-08 | 2560 | sp | 61940 - 61941 | A | DONE | 2 | S-M |  | LABCORP 2250014 |  | 2025-08-12 | Z | 2025-07-29 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 14
2025-08-04 | 1734 |  | 94049 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-08-05 | Z | 2025-08-04 | 40 | 0 | 0 |  | 0 | 50 |  | Reducers |  | 1
2025-08-06 | 1735 |  | 77301 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-08-06 | Z | 2025-08-06 | 20 | 0 | 0 |  | 0 | 30 |  | VAV |  | 0
2025-08-04 | 2785 | sp | SALP-L1F-04 | A | DONE | 35 | M-L | neal | MONROE HS 6240018 | spiral mate | 2025-08-05 | Z | 2025-04-29 | 140 | 720 | 0 |  | 0 | 1470 |  |  |  | 98
2025-08-08 | 2789 | sp | SALP-L1F-08 | A | DONE | 17 | S-M | neal | MONROE HS 6240018 | spiral mate | 2025-08-12 | Z | 2025-04-29 | 60 | 360 | 0 |  | 0 | 520 |  |  |  | 105 | 2025-06-24 | 2025-08-05
2025-08-08 | 2790 | bth | SALP-L1F-09 | A | DONE | 8 | S-M | neal | MONROE HS 6240018 | spiral mate , 2" liner | 2025-08-12 | Z | 2025-04-29 | 130 | 50 | 0 |  | 90 | 370 |  |  |  | 105 | 2025-06-24 | 2025-08-05
2025-08-08 | 2791 | sp | SALP-L1F-10 | A | DONE | 17 | S-M | neal | MONROE HS 6240018 | spiral mate | 2025-08-12 | Z | 2025-04-29 | 70 | 340 | 0 |  | 0 | 470 |  |  |  | 105 | 2025-06-24 | 2025-08-05
2025-08-08 | 2792 | bth | SALP-L1F-11 | A | DONE | 14 | S-M | neal | MONROE HS 6240018 | spiral mate | 2025-08-12 | Z | 2025-04-29 | 100 | 250 | 0 |  | 0 | 440 |  |  |  | 105 | 2025-06-24 | 2025-08-05
2025-08-07 | 2793 |  | SALP-L1F-12 | A | DONE | 19 | M |  | MONROE HS 6240018 | 2" liner | 2025-08-12 | Z | 2025-04-29 | 340 | 0 | 120 | A | 330 | 840 |  |  |  | 105 |  | 2025-08-05
2025-08-08 | 2794 |  | SALP-L1F-13 | A | DONE | 18 | M |  | MONROE HS 6240018 | VD , 2" liner | 2025-08-12 | Z | 2025-04-29 | 150 | 0 | 280 | A | 350 | 920 |  |  |  | 105 |  | 2025-08-05
2025-08-08 | 2795 |  | SALP-L1F-14 | A | DONE | 18 | M |  | MONROE HS 6240018 | VD , 2" liner | 2025-08-12 | Z | 2025-04-29 | 160 | 0 | 270 | A | 320 | 850 |  |  |  | 105 |  | 2025-08-05
2025-08-08 | 2796 |  | SALP-L1F-15 | A | DONE | 14 | M |  | MONROE HS 6240018 | VD , 2" liner | 2025-08-12 | Z | 2025-04-29 | 110 | 0 | 240 | A | 280 | 770 |  |  |  | 105 |  | 2025-08-05
2025-08-08 | 2797 |  | SALP-L1F-16 | A | DONE | 17 | M |  | MONROE HS 6240018 | VD , 2" liner | 2025-08-12 | Z | 2025-04-29 | 260 | 0 | 150 | A | 300 | 680 |  |  |  | 105 |  | 2025-08-05
2025-08-08 | 2798 |  | SALP-L1F-17 | A | DONE | 4 | S |  | MONROE HS 6240018 | VD | 2025-08-12 | Z | 2025-04-29 | 80 | 0 | 0 |  | 0 | 100 |  |  |  | 105 |  | 2025-08-05
2025-08-07 | 2799 |  | SALP-L1F-18 | A | DONE | 6 | S |  | MONROE HS 6240018 | 2" liner | 2025-08-12 | Z | 2025-04-29 | 0 | 0 | 130 | A | 120 | 190 |  |  |  | 105 | 2025-06-24 | 2025-08-05
2025-08-08 | 3029 | bth | 85334 | A | DONE | 5 | S |  | MONROE HS 6240018 | bird s. | 2025-08-12 | Z | 2025-07-28 | 100 | 20 | 0 |  | 0 | 140 |  | B-section |  | 15
2025-08-08 | 3031 |  | 85336 | A | DONE | 3 | S | neal | MONROE HS 6240018 |  | 2025-08-12 | Z | 2025-07-28 | 60 | 0 | 0 |  | 0 | 180 |  | E Saddle hangers |  | 15
2025-08-08 | 3800 |  | SALP-L1F-19 | A | DONE | 6 | S |  | MONROE HS 6240018 | 2" liner | 2025-08-12 | Z | 2025-04-29 | 0 | 0 | 130 | A | 120 | 190 |  |  |  | 105 | 2025-06-24 | 2025-08-05
2025-08-08 | 1595a |  | EA-L1C-01 | A | DONE | 3 | S-M |  | MONROE HS 6240018 | partial | 2025-08-12 | Z | 2025-04-28 | 70 | 0 | 0 |  | 40 | 110 |  |  |  | 106
2025-08-08 | 2758a |  | SALP-L1C-01 | A | DONE | 5 | S-M |  | MONROE HS 6240018 | flex , 2" liner , partial | 2025-08-12 | Z | 2025-04-28 | 120 | 0 | 0 |  | 100 | 180 |  |  |  | 106
2025-08-04 | 3254 | w | 79516 | A | DONE | 2 | S-M | ss | ONE 09 6240037 |  | 2025-08-04 | Z | 2025-07-23 | 20 | 0 | 0 |  | 0 | 40 |  | FH condensate pans |  | 12
2025-08-05 | 3255 |  | 79517 | A | DONE | 2 | S | alum | ONE 09 6240037 | flex | 2025-08-11 | Z | 2025-07-28 | 30 | 0 | 0 |  | 0 | 20 |  | CH Kitchen D.W EA |  | 14
2025-08-05 | 3256 |  | 79518 | A | DONE | 2 | S |  | ONE 09 6240037 |  | 2025-08-06 | Z | 2025-08-05 | 20 | 0 | 0 |  | 0 | 20 |  | CH Vesti 115 |  | 1
2025-08-08 | 3257 | w | 79520 | A | DONE | 2 | S | BI | ONE 09 6240037 |  | 2025-08-07 | Z | 2025-08-07 | 20 | 0 | 0 |  | 0 | 20 |  | CH Hood |  | 0
2025-08-05 | 4234 |  | 81646 | A | DONE | 2 | S |  | PECATONICA 6240005 | 1" liner | 2025-08-11 | Z | 2025-08-05 | 20 | 0 | 0 |  | 20 | 20 |  | RE-5 |  | 6
2025-08-08 | 802 |  | 76758 | A | DONE | 4 | S |  | PEWAUKEE HS 6240030 |  | 2025-08-12 | Z | 2025-08-06 | 80 | 0 | 0 |  | 0 | 150 |  | Culinary SA |  | 6
2025-08-04 | 4605 | bth | L1B-SAT V-16 | A | DONE | 36 | M-L | pt.neal | PEWAUKEE HS 6240030 | VD's , 2" liner | 2025-08-06 | Z | 2025-07-08 | 460 | 100 | 340 | A | 430 | 1200 |  |  |  | 29
2025-08-05 | 4609 | sp | L1B-KILN EA 1 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-06 | Z | 2025-07-08 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 29
2025-08-05 | 4610 | sp | L1B-KILN EA 2 | A | DONE | 5 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-06 | Z | 2025-07-08 | 20 | 90 | 0 |  | 0 | 120 |  |  |  | 29
2025-08-08 | 4613 | bth | L1B-SAT V-11 | A | DONE | 6 | S |  | PEWAUKEE HS 6240030 | 2" liner | 2025-08-13 | Z | 2025-07-09 | 50 | 40 | 40 | A | 50 | 130 |  |  |  | 35
2025-08-08 | 4614 | bth | L1B-SAT V-12 | A | DONE | 6 | S |  | PEWAUKEE HS 6240030 | 2" liner | 2025-08-13 | Z | 2025-07-09 | 70 | 60 | 0 |  | 40 | 140 |  |  |  | 35
2025-08-08 | 4624 |  | L1B-MUH 1 | Delete |  |  | S-M | neal | PEWAUKEE HS 6240030 | bird s. | 2025-08-20 | Z | 2025-07-09 | [5 empty] | 280 |  |  |  | 42
2025-08-05 | 4649 |  | 76805 | A | DONE | 18 | S-M |  | PEWAUKEE HS 6240030 | 1" liner | 2025-08-11 | Z | 2025-07-28 | 440 | 0 | 0 |  | 410 | 730 |  | EA fan drops |  | 14
2025-08-05 | 4728 |  | L01_AREA_052_RA_001 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 100 | 0 | 0 |  | 0 | 200 |  |  |  | 23
2025-08-05 | 4729 |  | L01_AREA_052_RA_002 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 23
2025-08-05 | 4730 | bth | L01_AREA_052_SALP_001 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 60 | 20 | 0 |  | 0 | 90 |  |  |  | 23
2025-08-05 | 4731 | sp | L01_AREA_052_SALP_002 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 23
2025-08-06 | 4732 | sp | L01_AREA_052_SALP_003 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 23
2025-08-06 | 4733 | bth | L01_AREA_052_SALP_004 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 23
2025-08-05 | 4734 | bth | L01_AREA_052_SALP_005 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 120 | 40 | 40 | A | 0 | 240 |  |  |  | 23
2025-08-05 | 4735 | sp | L01_AREA_052_SALP_006 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 23
2025-08-05 | 4736 | sp | L01_AREA_052_SALP_007 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 23
2025-08-05 | 4737 | sp | L01_AREA_052_SALP_008 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 23
2025-08-06 | 4738 | bth | L01_AREA_052_SALP_009 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 80 | 20 | 30 | A | 0 | 150 |  |  |  | 23
2025-08-04 | 4739 | sp | L01_AREA_052_SALP_010 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 23
2025-08-04 | 4740 | sp | L01_AREA_052_SALP_011 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 60 | 50 | 0 |  | 0 | 120 |  |  |  | 23
2025-08-06 | 4741 | bth | L01_AREA_052_SALP_012 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 140 | 40 | 40 | A | 0 | 290 |  |  |  | 23
2025-08-05 | 4742 | bth | L01_AREA_052_SALP_013 | A | DONE | 13 | S-M |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 250 | 20 | 40 | A | 0 | 350 |  |  |  | 23
2025-08-05 | 4743 | bth | L01_AREA_052_SALP_014 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 50 | 70 | 0 |  | 0 | 140 |  |  |  | 23
2025-08-05 | 4744 | sp | L01_AREA_052_SALP_015 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 23
2025-08-05 | 4745 | bth | L01_AREA_052_SALP_016 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-08 | Z | 2025-07-16 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 23
2025-08-05 | 4775 |  | L02_AREA_700_WEST_OA_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | bird s. , VD | 2025-07-31 | Z | 2025-07-23 | 40 | 0 | 0 |  | 0 | 80 |  |  |  | 8
2025-08-04 | 4780 |  | AHU_004_RAMP_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-07 | Z | 2025-07-24 | 200 | 0 | 0 |  | 0 | 470 |  |  |  | 14
2025-08-04 | 4781 |  | AHU_004_SAMP_001 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-07 | Z | 2025-07-24 | 200 | 0 | 70 | A | 0 | 720 |  |  |  | 14
2025-08-07 | 4791 |  | 76202 | L | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-08-15 | Z | 2025-07-29 | 100 | 0 | 0 |  | 0 | 150 |  | Office Flashing |  | 17
2025-08-07 | 4792 |  | 76205 | A | DONE | 10 | S-M | neal | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-08-05 | 240 | 0 | 0 |  | 0 | 330 |  | Area 700 |  | 9
2025-08-06 | 4794 |  | 80346 | A | DONE | 2 | S-M | neal | PROJECT DOVE 6240041 |  | 2025-08-08 | Z | 2025-08-05 | 40 | 0 | 0 |  | 0 | 50 |  | 700 Hangers |  | 3
2025-08-06 | 4808 |  | 76167 | A | DONE | 2 | S | 2 | PROJECT DOVE 6240041 |  | 2025-08-08 | Z | 2025-08-06 | 30 | 0 | 0 |  | 0 | 40 |  | 900 EA |  | 2
2025-08-08 | 4811 |  | 76215 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-08-08 | Z | 2025-08-07 | 0 | 0 | 160 |  | 0 | 190 |  | Flat Stock |  | 1
2025-08-06 | 1986 |  | 75816 - 75818 | A | DONE | 6 | S-M |  | REEDSBURG HS 6250010 | paint | 2025-08-08 | Z | 2025-08-06 | 140 | 0 | 0 |  | 100 | 210 |  | TA outs |  | 2
2025-08-08 | 858 | sp | 68937 | A | DONE | 2 | S | ss | SPH SURGERY 6240039 |  | 2025-08-11 | Z | 2025-08-01 | 30 | 0 | 0 |  | 0 | 40 |  | Equipment EA |  | 10
2025-08-06 | 3695 | sp | 68500 | A | DONE | 5 | S-M | ss | SPH SURGERY 6240039 |  | 2025-08-11 | Z | 2025-07-29 | 40 | 80 | 0 |  | 0 | 120 |  | SS Duct |  | 13
2025-08-04 | 3696 | w | 68936 | A | DONE | 2 | S | ss | SPH SURGERY 6240039 | bird s. | 2025-08-11 | Z | 2025-07-31 | 20 | 0 | 0 |  | 0 | 30 |  | Wall caps |  | 11
2025-08-04 | 506 |  | 81655 | A | DONE | 3 | S |  | SW HEALTH MOB 6250015 |  | 2025-08-11 | Z | 2025-07-22 | 60 | 0 | 0 |  | 0 | 120 |  | Roof Jack Flashing |  | 20
2025-08-05 | 507 | w | 81656 | A | DONE | 3 | S-M |  | SW HEALTH MOB 6250015 | strut | 2025-08-11 | Z | 2025-07-23 | 60 | 0 | 0 |  | 0 | 130 |  | AC-1 curb cap / rails |  | 19
2025-08-05 | 508 | w | 81657 | A | DONE | 2 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-08-11 | Z | 2025-07-23 | 20 | 0 | 0 |  | 0 | 50 |  | AC-1 cap / rails |  | 19
2025-08-06 | 509 | sp | 75501 | A | DONE | 4 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-08-11 | Z | 2025-07-28 | 20 | 60 | 0 |  | 0 | 70 |  | AHU-D South RA |  | 14
2025-08-05 | 510 |  | 75502 | A | DONE | 8 | S-M |  | SW HEALTH OR 5 6250004 | VD | 2025-08-11 | Z | 2025-07-28 | 80 | 0 | 110 | A | 0 | 240 |  | AHU-D North RA |  | 14
2025-08-05 | 511 | bth | 75522 - 75524 | A | DONE | 18 | S-M |  | SW HEALTH OR 5 6250004 | oval | 2025-08-11 | Z | 2025-07-28 | 230 | 30 | 180 | A | 0 | 520 |  | AHU-D RA main / SA |  | 14
2025-08-06 | 513 |  | 75526 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-08-11 | Z | 2025-08-04 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 7
2025-08-05 | 847 |  | 75513 , 75515 - 75516 | A | DONE | 10 | S-M |  | SW HEALTH OR 5 6250004 | VD's | 2025-08-11 | Z | 2025-07-01 | 230 | 0 | 0 |  | 0 | 340 |  | VAV CR-01 |  | 41
2025-08-06 | 848 | sp | 75514 | A | DONE | 2 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-08-11 | Z | 2025-07-01 | 0 | 20 | 0 |  | 0 | 20 |  | VAV CR-01 |  | 41
2025-08-05 | 3780 | w | L5-EAT 575 SS | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-07-30 | Z | 2025-07-11 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 19
2025-08-06 | 3797 | sp | 61943 | A | DONE | 3 | S |  | UW-AVRL 6240038 |  | 2025-08-13 | Z | 2025-07-31 | 20 | 40 | 0 |  | 0 | 50 |  | 5th floor mech room |  | 13
2025-08-06 | 3798 | w | L5D-EAMP SS 2 | A | DONE | 4 | S-M | ss | UW-AVRL 6240038 |  | 2025-08-13 | Z | 2025-07-31 | 90 | 0 | 0 |  | 0 | 270 |  |  |  | 13
2025-08-08 | 3799 | w | 61944 | A | DONE | 2 | S | ss | UW-AVRL 6240038 | angle rings | 2025-08-18 | Z | 2025-08-06 | 20 | 0 | 0 |  | 0 | 70 |  | 5th Floor tie ins |  | 12
2025-08-04 | 3793r | w | 61937 | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-08-13 | Z | 2025-08-01 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 12
2025-08-06 | 2100 |  | L4-SAT 3-4-10 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 50 | 0 | 40 | A | 20 | 120 |  |  |  | 20
2025-08-06 | 2101 | bth | L4-SAT 3-4-12 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 40 | 20 | 0 |  | 30 | 60 |  |  |  | 20
2025-08-07 | 2102 | bth | L4-SAT 3-4-13 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 60 | 60 | 90 | A | 40 | 250 |  |  |  | 20
2025-08-06 | 2103 | bth | L4-SAT 3-4-14 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 20 | 20 | 30 | A | 30 | 80 |  |  |  | 20
2025-08-08 | 2104 | bth | L4-SAT 3-4-15 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 40 | 20 | 40 | A | 40 | 130 |  |  |  | 20
2025-08-06 | 2105 | bth | L4-SAT 3-4-16 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 50 | 20 | 40 | A | 30 | 130 |  |  |  | 20
2025-08-06 | 2106 | bth | L4-SAT 3-4-17 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 10 | 20 | 30 | A | 30 | 60 |  |  |  | 20
2025-08-06 | 2107 | bth | L4-SAT 3-4-18 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 20
2025-08-06 | 2108 | bth | L4-SAT 3-4-19 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 30 | 30 | 30 | A | 40 | 100 |  |  |  | 20
2025-08-07 | 2109 | bth | L4-SAT 3-4-20 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 60 | 0 | 20 | A | 20 | 110 |  |  |  | 20
2025-08-06 | 2110 | bth | L4-SAT 3-4-21 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 30 | 20 | 30 | A | 40 | 90 |  |  |  | 20
2025-08-07 | 2111 | bth | L4-SAT 3-4-22 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 20 | 20 | 0 |  | 20 | 50 |  |  |  | 20
2025-08-07 | 2112 |  | L4-SAT 3-4-23 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 50 | 0 | 90 | A | 30 | 180 |  |  |  | 20
2025-08-07 | 2113 | bth | L4-SAT 3-4-24 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 80 | 60 | 0 |  | 30 | 160 |  |  |  | 20
2025-08-07 | 2114 | bth | L4-SAT 3-4-25 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 50 | 20 | 60 | A | 30 | 150 |  |  |  | 20
2025-08-07 | 2115 | bth | L4-SAT 3-4-26 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 20 | 30 | 20 | A | 30 | 70 |  |  |  | 20
2025-08-07 | 2116 | bth | L4-SAT 3-4-27 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 60 | 40 | 50 | A | 30 | 180 |  |  |  | 20
2025-08-07 | 2117 |  | L4-SAT 3-4-38 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VD's , VAV , 1" liner | 2025-08-11 | Z | 2025-07-22 | 70 | 0 | 0 |  | 30 | 100 |  |  |  | 20
2025-08-06 | 2118 |  | L4-TA 1 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 40 | 0 | 30 | A | 60 | 90 |  |  |  | 20
2025-08-07 | 2119 |  | L4-TA 2 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 40 | 0 | 30 | A | 60 | 100 |  |  |  | 20
2025-08-06 | 2120 |  | L4-TA 3 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 50 | 0 | 30 | A | 60 | 100 |  |  |  | 20
2025-08-07 | 2121 |  | L4-TA 4 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 70 | 0 | 0 |  | 60 | 100 |  |  |  | 20
2025-08-07 | 2122 |  | L4-TA 5 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 70 | 0 | 0 |  | 60 | 90 |  |  |  | 20
2025-08-07 | 2123 |  | L4-TA 6 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 60 | 0 | 0 |  | 50 | 90 |  |  |  | 20
2025-08-06 | 2124 |  | L4-TA 7 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 80 | 0 | 40 | A | 100 | 160 |  |  |  | 20
2025-08-06 | 2125 |  | L4-TA 8 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 50 | 0 | 40 | A | 80 | 120 |  |  |  | 20
2025-08-07 | 2126 |  | L4-TA 9 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 40 | 0 | 0 |  | 40 | 70 |  |  |  | 20
2025-08-07 | 2127 |  | L4-CUH 19 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-08-11 | Z | 2025-07-22 | 120 | 0 | 30 | A | 0 | 200 |  |  |  | 20
2025-08-06 | 2149 |  | 82979 - 82980 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-11 | Z | 2025-07-31 | 80 | 0 | 50 | A | 0 | 150 |  | L1-EAMP 2 ,RAMP 1 |  | 11
2025-08-05 | 2152 | w | 82984 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-07 | Z | 2025-08-04 | 20 | 0 | 0 |  | 0 | 80 |  |  |  | 3
2025-08-05 | 3997 |  | 82179 - 82180 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2025-08-11 | Z | 2025-07-29 | 60 | 0 | 0 |  | 0 | 100 |  | 009 , BSMT Louver |  | 13
2025-08-04 | 1885 |  | 75720 | A | DONE | 2 | S |  | UWP-OTTENSMAN 6240031 | paint | 2025-08-07 | Z | 2025-07-31 | 20 | 0 | 0 |  | 20 | 40 |  | TA Rm 42 |  | 7
2025-08-07 | 2873 |  | 84870 - 84871 | A | DONE | 5 | S-M |  | UWRF 6230010 | paint | 2025-08-12 | Z | 2025-07-24 | 120 | 0 | 0 |  | 100 | 170 |  | 1st floor GET |  | 19
2025-08-07 | 2874 |  | 84872 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2025-08-12 | Z | 2025-07-24 | 70 | 0 | 0 |  | 0 | 110 |  | GE tie in |  | 19
2025-08-07 | 2875 |  | 84873 | A | DONE | 2 | S |  | UWRF 6230010 | paint , 1" liner | 2025-08-12 | Z | 2025-07-24 | 30 | 0 | 0 |  | 30 | 50 |  | 1st floor TA |  | 19
2025-08-05 | 2876 | sp | 84874 | A | DONE | 3 | S | ss | UWRF 6230010 |  | 2025-08-12 | Z | 2025-07-30 | 20 | 40 | 0 |  | 0 | 60 |  | EA Drops |  | 13
2025-08-06 | 3588 |  | 85035 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 | paint | 2025-08-13 | Z | 2025-07-30 | 20 | 0 | 0 |  | 30 | 50 |  | TA |  | 14
2025-08-04 | 611 | w | 82908 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-23 | 20 | 0 | 0 |  | 0 | 20 |  | Dust collector storage |  | 16
2025-08-04 | 612 |  | L02_A_SAMP_001 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-28 | 200 | 0 | 50 | A | 0 | 410 |  |  |  | 11
2025-08-04 | 613 |  | L02_A_SAMP_002 | A | DONE | 16 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-28 | 340 | 0 | 50 | A | 0 | 530 |  |  |  | 11
2025-08-04 | 614 |  | L02_A_SAMP_003 | A | DONE | 19 | M-L |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-28 | 230 | 0 | 240 | A | 0 | 1050 |  |  |  | 11
2025-08-04 | 615 |  | L02_A_SAMP_004 | A | DONE | 18 | M |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-28 | 320 | 0 | 110 | A | 0 | 760 |  |  |  | 11
2025-08-04 | 616 |  | L02_A_SAMP_005 | A | DONE | 26 | M-L |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-28 | 480 | 0 | 150 | A | 0 | 1310 |  |  |  | 11
2025-08-04 | 617 |  | L02_A_RAD_027 | A | DONE | 16 | M |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-28 | 90 | 0 | 290 | A | 0 | 580 |  |  |  | 11
2025-08-04 | 618 |  | L02_A_RAD_028 | A | DONE | 28 | M |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-28 | 280 | 0 | 410 | A | 0 | 1000 |  |  |  | 11
2025-08-04 | 619 |  | 83320 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 | bird s. | 2025-08-08 | Z | 2025-07-30 | 50 | 0 | 0 |  | 0 | 130 |  | 2nd RA |  | 9
2025-08-04 | 620 |  | 83369 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-30 | 20 | 0 | 0 |  | 20 | 20 |  | 1st-D HP2-101 |  | 9
2025-08-04 | 621 | sp | 83370 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-30 | 0 | 20 | 0 |  | 0 | 20 |  | 1st-D HP2-101 |  | 9
2025-08-04 | 622 | w | 83372 | A | DONE | 2 | S | ss | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-07-30 | 20 | 0 | 0 |  | 0 | 20 |  | KEA tie in |  | 9
2025-08-06 | 2299 | w | 82909 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-08 | Z | 2025-08-06 | 20 | 0 | 0 |  | 0 | 20 |  | Wall Sleeve |  | 2
[6 empty] | 1386 | [13 empty] | 43280
WEEK OF 8-11-2025
2025-08-15 | 2745 | sp | 75208 - 75210 | A | DONE | 179 | M-L |  | BARTILLION 6240024 | spiralmates , 1" DW | 2025-08-19 | Z | 2025-07-16 | 290 | 4180 | 0 |  | 1180 | 3870 |  | SA Dorm 1,2 |  | 34
2025-08-14 | 552 | w | 84360 | A | DONE | 4 | S | BI | BARTILLION 6240024 |  | 2025-08-15 | Z | 2025-07-24 | 40 | 0 | 0 |  | 0 | 150 |  | Gease duct conn. |  | 22
2025-08-14 | 554 | w | 84363 | A | DONE | 2 | S | ss | BARTILLION 6240024 | BDD | 2025-08-15 | Z | 2025-07-31 | 30 | 0 | 0 |  | 0 | 60 |  | Dishwasher EA |  | 15
2025-08-15 | 561 |  | 75229 - 75232 | A | DONE | 10 | S-M |  | BARTILLION 6240024 | paint | 2025-08-19 | Z | 2025-08-11 | 230 | 0 | 0 |  | 70 | 340 |  | EA tie in corr. / misc |  | 8
2025-08-15 | 565 |  | 75251 | A | DONE | 2 | S | ss | BARTILLION 6240024 |  | 2025-08-15 | Z | 2025-08-15 | 20 | 0 | 0 |  | 0 | 20 |  | Vent flashing |  | 0
2025-08-12 | 260 |  | 84734 | A | DONE | 2 | S |  | DEFOREST MS 4250020 |  | 2025-08-13 | Z | 2025-08-08 | 20 | 0 | 0 |  | 0 | 20 |  | RD EC'S |  | 5
2025-08-13 | 3527 | bth | 73770 | A | DONE | 6 | S-M |  | DELLSHIRE 6240017 |  | 2025-08-18 | Z | 2025-08-06 | 90 | 60 | 0 |  | 0 | 160 |  | 2nd Floor retail 220 |  | 12
2025-08-14 | 3528 | bth | 73771 | A | DONE | 6 | S-M | pcd | DELLSHIRE 6240017 | bird s. | 2025-08-18 | Z | 2025-08-06 | 120 | 20 | 0 |  | 0 | 170 |  | EF-4 LL |  | 12
2025-08-13 | 881b |  | 73663 | A | DONE | 65 | M-L |  | DELLSHIRE 6240017 | paint , 1" liner | 2025-08-18 | Z | 2025-07-01 | 1620 | 0 | 0 |  | 1640 | 2800 |  |  |  | 48
2025-08-12 | 1619 | bth | Z1-SAMP 1 | A | DONE | 5 | S |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 70 | 50 | 0 |  | 0 | 140 |  |  |  | 29
2025-08-11 | 1620 | bth | Z1-SAMP 2 | A | DONE | 15 | M |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 160 | 30 | 180 | A | 0 | 480 |  |  |  | 29
2025-08-11 | 1621 | bth | Z1-SAMP 3 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 60 | 30 | 0 |  | 0 | 100 |  |  |  | 29
2025-08-11 | 1622 | bth | Z1-SAMP 4 | A | DONE | 24 | M |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 340 | 30 | 220 | A | 0 | 770 |  |  |  | 29
2025-08-11 | 1623 |  | Z1-SAMP 5 | A | DONE | 23 | M | neal | DOC JDC 6240023 | VD's | 2025-08-14 | Z | 2025-07-16 | 210 | 0 | 350 | A | 0 | 690 |  |  |  | 29
2025-08-12 | 1624 | bth | Z1-SAMP 6 | A | DONE | 8 | S |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 80 | 20 | 90 | A | 0 | 230 |  |  |  | 29
2025-08-12 | 1625 |  | Z1-SAMP 7 | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 340 | 0 | 110 | A | 0 | 770 |  |  |  | 29
2025-08-13 | 1626 |  | Z1-SAMP 8 | A | DONE | 5 | S | neal | DOC JDC 6240023 | VD's | 2025-08-14 | Z | 2025-07-16 | 110 | 0 | 0 |  | 0 | 160 |  |  |  | 29
2025-08-12 | 1627 |  | Z1-SAMP 9 | A | DONE | 5 | S |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 80 | 0 | 30 | A | 0 | 160 |  |  |  | 29
2025-08-12 | 1628 | bth | Z1-SAMP 10 | A | DONE | 15 | S-M |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 130 | 200 | 40 | A | 0 | 500 |  |  |  | 29
2025-08-13 | 1629 | bth | Z1-SAMP 11 | A | DONE | 12 | S-M |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 210 | 50 | 40 | A | 0 | 350 |  |  |  | 29
2025-08-12 | 1630 | bth | Z1-SAMP 12 | A | DONE | 31 | M-L |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 480 | 80 | 210 | A | 0 | 1210 |  |  |  | 29
2025-08-12 | 1631 | bth | Z1-SAMP 13 | A | DONE | 24 | M-L |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 360 | 50 | 170 | A | 0 | 1260 |  |  |  | 29
2025-08-12 | 1632 | bth | Z1-SAMP 14 | A | DONE | 14 | S-M |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-16 | 80 | 70 | 200 | A | 0 | 400 |  |  |  | 29
2025-08-12 | 1633 | sp | Z1-SAMP 15 | A | DONE | 3 | S |  | DOC JDC 6240023 | flex | 2025-08-14 | Z | 2025-07-16 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 29
2025-08-11 | 693 |  | 74304 DUCT | A | DONE | 6 | S |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-24 | 150 | 0 | 0 |  | 0 | 210 |  | Drywall sleeves |  | 21
2025-08-11 | 694 |  | 74304 PIPE | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-24 | 100 | 0 | 0 |  | 0 | 130 |  | Drywall sleeves |  | 21
2025-08-12 | 732 | w | 74306 - 74307 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-08-14 | Z | 2025-07-30 | 20 | 0 | 0 |  | 0 | 40 |  | Chiller drywall sleeves |  | 15
2025-08-13 | 3216 |  | 65694 - 65696 | A | DONE | 22 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-07-28 | 280 | 0 | 270 | A | 0 | 650 |  | RTU-1 |  | 21
2025-08-13 | 3217 | sp | 65697 | A | DONE | 3 | S |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-07-28 | 0 | 70 | 0 |  | 0 | 70 |  | RTU-1 SA |  | 21
2025-08-13 | 3218 |  | 65698 - 65699 | A | DONE | 9 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-07-28 | 100 | 0 | 120 | A | 0 | 270 |  | RTU-1 RA |  | 21
2025-08-13 | 3219 | sp | 65662 | A | DONE | 4 | S |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-07-28 | 20 | 60 | 0 |  | 0 | 60 |  | RTU-1 RA |  | 21
2025-08-13 | 3220 |  | 65692 | A | DONE | 9 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-07-28 | 140 | 0 | 70 | A | 0 | 240 |  | RTU-2 RA |  | 21
2025-08-13 | 3221 |  | 65684 | A | DONE | 6 | S |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-07-28 | 100 | 0 | 40 | A | 0 | 160 |  | RTU-2 SA |  | 21
2025-08-14 | 3222 |  | 65686 | A | DONE | 6 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-07-28 | 50 | 80 | 0 |  | 0 | 130 |  | Existing |  | 21
2025-08-14 | 3225 | sp | 77251 - 77252 | A | DONE | 5 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-08-06 | 70 | 50 | 0 |  | 0 | 130 |  | RTU-4 |  | 12
2025-08-14 | 3226 | sp | 77253 | A | DONE | 6 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-08-06 | 20 | 110 | 0 |  | 0 | 120 |  | RTU-6 |  | 12
2025-08-14 | 3227 | sp | 77256 | A | DONE | 5 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-08-06 | 30 | 90 | 0 |  | 0 | 120 |  | RTU-7 |  | 12
2025-08-13 | 3229 |  | 69991 | A | DONE | 6 | S-M |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-08-07 | 150 | 0 | 0 |  | 0 | 210 |  | ANGLES |  | 11
2025-08-14 | 3230 |  | 77257 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-08-12 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 6
2025-08-15 | 3231 |  | 77258 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-08-18 | Z | 2025-08-14 | 20 | 0 | 0 |  | 0 | 20 |  | RTU-5 RA |  | 4
2025-08-12 | 1736 | sp | 94050 | A | DONE | 2 | S |  | MCDS 6250005 |  | 2025-08-13 | Z | 2025-08-12 | 20 | 0 | 0 |  | 0 | 30 |  | Misc outs |  | 1
2025-08-14 | 1737 |  | 64066 | A | DONE | 2 | S |  | MCDS 8250007 |  | 2025-08-14 | Z | 2025-08-14 | 40 | 0 | 0 |  | 0 | 100 |  | Misc |  | 0
2025-08-11 | 258 |  | 74027 - 74028 | A | DONE | 3 | S-M |  | MCPASD 4250026 |  | 2025-08-14 | Z | 2025-08-06 | 60 | 0 | 0 |  | 0 | 80 |  | AHU-1 |  | 8
2025-08-12 | 259 | bth | 74029 - 74033 | A | DONE | 8 | S |  | MCPASD 4250026 | flex | 2025-08-14 | Z | 2025-08-06 | 100 | 90 | 0 |  | 0 | 180 |  | VAV-I1-01,02,03 |  | 8
2025-08-13 | 263 |  | 74034 | A | DONE | 2 | S |  | MCPASD 4250026 |  | 2025-08-14 | Z | 2025-08-13 | 20 | 0 | 0 |  | 0 | 30 |  | VAV - L1-02 |  | 1
2025-08-15 | 269 |  | 84736 | A | DONE | 3 | S |  | MCPASD 4250026 |  | 2025-08-15 | Z | 2025-08-15 | 70 | 0 | 0 |  | 0 | 110 |  | Angle |  | 0
2025-08-15 | 2097 | sp | SALP-L1G-02 | A | DONE | 26 | M-L | neal | MONROE HS 6240018 | VD's | 2025-08-19 | Z | 2025-06-18 | 240 | 410 | 0 |  | 0 | 770 |  |  |  | 62 | 2025-08-26
2025-08-15 | 2098 | sp | SALP-L1G-03 | A | DONE | 26 | M | neal | MONROE HS 6240018 | VD's | 2025-08-19 | Z | 2025-06-18 | 230 | 410 | 0 |  | 0 | 770 |  |  |  | 62 | 2025-08-26
2025-08-15 | 3032 |  | 85337 | A | DONE | 2 | S-M | neal | MONROE HS 6240018 |  | 2025-08-19 | Z | 2025-08-08 | 40 | 0 | 0 |  | 0 | 110 |  | HANGERS |  | 12
2025-08-12 | 3258 | bth | 79521 | A | DONE | 2 | S |  | ONE 09 6240037 | flex | 2025-08-15 | Z | 2025-08-11 | 20 | 0 | 0 |  | 0 | 20 |  | Wine Cooler Duct |  | 4
2025-08-14 | 3259 |  | 79522 | A | DONE | 2 | S | BI | ONE 09 6240037 |  | 2025-08-19 | Z | 2025-08-12 | 20 | 0 | 0 |  | 0 | 70 |  | FH-Hood Taps |  | 7
2025-08-14 | 4235 |  | 77151 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2025-08-18 | Z | 2025-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 27A |  | 6
2025-08-11 | 4615 | bth | L1B-SAT V-13.1 | A | DONE | 17 | S-M | pt.neal | PEWAUKEE HS 6240030 | 2" liner | 2025-08-13 | Z | 2025-07-09 | 180 | 140 | 90 | A | 140 | 490 |  |  |  | 35
2025-08-11 | 4616 | sp | L1B-SAT V-13.2 | A | DONE | 9 | S | neal | PEWAUKEE HS 6240030 | VD's | 2025-08-13 | Z | 2025-07-09 | 60 | 160 | 0 |  | 0 | 280 |  |  |  | 35
2025-08-11 | 4617 | sp | L1B-SAT V-13.3 | A | DONE | 10 | S | neal | PEWAUKEE HS 6240030 | VD's | 2025-08-13 | Z | 2025-07-09 | 70 | 160 | 0 |  | 0 | 290 |  |  |  | 35
2025-08-11 | 4618 | bth | L1B-SAT V-13.4 | A | DONE | 12 | S-M | neal | PEWAUKEE HS 6240030 | VD's , 2" liner | 2025-08-13 | Z | 2025-07-09 | 110 | 170 | 0 |  | 0 | 330 |  |  |  | 35
2025-08-11 | 4619 | bth | L1B-SAT V-14 | A | DONE | 25 | M | neal | PEWAUKEE HS 6240030 | VD's , 2" liner | 2025-08-13 | Z | 2025-07-09 | 390 | 60 | 160 | A | 360 | 940 |  |  |  | 35
2025-08-11 | 4620 | bth | L1B-SAMP 1 | A | DONE | 44 | L |  | PEWAUKEE HS 6240030 | oval , flange , 2" liner | 2025-08-13 | Z | 2025-07-09 | 600 | 480 | 0 |  | 210 | 1940 |  |  |  | 35
2025-08-12 | 4621 | sp | L1B-SAMP 2 | A | DONE | 35 | L |  | PEWAUKEE HS 6240030 | oval , accuflange | 2025-08-13 | Z | 2025-07-09 | 310 | 560 | 0 |  | 0 | 1550 |  |  |  | 35
2025-08-15 | 4622 |  | L1B-RE-9 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 | bird s. | 2025-08-20 | Z | 2025-07-09 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 42
2025-08-15 | 4623 |  | L1B-RE-8 | A | DONE | 8 | S-M | neal | PEWAUKEE HS 6240030 | bird s. | 2025-08-20 | Z | 2025-07-09 | 90 | 0 | 90 | A | 0 | 230 |  |  |  | 42
2025-08-15 | 4625 |  | L1B-TA 3 | A | DONE | 3 | S |  | PEWAUKEE HS 6240030 | bird s. , 1" liner | 2025-08-20 | Z | 2025-07-09 | 70 | 0 | 0 |  | 60 | 100 |  |  |  | 42
2025-08-15 | 4626 |  | L1B-RE-2A 1 | A | DONE | 12 | S-M | neal | PEWAUKEE HS 6240030 | 1" liner | 2025-08-20 | Z | 2025-07-09 | 150 | 0 | 150 | A | 240 | 440 |  |  |  | 42
2025-08-15 | 4627 |  | L1B-RE-2B 1 | A | DONE | 20 | M | neal | PEWAUKEE HS 6240030 | 1" liner | 2025-08-20 | Z | 2025-07-09 | 230 | 0 | 250 | A | 390 | 710 |  |  |  | 42
2025-08-15 | 4629 |  | L1B-RAMP 2 | A | DONE | 21 | M |  | PEWAUKEE HS 6240030 | bird s. , 1" liner | 2025-08-20 | Z | 2025-07-09 | 250 | 0 | 270 | A | 460 | 880 |  |  |  | 42
2025-08-15 | 4630 |  | L1B-RAMP 3 | A | DONE | 14 | S-M |  | PEWAUKEE HS 6240030 | bird s. , 1" liner | 2025-08-20 | Z | 2025-07-09 | 150 | 0 | 190 | A | 290 | 690 |  |  |  | 42
2025-08-15 | 803 |  | 76760 | A | DONE | 3 | S | pt.neal | PEWAUKEE HS 6240030 |  | 2025-08-20 | Z | 2025-08-06 | 60 | 0 | 0 |  | 0 | 100 |  | BC-1 tie in |  | 14
2025-08-11 | 1386 | bth | L2_AREA_500_MA_003 | A | DONE | 43 | L |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-08-21 | Z | 2025-06-26 | 340 | 730 | 0 |  | 0 | 2590 |  |  |  | 56
2025-08-11 | 1387 | sp | L2_AREA_500_MA_004 | A | DONE | 45 | L |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-08-21 | Z | 2025-06-26 | 320 | 790 | 0 |  | 0 | 2310 |  |  |  | 56
2025-08-14 | 4747 | bth | L01_AREA_052_SALP_017 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 29
2025-08-14 | 4748 | bth | L01_AREA_052_SALP_018 | A | DONE | 11 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 180 | 20 | 60 | A | 0 | 290 |  |  |  | 29
2025-08-13 | 4749 | sp | L01_AREA_052_SALP_019 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 29
2025-08-14 | 4750 | bth | L01_AREA_052_SALP_020 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 170 | 20 | 0 |  | 0 | 210 |  |  |  | 29
2025-08-14 | 4751 | bth | L01_AREA_052_SALP_021 | A | DONE | 9 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 80 | 90 | 40 | A | 0 | 220 |  |  |  | 29
2025-08-14 | 4752 | bth | L01_AREA_052_SALP_022 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 80 | 50 | 0 |  | 0 | 130 |  |  |  | 29
2025-08-13 | 4753 | sp | L01_AREA_052_SALP_023 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 0 | 40 | 0 |  | 0 | 40 |  |  |  | 29
2025-08-13 | 4754 | sp | L01_AREA_052_SALP_024 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 29
2025-08-13 | 4755 | sp | L01_AREA_052_SALP_025 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 29
2025-08-14 | 4756 | bth | L01_AREA_052_SALP_026 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 70 | 40 | 0 |  | 0 | 120 |  |  |  | 29
2025-08-14 | 4757 | bth | L01_AREA_052_SALP_027 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 29
2025-08-13 | 4758 | sp | L01_AREA_052_SALP_028 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 20 | 80 | 0 |  | 0 | 70 |  |  |  | 29
2025-08-14 | 4759 | bth | L01_AREA_052_SALP_029 | A | DONE | 10 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 170 | 40 | 40 | A | 0 | 270 |  |  |  | 29
2025-08-14 | 4760 | bth | L01_AREA_052_SALP_030 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-15 | Z | 2025-07-17 | 50 | 50 | 30 | A | 0 | 130 |  |  |  | 29
2025-08-11 | 4772 |  | L02_AREA_700_WEST_MA_003 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-07-31 | Z | 2025-07-23 | 180 | 0 | 0 |  | 0 | 560 |  |  |  | 8
2025-08-11 | 4773 |  | L02_AREA_700_WEST_MA_004 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-07-31 | Z | 2025-07-23 | 150 | 0 | 0 |  | 0 | 450 |  |  |  | 8
2025-08-11 | 4782 |  | L01_AREA_700_WEST_EA_001 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-07-24 | 120 | 0 | 140 | A | 0 | 370 |  |  |  | 21
2025-08-12 | 4783 |  | L01_AREA_700_WEST_EA_002 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | VD's | 2025-08-14 | Z | 2025-07-24 | 160 | 0 | 40 | A | 0 | 230 |  |  |  | 21
2025-08-11 | 4784 |  | L01_AREA_700_WEST_MA_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-07-24 | 150 | 0 | 50 | A | 0 | 350 |  |  |  | 21
2025-08-11 | 4785 |  | L01_AREA_700_WEST_MA_002 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | VD | 2025-08-14 | Z | 2025-07-24 | 60 | 0 | 100 | A | 0 | 200 |  |  |  | 21
2025-08-11 | 4786 | bth | L01_AREA_700_WEST_MA_003 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-07-24 | 60 | 80 | 0 |  | 0 | 180 |  |  |  | 21
2025-08-11 | 4793 |  | 76204 , 76207 - 76209 | A | DONE | 6 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-08-05 | 140 | 0 | 0 |  | 0 | 270 |  | Office Flashing |  | 9
2025-08-11 | 4805 |  | 76210 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-08-06 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 8
2025-08-11 | 4806 |  | 76212 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-08-06 | 20 | 0 | 0 |  | 0 | 20 |  | SAMP 10 |  | 8
2025-08-11 | 4809 |  | 76168 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-08-07 | 30 | 0 | 0 |  | 0 | 40 |  | AREA 900 EA |  | 7
2025-08-11 | 4810 |  | 80347 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-14 | Z | 2025-08-07 | 30 | 0 | 0 |  | 0 | 70 |  | MAU 13 RAMP |  | 7
2025-08-14 | 4837 |  | 76254 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-15 | Z | 2025-08-14 | 40 | 0 | 0 |  | 0 | 230 |  | Plates |  | 1
2025-08-13 | 3048 |  | 37569 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 | bird s. | 2025-08-15 | Z | 2025-08-12 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 3
2025-08-11 | 859 |  | 68879 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-08-18 | Z | 2025-08-07 | 20 | 0 | 0 |  | 0 | 20 |  | Bird screen |  | 11
2025-08-14 | 860 |  | 68881 | A | DONE | 2 | S | pt.ss | SPH SURGERY 6240039 |  | 2025-08-18 | Z | 2025-08-11 | 20 | 20 | 0 |  | 0 | 40 |  | SA misc |  | 7
2025-08-14 | 512 |  | 75525 | A | DONE | 14 | S-M | neal | SW HEALTH OR 5 6250004 | 3" DW | 2025-08-18 | Z | 2025-08-04 | 330 | 0 | 0 |  | 60 | 470 |  | Exposed |  | 14
2025-08-11 | 3100 | sp | 61945 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-08-13 | Z | 2025-08-07 | 20 | 10 | 0 |  | 10 | 30 |  | 5TH FL |  | 6
2025-08-14 | 3101 | sp | 61946 | A | DONE | 2 | S | alum | UW-AVRL 6240038 |  | 2025-08-18 | Z | 2025-08-08 | 20 | 20 | 0 |  | 0 | 40 |  | EAT-577 |  | 10
2025-08-14 | 3103 |  | 61948 | A | DONE | 5 | S |  | UW-AVRL 6240038 | paint | 2025-08-18 | Z | 2025-08-11 | 120 | 0 | 0 |  | 20 | 130 |  | Freezer Farm basement |  | 7
2025-08-11 | 3796 |  | 61942 | A | DONE | 4 | S |  | UW-AVRL 6240038 | flex | 2025-08-13 | Z | 2025-07-31 | 80 | 0 | 0 |  | 0 | 140 |  | 5th floor mech room |  | 13
2025-08-15 | 1407 |  | 83833 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VD | 2025-08-19 | Z | 2025-08-14 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 5
2025-08-14 | 2128 | bth | L4-SAT-3-4-1 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 80 | 20 | 40 | A | 20 | 170 |  |  |  | 22
2025-08-14 | 2129 | bth | L4-SAT-3-4-2 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 90 | 10 | 0 |  | 30 | 110 |  |  |  | 22
2025-08-14 | 2130 | bth | L4-SAT-3-4-3 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 20 | 20 | 30 | A | 30 | 60 |  |  |  | 22
2025-08-14 | 2131 | bth | L4-SAT-3-4-4 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 40 | 10 | 30 | A | 50 | 90 |  |  |  | 22
2025-08-14 | 2132 | bth | L4-SAT-3-4-5 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 20 | 50 | 30 | A | 30 | 100 |  |  |  | 22
2025-08-14 | 2133 | bth | L4-SAT-3-4-6 | A | DONE | 16 | M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 190 | 170 | 30 | A | 50 | 410 |  |  |  | 22
2025-08-15 | 2134 | bth | L4-SAT-3-4-7 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 22
2025-08-15 | 2135 | bth | L4-SAT-3-4-8 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 20 | 20 | 30 | A | 30 | 50 |  |  |  | 22
2025-08-15 | 2136 | bth | L4-SAT-3-4-9 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 20 | 20 | 30 | A | 30 | 80 |  |  |  | 22
2025-08-14 | 2137 | bth | L4-SAT-3-4-11 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 20 | 50 | 30 | A | 30 | 100 |  |  |  | 22
2025-08-14 | 2138 | bth | L4-SAT-3-4-28 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 60 | 20 | 0 |  | 30 | 90 |  |  |  | 22
2025-08-14 | 2139 | bth | L4-SAT-3-4-29 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 90 | 20 | 50 | A | 100 | 190 |  |  |  | 22
2025-08-15 | 2140 | bth | L4-SAT-3-4-30 | A | DONE | 8 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 120 | 30 | 50 | A | 90 | 220 |  |  |  | 22
2025-08-15 | 2141 | bth | L4-SAT-3-4-31 | A | DONE | 12 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 90 | 160 | 30 | A | 30 | 290 |  |  |  | 22
2025-08-15 | 2142 | bth | L4-SAT-3-4-32 | A | DONE | 13 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 60 | 260 | 0 |  | 20 | 380 |  |  |  | 22
2025-08-14 | 2143 | bth | L4-SAT-3-4-33 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 60 | 20 | 60 | A | 40 | 160 |  |  |  | 22
2025-08-15 | 2144 | bth | L4-SAT-3-4-34 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 60 | 20 | 20 | A | 30 | 100 |  |  |  | 22
2025-08-15 | 2145 | bth | L4-SAT-3-4-35 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 30 | 20 | 30 | A | 30 | 70 |  |  |  | 22
2025-08-15 | 2146 | bth | L4-SAT-3-4-36 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 60 | 50 | 20 | A | 30 | 130 |  |  |  | 22
2025-08-15 | 2147 | bth | L4-SAT-3-4-37 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-19 | Z | 2025-07-28 | 70 | 20 | 60 | A | 20 | 170 |  |  |  | 22
2025-08-14 | 2148 |  | L4-FCU 5 | A | DONE | 5 | S | pt.neal | UW-LEVY HALL 6230028 | VD's | 2025-08-19 | Z | 2025-07-28 | 120 | 0 | 0 |  | 0 | 190 |  |  |  | 22
2025-08-14 | 2150 |  | 82981 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | DM Frames | 2025-08-19 | Z | 2025-08-04 | 20 | 0 | 0 |  | 0 | 20 |  | L4,5 Fire damers |  | 15
2025-08-14 | 2151 |  | 82982 - 82983 | A | DONE | 4 | S-M |  | UW-LEVY HALL 6230028 | flex , MOD'S | 2025-08-19 | Z | 2025-08-04 | 100 | 0 | 0 |  | 0 | 200 |  | LL SAMP 10 |  | 15
2025-08-14 | 2177 |  | 82985 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-19 | Z | 2025-08-11 | 20 | 0 | 0 |  | 0 | 20 |  | L2 bathroom EA outs |  | 8
2025-08-15 | 3270 | bth | 38167 - 38169 | A | DONE | 5 | S-M |  | UWSP ALBERTSON 6230016 | flex | 2025-08-19 | Z | 2025-08-11 | 100 | 20 | 0 |  | 0 | 120 |  | Misc outs |  | 8
2025-08-15 | 3271 |  | 38170 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-08-19 | Z | 2025-08-14 | 30 | 0 | 0 |  | 0 | 40 |  | 1st , 4th |  | 5
2025-08-12 | 3087 | sp | 54528 | A | DONE | 4 | S |  | UW-VET MED 6210014 | angle rings | 2025-08-15 | Z | 2025-08-01 | 80 | 20 | 0 |  | 0 | 150 |  | CB-337 |  | 14
2025-08-12 | 3088 |  | 54529 | A | DONE | 4 | S |  | UW-VET MED 6210014 |  | 2025-08-15 | Z | 2025-08-01 | 80 | 0 | 0 |  | 0 | 90 |  | CB-337 |  | 14
2025-08-13 | 3589 |  | 85036 | A | DONE | 2 | S |  | UW-WHITEWATER ML 6250001 |  | 2025-08-14 | Z | 2025-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | RHC-2059 |  | 2
2025-08-13 | 3877 |  | 74795 | A | DONE | 2 | S |  | UW-WITTE HALL 6250003 |  | 2025-08-18 | Z | 2025-07-24 | 40 | 0 | 0 |  | 0 | 60 |  | Roof EA |  | 25
2025-08-13 | 3882 |  | 58170 | A | DONE | 15 | S |  | UW-WITTE HALL 6250003 | 3" DW | 2025-08-18 | Z | 2025-08-07 | 360 | 0 | 0 |  | 130 | 290 |  | SA Drops |  | 11
2025-08-12 | 1500 |  | 83373 , 83375 | A | DONE | 2 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-15 | Z | 2025-08-07 | 30 | 0 | 0 |  | 20 | 40 |  | 2nd C HP-2-215 |  | 8
2025-08-13 | 1501 | sp | 83376 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-08-07 | 0 | 80 | 0 |  | 0 | 70 |  | Misc |  | 8
2025-08-13 | 1502 |  | 79889 | A | DONE | 3 | S | pt.neal | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-08-12 | 70 | 0 | 0 |  | 0 | 100 |  | Flatstock |  | 3
2025-08-14 | 1503 | sp | 83470 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-08-14 | 20 | 60 | 0 |  | 0 | 60 |  | 2nd C |  | 1
2025-08-15 | 623 |  | L01_C_SALP_001 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-15 | Z | 2025-07-30 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 16
2025-08-13 | 624 | bth | L01_C_SALP_002 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-15 | Z | 2025-07-30 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 16
2025-08-13 | 625 | bth | L01_C_SALP_003 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-15 | Z | 2025-07-30 | 40 | 40 | 0 |  | 0 | 90 |  |  |  | 16
2025-08-13 | 626 | bth | L01_C_SALP_004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 30 | 30 | 40 | A | 0 | 100 |  |  |  | 16
2025-08-13 | 627 | bth | L01_C_SALP_005 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-15 | Z | 2025-07-30 | 40 | 60 | 0 |  | 0 | 110 |  |  |  | 16
2025-08-13 | 628 | bth | L01_C_SALP_006 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-15 | Z | 2025-07-30 | 50 | 50 | 0 |  | 0 | 100 |  |  |  | 16
2025-08-13 | 629 | bth | L01_C_SALP_007 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-15 | Z | 2025-07-30 | 40 | 40 | 50 | A | 0 | 140 |  |  |  | 16
2025-08-13 | 630 | bth | L01_C_SALP_008 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 20 | 40 | 50 | A | 0 | 120 |  |  |  | 16
2025-08-13 | 631 | bth | L01_C_SALP_009 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-15 | Z | 2025-07-30 | 30 | 80 | 0 |  | 0 | 110 |  |  |  | 16
2025-08-13 | 632 | bth | L01_C_SOA_001 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 50 | 20 | 70 | A | 0 | 160 |  |  |  | 16
2025-08-13 | 633 | bth | L01_C_SOA_002 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 20 | 50 | 60 | A | 0 | 120 |  |  |  | 16
2025-08-13 | 634 | bth | L01_C_SOA_003 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 20 | 60 | 60 | A | 0 | 150 |  |  |  | 16
2025-08-13 | 635 | bth | L01_C_SOA_004 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 40 | 90 | 40 | A | 0 | 180 |  |  |  | 16
2025-08-13 | 636 | bth | L01_C_SOA_005 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 110 | 40 | 60 | A | 0 | 240 |  |  |  | 16
2025-08-13 | 637 |  | L01_C_RAD_001 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-15 | Z | 2025-07-30 | 60 | 0 | 0 |  | 50 | 100 |  |  |  | 16
2025-08-13 | 638 | bth | L01_C_RAD_002 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-15 | Z | 2025-07-30 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 16
2025-08-13 | 639 | bth | L01_C_RAD_003 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-15 | Z | 2025-07-30 | 70 | 30 | 50 | A | 70 | 170 |  |  |  | 16
2025-08-13 | 640 | bth | L01_C_RAD_004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-15 | Z | 2025-07-30 | 50 | 40 | 0 |  | 30 | 100 |  |  |  | 16
2025-08-13 | 641 | bth | L01_C_RAD_005 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-15 | Z | 2025-07-30 | 60 | 30 | 0 |  | 30 | 90 |  |  |  | 16
2025-08-13 | 642 | bth | L01_C_RAD_006 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-15 | Z | 2025-07-30 | 60 | 30 | 0 |  | 40 | 100 |  |  |  | 16
2025-08-13 | 643 | bth | L01_C_RAD_007 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-15 | Z | 2025-07-30 | 50 | 30 | 0 |  | 20 | 80 |  |  |  | 16
2025-08-13 | 644 | bth | L01_C_EAD_001 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 70 | 70 | 130 | A | 0 | 300 |  |  |  | 16
2025-08-13 | 645 | bth | L01_C_EAD_002 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 130 | 80 | 0 |  | 0 | 270 |  |  |  | 16
2025-08-13 | 646 | bth | L01_C_EAD_003 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 20 | 20 | 70 | A | 0 | 130 |  |  |  | 16
2025-08-13 | 647 | bth | L01_C_EAD_004 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 20 | 40 | 40 | A | 0 | 110 |  |  |  | 16
2025-08-13 | 648 | bth | L01_C_EAD_005 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 40 | 20 | 50 | A | 0 | 140 |  |  |  | 16
2025-08-15 | 649 | sp | L01_C_EAD_006 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-15 | Z | 2025-07-30 | 30 | 100 | 0 |  | 0 | 120 |  |  |  | 16
[6 empty] | 1479 | [13 empty] | 47280 |  |  |  | 3970 | 8.397%
WEEK OF 8-18-2025
2025-08-18 | 560 | sp | 75228 | A | DONE | 3 | S-M |  | BARTILLION 6240024 |  | 2025-08-19 | Z | 2025-08-11 | 40 | 20 | 0 |  | 0 | 50 |  | Misc outs |  | 8
2025-08-22 | 562 | bth | 84367 | A | DONE | 8 | S |  | BARTILLION 6240024 | paint | 2025-08-25 | Z | 2025-08-12 | 200 | 0 | 0 |  | 50 | 280 |  | Stair C RA |  | 13
2025-08-22 | 563 | sp | 84371 | A | DONE | 4 | S |  | BARTILLION 6240024 |  | 2025-08-25 | Z | 2025-08-14 | 40 | 40 | 0 |  | 0 | 90 |  | L2-SA |  | 11
2025-08-22 | 564 |  | 84368 - 84370 | A | DONE | 4 | S-M |  | BARTILLION 6240024 |  | 2025-08-25 | Z | 2025-08-14 | 90 | 0 | 0 |  | 0 | 130 |  | Misc |  | 11
2025-08-22 | 566 | sp | 75234 | A | DONE | 2 | S |  | BARTILLION 6240024 | 1" spiral acoustic | 2025-08-25 | Z | 2025-08-18 | 20 | 30 | 0 |  | 50 | 70 |  | AV 1-1 , 1-5 |  | 7
2025-08-22 | 567 |  | 75233 | A | DONE | 3 | S-M |  | BARTILLION 6240024 |  | 2025-08-25 | Z | 2025-08-19 | 70 | 0 | 0 |  | 0 | 100 |  | Coil to ERV |  | 6
2025-08-22 | 568 | sp | 75235 | A | DONE | 4 | S-M |  | BARTILLION 6240024 | 1" spiral acoustic ,liner | 2025-08-25 | Z | 2025-08-19 | 70 | 30 | 0 |  | 120 | 140 |  | Flex Rm outs |  | 6
2025-08-22 | 569 | w | 75252 | A | DONE | 2 | S | BI | BARTILLION 6240024 |  | 2025-08-25 | Z | 2025-08-22 | 20 | 0 | 0 |  | 0 | 20 |  | Grease out |  | 3
2025-08-21 | 2490 | sp | 77260 - 77263 | A | DONE | 3 | S-M | neal | CDIS 6220028 |  | 2025-08-26 | Z | 2025-08-19 | 40 | 20 | 0 |  | 0 | 70 |  | Misc |  | 7
2025-08-20 | 272 |  | 84737 | A | DONE | 2 | S | ss | DEFOREST MS 4250020 |  | 2025-08-22 | Z | 2025-08-20 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2025-08-22 | 3529 | bth | 73772 , 73774 | A | DONE | 10 | S-M |  | DELLSHIRE 6240017 |  | 2025-08-25 | Z | 2025-08-14 | 60 | 170 | 0 |  | 0 | 220 |  | 4th Fl 4216 , 1st VAV |  | 11
2025-08-18 | 3530 |  | 73773 | A | DONE | 2 | S-M |  | DELLSHIRE 6240017 |  | 2025-08-20 | Z | 2025-08-14 | 40 | 0 | 0 |  | 0 | 50 |  | 2nd Fl SA outs |  | 6
2025-08-22 | 3531 |  | 73775 - 73776 | A | DONE | 32 | M |  | DELLSHIRE 6240017 |  | 2025-08-25 | Z | 2025-08-14 | 790 | 0 | 0 |  | 0 | 1680 |  | LL OA AHU-2 , 3 |  | 11
2025-08-22 | 3532 |  | 73778 | A | DONE | 7 | M |  | DELLSHIRE 6240017 |  | 2025-08-25 | Z | 2025-08-14 | 170 | 0 | 0 |  | 0 | 500 |  | L-3 AHU-3 |  | 11
2025-08-20 | 1634 | bth | Z1-SAMP 16 | A | DONE | 25 | M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-16 | 250 | 30 | 340 | A | 0 | 890 |  |  |  | 36
2025-08-19 | 1635 | bth | Z1-SAMP 17 | A | DONE | 26 | M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-16 | 290 | 40 | 320 | A | 0 | 970 |  |  |  | 36
2025-08-20 | 1636 | bth | Z1-SAMP 18 | A | DONE | 15 | S-M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-16 | 60 | 60 | 240 | A | 0 | 420 |  |  |  | 36
2025-08-20 | 1637 | bth | Z1-SAMP 19 | A | DONE | 17 | M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-16 | 290 | 50 | 80 | A | 0 | 540 |  |  |  | 36
2025-08-19 | 1638 | bth | Z1-SAMP 20 | A | DONE | 14 | S-M |  | DOC JDC 6240023 | VD | 2025-08-21 | Z | 2025-07-16 | 180 | 40 | 130 | A | 0 | 410 |  |  |  | 36
2025-08-21 | 1639 |  | Z1-SAMP 21 | A | DONE | 5 | S-M |  | DOC JDC 6240023 | MOD | 2025-08-21 | Z | 2025-07-16 | 110 | 0 | 0 |  | 0 | 290 |  |  |  | 36
2025-08-20 | 1640 | bth | Z1-SAMP 22 | A | DONE | 11 | S-M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-16 | 160 | 20 | 80 | A | 0 | 360 |  |  |  | 36
2025-08-19 | 1641 |  | Z1-SAMP 23 | A | DONE | 13 | S-M | neal | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-16 | 150 | 0 | 160 | A | 0 | 420 |  |  |  | 36
2025-08-20 | 1642 | bth | Z1-SAMP 24 | A | DONE | 5 | S |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-16 | 40 | 80 | 0 |  | 0 | 130 |  |  |  | 36
2025-08-20 | 1643 |  | Z1-SAMP 25 | A | DONE | 5 | S | neal | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-16 | 70 | 0 | 50 | A | 0 | 130 |  |  |  | 36
2025-08-21 | 1644 |  | Z2-SAMP 26 | A | DONE | 9 | S-M | neal | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-22 | 220 | 0 | 0 |  | 0 | 360 |  |  |  | 30
2025-08-20 | 1645 | bth | Z2-SAMP 27 | A | DONE | 25 | M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-22 | 230 | 30 | 360 | A | 0 | 870 |  |  |  | 30
2025-08-20 | 1646 | bth | Z2-SAMP 28 | A | DONE | 8 | S |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-22 | 100 | 60 | 30 | A | 0 | 210 |  |  |  | 30
2025-08-20 | 1647 | bth | Z2-SAMP 29 | A | DONE | 15 | S-M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-22 | 200 | 90 | 70 | A | 0 | 440 |  |  |  | 30
2025-08-20 | 1648 | bth | Z2-SAMP 30 | A | DONE | 8 | S |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-22 | 120 | 20 | 40 | A | 0 | 200 |  |  |  | 30
2025-08-21 | 1649 | bth | Z2-SAMP 31 | A | DONE | 12 | S-M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-22 | 70 | 20 | 200 | A | 0 | 350 |  |  |  | 30
2025-08-22 | 2211 |  | 74308 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-08-25 | Z | 2025-08-19 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2025-08-21 | 650 | bth | Z2-SAMP 32 | A | DONE | 2 | S |  | DOC JDC 6240023 | flex | 2025-08-21 | Z | 2025-07-22 | 20 | 20 | 0 |  | 0 | 60 |  |  |  | 30
2025-08-21 | 651 | bth | Z2-SAMP 33 | A | DONE | 30 | M-L |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-22 | 400 | 40 | 290 | A | 0 | 1340 |  |  |  | 30
2025-08-20 | 652 | bth | Z2-SAMP 34 | A | DONE | 11 | S-M |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-22 | 90 | 30 | 140 | A | 0 | 310 |  |  |  | 30
2025-08-21 | 710 | bth | Z2-EA 41 | A | DONE | 9 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-30 | 160 | 50 | 0 |  | 0 | 280 |  |  |  | 22
2025-08-20 | 711 | bth | Z2-EA 42 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-30 | 80 | 20 | 0 |  | 0 | 150 |  |  |  | 22
2025-08-20 | 712 | bth | Z2-EA 43 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-30 | 80 | 20 | 0 |  | 0 | 110 |  |  |  | 22
2025-08-20 | 713 |  | Z2-EA 44 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD | 2025-08-21 | Z | 2025-07-30 | 80 | 20 | 0 |  | 0 | 110 |  |  |  | 22
2025-08-20 | 714 |  | Z2-EA 45 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD | 2025-08-21 | Z | 2025-07-30 | 50 | 0 | 30 | A | 0 | 100 |  |  |  | 22
2025-08-20 | 719 |  | Z2-EA 50 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-07-30 | 90 | 0 | 0 |  | 0 | 110 |  |  |  | 22
2025-08-20 | 720 | bth | Z2-EA 51 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-30 | 80 | 20 | 0 |  | 0 | 110 |  |  |  | 22
2025-08-20 | 721 | bth | Z2-EA 52 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-30 | 80 | 20 | 0 |  | 0 | 110 |  |  |  | 22
2025-08-20 | 723 | bth | Z2-EA 54 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-30 | 80 | 20 | 0 |  | 0 | 110 |  |  |  | 22
2025-08-20 | 724 | bth | Z2-EA 55 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-07-30 | 90 | 0 | 0 |  | 0 | 120 |  |  |  | 22
2025-08-20 | 768 |  | Z3-EA 68 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-08-06 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 15
2025-08-20 | 769 | bth | Z3-EA 69 | A | DONE | 8 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-08-06 | 60 | 20 | 0 |  | 0 | 100 |  |  |  | 15
2025-08-20 | 770 | bth | Z3-EA 70 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-08-06 | 70 | 20 | 0 |  | 0 | 90 |  |  |  | 15
2025-08-20 | 771 | bth | Z3-EA 71 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-08-06 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 15
2025-08-20 | 772 | bth | Z3-EA 72 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-08-06 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 15
2025-08-20 | 773 |  | Z3-EA 74 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-08-21 | Z | 2025-08-06 | 50 | 0 | 0 |  | 0 | 50 |  |  |  | 15
2025-08-20 | 774 | bth | Z3-EA 77 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-08-06 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 15
2025-08-20 | 775 | bth | Z3-EA 78 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-08-06 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 15
2025-08-20 | 776 | bth | Z3-EA 79 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-08-06 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 15
2025-08-20 | 777 | bth | Z3-EA 80 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD's | 2025-08-21 | Z | 2025-08-06 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 15
2025-08-22 | 1020 |  | 56826 | A | DONE | 2 | S |  | EXACT SEQ 2250029 |  | 2025-08-25 | Z | 2025-08-21 | 20 | 0 | 0 |  | 0 | 40 |  | RD EC's |  | 4
2025-08-18 | 1019 |  | 56827 | A | DONE | 2 | S | alum | EXACT TL-5 6240014 |  | 2025-08-21 | Z | 2025-08-14 | 20 | 0 | 0 |  | 0 | 20 |  | Glass wash |  | 7
2025-08-21 | 264 |  | 74035 | A | DONE | 5 | S |  | FAIRCHILD EQUIP. 4250033 | 1" liner | 2025-08-22 | Z | 2025-08-14 | 110 | 0 | 0 |  | 70 | 140 |  | RTU-1 Drops |  | 8
2025-08-21 | 265 | bth | 74036 - 74039 | A | DONE | 23 | M |  | FAIRCHILD EQUIP. 4250033 | 1" liner | 2025-08-22 | Z | 2025-08-14 | 90 | 470 | 0 |  | 20 | 580 |  | RTU-1 |  | 8
2025-08-20 | 266 | bth | 74040 - 74042 | A | DONE | 6 | S-M |  | FAIRCHILD EQUIP. 4250033 |  | 2025-08-22 | Z | 2025-08-14 | 150 | 0 | 0 |  | 0 | 180 |  | RTU-1 |  | 8
2025-08-21 | 267 |  | 74045 - 74046 | A | DONE | 3 | S-M |  | FAIRCHILD EQUIP. 4250033 | bird s. , 1" liner | 2025-08-22 | Z | 2025-08-14 | 70 | 0 | 0 |  | 40 | 80 |  | RTU-1 |  | 8
2025-08-21 | 270 | sp | 85037 | A | DONE | 3 | S |  | JPC SAWMILL 2240068 |  | 2025-08-25 | Z | 2025-08-19 | 30 | 50 | 0 |  | 0 | 70 |  | F-1 |  | 6
2025-08-21 | 271 |  | 85038 | A | DONE | 2 | S |  | JPC SAWMILL 2240068 | bird s. , CD | 2025-08-25 | Z | 2025-08-19 | 50 | 0 | 0 |  | 0 | 70 |  | L-1 |  | 6
2025-08-20 | 273 |  | 84293 | A | DONE | 2 | S |  | MHS 4250026 |  | 2025-08-20 | Z | 2025-08-20 | 20 | 0 | 0 |  | 0 | 20 |  | EC |  | 0
2025-08-18 | 2095 |  | EA-L1G-01 | A | DONE | 14 | M | neal | MONROE HS 6240018 | CD , 1" liner | 2025-08-19 | Z | 2025-06-18 | 270 | 0 | 80 | A | 150 | 550 |  |  |  | 62 | 2025-08-26
2025-08-18 | 2096 | sp | SALP-L1G-01 | A | DONE | 40 | M-L | neal | MONROE HS 6240018 | spiral mate | 2025-08-19 | Z | 2025-06-18 | 270 | 720 | 0 |  | 0 | 1550 |  |  |  | 62 | 2025-08-26
2025-08-18 | 2099 | sp | SALP-L1G-04 | A | DONE | 21 | M | neal | MONROE HS 6240018 | VD's | 2025-08-19 | Z | 2025-06-18 | 190 | 320 | 0 |  | 0 | 580 |  |  |  | 62 | 2025-08-26
2025-08-18 | 3000 | sp | SALP-L1G-05 | A | DONE | 21 | M | neal | MONROE HS 6240018 | VD's | 2025-08-19 | Z | 2025-06-18 | 230 | 310 | 0 |  | 0 | 630 |  |  |  | 62 | 2025-08-26
2025-08-18 | 3001 | sp | SALP-L1G-06 | A | DONE | 13 | S-M | neal | MONROE HS 6240018 |  | 2025-08-19 | Z | 2025-06-18 | 60 | 270 | 0 |  | 0 | 380 |  |  |  | 62 | 2025-08-26
2025-08-18 | 3002 | bth | SALP-L1G-07 | A | DONE | 57 | L | neal | MONROE HS 6240018 | spiral mate , 2" liner | 2025-08-19 | Z | 2025-06-18 | 580 | 840 | 0 |  | 0 | 2950 |  |  |  | 62
2025-08-22 | 275 |  | 84295 | A | DONE | 2 | S |  | PARKER HS 2250043 | paint | 2025-08-22 | Z | 2025-08-22 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 0
2025-08-21 | 4236 |  | 77152 | A | DONE | 2 | S |  | PECATONICA 6240005 | VD | 2025-08-25 | Z | 2025-08-19 | 30 | 0 | 0 |  | 0 | 40 |  | RE-11 |  | 6
2025-08-21 | 4237 | sp | 77153 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2025-08-25 | Z | 2025-08-19 | 20 | 30 | 0 |  | 0 | 50 |  | Pink phase |  | 6
2025-08-20 | 4238 |  | 77155 | A | DONE | 4 | S |  | PECATONICA 6240005 | paint | 2025-08-25 | Z | 2025-08-20 | 30 | 60 | 0 |  | 0 | 80 |  | RE-11 |  | 5
2025-08-18 | 4628 |  | L1B-RAMP 1 | A | DONE | 28 | M-L | neal | PEWAUKEE HS 6240030 | 1" liner | 2025-08-20 | Z | 2025-07-09 | 480 | 0 | 210 | A | 510 | 1420 |  |  |  | 42
2025-08-22 | 804 |  | 76715 - 76716 | A | DONE | 10 | S-M |  | PEWAUKEE HS 6240030 | 1" liner , 2 " liner | 2025-08-25 | Z | 2025-08-11 | 250 | 0 | 0 |  | 180 | 500 |  | AHU Roof drop RAHU-2 |  | 14
2025-08-19 | 805 | w | 76723 | A | DONE | 2 | S | BI | PEWAUKEE HS 6240030 |  | 2025-08-20 | Z | 2025-08-18 | 20 | 0 | 0 |  | 0 | 20 |  | SA offset grease duct |  | 2
2025-08-19 | 806 |  | 76725 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-08-20 | Z | 2025-08-18 | 20 | 0 | 0 |  | 0 | 60 |  | Punch list flashing |  | 2
2025-08-21 | 807 |  | 76726 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-25 | Z | 2025-08-19 | 60 | 0 | 0 |  | 0 | 80 |  | CGS Flat Stock |  | 6
2025-08-20 | 817 |  | L1B-DC SA | delete | DONE | n/a | S-M | pt.neal | PEWAUKEE HS 6240030 | bird s. | 2025-09-03 | Z | 2025-08-20 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 14
2025-08-18 | 476 | bth | L02_NC_SALP_001 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-04-23 | 120 | 20 | 30 | A | 0 | 220 |  |  |  | 120
2025-08-21 | 477 |  | L02_NC_MA_001 | A | DONE | 22 | M | ss | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-04-23 | 530 | 0 | 0 |  | 0 | 930 |  |  |  | 120
2025-08-19 | 478 | bth | L02_NC_EA_001 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-04-23 | 90 | 20 | 0 |  | 0 | 150 |  |  |  | 120
2025-08-19 | 479 | bth | L02_NC_EA_002 | A | DONE | 10 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-04-23 | 130 | 20 | 80 | A | 0 | 270 |  |  |  | 120
2025-08-22 | 4795 |  | L02_AREA_052_SAMP_001 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 | 404 | 2025-08-22 | Z | 2025-08-05 | 210 | 0 | 0 |  | 0 | 450 |  |  |  | 17
2025-08-22 | 4797 |  | L02_AREA_052_SAMP_003 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 | 404 | 2025-08-22 | Z | 2025-08-05 | 70 | 0 | 140 | A | 0 | 410 |  |  |  | 17
2025-08-22 | 4798 | bth | L02_AREA_052_SAMP_004 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-22 | Z | 2025-08-05 | 120 | 40 | 0 |  | 0 | 270 |  |  |  | 17
2025-08-22 | 4799 | bth | L02_AREA_052_SAMP_005 | A | DONE | 14 | M |  | PROJECT DOVE 6240041 | 404 | 2025-08-22 | Z | 2025-08-05 | 110 | 70 | 150 | A | 0 | 840 |  |  |  | 17
2025-08-18 | 480 |  | L02_NC_EA_003 | A | DONE | 12 | S-M |  | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-04-23 | 90 | 0 | 210 | A | 0 | 380 |  |  |  | 120
2025-08-22 | 4800 | bth | L02_AREA_052_SAMP_006 | A | DONE | 10 | S-M |  | PROJECT DOVE 6240041 | 404 | 2025-08-22 | Z | 2025-08-05 | 150 | 40 | 50 | A | 0 | 440 |  |  |  | 17
2025-08-19 | 4807 |  | 76211 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-08-06 | 30 | 0 | 0 |  | 0 | 30 |  | IMP Hallway |  | 15
2025-08-19 | 481 | bth | L02_NC_SAMP_001 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-04-23 | 140 | 20 | 50 | A | 0 | 380 |  |  |  | 120
2025-08-19 | 4813 |  | 76251 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-21 | Z | 2025-08-12 | 50 | 0 | 0 |  | 0 | 50 |  | EF-2 |  | 9
2025-08-22 | 4814a |  | L02_AREA_052_EA_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | partial , 404 | 2025-08-22 | Z | 2025-08-12 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 10
2025-08-19 | 482 | bth | L02_NC_SAMP_002 | A | DONE | 10 | S-M |  | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-04-23 | 90 | 60 | 100 | A | 0 | 350 |  |  |  | 120
2025-08-22 | 4820a | sp | L02_AREA_052_EA_007 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | partial , 404 | 2025-08-22 | Z | 2025-08-12 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 10
2025-08-22 | 4821 |  | L02_AREA_052_EA_008 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | bird s. , 404 | 2025-08-22 | Z | 2025-08-12 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 10
2025-08-19 | 4822 |  | L02_AREA_052_RA_001 | A | DONE | 12 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-21 | Z | 2025-08-12 | 150 | 0 | 150 | A | 0 | 380 |  |  |  | 9
2025-08-22 | 4824 |  | MAU_10_MA_001 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-22 | Z | 2025-08-12 | 80 | 0 | 0 |  | 0 | 230 |  |  |  | 10
2025-08-22 | 4825 |  | MAU_10_RAMP_001 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-22 | Z | 2025-08-12 | 60 | 0 | 70 | A | 0 | 270 |  |  |  | 10
2025-08-22 | 4828 |  | AHU_006_RAMP_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-22 | Z | 2025-08-12 | 50 | 0 | 0 |  | 0 | 80 |  |  |  | 10
2025-08-22 | 4829 |  | AHU_006_SAMP_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-22 | Z | 2025-08-12 | 20 | 0 | 30 | A | 0 | 70 |  |  |  | 10
2025-08-18 | 483 |  | L02_NC_RAMP_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-21 | Z | 2025-04-23 | 50 | 0 | 0 |  | 0 | 80 |  |  |  | 120
2025-08-22 | 4831 |  | MAU_08_RAMP_001 | A | DONE | 6 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 140 | 0 | 0 |  | 0 | 270 |  |  |  | 16
2025-08-22 | 4832 |  | AHU_005_RAMP_001 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-22 | Z | 2025-08-12 | 140 | 0 | 0 |  | 0 | 250 |  |  |  | 10
2025-08-22 | 4833 |  | AHU_005_SAMP_001 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | 321 | 2025-08-22 | Z | 2025-08-12 | 180 | 0 | 0 |  | 0 | 330 |  |  |  | 10
2025-08-19 | 4834 |  | 76217 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-22 | Z | 2025-08-12 | 30 | 0 | 0 |  | 0 | 50 |  | L2 Riser |  | 10
2025-08-20 | 4838 |  | 76301 | A | DONE | 2 | S | neal | PROJECT DOVE 6240041 |  | 2025-08-21 | Z | 2025-08-18 | 20 | 0 | 0 |  | 0 | 90 |  | 700 Hangers |  | 3
2025-08-22 | 1350 |  | 68939 | A | DONE | 2 | S |  | RC INT. SCHOOL 6250011 |  | 2025-08-26 | Z | 2025-08-22 | 30 | 0 | 0 |  | 0 | 50 |  | Classrooms |  | 4
2025-08-22 | 861 | sp | 68938 | A | DONE | 2 | S | ss | SPH SURGERY 6240039 |  | 2025-08-25 | Z | 2025-08-19 | 20 | 20 | 0 |  | 0 | 50 |  | Misc |  | 6
2025-08-22 | 274 | sp | 77303 | A | DONE | 2 | S |  | SUNSET RIDGE 2250022 |  | 2025-08-25 | Z | 2025-08-22 | 20 | 20 | 0 |  | 0 | 30 |  | Kiln EA |  | 3
2025-08-20 | 514 |  | 73580 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 |  | 2025-08-25 | Z | 2025-08-14 | 20 | 0 | 0 |  | 0 | 20 |  | LPC Storm Collor |  | 11
2025-08-21 | 515 |  | 75527 | A | DONE | 2 | S |  | SW HEALTH OR 5 6250004 | paint | 2025-08-25 | Z | 2025-08-18 | 30 | 0 | 0 |  | 0 | 30 |  | Existing caps |  | 7
2025-08-21 | 516 | bth | 75528 - 75531 | A | DONE | 8 | M |  | SW HEALTH OR 5 6250004 | oval | 2025-08-25 | Z | 2025-08-18 | 120 | 70 | 0 |  | 0 | 260 |  | AHU-D SA/RA |  | 7
2025-08-21 | 517 |  | 75532 | A | DONE | 2 | S | neal | SW HEALTH OR 5 6250004 |  | 2025-08-25 | Z | 2025-08-18 | 30 | 0 | 0 |  | 0 | 30 |  | AHU-D Patch |  | 7
2025-08-18 | 3102 | sp | 61947 | A | DONE | 6 | S-M |  | UW-AVRL 6240038 |  | 2025-08-18 | Z | 2025-08-11 | 50 | 80 | 0 |  | 0 | 130 |  | Freezer Farm basement |  | 7
2025-08-18 | 3104 | sp | 61949 - 61950 | A | DONE | 11 | S-M |  | UW-AVRL 6240038 |  | 2025-08-18 | Z | 2025-08-11 | 70 | 190 | 0 |  | 0 | 260 |  | Freezer Farm basement |  | 7
2025-08-18 | 3105 |  | 69054 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-08-20 | Z | 2025-08-14 | 20 | 0 | 0 |  | 0 | 30 |  | BSL-3 lab |  | 6
2025-08-20 | 3106 |  | 69055 | A | DONE | 2 | S |  | UW-AVRL 6240038 | flex | 2025-08-25 | Z | 2025-08-20 | 40 | 0 | 0 |  | 0 | 50 |  | Misc |  | 5
2025-08-20 | 3107 |  | 69056 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-08-25 | Z | 2025-08-20 | 40 | 0 | 0 |  | 0 | 40 |  | Mech Rm Tie in |  | 5
2025-08-22 | 1408 | sp | 83834 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-14 | 0 | 20 | 0 |  | 0 | 20 |  | Rm 3269 |  | 11
2025-08-21 | 1409 |  | 83835 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-08-25 | Z | 2025-08-15 | 50 | 0 | 0 |  | 20 | 60 |  | L4-RAMP 9 #7 |  | 10
2025-08-22 | 1413 | sp | 83837 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-19 | 20 | 70 | 0 |  | 0 | 70 |  | EF 48 Roof curb |  | 6
2025-08-22 | 2178 |  | 74127 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-11 | 20 | 0 | 0 |  | 0 | 30 |  | L-4 SAMP 10 |  | 14
2025-08-22 | 1886 |  | 75722 | A | DONE | 2 | S |  | UWP-WF 6240021 |  | 2025-08-25 | Z | 2025-08-19 | 20 | 0 | 0 |  | 0 | 30 |  | Filter Channel |  | 6
2025-08-18 | 2877 |  | 84883 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-08-20 | Z | 2025-08-14 | 20 | 0 | 0 |  | 0 | 20 |  | Rm 111 W. |  | 6
2025-08-21 | 3090 |  | 54530 | A | DONE | 2 | S |  | UW-VET MED 6210014 | 1" liner | 2025-08-22 | Z | 2025-08-18 | 20 | 0 | 0 |  | 20 | 20 |  | Area 13 |  | 4
2025-08-19 | 3089 |  | 58171 - 58173 | A | DONE | 50 | M |  | UW-WITTE HALL 6250003 | 3" DW | 2025-08-20 | Z | 2025-08-14 | 1240 | 0 | 0 |  | 460 | 1550 |  | Roof EA |  | 6
2025-08-19 | 3876 |  | 74793 - 74794 | A | DONE | 82 | M-L | perf | UW-WITTE HALL 6250003 | 3" DW | 2025-08-20 | Z | 2025-07-24 | 1680 | 0 | 360 | A | 700 | 2190 |  | Roof EA |  | 27
2025-08-18 | 1504 |  | 83472 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-08-15 | 50 | 0 | 0 |  | 0 | 80 |  | 2nd B Flashing |  | 7
2025-08-18 | 1505 |  | 83473 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-08-15 | 210 | 0 | 0 |  | 0 | 240 |  | Flashing |  | 7
2025-08-21 | 1506 |  | 83321 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-08-22 | Z | 2025-08-18 | 60 | 0 | 0 |  | 20 | 80 |  | Outs |  | 4
2025-08-21 | 1929 | bth | L02_B_SALP_001 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-22 | Z | 2025-07-10 | 120 | 60 | 0 |  | 0 | 190 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1930 | bth | L02_B_SALP_002 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-22 | Z | 2025-07-10 | 60 | 60 | 50 | A | 0 | 190 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1931 | sp | L02_B_SALP_003 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-08-22 | Z | 2025-07-10 | 50 | 100 | 0 |  | 0 | 190 |  |  |  | 43 | 2025-08-08
2025-08-22 | 1932 | sp | L02_B_SALP_004 | A | DONE | 9 | S | pt.neal | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 20 | 200 | 0 |  | 0 | 260 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1933 | bth | L02_B_SAMP_001 | A | DONE | 15 | M | neal | WAUNAKEE MS 6230013 | spiral mates | 2025-08-22 | Z | 2025-07-10 | 170 | 190 | 0 |  | 0 | 670 |  |  |  | 43 | 2025-08-08
2025-08-22 | 1934 | sp | L02_B_SAMP_002 | A | DONE | 18 | M | neal | WAUNAKEE MS 6230013 | spiral mates | 2025-08-22 | Z | 2025-07-10 | 20 | 420 | 0 |  | 0 | 580 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1935 | sp | L02_B_SAMP_003 | A | DONE | 27 | M | neal | WAUNAKEE MS 6230013 | spiral mates | 2025-08-22 | Z | 2025-07-10 | 80 | 580 | 0 |  | 0 | 970 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1936 | sp | L02_B_SAMP_004 | A | DONE | 18 | M | neal | WAUNAKEE MS 6230013 | spiral mates | 2025-08-22 | Z | 2025-07-10 | 40 | 410 | 0 |  | 0 | 560 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1937 | sp | L02_B_SAMP_005 | A | DONE | 26 | M | neal | WAUNAKEE MS 6230013 | spiral mates | 2025-08-22 | Z | 2025-07-10 | 90 | 560 | 0 |  | 0 | 990 |  |  |  | 43 | 2025-08-08
2025-08-22 | 1938 | sp | L02_B_SAMP_006 | A | DONE | 18 | M | neal | WAUNAKEE MS 6230013 | spiral mates | 2025-08-22 | Z | 2025-07-10 | 20 | 420 | 0 |  | 0 | 580 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1939 |  | L02_B_SOA_001 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 80 | 0 | 0 |  | 0 | 100 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1940 |  | L02_B_SOA_002 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 50 | 0 | 120 | A | 0 | 220 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1941 | bth | L02_B_SOA_003 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 50 | 50 | 140 | A | 0 | 280 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1942 | sp | L02_B_SOA_004 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1943 |  | L02_B_EAD_001 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 90 | 0 | 0 |  | 0 | 110 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1944 |  | L02_B_EAD_002 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 30 | 0 | 50 | A | 0 | 100 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1945 | bth | L02_B_EAD_003 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 30 | 40 | 50 | A | 0 | 130 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1946 | bth | L02_B_EAD_004 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-10 | 20 | 90 | 0 |  | 0 | 110 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1947 |  | L02_B_RAD_001 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-22 | Z | 2025-07-10 | 90 | 0 | 70 | A | 110 | 190 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1948 |  | L02_B_RAD_002 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-22 | Z | 2025-07-10 | 80 | 0 | 70 | A | 110 | 190 |  |  |  | 43 | 2025-08-08
2025-08-21 | 1949 |  | L02_B_RAD_003 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-22 | Z | 2025-07-10 | 110 | 0 | 0 |  | 80 | 170 |  |  |  | 43 | 2025-08-08
2025-08-22 | 600 |  | L02_B_RAD_004 | A | DONE | 30 | M | neal | WAUNAKEE MS 6230013 | VD's , 1" liner | 2025-08-22 | Z | 2025-07-10 | 430 | 0 | 300 | A | 0 | 1000 |  |  |  | 43 | 2025-08-08
2025-08-21 | 603 | sp | L01_B_SALP_001 | A | DONE | 8 | S | neal | WAUNAKEE MS 6230013 | flex | 2025-08-22 | Z | 2025-07-14 | 30 | 150 | 0 |  | 0 | 220 |  |  |  | 39
2025-08-21 | 604 | sp | L01_B_SALP_002 | A | DONE | 8 | S | neal | WAUNAKEE MS 6230013 | flex | 2025-08-22 | Z | 2025-07-14 | 40 | 150 | 0 |  | 0 | 220 |  |  |  | 39
2025-08-21 | 605 | sp | L01_B_SOA_001 | A | DONE | 6 | S | neal | WAUNAKEE MS 6230013 |  | 2025-08-22 | Z | 2025-07-14 | 20 | 120 | 0 |  | 0 | 150 |  |  |  | 39
2025-08-21 | 606 | bth | L01_B_SOA_002 | A | DONE | 6 | S | neal | WAUNAKEE MS 6230013 | VD | 2025-08-22 | Z | 2025-07-14 | 30 | 50 | 60 | A | 0 | 170 |  |  |  | 39
2025-08-21 | 607 |  | L01_B_RAD_001 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-22 | Z | 2025-07-14 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 39
2025-08-22 | 608 |  | L01_B_RAD_002 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-08-22 | Z | 2025-07-14 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 39
[6 empty] | 1366 | [13 empty] | 46470 |  |  |  | 10100 | 21.73%
WEEK OF 8-25-2025
2025-08-25 | 268 |  | 81425 | A | DONE | 2 | S |  | ABORETUM 20009852 | filter rack | 2025-09-02 | Z | 2025-08-14 | 20 | 0 | 0 |  | 20 | 20 |  | Filter Rack |  | 19
2025-08-28 | 2746 | sp | 75211 - 75212 | A | DONE | 121 | M-L |  | BARTILLION 6240024 | spiralmates , 1" DW | 2025-08-29 | Z | 2025-07-16 | 200 | 2810 | 0 |  | 800 | 2610 |  | SA Dorm 1,2nd Floor outs |  | 44
2025-08-27 | 3533 |  | 73804 | A | DONE | 2 | S |  | DELLSHIRE 6240017 | 2" liner | 2025-09-02 | Z | 2025-08-19 | 50 | 0 | 0 |  | 30 | 60 |  | Lobby drum outs |  | 14
2025-08-28 | 3534 |  | 100326 , 100276 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-09-02 | Z | 2025-08-19 | 20 | 0 | 0 |  | 0 | 80 |  | Extensions |  | 14
2025-08-27 | 3535 |  | 73805 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-09-02 | Z | 2025-08-22 | 40 | 0 | 0 |  | 0 | 80 |  | Area well flashing / chase |  | 11
2025-08-27 | 2213 |  | 74309 | A | DONE | 2 | S | BI | DOC JDC 6240023 |  | 2025-08-28 | Z | 2025-08-20 | 50 | 0 | 0 |  | 0 | 130 |  | Flat Stock |  | 8
2025-08-25 | 3232 |  | 69992 | A | DONE | 2 | S-M |  | HISTOSONICS 6250009 | paint , 1" liner | 2025-08-26 | Z | 2025-08-22 | 20 | 0 | 0 |  | 20 | 30 |  | Misc |  | 4
2025-08-27 | 279 |  | 85039 | A | DONE | 5 | S | neal | JPC SAWMILL 2240068 |  | 2025-08-28 | Z | 2025-08-26 | 120 | 0 | 0 |  | 0 | 160 |  | WALLS |  | 2
2025-08-26 | 278 |  | 84735 | A | DONE | 2 | S |  | KEVIN M. 1000382 | bird s. | 2025-08-26 | Z | 2025-08-26 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 0
2025-08-25 | 277 |  | 74047 | A | DONE | 2 | S | pt.neal | MCPASD 4250026 | 1" liner | 2025-08-28 | Z | 2025-08-25 | 30 | 0 | 0 |  | 20 | 30 |  | Misc |  | 3
2025-08-29 | 2088 |  | OA-L2F-04 | A | DONE | 42 | L |  | MONROE HS 6240018 | CD | 2025-09-03 | Z | 2025-06-18 | 720 | 0 | 330 |  | 0 | 2140 |  |  |  | 77 | 2025-08-12
2025-08-29 | 2089 |  | RA-L2F-01 | A | DONE | 7 | S |  | MONROE HS 6240018 | CD | 2025-09-03 | Z | 2025-06-18 | 120 | 0 | 40 |  | 0 | 220 |  |  |  | 77 | 2025-08-12
2025-08-29 | 2090 |  | RA-L2F-02 | A | DONE | 8 | S |  | MONROE HS 6240018 | CD | 2025-09-03 | Z | 2025-06-18 | 160 | 0 | 40 |  | 0 | 280 |  |  |  | 77 | 2025-08-12
2025-08-29 | 2093 |  | SALP-L2F-03 | A | DONE | 35 | M |  | MONROE HS 6240018 | 2" liner | 2025-09-03 | Z | 2025-06-18 | 360 | 0 | 150 |  | 370 | 740 |  |  |  | 77 | 2025-08-12
2025-08-29 | 2094 |  | SALP-L2F-04 | A | DONE | 49 | M |  | MONROE HS 6240018 | 2" liner | 2025-09-03 | Z | 2025-06-18 | 460 | 0 | 240 |  | 530 | 1150 |  |  |  | 77 | 2025-08-12
2025-08-28 | 3033 |  | 83651 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-09-03 | Z | 2025-08-19 | 40 | 0 | 0 |  | 40 | 70 |  | 1st B |  | 15
2025-08-29 | 3034 |  | 85338 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-09-03 | Z | 2025-08-19 | 50 | 0 | 0 |  | 50 | 80 |  | L1-A1-EA |  | 15
2025-08-25 | 3035 | bth | 85339 | A | DONE | 5 | S | neal | MONROE HS 6240018 |  | 2025-08-26 | Z | 2025-08-22 | 120 | 0 | 0 |  | 0 | 270 |  | Gym |  | 4
2025-08-25 | 3808 | bth | EA-LL-01 | A | DONE | 20 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-08-26 | Z | 2025-05-15 | 90 | 240 | 150 | A | 170 | 540 |  |  |  | 103 | 2025-06-17 | 2025-07-29
2025-08-25 | 3809 | bth | EA-LL-02 | A | DONE | 38 | M-L |  | MONROE HS 6240018 | 1" liner | 2025-08-26 | Z | 2025-05-15 | 320 | 240 | 380 | A | 600 | 1340 |  |  |  | 103 | 2025-06-17 | 2025-07-29
2025-08-25 | 3810 | bth | EA-LL-03 | A | DONE | 19 | S-M |  | MONROE HS 6240018 | 1" liner | 2025-08-26 | Z | 2025-05-15 | 150 | 110 | 210 | A | 270 | 550 |  |  |  | 103 | 2025-06-17 | 2025-07-29
2025-08-25 | 3811 | bth | EA-LL-04 | A | DONE | 18 | S-M |  | MONROE HS 6240018 | VD , 1" liner | 2025-08-26 | Z | 2025-05-15 | 200 | 110 | 130 | A | 260 | 560 |  |  |  | 103 | 2025-06-17 | 2025-07-29
2025-08-25 | 3812 |  | EA-LL-05 | A | DONE | 27 | M | neal | MONROE HS 6240018 | 1" liner | 2025-08-26 | Z | 2025-05-15 | 320 | 0 | 340 | A | 590 | 940 |  |  |  | 103 | 2025-06-17 | 2025-07-29
2025-08-26 | 3813 |  | RA-LL-02 | A | DONE | 95 | L |  | MONROE HS 6240018 | VD , 1" liner | 2025-08-26 | Z | 2025-05-15 | 1470 | 0 | 890 | A | 1790 | 4560 |  |  |  | 103 | 2025-06-17 | 2025-07-29
2025-08-28 | 3822 |  | RA-LL-03 | A | DONE | 102 | S-M |  | MONROE HS 6240018 | partial | 2025-09-02 | Z | 2025-08-28 | 0 | 0 | 1330 |  | 1220 | 2220 |  | coil line duct |  | 5
2025-08-25 | 260 |  | 75718 | A | DONE | 2 | S |  | MSN 2250040 |  | 2025-08-29 | Z | 2025-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | MSN DR-6 |  | 17
2025-08-26 | 261 |  | 75721 | A | DONE | 2 | S | alum | MSN 2250040 |  | 2025-08-29 | Z | 2025-08-12 | 30 | 0 | 0 |  | 0 | 60 |  | DR-3 Cabinet 206.01.16 |  | 17
2025-08-26 | 3260 |  | 79524 - 79525 | A | DONE | 21 | S-M |  | ONE 09 6240037 |  | 2025-08-28 | Z | 2025-08-19 | 310 | 0 | 200 | A | 0 | 600 |  | MAU 1,2 |  | 9
2025-08-25 | 3261 | w | 79526 | A | DONE | 2 | S | BI | ONE09 6240037 |  | 2025-08-26 | Z | 2025-08-25 | 20 | 0 | 0 |  | 0 | 40 |  | FH Vendor ED |  | 1
2025-08-26 | 3262 | w | 79527 | A | DONE | 2 | S | BI | ONE09 6240037 |  | 2025-08-27 | Z | 2025-08-25 | 40 | 0 | 0 |  | 0 | 130 |  | FH Grease duct |  | 2
2025-08-26 | 4631 | sp | L1B-EA WELDING 1 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-27 | Z | 2025-07-10 | 20 | 50 | 0 |  | 0 | 90 |  |  |  | 48
2025-08-26 | 4632 | sp | L1B-EA LASER 1 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-27 | Z | 2025-07-10 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 48
2025-08-26 | 4633 | sp | L1B-EA LASER 2 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-27 | Z | 2025-07-10 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 48
2025-08-26 | 4634 |  | L1B-BCU-1 RA 1 | A | DONE | 9 | S-M | pt.neal | PEWAUKEE HS 6240030 | CD's , 1" liner | 2025-08-27 | Z | 2025-07-10 | 140 | 0 | 80 | A | 140 | 320 |  |  |  | 48
2025-08-26 | 4635 | bth | L1B-BCU-1 SA 1 | A | DONE | 26 | M | neal | PEWAUKEE HS 6240030 | VD's , 2" liner | 2025-08-27 | Z | 2025-07-10 | 200 | 450 | 0 |  | 80 | 840 |  |  |  | 48
2025-08-26 | 4636 |  | L1B-RE-12 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-27 | Z | 2025-07-10 | 40 | 0 | 30 | A | 0 | 110 |  |  |  | 48
2025-08-26 | 4637 |  | L1B-RE-13 | A | DONE | 7 | S-M | neal | PEWAUKEE HS 6240030 |  | 2025-08-27 | Z | 2025-07-10 | 170 | 0 | 0 |  | 0 | 250 |  |  |  | 48
2025-08-26 | 4638 |  | L1B-RE-14 | A | DONE | 4 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-27 | Z | 2025-07-10 | 100 | 0 | 0 |  | 0 | 180 |  |  |  | 48
2025-08-26 | 4639 |  | L1B-RE-3 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-08-27 | Z | 2025-07-10 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 48
2025-08-26 | 4640 | bth | L1B-BCU-2 SA 1 | A | DONE | 29 | M | neal | PEWAUKEE HS 6240030 | 2" liner | 2025-08-27 | Z | 2025-07-15 | 160 | 450 | 100 | A | 90 | 1020 |  |  |  | 43
2025-08-26 | 4641 |  | L1B-RE-4 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 | bird s. | 2025-08-27 | Z | 2025-07-15 | 60 | 0 | 0 |  | 0 | 120 |  |  |  | 43
2025-08-27 | 4642 |  | L1B-BCU-2 RA 1 | A | DONE | 5 | S | neal | PEWAUKEE HS 6240030 | bird s. | 2025-08-27 | Z | 2025-07-15 | 110 | 0 | 0 |  | 0 | 200 |  |  |  | 43
2025-08-26 | 4796 | sp | L02_AREA_052_SAMP_002 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-28 | Z | 2025-08-05 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 23
2025-08-26 | 4801 |  | L02_AREA_052_SAMP_007 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 | 404 | 2025-08-28 | Z | 2025-08-05 | 180 | 0 | 40 | A | 0 | 440 |  |  |  | 23
2025-08-26 | 4802 | bth | L02_AREA_052_SAMP_008 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 | 404 | 2025-08-28 | Z | 2025-08-05 | 80 | 30 | 100 | A | 0 | 270 |  |  |  | 23
2025-08-26 | 4803 | bth | L02_AREA_052_SAMP_009 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-28 | Z | 2025-08-05 | 30 | 20 | 20 | A | 0 | 80 |  |  |  | 23
2025-08-26 | 4804 | bth | L02_AREA_052_SAMP_010 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-28 | Z | 2025-08-05 | 120 | 20 | 0 |  | 0 | 190 |  |  |  | 23
2025-08-25 | 4812 |  | 76216 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 70 | 0 | 0 |  | 0 | 100 |  | Office Flashing |  | 16
2025-08-27 | 4814 |  | L02_AREA_052_EA_001 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | partial | 2025-08-28 | Z | 2025-08-12 | 60 | 0 | 90 | A | 0 | 190 |  |  |  | 16
2025-08-26 | 4815 |  | L02_AREA_052_EA_002 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | VD | 2025-08-28 | Z | 2025-08-12 | 90 | 0 | 70 | A | 0 | 200 |  |  |  | 16
2025-08-26 | 4816 | sp | L02_AREA_052_EA_003 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 16
2025-08-26 | 4817 | sp | L02_AREA_052_EA_004 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 16
2025-08-26 | 4818 | bth | L02_AREA_052_EA_005 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 16
2025-08-26 | 4819 | sp | L02_AREA_052_EA_006 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 16
2025-08-28 | 4820 |  | L02_AREA_052_EA_007 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | partial | 2025-08-28 | Z | 2025-08-12 | 40 | 0 | 0 |  | 0 | 110 |  |  |  | 16
2025-08-25 | 4826 |  | MAU_09_MA_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 190 | 0 | 0 |  | 0 | 490 |  |  |  | 16
2025-08-25 | 4827 |  | MAU_09_RA_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 190 | 0 | 0 |  | 0 | 520 |  |  |  | 16
2025-08-25 | 4830 |  | MAU_08_MA_001 | A | DONE | 6 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-12 | 140 | 0 | 0 |  | 0 | 330 |  |  |  | 16
2025-08-26 | 4835 |  | 76252 - 76253 | A | DONE | 19 | M |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-14 | 330 | 0 | 130 | A | 0 | 590 |  | 600 Drops |  | 14
2025-08-25 | 4836 | w | 76218 | A | DONE | 2 | S-M |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-14 | 20 | 0 | 0 |  | 0 | 90 |  | LU-0002 |  | 14
2025-08-25 | 4847 | w | 80348 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-19 | 20 | 0 | 0 |  | 0 | 100 |  | Misc |  | 9
2025-08-25 | 4848 |  | 76219 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 404 | 2025-08-28 | Z | 2025-08-20 | 20 | 0 | 0 |  | 0 | 20 |  | L02_052_EA_001 |  | 8
2025-08-28 | 4850 | w | L02_AREA_200_MA_003 | A | DONE | 6 | S-M | ss | PROJECT DOVE 6240041 | VD's | 2025-09-04 | Z | 2025-08-20 | 150 | 0 | 0 |  | 0 | 310 |  |  |  | 15
2025-08-26 | 4852 |  | 76220 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-21 | 50 | 0 | 0 |  | 0 | 80 |  | VAV-0405 Office |  | 7
2025-08-26 | 4854 |  | 76222 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-08-28 | Z | 2025-08-22 | 20 | 0 | 0 |  | 0 | 20 |  | Office |  | 6
2025-08-26 | 946 | sp | 37570 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 |  | 2025-08-28 | Z | 2025-08-25 | 20 | 30 | 0 |  | 0 | 60 |  | Misc |  | 3
2025-08-27 | 276 | w | 8223 | A | DONE | 2 | S |  | RAMC CLINIC 6259999 | wood nailer , 1-1/2 DB | 2025-09-03 | Z | 2025-08-22 | 20 | 0 | 0 |  | 20 | 30 |  | Roof Curb |  | 12
2025-08-25 | 2415 |  | 76727 | A | DONE | 2 | S |  | ST.BERNARD 2230056 | paint | 2025-08-26 | Z | 2025-08-22 | 20 | 0 | 0 |  | 20 | 20 |  | Grile box |  | 4
2025-08-28 | 529 |  | 98729 | A | DONE | 2 | S | bi | SW HEALTH MOB 6250015 |  | 2025-08-28 | Z | 2025-08-28 | 20 | 0 | 0 |  | 0 | 20 |  | BI Caps |  | 0.5
2025-08-27 | 518 | sp | 75533 - 75534 | A | DONE | 8 | S-M |  | SW HEALTH OR 5 6250004 | oval | 2025-09-02 | Z | 2025-08-22 | 140 | 50 | 0 |  | 0 | 210 |  | E1-02 HP |  | 11
2025-08-27 | 519 |  | 75535 - 75540 | A | DONE | 9 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-09-02 | Z | 2025-08-22 | 80 | 90 | 50 | A | 0 | 240 |  | Misc |  | 11
2025-08-27 | 520 |  | 75541 | A | DONE | 2 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-09-02 | Z | 2025-08-22 | 20 | 0 | 0 |  | 0 | 30 |  | HP SA |  | 11
2025-08-27 | 521 |  | 75542 | A | DONE | 4 | S-M |  | SW HEALTH OR 5 6250004 |  | 2025-09-02 | Z | 2025-08-22 | 20 | 80 | 0 |  | 0 | 90 |  | Extra |  | 11
2025-08-28 | 4657 | w | 82232 | A | DONE | 2 | S | neal | TOMAH HEALTH 6250006 | paint | 2025-09-02 | Z | 2025-08-14 | 20 | 0 | 0 |  | 0 | 20 |  | RTU Sleeve |  | 19
2025-08-26 | 3108 | w | 69057 | A | DONE | 2 | S | ss | UW-AVRL 6240038 | Flanges Ordered | 2025-08-29 | Z | 2025-08-21 | 20 | 0 | 0 |  | 0 | 60 |  | 5th FL Tie In |  | 8
2025-08-25 | 1410 |  | 83836 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-09-02 | Z | 2025-08-18 | 40 | 0 | 0 |  | 0 | 40 |  | L5 Misc |  | 15
2025-08-27 | 1414 |  | 83839 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-09-02 | Z | 2025-08-25 | 20 | 0 | 0 |  | 0 | 40 |  | EL Shaft RAMP 4th / 5th |  | 8
2025-08-27 | 1423 |  | 83843 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-27 | Z | 2025-08-27 | 20 | 0 | 0 |  | 0 | 20 |  | L3-West Shaft-SAMP-1 |  | 0.5
2025-08-25 | 2153 | bth | L5-SAT 3-5-11 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 50 | 20 | 40 | A | 20 | 130 |  |  |  | 20
2025-08-25 | 2154 | bth | L5-SAT 3-5-12 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 30 | 20 | 40 | A | 30 | 110 |  |  |  | 20
2025-08-25 | 2155 | bth | L5-SAT 3-5-13 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 20
2025-08-25 | 2156 | bth | L5-SAT 3-5-14 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 30 | 20 | 0 |  | 30 | 60 |  |  |  | 20
2025-08-25 | 2157 | bth | L5-SAT 3-5-15 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 50 | 50 | 0 |  | 30 | 100 |  |  |  | 20
2025-08-25 | 2158 | bth | L5-SAT 3-5-16 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 120 | 70 | 0 |  | 40 | 220 |  |  |  | 20
2025-08-25 | 2159 |  | L5-SAT 3-5-17 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 90 | 0 | 40 | A | 40 | 150 |  |  |  | 20
2025-08-25 | 2160 |  | L5-SAT 3-5-18 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 20
2025-08-25 | 2161 | bth | L5-SAT 3-5-19 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 60 | 50 | 0 |  | 40 | 130 |  |  |  | 20
2025-08-25 | 2162 | bth | L5-SAT 3-5-20 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 80 | 20 | 60 | A | 30 | 170 |  |  |  | 20
2025-08-25 | 2163 | bth | L5-SAT 3-5-21 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VD , VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 50 | 20 | 0 |  | 20 | 90 |  |  |  | 20
2025-08-25 | 2164 | bth | L5-SAT 3-5-22 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 40 | 20 | 0 |  | 30 | 70 |  |  |  | 20
2025-08-25 | 2165 | bth | L5-SAT 3-5-23 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 60 | 20 | 0 |  | 30 | 100 |  |  |  | 20
2025-08-25 | 2166 |  | L5-SAT 3-5-24 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 100 | 0 | 0 |  | 40 | 110 |  |  |  | 20
2025-08-25 | 2167 | bth | L5-SAT 3-5-25 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 90 | 20 | 20 | A | 30 | 150 |  |  |  | 20
2025-08-25 | 2168 | bth | L5-SAT 3-5-26 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 60 | 20 | 20 | A | 20 | 120 |  |  |  | 20
2025-08-25 | 2169 | bth | L5-SAT 3-5-27 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 50 | 40 | 0 |  | 30 | 90 |  |  |  | 20
2025-08-25 | 2170 | bth | L5-SAT 3-5-28 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-08-25 | Z | 2025-08-05 | 50 | 20 | 0 |  | 30 | 70 |  |  |  | 20
2025-08-25 | 2171 |  | L5-TA 1 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-05 | 70 | 0 | 0 |  | 50 | 90 |  |  |  | 20
2025-08-25 | 2172 |  | L5-TA 2 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-05 | 70 | 0 | 0 |  | 50 | 90 |  |  |  | 20
2025-08-25 | 2173 |  | L5-TA 3 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-05 | 70 | 0 | 0 |  | 60 | 100 |  |  |  | 20
2025-08-25 | 2174 |  | L5-TA 4 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-05 | 80 | 0 | 0 |  | 60 | 100 |  |  |  | 20
2025-08-25 | 2175 |  | L5-TA 5 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-05 | 80 | 0 | 0 |  | 60 | 100 |  |  |  | 20
2025-08-25 | 2176 |  | L5-TA 7 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2025-08-25 | Z | 2025-08-05 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 20
2025-08-28 | 2179 |  | MER-SAMP 1 | A | DONE | 84 | L |  | UW-LEVY HALL 6230028 | partial , VD's | 2025-09-02 | Z | 2025-08-12 | 2090 | 0 | 0 |  | 0 | 5630 |  |  |  | 21
2025-08-28 | 2180 |  | MER-SAMP 2 | A | DONE | 71 | L |  | UW-LEVY HALL 6230028 |  | 2025-09-02 | Z | 2025-08-12 | 1560 | 0 | 200 | A | 0 | 3030 |  |  |  | 21
2025-08-29 | 2183 | bth | L5-SAT 3-5-2 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 80 | 10 | 0 |  | 30 | 100 |  |  |  | 21
2025-08-28 | 2184 |  | L5-SAT 3-5-3 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 60 | 0 | 20 |  | 30 | 110 |  |  |  | 21
2025-08-28 | 2185 | bth | L5-SAT 3-5-4 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 70 | 10 | 20 |  | 30 | 130 |  |  |  | 21
2025-08-29 | 2187 | bth | L5-SAT 3-5-6 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 50 | 70 | 0 |  | 30 | 130 |  |  |  | 21
2025-08-28 | 2188 |  | L5-SAT 3-5-7 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-09-02 | Z | 2025-08-12 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 21
2025-08-29 | 2189 | bth | L5-SAT 3-5-8 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 20 | 10 | 30 |  | 30 | 60 |  |  |  | 21
2025-08-28 | 2191 | bth | L5-SAT 3-5-10 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 30 | 0 | 30 |  | 30 | 60 |  |  |  | 21
2025-08-29 | 2192 | bth | L5-SAT 3-5-29 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 60 | 30 | 30 |  | 30 | 150 |  |  |  | 21
2025-08-29 | 2194 | bth | L5-SAT 3-5-31 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 90 | 270 | 60 |  | 40 | 470 |  |  |  | 21
2025-08-29 | 2195 | bth | L5-SAT 3-5-32 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 40 | 10 | 30 |  | 30 | 100 |  |  |  | 21
2025-08-29 | 2196 | bth | L5-SAT 3-5-33 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 60 | 40 | 110 |  | 30 | 270 |  |  |  | 21
2025-08-26 | 3091 |  | PRE-FAB HANGERS | A | DONE | 2 | S | neal | UW-VET MED 6210014 |  | 2025-09-02 | Z | 2025-08-18 | 20 | 0 | 0 |  | 0 | 30 |  | Hangers |  | 15
2025-08-27 | 3092 | sp | 54531 | A | DONE | 8 | S-M |  | UW-VET MED 6210014 |  | 2025-09-02 | Z | 2025-08-18 | 20 | 170 | 0 |  | 0 | 180 |  | CB 372 |  | 15
2025-08-27 | 1514 |  | 83385 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-27 | 40 | 0 | 0 |  | 0 | 50 |  | GYM |  | 2
2025-08-26 | 2250 |  | L02_A_EAD_002 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 140 | 0 | 40 | A | 0 | 230 |  |  |  | 24
2025-08-26 | 2251 | bth | L02_A_EAD_003 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 30 | 20 | 220 | A | 0 | 310 |  |  |  | 24
2025-08-26 | 2252 | bth | L02_A_EAD_004 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 40 | 20 | 130 | A | 0 | 220 |  |  |  | 24
2025-08-26 | 2253 | bth | L02_A_EAD_005 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 60 | 20 | 70 | A | 0 | 150 |  |  |  | 24
2025-08-26 | 2254 | bth | L02_A_EAD_006 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 30 | 20 | 110 | A | 0 | 180 |  |  |  | 24
2025-08-26 | 2255 |  | L02_A_EAD_007 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 90 | 0 | 90 | A | 0 | 210 |  |  |  | 24
2025-08-27 | 2256 | bth | L02_A_EAD_008 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 24
2025-08-27 | 2257 | bth | L02_A_EAD_009 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 120 | 0 |  | 0 | 120 |  |  |  | 24
2025-08-26 | 2258 | bth | L02_A_EAD_010 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 24
2025-08-26 | 2259 |  | L02_A_EAD_011 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 40 | 0 | 50 | A | 0 | 110 |  |  |  | 24
2025-08-27 | 2260 | bth | L02_A_EAD_012 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 70 | 40 | 0 |  | 0 | 130 |  |  |  | 24
2025-08-26 | 2261 |  | L02_A_EAD_013 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 0 | 60 | A | 0 | 90 |  |  |  | 24
2025-08-26 | 2262 | sp | L02_A_EAD_014 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 24
2025-08-26 | 2263 |  | L02_A_EAD_015 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 70 | 0 | 80 | A | 0 | 200 |  |  |  | 24
2025-08-27 | 2264 | bth | L02_A_EAD_016 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 | VD | 2025-08-29 | Z | 2025-08-05 | 60 | 20 | 100 | A | 0 | 200 |  |  |  | 24
2025-08-26 | 2265 | sp | L02_A_EAD_017 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 30 | 0 |  | 0 | 30 |  |  |  | 24
2025-08-26 | 2266 | sp | L02_A_EAD_018 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 24
2025-08-26 | 2267 | sp | L02_A_EAD_019 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 0 | 90 | 0 |  | 0 | 80 |  |  |  | 24
2025-08-27 | 2268 | sp | L02_A_EAD_020 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 24
2025-08-27 | 2269 |  | L02_A_SOA_002 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 170 | 0 | 40 | A | 0 | 260 |  |  |  | 24
2025-08-27 | 2270 | bth | L02_A_SOA_003 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 130 | 0 | 40 | A | 0 | 230 |  |  |  | 24
2025-08-27 | 2271 |  | L02_A_SOA_004 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 60 | 0 | 100 | A | 0 | 200 |  |  |  | 24
2025-08-27 | 2272 |  | L02_A_SOA_005 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 50 | 0 | 130 | A | 0 | 220 |  |  |  | 24
2025-08-27 | 2273 | bth | L02_A_SOA_006 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 40 | 70 | 130 | A | 0 | 280 |  |  |  | 24
2025-08-27 | 2274 |  | L02_A_SOA_007 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 90 | 0 | 180 | A | 0 | 360 |  |  |  | 24
2025-08-26 | 2275 | sp | L02_A_SOA_008 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 120 | 0 |  | 0 | 120 |  |  |  | 24
2025-08-26 | 2276 | sp | L02_A_SOA_009 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 24
2025-08-26 | 2277 | sp | L02_A_SOA_010 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 24
2025-08-26 | 2278 | sp | L02_A_SOA_011 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 0 | 40 | 0 |  | 0 | 40 |  |  |  | 24
2025-08-26 | 2279 | sp | L02_A_SOA_012 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 24
2025-08-27 | 2280 |  | L02_A_SOA_013 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 40 | 0 | 160 | A | 0 | 240 |  |  |  | 24
2025-08-27 | 2281 | sp | L02_A_SOA_014 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 150 | 0 |  | 0 | 160 |  |  |  | 24
2025-08-27 | 2282 | sp | L02_A_SOA_015 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 100 | 0 |  | 0 | 100 |  |  |  | 24
2025-08-26 | 2283 | sp | L02_A_SOA_016 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 24
2025-08-27 | 2284 |  | L02_A_SOA_017 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 110 | 0 | 50 | A | 0 | 190 |  |  |  | 24
2025-08-27 | 2285 |  | L02_A_SOA_018 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 90 | 0 | 90 | A | 0 | 220 |  |  |  | 24
2025-08-27 | 2286 | bth | L02_A_SOA_019 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 30 | 20 | 120 | A | 0 | 190 |  |  |  | 24
2025-08-27 | 2287 |  | L02_A_SOA_020 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 80 | 0 | 100 | A | 0 | 210 |  |  |  | 24
2025-08-27 | 2288 |  | L02_A_SOA_021 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 60 | 0 | 70 | A | 0 | 160 |  |  |  | 24
2025-08-27 | 2289 |  | L02_A_SOA_022 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 120 | 20 | 0 |  | 0 | 160 |  |  |  | 24
2025-08-27 | 2290 | sp | L02_A_SOA_023 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 30 | 0 |  | 0 | 30 |  |  |  | 24
2025-08-26 | 2291 | sp | L02_A_SOA_024 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 24
2025-08-28 | 2292 | sp | L02_A_SOA_025 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 40 | 0 |  | 0 | 40 |  |  |  | 24
2025-08-26 | 2293 | sp | L02_A_SOA_026 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 24
2025-08-27 | 2294 | bth | L02_A_SOA_027 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 90 | 20 | 30 | A | 0 | 140 |  |  |  | 24
2025-08-27 | 2295 |  | L02_A_SOA_028 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 70 | 0 | 70 | A | 0 | 190 |  |  |  | 24
2025-08-27 | 2296 | bth | L02_A_SOA_029 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 30 | 110 | A | 0 | 180 |  |  |  | 24
2025-08-28 | 2297 |  | L02_A_SOA_030 | A | DONE | 9 | M |  | WAUNAKEE MS 6230013 | VD | 2025-08-29 | Z | 2025-08-05 | 220 | 0 | 0 |  | 0 | 580 |  |  |  | 24
2025-08-27 | 2298 | sp | L02_A_SOA_031 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-08-29 | Z | 2025-08-05 | 20 | 60 | 0 |  | 0 | 60 |  |  |  | 24
[6 empty] | 1500 | [13 empty] | 48640 |  |  |  | 4800 | 9.868%
WEEK OF 9-1-2025
2025-09-04 | 570 |  | 75236 - 75237 | A | DONE | 3 | S |  | BARTILLION 6240024 |  | 2025-09-09 | Z | 2025-08-25 | 60 | 0 | 0 |  | 0 | 90 |  | SA Mech |  | 15
2025-09-04 | 572 |  | 75241 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2025-09-09 | Z | 2025-08-25 | 40 | 0 | 0 |  | 0 | 60 |  | EA Outs |  | 15
2025-09-04 | 573 |  | 75242 | A | DONE | 5 | S |  | BARTILLION 6240024 | 1" liner | 2025-09-09 | Z | 2025-08-25 | 120 | 0 | 0 |  | 110 | 190 |  | Dorm 4 SA |  | 15
2025-09-04 | 574 |  | 75243 | A | DONE | 12 | S-M |  | BARTILLION 6240024 |  | 2025-09-09 | Z | 2025-08-25 | 200 | 0 | 80 | A | 0 | 560 |  | RA Off AHU 2nd Floor |  | 15
2025-09-05 | 575 |  | 75244 | A | DONE | 5 | S-M |  | BARTILLION 6240024 | VD's , 1" liner | 2025-09-09 | Z | 2025-08-25 | 120 | 0 | 0 |  | 40 | 180 |  | 2nd Mech Room |  | 15
2025-09-04 | 577 |  | 75248 - 75249 | A | DONE | 6 | S |  | BARTILLION 6240024 | paint | 2025-09-09 | Z | 2025-08-25 | 140 | 0 | 0 |  | 100 | 310 |  | EA 1st Mech to Louver |  | 15
2025-09-03 | 579 | sp | 75261 | A | DONE | 8 | S-M |  | BARTILLION 6240024 | 1" DW | 2025-09-03 | Z | 2025-09-03 | 40 | 140 | 0 |  | 40 | 170 |  | Dorm #1 |  | 0
2025-09-03 | 2210 |  | 73916 | A | DONE | 3 | S-M |  | DOC JDC 6240023 |  | 2025-09-04 | Z | 2025-08-18 | 60 | 0 | 0 |  | 0 | 100 |  | MUA on roof |  | 17
2025-09-03 | 2212 |  | 73917 - 73918 | A | DONE | 4 | S-M |  | DOC JDC 6240023 |  | 2025-09-04 | Z | 2025-08-19 | 90 | 0 | 0 |  | 0 | 130 |  | Pitched roof drop |  | 16
2025-09-02 | 2214 | w | 73919 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-09-04 | Z | 2025-08-28 | 40 | 0 | 0 |  | 20 | 70 |  | DC Duct Rail |  | 7
2025-09-02 | 654 |  | Z1-OA 4 | A | DONE | 9 | S-M |  | DOC JDC 6240023 | VD | 2025-09-04 | Z | 2025-07-22 | 120 | 0 | 110 | A | 0 | 270 |  |  |  | 44
2025-09-05 | 1037 | bth | ES SL-EA 6 | A | DONE | 8 | S |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 140 | 20 | 30 | L | 0 | 220 |  |  |  | 15
2025-09-03 | 1300 |  | ES SL-SAT 1891 | delete | DONE | n/a | S |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 29
2025-09-02 | 280 |  | 74048 | A | DONE | 2 | S |  | FAIRFIELD EQ 4250033 | 1"liner | 2025-09-03 | Z | 2025-09-02 | 20 | 0 | 0 |  | 20 | 20 |  | RTU |  | 1
2025-09-02 | 3233 |  | 69993 | A | DONE | 2 | S-M |  | HISTOSONICS 6250009 |  | 2025-09-03 | Z | 2025-08-22 | 30 | 0 | 0 |  | 0 | 40 |  | Drops |  | 12
2025-09-04 | 3234 | bth | 77264-65 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-09-08 | Z | 2025-08-28 | 40 | 0 | 0 |  | 0 | 70 |  | Misc |  | 11
2025-09-05 | 2081 |  | EA-L2F-01 | A | DONE | 18 | M |  | MONROE HS 6240018 | 1" liner | 2025-09-10 | Z | 2025-06-18 | 330 | 0 | 100 | A | 380 | 790 |  |  |  | 84 | 2025-08-12
2025-09-05 | 2082 |  | EA-L2F-02 | A | DONE | 9 | S |  | MONROE HS 6240018 |  | 2025-09-10 | Z | 2025-06-18 | 220 | 0 | 0 |  | 0 | 350 |  |  |  | 84 | 2025-08-12
2025-09-05 | 2083 |  | EA-L2F-03 | A | DONE | 13 | S-M |  | MONROE HS 6240018 | CD , 1" liner | 2025-09-10 | Z | 2025-06-18 | 230 | 0 | 80 | A | 210 | 440 |  |  |  | 84 | 2025-08-12
2025-09-05 | 2084 |  | EA-L2F-04 | A | DONE | 14 | S-M |  | MONROE HS 6240018 | CD , 1" liner | 2025-09-10 | Z | 2025-06-18 | 260 | 0 | 80 | A | 190 | 410 |  |  |  | 84 | 2025-08-12
2025-09-05 | 2085 |  | OA-L2F-01 | A | DONE | 2 | S |  | MONROE HS 6240018 | CD | 2025-09-10 | Z | 2025-06-18 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 84 | 2025-08-12
2025-09-05 | 2086 |  | OA-L2F-02 | A | DONE | 4 | S |  | MONROE HS 6240018 | CD | 2025-09-10 | Z | 2025-06-18 | 80 | 0 | 0 |  | 0 | 100 |  |  |  | 84 | 2025-08-12
2025-09-05 | 2087 |  | OA-L2F-03 | A | DONE | 14 | M |  | MONROE HS 6240018 | CD | 2025-09-10 | Z | 2025-06-18 | 200 | 0 | 150 | A | 0 | 590 |  |  |  | 84 | 2025-08-12
2025-09-02 | 2091 |  | SALP-L2F-01 | A | DONE | 51 | M-L |  | MONROE HS 6240018 | 2" liner | 2025-09-03 | Z | 2025-06-18 | 510 | 0 | 160 | A | 600 | 1290 |  |  |  | 77 | 2025-08-12
2025-09-02 | 2092 |  | SALP-L2F-02 | A | DONE | 34 | M-L |  | MONROE HS 6240018 | 2" liner | 2025-09-03 | Z | 2025-06-18 | 590 | 0 | 240 | A | 640 | 1210 |  |  |  | 77 | 2025-08-12
2025-09-05 | 3013 | sp | SALP-L2E-14 | A | DONE | 154 | L | neal | MONROE HS 6240018 | 2" DW, s.mates | 2025-09-09 | Z | 2025-07-01 | 300 | 3540 | 0 |  | 850 | 4330 |  |  |  | 70 | 2025-08-12 | 2025-08-19
2025-09-03 | 3014 | sp | SALP-L2E-15 | A | DONE | 102 | L | neal | MONROE HS 6240018 | 2" DW, s.mates | 2025-09-09 | Z | 2025-07-01 | 760 | 1790 | 0 |  | 730 | 3380 |  |  |  | 70 | 2025-08-12 | 2025-08-19
2025-09-03 | 3015 | sp | SALP-L2E-16 | A | DONE | 148 | L | neal | MONROE HS 6240018 | 2" DW, s.mates | 2025-09-09 | Z | 2025-07-01 | 810 | 2870 | 0 |  | 1160 | 3840 |  |  |  | 70 | 2025-08-12 | 2025-08-19
2025-09-04 | 3020 | sp | SALP-L2E-10 | A | DONE | 4 | S | neal | MONROE HS 6240018 |  | 2025-09-09 | Z | 2025-07-23 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 48 | 2025-08-12 | 2025-08-19
2025-09-04 | 3021 | sp | SALP-L2E-11 | A | DONE | 4 | S | neal | MONROE HS 6240018 |  | 2025-09-09 | Z | 2025-07-23 | 20 | 80 | 0 |  | 0 | 100 |  |  |  | 48 | 2025-08-12 | 2025-08-19
2025-09-04 | 3037 | bth | 85341 | A | DONE | 9 | S |  | MONROE HS 6240018 |  | 2025-09-05 | Z | 2025-09-03 | 80 | 50 | 90 | A | 0 | 250 |  | Mock up |  | 2
2025-09-04 | 3264 |  | 79531 - 79532 | A | DONE | 5 | S-M |  | ONE 09 6240037 | paint | 2025-09-08 | Z | 2025-09-03 | 110 | 0 | 0 |  | 0 | 200 |  | Wine cooler / PCU |  | 5
2025-09-03 | 3263 |  | 79523,28-30 | A | DONE | 11 | S-M |  | ONE-09 WILSON 6240037 |  | 2025-09-04 | Z | 2025-09-02 | 270 | 0 | 0 |  | 0 | 390 |  | MISC |  | 2
2025-09-02 | 818 |  | 76806 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-28 | 20 | 0 | 0 |  | 0 | 20 |  | HANGERS |  | 6
2025-09-05 | 819 |  | 76736-37 | A | DONE | 6 | M | neal | PEWAUKEE HS 6240030 |  | 2025-09-10 | Z | 2025-08-28 | 150 | 0 | 0 |  | 0 | 230 |  | PANS & TEE |  | 13
2025-09-05 | 825 |  | 76808 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-09-10 | Z | 2025-09-05 | 20 | 0 | 0 |  | 0 | 20 |  | Fire Damper tie in |  | 5
2025-09-03 | 1352 |  | L02_AREA_300_RAMP_001 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 220 | 0 | 50 | F | 0 | 490 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1353 | sp | L02_AREA_300_RAMP_002 | A | DONE | 18 | S-M |  | PROJECT DOVE 6240041 | VD , spiral mates | 2025-09-04 | Z | 2025-06-10 | 40 | 390 | 0 |  | 0 | 610 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1354 | sp | L02_AREA_300_RAMP_003 | F | DONE | 11 | S-M |  | PROJECT DOVE 6240041 | spiral mates | 2025-09-04 | Z | 2025-06-10 | 110 | 160 | 0 |  | 0 | 360 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1355 | sp | L02_AREA_300_RAMP_004 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 20 | 60 | 0 |  | 0 | 60 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1356 | sp | L02_AREA_300_RAMP_005 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 20 | 160 | 0 |  | 0 | 190 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1357 | sp | L02_AREA_300_RAMP_006 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 20 | 100 | 0 |  | 0 | 90 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1358 | sp | L02_AREA_300_RAMP_007 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1359 | sp | L02_AREA_300_RAMP_008 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 20 | 90 | 0 |  | 0 | 90 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1360 | sp | L02_AREA_300_RAMP_009 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 20 | 100 | 0 |  | 0 | 100 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1361 | bth | L02_AREA_300_SALP_001 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 40 | 60 | 0 |  | 0 | 110 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1362 |  | L02_AREA_300_SALP_002 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1363 | bth | L02_AREA_300_SALP_003 | A | DONE | 9 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 60 | 70 | 80 | A | 0 | 230 |  |  |  | 86 | 2025-06-19
2025-09-02 | 1364 | bth | L02_AREA_300_SAMP_001 | A | DONE | 7 | S-M |  | PROJECT DOVE 6240041 | 321 | 2025-09-04 | Z | 2025-06-10 | 120 | 20 | 120 | A | 0 | 380 |  |  |  | 86 | 2025-06-19
2025-09-05 | 1610 |  | 76263 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-09-05 | 130 | 0 | 0 |  | 0 | 160 |  | EC |  | 6
2025-09-02 | 4552 |  | L02_AREA_300_RAMP_010 | A | DONE | 25 | M-L | ss | PROJECT DOVE 6240041 | 321 , VD's | 2025-09-04 | Z | 2025-07-01 | 620 | 0 | 0 |  | 0 | 1510 |  |  |  | 65
2025-09-03 | 4553 |  | L02_AREA_300_RAMP_011 | A | DONE | 23 | M-L | ss | PROJECT DOVE 6240041 | 321 , VD | 2025-09-04 | Z | 2025-07-01 | 560 | 0 | 0 |  | 0 | 1590 |  |  |  | 65
2025-09-03 | 4727 | w | L01_AREA_052_EA_013 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 |  | 2025-09-04 | Z | 2025-08-26 | 20 | 80 | 0 |  | 0 | 80 |  |  |  | 9
2025-09-03 | 4820 | w | L02_AREA_052_EA_007 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-09-04 | Z | 2025-08-26 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 9
2025-09-02 | 4839 |  | L02_AREA_052_TA_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-09-04 | Z | 2025-08-19 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 16
2025-09-02 | 4840 |  | L02_AREA_052_TA_002 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-09-04 | Z | 2025-08-19 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 16
2025-09-02 | 4841 |  | L02_AREA_052_TA_003 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-09-04 | Z | 2025-08-19 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 16
2025-09-02 | 4842 |  | L02_AREA_052_TA_004 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-09-04 | Z | 2025-08-19 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 16
2025-09-03 | 4843 |  | L02_AREA_052_TA_005 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-09-04 | Z | 2025-08-19 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 16
2025-09-03 | 4844 |  | L02_AREA_052_TA_006 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-09-04 | Z | 2025-08-19 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 16
2025-09-03 | 4845 |  | L02_AREA_052_TA_007 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-09-04 | Z | 2025-08-19 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 16
2025-09-02 | 4846 |  | L02_AREA_052_TA_008 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" liner | 2025-09-04 | Z | 2025-08-19 | 20 | 0 | 0 |  | 20 | 40 |  | RE-11 |  | 16
2025-09-02 | 4849 | w | L02_AREA_200_RAMP_002 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 |  | 2025-09-04 | Z | 2025-08-20 | 100 | 0 | 0 |  | 0 | 260 |  |  |  | 15
2025-09-02 | 4851 |  | 76255 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-04 | Z | 2025-08-20 | 50 | 0 | 0 |  | 0 | 170 |  | Welding Bands |  | 15
2025-09-03 | 4853 |  | 76221 | A | DONE | 6 | S-M |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 140 | 0 | 0 |  | 0 | 320 |  | Misc |  | 14
2025-09-03 | 4855 |  | L02_AREA_052_MA_001 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 100 | 20 | 0 |  | 0 | 220 |  |  |  | 14
2025-09-03 | 4856 |  | L02_AREA_052_SALP_001 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 80 | 0 | 30 | A | 0 | 140 |  |  |  | 14
2025-09-03 | 4857 | bth | L02_AREA_052_SALP_002 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 30 | 50 | 0 |  | 0 | 90 |  |  |  | 14
2025-09-03 | 4858 |  | L02_AREA_052_SALP_003 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 120 | 0 | 30 | A | 0 | 190 |  |  |  | 14
2025-09-03 | 4859 |  | L02_AREA_052_SALP_004 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 14
2025-09-04 | 4860 | sp | L02_AREA_052_SALP_005 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 20 | 50 | 0 |  | 0 | 50 |  |  |  | 14
2025-09-04 | 4861 | bth | L02_AREA_052_SALP_006 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 14
2025-09-04 | 4862 | sp | L02_AREA_052_SALP_007 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 20 | 70 | 0 |  | 0 | 70 |  |  |  | 14
2025-09-04 | 4863 | bth | L02_AREA_052_SALP_008 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 130 | 50 | 0 |  | 0 | 240 |  |  |  | 14
2025-09-04 | 4864 | sp | L02_AREA_052_SALP_009 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 14
2025-09-04 | 4865 | sp | L02_AREA_052_SALP_010 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 14
2025-09-03 | 4866 | bth | L02_AREA_052_SALP_011 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 50 | 20 | 100 | A | 0 | 200 |  |  |  | 14
2025-09-03 | 4867 | bth | L02_AREA_052_SALP_012 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-22 | 40 | 90 | 0 |  | 0 | 140 |  |  |  | 14
2025-09-03 | 4868 |  | L02_AREA_052_SALP_013 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD | 2025-09-05 | Z | 2025-08-22 | 70 | 0 | 70 | A | 0 | 190 |  |  |  | 14
2025-09-04 | 4869 | sp | L02_AREA_052_SALP_014 | A | DONE | 10 | S-M |  | PROJECT DOVE 6240041 | VD's | 2025-09-05 | Z | 2025-08-22 | 50 | 180 | 0 |  | 0 | 290 |  |  |  | 14
2025-09-03 | 4870 | sp | L02_AREA_052_SALP_015 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 | VD's | 2025-09-05 | Z | 2025-08-22 | 30 | 150 | 0 |  | 0 | 210 |  |  |  | 14
2025-09-03 | 4871 |  | 76256 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-25 | 20 | 0 | 0 |  | 0 | 20 |  | L01_AREA_052_RA_002 |  | 11
2025-09-03 | 4872 |  | 76257 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-09-04 | Z | 2025-08-26 | 60 | 0 | 0 |  | 0 | 150 |  | L02_052_SAMP_05 |  | 9
2025-09-04 | 4874 |  | 76260 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-08-27 | 50 | 0 | 0 |  | 0 | 80 |  | L02-52-SAMP03 |  | 9
2025-09-02 | 4892 |  | 80350 | A | DONE | 7 | S | neal | PROJECT DOVE 6240041 |  | 2025-09-04 | Z | 2025-08-28 | 70 | 0 | 120 | A | 0 | 230 |  | EF-48 |  | 7
2025-09-03 | 4893 | sp | 76169,76353 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-09-02 | 20 | 0 | 0 |  | 0 | 20 |  | OUTS |  | 3
2025-09-03 | 4894 |  | 76355 | A | DONE | 4 | S | neal | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-09-02 | 80 | 0 | 0 |  | 0 | 110 |  | ANGLES |  | 3
2025-09-05 | 4895 |  | 76356 | A | DONE | 8 | S | neal | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-09-02 | 180 | 0 | 0 |  | 0 | 250 |  | ANGLES |  | 9
2025-09-03 | 4897 | sp | 76357 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-09-02 | 20 | 0 | 0 |  | 0 | 20 |  | VAV 0413-14 |  | 3
2025-09-03 | 4898 |  | 84296 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-05 | Z | 2025-09-03 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeve |  | 2
2025-09-02 | 3049 |  | 81862 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 | flex | 2025-09-02 | Z | 2025-08-29 | 0 | 0 | 10 | A | 0 | 10 |  | 1-Flex only |  | 4
2025-09-03 | 3697 | sp | 68921 | A | DONE | 10 | S-M |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 40 | 190 | 0 |  | 0 | 230 |  | Blue Phase - East |  | 39
2025-09-04 | 3698 |  | 68922 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 50 | 0 | 0 |  | 0 | 70 |  | Blue Phase - East |  | 39
2025-09-04 | 3699 | sp | 68923 - 68924 | A | DONE | 13 | S-M |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 30 | 290 | 0 |  | 0 | 300 |  | Blue Phase - Ex East |  | 39
2025-09-03 | 850 | sp | 68925 | A | DONE | 6 | S-M |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 30 | 120 | 0 |  | 0 | 140 |  | Blue Phase - Center |  | 39
2025-09-04 | 851 |  | 68926 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 20 | 0 | 0 |  | 0 | 30 |  | Blue Phase - Center |  | 39
2025-09-04 | 852 |  | 68927 - 68929 | A | DONE | 11 | S-M |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 50 | 220 | 0 |  | 0 | 250 |  | Blue Phase - Left |  | 39
2025-09-04 | 853 |  | 68930 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 30 | 0 | 0 |  | 0 | 50 |  | Blue Phase - VAV 4-52 |  | 39
2025-09-03 | 854 | sp | 68931 - 68932 | A | DONE | 6 | S-M |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 20 | 120 | 0 |  | 0 | 120 |  | Blue Phase - VAV 4-52 |  | 39
2025-09-03 | 855 | sp | 68933 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 20 | 80 | 0 |  | 0 | 90 |  | Blue Phase - VAV 4-51 |  | 39
2025-09-04 | 856 |  | 68934 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 30 | 0 | 0 |  | 0 | 40 |  | Blue Phase - VAV 4-51 |  | 39
2025-09-03 | 857 | sp | 68935 | A | DONE | 7 | S-M |  | SPH SURGERY 6240039 |  | 2025-09-08 | Z | 2025-07-31 | 20 | 140 | 0 |  | 0 | 160 |  | Blue Phase - EA |  | 39
2025-09-03 | 530 |  | 75543 | A | DONE | 2 | S |  | SW HEALTH OR5 6250004 |  | 2025-09-08 | Z | 2025-09-02 | 20 | 0 | 0 |  | 0 | 20 |  | TEMP CAP |  | 6
2025-09-04 | 4656 |  | 82228 - 82229 | A | DONE | 6 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-08-04 | 130 | 0 | 0 |  | 0 | 220 |  | RTU SA / RA drops |  | 42
2025-09-02 | 3093 |  | 54532 | A | DONE | 2 | S | ss | UW VET MED 2250030 |  | 2025-09-05 | Z | 2025-09-02 | 20 | 0 | 0 |  | 0 | 20 |  | ANGLES |  | 3
2025-09-03 | 3109 | w | 69058 | A | DONE | 2 | S | ss | UW-AVRL 6240038 |  | 2025-09-05 | Z | 2025-08-29 | 20 | 0 | 0 |  | 0 | 30 |  | 5TH FL |  | 7
2025-09-05 | 3110 |  | 69059 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-09-08 | Z | 2025-09-05 | 20 | 0 | 0 |  | 0 | 30 |  | Mock up cap |  | 3
2025-09-02 | 1400 | bth | L5-SAT 3-5-37 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 40 | 30 | 40 | A | 40 | 140 |  |  |  | 21
2025-09-02 | 1401 | bth | L5-SAT 3-5-38 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-09-02 | Z | 2025-08-12 | 30 | 20 | 0 |  | 20 | 50 |  |  |  | 21
2025-09-02 | 1402 | bth | L5-SAT 3-5-39 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-09-02 | Z | 2025-08-12 | 80 | 20 | 40 | A | 30 | 180 |  |  |  | 21
2025-09-02 | 1403 | bth | L5-SAT 3-5-40 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 60 | 20 | 0 |  | 30 | 90 |  |  |  | 21
2025-09-02 | 1404 | bth | L5-SAT 3-5-41 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 60 | 10 | 40 | A | 30 | 150 |  |  |  | 21
2025-09-02 | 1405 |  | L5-TA 6 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-09-02 | Z | 2025-08-12 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 21
2025-09-02 | 1406 |  | L5-FCU 6 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VD , flex | 2025-09-02 | Z | 2025-08-12 | 110 | 0 | 30 | A | 0 | 190 |  |  |  | 21
2025-09-04 | 1415 |  | 83838 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-09-09 | Z | 2025-08-25 | 20 | 0 | 0 |  | 20 | 20 |  | LP SA |  | 15
2025-09-04 | 1419 |  | LL-GEN. EA 1 | A | DONE | 30 | M-L |  | UW-LEVY HALL 6230028 | MOD | 2025-09-09 | Z | 2025-08-26 | 730 | 0 | 0 |  | 0 | 2000 |  |  |  | 14
2025-09-05 | 1420 |  | LL-GEN. SA 1 | A | DONE | 6 | S-M |  | UW-LEVY HALL 6230028 | MOD | 2025-09-09 | Z | 2025-08-26 | 130 | 0 | 0 |  | 0 | 520 |  |  |  | 14
2025-09-04 | 1421 |  | 83840 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-09-09 | Z | 2025-08-26 | 40 | 0 | 0 |  | 30 | 80 |  | L2 EL SHAFT SAMP 1 |  | 14
2025-09-05 | 1422 |  | 83842 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-09-09 | Z | 2025-08-27 | 20 | 0 | 0 |  | 0 | 40 |  | EL-SHAFT RAMP3-L3 |  | 13
2025-09-02 | 2181 |  | MER-SAMP 3 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-09-02 | Z | 2025-08-12 | 70 | 0 | 140 | A | 0 | 500 |  |  |  | 21
2025-09-02 | 2182 | bth | L5-SAT 3-5-1 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 90 | 10 | 60 | A | 30 | 200 |  |  |  | 21
2025-09-02 | 2186 |  | L5-SAT 3-5-5 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 80 | 0 | 20 | A | 30 | 120 |  |  |  | 21
2025-09-02 | 2190 | bth | L5-SAT 3-5-9 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 90 | 30 | 20 | A | 30 | 170 |  |  |  | 21
2025-09-02 | 2193 | bth | L5-SAT 3-5-30 | A | DONE | 11 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 90 | 30 | 80 | A | 60 | 230 |  |  |  | 21
2025-09-02 | 2197 | bth | L5-SAT 3-5-34 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 40 | 20 | 0 |  | 30 | 70 |  |  |  | 21
2025-09-02 | 2198 | bth | L5-SAT 3-5-35 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 60 | 10 | 20 | A | 30 | 120 |  |  |  | 21
2025-09-02 | 2199 | bth | L5-SAT 3-5-36 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VAV , 1" liner | 2025-09-02 | Z | 2025-08-12 | 90 | 20 | 20 | A | 30 | 150 |  |  |  | 21
2025-09-05 | 3884 |  | 58174 | A | DONE | 2 | S |  | UW-WITTE HALL 6250003 |  | 2025-09-08 | Z | 2025-09-05 | 20 | 0 | 0 |  | 0 | 20 |  | Roof |  | 3
2025-09-03 | 1508 |  | 79894 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-05 | Z | 2025-08-18 | 60 | 0 | 0 |  | 0 | 120 |  | MAU-3 |  | 18
2025-09-03 | 1511 |  | 83380 - 83382 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-05 | Z | 2025-08-26 | 120 | 0 | 0 |  | 0 | 190 |  | 1st Floor tie ins |  | 10
2025-09-03 | 1512 |  | 83384 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 | paint | 2025-09-05 | Z | 2025-08-26 | 210 | 0 | 0 |  | 220 | 300 |  | 1st Floor tie ins |  | 10
2025-09-03 | 1513 |  | 83407 - 83409 | A | DONE | 27 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-05 | Z | 2025-08-26 | 660 | 0 | 0 |  | 0 | 1560 |  | DOAS / PH tie ins |  | 10
2025-09-05 | 1516 | bth | 79896 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | 1"liner | 2025-09-12 | Z | 2025-08-28 | 110 | 50 | 0 |  | 60 | 180 |  | HEAT PUMP |  | 15
2025-09-03 | 1517 |  | 82911-12 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-05 | Z | 2025-08-29 | 110 | 0 | 0 |  | 0 | 190 |  | L02-Outs |  | 7
2025-09-05 | 1518 |  | 83386 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-08-29 | 50 | 0 | 0 |  | 0 | 70 |  | Flashing |  | 14
2025-09-04 | 1522 |  | 83387 - 83388 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-09-05 | Z | 2025-09-03 | 20 | 0 | 0 |  | 0 | 90 |  | Wresting room / Hangers |  | 2
WEEK OF 9-8-2025
2025-09-08 | 571 | bth | 75238 - 75240 | A | DONE | 12 | S-M |  | BARTILLION 6240024 | 1" spiral , 1" liner | 2025-09-09 | Z | 2025-08-25 | 150 | 150 | 0 |  | 100 | 350 |  | AV 2-5 LP |  | 15
2025-09-08 | 576 |  | 75245 - 75247 | A | DONE | 8 | S |  | BARTILLION 6240024 | paint | 2025-09-09 | Z | 2025-08-25 | 180 | 0 | 0 |  | 80 | 390 |  | OA / EA Louver 2nd Mech |  | 15
2025-09-08 | 578 | w | 75253 | A | DONE | 2 | S | ss | BARTILLION 6240024 |  | 2025-09-09 | Z | 2025-08-28 | 20 | 0 | 0 |  | 0 | 40 |  | DISHWASHER |  | 12
2025-09-10 | 580 |  | 75250 | A | DONE | 8 | S-M |  | BARTILLION 6240024 | paint | 2025-09-16 | Z | 2025-09-03 | 180 | 0 | 0 |  | 0 | 220 |  | 2nd RA A-Section |  | 13
2025-09-10 | 581 | bth | 75254 | A | DONE | 2 | S |  | BARTILLION 6240024 | 1" liner | 2025-09-16 | Z | 2025-09-03 | 20 | 20 | 0 |  | 20 | 40 |  | AU |  | 13
2025-09-11 | 582 | bth | 75255 - 75257 | A | DONE | 9 | S-M |  | BARTILLION 6240024 |  | 2025-09-16 | Z | 2025-09-03 | 130 | 30 | 60 | A | 0 | 260 |  | AU |  | 13
2025-09-10 | 583 | bth | 75258 - 75260 | A | DONE | 20 | S-M |  | BARTILLION 6240024 | paint , 1" liner | 2025-09-16 | Z | 2025-09-03 | 370 | 40 | 80 | A | 230 | 610 |  | 2nd TA |  | 13
2025-09-09 | 3537 |  | 73867 | A | DONE | 6 | S |  | DELLSHIRE 6240017 |  | 2025-09-15 | Z | 2025-08-27 | 140 | 0 | 0 |  | 0 | 160 |  | EF-6-1ST FL |  | 19
2025-09-11 | 3540 |  | 73790 | A | DONE | 3 | S-M | neal | DELLSHIRE 6240017 |  | 2025-09-15 | Z | 2025-08-28 | 70 | 0 | 0 |  | 0 | 90 |  | 2ND FL HANGERS |  | 18
2025-09-09 | 3541 |  | 73791 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-09-15 | Z | 2025-08-28 | 50 | 0 | 0 |  | 0 | 50 |  | MISC |  | 18
2025-09-09 | 3542 | bth | 73807 - 73808 | A | DONE | 20 | S-M |  | DELLSHIRE 6240017 | paint | 2025-09-15 | Z | 2025-09-04 | 390 | 90 | 0 |  | 0 | 610 |  | Misc outs |  | 11
2025-09-08 | 1022 | bth | ES SL-EA 1 | A | DONE | 31 | M |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 390 | 40 | 330 | A | 0 | 1060 |  |  |  | 15
2025-09-08 | 1023 | bth | ES SL-EA 5 | A | DONE | 15 | S-M |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 190 | 60 | 120 | A | 0 | 430 |  |  |  | 15
2025-09-08 | 1034 | bth | ES SL-EA 3 | A | DONE | 8 | S |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 140 | 20 | 30 | A | 0 | 210 |  |  |  | 15
2025-09-08 | 1035 | bth | ES SL-EA 4 | A | DONE | 5 | S |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 60 | 20 | 30 | A | 0 | 110 |  |  |  | 15
2025-09-08 | 1038 | bth | ES SL-EA 7 | A | DONE | 5 | S |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 50 | 20 | 50 | A | 0 | 130 |  |  |  | 15
2025-09-08 | 1039 | bth | ES SL-EA 8 | A | DONE | 8 | S |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 120 | 30 | 30 | A | 0 | 180 |  |  |  | 15
2025-09-08 | 1041 | sp | ES SL-EAT 1889 | A | DONE | 2 | S |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 15
2025-09-08 | 1301 |  | ES SL--SAT 1893 | A | DONE | 16 | S-M |  | ES SEQUENCING 2250029 |  | 2025-09-10 | Z | 2025-08-26 | 300 | 0 | 100 | A | 0 | 460 |  |  |  | 15
2025-09-08 | 1302 | sp | 56830 | A | DONE | 2 | S |  | EXACT GSO 2250026 |  | 2025-09-10 | Z | 2025-08-26 | 20 | 30 | 0 |  | 0 | 60 |  | SA Spiral |  | 15
2025-09-08 | 1305 |  | 56834 | A | DONE | 2 | S |  | EXACT SEQ 2250029 |  | 2025-09-10 | Z | 2025-08-28 | 20 | 0 | 0 |  | 0 | 30 |  | WALL SLEEVES |  | 13
2025-09-11 | 3235 |  | CALL IN | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-09-11 | Z | 2025-09-11 | 20 | 0 | 0 |  | 0 | 20 |  | RD EC'S |  | 0
| 1465 |  | TA-L1E-01 | Delete |  |  | S |  | MONROE HS 6240018 | 1" liner | 2025-09-30 | Z | 2025-09-09 | [9 empty] | 21
| 1466 |  | TA-L1E-02 | Delete |  |  | S-M |  | MONROE HS 6240018 |  | 2025-09-30 | Z | 2025-09-09 | [9 empty] | 21
| 1478 |  | RA-L1E-06 | Delete |  |  | M-L |  | MONROE HS 6240018 | 1" liner | 2025-09-30 | Z | 2025-09-09 | [9 empty] | 21
2025-09-08 | 3011 | sp | SALP-L2E-12 | A | DONE | 25 | M | neal | MONROE HS 6240018 | 2" DW, s.mates | 2025-09-09 | Z | 2025-07-01 | 190 | 1580 | 0 |  | 410 | 1600 |  |  |  | 70 | 2025-08-12 | 2025-08-19
2025-09-08 | 3012 | sp | SALP-L2E-13 | A | DONE | 154 | L | neal | MONROE HS 6240018 | 2" DW, s.mates | 2025-09-09 | Z | 2025-07-01 | 290 | 3550 | 0 |  | 850 | 4340 |  |  |  | 70 | 2025-08-12 | 2025-08-19
2025-09-08 | 3036 |  | 85340 | A | DONE | 3 | S | neal | MONROE HS 6240018 | spiral mate | 2025-09-10 | Z | 2025-08-26 | 40 | 30 | 0 |  | 0 | 70 |  | L1F |  | 15
2025-09-08 | 3038 |  | 84297 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-09-08 | Z | 2025-09-08 | 20 | 0 | 0 |  | 0 | 20 |  | Rock Co. |  | 0
2025-09-08 | 281 |  | 70250 | A | DONE | 2 | S |  | OAKWOOD 10064379 |  | 2025-09-11 | Z | 2025-09-08 | 20 | 0 | 0 |  | 0 | 20 |  | AC 6 |  | 3
2025-09-08 | 3265 | w | 79533 | A | DONE | 2 | S | BI | ONE 09 6240037 |  | 2025-09-08 | Z | 2025-09-03 | 40 | 0 | 0 |  | 0 | 130 |  | PCU BI |  | 5
2025-09-09 | 808 | sp | L1B-DC 1 | A | DONE | 4 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 40 | 50 | 0 |  | 0 | 280 |  |  |  | 14
2025-09-09 | 809 | sp | L1B-DC 2 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 10 | 60 | 0 |  | 0 | 150 |  |  |  | 14
2025-09-09 | 810 | sp | L1B-DC 3 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 20 | 50 | 0 |  | 0 | 180 |  |  |  | 14
2025-09-10 | 811 | sp | L1B-DC 4 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 20 | 50 | 0 |  | 0 | 110 |  |  |  | 14
2025-09-10 | 812 | sp | L1B-DC 5 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 10 | 30 | 0 |  | 0 | 260 |  |  |  | 14
2025-09-09 | 813 | sp | L1B-DC 6 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 20 | 60 | 0 |  | 0 | 180 |  |  |  | 14
2025-09-10 | 814 | sp | L1B-DC 7 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 10 | 70 | 0 |  | 0 | 120 |  |  |  | 14
2025-09-09 | 815 | sp | L1B-DC 8 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 10 | 60 | 0 |  | 0 | 100 |  |  |  | 14
2025-09-10 | 816 | sp | L1B-DC 9 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-09-03 | Z | 2025-08-20 | 10 | 60 | 0 |  | 0 | 90 |  |  |  | 14
2025-09-11 | 820 |  | 76728 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-09-16 | Z | 2025-08-29 | 40 | 0 | 0 |  | 0 | 110 |  | Dust Collection |  | 18
2025-09-10 | 821 |  | 76738 | A | DONE | 3 | S |  | PEWAUKEE HS 6240030 |  | 2025-09-16 | Z | 2025-09-02 | 60 | 0 | 0 |  | 0 | 150 |  | EXISTING LOUVER |  | 14
2025-09-09 | 823 |  | 76807 | A | DONE | 6 | S-M | neal | PEWAUKEE HS 6240030 |  | 2025-09-16 | Z | 2025-09-05 | 150 | 0 | 0 |  | 0 | 200 |  | DC Hangers |  | 11
2025-09-09 | 829 |  | 76767 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-09-16 | Z | 2025-09-08 | 40 | 0 | 0 |  | 0 | 50 |  | Booster coil |  | 8
2025-09-09 | 1300 |  | L01_NC_TA_001 | A | DONE |  | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-15 | 60 | 0 | 0 |  | 50 | 90 |  |  |  | 119
2025-09-09 | 1308 | bth | L01_NC_SALP_001 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 150 | 110 | 0 |  | 0 | 300 |  |  |  | 115 | 2025-06-26
2025-09-09 | 1309 | sp | L01_NC_SALP_002 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 115 | 2025-06-26
2025-09-12 | 1310 | sp | L01_NC_SALP_003 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 20 | 60 | 0 |  | 0 | 70 |  |  |  | 115 | 2025-06-26
2025-09-12 | 1311 | sp | L01_NC_SALP_004 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 20 | 60 | 0 |  | 0 | 60 |  |  |  | 115 | 2025-06-26
2025-09-08 | 1312 |  | L01_NC_MA_001 | A | DONE | 17 | M |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 90 | 0 | 320 | A | 0 | 680 |  |  |  | 115 | 2025-06-26
2025-09-08 | 1313 |  | L01_NC_MA_002 | A | DONE | 21 | M-L |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 0 | 0 | 510 | A | 0 | 870 |  |  |  | 115 | 2025-06-26
2025-09-08 | 1314 |  | L01_NC_MA_003 | A | DONE | 15 | M |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 50 | 0 | 320 | A | 0 | 690 |  |  |  | 115 | 2025-06-26
2025-09-08 | 1315 | sp | L01_NC_EA_001 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 40 | 130 | 0 |  | 0 | 160 |  |  |  | 115 | 2025-06-26
2025-09-09 | 1316 | bth | L01_NC_EA_002 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-05-19 | 60 | 30 | 60 | A | 0 | 150 |  |  |  | 115 | 2025-06-26
2025-09-08 | 1331 |  | L01_AREA_300_MA_001 | A | DONE | 6 | S | ss | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 90 | 0 | 50 | A | 0 | 200 |  |  |  | 100 | 2025-06-26
2025-09-08 | 1332 |  | L01_AREA_300_MA_002 | A | DONE | 12 | S-M | ss | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 250 | 0 | 50 | A | 0 | 410 |  |  |  | 100 | 2025-06-26
2025-09-12 | 1333 | bth | L01_AREA_300_MA_004 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 70 | 0 | 0 |  | 0 | 140 |  |  |  | 100 | 2025-06-26
2025-09-09 | 1334 | sp | L01_AREA_300_RA_001 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 20 | 50 | 0 |  | 0 | 40 |  |  |  | 100 | 2025-06-26
2025-09-09 | 1335 | sp | L01_AREA_300_RA_002 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 0 | 50 | 0 |  | 0 | 50 |  |  |  | 100 | 2025-06-26
2025-09-08 | 1336 |  | L01_AREA_300_SALP_001 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 30 | 0 | 80 | A | 0 | 130 |  |  |  | 100 | 2025-06-26
2025-09-09 | 1337 | sp | L01_AREA_300_SALP_002 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 0 | 40 | 0 |  | 0 | 30 |  |  |  | 100 | 2025-06-26
2025-09-09 | 1338 | sp | L01_AREA_300_SALP_003 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 100 | 2025-06-26
2025-09-09 | 1339 | sp | L01_AREA_300_SALP_004 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 100 | 2025-06-26
2025-09-08 | 1340 |  | L01_AREA_300_SALP_005 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 80 | 0 | 0 |  | 0 | 90 |  |  |  | 100 | 2025-06-26
2025-09-08 | 1341 |  | L01_AREA_300_SALP_006 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 30 | 0 | 20 | A | 0 | 60 |  |  |  | 100 | 2025-06-26
2025-09-12 | 1342 | sp | L01_AREA_300_SALP_007 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 100 | 2025-06-26
2025-09-12 | 1343 | sp | L01_AREA_300_SALP_008 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 100 | 2025-06-26
2025-09-08 | 1344 |  | L01_AREA_300_SAMP_001 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 30 | 0 | 70 | A | 0 | 110 |  |  |  | 100 | 2025-06-26
2025-09-12 | 1345 | sp | L01_AREA_300_SAMP_002 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 100 | 2025-06-26
2025-09-09 | 1346 | sp | L01_AREA_300_SAMP_003 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 321 | 2025-09-11 | Z | 2025-06-03 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 100 | 2025-06-26
2025-09-09 | 1600 | sp | 76261 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-09-04 | 50 | 30 | 0 |  | 0 | 110 |  | MAU 13 SA S. |  | 8
2025-09-12 | 1602 | w | L02_AREA_200_RAMP_003 | A | DONE | 3 | S | ss | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-09-04 | 60 | 0 | 0 |  | 0 | 190 |  |  |  | 8
2025-09-09 | 1611 |  | 76264 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-09-08 | 20 | 0 | 0 |  | 0 | 50 |  | LO2-052-SAMP-3 |  | 3
2025-09-08 | 1612 |  | 73659 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-09-08 | 100 | 0 | 0 |  | 0 | 140 |  | Flat stock |  | 3
2025-09-13 | 4823 |  | L02_AREA_052_RAMP_002 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-12 | 100 | 0 | 0 |  | 0 | 120 |  |  |  | 31
2025-09-08 | 4875 |  | MAU-01-MA-001 | A | DONE | 4 | M |  | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-08-27 | 100 | 0 | 0 |  | 0 | 220 |  |  |  | 15
2025-09-08 | 4876 |  | MAU-01-RAMP-001 | A | DONE | 5 | M |  | PROJECT DOVE 6240041 |  | 2025-09-11 | Z | 2025-08-27 | 120 | 0 | 0 |  | 0 | 200 |  |  |  | 15
2025-09-13 | 4879 | bth | L02-AREA 052-SALP-18 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 50 | 0 | 30 | A | 0 | 90 |  |  |  | 16
2025-09-11 | 4658 |  | EXP-RA-01 | A | DONE | 10 | S-M |  | TOMAH HEALTH 6250006 | bird s. | 2025-09-15 | Z | 2025-09-08 | 230 | 0 | 0 |  | 0 | 310 |  |  |  | 7
2025-09-11 | 4659 | bth | EXP-RA-02 | A | DONE | 11 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 120 | 30 | 110 | A | 0 | 310 |  |  |  | 7
2025-09-10 | 4660 |  | EXP-RA-03 | A | DONE | 18 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 140 | 0 | 290 | A | 0 | 680 |  |  |  | 7
2025-09-11 | 4661 | bth | EXP-RA-04 | A | DONE | 11 | S-M |  | TOMAH HEALTH 6250006 | VD's | 2025-09-15 | Z | 2025-09-08 | 170 | 30 | 60 | A | 0 | 310 |  |  |  | 7
2025-09-11 | 4662 | bth | EXP-RA-05 | A | DONE | 26 | M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 350 | 20 | 260 | A | 0 | 970 |  |  |  | 7
2025-09-11 | 4663 |  | EXP-RA-06 | A | DONE | 27 | M |  | TOMAH HEALTH 6250006 | VD's | 2025-09-15 | Z | 2025-09-08 | 380 | 0 | 290 | A | 0 | 1170 |  |  |  | 7
2025-09-11 | 4664 |  | EXP-RA-07 | A | DONE | 28 | M |  | TOMAH HEALTH 6250006 | VD | 2025-09-15 | Z | 2025-09-08 | 550 | 0 | 140 | A | 0 | 1140 |  |  |  | 7
2025-09-11 | 4665 | bth | EXP-RA-08 | A | DONE | 18 | S-M |  | TOMAH HEALTH 6250006 | VD | 2025-09-15 | Z | 2025-09-08 | 340 | 20 | 90 | A | 0 | 520 |  |  |  | 7
2025-09-11 | 4666 | bth | EXP-RA-09 | A | DONE | 10 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 70 | 80 | 80 | A | 0 | 260 |  |  |  | 7
2025-09-11 | 4667 |  | EXP-RA-10 | A | DONE | 10 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 200 | 0 | 50 | A | 0 | 340 |  |  |  | 7
2025-09-11 | 4668 | bth | EXP-RA-11 | A | DONE | 11 | S-M |  | TOMAH HEALTH 6250006 | VD's | 2025-09-15 | Z | 2025-09-08 | 170 | 0 | 90 | A | 0 | 340 |  |  |  | 7
2025-09-12 | 4669 | bth | EXP-SAMP-01 | A | DONE | 16 | M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 250 | 40 | 90 | A | 0 | 490 |  |  |  | 7
2025-09-11 | 4670 | bth | EXP-SAMP-02 | A | DONE | 13 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 90 | 20 | 200 | A | 0 | 410 |  |  |  | 7
2025-09-11 | 4671 | bth | EXP-SAMP-03 | A | DONE | 14 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 170 | 40 | 130 | A | 0 | 430 |  |  |  | 7
2025-09-11 | 4672 | bth | EXP-SAMP-04 | A | DONE | 11 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 110 | 30 | 140 | A | 0 | 350 |  |  |  | 7
2025-09-11 | 4673 | bth | EXP-SAMP-05 | A | DONE | 23 | M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 460 | 10 | 110 | A | 0 | 800 |  |  |  | 7
2025-09-11 | 4674 | bth | EXP-SAMP-06 | A | DONE | 13 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 220 | 20 | 100 | A | 0 | 470 |  |  |  | 7
2025-09-12 | 4675 | bth | EXP-SAMP-07 | A | DONE | 9 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 140 | 50 | 40 | A | 0 | 300 |  |  |  | 7
2025-09-12 | 4676 | bth | EXP-SAMP-08 | A | DONE | 11 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-15 | Z | 2025-09-08 | 240 | 20 | 0 |  | 0 | 300 |  |  |  | 7
2025-09-13 | 1419A |  | 82991 | A | DONE | 2 | M |  | UW-LEVY HALL 6230028 |  | 2025-09-16 | Z | 2025-09-11 | 29 | 0 | 0 |  | 0 | 1570 |  | ELBOW |  | 5
2025-09-09 | 1424 |  | 83847 | A | DONE | 30 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-09-16 | Z | 2025-09-05 | 730 | 0 | 0 |  | 160 | 730 |  | L3 Bathroom tie in |  | 11
2025-09-10 | 1425 |  | 83845 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-09-16 | Z | 2025-09-05 | 50 | 0 | 0 |  | 0 | 70 |  | LVL 3,4 misc |  | 11
2025-09-10 | 1426 | bth | 83849 | A | DONE | 6 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-09-16 | Z | 2025-09-08 | 20 | 120 | 0 |  | 0 | 130 |  | L4 EAMP Copier duct |  | 8
2025-09-10 | 1428 |  | 74851 | A | DONE | 10 | S | ss | UW-LEVY HALL 6230028 |  | 2025-09-11 | Z | 2025-09-10 | 240 | 0 | 0 |  | 0 | 490 |  | Flat stock |  | 1
2025-09-13 | 2883 |  | 84884 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-09-16 | Z | 2025-09-10 | 20 | 0 | 0 |  | 0 | 20 |  | 307F |  | 6
2025-09-08 | 3883 |  | 83841 | A | DONE | 3 | S |  | UW-WITTE HALL 6250003 | 4"liner | 2025-09-09 | Z | 2025-08-27 | 70 | 0 | 0 |  | 120 | 240 |  | PIPE COVER |  | 13
2025-09-11 | 3885 | w | 97776 | A | DONE | 2 | S | ss | UW-WITTE HALL 6250003 |  | 2025-09-12 | Z | 2025-09-08 | 20 | 0 | 0 |  | 0 | 20 |  | Cover |  | 4
2025-09-10 | 3886 |  | 58175 | A | DONE | 3 | S |  | UW-WITTE HALL 6250003 | 1" liner | 2025-09-10 | Z | 2025-09-10 | 60 | 0 | 0 |  | 0 | 80 |  | SA Drop |  | 0
2025-09-10 | 1515 |  | 56213 | A | DONE | 2 | S | ss | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-08-28 | 30 | 20 | 0 |  | 0 | 50 |  | HOOD RM 1225 |  | 15
2025-09-09 | 1521 |  | 73759-60,75301 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | paint | 2025-09-12 | Z | 2025-09-02 | 190 | 0 | 0 |  | 0 | 220 |  | Misc Tie Ins |  | 10
2025-09-09 | 1523 |  | 73761 - 73764 | A | DONE | 11 | M |  | WAUNAKEE MS 6230013 | paint | 2025-09-12 | Z | 2025-09-03 | 260 | 0 | 0 |  | 0 | 300 |  | 1st floor tie in |  | 9
2025-09-11 | 1524 | w | 73766 | A | DONE | 2 | S | ss | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 20 | 0 | 0 |  | 0 | 50 |  | KH-1,2 |  | 9
2025-09-09 | 1525 | sp | 73765 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 20 | 30 | 0 |  | 0 | 50 |  | 1st floor tie in |  | 9
2025-09-08 | 1526 |  | PH_A_EA_005 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 110 | 0 | 0 |  | 0 | 150 |  |  |  | 9
2025-09-09 | 1527 |  | PH_A_EA_006 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 90 | 0 | 0 |  | 0 | 130 |  |  |  | 9
2025-09-09 | 1528 |  | PH_A_OA_007 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 | CD | 2025-09-12 | Z | 2025-09-03 | 150 | 0 | 70 | A | 0 | 400 |  |  |  | 9
2025-09-09 | 1529 |  | PH_A_OA_008 | A | DONE | 21 | M |  | WAUNAKEE MS 6230013 | CD | 2025-09-12 | Z | 2025-09-03 | 520 | 0 | 0 |  | 0 | 930 |  |  |  | 9
2025-09-08 | 1530 |  | PH_A_RA_002 | A | DONE | 29 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 370 | 0 | 340 | A | 0 | 1020 |  |  |  | 9
2025-09-09 | 1531 |  | PH_A_RA_003 | A | DONE | 24 | M-L |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 460 | 0 | 140 | A | 0 | 950 |  |  |  | 9
2025-09-09 | 1532 |  | PH_A_RA_004 | A | DONE | 14 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 330 | 0 | 0 |  | 0 | 870 |  |  |  | 9
2025-09-09 | 1533 |  | PH_A_RA_005 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 | CD | 2025-09-12 | Z | 2025-09-03 | 230 | 0 | 60 | A | 0 | 460 |  |  |  | 9
2025-09-09 | 1534 |  | PH_A_RA_006 | A | DONE | 16 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 240 | 0 | 150 | A | 0 | 570 |  |  |  | 9
2025-09-09 | 1535 |  | PH_A_RA_007 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 | CD | 2025-09-12 | Z | 2025-09-03 | 80 | 0 | 120 | A | 0 | 450 |  |  |  | 9
2025-09-09 | 1536 |  | PH_A_RA_008 | A | DONE | 21 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-03 | 510 | 0 | 0 |  | 0 | 1000 |  |  |  | 9
2025-09-10 | 1537 |  | L02_A_RAD_001 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 90 | 0 | 30 | A | 90 | 160 |  |  |  | 8
2025-09-10 | 1538 |  | L02_A_RAD_002 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 8
2025-09-10 | 1539 | bth | L02_A_RAD_003 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 90 | 20 | 0 |  | 80 | 130 |  |  |  | 8
2025-09-10 | 1540 |  | L02_A_RAD_004 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 160 | 0 | 70 | A | 170 | 300 |  |  |  | 8
2025-09-10 | 1541 |  | L02_A_RAD_005 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 160 | 0 | 70 | A | 170 | 290 |  |  |  | 8
2025-09-10 | 1542 | bth | L02_A_RAD_006 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-09-12 | Z | 2025-09-04 | 60 | 20 | 0 |  | 40 | 80 |  |  |  | 8
2025-09-10 | 1543 |  | L02_A_RAD_007 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 8
2025-09-10 | 1544 | bth | L02_A_RAD_008 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-09-12 | Z | 2025-09-04 | 30 | 50 | 0 |  | 20 | 80 |  |  |  | 8
2025-09-10 | 1545 | bth | L02_A_RAD_009 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-09-12 | Z | 2025-09-04 | 40 | 20 | 0 |  | 30 | 70 |  |  |  | 8
2025-09-10 | 1546 |  | L02_A_RAD_010 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 280 | 0 | 0 |  | 200 | 350 |  |  |  | 8
2025-09-10 | 1547 | bth | L02_A_RAD_011 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 50 | 30 | 0 |  | 30 | 90 |  |  |  | 8
2025-09-10 | 1548 |  | L02_A_RAD_012 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 120 | 0 | 0 |  | 100 | 190 |  |  |  | 8
2025-09-12 | 1549 |  | L02_A_RAD_013 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-09-12 | Z | 2025-09-04 | 110 | 0 | 0 |  | 80 | 130 |  |  |  | 8
2025-09-12 | 1550 |  | L02_A_RAD_014 | A | DONE | 11 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 150 | 0 | 0 |  | 110 | 200 |  |  |  | 8
2025-09-12 | 1551 |  | L02_A_RAD_015 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-09-12 | Z | 2025-09-04 | 90 | 0 | 0 |  | 60 | 120 |  |  |  | 8
2025-09-12 | 1552 | bth | L02_A_RAD_016 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 30 | 30 | 0 |  | 10 | 70 |  |  |  | 8
2025-09-12 | 1553 |  | L02_A_RAD_017 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 130 | 0 | 0 |  | 80 | 160 |  |  |  | 8
2025-09-12 | 1554 |  | L02_A_RAD_018 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-09-12 | Z | 2025-09-04 | 80 | 0 | 0 |  | 60 | 110 |  |  |  | 8
2025-09-12 | 1555 | bth | L02_A_RAD_019 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 40 | 10 | 0 |  | 20 | 60 |  |  |  | 8
2025-09-12 | 1556 | sp | L02_A_RAD_020 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 0 | 60 | 0 |  | 0 | 50 |  |  |  | 8
2025-09-12 | 1557 |  | L02_A_RAD_021 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 8
2025-09-12 | 1558 | sp | L02_A_RAD_022 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 10 | 60 | 0 |  | 0 | 70 |  |  |  | 8
2025-09-12 | 1559 | sp | L02_A_RAD_023 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 10 | 60 | 0 |  | 0 | 60 |  |  |  | 8
2025-09-12 | 1560 | sp | L02_A_RAD_024 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 10 | 20 | 0 |  | 0 | 30 |  |  |  | 8
2025-09-12 | 1561 | bth | L02_A_RAD_025 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 50 | 20 | 0 |  | 40 | 80 |  |  |  | 8
2025-09-12 | 1562 |  | L02_A_RAD_026 | A | DONE | 11 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-09-12 | Z | 2025-09-04 | 50 | 0 | 90 | A | 120 | 180 |  |  |  | 8
2025-09-12 | 1563 | bth | L02_A_SALP_001 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 50 | 30 | 20 | A | 0 | 120 |  |  |  | 8
2025-09-11 | 1564 |  | L02_A_SALP_002 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 100 | 0 | 0 |  | 0 | 110 |  |  |  | 8
2025-09-12 | 1565 | bth | L02_A_SALP_003 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 50 | 260 | 0 |  | 0 | 290 |  |  |  | 8
2025-09-12 | 1566 | sp | L02_A_SALP_004 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 10 | 50 | 0 |  | 0 | 50 |  |  |  | 8
2025-09-12 | 1567 | bth | L02_A_SALP_005 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 70 | 20 | 0 |  | 0 | 90 |  |  |  | 8
2025-09-11 | 1568 |  | L02_A_SALP_006 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 80 | 0 | 20 | A | 0 | 120 |  |  |  | 8
2025-09-12 | 1569 | bth | L02_A_SALP_007 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 50 | 30 | 20 | A | 0 | 110 |  |  |  | 8
2025-09-12 | 1570 |  | L02_A_SALP_008 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 60 | 0 | 110 | A | 0 | 200 |  |  |  | 8
2025-09-12 | 1571 | bth | L02_A_SALP_009 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 110 | 50 | 60 | A | 0 | 240 |  |  |  | 8
2025-09-12 | 1572 |  | L02_A_SALP_010 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 120 | 0 | 60 | A | 0 | 210 |  |  |  | 8
2025-09-12 | 1573 | bth | L02_A_SALP_011 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 70 | 40 | 30 | A | 0 | 140 |  |  |  | 8
2025-09-12 | 1574 | sp | L02_A_SALP_012 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 8
2025-09-12 | 1575 | sp | L02_A_SALP_013 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 8
2025-09-13 | 1576 | sp | L02_A_SALP_014 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 10 | 40 | 0 |  | 0 | 40 |  |  |  | 8
2025-09-12 | 1577 |  | L02_A_SALP_015 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 120 | 0 | 0 |  | 0 | 150 |  |  |  | 8
2025-09-12 | 1578 | bth | L02_A_SALP_016 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 50 | 130 | 90 | A | 0 | 280 |  |  |  | 8
2025-09-13 | 1579 | bth | L02_A_SALP_017 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 40 | 20 | 0 |  | 0 | 60 |  |  |  | 8
2025-09-13 | 1580 | sp | L02_A_SALP_018 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 10 | 30 | 0 |  | 0 | 30 |  |  |  | 8
2025-09-12 | 1581 |  | L02_A_SALP_019 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 80 | 0 | 30 | A | 0 | 140 |  |  |  | 8
2025-09-13 | 1582 | bth | L02_A_SALP_020 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 90 | 40 | 50 | A | 0 | 190 |  |  |  | 8
2025-09-12 | 1584 | bth | L02_A_SALP_022 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 100 | 10 | 80 | A | 0 | 230 |  |  |  | 8
2025-09-13 | 1586 | sp | L02_A_SALP_024 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 30 | 30 | 20 | A | 0 | 90 |  |  |  | 8
2025-09-13 | 1587 |  | L02_A_SALP_025 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 10 | 70 | 0 |  | 0 | 70 |  |  |  | 8
2025-09-13 | 1588 | bth | L02_A_SALP_026 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 80 | 0 | 50 | A | 0 | 160 |  |  |  | 8
2025-09-13 | 1589 | bth | L02_A_SALP_027 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 90 | 40 | 50 | A | 0 | 200 |  |  |  | 8
2025-09-13 | 1590 | bth | L02_A_SALP_028 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 30 | 40 | 50 | A | 0 | 130 |  |  |  | 8
2025-09-13 | 1591 | bth | L02_A_SALP_029 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 40 | 30 | 50 | A | 0 | 120 |  |  |  | 8
2025-09-13 | 1592 | bth | L02_A_SALP_030 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 40 | 50 | 0 |  | 0 | 90 |  |  |  | 8
2025-09-09 | 1595 |  | 75302 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | VD | 2025-09-12 | Z | 2025-09-05 | 20 | 0 | 0 |  | 0 | 20 |  | VD |  | 7
2025-09-08 | 1596 |  | 73812 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-08 | 40 | 0 | 0 |  | 0 | 40 |  | EA outs |  | 4
2025-09-09 | 1598 |  | 83379 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-16 | Z | 2025-09-08 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd RA |  | 8
[6 empty] | 1415 | [13 empty] | 47290
WEEK OF 9-15-2025
2025-09-18 | 2491 |  | 77268 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2025-09-23 | Z | 2025-09-18 | 20 | 0 | 0 |  | 20 | 20 |  | RFI 1433 |  | 5
2025-09-18 | 282 |  | 82234 | A | DONE | 3 | S |  | CODY S 1000384 |  | 2025-09-19 | Z | 2025-09-15 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 4
2025-09-15 | 3536 | bth | 73782,85,87-89 | A | DONE | 81 | L | neal | DELLSHIRE 6240017 | spiral mate | 2025-09-15 | Z | 2025-08-27 | 360 | 1490 | 160 | A | 0 | 2410 |  | AHU-5-SA |  | 19
2025-09-15 | 3543 |  | 73792 | A | DONE | 3 | S |  | DELLSHIRE 6240017 |  | 2025-09-17 | Z | 2025-09-10 | 60 | 0 | 0 |  | 0 | 80 |  | Misc |  | 7
2025-09-18 | 2215 |  | Z3-OA 15 | A | DONE | 24 | M-L |  | DOC JDC 6240023 | VD's | 2025-09-18 | Z | 2025-09-10 | 350 | 0 | 230 | A | 0 | 920 |  |  |  | 8
2025-09-18 | 2216 |  | Z3-OA 16 | A | DONE | 12 | S-M |  | DOC JDC 6240023 | VD's | 2025-09-18 | Z | 2025-09-10 | 220 | 0 | 70 | A | 0 | 350 |  |  |  | 8
2025-09-19 | 2217 |  | Z3-OA 17 | A | DONE | 19 | M |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-10 | 240 | 0 | 220 | A | 0 | 560 |  |  |  | 8
2025-09-19 | 2218 |  | Z3-OA 18 | A | DONE | 10 | S-M |  | DOC JDC 6240023 | VD's | 2025-09-18 | Z | 2025-09-10 | 170 | 0 | 70 | A | 0 | 390 |  |  |  | 8
2025-09-19 | 2219 |  | Z3-OA 19 | A | DONE | 14 | S-M |  | DOC JDC 6240023 | VD's | 2025-09-18 | Z | 2025-09-10 | 200 | 0 | 130 | A | 0 | 390 |  |  |  | 8
2025-09-19 | 2220 |  | Z3-OA 20 | A | DONE | 7 | S-M |  | DOC JDC 6240023 | VD's | 2025-09-18 | Z | 2025-09-10 | 130 | 0 | 40 | A | 0 | 290 |  |  |  | 8
2025-09-19 | 2241 | bth | Z3-SAT-4-1-4_2 | A | DONE | 14 | S-M |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-16 | 20 | 140 | 170 | A | 0 | 370 |  |  |  | 2
2025-09-19 | 2242 | bth | Z3-RA 39 | A | DONE | 8 | S |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-16 | 90 | 30 | 70 | A | 0 | 220 |  |  |  | 2
2025-09-19 | 2243 | bth | Z3-RA 40 | A | DONE | 27 | M |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-16 | 280 | 190 | 190 | A | 0 | 810 |  |  |  | 2
2025-09-19 | 2244 | bth | Z3-RA 41 | A | DONE | 16 | S-M |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-16 | 100 | 150 | 150 | A | 0 | 450 |  |  |  | 2
2025-09-19 | 2245 | bth | Z3-RA 42 | A | DONE | 17 | S-M |  | DOC JDC 6240023 | VD | 2025-09-18 | Z | 2025-09-16 | 180 | 110 | 120 | A | 0 | 520 |  |  |  | 2
2025-09-19 | 2246 | bth | Z3-RA 43 | A | DONE | 22 | M |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-16 | 260 | 200 | 80 | A | 0 | 650 |  |  |  | 2
2025-09-19 | 2247 | bth | Z3-RA 44 | A | DONE | 6 | S |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-16 | 30 | 100 | 0 |  | 0 | 140 |  |  |  | 2
2025-09-18 | 2249 |  | 73921 - 73922 | A | DONE | 6 | S-M |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-17 | 140 | 0 | 0 |  | 0 | 200 |  | Zone 3 Roof drops |  | 1
2025-09-16 | 659 |  | Z1-OA 9 | A | DONE | 8 | S-M |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-07-22 | 70 | 0 | 110 | A | 0 | 300 |  |  |  | 58
2025-09-15 | 1024 | bth | ES SL-BCU 1893-1 | A | DONE | 29 | M |  | ES SEQUENCING 2250029 |  | 2025-09-17 | Z | 2025-08-26 | 530 | 20 | 160 | A | 0 | 850 |  |  |  | 22
2025-09-16 | 1025 | bth | ES SL-BCU 1893-2 | A | DONE | 28 | M |  | ES SEQUENCING 2250029 |  | 2025-09-17 | Z | 2025-08-26 | 380 | 100 | 200 | A | 0 | 840 |  |  |  | 22
2025-09-16 | 1026 | bth | ES SL-BCU 1893-3 | A | DONE | 28 | M |  | ES SEQUENCING 2250029 |  | 2025-09-17 | Z | 2025-08-26 | 310 | 50 | 320 | A | 0 | 870 |  |  |  | 22
2025-09-16 | 1027 |  | ES SL-BCU 1893-4 | A | DONE | 19 | S-M |  | ES SEQUENCING 2250029 |  | 2025-09-17 | Z | 2025-08-26 | 370 | 0 | 90 | A | 0 | 540 |  |  |  | 22
2025-09-16 | 1029 |  | ES SL-EA 10 | A | DONE | 15 | S-M |  | ES SEQUENCING 2250029 | BDD | 2025-09-17 | Z | 2025-08-26 | 330 | 0 | 40 | A | 0 | 430 |  |  |  | 22
2025-09-16 | 1030 |  | ES SL-EA 11 | A | DONE | 49 | S-M |  | ES SEQUENCING 2250029 | BDD | 2025-09-17 | Z | 2025-08-26 | 960 | 0 | 250 | A | 0 | 1680 |  |  |  | 22
2025-09-17 | 1032 |  | ES SL-EA 13 | A | DONE | 8 | S |  | ES SEQUENCING 2250029 |  | 2025-09-17 | Z | 2025-08-26 | 200 | 0 | 0 |  | 0 | 300 |  |  |  | 22
2025-09-17 | 1040 |  | ES SL-EA 9 | A | DONE | 10 | S-M |  | ES SEQUENCING 2250029 | BDD | 2025-09-17 | Z | 2025-08-26 | 160 | 0 | 80 | A | 0 | 360 |  |  |  | 22
2025-09-16 | 1303 | bth | 56831 - 56832 | A | DONE | 7 | S-M |  | EXACT MAILROOM 2250027 | paint | 2025-09-17 | Z | 2025-08-26 | 40 | 120 | 0 |  | 0 | 170 |  | SA Spiral , Grile |  | 22
2025-09-15 | 1304 |  | 56833 | A | DONE | 8 | S |  | EXACT MAILROOM 2250027 | 1" liner | 2025-09-17 | Z | 2025-08-26 | 110 | 0 | 0 |  | 80 | 130 |  | TA |  | 22
2025-09-15 | 1306 | sp | 56835 | A | DONE | 2 | S |  | EXACT MAILROOM 2250027 |  | 2025-09-17 | Z | 2025-09-12 | 50 | 0 | 0 |  | 0 | 60 |  | VAV 114 |  | 5
2025-09-15 | 3236 |  | 77266-67 | A | DONE | 3 | S |  | HISTOSONICS 6250009 |  | 2025-09-17 | Z | 2025-09-11 | 70 | 0 | 0 |  | 0 | 80 |  | EF-1,2 |  | 6
2025-09-18 | 1455a | bth | SALP-L1E-16 | A | DONE | 27 | S-M |  | MONROE HS 6240018 | partial,s.mates,2" liner | 2025-09-18 | Z | 2025-09-16 | 660 | 0 | 0 |  | 320 | 1130 |  |  |  | 2
2025-09-18 | 3039 |  | 85342 - 85343 | A | DONE | 7 | S-M |  | MONROE HS 6240018 |  | 2025-09-17 | Z | 2025-09-09 | 170 | 0 | 0 |  | 0 | 490 |  | Louvers |  | 8
2025-09-17 | 285 |  | 84738 | A | DONE | 2 | S |  | OAKWOOD 10064379 |  | 2025-09-17 | Z | 2025-09-17 | 20 | 0 | 0 |  | 0 | 20 |  | AHU |  | 0
2025-09-16 | 822 | bth | 76763 , 65 - 66 | A | DONE | 8 | S-M | pt.neal | PEWAUKEE HS 6240030 | VD , 1" liner | 2025-09-16 | Z | 2025-09-05 | 170 | 20 | 0 |  | 0 | 220 |  | SAT V-19 |  | 11
2025-09-17 | 826 | sp | L1B-DC EA ROOF | A | DONE | 4 | S-M | pt.neal | PEWAUKEE HS 6240030 | flanges | 2025-09-16 | Z | 2025-09-05 | 50 | 40 | 0 |  | 0 | 180 |  |  |  | 11
2025-09-17 | 827 | w | L1C-DC SA | A | DONE | 28 | M | pt.neal | PEWAUKEE HS 6240030 | flanges | 2025-09-16 | Z | 2025-09-05 | 680 | 0 | 0 |  | 0 | 1680 |  |  |  | 11
2025-09-16 | 828 | w | 76729 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | 2" DB | 2025-09-16 | Z | 2025-09-08 | 30 | 0 | 0 |  | 30 | 110 |  | DC Curb cap |  | 8
2025-09-15 | 830 |  | 76810 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-09-16 | Z | 2025-09-08 | 50 | 0 | 0 |  | 0 | 50 |  | Dark room |  | 8
2025-09-16 | 833 |  | 76746 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-09-16 | Z | 2025-09-10 | 20 | 0 | 0 |  | 0 | 30 |  | DC Gussets |  | 6
2025-09-17 | 834 |  | 76748 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-09-16 | Z | 2025-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | Roof duct hangers |  | 0
2025-09-15 | 1601 | w | L02_AREA_200_RAMP_001 | A | DONE | 5 | S-M | ss | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-09-04 | 120 | 0 | 0 |  | 0 | 380 |  |  |  | 8
2025-09-19 | 1603 | w | L02_AREA_300_MA_009 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-09-25 | Z | 2025-09-04 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 21
2025-09-18 | 1614 |  | 76360 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-09-18 | Z | 2025-09-16 | 20 | 0 | 0 |  | 0 | 60 |  | SS Hangers |  | 2
2025-09-18 | 4700 |  | L02_AREA_400_EA_002 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-09-18 | Z | 2025-07-11 | 70 | 0 | 0 |  | 0 | 170 |  |  |  | 69
2025-09-17 | 4701 |  | L02_AREA_400_EA_003 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-09-18 | Z | 2025-07-11 | 70 | 0 | 0 |  | 0 | 90 |  |  |  | 69
2025-09-17 | 4702 |  | L02_AREA_400_EA_004 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-09-18 | Z | 2025-07-11 | 50 | 0 | 0 |  | 0 | 90 |  |  |  | 69
2025-09-18 | 4705 |  | L02_AREA_400_RAMP_002 | A | DONE | 86 | L |  | PROJECT DOVE 6240041 | bird s. , 1" DW | 2025-09-18 | Z | 2025-07-11 | 1980 | 0 | 150 | A | 560 | 3970 |  |  |  | 69
2025-09-19 | 4706 |  | L02_AREA_400_RAMP_003 | A | DONE | 71 | M-L |  | PROJECT DOVE 6240041 | 1" DW | 2025-09-18 | Z | 2025-07-11 | 1610 | 0 | 150 | A | 860 | 1660 |  |  |  | 69
2025-09-15 | 4877 | bth | L02-AREA 052-SALP-16 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 70 | 40 | 0 |  | 0 | 120 |  |  |  | 16
2025-09-15 | 4878 | sp | L02-AREA 052-SALP-17 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 16
2025-09-15 | 4880 | sp | L02-AREA 052-SALP-19 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 10 | 60 | 0 |  | 0 | 60 |  |  |  | 16
2025-09-15 | 4881 | sp | L02-AREA 052-SALP-20 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 16
2025-09-15 | 4882 | sp | L02-AREA 052-SALP-21 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 10 | 90 | 0 |  | 0 | 120 |  |  |  | 16
2025-09-15 | 4883 | sp | L02-AREA 052-SALP-22 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 10 | 50 | 0 |  | 0 | 50 |  |  |  | 16
2025-09-15 | 4884 | bth | L02-AREA 052-SALP-23 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 40 | 30 | 0 |  | 0 | 70 |  |  |  | 16
2025-09-15 | 4885 | bth | L02-AREA 052-SALP-24 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 70 | 70 | 0 |  | 0 | 140 |  |  |  | 16
2025-09-15 | 4886 | bth | L02-AREA 052-SALP-25 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 50 | 30 | 70 | A | 0 | 160 |  |  |  | 16
2025-09-15 | 4887 | sp | L02-AREA 052-SALP-26 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 0 | 40 | 0 |  | 0 | 40 |  |  |  | 16
2025-09-15 | 4888 | sp | L02-AREA 052-SALP-27 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 10 | 40 | 0 |  | 0 | 50 |  |  |  | 16
2025-09-15 | 4889 |  | L02-AREA 052-SALP-28 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 120 | 0 | 0 |  | 0 | 140 |  |  |  | 16
2025-09-15 | 4890 | bth | L02-AREA 052-SALP-29 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 80 | 70 | 0 |  | 0 | 150 |  |  |  | 16
2025-09-15 | 4891 |  | L02-AREA 052-SALP-30 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-12 | Z | 2025-08-27 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 16
2025-09-18 | 4899 |  | 76170 - 76171 | A | DONE | 88 | M |  | PROJECT DOVE 6240041 | 1" DW | 2025-09-18 | Z | 2025-09-03 | 2200 | 0 | 0 |  | 900 | 4790 |  | Area 400 Drops |  | 15
2025-09-16 | 3111 |  | 61938 | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-09-18 | Z | 2025-09-11 | 20 | 0 | 0 |  | 20 | 40 |  | 5TH FL 198 |  | 7
2025-09-15 | 1427 |  | 76114 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-09-16 | Z | 2025-09-10 | 50 | 0 | 0 |  | 0 | 70 |  | PH |  | 6
2025-09-15 | 2884 |  | 84885 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2025-09-16 | Z | 2025-09-10 | 10 | 0 | 0 |  | 0 | 10 |  | 307D |  | 6
2025-09-16 | 3272 |  | 38171-72 | A | DONE | 7 | S-M |  | UWSP-ALBERTSON 6230016 |  | 2025-09-16 | Z | 2025-09-11 | 170 | 0 | 0 |  | 0 | 230 |  | 1ST FL |  | 5
2025-09-19 | 3098 |  | 54537 | A | DONE | 6 | S-M | ss | UW-VET MED 2250030 |  | 2025-09-23 | Z | 2025-09-16 | 130 | 0 | 0 |  | 0 | 130 |  | BSL 3 |  | 7
2025-09-17 | 3094 | bth | 54533 - 54534 | A | DONE | 4 | S-M |  | UW-VET MED 6210014 | flex | 2025-09-19 | Z | 2025-09-08 | 90 | 0 | 0 |  | 0 | 170 |  | CB 337 outs |  | 11
2025-09-16 | 3095 |  | 54535 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2025-09-19 | Z | 2025-09-11 | 20 | 0 | 0 |  | 0 | 40 |  | 10-D Outs |  | 8
2025-09-19 | 3096 |  | 54536 | A | DONE | 2 | S |  | UW-VET MED 6240014 |  | 2025-09-19 | Z | 2025-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | 7B Flashing |  | 3
2025-09-19 | 3097 |  | 54538 | A | DONE | 2 | S |  | UW-VET MED 6240014 | bird s. | 2025-09-19 | Z | 2025-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 3
2025-09-16 | 1519 | sp | 78045,79899 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | spiral mate | 2025-09-12 | Z | 2025-08-29 | 140 | 90 | 0 |  | 0 | 330 |  | DC-1 |  | 14
2025-09-16 | 1520 | sp | 78046,79900 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | spiral mate | 2025-09-12 | Z | 2025-08-29 | 180 | 70 | 0 |  | 0 | 350 |  | DC-2 |  | 14
2025-09-15 | 1583 | bth | L02_A_SALP_021 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 30 | 40 | 0 |  | 0 | 70 |  |  |  | 8
2025-09-15 | 1585 | bth | L02_A_SALP_023 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-04 | 40 | 50 | 90 | A | 0 | 200 |  |  |  | 8
2025-09-15 | 1593 | bth | L02_A_SALP_031 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 8
2025-09-15 | 1594 | sp | L02_A_SALP_032 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 | flex | 2025-09-12 | Z | 2025-09-04 | 40 | 190 | 0 |  | 0 | 210 |  |  |  | 8
2025-09-18 | 1597 |  | 83323 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-09-12 | Z | 2025-09-08 | 20 | 20 | 0 |  | 0 | 40 |  | Weight room |  | 4
2025-09-18 | 1599 |  | 82913 | A | DONE | 2 | S | BI | WAUNAKEE MS 6230013 |  | 2025-09-19 | Z | 2025-09-10 | 20 | 0 | 0 |  | 0 | 20 |  | 1st Floor Hood tie in |  | 9
2025-09-15 | 1650 |  | 73813 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | 1-1/2" wrap | 2025-09-16 | Z | 2025-09-10 | 40 | 0 | 0 |  | 0 | 50 |  | L02 SAMP PH |  | 6
2025-09-16 | 1651 |  | 73768,73815 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-19 | Z | 2025-09-11 | 30 | 0 | 0 |  | 0 | 50 |  | 1ST FL - RISER |  | 8
2025-09-17 | 2717 |  | 76117 | A | DONE | 2 | S | neal | WSCC 6240006 | paint | 2025-09-17 | Z | 2025-09-17 | 20 | 0 | 0 |  | 20 | 20 |  | Covers |  | 0
[6 empty] | 982 | [13 empty] | 33960 |  |  |  | 12400 | 36.51%
WEEK OF 9-22-2025
2025-09-27 | 289 |  | 84740 | A | DONE | 2 | S |  | 8020 HP 4250031 |  | 2025-09-29 | Z | 2025-09-22 | 50 | 0 | 0 |  | 0 | 60 |  | MisC |  | 7
2025-09-25 | 2450 | w | 82705 , 82708 | A | DONE | 2 | S |  | ANTIGO ELEM. 6250017 | 1" FB | 2025-09-29 | Z | 2025-09-22 | 30 | 0 | 0 |  | 40 | 80 |  | 1st Floor Sleeves Area A |  | 7
2025-09-27 | 584 | sp | 75262 - 75263 | A | DONE | 11 | M |  | BARTILLION 6240024 | 1" sprial acoustic | 2025-09-24 | Z | 2025-09-17 | 110 | 150 | 0 |  | 220 | 300 |  | AV 2-2 Storage Rm. |  | 7
2025-09-27 | 585 |  | 75264 - 75266 | A | DONE | 8 | S-M |  | BARTILLION 6240024 |  | 2025-09-24 | Z | 2025-09-17 | 200 | 0 | 0 |  | 0 | 270 |  | 2-2 Bathroom |  | 7
2025-09-27 | 586 | sp | 75268 | A | DONE | 4 | S-M |  | BARTILLION 6240024 | 1" sprial acoustic | 2025-09-24 | Z | 2025-09-17 | 70 | 20 | 0 |  | 50 | 90 |  | SA 2nd Mech |  | 7
2025-09-27 | 587 |  | 75269 | A | DONE | 2 | S |  | BARTILLION 6240024 | 1" liner | 2025-09-24 | Z | 2025-09-17 | 30 | 0 | 0 |  | 30 | 50 |  | RC 2-4 2nd |  | 7
2025-09-27 | 588 | bth | 75270 | A | DONE | 4 | S |  | BARTILLION 6240024 |  | 2025-09-24 | Z | 2025-09-17 | 60 | 20 | 0 |  | 0 | 110 |  | EA 2nd Mech |  | 7
2025-09-23 | 2906 |  | 97777 | A | DONE | 2 | S | BI | BROOM ST. 6240033 |  | 2025-09-25 | Z | 2025-09-23 | 20 | 0 | 0 |  | 0 | 50 |  | Caps |  | 2
2025-09-23 | 3538 |  | 73779-81 | A | DONE | 31 | S-M | neal | DELLSHIRE 6240017 |  | 2025-09-22 | Z | 2025-08-27 | 200 | 0 | 570 | A | 0 | 930 |  | VAV-8-1-2ND |  | 26
2025-09-24 | 3539 | sp | 73783 | A | DONE | 15 | S-M | neal | DELLSHIRE 6240017 |  | 2025-09-22 | Z | 2025-08-27 | 70 | 300 | 0 |  | 0 | 460 |  | AHU-5 |  | 26
2025-09-25 | 3544 |  | 73812-13 | A | DONE | 32 | M |  | DELLSHIRE 6240017 |  | 2025-09-22 | Z | 2025-09-11 | 240 | 0 | 560 | A | 0 | 1520 |  | Meeting Space HP |  | 11
2025-09-25 | 3545 | bth | 73814,17 | A | DONE | 20 | S-M |  | DELLSHIRE 6240017 |  | 2025-09-22 | Z | 2025-09-11 | 280 | 90 | 130 | A | 0 | 750 |  | VAV-6-2 |  | 11
2025-09-25 | 3546 | bth | 73815-16 | A | DONE | 20 | S-M |  | DELLSHIRE 6240017 |  | 2025-09-22 | Z | 2025-09-11 | 180 | 250 | 50 | A | 0 | 580 |  | VAV-6-1 |  | 11
2025-09-22 | 2248 |  | 73920 | A | DONE | 10 | S-M |  | DOC JDC 6240023 |  | 2025-09-18 | Z | 2025-09-17 | 240 | 0 | 0 |  | 0 | 590 |  | Mech Rm Roof drops |  | 1
2025-09-23 | 4728 |  | 74310 | A | DONE | 7 | S-M |  | DOC JDC 6240023 |  | 2025-09-25 | Z | 2025-09-19 | 170 | 0 | 0 |  | 0 | 290 |  | Flatstock |  | 6
2025-09-23 | 286 |  | 84739 | A | DONE | 2 | S |  | EGENESIS 10064865 |  | 2025-09-23 | Z | 2025-09-19 | 20 | 0 | 0 |  | 0 | 20 |  | F1 |  | 4
2025-09-27 | 1031 | sp | ES SL-EA 12 | A | DONE | 5 | M-L |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 20 | 90 | 0 |  | 0 | 120 |  |  |  | 29
2025-09-27 | 1043 | sp | ES SL-EAT 3055 | A | DONE | 5 | S |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 20 | 100 | 0 |  | 0 | 140 |  |  |  | 29
2025-09-27 | 1044 | sp | ES SL-SALP 1 | A | DONE | 6 | S |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 90 | 40 | 0 |  | 0 | 140 |  |  |  | 29
2025-09-27 | 1046 | sp | ES SL-SALP 3 | A | DONE | 3 | S |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 29
2025-09-27 | 1047 | sp | ES SL-SALP 4 | A | DONE | 2 | S |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 29
2025-09-27 | 1049 | sp | ES SL-SAT 1889 | A | DONE | 2 | S |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 29
2025-09-24 | 283 | w | 85041 - 85043 | A | DONE | 2 | S-M | BI | JPC SAWMILL 2240068 | nipple | 2025-09-29 | Z | 2025-09-16 | 20 | 0 | 0 |  | 0 | 60 |  | Dust collector |  | 13
2025-09-24 | 284 | w | 85044 | A | DONE | 2 | S |  | JPC SAWMILL 2240068 |  | 2025-09-29 | Z | 2025-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | Dust collector |  | 13
2025-09-22 | 287 |  | 73923 | A | DONE | 2 | S |  | LODI HS 4250042 |  | 2025-09-22 | Z | 2025-09-22 | 20 | 0 | 0 |  | 0 | 20 |  | Flue gas connection |  | 0
2025-09-25 | 1450 | bth | SALP-L1E-11 | A | DONE | 7 | S |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 60 | 40 | 60 | A | 90 | 200 |  |  |  | 14
2025-09-27 | 1451 | bth | SALP-L1E-12 | A | DONE | 15 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 100 | 90 | 180 | A | 220 | 470 |  |  |  | 14
2025-09-25 | 1452 | bth | SALP-L1E-13 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 80 | 130 | 60 | A | 70 | 300 |  |  |  | 14
2025-09-27 | 1453 |  | SALP-L1E-14 | A | DONE | 8 | S |  | MONROE HS 6240018 |  | 2025-09-23 | Z | 2025-09-09 | 60 | 120 | 0 |  | 0 | 230 |  |  |  | 14
2025-09-27 | 1454 |  | SALP-L1E-15 | A | DONE | 37 | M-L |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 510 | 0 | 400 | A | 700 | 1800 |  |  |  | 14
2025-09-27 | 1455 | bth | SALP-L1E-16 | A | DONE | 28 | M-L |  | MONROE HS 6240018 | partial , 2" liner | 2025-09-23 | Z | 2025-09-09 | 140 | 0 | 560 | A | 580 | 1290 |  |  |  | 14
2025-09-25 | 1456 | sp | SALP-L1E-17 | A | DONE | 14 | M | neal | MONROE HS 6240018 | 2" DW , accuflange | 2025-09-23 | Z | 2025-09-09 | 40 | 290 | 0 |  | 120 | 310 |  |  |  | 14
2025-09-27 | 1457 | bth | SAMP-L1E-01 | A | DONE | 16 | S-M |  | MONROE HS 6240018 |  | 2025-09-23 | Z | 2025-09-09 | 160 | 220 | 0 |  | 0 | 430 |  |  |  | 14
2025-09-24 | 1458 | sp | SAMP-L1E-02 | A | DONE | 8 | S |  | MONROE HS 6240018 |  | 2025-09-23 | Z | 2025-09-09 | 20 | 160 | 0 |  | 0 | 170 |  |  |  | 14
2025-09-25 | 1459 | bth | SAMP-L1E-03 | A | DONE | 27 | M |  | MONROE HS 6240018 | oval , accuflange | 2025-09-23 | Z | 2025-09-09 | 220 | 440 | 0 |  | 70 | 1100 |  |  |  | 14
2025-09-27 | 1460 | sp | SAMP-L1E-04 | A | DONE | 12 | S-M |  | MONROE HS 6240018 | oval , accuflange | 2025-09-23 | Z | 2025-09-09 | 80 | 200 | 0 |  | 0 | 560 |  |  |  | 14
2025-09-24 | 1461 | sp | SAMP-L1E-05 | A | DONE | 6 | S |  | MONROE HS 6240018 |  | 2025-09-23 | Z | 2025-09-09 | 20 | 120 | 0 |  | 0 | 120 |  |  |  | 14
2025-09-25 | 1462 | sp | SAMP-L1E-06 | A | DONE | 21 | M |  | MONROE HS 6240018 | oval , accuflange | 2025-09-23 | Z | 2025-09-09 | 90 | 430 | 0 |  | 0 | 800 |  |  |  | 14
2025-09-24 | 1463 | sp | SAMP-L1E-07 | A | DONE | 19 | S-M |  | MONROE HS 6240018 |  | 2025-09-23 | Z | 2025-09-09 | 80 | 380 | 0 |  | 0 | 510 |  |  |  | 14
2025-09-24 | 1464 | sp | SAMP-L1E-08 | A | DONE | 8 | S |  | MONROE HS 6240018 |  | 2025-09-23 | Z | 2025-09-09 | 20 | 160 | 0 |  | 0 | 180 |  |  |  | 14
2025-09-24 | 1479 |  | 83613 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-09-23 | Z | 2025-09-17 | 20 | 0 | 0 |  | 0 | 20 |  | CGS Pipe covers |  | 6
2025-09-27 | 3024 | bth | SALP-L2E-09 | A | DONE | 29 | M | neal | MONROE HS 6240018 | partial,s.mates,2" liner | 2025-09-23 | Z | 2025-09-17 | 490 | 230 | 0 |  | 170 | 840 |  |  |  | 6
2025-09-25 | 3040 | bth | SALP-L1E-01 | A | DONE | 7 | S |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 100 | 60 | 0 |  | 50 | 190 |  |  |  | 14
2025-09-27 | 3041 | bth | SALP-L1E-02 | A | DONE | 8 | S | pt.neal | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 90 | 100 | 0 |  | 20 | 240 |  |  |  | 14
2025-09-25 | 3042 | bth | SALP-L1E-03 | A | DONE | 18 | M | neal | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 160 | 260 | 30 | A | 60 | 540 |  |  |  | 14
2025-09-25 | 3043 | bth | SALP-L1E-04 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 40 | 0 | 190 | A | 190 | 330 |  |  |  | 14
2025-09-27 | 3044 | bth | SALP-L1E-05 | A | DONE | 11 | S-M | neal | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 110 | 150 | 0 |  | 0 | 320 |  |  |  | 14
2025-09-27 | 3045 | bth | SALP-L1E-06 | A | DONE | 8 | S |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 80 | 30 | 70 | A | 100 | 210 |  |  |  | 14
2025-09-27 | 3046 | bth | SALP-L1E-07 | A | DONE | 9 | S |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 110 | 110 | 0 |  | 80 | 250 |  |  |  | 14
2025-09-27 | 3047 | bth | SALP-L1E-08 | A | DONE | 15 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 150 | 110 | 110 | A | 180 | 450 |  |  |  | 14
2025-09-27 | 3048 | bth | SALP-L1E-09 | A | DONE | 21 | M |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 110 | 240 | 160 | A | 200 | 590 |  |  |  | 14
2025-09-27 | 3049 | bth | SALP-L1E-10 | A | DONE | 19 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-09-23 | Z | 2025-09-09 | 120 | 240 | 110 | A | 150 | 510 |  |  |  | 14
2025-09-24 | 3266 | sp | 79540 | A | DONE | 3 | S |  | ONE 09 6240037 | paint | 2025-09-22 | Z | 2025-09-18 | 40 | 20 | 0 |  | 20 | 50 |  | Kitchen Reducer |  | 4
2025-09-27 | 835 |  | 76771 | A | DONE | 4 | S |  | PEWAUKEE HS 6240030 | VD's | 2025-09-24 | Z | 2025-09-16 | 90 | 0 | 0 |  | 0 | 120 |  | RE Dampers |  | 8
2025-09-25 | 1394 |  | L02_AREA_300_MA_001 | A | DONE | 72 | L | ss | PROJECT DOVE 6240041 | 321 , VD's | 2025-09-18 | Z | 2025-07-01 | 1780 | 0 | 0 |  | 0 | 3830 |  |  |  | 79
2025-09-25 | 1395 |  | L02_AREA_300_MA_002 | A | DONE | 41 | L | ss | PROJECT DOVE 6240041 | 321 , VD's | 2025-09-18 | Z | 2025-07-01 | 1010 | 0 | 0 |  | 0 | 2070 |  |  |  | 79
2025-09-23 | 1604 | w | L02_AREA_700_WEST_SAMP_005 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-04 | 100 | 0 | 0 |  | 0 | 210 |  |  |  | 28
2025-09-23 | 1605 | w | L02_AREA_700_WEST_SAMP_006 | A | DONE | 5 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-04 | 120 | 0 | 0 |  | 0 | 240 |  |  |  | 28
2025-09-22 | 1606 | w | L02_AREA_700_WEST_RAMP_005 | A | DONE | 7 | S-M | ss | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-04 | 160 | 0 | 0 |  | 0 | 360 |  |  |  | 28
2025-09-27 | 1615 |  | 76361 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 |  | 2025-09-25 | Z | 2025-09-16 | 40 | 0 | 0 |  | 0 | 100 |  | SS Hangers |  | 9
2025-09-23 | 1632 |  | 76362 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-25 | Z | 2025-09-17 | 40 | 0 | 0 |  | 0 | 50 |  | Flashing |  | 8
2025-09-23 | 1633 |  | 76363 | A | DONE | 8 | S | neal | PROJECT DOVE 6240041 |  | 2025-09-25 | Z | 2025-09-18 | 180 | 0 | 0 |  | 0 | 250 |  | Flashing |  | 7
2025-09-22 | 1638 |  | 76364 | A | DONE | 2 | S | SS | PROJECT DOVE 6240041 |  | 2025-09-23 | Z | 2025-09-22 | 30 | 0 | 0 |  | 0 | 80 |  | L02_AREA_300_RAMP 10 |  | 1
2025-09-24 | 1642 |  | 76365 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-09-25 | Z | 2025-09-24 | 20 | 0 | 0 |  | 0 | 20 |  | Flat stock |  | 1
2025-09-22 | 4704 |  | L02_AREA_400_OA_001 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-09-18 | Z | 2025-07-11 | 190 | 0 | 0 |  | 0 | 520 |  |  |  | 69
2025-09-22 | 4707 |  | L02_AREA_400_RAMP_004 | A | DONE | 82 | M-L |  | PROJECT DOVE 6240041 | bird s. , 1" DW | 2025-09-18 | Z | 2025-07-11 | 1750 | 0 | 300 | A | 610 | 3900 |  |  |  | 69
2025-09-22 | 4708 |  | L02_AREA_400_RAMP_005 | A | DONE | 61 | M-L |  | PROJECT DOVE 6240041 | bird s. , 1" DW | 2025-09-18 | Z | 2025-07-11 | 1430 | 0 | 80 | A | 710 | 1540 |  |  |  | 69
2025-09-22 | 4709 |  | L02_AREA_400_SAMP_001 | A | DONE | 52 | M-L |  | PROJECT DOVE 6240041 | VD , 1" DW | 2025-09-18 | Z | 2025-07-11 | 1210 | 0 | 70 | A | 600 | 1310 |  |  |  | 69
2025-09-23 | 4710 |  | L02_AREA_400_SAMP_002 | A | DONE | 67 | M-L |  | PROJECT DOVE 6240041 | VD , 1" DW | 2025-09-18 | Z | 2025-07-11 | 1590 | 0 | 70 | A | 740 | 1900 |  |  |  | 69
2025-09-23 | 4711 |  | L02_AREA_400_SAMP_003 | A | DONE | 44 | M-L |  | PROJECT DOVE 6240041 | VD , 1" DW | 2025-09-18 | Z | 2025-07-11 | 1030 | 0 | 70 | A | 520 | 1090 |  |  |  | 69
2025-09-23 | 4712 |  | L02_AREA_400_SAMP_004 | A | DONE | 65 | M-L |  | PROJECT DOVE 6240041 | VD , 1" DW | 2025-09-18 | Z | 2025-07-11 | 1550 | 0 | 70 | A | 720 | 1800 |  |  |  | 69
2025-09-27 | 4896 |  | 76354 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-02 | 30 | 0 | 0 |  | 0 | 200 |  | HANGERS |  | 37
2025-09-22 | 288 |  | 92225 | A | DONE | 2 | S |  | RAMC 2250044 |  | 2025-09-22 | Z | 2025-09-22 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2025-09-23 | 1351 |  | 68882 | A | DONE | 5 | S |  | RICHLAND CTR 6250011 |  | 2025-09-22 | Z | 2025-09-10 | 70 | 0 | 40 | A | 0 | 120 |  | EF-13 |  | 12
2025-09-22 | 1352 | sp | 68883 | A | DONE | 4 | S |  | RICHLAND CTR 6250011 |  | 2025-09-22 | Z | 2025-09-10 | 20 | 60 | 0 |  | 0 | 60 |  | EF-13 |  | 12
2025-09-23 | 1353 |  | 68884 | A | DONE | 2 | S |  | RICHLAND CTR 6250011 | 1/2" liner | 2025-09-22 | Z | 2025-09-10 | 40 | 0 | 0 |  | 40 | 50 |  | Bathroom TA |  | 12
2025-09-23 | 528 |  | 81672 | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 | 1" liner | 2025-09-22 | Z | 2025-08-27 | 80 | 0 | 0 |  | 70 | 100 |  | EF DROPS |  | 26
2025-09-22 | 532 |  | DH-002 | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 |  | 2025-09-22 | Z | 2025-09-11 | 20 | 0 | 0 |  | 0 | 60 |  | RTU-2-Hangers |  | 11
2025-09-25 | 1429 |  | 83850 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-09-23 | Z | 2025-09-10 | 20 | 0 | 0 |  | 0 | 30 |  | L4-RAMP-3 EL SHAFT |  | 13
2025-09-27 | 1430 |  | MER-EAMP 1 | A | DONE | 40 | M-L |  | UW-LEVY HALL 6230028 |  | 2025-10-02 | Z | 2025-09-10 | 430 | 0 | 550 |  | 0 | 1660 |  |  |  | 22
2025-09-24 | 1433 |  | 76115 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-09-23 | Z | 2025-09-16 | 40 | 0 | 0 |  | 0 | 80 |  | PH |  | 7
2025-09-22 | 1435 |  | 76118 | A | DONE | 6 | S |  | UW-LEVY HALL 6230028 | 1" liner | 2025-09-23 | Z | 2025-09-18 | 130 | 0 | 0 |  | 30 | 190 |  | E. PH Shaft |  | 5
2025-09-23 | 2878 | bth | 77351 - 77354 | A | DONE | 17 | M | PCD | UWRF 6230010 |  | 2025-09-23 | Z | 2025-09-04 | 180 | 140 | 90 | A | 0 | 490 |  | CD-131 , 122 |  | 19
2025-09-23 | 2879 | sp | 84876 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2025-09-23 | Z | 2025-09-04 | 30 | 110 | 0 |  | 0 | 140 |  | CD-122 |  | 19
2025-09-22 | 2880 | bth | 84877 - 84878 | A | DONE | 7 | S |  | UWRF 6230010 |  | 2025-09-23 | Z | 2025-09-04 | 70 | 100 | 0 |  | 0 | 180 |  | CD-128 |  | 19
2025-09-23 | 2881 | sp | 84879 | A | DONE | 3 | S-M | PCD | UWRF 6230010 |  | 2025-09-23 | Z | 2025-09-04 | 30 | 30 | 0 |  | 0 | 60 |  | CD-128 |  | 19
2025-09-22 | 2882 | sp | 84880 | A | DONE | 5 | S-M |  | UWRF 6230010 |  | 2025-09-23 | Z | 2025-09-04 | 30 | 80 | 0 |  | 0 | 100 |  | CD-122 |  | 19
2025-09-24 | 3099 | sp | 54539 | A | DONE | 2 | S |  | UW-VET MED 2250030 |  | 2025-09-23 | Z | 2025-09-17 | 20 | 0 | 0 |  | 0 | 20 |  | Testing |  | 6
2025-09-23 | 1652 |  | 73816 - 73817 , 75303 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | paint | 2025-09-19 | Z | 2025-09-16 | 150 | 0 | 0 |  | 70 | 260 |  | SOA Outs |  | 3
2025-09-23 | 1654 |  | PH_A_OA_005 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-19 | Z | 2025-09-17 | 90 | 0 | 0 |  | 0 | 170 |  |  |  | 2
2025-09-24 | 1655 |  | PH_A_OA_006 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 | VD | 2025-09-19 | Z | 2025-09-17 | 130 | 0 | 170 | A | 0 | 420 |  |  |  | 2
2025-09-25 | 1656 |  | PH_A_SAMP_001 | A | DONE | 19 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-19 | Z | 2025-09-17 | 320 | 0 | 150 | A | 0 | 890 |  |  |  | 2
2025-09-25 | 1657 |  | PH_A_SAMP_002 | A | DONE | 11 | M |  | WAUNAKEE MS 6230013 | CD | 2025-09-19 | Z | 2025-09-17 | 140 | 0 | 120 | A | 0 | 570 |  |  |  | 2
2025-09-25 | 1658 |  | PH_A_SAMP_003 | A | DONE | 12 | M |  | WAUNAKEE MS 6230013 | CD | 2025-09-19 | Z | 2025-09-17 | 240 | 0 | 60 | A | 0 | 530 |  |  |  | 2
2025-09-24 | 1659 |  | PH_A_SAMP_004 | A | DONE | 16 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-19 | Z | 2025-09-17 | 240 | 0 | 140 | A | 0 | 870 |  |  |  | 2
2025-09-25 | 1660 |  | PH_A_SAMP_005 | A | DONE | 8 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-19 | Z | 2025-09-17 | 190 | 0 | 0 |  | 0 | 410 |  |  |  | 2
2025-09-24 | 1661 |  | PH_A_SAMP_006 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-19 | Z | 2025-09-17 | 70 | 0 | 90 | A | 0 | 260 |  |  |  | 2
2025-09-24 | 1662 |  | PH_A_SAMP_007 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-19 | Z | 2025-09-17 | 130 | 0 | 130 | A | 0 | 350 |  |  |  | 2
[6 empty] | 1343 | [13 empty] | 47480 |  |  |  | 11750 | 24.75%
WEEK OF 9-29-2025
2025-10-03 | 2451 | w | 82706 - 82707 | A | done | 6 | S-M |  | ANTIGO ELEM. 6250017 |  | 2025-10-06 | Z | 2025-09-23 | 140 | 0 | 0 |  | 70 | 330 |  | 1st floor B,C,D Sleeves |  | 13
2025-10-02 | 589 |  | 84373 - 84374 | A | done | 10 | S-M |  | BARTILLION 6240024 | 1" liner | 2025-09-30 | Z | 2025-09-18 | 240 | 0 | 0 |  | 210 | 350 |  | A-V 2-1 |  | 12
2025-10-02 | 590 |  | 84375 | A | done | 2 | S |  | BARTILLION 6240024 |  | 2025-09-30 | Z | 2025-09-18 | 20 | 0 | 0 |  | 0 | 30 |  | RA 2nd tie in |  | 12
2025-10-01 | 591 | sp | 84376 | A | DONE | 4 | S |  | BARTILLION 6240024 |  | 2025-09-30 | Z | 2025-09-18 | 60 | 20 | 0 |  | 0 | 90 |  | A-V 2-7 |  | 12
2025-09-30 | 592 | sp | 84377 | A | DONE | 6 | S-M |  | BARTILLION 6240024 | 1" DW | 2025-09-30 | Z | 2025-09-23 | 30 | 120 | 0 |  | 30 | 130 |  | Replacement pay room |  | 7
2025-10-02 | 593 |  | 84378 | A | done | 5 | S |  | BARTILLION 6240024 | paint | 2025-09-30 | Z | 2025-09-24 | 110 | 0 | 0 |  | 120 | 160 |  | Grille boxes |  | 6
2025-10-02 | 594 |  | 84379 | A | done | 15 | S |  | BARTILLION 6240024 |  | 2025-09-30 | Z | 2025-09-24 | 360 | 0 | 0 |  | 0 | 870 |  | AHU-1 RA tie in |  | 6
2025-10-02 | 595 |  | 84380 | A | done | 2 | S |  | BARTILLION 6240024 |  | 2025-09-30 | Z | 2025-09-24 | 40 | 0 | 0 |  | 0 | 60 |  | Coil Mech Rm tie in |  | 6
2025-10-02 | 2904 | sp | 79535 - 79539 | A | done | 13 | M | pt.alum | BROOM ST. 6240033 |  | 2025-09-30 | Z | 2025-09-16 | 140 | 180 | 0 |  | 0 | 290 |  | L2/L3 E. WP Type 1-5 |  | 14
2025-09-29 | 2905 |  | 80915 | A | DONE | 88 | M-L |  | BROOM ST. 6240033 |  | 2025-09-29 | Z | 2025-09-22 | 2180 | 0 | 0 |  | 0 | 2400 |  | HP Covers |  | 7
2025-10-01 | 3547 | bth | 73818-22 | A | DONE | 59 | M |  | DELLSHIRE 6240017 |  | 2025-10-06 | Z | 2025-09-11 | 610 | 320 | 550 | A | 70 | 2050 |  |  |  | 25
2025-09-30 | 3548 |  | 73823 | A | DONE | 15 | S-M |  | DELLSHIRE 6240017 |  | 2025-09-29 | Z | 2025-09-18 | 220 | 20 | 130 | A | 0 | 500 |  | 242 SA |  | 11
2025-10-01 | 3549 | bth | 73793 - 73795 | A | DONE | 56 | M |  | DELLSHIRE 6240017 |  | 2025-09-29 | Z | 2025-09-18 | 320 | 740 | 330 | A | 0 | 1670 |  | SA |  | 11
2025-10-02 | 3591 | bth | 74003 | A | done | 8 | S-M |  | DELLSHIRE 6240017 |  | 2025-10-02 | Z | 2025-09-18 | 50 | 150 | 0 |  | 0 | 190 |  | VAV 8-4 , 7-A LP |  | 14
2025-10-03 | 3592 |  | 74002 | A | done | 24 | S-M |  | DELLSHIRE 6240017 |  | 2025-10-02 | Z | 2025-09-18 | 500 | 0 | 100 | A | 0 | 960 |  | Restaurant RA |  | 14
2025-10-03 | 3594 |  | 73797 | A | done | 19 | S-M |  | DELLSHIRE 6240017 |  | 2025-10-02 | Z | 2025-09-18 | 230 | 0 | 230 | A | 0 | 620 |  | Kitchen SA |  | 14
2025-09-29 | 4729 |  | 73924 | A | DONE | 2 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-23 | 20 | 0 | 0 |  | 0 | 60 |  | Sec. Bar Filler |  | 9
2025-10-01 | 4730 |  | 73925 | A | DONE | 9 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-23 | 220 | 0 | 0 |  | 0 | 280 |  | Flashing |  | 9
2025-09-30 | 4746 |  | EMAIL | A | DONE | 3 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-30 | 60 | 0 | 0 |  | 0 | 150 |  | Angles |  | 2
2025-09-29 | 1021 |  | ES SL-EA 2 | A | DONE | 12 | S-M |  | ES SEQUENCING 2250029 | flex | 2025-09-24 | Z | 2025-08-26 | 240 | 0 | 60 | A | 0 | 410 |  |  |  | 29
2025-09-29 | 1042 | bth | ES SL-EAT 1891 | A | DONE | 2 | S |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 29
2025-09-29 | 1048 | bth | ES SL-SAMP 1 | A | DONE | 9 | S |  | ES SEQUENCING 2250029 |  | 2025-09-24 | Z | 2025-08-26 | 160 | 30 | 30 | A | 0 | 330 |  |  |  | 29
2025-10-01 | 1307 |  | 56836 | A | DONE | 4 | S-M |  | EXACT SEQUENCER 2250029 |  | 2025-10-01 | Z | 2025-09-23 | 80 | 0 | 0 |  | 0 | 90 |  | BCU-4 RA |  | 8
2025-10-03 | 290 |  | 37572 | A | DONE | 2 | S |  | JOE S. 1000385 |  | 2025-10-03 | Z | 2025-09-25 | 30 | 0 | 0 |  | 0 | 80 |  | Misc |  | 8
2025-09-30 | 292 |  | 84298 | A | DONE | 6 | S | pt.ss | KEVIN M. 1000382 | paint | 2025-10-03 | Z | 2025-09-29 | 130 | 0 | 0 |  | 20 | 150 |  | Misc |  | 4
2025-10-03 | 292r |  | 84298 | A | DONE | 2 | S |  | KEVIN M. 1000382 |  | 2025-10-06 | Z | 2025-10-03 | 20 | 0 | 0 |  | 0 | 20 |  | 90 |  | 3
2025-09-29 | 2561 | bth | 69061 | A | DONE | 3 | S |  | LABCORP 6240016 | paint | 2025-10-02 | Z | 2025-09-26 | 50 | 20 | 0 |  | 30 | 60 |  | 1st floor office |  | 6
2025-10-01 | 1467 |  | TA-L1E-03 | A | DONE | 4 | S |  | MONROE HS 6240018 |  | 2025-09-30 | Z | 2025-09-09 | 100 | 0 | 0 |  | 90 | 140 |  |  |  | 21
2025-10-01 | 1468 | sp | EA-L1E-01 | A | DONE | 6 | S | pt.neal | MONROE HS 6240018 | flex | 2025-09-30 | Z | 2025-09-09 | 30 | 110 | 0 |  | 0 | 160 |  |  |  | 21
2025-10-02 | 1469 | bth | EA-L1E-02 | A | done | 27 | M | neal | MONROE HS 6240018 | VD's | 2025-09-30 | Z | 2025-09-09 | 230 | 440 | 0 |  | 40 | 810 |  |  |  | 21
2025-10-01 | 1470 |  | EA-L1E-03 | A | DONE | 4 | S |  | MONROE HS 6240018 |  | 2025-09-30 | Z | 2025-09-09 | 90 | 0 | 0 |  | 0 | 120 |  |  |  | 21
2025-10-01 | 1471 | bth | EA-L1E-04 | A | DONE | 8 | S | pt.alum | MONROE HS 6240018 |  | 2025-09-30 | Z | 2025-09-09 | 90 | 20 | 70 | A | 0 | 210 |  |  |  | 21
2025-10-01 | 1472 | bth | EA-L1E-05 | A | DONE | 9 | S |  | MONROE HS 6240018 |  | 2025-09-30 | Z | 2025-09-09 | 140 | 80 | 0 |  | 0 | 240 |  |  |  | 21
2025-10-01 | 1473 |  | RA-L1E-01 | A | DONE | 28 | M-L |  | MONROE HS 6240018 | 1" liner | 2025-09-30 | Z | 2025-09-09 | 290 | 0 | 400 | A | 620 | 1330 |  |  |  | 21
2025-10-01 | 1474 |  | RA-L1E-02 | A | DONE | 22 | M |  | MONROE HS 6240018 | 1" liner | 2025-09-30 | Z | 2025-09-09 | 350 | 0 | 200 | A | 430 | 850 |  |  |  | 21
2025-10-01 | 1475 |  | RA-L1E-03 | A | DONE | 25 | M-L |  | MONROE HS 6240018 | 1" liner | 2025-09-30 | Z | 2025-09-09 | 320 | 0 | 300 | A | 550 | 1360 |  |  |  | 21
2025-10-02 | 1476 |  | RA-L1E-04 | A | done | 31 | M-L |  | MONROE HS 6240018 | 1" liner | 2025-09-30 | Z | 2025-09-09 | 310 | 0 | 450 | A | 680 | 1560 |  |  |  | 21
2025-10-01 | 1477 |  | RA-L1E-05 | A | DONE | 46 | M-L |  | MONROE HS 6240018 | 1" liner | 2025-09-30 | Z | 2025-09-09 | 750 | 0 | 390 | A | 860 | 2040 |  |  |  | 21
2025-10-03 | 1480 |  | 83614 | A | done | 2 | S | neal | MONROE HS 6240018 |  | 2025-10-01 | Z | 2025-09-18 | 20 | 0 | 0 |  | 0 | 60 |  | CGS Skuttle |  | 13
2025-10-01 | 3022 | sp | SAMP-L2E-05 | A | DONE | 20 | M | neal | MONROE HS 6240018 |  | 2025-09-30 | Z | 2025-07-24 | 120 | 380 | 0 |  | 0 | 590 |  |  |  | 68 | 2025-08-12
2025-10-02 | 3023 | bth | SAMP-L2E-01 | A | done | 20 | M | pt.neal | MONROE HS 6240018 | 2" liner | 2025-09-30 | Z | 2025-07-24 | 170 | 310 | 0 |  | 60 | 600 |  |  |  | 68 | 2025-08-12
2025-10-02 | 3024 | bth | SALP-L2E-09 | A | done | 18 | M-L | neal | MONROE HS 6240018 | partial,s.mates,2" liner | 2025-09-30 | Z | 2025-07-24 | 160 | 0 | 270 | A | 370 | 790 |  |  |  | 68 | 2025-08-12
2025-10-02 | 3025 |  | SALP-L2E-02 | A | done | 37 | M-L | pt.neal | MONROE HS 6240018 | 2" liner | 2025-09-30 | Z | 2025-07-24 | 810 | 0 | 110 | A | 650 | 1510 |  |  |  | 68 | 2025-08-12
2025-10-02 | 3026 |  | RA-L2E-04 | A | done | 23 | M | pt.neal | MONROE HS 6240018 | 1" liner | 2025-09-30 | Z | 2025-07-24 | 510 | 0 | 60 | A | 500 | 1180 |  |  |  | 68 | 2025-08-12
2025-10-02 | 3027 |  | RA-L2E-02 | A | done | 25 | M |  | MONROE HS 6240018 | CD's , 1" liner | 2025-09-30 | Z | 2025-07-24 | 620 | 0 | 0 |  | 390 | 1280 |  |  |  | 68 | 2025-08-12
2025-10-03 | 3905 |  | 85344 | A | done | 10 | S-M |  | MONROE HS 6240018 |  | 2025-10-01 | Z | 2025-09-19 | 240 | 0 | 0 |  | 0 | 510 |  | F2 Mech |  | 12
2025-10-03 | 3906 |  | 85345 | A | done | 2 | S |  | MONROE HS 6240018 |  | 2025-10-01 | Z | 2025-09-19 | 30 | 0 | 0 |  | 0 | 50 |  | F2 Mech |  | 12
2025-10-03 | 3907 |  | 85346 | A | done | 2 | S |  | MONROE HS 6240018 |  | 2025-10-01 | Z | 2025-09-19 | 30 | 0 | 0 |  | 20 | 50 |  | 1st floor |  | 12
2025-10-03 | 3908 |  | 85347 | A | done | 4 | S | neal | MONROE HS 6240018 |  | 2025-10-01 | Z | 2025-09-19 | 100 | 0 | 0 |  | 0 | 160 |  | Flashing |  | 12
2025-10-01 | 3267 |  | 79542 | A | DONE | 2 | S |  | ONE 09 6240037 |  | 2025-10-07 | Z | 2025-09-30 | 20 | 0 | 0 |  | 20 | 30 |  | Grille boxes |  | 7
2025-10-01 | 3268 |  | 79543 | A | DONE | 2 | S |  | ONE09 6240037 |  | 2025-10-06 | Z | 2025-10-01 | 20 | 0 | 0 |  | 0 | 40 |  | ERV-1 |  | 5
2025-09-29 | 824 | sp | 76739 | A | DONE | 12 | S-M | neal | PEWAUKEE HS 6240030 |  | 2025-09-24 | Z | 2025-09-05 | 0 | 290 | 0 |  | 0 | 390 |  | DC drops |  | 19
2025-09-29 | 831 |  | 76740 | A | DONE | 8 | S | neal | PEWAUKEE HS 6240030 | bird s. | 2025-09-24 | Z | 2025-09-10 | 190 | 0 | 0 |  | 160 | 400 |  | MAU-1 |  | 14
2025-09-29 | 832 | bth | 76742 , 76744 - 76745 | A | DONE | 4 | S-M | neal | PEWAUKEE HS 6240030 | CD's | 2025-09-24 | Z | 2025-09-10 | 60 | 20 | 0 |  | 0 | 100 |  | RE Drops |  | 14
2025-10-02 | 836 | bth | 76773 | A | done | 2 | S | neal | PEWAUKEE HS 6240030 | flex | 2025-10-01 | Z | 2025-09-19 | 30 | 20 | 0 |  | 0 | 70 |  | BCU-2 |  | 12
2025-10-03 | 837 |  | 76750 | A | done | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-10-01 | Z | 2025-09-22 | 50 | 0 | 0 |  | 0 | 60 |  | BCU-2 OA |  | 9
2025-09-30 | 838 |  | 76811 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-10-01 | Z | 2025-09-22 | 20 | 0 | 0 |  | 0 | 20 |  | Spark Det. Brackets |  | 9
2025-10-03 | 839 |  | 76812 | A | done | 2 | S |  | PEWAUKEE HS 6240030 | CD's | 2025-10-01 | Z | 2025-09-24 | 20 | 0 | 0 |  | 20 | 30 |  | RE CD's |  | 7
2025-09-29 | 840 | sp | 76814 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | flex | 2025-10-01 | Z | 2025-09-29 | 20 | 20 | 0 |  | 0 | 60 |  | UE-2 |  | 2
| 903 |  | L02_600_EA_004 | delete |  |  | n/a |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-09-30 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 16
2025-10-02 | 916 |  | 76366 | A | DONE | 2 | S-M | ss | PROJECT DOVE 6240041 |  | 2025-10-06 | Z | 2025-10-02 | 50 | 0 | 0 |  | 0 | 110 |  | Flat stock |  | 4
2025-10-03 | 918 |  | 76367 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-03 | Z | 2025-10-03 | 20 | 0 | 0 |  | 0 | 70 |  | L02 700 SAMP-3 |  | 0
2025-10-02 | 1607 | w | L02_AREA_700_WEST_RAMP_006 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-04 | 50 | 0 | 0 |  | 0 | 110 |  |  |  | 28
2025-10-02 | 1617 |  | 76265 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-17 | 30 | 0 | 0 |  | 0 | 50 |  | Office 052 |  | 15
2025-09-30 | 1631 |  | 76176 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" DW | 2025-09-29 | Z | 2025-09-17 | 30 | 0 | 0 |  | 20 | 30 |  | 400 AHU-7D |  | 12
2025-10-03 | 1634 |  | 76175 | A | done | 9 | S |  | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-19 | 140 | 0 | 80 | A | 0 | 430 |  | Roof Drops |  | 13
2025-10-03 | 1635 |  | 76177 - 76178 | A | done | 19 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-10-02 | Z | 2025-09-19 | 460 | 0 | 0 |  | 0 | 1410 |  | 900 Louver duct |  | 13
2025-10-03 | 1636 |  | 76179 - 76181 | A | done | 12 | S-M |  | PROJECT DOVE 6240041 | bird s. | 2025-10-02 | Z | 2025-09-19 | 290 | 0 | 0 |  | 0 | 560 |  | Roof Drops |  | 13
2025-10-03 | 1639 |  | 76182 | A | done | 4 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-10-02 | Z | 2025-09-22 | 80 | 0 | 0 |  | 0 | 120 |  | Roof drops |  | 10
2025-10-03 | 1645 |  | 76273 | A | done | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-24 | 20 | 0 | 0 |  | 0 | 20 |  | 052 RA 001 |  | 8
2025-09-30 | 1647 | sp | 76276 - 76277 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-25 | 30 | 60 | 0 |  | 0 | 100 |  | Waste water / Mezz 052 |  | 7
2025-10-01 | 1631r |  | 76176 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | 1" DW | 2025-10-02 | Z | 2025-10-01 | 40 | 0 | 0 |  | 20 | 80 |  | 400 AHU-7D |  | 1
2025-10-01 | 293 |  | 84741 | A | DONE | 2 | S |  | STOUGHTON HEALTH 4250039 |  | 2025-10-06 | Z | 2025-09-30 | 20 | 0 | 0 |  | 0 | 30 |  | VAV 1-9 |  | 6
2025-09-29 | 531 |  | 81673 | A | DONE | 11 | M |  | SW HEALTH MOB 6250015 |  | 2025-09-30 | Z | 2025-09-10 | 270 | 0 | 0 |  | 0 | 790 |  | RTU-1 Drop |  | 20 | 2025-10-06
2025-09-30 | 543 |  | PRE-FAB HANGERS | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 |  | 2025-09-29 | Z | 2025-09-18 | 20 | 0 | 0 |  | 0 | 30 |  | DH-0004 Tear drop |  | 11
2025-10-01 | 4677 |  | 82235 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-15 | 30 | 0 | 0 |  | 0 | 40 |  | Ex Drops |  | 14
2025-09-30 | 4678 | bth | EXP-EA-01 | A | DONE | 5 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 50 | 50 | 20 | A | 0 | 140 |  |  |  | 13
2025-09-29 | 4679 | sp | EXP-EA-02 | A | DONE | 3 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 13
2025-09-29 | 4680 | sp | EXP-EA-03 | A | DONE | 3 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 13
2025-09-29 | 4681 | sp | EXP-EA-04 | A | DONE | 5 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 13
2025-10-01 | 4682 | bth | EXP-SALP-01 | A | DONE | 15 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 200 | 0 | 170 | A | 0 | 480 |  |  |  | 13
2025-10-01 | 4683 | sp | EXP-SALP-02 | A | DONE | 4 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 30 | 70 | 0 |  | 0 | 100 |  |  |  | 13
2025-09-30 | 4684 | bth | EXP-SALP-03 | A | DONE | 8 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 120 | 40 | 40 | A | 0 | 240 |  |  |  | 13
2025-10-01 | 4685 | bth | EXP-SALP-04 | A | DONE | 4 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 50 | 30 | 0 |  | 0 | 90 |  |  |  | 13
2025-09-30 | 4686 | bth | EXP-SALP-05 | A | DONE | 5 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 40 | 40 | 30 | A | 0 | 120 |  |  |  | 13
2025-10-01 | 4687 | bth | EXP-SALP-06 | A | DONE | 5 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 90 | 0 | 30 | A | 0 | 170 |  |  |  | 13
2025-09-30 | 4688 | sp | EXP-SALP-07 | A | DONE | 6 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 50 | 80 | 0 |  | 0 | 130 |  |  |  | 13
2025-09-29 | 4689 | sp | EXP-SALP-08 | A | DONE | 4 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 40 | 50 | 0 |  | 0 | 90 |  |  |  | 13
2025-09-30 | 4690 | bth | EXP-SALP-09 | A | DONE | 6 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 80 | 0 | 50 | A | 0 | 180 |  |  |  | 13
2025-09-29 | 4691 | sp | EXP-SALP-10 | A | DONE | 3 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 20 | 40 | 0 |  | 0 | 40 |  |  |  | 13
2025-10-01 | 4692 | bth | EXP-SALP-13 | A | DONE | 13 | S-M |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 210 | 0 | 100 | A | 0 | 390 |  |  |  | 13
2025-09-29 | 4693 | sp | EXP-EA-05 | A | DONE | 3 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 13
2025-10-01 | 4694 |  | EXP-EA-06 | A | DONE | 5 | S |  | TOMAH HEALTH 6250006 |  | 2025-09-29 | Z | 2025-09-16 | 70 | 0 | 50 | A | 0 | 150 |  |  |  | 13
2025-10-02 | 4697 |  | 82238 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-10-06 | Z | 2025-10-02 | 20 | 0 | 0 |  | 0 | 20 |  | TAB-1766 |  | 4
2025-10-03 | 3112 |  | 69062 | A | done | 2 | S |  | UW-AVRL 6240038 |  | 2025-10-06 | Z | 2025-09-29 | 20 | 0 | 0 |  | 0 | 40 |  | BSL-3 Testing |  | 7
2025-10-03 | 3113 |  | HAND DRAWN | A | done | 2 | S | ss | UW-AVRL 6240038 |  | 2025-10-01 | Z | 2025-10-01 | 20 | 0 | 0 |  | 0 | 50 |  | Offset |  | 0
2025-10-03 | 3114 |  | 69063 | A | done | 2 | S |  | UW-AVRL 6240038 |  | 2025-10-06 | Z | 2025-10-02 | 20 | 0 | 0 |  | 0 | 20 |  | BSL-3 Lab |  | 4
2025-09-29 | 1411 |  | MER-RAMP 4 | A | DONE | 19 | M |  | UW-LEVY HALL 6230028 |  | 2025-09-25 | Z | 2025-08-19 | 410 | 0 | 70 | A | 0 | 940 |  |  |  | 37
2025-09-30 | 1412 |  | MER-RAMP 1 | A | DONE | 88 | L |  | UW-LEVY HALL 6230028 | MOD's | 2025-09-25 | Z | 2025-08-19 | 2190 | 0 | 0 |  | 0 | 6030 |  |  |  | 37
2025-10-03 | 1417 |  | MER-RAMP 3 | A | done | 55 | L |  | UW-LEVY HALL 6230028 |  | 2025-10-02 | Z | 2025-08-26 | 620 | 0 | 750 | A | 0 | 2690 |  |  |  | 37
2025-10-03 | 1418 |  | MER-RAMP 5 | A | done | 33 | S-M |  | UW-LEVY HALL 6230028 | partial | 2025-10-02 | Z | 2025-08-26 | 510 | 0 | 300 | A | 0 | 1570 |  |  |  | 37
2025-10-01 | 1434 | bth | 82992 | A | DONE | 9 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-09-30 | Z | 2025-09-17 | 90 | 120 | 0 |  | 0 | 200 |  | L3 EAMP Wall drops |  | 13
2025-09-29 | 1443 |  | 82993 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-09-30 | Z | 2025-09-19 | 20 | 0 | 0 |  | 0 | 20 |  | L4 EAMP 1 |  | 11
2025-09-30 | 4803 |  | 76119 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-10-02 | Z | 2025-09-22 | 20 | 0 | 0 |  | 0 | 90 |  | FSD 12,13 Extensions |  | 10
2025-09-30 | 3273 |  | 38173 - 38175 | A | DONE | 2 | S-M |  | UWSP ALBERTSON 6230016 | flex | 2025-09-30 | Z | 2025-09-19 | 50 | 0 | 0 |  | 0 | 80 |  | BCU-2 |  | 11
2025-10-02 | 3274 |  | 81351 | A | done | 2 | S |  | UWSP ALBERTSON 6230016 | flex , VD's | 2025-09-30 | Z | 2025-09-25 | 50 | 0 | 0 |  | 0 | 60 |  | 1st floor |  | 5
2025-10-01 | 3123 |  | 84299 | A | DONE | 8 | S-M | ss | UW-VET MED 2250030 |  | 2025-10-01 | Z | 2025-10-01 | 200 | 0 | 0 |  | 0 | 350 |  | Angles |  | 0
2025-10-03 | 3122 |  | 54543 | A | DONE | 2 | S |  | UW-VET MED 6210014 | flex | 2025-10-03 | Z | 2025-09-26 | 20 | 0 | 0 |  | 0 | 20 |  | 1st Hall |  | 7
2025-09-29 | 1509 | sp/w | 79890 - 79891 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | angle rings | 2025-09-05 | Z | 2025-08-18 | 80 | 50 | 0 |  | 0 | 260 |  | DC-1 |  | 18
2025-09-29 | 1510 | sp/w | 79892 , 79895 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 | angle rings | 2025-09-05 | Z | 2025-08-18 | 50 | 50 | 0 |  | 0 | 250 |  | DC-2 |  | 18
2025-09-30 | 1653 |  | 73769 , 73772 | A | DONE | 3 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-17 | 60 | 0 | 0 |  | 0 | 80 |  | 2nd RA tie ins |  | 9
2025-09-30 | 1663 |  | 73774 - 73776 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 | paint | 2025-09-26 | Z | 2025-09-17 | 330 | 0 | 0 |  | 300 | 480 |  | 1st tie in |  | 9
2025-09-30 | 1664 |  | PH_A_OA_001 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-18 | 220 | 0 | 0 |  | 0 | 480 |  |  |  | 8
2025-09-29 | 1665 |  | PH_A_OA_002 | A | DONE | 18 | M |  | WAUNAKEE MS 6230013 | CD's | 2025-09-26 | Z | 2025-09-18 | 450 | 0 | 0 |  | 0 | 1120 |  |  |  | 8
2025-09-30 | 1666 |  | PH_A_OA_003 | A | DONE | 18 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-18 | 60 | 0 | 390 | A | 0 | 980 |  |  |  | 8
2025-09-30 | 1667 |  | PH_A_OA_004 | A | DONE | 13 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-18 | 190 | 0 | 130 | A | 0 | 820 |  |  |  | 8
2025-09-30 | 1668 |  | PH_A_SOA_001 | A | DONE | 21 | M-L |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-18 | 450 | 0 | 60 | A | 0 | 980 |  |  |  | 8
2025-09-29 | 1669 |  | PH_A_SOA_002 | A | DONE | 16 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-18 | 170 | 0 | 230 | A | 0 | 590 |  |  |  | 8
2025-09-30 | 1670 |  | PH_A_EA_001 | A | DONE | 21 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-18 | 460 | 0 | 60 | A | 0 | 880 |  |  |  | 8
2025-09-30 | 1671 |  | PH_A_EA_002 | A | DONE | 17 | M |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-18 | 250 | 0 | 170 | A | 0 | 690 |  |  |  | 8
2025-09-30 | 1672 |  | PH_A_EA_003 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-18 | 240 | 0 | 0 |  | 0 | 520 |  |  |  | 8
2025-10-03 | 1695 | bth | L01_A_EAD_002 | L | done | 8 | S | alum | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 50 | 50 | 100 | A | 0 | 130 |  |  |  | 14
2025-10-03 | 1696 | sp | L01_A_EAD_003 | L | done | 5 | S | alum | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 40 | 70 | 0 |  | 0 | 90 |  |  |  | 14
2025-10-03 | 2312 | w | L01_A_GEA_001 | A | DONE | 6 | S-M | BI | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 130 | 0 | 0 |  | 0 | 460 |  |  |  | 14
2025-10-03 | 2313 | w | L01_A_GEA_002 | A | DONE | 6 | S-M | BI | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 130 | 0 | 0 |  | 0 | 390 |  |  |  | 14
2025-09-30 | 2357 |  | 75353 | F | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-09-26 | Z | 2025-09-25 | 30 | 0 | 0 |  | 0 | 50 |  | L02 SAMP PH |  | 1
2025-09-29 | 291 |  | EMAIL | A | DONE | 2 | S |  | WSCC 8240004 |  | 2025-09-29 | Z | 2025-09-29 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 0
[6 empty] | 1402 | [13 empty] | 57210
WEEK OF 10-06-2025
2025-10-08 | 596 | sp | 74801 | A | DONE | 2 | S | ss | BARTILLION 6240024 |  | 2025-10-07 | Z | 2025-10-07 | 10 | 0 | 0 |  | 0 | 100 |  | Rolled spiral |  | 0
2025-10-08 | 597 |  | 84381 | A | DONE | 2 | S |  | BARTILLION 6240024 | 1" liner | 2025-10-16 | Z | 2025-10-08 | 40 | 0 | 0 |  | 30 | 60 |  | A.V. 2-1 |  | 8
2025-10-08 | 3590 | bth | 73824 | A | DONE | 37 | S-M |  | DELLSHIRE 6240017 |  | 2025-10-06 | Z | 2025-09-18 | 50 | 40 | 830 | A | 0 | 1300 |  | Corr. 237 SA |  | 18
2025-10-08 | 3593 |  | 73796 | A | DONE | 16 | S-M |  | DELLSHIRE 6240017 |  | 2025-10-06 | Z | 2025-09-18 | 200 | 0 | 200 | A | 0 | 590 |  | Kitchen Riser |  | 18
2025-10-08 | 3595 |  | 74051 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-10-09 | Z | 2025-09-25 | 30 | 0 | 0 |  | 0 | 40 |  | 2nd Floor Elevator |  | 14
2025-10-06 | 2224 |  | Z3-EA 64 | A | DONE | 17 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-10 | 200 | 0 | 210 | A | 0 | 540 |  |  |  | 22
2025-10-06 | 2225 |  | Z3-EA 65 | A | DONE | 19 | M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-10 | 410 | 0 | 50 | A | 0 | 670 |  |  |  | 22
2025-10-07 | 2233 |  | Z3-EA 83 | A | DONE | 15 | S-M |  | DOC JDC 6240023 | VD | 2025-10-16 | Z | 2025-09-10 | 290 | 0 | 70 | A | 0 | 480 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-06 | 2234 |  | Z3-EA 84 | A | DONE | 9 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-10 | 160 | 0 | 60 | A | 0 | 300 |  |  |  | 22
2025-10-07 | 2235 |  | Z3-EA 85 | A | DONE | 7 | S |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-10 | 80 | 0 | 90 | A | 0 | 220 |  |  |  | 22
2025-10-07 | 2236 |  | Z3-EA 86 | A | DONE | 8 | S |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-10 | 80 | 30 | 90 | A | 0 | 240 |  |  |  | 22
2025-10-07 | 2237 |  | Z3-EA 87 | A | DONE | 8 | S |  | DOC JDC 6240023 | VD | 2025-10-02 | Z | 2025-09-10 | 100 | 0 | 100 | A | 0 | 240 |  |  |  | 22
2025-10-07 | 2238 |  | Z3-EA 88 | A | DONE | 12 | S-M |  | DOC JDC 6240023 | VD | 2025-10-02 | Z | 2025-09-10 | 240 | 0 | 40 | A | 0 | 370 |  |  |  | 22
2025-10-06 | 2239 |  | Z3-EA 89.5 | A | DONE | 11 | S-M |  | DOC JDC 6240023 | VD | 2025-10-02 | Z | 2025-09-10 | 190 | 0 | 70 | A | 0 | 370 |  |  |  | 22
2025-10-06 | 2240 |  | Z3-EA 89 | A | DONE | 17 | S-M |  | DOC JDC 6240023 | VD's | 2025-10-02 | Z | 2025-09-10 | 340 | 0 | 70 | A | 0 | 480 |  |  |  | 22
2025-10-06 | 3184 | bth | Z3-SAMP 39 | A | DONE | 10 | S-M |  | DOC JDC 6240023 |  | 2025-10-09 | Z | 2025-09-18 | 150 | 80 | 0 |  | 0 | 330 |  |  |  | 21 | 2025-10-02
2025-10-06 | 3185 | bth | Z3-SAMP 40 | A | DONE | 19 | M |  | DOC JDC 6240023 |  | 2025-10-09 | Z | 2025-09-18 | 140 | 50 | 280 |  | 0 | 720 |  |  |  | 21 | 2025-10-02
2025-10-06 | 3186 | bth | Z3-SAMP 41 | A | DONE | 21 | M |  | DOC JDC 6240023 |  | 2025-10-09 | Z | 2025-09-18 | 170 | 60 | 280 |  | 0 | 760 |  |  |  | 21 | 2025-10-02
2025-10-06 | 3187 | bth | Z3-SAMP 42 | A | DONE | 20 | M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-18 | 410 | 20 | 50 | A | 0 | 630 |  |  |  | 14
2025-10-06 | 3188 | bth | Z3-SAMP 43.5 | A | DONE | 11 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-18 | 130 | 30 | 110 | A | 0 | 340 |  |  |  | 14
2025-10-06 | 3189 |  | Z3-SAMP 43 | A | DONE | 10 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-18 | 150 | 0 | 90 | A | 0 | 330 |  |  |  | 14
2025-10-06 | 3190 | bth | Z3-SAMP 44 | A | DONE | 16 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-18 | 110 | 130 | 160 | A | 0 | 460 |  |  |  | 14
2025-10-07 | 3191 | bth | Z3-SAMP 45 | A | DONE | 15 | S-M |  | DOC JDC 6240023 |  | 2025-10-02 | Z | 2025-09-18 | 170 | 40 | 150 | A | 0 | 450 |  |  |  | 14
2025-10-08 | 4750 |  | 74802 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-10-08 | Z | 2025-10-08 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2025-10-09 | 1308 | sp | 56837 - 56839 | A | DONE | 6 | S-M |  | EXACT SEQUENCER 2250029 |  | 2025-10-08 | Z | 2025-09-30 | 120 | 30 | 0 |  | 0 | 170 |  | FCU 1800 C SA |  | 8
2025-10-09 | 3237 |  | 69994 | A | DONE | 2 | S |  | HISTOSONIC 6250009 | VD | 2025-10-10 | Z | 2025-10-08 | 30 | 0 | 0 |  | 0 | 40 |  | Return |  | 2
2025-10-09 | 1481 | bth | SAMP-L2E-02 | A | DONE | 9 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-10-08 | Z | 2025-09-18 | 130 | 20 | 70 | A | 130 | 400 |  |  |  | 20
2025-10-10 | 1482 | bth | SAMP-L2E-03 | A | DONE | 19 | M |  | MONROE HS 6240018 |  | 2025-10-08 | Z | 2025-09-18 | 110 | 80 | 270 | A | 0 | 630 |  |  |  | 20
2025-10-09 | 1483 | bth | SAMP-L2E-04 | A | DONE | 14 | S-M |  | MONROE HS 6240018 |  | 2025-10-08 | Z | 2025-09-18 | 150 | 120 | 80 | A | 0 | 420 |  |  |  | 20
2025-10-09 | 1484 | bth | SALP-L2E-01 | A | DONE | 5 | S-M |  | MONROE HS 6240018 | flex | 2025-10-08 | Z | 2025-09-18 | 200 | 10 | 0 |  | 100 | 320 |  |  |  | 20
2025-10-09 | 1485 |  | SALP-L2E-03 | A | DONE | 3 | S |  | MONROE HS 6240018 | 2" liner | 2025-10-08 | Z | 2025-09-18 | 60 | 0 | 0 |  | 50 | 100 |  |  |  | 20
2025-10-09 | 1486 | bth | SALP-L2E-04 | A | DONE | 21 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-10-08 | Z | 2025-09-18 | 210 | 60 | 240 | A | 330 | 660 |  |  |  | 20
2025-10-10 | 1487 | bth | SALP-L2E-05 | A | DONE | 19 | M |  | MONROE HS 6240018 | 2" liner | 2025-10-08 | Z | 2025-09-18 | 230 | 60 | 190 | A | 250 | 680 |  |  |  | 20
2025-10-10 | 1488 | bth | SALP-L2E-06 | A | DONE | 11 | S-M |  | MONROE HS 6240018 | 2" liner | 2025-10-08 | Z | 2025-09-18 | 60 | 100 | 110 | A | 140 | 340 |  |  |  | 20
2025-10-10 | 1489 | bth | SALP-L2E-07 | A | DONE | 13 | S-M | neal | MONROE HS 6240018 | 2" liner | 2025-10-08 | Z | 2025-09-18 | 180 | 130 | 0 |  | 100 | 430 |  |  |  | 20
2025-10-08 | 1490 | sp | SALP-L2E-08 | A | DONE | 11 | S | neal | MONROE HS 6240018 |  | 2025-10-08 | Z | 2025-09-18 | 30 | 230 | 0 |  | 0 | 300 |  |  |  | 20
2025-10-10 | 1491 |  | RA-L2E-03 | A | DONE | 22 | M |  | MONROE HS 6240018 | CD's , 1" liner | 2025-10-08 | Z | 2025-09-18 | 490 | 0 | 60 | A | 240 | 1040 |  |  |  | 20
2025-10-10 | 1492 |  | RA-L2E-01 | A | DONE | 12 | M |  | MONROE HS 6240018 | 1" liner | 2025-10-08 | Z | 2025-09-18 | 300 | 0 | 0 |  | 270 | 904 |  |  |  | 20
2025-10-10 | 1493 |  | RA-L2E-05 | A | DONE | 25 | M | neal | MONROE HS 6240018 | 1" liner | 2025-10-08 | Z | 2025-09-18 | 200 | 0 | 420 | A | 520 | 1290 |  |  |  | 20
2025-10-10 | 1494 |  | RA-L2E-06 | A | DONE | 19 | M |  | MONROE HS 6240018 | 1" liner | 2025-10-08 | Z | 2025-09-18 | 210 | 0 | 250 | A | 410 | 870 |  |  |  | 20
2025-10-10 | 1495 | bth | EA-L2E-01 | A | DONE | 10 | S-M |  | MONROE HS 6240018 | flex , 1" liner | 2025-10-08 | Z | 2025-09-18 | 220 | 10 | 0 |  | 80 | 350 |  |  |  | 20
2025-10-10 | 1496 |  | EA-L2E-02 | A | DONE | 7 | S |  | MONROE HS 6240018 | CD , 1" liner | 2025-10-08 | Z | 2025-09-18 | 120 | 0 | 50 | A | 90 | 210 |  |  |  | 20
2025-10-10 | 1498 |  | EA-L2E-04 | A | DONE | 4 | S |  | MONROE HS 6240018 | CD | 2025-10-08 | Z | 2025-09-18 | 90 | 0 | 0 |  | 0 | 120 |  |  |  | 20
2025-10-07 | 1499 | sp | EA-L2E-05 | A | DONE | 11 | S-M | neal | MONROE HS 6240018 |  | 2025-10-08 | Z | 2025-09-18 | 30 | 240 | 0 |  | 0 | 310 |  |  |  | 20
2025-10-10 | 3900 |  | EA-L2E-06 | A | DONE | 5 | S |  | MONROE HS 6240018 | CD | 2025-10-08 | Z | 2025-09-18 | 60 | 20 | 30 | A | 0 | 140 |  |  |  | 20
2025-10-10 | 3901 |  | OA-L2E-01 | A | DONE | 14 | S-M |  | MONROE HS 6240018 | flex , CD | 2025-10-08 | Z | 2025-09-18 | 230 | 0 | 120 | A | 0 | 440 |  |  |  | 20
2025-10-10 | 3902 |  | OA-L2E-02 | A | DONE | 17 | M |  | MONROE HS 6240018 | CD | 2025-10-08 | Z | 2025-09-18 | 260 | 0 | 150 | A | 0 | 900 |  |  |  | 20
2025-10-10 | 3903 |  | OA-L2E-03 | A | DONE | 25 | M-L |  | MONROE HS 6240018 | CD | 2025-10-08 | Z | 2025-09-18 | 360 | 0 | 250 | A | 0 | 1150 |  |  |  | 20
2025-10-10 | 3904 |  | TA-L2E-01 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-10-08 | Z | 2025-09-18 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 20
2025-10-09 | 3909 |  | 85348 - 85350 | A | DONE | 9 | S-M | pt.neal | MONROE HS 6240018 |  | 2025-10-08 | Z | 2025-09-29 | 203 | 0 | 0 |  | 0 | 320 |  | L2-A,F,L1-C |  | 9
2025-10-10 | 3910 |  | 83751 - 83752 | A | DONE | 15 | S-M |  | MONROE HS 6240018 |  | 2025-10-08 | Z | 2025-09-29 | 130 | 0 | 0 |  | 0 | 380 |  | L2-A , L2-C |  | 9
2025-10-10 | 3911 |  | 83753 | A | DONE | 7 | S | neal | MONROE HS 6240018 | 1" liner | 2025-10-08 | Z | 2025-09-29 | 20 | 70 | 70 | A | 0 | 180 |  | L1-F |  | 9
2025-10-09 | 3912 | w/sp | 83754 | A | DONE | 14 | S-M |  | MONROE HS 6240018 | bird s. ,1" DB | 2025-10-08 | Z | 2025-09-30 | 80 | 270 | 0 |  | 0 | 380 |  | Boiler Intake |  | 8
2025-10-09 | 841 |  | 76775 , 76778 | A | DONE | 3 | S-M |  | PEWAUKEE HS 6240030 | 2" liner | 2025-10-08 | Z | 2025-09-29 | 70 | 0 | 0 |  | 50 | 140 |  | RAHU-2 SA |  | 9
2025-10-08 | 842 | sp | 76813 , 76815 | A | DONE | 4 | S-M |  | PEWAUKEE HS 6240030 | flex | 2025-10-08 | Z | 2025-09-29 | 20 | 70 | 0 |  | 0 | 110 |  | UE-1 |  | 9
2025-10-09 | 843 |  | 76780 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 | 1" liner | 2025-10-08 | Z | 2025-09-29 | 60 | 0 | 0 |  | 60 | 170 |  | RAMP tie in |  | 9
2025-10-07 | 844 |  | 76817 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-10-13 | Z | 2025-10-02 | 10 | 0 | 0 |  | 0 | 20 |  | Kilm room flashing |  | 11
2025-10-09 | 845 |  | 76781 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | oval | 2025-10-13 | Z | 2025-10-03 | 20 | 0 | 0 |  | 0 | 90 |  | High pressure SAMP |  | 10
2025-10-07 | 846 |  | 76818 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-10-13 | Z | 2025-10-06 | 50 | 0 | 0 |  | 0 | 110 |  | Flashing |  | 7
2025-10-06 | 4615r | sp | 84300 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-10-07 | Z | 2025-10-06 | 10 | 0 | 0 |  | 0 | 40 |  | Piece #13-remake |  | 1
2025-10-09 | 915 | sp | 76302 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-10-01 | 30 | 30 | 0 |  | 0 | 90 |  |  |  | 8
2025-10-07 | 919 | w | 76185 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 | birdscreen | 2025-10-08 | Z | 2025-10-06 | 30 | 0 | 0 |  | 0 | 90 |  | Area 200 ss |  | 2
2025-10-08 | 920 | w | L01_AREA_200_MA_001 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 | vd | 2025-10-08 | Z | 2025-10-06 | 90 | 0 | 0 |  | 0 | 220 |  |  |  | 2
2025-10-07 | 922 |  | 76188 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 | birdscreen | 2025-10-09 | Z | 2025-10-06 | 10 | 0 | 0 |  | 0 | 30 |  |  |  | 3
2025-10-10 | 1396 |  | L02_AREA_300_MA_003 | A | DONE | 46 | L | ss | PROJECT DOVE 6240041 | 321 , VD's | 2025-10-02 | Z | 2025-07-01 | 1140 | 0 | 0 |  | 0 | 2280 |  |  |  | 93
2025-10-07 | 1397 |  | L02_AREA_300_MA_004 | A | DONE | 13 | S-M | ss | PROJECT DOVE 6240041 | 321 | 2025-10-02 | Z | 2025-07-01 | 320 | 0 | 0 |  | 0 | 560 |  |  |  | 93
2025-10-08 | 1608 | w | L02_AREA_700_WEST_RAMP_004 | A | DONE | 4 | S-M | ss | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-04 | 100 | 0 | 0 |  | 0 | 330 |  |  |  | 35
2025-10-06 | 1613 | w | 76172-73 | A | DONE | 17 | M | ss | PROJECT DOVE 6240041 |  | 2025-09-25 | Z | 2025-09-11 | 410 | 0 | 0 |  | 0 | 1150 |  | 200/300 ROOF |  | 14
2025-10-06 | 1616 |  | 76174 | A | DONE | 17 | S-M | ss | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-17 | 420 | 0 | 0 |  | 0 | 1160 |  | MAU-5 Roof drops |  | 15
2025-10-09 | 1625 | sp | L01_AREA_700_EAST_SALP_001 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 10 | 100 | 0 |  | 0 | 130 |  |  |  | 22
2025-10-09 | 1627 | sp | L01_AREA_700_EAST_SALP_003 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 22
2025-10-09 | 1630 | bth | L01_AREA_700_EAST_MA_003 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 50 | 40 | 0 |  | 0 | 100 |  |  |  | 22
2025-10-10 | 1637 | w | 76183 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-02 | Z | 2025-09-19 | 20 | 0 | 0 |  | 0 | 60 |  | Roof Drops |  | 13
2025-10-08 | 1640 |  | 76266 - 76267 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-07 | Z | 2025-09-24 | 60 | 0 | 70 | A | 0 | 160 |  | Guard shack |  | 13
2025-10-10 | 1641 | bth | 76268 - 76269 | A | DONE | 9 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-07 | Z | 2025-09-24 | 40 | 150 | 30 | A | 0 | 210 |  | Guard shack |  | 13
2025-10-09 | 1643 |  | 76272 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | filter rack | 2025-10-07 | Z | 2025-09-24 | 30 | 0 | 0 |  | 0 | 70 |  | Guard shack |  | 13
2025-10-09 | 1644 |  | 76270 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-07 | Z | 2025-09-24 | 40 | 0 | 0 |  | 0 | 50 |  | L02 AREA 052 |  | 13
2025-10-09 | 1646 |  | 76274 - 76275 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-10-07 | Z | 2025-09-25 | 150 | 0 | 0 |  | 0 | 170 |  | Waste water |  | 12
2025-10-08 | 1649 |  | 76279 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-10-09 | Z | 2025-09-26 | 10 | 0 | 0 |  | 0 | 20 |  | MAU-10 |  | 13
2025-10-09 | 4873 |  | 76258 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-08-26 | 40 | 0 | 0 |  | 0 | 70 |  | Tear drop hangers |  | 44
2025-10-10 | 295 |  | 84742 | A | DONE | 3 | S |  | RICH H. 1000386 | 2" liner | 2025-10-13 | Z | 2025-10-08 | 60 | 0 | 0 |  | 0 | 70 |  | Misc |  | 5
2025-10-08 | 1369 |  | 75861 | A | DONE | 7 | S-M |  | RICHLAND CTR. 6250011 |  | 2025-10-13 | Z | 2025-09-30 | 70 | 0 | 90 | A | 0 | 210 |  | Lobby duct |  | 13
2025-10-08 | 1370 | sp | 75862 | A | DONE | 6 | S-M |  | RICHLAND CTR. 6250011 |  | 2025-10-13 | Z | 2025-09-30 | 0 | 140 | 0 |  | 0 | 130 |  | Lobby duct |  | 13
2025-10-07 | 3143 |  | Hand Drawn | A | DONE | 3 | S |  | SAUK PRAIRIE MOB 6220023 |  | 2025-10-07 | Z | 2025-10-06 | 40 | 0 | 0 |  | 0 | 60 |  | Flat stock |  | 1
2025-10-08 | 2416 |  | 76816 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2025-10-08 | Z | 2025-10-01 | 20 | 0 | 0 |  | 0 | 40 |  | Split system backing |  | 7
2025-10-08 | 522 |  | 81658 - 81660 | A | DONE | 67 | M |  | SW HEALTH MOB 6250015 |  | 2025-10-06 | Z | 2025-08-26 | 530 | 0 | 1130 | A | 0 | 2570 |  | RTU 2 |  | 41
2025-10-08 | 523 |  | 81661 - 81664 | A | DONE | 24 | M |  | SW HEALTH MOB 6250015 | VD | 2025-10-06 | Z | 2025-08-26 | 280 | 20 | 290 | A | 0 | 780 |  | RTU 2 |  | 41
2025-10-06 | 524 | sp | 81665 | A | DONE | 27 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-06 | Z | 2025-08-26 | 40 | 620 | 0 |  | 0 | 670 |  | RTU 2 |  | 41
2025-10-08 | 525 |  | 81666-67 | A | DONE | 14 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-06 | Z | 2025-08-27 | 120 | 0 | 210 | A | 0 | 390 |  | AHU-2-RA-2nd to chase |  | 40
2025-10-08 | 526 | bth | 81668-69 | A | DONE | 9 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-06 | Z | 2025-08-27 | 110 | 40 | 70 | A | 0 | 240 |  | AHU-2-RA-RM 208 |  | 40
2025-10-08 | 527 |  | 81670-71 | A | DONE | 5 | S |  | SW HEALTH MOB 6250015 |  | 2025-10-06 | Z | 2025-08-27 | 60 | 0 | 50 | A | 0 | 140 |  | AHU-2-RA-RM 206 |  | 40
2025-10-08 | 533 |  | 81674-77 | A | DONE | 34 | M |  | SW HEALTH MOB 6250015 |  | 2025-10-13 | Z | 2025-09-12 | 260 | 0 | 590 | A | 0 | 1200 |  | RTU-2 |  | 31
2025-10-09 | 534 | sp | 81678-79 | A | DONE | 12 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-13 | Z | 2025-09-12 | 20 | 270 | 0 |  | 0 | 260 |  | RTU-2 |  | 31
2025-10-08 | 535 |  | 81680 | A | DONE | 11 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-13 | Z | 2025-09-12 | 210 | 0 | 50 | A | 0 | 300 |  | RTU-2 |  | 31
2025-10-08 | 536 |  | 81682-84 | A | DONE | 37 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-13 | Z | 2025-09-15 | 350 | 10 | 560 | A | 0 | 1460 |  | RTU-1 |  | 28
2025-10-08 | 2106 |  | 69751 | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 |  | 2025-10-13 | Z | 2025-09-25 | 20 | 0 | 0 |  | 0 | 40 |  | Storm collars |  | 18
2025-10-09 | 4695 |  | 82236 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-10-06 | Z | 2025-09-22 | 50 | 0 | 0 |  | 0 | 80 |  | RA Outs |  | 14
2025-10-09 | 4696 |  | 82237 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-10-06 | Z | 2025-09-23 | 20 | 0 | 0 |  | 0 | 20 |  | RA out |  | 13
2025-10-07 | 3115 |  | Hand Drawn | A | DONE | 2 | S |  | UW-AVRL 6240038 |  | 2025-10-08 | Z | 2025-10-07 | 20 | 0 | 0 |  | 0 | 40 |  | End caps |  | 1
2025-10-10 | 1431 |  | MER-EAMP 2 | A | DONE | 16 | M |  | UW-LEVY HALL 6230028 |  | 2025-10-09 | Z | 2025-09-10 | 220 | 0 | 180 | A | 0 | 660 |  |  |  | 29
2025-10-09 | 1444 |  | MER-RAMP 7 | A | DONE | 16 | M |  | UW-LEVY HALL 6230028 | s.mates,MOD,1" liner | 2025-10-07 | Z | 2025-09-22 | 390 | 0 | 0 |  | 320 | 850 |  |  |  | 15
2025-10-09 | 1445 |  | MER-RAMP 8 | A | DONE | 32 | M |  | UW-LEVY HALL 6230028 | MOD's , 1" liner | 2025-10-07 | Z | 2025-09-22 | 230 | 0 | 70 | A | 230 | 600 |  |  |  | 15
2025-10-09 | 1446 |  | MER-EAMP 4 | A | DONE | 20 | M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-10-07 | Z | 2025-09-22 | 430 | 0 | 0 |  | 370 | 830 |  |  |  | 15
2025-10-09 | 4801 |  | MER-SAMP 4 | A | DONE | 43 | M-L |  | UW-LEVY HALL 6230028 |  | 2025-10-07 | Z | 2025-09-22 | 580 | 0 | 0 |  | 490 | 1330 |  |  |  | 15
2025-10-09 | 4804 |  | 82996 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-10-07 | Z | 2025-09-24 | 20 | 0 | 0 |  | 0 | 20 |  | L1 Mech Room |  | 13
2025-10-09 | 4805 | bth | 82997 | A | DONE | 16 | S |  | UW-LEVY HALL 6230028 |  | 2025-10-07 | Z | 2025-09-24 | 70 | 320 | 0 |  | 0 | 360 |  | L2 SAMP 17/EAMP 2 |  | 13
2025-10-09 | 4806 |  | 82998 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-10-07 | Z | 2025-09-24 | 20 | 0 | 0 |  | 0 | 20 |  | L4 EAMP 1 |  | 13
2025-10-09 | 4807 |  | 82999 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | flex | 2025-10-07 | Z | 2025-09-26 | 11 | 0 | 0 |  | 0 | 30 |  | L4-CUH-19 |  | 11
2025-10-08 | 4808 |  | 74852 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-10-09 | Z | 2025-09-26 | 10 | 0 | 0 |  | 0 | 10 |  | EA tie in |  | 13
2025-10-09 | 4809 | bth | 83000 | A | DONE | 5 | S-M |  | UW-LEVY HALL 6230028 |  | 2025-10-09 | Z | 2025-09-26 | 60 | 70 | 0 |  | 0 | 200 |  | L5-SAT-3-5-31 |  | 13
2025-10-09 | 4810 |  | 74853 - 74854 | A | DONE | 3 | S-M |  | UW-LEVY HALL 6230028 | flex | 2025-10-09 | Z | 2025-09-26 | 60 | 0 | 0 |  | 0 | 100 |  | 3rd floor FCU RA |  | 13
2025-10-09 | 1412r |  | MER-RAMP 1 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-10-07 | Z | 2025-10-07 | 50 | 0 | 0 |  | 0 | 100 |  | EC remake |  | 0
2025-10-07 | 1418a |  | MER-RAMP 5 | L | DONE | 2 | M-L |  | UW-LEVY HALL 6230028 | partial | 2025-10-09 | Z | 2025-08-26 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 44
2025-10-08 | 2885 | sp | 84891 | A | DONE | 3 | S-M | ss | UWRF 6230010 |  | 2025-10-09 | Z | 2025-10-02 | 20 | 50 | 0 |  | 0 | 60 |  | Acid Cabinets |  | 7 | 2025-10-14
2025-10-10 | 2886 |  | 84892 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2025-10-14 | Z | 2025-10-09 | 20 | 0 | 0 |  | 20 | 20 |  | 2nd Floor TA |  | 5
2025-10-06 | 2200 |  | 99029 | A | DONE | 2 | S | BI | UW-STOUT 6250008 |  | 2025-10-03 | Z | 2025-10-01 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 2
2025-10-07 | 1507 |  | 78043 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 | spiral mate | 2025-09-05 | Z | 2025-08-18 | 70 | 50 | 0 |  | 0 | 160 |  | MAU-3 |  | 18
2025-10-07 | 1673 |  | L01_A_SOA_001 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 130 | 0 | 50 | A | 0 | 240 |  |  |  | 14
2025-10-07 | 1674 | bth | L01_A_SOA_002 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 70 | 20 | 60 | A | 0 | 180 |  |  |  | 14
2025-10-07 | 1675 | bth | L01_A_SOA_003 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 60 | 60 | 90 | A | 0 | 230 |  |  |  | 14
2025-10-07 | 1676 | bth | L01_A_SOA_004 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 100 | 0 | 120 | A | 0 | 290 |  |  |  | 14
2025-10-07 | 1677 |  | L01_A_SOA_005 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 30 | 0 | 180 | A | 0 | 260 |  |  |  | 14
2025-10-07 | 1678 | bth | L01_A_SOA_006 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 40 | 20 | 90 | A | 0 | 190 |  |  |  | 14
2025-10-07 | 1679 | sp | L01_A_SOA_007 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 14
2025-10-07 | 1680 | bth | L01_A_SOA_008 | A | DONE | 6 | S | neal | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 110 | 0 |  | 0 | 160 |  |  |  | 14
2025-10-07 | 1681 | bth | L01_A_SOA_009 | A | DONE | 3 | S | neal | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 14
2025-10-07 | 1682 | bth | L01_A_SOA_010 | A | DONE | 2 | S | neal | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 14
2025-10-07 | 1683 | sp | L01_A_SOA_011 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 100 | 0 |  | 0 | 110 |  |  |  | 14
2025-10-07 | 1684 | sp | L01_A_SOA_012 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 100 | 0 |  | 0 | 110 |  |  |  | 14
2025-10-07 | 1685 | sp | L01_A_SOA_013 | A | DONE | 15 | S-M | neal | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 170 | 40 | 150 | A | 0 | 490 |  |  |  | 14
2025-10-07 | 1686 |  | L01_A_SOA_014 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 140 | 0 | 180 | A | 0 | 390 |  |  |  | 14
2025-10-07 | 1687 | bth | L01_A_SOA_015 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 130 | 20 | 140 | A | 0 | 330 |  |  |  | 14
2025-10-06 | 1688 | sp | L01_A_SOA_016 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 14
2025-10-06 | 1689 | sp | L01_A_SOA_017 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 80 | 0 |  | 0 | 110 |  |  |  | 14
2025-10-08 | 1690 | bth | L01_A_SOA_018 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 40 | 20 | 50 | A | 0 | 130 |  |  |  | 14
2025-10-07 | 1691 | bth | L01_A_SOA_019 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 50 | 20 | 50 | A | 0 | 130 |  |  |  | 14
2025-10-07 | 1692 | bth | L01_A_SOA_020 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 30 | 70 | 40 | A | 0 | 140 |  |  |  | 14
2025-10-06 | 1693 | sp | L01_A_SOA_021 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 14
2025-10-07 | 1694 | bth | L01_A_EAD_001 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 120 | 0 | 140 | A | 0 | 420 |  |  |  | 14
2025-10-07 | 1697 | sp | L01_A_EAD_004 | A | DONE | 3 | S | alum | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 50 | 0 |  | 0 | 30 |  |  |  | 14
2025-10-07 | 1698 | bth | L01_A_EAD_005 | A | DONE | 7 | S | alum | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 30 | 0 | 140 | A | 0 | 120 |  |  |  | 14
2025-10-07 | 1699 | bth | L01_A_EAD_006 | A | DONE | 5 | S | alum | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 50 | 0 | 60 | A | 0 | 70 |  |  |  | 14
2025-10-07 | 2300 | bth | L01_A_EAD_007 | A | DONE | 5 | S | alum | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 40 | 30 | 40 | A | 0 | 70 |  |  |  | 14
2025-10-06 | 2301 | sp | L01_A_EAD_008 | A | DONE | 5 | S | alum | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 30 | 90 | 0 |  | 0 | 60 |  |  |  | 14
2025-10-06 | 2302 | sp | L01_A_EAD_009 | A | DONE | 4 | S | alum | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 30 | 70 | 0 |  | 0 | 50 |  |  |  | 14
2025-10-07 | 2303 |  | L01_A_EAD_010 | A | DONE | 11 | S-M | neal | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 80 | 0 | 180 | A | 0 | 350 |  |  |  | 14
2025-10-07 | 2304 |  | L01_A_EAD_011 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 80 | 0 | 250 | A | 0 | 440 |  |  |  | 14
2025-10-07 | 2305 | bth | L01_A_EAD_012 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 150 | 0 | 90 | A | 0 | 280 |  |  |  | 14
2025-10-07 | 2306 |  | L01_A_EAD_013 | A | DONE | 5 | S | neal | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 60 | 0 | 50 | A | 0 | 150 |  |  |  | 14
2025-10-07 | 2307 |  | L01_A_EAD_014 | A | DONE | 8 | S | neal | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 140 | 0 | 40 | A | 0 | 210 |  |  |  | 14
2025-10-08 | 2308 | bth | L01_A_EAD_015 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 140 | 20 | 40 | A | 0 | 260 |  |  |  | 14
2025-10-08 | 2309 |  | L01_A_EAD_016 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 40 | 0 | 60 | A | 0 | 120 |  |  |  | 14
2025-10-08 | 2310 |  | L01_A_EAD_017 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 60 | 0 | 70 | A | 0 | 160 |  |  |  | 14
2025-10-08 | 2311 | sp | L01_A_EAD_018 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 14
2025-10-06 | 2314 | w | L01_A_KEA_001 | A | DONE | 2 | S | SS | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 50 | 0 | 0 |  | 0 | 130 |  |  |  | 14
2025-10-07 | 2315 | w | L01_A_KEA_002 | A | DONE | 3 | S | SS | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 70 | 0 | 0 |  | 0 | 170 |  |  |  | 14
2025-10-07 | 2316 | w | L01_A_KEA_003 | A | DONE | 2 | S | SS | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 50 | 0 | 0 |  | 0 | 140 |  |  |  | 14
2025-10-07 | 2317 | bth | L01_A_OA_001 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 240 | 20 | 0 |  | 0 | 290 |  |  |  | 14
2025-10-07 | 2318 | bth | L01_A_OA_002 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-19 | 180 | 20 | 0 |  | 0 | 270 |  |  |  | 14
2025-10-10 | 2322 | sp | L01_A_SALP_018 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 40 | 30 | 0 |  | 0 | 70 |  |  |  | 21
2025-10-10 | 2323 | sp | L01_A_SALP_019 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 30 | 40 | 0 |  | 0 | 70 |  |  |  | 21
2025-10-10 | 2327 | sp | L01_A_SALP_023 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 21
2025-10-07 | 2356 |  | 82915 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | bird s. | 2025-10-03 | Z | 2025-09-19 | 20 | 0 | 0 |  | 0 | 40 |  | EF-Roof |  | 14
2025-10-07 | 2358 |  | 75351 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-03 | Z | 2025-09-25 | 70 | 0 | 0 |  | 0 | 120 |  | A PH |  | 8
[6 empty] | 1556 | [13 empty] | 53364 |  |  |  | 5130 | 9.613%
WEEK OF 10-13-2025
2025-10-16 | 598 |  | 84382 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2025-10-17 | Z | 2025-10-13 | 30 | 0 | 0 |  | 0 | 60 |  | Ret Tie in 2nd floor |  | 4
2025-10-17 | 599 |  | 74251-53 | A | DONE | 3 | S |  | BARTILLION 6240024 |  | 2025-10-20 | Z | 2025-10-14 | 60 | 0 | 0 |  | 0 | 140 |  | OA outs and flashing |  | 6
2025-10-17 | 2908 | sp | 80406-08 | A | DONE | 30 | S |  | BROOM ST 6240033 |  | 2025-10-22 | Z | 2025-10-16 | 180 | 550 | 0 |  | 0 | 660 |  | Flashing |  | 6
2025-10-13 | 2907 | w | 80402 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-10-13 | Z | 2025-10-13 | 20 | 0 | 0 |  | 0 | 30 |  | Sleeve |  | 0
2025-10-16 | 3596 |  | 74053,73736-37 | A | DONE | 20 | S |  | DELLSHIRE 6240017 | flex | 2025-10-15 | Z | 2025-10-08 | 500 | 0 | 0 |  | 0 | 860 |  | Misc |  | 7
2025-10-14 | 3597 |  | 74005 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-10-15 | Z | 2025-10-09 | 20 | 0 | 0 |  | 0 | 50 |  | Restaurant Offset |  | 6
2025-10-15 | 1640r | bth | Z1-SAMP 22 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-10-15 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2025-10-17 | 2201 | bth | Z1-SAT-4-1-17_3 | A | DONE | 13 | S-M |  | DOC JDC 6240023 | VD | 2025-10-23 | Z | 2025-07-31 | 100 | 80 | 130 |  | 0 | 350 |  |  |  | 84 | 2025-09-18
2025-10-17 | 2223 |  | Z3-EA 63 | A | DONE | 24 | M |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-09-10 | 310 | 0 | 280 | F | 0 | 780 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-17 | 2226 |  | Z3-EA 66 | A | DONE | 14 | S-M |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-09-10 | 240 | 0 | 90 | F | 0 | 470 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-17 | 2227 |  | Z3-EA 67 | A | DONE | 10 | S-M |  | DOC JDC 6240023 | VD | 2025-10-16 | Z | 2025-09-10 | 120 | 0 | 130 | F | 0 | 320 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-17 | 2228 |  | Z3-EA 73 | A | DONE | 5 | S |  | DOC JDC 6240023 | VD | 2025-10-16 | Z | 2025-09-10 | 90 | 0 | 30 | F | 0 | 170 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-17 | 2229 |  | Z3-EA 75 | A | DONE | 13 | S-M |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-09-10 | 190 | 20 | 110 | F | 0 | 450 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-17 | 2230 |  | Z3-EA 76 | A | DONE | 10 | S-M |  | DOC JDC 6240023 | VD | 2025-10-16 | Z | 2025-09-10 | 140 | 0 | 110 | F | 0 | 320 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-17 | 2231 |  | Z3-EA 81 | A | DONE | 6 | S |  | DOC JDC 6240023 | VD | 2025-10-16 | Z | 2025-09-10 | 80 | 0 | 50 | F | 0 | 170 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-17 | 2232 |  | Z3-EA 82 | A | DONE | 16 | M |  | DOC JDC 6240023 | VD | 2025-10-16 | Z | 2025-09-10 | 240 | 0 | 160 | F | 0 | 620 |  |  |  | 36 | 2025-10-02 | 2025-10-09
2025-10-17 | 3180 |  | Z3-SAMP 35 | A | DONE | 8 | S |  | DOC JDC 6240023 | flex | 2025-10-16 | Z | 2025-09-18 | 110 | 0 | 70 | F | 0 | 260 |  |  |  | 28 | 2025-10-02 | 2025-10-09
2025-10-17 | 3181 |  | Z3-SAMP 36 | A | DONE | 29 | M-L |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-09-18 | 380 | 0 | 330 | F | 0 | 1180 |  |  |  | 28 | 2025-10-02 | 2025-10-09
2025-10-17 | 3182 | bth | Z3-SAMP 37 | A | DONE | 16 | M-L |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-09-18 | 260 | 20 | 110 | F | 0 | 650 |  |  |  | 28 | 2025-10-02 | 2025-10-09
2025-10-17 | 3183 | bth | Z3-SAMP 38 | A | DONE | 10 | S-M |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-09-18 | 140 | 30 | 80 | F | 0 | 340 |  |  |  | 28 | 2025-10-02 | 2025-10-09
2025-10-17 | 4700 |  | Z3-RA 38 | A | DONE | 24 | M |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-09-18 | 370 | 40 | 190 | F | 0 | 920 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-15 | 4716 | bth | Z3-SAT-4-1-3 | A | DONE | 7 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 100 | 60 | 0 |  | 20 | 200 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-16 | 4717 | bth | Z3-SAT-4-1-4_1 | A | DONE | 11 | S-M |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 140 | 30 | 90 | F | 30 | 330 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-16 | 4718 | bth | Z3-SAT-4-1-5 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 30 | 40 | 0 |  | 20 | 70 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-15 | 4719 | bth | Z3-SAT-4-1-6 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 30 | 20 | 0 |  | 20 | 60 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-15 | 4720 | bth | Z3-SAT-4-1-7 | A | DONE | 4 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 50 | 40 | 0 |  | 40 | 100 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-16 | 4721 | bth | Z3-SAT-4-1-8 | A | DONE | 5 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 40 | 20 | 50 | F | 50 | 140 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-15 | 4722 | bth | Z3-SAT-4-1-9 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 20 | 20 | 20 | F | 30 | 80 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-16 | 4723 | bth | Z3-SAT-4-1-10 | A | DONE | 4 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 30 | 20 | 30 | F | 40 | 80 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-17 | 4724 | bth | Z3-SAT-4-1-11 | A | DONE | 4 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 30 | 20 | 30 | F | 40 | 90 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-15 | 4725 | bth | Z3-SAT-4-1-12 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 50 | 20 | 0 | F | 30 | 70 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-16 | 4726 | bth | Z3-SAT-4-1-13 | A | DONE | 7 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 60 | 100 | 0 | F | 30 | 160 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-16 | 4727 | bth | Z3-SAT-4-1-14 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-16 | Z | 2025-09-18 | 70 | 0 | 0 | F | 0 | 200 |  |  |  | 28 | 2025-11-13 | 2025-11-20
2025-10-14 | 4735 |  | ZP-REL 1 | A | DONE | 26 | M-L |  | DOC JDC 6240023 | MOD-4C | 2025-10-09 | Z | 2025-09-30 | 650 | 0 | 0 |  | 0 | 1700 |  |  |  | 9
2025-10-15 | 4736 |  | ZP-REL 2 | A | DONE | 22 | M |  | DOC JDC 6240023 | MOD-4A | 2025-10-09 | Z | 2025-09-30 | 60 | 0 | 480 | F | 0 | 1180 |  |  |  | 9
2025-10-16 | 4737 |  | ZP-REL 3 | A | DONE | 14 | M |  | DOC JDC 6240023 | MOD-3A | 2025-10-09 | Z | 2025-09-30 | 100 | 0 | 230 | F | 0 | 660 |  |  |  | 9
2025-10-17 | 4739 |  | ZP-REL 5 | A | DONE | 20 | M | semi | DOC JDC 6240023 | MOD-2E | 2025-10-09 | Z | 2025-09-30 | 300 | 0 | 180 | F | 0 | 570 |  |  |  | 9
2025-10-14 | 4742 |  | ZP-REL 8 | A | DONE | 14 | M | pt.semi | DOC JDC 6240023 | MOD-1C | 2025-10-09 | Z | 2025-09-30 | 300 | 0 | 50 | F | 0 | 680 |  |  |  | 9
2025-10-14 | 4743 |  | ZP-REL 9 | A | DONE | 25 | M-L | pt.semi | DOC JDC 6240023 | MOD-3C | 2025-10-09 | Z | 2025-09-30 | 500 | 0 | 120 | F | 0 | 1250 |  |  |  | 9
2025-10-14 | 4744 |  | ZP-REL 10 | A | DONE | 19 | M | pt.semi | DOC JDC 6240023 | MOD-5A, 5C | 2025-10-09 | Z | 2025-09-30 | 320 | 0 | 150 | F | 0 | 810 |  |  |  | 9
2025-10-14 | 4745 |  | ZP-REL 11 | A | DONE | 21 | M | pt.semi | DOC JDC 6240023 | MOD-2C | 2025-10-09 | Z | 2025-09-30 | 450 | 0 | 60 | F | 0 | 760 |  |  |  | 9
2025-10-16 | 4747 |  | 73926 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-10-08 | 90 | 0 | 0 |  | 0 | 120 |  | Sec. bar sleeves |  | 8
2025-10-16 | 4748 |  | 74162-74163 | A | DONE | 7 | S |  | DOC JDC 6240023 |  | 2025-10-16 | Z | 2025-10-08 | 160 | 0 | 0 |  | 0 | 340 |  | Z2-SAMP-31 |  | 8
2025-10-17 | 4752 | sp | 73929 | A | DONE | 9 | S |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-10-15 | 20 | 200 | 0 |  | 0 | 200 |  | Extra Spiral |  | 8
2025-10-16 | 1313 |  | 36344 | A | DONE | 2 | S | ss | EXACT 8250028 |  | 2025-10-20 | Z | 2025-10-09 | 10 | 0 | 0 |  | 0 | 30 |  | Misc |  | 11
2025-10-16 | 1315 |  | 56846 | A | DONE | 2 | S |  | EXACT SEQ. 2250029 |  | 2025-10-22 | Z | 2025-10-14 | 10 | 0 | 0 |  | 0 | 10 |  | SAT 2830 |  | 8
2025-10-15 | 1309 | sp | 56840 - 56841 | A | DONE | 9 | S |  | EXACT SEQUENCER 2250029 |  | 2025-10-15 | Z | 2025-10-02 | 180 | 30 | 0 |  | 0 | 250 |  | Elbows |  | 13
2025-10-15 | 1310 |  | 56842 | A | DONE | 2 | S |  | EXACT SEQUENCER 2250029 |  | 2025-10-15 | Z | 2025-10-02 | 20 | 0 | 0 |  | 0 | 20 |  | SAT 1891 |  | 13
2025-10-15 | 1311 |  | 56843 | A | DONE | 2 | S |  | EXACT SEQUENCER 2250029 |  | 2025-10-15 | Z | 2025-10-03 | 20 | 20 | 0 |  | 0 | 30 |  | SAT 1893 |  | 12
2025-10-16 | 1312 | bth | 56844 | A | DONE | 2 | S |  | EXACT SEQUENCING 2250029 |  | 2025-10-15 | Z | 2025-10-08 | 30 | 20 | 0 |  | 0 | 30 |  | EF 1893 |  | 7
2025-10-16 | 1314 |  | 56845 | A | DONE | 2 | S |  | EXACT SEQUENCING 2250029 |  | 2025-10-22 | Z | 2025-10-10 | 10 | 0 | 0 |  | 0 | 20 |  | EF 1893 |  | 12
2025-10-14 | 297 |  | 74054 - 74055 | A | DONE | 5 | S-M |  | KALAHARI RTU 4250012 | flex , 1" liner | 2025-10-14 | Z | 2025-10-13 | 120 | 0 | 0 |  | 50 | 350 |  | RTU |  | 1
2025-10-14 | 296 |  | 69996 | A | DONE | 2 | S |  | MENDOTA 2250048 | VD | 2025-10-20 | Z | 2025-10-13 | 50 | 0 | 0 |  | 0 | 130 |  | Misc |  | 7
2025-10-15 | 1497 | bth | EA-L2E-03 | A | DONE | 5 | S |  | MONROE HS 6240018 | CD , 1" liner | 2025-10-08 | Z | 2025-09-18 | 60 | 30 | 30 | A | 30 | 140 |  |  |  | 20
2025-10-14 | 3913 |  | 83617 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-10-15 | Z | 2025-10-09 | 30 | 0 | 0 |  | 0 | 30 |  | Z-Flashing |  | 6
2025-10-17 | 3914 |  | 83755 | A | DONE | 4 | S |  | MONROE HS 6240018 |  | 2025-10-15 | Z | 2025-10-09 | 80 | 0 | 0 |  | 0 | 120 |  | RA |  | 6
2025-10-16 | 299 |  | 84743 | A | DONE | 2 | S |  | NEW GLARUS 4250044 |  | 2025-10-17 | Z | 2025-10-16 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2025-10-14 | 298 |  | 85368 | A | DONE | 2 | S |  | OAKWOOD 10064913 |  | 2025-10-15 | Z | 2025-10-14 | 10 | 0 | 0 |  | 0 | 20 |  | AC Coil |  | 1
2025-10-15 | 294 |  | 74053 | A | DONE | 38 | S | pt.alum | OAKWOOD THE OAKS 4250047 |  | 2025-10-17 | Z | 2025-10-06 | 950 | 0 | 0 |  | 0 | 1100 |  |  |  | 11
2025-10-14 | 3270 |  | 74803 | A | DONE | 2 | S | ss | ONE 09 6240037 |  | 2025-10-14 | Z | 2025-10-14 | 10 | 0 | 0 |  | 0 | 10
2025-10-13 | 3269 |  | 79544 | A | DONE | 2 | S |  | ONE09 6240037 |  | 2025-10-14 | Z | 2025-10-07 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 7
2025-10-17 | 1052 |  | 74805 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-10-17 | Z | 2025-10-17 | 20 | 0 | 0 |  | 0 | 20 |  | hat channel |  | 0
2025-10-16 | 847 |  | 76783,76785,76819 | A | DONE | 5 | S |  | PEWAUKEE HS 6240030 | flex,VD,birdscreen | 2025-10-15 | Z | 2025-10-07 | 120 | 0 | 0 |  | 0 | 190 |  |  |  | 8
2025-10-16 | 848 |  | 76786 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | flex | 2025-10-15 | Z | 2025-10-09 | 20 | 0 | 0 |  | 0 | 20 |  | BCU-SA |  | 6
2025-10-17 | 849 |  | 76823,76825 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | birdscreen | 2025-10-23 | Z | 2025-10-16 | 40 | 0 | 0 |  | 0 | 110 |  | Flashing |  | 7
2025-10-16 | 1006 | w | L01_AREA_700_WEST_RAMP_001 | A | DONE | 5 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-13 | 120 | 0 | 0 |  | 0 | 240 |  |  |  | 10
2025-10-14 | 1008 |  | 74804 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-14 | Z | 2025-10-14 | 20 | 0 | 0 |  | 0 | 20 |  | Flat stock |  | 0
2025-10-13 | 1398 |  | L02_AREA_300_MA_005 | A | DONE | 15 | M | ss | PROJECT DOVE 6240041 | 321 | 2025-10-09 | Z | 2025-07-01 | 360 | 0 | 0 |  | 0 | 720 |  |  |  | 100
2025-10-13 | 1399 |  | L02_AREA_300_MA_006 | A | DONE | 18 | M | ss | PROJECT DOVE 6240041 | 321 | 2025-10-09 | Z | 2025-07-01 | 430 | 0 | 0 |  | 0 | 740 |  |  |  | 100
2025-10-16 | 1618 |  | L02_AREA_300_PEA_001 | A | DONE | 6 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 140 | 0 | 0 |  | 0 | 290 |  |  |  | 22
2025-10-15 | 1619 |  | L02_AREA_300_PSA_001 | A | DONE | 18 | M | ss | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 140 | 0 | 0 |  | 0 | 430 |  |  |  | 22
2025-10-17 | 1620 |  | L02_AREA_300_PSA_002 | A | DONE | 13 | M | ss | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 310 | 0 | 0 |  | 0 | 1050 |  |  |  | 22
2025-10-15 | 1621 |  | L01_AREA_300_PEA_001 | A | DONE | 10 | S-M | ss | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 250 | 0 | 0 |  | 0 | 590 |  |  |  | 22
2025-10-16 | 1623 |  | L01_AREA_300_PSA_001 | A | DONE | 17 | M | ss | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 420 | 0 | 0 |  | 0 | 1280 |  |  |  | 22
2025-10-15 | 1624 |  | L01_AREA_300_PSA_002 | A | DONE | 16 | M | ss | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 390 | 0 | 0 |  | 0 | 1120 |  |  |  | 22
2025-10-13 | 1626 | sp | L01_AREA_700_EAST_SALP_002 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 10 | 60 | 0 |  | 0 | 70 |  |  |  | 22
2025-10-13 | 1628 | bth | L01_AREA_700_EAST_MA_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 22
2025-10-13 | 1629 | bth | L01_AREA_700_EAST_MA_002 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 70 | 0 | 0 |  | 0 | 110 |  |  |  | 22
2025-10-13 | 1648 |  | 76278 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-26 | 30 | 0 | 0 |  | 0 | 40 |  | M20F2352 |  | 13
2025-10-13 | 4550 |  | L02_AREA_300_MA_007 | A | DONE | 9 | S-M | ss | PROJECT DOVE 6240041 | 321 | 2025-10-09 | Z | 2025-07-01 | 220 | 0 | 0 |  | 0 | 430 |  |  |  | 100
2025-10-15 | 4551 |  | L02_AREA_300_MA_008 | A | DONE | 13 | S-M | ss | PROJECT DOVE 6240041 | 321 | 2025-10-09 | Z | 2025-07-01 | 310 | 0 | 0 |  | 0 | 500 |  |  |  | 100
2025-10-17 | 901 |  | L02_600_EA_002 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 | bird s. , VD | 2025-10-16 | Z | 2025-09-30 | 200 | 0 | 0 |  | 0 | 340 |  |  |  | 16
2025-10-17 | 904 | bth | L02_600_EA_005 | A | DONE | 12 | S |  | PROJECT DOVE 6240041 | spiral mates | 2025-10-16 | Z | 2025-09-30 | 90 | 200 | 0 |  | 0 | 440 |  |  |  | 16
2025-10-15 | 906 | sp | L02_600_EA_007 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-09-30 | 20 | 60 | 0 |  | 0 | 90 |  |  |  | 16
2025-10-15 | 907 | sp | L02_600_EA_008 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-09-30 | 20 | 70 | 0 |  | 0 | 100 |  |  |  | 16
2025-10-16 | 908 | sp | L02_600_EA_009 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-09-30 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 16
2025-10-17 | 913 |  | 76186 | A | DONE | 5 | S-M |  | PROJECT DOVE 6240041 | 1" DW | 2025-10-16 | Z | 2025-10-02 | 120 | 0 | 0 |  | 50 | 120 |  | 400 Tower |  | 14
2025-10-17 | 930 | sp | L02_1600_SALP_008 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 20 | 110 | 0 |  | 0 | 150 |  |  |  | 16
2025-10-17 | 931 | sp | L02_1600_SALP_009 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 50 | 90 | 0 |  | 0 | 170 |  |  |  | 16
2025-10-17 | 933 | sp | L02_1600_SALP_011 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 10 | 60 | 0 |  | 0 | 60 |  |  |  | 16
2025-10-17 | 935 | sp | L02_1600_SALP_013 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 10 | 40 | 0 |  | 0 | 50 |  |  |  | 16
2025-10-17 | 938 | sp | L02_1600_SALP_016 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 10 | 40 | 0 |  | 0 | 50 |  |  |  | 16
2025-10-17 | 939 | sp | L02_1600_SALP_017 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 10 | 70 | 0 |  | 0 | 70 |  |  |  | 16
2025-10-17 | 940 | sp | L02_1600_SALP_018 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 10 | 100 | 0 |  | 0 | 120 |  |  |  | 16
2025-10-17 | 942 | sp | L02_1600_SALP_020 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 20 | 150 | 0 |  | 0 | 180 |  |  |  | 16
2025-10-17 | 943 | sp | L02_1600_SALP_021 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 10 | 40 | 0 |  | 0 | 40 |  |  |  | 16
2025-10-13 | 947 |  | 76368 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-10-08 | 20 | 0 | 0 |  | 0 | 40 |  | Flat stock |  | 8
2025-10-17 | 955 | sp | L02_600_RA_003 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-08 | 10 | 130 | 0 |  | 0 | 130 |  |  |  | 15
2025-10-17 | 2117 |  | 81750 | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 |  | 2025-10-20 | Z | 2025-10-09 | 30 | 0 | 0 |  | 0 | 60 |  | RTU-2 RA Offset |  | 11
2025-10-14 | 523r |  | 81661 - 81664 | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 | VD | 2025-10-20 | Z | 2025-10-14 | 30 | 0 | 0 |  | 0 | 50 |  | RTU 2 |  | 6
2025-10-16 | 537 |  | 81685 - 81687 | A | DONE | 31 | M |  | SW HEALTH MOB 6250015 |  | 2025-10-20 | Z | 2025-09-16 | 350 | 0 | 420 | F | 0 | 910 |  | RTU-1 RA 2nd floor |  | 34
2025-10-16 | 538 |  | 81688 - 81691 | A | DONE | 32 | M |  | SW HEALTH MOB 6250015 |  | 2025-10-20 | Z | 2025-09-16 | 190 | 0 | 590 | F | 0 | 980 |  | RTU-1 RA 2nd floor |  | 34
2025-10-16 | 539 |  | 81696 - 81698 | A | DONE | 13 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-20 | Z | 2025-09-17 | 130 | 0 | 190 | F | 0 | 380 |  | RTU-1 branch duct |  | 33
2025-10-16 | 540 |  | 81692 - 81695 | A | DONE | 33 | M |  | SW HEALTH MOB 6250015 | VD | 2025-10-20 | Z | 2025-09-17 | 520 | 0 | 300 | F | 0 | 1290 |  | RTU-1 branch duct |  | 33
2025-10-17 | 4698 |  | 82239 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-10-20 | Z | 2025-10-09 | 30 | 0 | 0 |  | 0 | 50 |  | Misc Outs |  | 11
2025-10-13 | 1416 |  | MER-RAMP 2 | A | DONE | 102 | L |  | UW-LEVY HALL 6230028 | MOD's | 2025-10-09 | Z | 2025-08-26 | 2420 | 0 | 150 | F | 0 | 5590 |  |  |  | 44
2025-10-13 | 1432 |  | MER-EAMP 3 RISER | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2025-10-09 | Z | 2025-09-10 | 60 | 0 | 20 | F | 0 | 110 |  |  |  | 29
2025-10-16 | 4811 |  | 78251 - 78252 | A | DONE | 4 | S-M |  | UW-LEVY HALL 6230028 | flex , paint | 2025-10-14 | Z | 2025-09-29 | 90 | 0 | 0 |  | 20 | 180 |  | LL FCU-1 SA , RA |  | 15
2025-10-17 | 4812 |  | 78253 - 78254 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 | flex , 1" liner | 2025-10-16 | Z | 2025-10-01 | 80 | 0 | 0 |  | 40 | 170 |  | LL Bathroom |  | 15
2025-10-14 | 4813 | w | 76120 | A | DONE | 2 | S | ss | UW-LEVY HALL 6230028 | 1-1/2" DB | 2025-10-16 | Z | 2025-10-02 | 40 | 0 | 0 |  | 20 | 90 |  | Gen EA |  | 14
2025-10-17 | 4815 |  | 78257 - 78259 | A | DONE | 16 | S-M |  | UW-LEVY HALL 6230028 | 1" liner | 2025-10-16 | Z | 2025-10-02 | 380 | 0 | 0 |  | 280 | 550 |  | 5th Floor TA / EA |  | 14
2025-10-14 | 2319 | bth | L01_A_SALP_015 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 120 | 30 | 50 | F | 0 | 220 |  |  |  | 21
2025-10-13 | 2320 | bth | L01_A_SALP_016 | F | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 60 | 30 | 30 | F | 0 | 140 |  |  |  | 21
2025-10-13 | 2321 | bth | L01_A_SALP_017 | F | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 140 | 20 | 100 | F | 0 | 290 |  |  |  | 21
2025-10-14 | 2324 | bth | L01_A_SALP_020 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 70 | 0 | 60 | F | 0 | 160 |  |  |  | 21
2025-10-14 | 2325 |  | L01_A_SALP_021 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 20 | 30 | 0 |  | 0 | 30 |  |  |  | 21
2025-10-15 | 2326 | bth | L01_A_SALP_022 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 40 | 20 | 0 |  | 0 | 60 |  |  |  | 21
2025-10-14 | 2328 |  | L01_A_RAD_001 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 21
2025-10-14 | 2329 | bth | L01_A_RAD_002 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 50 | 40 | 0 |  | 40 | 100 |  |  |  | 21
2025-10-15 | 2330 |  | L01_A_RAD_003 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-10-10 | Z | 2025-09-19 | 80 | 0 | 20 | F | 70 | 110 |  |  |  | 21
2025-10-15 | 2331 |  | L01_A_RAD_004 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 21
2025-10-15 | 2332 | bth | L01_A_RAD_005 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-10-10 | Z | 2025-09-19 | 40 | 20 | 0 |  | 20 | 50 |  |  |  | 21
2025-10-15 | 2333 |  | L01_A_RAD_006 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 20 | 0 | 40 | F | 40 | 80 |  |  |  | 21
2025-10-14 | 2334 |  | L01_A_RAD_007 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 80 | 0 | 40 | F | 80 | 140 |  |  |  | 21
2025-10-15 | 2335 |  | L01_A_RAD_008 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 140 | 0 | 30 | F | 110 | 240 |  |  |  | 21
2025-10-15 | 2336 |  | L01_A_RAD_009 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 270 | 0 | 0 |  | 230 | 490 |  |  |  | 21
2025-10-15 | 2337 |  | L01_A_RAD_010 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 70 | 0 | 0 |  | 60 | 110 |  |  |  | 21
2025-10-15 | 2338 | bth | L01_A_RAD_011 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 40 | 20 | 0 |  | 30 | 70 |  |  |  | 21
2025-10-15 | 2339 | bth | L01_A_RAD_012 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 50 | 20 | 40 | F | 60 | 110 |  |  |  | 21
2025-10-15 | 2340 |  | L01_A_RAD_013 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 | 1" liner | 2025-10-10 | Z | 2025-09-19 | 50 | 0 | 100 | F | 110 | 180 |  |  |  | 21
2025-10-15 | 2341 | bth | L01_A_RAD_014 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 | flex , 1" liner | 2025-10-10 | Z | 2025-09-19 | 30 | 20 | 0 |  | 20 | 50 |  |  |  | 21
2025-10-14 | 2342 |  | L01_A_SALP_001 | A | DONE | 7 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 70 | 20 | 70 | F | 0 | 170 |  |  |  | 21
2025-10-13 | 2343 | sp | L01_A_SALP_002 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 21
2025-10-15 | 2344 | bth | L01_A_SALP_003 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 30 | 60 | 20 | F | 0 | 110 |  |  |  | 21
2025-10-13 | 2345 | sp | L01_A_SALP_004 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 20 | 90 | 0 |  | 0 | 90 |  |  |  | 21
2025-10-13 | 2346 | sp | L01_A_SALP_005 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 21
2025-10-14 | 2347 | bth | L01_A_SALP_006 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 50 | 20 | 20 | F | 0 | 90 |  |  |  | 21
2025-10-15 | 2348 |  | L01_A_SALP_007 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 80 | 0 | 70 | F | 0 | 190 |  |  |  | 21
2025-10-15 | 2349 |  | L01_A_SALP_008 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 70 | 0 | 30 | F | 0 | 110 |  |  |  | 21
2025-10-15 | 2350 | bth | L01_A_SALP_009 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 60 | 20 | 40 | F | 0 | 120 |  |  |  | 21
2025-10-15 | 2351 | bth | L01_A_SALP_010 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 70 | 140 | 0 |  | 0 | 210 |  |  |  | 21
2025-10-15 | 2352 | bth | L01_A_SALP_011 | A | DONE | 9 | S |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 40 | 120 | 50 | F | 0 | 200 |  |  |  | 21
2025-10-13 | 2353 | sp | L01_A_SALP_012 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-19 | 0 | 40 | 0 |  | 0 | 40 |  |  |  | 21
2025-10-15 | 2354 | bth | L01_A_SALP_013 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 120 | 40 | 70 | F | 0 | 250 |  |  |  | 21
2025-10-15 | 2355 | bth | L01_A_SALP_014 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | flex | 2025-10-10 | Z | 2025-09-19 | 190 | 20 | 30 | F | 0 | 260 |  |  |  | 21
2025-10-14 | 2359 |  | 75354 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-10 | Z | 2025-09-30 | 30 | 0 | 0 |  | 0 | 70 |  | A-PH |  | 10
2025-10-14 | 2360 |  | 83393 - 83395 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 | paint | 2025-10-10 | Z | 2025-09-30 | 130 | 0 | 0 |  | 30 | 190 |  | 2nd D RA |  | 10
2025-10-15 | 2361 |  | 83392 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-17 | Z | 2025-10-10 | 50 | 0 | 0 |  | 0 | 60 |  | 2nd D-RA |  | 7
2025-10-15 | 2362 |  | 83325 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-17 | Z | 2025-10-13 | 20 | 0 | 0 |  | 0 | 30 |  | Misc outs |  | 4
2025-10-15 | 2363 | w | 83058 | A | DONE | 2 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-17 | Z | 2025-10-13 | 20 | 0 | 0 |  | 0 | 50 |  | PH EA Drip Pan |  | 4
2025-10-16 | 2364 |  | 75356 , 75358 - 75359 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 | CD's | 2025-10-17 | Z | 2025-10-13 | 230 | 0 | 0 |  | 0 | 440 |  | PH Outs |  | 4
2025-10-15 | 2365 |  | PH_A_RA_001 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 |  | 2025-10-17 | Z | 2025-10-13 | 140 | 0 | 0 |  | 0 | 340 |  |  |  | 4
[6 empty] | 1284 | [13 empty] | 47540
WEEK OF 10-20-2025
2025-10-20 | 1039 |  | 79547 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2025-10-21 | Z | 2025-10-16 | 20 | 0 | 0 |  | 10 | 40 |  | Findorf office |  | 5
2025-10-21 | 1050 |  | 74254 | A | DONE | 2 | S |  | BARTILLION 6240024 | paint black | 2025-10-22 | Z | 2025-10-17 | 20 | 0 | 0 |  | 20 | 30 |  | ceiling finishes |  | 5
2025-10-22 | 2950 | sp | 74255 | A | DONE | 2 | S |  | BARTILLION 6240024 | 1" liner | 2025-10-22 | Z | 2025-10-22 | 10 | 0 | 0 |  | 10 | 10 |  | Out |  | 0
2025-10-21 | 01016 |  | Hand drawn | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-10-16 | Z | 2025-10-16 | 20 | 0 | 0 |  | 0 | 40 |  | Couplers |  | 0
2025-10-22 | 3593r |  | 73796 | A | DONE | 4 | S |  | DELLSHIRE 6240017 |  | 2025-10-23 | Z | 2025-10-22 | 0 | 0 | 80 |  | 0 | 120 |  | Kitchen Riser |  | 1
2025-10-21 | 3598 | bth | 75272-73 | A | DONE | 9 | S |  | DELLSHIRE 6240017 |  | 2025-10-23 | Z | 2025-10-17 | 210 | 10 | 0 |  | 60 | 310 |  | Kitchen SA |  | 6
2025-10-24 | 3599 |  | 74007-08 | A | DONE | 27 | M/L |  | DELLSHIRE 6240017 |  | 2025-10-30 | Z | 2025-10-17 | 360 | 0 | 310 |  | 0 | 930 |  | Kitchen RA |  | 13
2025-10-21 | 3950 | sp | 74011 | A | DONE | 5 | S | pcd | DELLSHIRE 6240017 | pcd | 2025-10-21 | Z | 2025-10-20 | 20 | 100 | 0 |  | 0 | 130 |  | Pool kitchen EA |  | 1
2025-10-24 | 3953 |  | 74056 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-10-27 | Z | 2025-10-22 | 30 | 0 | 0 |  | 0 | 40 |  | Corr. SA |  | 5
2025-10-22 | 2200 | bth | Z1-SAT-4-1-17_2 | A | DONE | 14 | S-M |  | DOC JDC 6240023 | VD | 2025-10-23 | Z | 2025-07-31 | 160 | 10 | 170 | F | 0 | 390 |  |  |  | 84 | 2025-09-18
2025-10-22 | 2202 | bth | Z1-SAT-4-1-18 | A | DONE | 4 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 60 | 20 | 0 | F | 40 | 90 |  |  |  | 84 | 2025-09-18
2025-10-22 | 2203 | bth | Z1-SAT-4-1-19 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 40 | 30 | 0 |  | 20 | 60 |  |  |  | 84 | 2025-09-18
2025-10-22 | 2204 | bth | Z1-SAT-4-1-20 | A | DONE | 6 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 30 | 90 | 30 | F | 30 | 150 |  |  |  | 84 | 2025-09-18
2025-10-22 | 2205 | bth | Z1-SAT-4-1-21 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 30 | 20 | 0 |  | 20 | 50 |  |  |  | 84 | 2025-09-18
2025-10-22 | 2206 | bth | Z1-SAT-4-1-22 | A | DONE | 7 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 50 | 90 | 30 | F | 50 | 180 |  |  |  | 84 | 2025-09-18
2025-10-22 | 2207 | bth | Z1-SAT-4-1-23 | A | DONE | 7 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 80 | 80 | 0 |  | 40 | 170 |  |  |  | 84 | 2025-09-18
2025-10-22 | 3196 | bth | Z3-RA 34 | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-09-18 | 320 | 10 | 100 | F | 0 | 610 |  |  |  | 35
2025-10-22 | 3197 | bth | Z3-RA 35 | A | DONE | 12 | S-M |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-09-18 | 70 | 30 | 200 | F | 0 | 440 |  |  |  | 35
2025-10-22 | 3198 | bth | Z3-RA 36 | A | DONE | 19 | S-M |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-09-18 | 320 | 20 | 120 | F | 0 | 630 |  |  |  | 35
2025-10-22 | 3199 | bth | Z3-RA 37 | A | DONE | 11 | S-M |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-09-18 | 110 | 20 | 140 | F | 0 | 470 |  |  |  | 35 |  | 2025-11-20
2025-10-22 | 4738 |  | ZP-REL 4 | A | DONE | 16 | M | semi | DOC JDC 6240023 | MOD-2A | 2025-10-09 | Z | 2025-09-30 | 150 | 0 | 230 | F | 0 | 610 |  |  |  | 9
2025-10-22 | 4740 |  | ZP-REL 6 | A | DONE | 7 | S-M | semi | DOC JDC 6240023 | MOD-1A | 2025-10-09 | Z | 2025-09-30 | 60 | 0 | 110 | F | 0 | 230 |  |  |  | 9
2025-10-22 | 4741 |  | ZP-REL 7 | A | DONE | 14 | M | semi | DOC JDC 6240023 | MOD-1E | 2025-10-09 | Z | 2025-09-30 | 270 | 0 | 70 | F | 0 | 430 |  |  |  | 9
2025-10-20 | 4749w | w | 74312 | A | DONE | 2 | S | ss | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-10-08 | 30 | 0 | 0 |  | 30 | 70 |  | Boiler vent caps |  | 15
2025-10-21 | 4751 |  | 73928 | A | DONE | 9 | S-M |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-10-09 | 220 | 0 | 0 |  | 0 | 490 |  | Misc |  | 14
2025-10-22 | 4772 |  | 84384-86 | A | DONE | 5 | S |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-10-17 | 120 | 0 | 0 |  | 0 | 170 |  | roof drops |  | 6
2025-10-22 | 658 |  | Z1-OA 8 | A | DONE | 13 | M |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-07-22 | 220 | 0 | 100 |  | 0 | 550 |  |  |  | 93 | 2025-10-23
2025-10-22 | 685 |  | Z1-EA 24 | A | DONE | 10 | S |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-07-22 | 120 | 0 | 110 | F | 0 | 260 |  |  |  | 93 | 2025-10-23
2025-10-22 | 686 | bth | Z1-EA 25 | A | DONE | 9 | S |  | DOC JDC 6240023 |  | 2025-10-23 | Z | 2025-07-22 | 20 | 140 | 50 | F | 0 | 230 |  |  |  | 93 | 2025-10-23
2025-10-22 | 687 |  | Z1-EA 26 | A | DONE | 10 | S-M |  | DOC JDC 6240023 | VD | 2025-10-23 | Z | 2025-07-22 | 190 | 0 | 70 | F | 0 | 360 |  |  |  | 93 | 2025-10-23
2025-10-22 | 688 |  | Z1-EA 27 | A | DONE | 11 | S-M |  | DOC JDC 6240023 | VD's | 2025-10-23 | Z | 2025-07-22 | 260 | 0 | 0 |  | 0 | 450 |  |  |  | 93 | 2025-10-23
2025-10-22 | 797 | bth | Z1-SAT-4-1-15 | A | DONE | 6 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 50 | 60 | 30 | F | 50 | 150 |  |  |  | 84 | 2025-09-18
2025-10-22 | 798 | bth | Z1-SAT-4-1-16 | A | DONE | 9 | S |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 50 | 130 | 30 | F | 40 | 200 |  |  |  | 84 | 2025-09-18
2025-10-22 | 799 | bth | Z1-SAT-4-1-17_1 | A | DONE | 13 | S-M |  | DOC JDC 6240023 | 1" liner | 2025-10-23 | Z | 2025-07-31 | 140 | 80 | 100 | F | 40 | 370 |  |  |  | 84 | 2025-09-18
2025-10-21 | 1021 |  | Hand Drawn |  | DONE | 2 | S |  | E387 |  | 2025-10-21 | Z | 2025-10-21 | 10 | 0 | 0 |  | 0 | 20 |  | Kitchen shelf |  | 0
2025-10-21 | 2250 |  | 74806 | A | DONE | 2 | S |  | E387 | paint black | 2025-10-23 | Z | 2025-10-21 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 2
2025-10-21 | 1316 |  | 56847 | A | DONE | 2 | S |  | EXACT MAILROOM 2250027 | 1" liner | 2025-10-22 | Z | 2025-10-15 | 10 | 0 | 0 |  | 10 | 20 |  | Transfer |  | 7
2025-10-21 | 1317 |  | 56848 | A | DONE | 2 | S |  | EXACT SEQ. 2250029 |  | 2025-10-22 | Z | 2025-10-17 | 20 | 0 | 0 |  | 0 | 30 |  | sat 1893 |  | 5
2025-10-22 | 1318 |  | 56849 | A | DONE | 2 | S |  | EXACT SEQ. 2250029 |  | 2025-10-23 | Z | 2025-10-21 | 20 | 0 | 0 |  | 0 | 30 |  | SAT warrenty |  | 2
2025-10-22 | 1319 |  | 56850 | A | DONE | 2 | S |  | EXACT SEQ. 2250029 |  | 2025-10-23 | Z | 2025-10-22 | 40 | 0 | 0 |  | 0 | 60 |  | Shut down |  | 1 |  | 2025-10-16
2025-10-20 | 3238 |  | 69997 - 69998 | A | DONE | 4 | S | pcd | HISTOSONICS 6250009 | flex | 2025-10-24 | Z | 2025-10-13 | 40 | 60 | 0 |  | 0 | 120 |  | Roof |  | 11
2025-10-22 | 2418 |  | 85046 | A | DONE | 2 | S |  | JPC SAWMILL 2240068 |  | 2025-10-29 | Z | 2025-10-22 | 10 | 0 | 0 |  | 0 | 20 |  | Air cooler pan |  | 7 |  | 2025-10-16
2025-10-21 | 2251 |  | 77269 | A | DONE | 2 | S |  | MENDOTA 2250048 |  | 2025-10-21 | Z | 2025-10-21 | 10 | 0 | 0 |  | 0 | 10 |  | Angle |  | 0
2025-10-20 | 3915 |  | 83619 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-10-21 | Z | 2025-10-14 | 10 | 0 | 0 |  | 0 | 20 |  | Gas cap |  | 7
2025-10-24 | 3916 |  | 83653A-54A | A | DONE | 10 | M |  | MONROE HS 6240018 |  | 2025-10-28 | Z | 2025-10-15 | 250 | 0 | 0 |  | 0 | 510 |  | Outs |  | 13
2025-10-24 | 3917 |  | 83653B | A | DONE | 2 | S | neal | MONROE HS 6240018 |  | 2025-10-28 | Z | 2025-10-15 | 20 | 0 | 0 |  | 10 | 70 |  | Outs |  | 13
2025-10-24 | 3918 |  | 83654B | A | DONE | 3 | S/M |  | MONROE HS 6240018 | 1" liner | 2025-10-28 | Z | 2025-10-15 | 70 | 0 | 0 |  | 60 | 120 |  | Outs |  | 13
2025-10-24 | 3920 |  | 85045 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2025-10-28 | Z | 2025-10-20 | 10 | 0 | 0 |  | 10 | 10 |  | Transfer |  | 8
2025-10-22 | 3921 |  | 85048 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-10-28 | Z | 2025-10-23 | 10 | 0 | 0 |  | 10 | 40 |  | Boiler breaching caps |  | 5
2025-10-20 | 3271 |  | 79545 | A | DONE | 2 | S | alum | ONE09 6240037 |  | 2025-10-21 | Z | 2025-10-14 | 60 | 0 | 0 |  | 0 | 50 |  | Dishwasher EA |  | 7
2025-10-21 | 3272 |  | 79546 | A | DONE | 2 | S |  | ONE09 6240037 | 2" liner | 2025-10-21 | Z | 2025-10-14 | 40 | 0 | 0 |  | 20 | 50 |  | ERU-2 |  | 7
2025-10-21 | 1051 |  | 76826 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 | 2" liner | 2025-10-23 | Z | 2025-10-17 | 20 | 0 | 0 |  | 0 | 30 |  | vav-out |  | 6
2025-10-20 | 1053 |  | 76827 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-10-21 | Z | 2025-10-20 | 20 | 0 | 0 |  | 0 | 50 |  | Dust collector |  | 1
2025-10-22 | 1055 |  | 76831 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | flex | 2025-10-29 | Z | 2025-10-22 | 30 | 0 | 0 |  | 0 | 40 |  | UE flex |  | 7
2025-10-24 | 1056 |  | 76788 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | 1" liner | 2025-10-28 | Z | 2025-10-22 | 30 | 0 | 0 |  | 20 | 40 |  | RA tie in |  | 6 |  | 2025-10-16
2025-10-20 | 850 | bth | 76824 | A | DONE | 8 | S | neal | PEWAUKEE HS 6240030 |  | 2025-10-23 | Z | 2025-10-16 | 100 | 80 | 0 |  | 0 | 220 |  | Flashing |  | 7
2025-10-24 | 1001 | sp | L01_600_RA_003 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 10 | 70 | 0 |  | 0 | 90 |  |  |  | 20
2025-10-20 | 1007 | w | L01_AREA_700_WEST_SAMP_001 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-13 | 80 | 0 | 0 |  | 0 | 220 |  |  |  | 10
2025-10-22 | 1009 |  | 76285 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-14 | 10 | 0 | 0 |  | 0 | 40 |  | 052 IT room |  | 16
2025-10-21 | 1010 |  | 76189 | A | DONE | 12 | S |  | PROJECT DOVE 6240041 | 1" dual wall | 2025-10-23 | Z | 2025-10-15 | 290 | 0 | 0 |  | 70 | 360 |  | 400 Tower |  | 8
2025-10-20 | 1012 |  | Hand drawn | A | DONE | 3 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-20 | Z | 2025-10-16 | 80 | 0 | 0 |  | 0 | 210 |  |  |  | 4
2025-10-22 | 1014w |  | L02_AREA_300_EA_001 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-20 | 100 | 0 | 0 |  | 0 | 250 |  |  |  | 10
2025-10-21 | 1026 |  | 76369 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-20 | 90 | 0 | 0 |  | 0 | 120 |  | Angle |  | 3
2025-10-24 | 1027 |  | 76370 | A | DONE | 3 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-21 | 70 | 0 | 0 |  | 0 | 120 |  | Curb cap |  | 9
2025-10-22 | 1028 |  | 76286 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-21 | 50 | 10 | 0 |  | 0 | 80 |  | Guard shack |  | 9
2025-10-22 | 1396r |  | L02_AREA_300_MA_003 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-10-22 | Z | 2025-10-22 | 40 | 0 | 0 |  | 0 | 50 |  | Remade taps |  | 0
2025-10-22 | 1622 |  | L01_AREA_300_PEA_002 | A | DONE | 27 | M-L | ss | PROJECT DOVE 6240041 |  | 2025-10-09 | Z | 2025-09-17 | 670 | 0 | 0 |  | 0 | 1400 |  |  |  | 22
2025-10-20 | 900 |  | L02_600_EA_001 | A | DONE | 18 | S-M |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-09-30 | 290 | 0 | 150 | F | 0 | 610 |  |  |  | 16
2025-10-20 | 902 | sp | L02_600_EA_003 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-09-30 | 30 | 70 | 0 |  | 0 | 110 |  |  |  | 16
2025-10-20 | 905 | bth | L02_600_EA_006 | A | DONE | 9 | S |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-09-30 | 100 | 20 | 90 | F | 0 | 240 |  |  |  | 16
2025-10-20 | 909 |  | L02_600_EA_010 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-09-30 | 30 | 0 | 30 | F | 0 | 80 |  |  |  | 16
2025-10-21 | 910 |  | L02_600_MA_001 | A | DONE | 14 | M |  | PROJECT DOVE 6240041 | VD | 2025-10-16 | Z | 2025-09-30 | 290 | 0 | 50 | F | 0 | 700 |  |  |  | 16
2025-10-21 | 911 |  | L02_600_MA_002 | A | DONE | 12 | M |  | PROJECT DOVE 6240041 | VD's | 2025-10-16 | Z | 2025-09-30 | 300 | 0 | 0 |  | 0 | 770 |  |  |  | 16
2025-10-20 | 912 | bth | L02_600_MA_003 | A | DONE | 20 | M-L |  | PROJECT DOVE 6240041 | spiral mates | 2025-10-16 | Z | 2025-09-30 | 220 | 50 | 220 | F | 0 | 1240 |  |  |  | 16
2025-10-20 | 914 |  | 76187 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | bird s. | 2025-10-16 | Z | 2025-10-02 | 40 | 0 | 0 |  | 0 | 60 |  | 400 Tower |  | 14
2025-10-20 | 917 |  | 76280 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | paint | 2025-10-23 | Z | 2025-10-03 | 30 | 0 | 0 |  | 10 | 60 |  | Transfer boot 052 |  | 20
2025-10-22 | 921 |  | 76281 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-10-06 | 50 | 0 | 0 |  | 0 | 70 |  |  |  | 10 |  | 2025-09-02
2025-10-20 | 923 | sp | L02_1600_SALP_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 16
2025-10-21 | 924 | bth | L02_1600_SALP_002 | A | DONE | 11 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 80 | 100 | 80 |  | 0 | 300 |  |  |  | 16
2025-10-20 | 925 | sp | L02_1600_SALP_003 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 16
2025-10-24 | 926 | sp | L02_1600_SALP_004 | A | DONE | 5 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 30 | 80 | 0 |  | 0 | 130 |  |  |  | 16
2025-10-20 | 927 | sp | L02_1600_SALP_005 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 20 | 110 | 0 |  | 0 | 160 |  |  |  | 16
2025-10-20 | 928 | sp | L02_1600_SALP_006 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 10 | 30 | 0 |  | 0 | 40 |  |  |  | 16
2025-10-20 | 929 | sp | L02_1600_SALP_007 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 16
2025-10-21 | 932 | sp | L02_1600_SALP_010 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 40 | 90 | 0 |  | 0 | 140 |  |  |  | 16
2025-10-21 | 934 | sp | L02_1600_SALP_012 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 30 | 50 | 0 |  | 0 | 80 |  |  |  | 16
2025-10-20 | 936 | bth | L02_1600_SALP_014 | A | DONE | 10 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 150 | 10 | 70 |  | 0 | 270 |  |  |  | 16
2025-10-20 | 937 | bth | L02_1600_SALP_015 | A | DONE | 8 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 120 | 60 | 0 |  | 0 | 220 |  |  |  | 16
2025-10-20 | 941 | sp | L02_1600_SALP_019 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 20 | 90 | 0 |  | 0 | 120 |  |  |  | 16
2025-10-21 | 944 |  | L02_1600_SAMP_001 | A | DONE | 7 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 160 | 0 | 0 |  | 0 | 350 |  |  |  | 16
2025-10-21 | 945 |  | L02_1600_SAMP_002 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-07 | 140 | 0 | 0 |  | 0 | 360 |  |  |  | 16
2025-10-21 | 946 |  | L02_1600_SAMP_003 | A | DONE | 9 | S-M |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-07 | 210 | 0 | 0 |  | 0 | 320 |  |  |  | 16
2025-10-21 | 948 |  | 76284 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-08 | 110 | 0 | 0 |  | 0 | 230 |  | 052 Crac |  | 15
2025-10-22 | 949 | bth | L02_600_MA_004 | A | DONE | 24 | M |  | PROJECT DOVE 6240041 | spiral mate | 2025-10-23 | Z | 2025-10-08 | 320 | 260 | 0 |  | 0 | 1360 |  |  |  | 15
2025-10-21 | 950 | bth | L02_600_MA_005 | A | DONE | 20 | M |  | PROJECT DOVE 6240041 | spiral mate | 2025-10-23 | Z | 2025-10-08 | 360 | 100 | 40 |  | 0 | 850 |  |  |  | 15
2025-10-21 | 951 | bth | L02_600_MA_006 | A | DONE | 19 | M |  | PROJECT DOVE 6240041 | spiral mate | 2025-10-23 | Z | 2025-10-08 | 240 | 220 | 0 |  | 0 | 1080 |  |  |  | 15
2025-10-21 | 952 | bth | L02_600_MA_007 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 | spiral mate | 2025-10-23 | Z | 2025-10-08 | 160 | 110 | 0 |  | 0 | 500 |  |  |  | 15
2025-10-21 | 953 | bth | L02_600_RA_001 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-08 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 15
2025-10-24 | 954 | sp | L02_600_RA_002 | A | DONE | 5 | S/M |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-08 | 10 | 100 | 0 |  | 0 | 140 |  |  |  | 15
2025-10-21 | 956 |  | L02_600_RAMP_001 | A | DONE | 9 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-08 | 220 | 0 | 0 |  | 0 | 400 |  |  |  | 15
2025-10-22 | 957 |  | L02_600_RAMP_002 | A | DONE | 6 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-08 | 130 | 0 | 0 |  | 0 | 330 |  |  |  | 15
2025-10-21 | 958 |  | L02_600_RAMP_003 | A | DONE | 7 | S-M |  | PROJECT DOVE 6240041 | birdscreen | 2025-10-23 | Z | 2025-10-08 | 170 | 0 | 0 | F | 0 | 490 |  |  |  | 15
2025-10-21 | 959 |  | L02_600_RAMP_004 | A | DONE | 7 | S-M |  | PROJECT DOVE 6240041 | birdscreen | 2025-10-23 | Z | 2025-10-08 | 170 | 0 | 0 |  | 0 | 500 |  |  |  | 15
2025-10-21 | 960 | bth | L02_600_RAMP_005 | A | DONE | 8 | S-M |  | PROJECT DOVE 6240041 | VD spiralmate | 2025-10-23 | Z | 2025-10-08 | 80 | 110 | 0 |  | 0 | 310 |  |  |  | 15
2025-10-21 | 961 |  | L02_600_SALP_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-08 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 15
2025-10-24 | 962 | sp | L02_600_SALP_002 | A | DONE | 7 | S/M |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-08 | 70 | 90 | 0 |  | 0 | 180 |  |  |  | 15
2025-10-20 | 963 | sp | L02_600_SALP_003 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-08 | 10 | 60 | 0 |  | 0 | 60 |  |  |  | 15
2025-10-20 | 964 | sp | L02_600_SALP_004 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-08 | 10 | 40 | 0 |  | 0 | 50 |  |  |  | 15
2025-10-20 | 965 | sp | L02_600_SALP_005 | A | DONE | 5 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-08 | 10 | 100 | 0 |  | 0 | 110 |  |  |  | 15
2025-10-20 | 966 | sp | L02_600_SALP_006 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-08 | 20 | 50 | 0 |  | 0 | 50 |  |  |  | 15
2025-10-20 | 967 | sp | L02_600_SALP_007 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-08 | 0 | 30 | 0 |  | 0 | 30 |  |  |  | 15
2025-10-21 | 968 | sp | L02_600_SALP_008 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | VD | 2025-10-23 | Z | 2025-10-08 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 15
2025-10-24 | 969 | sp | L02_600_SAMP_001 | A | DONE | 5 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-08 | 20 | 100 | 0 |  | 0 | 140 |  |  |  | 15
2025-10-20 | 970 | sp | L02_600_SAMP_002 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-23 | Z | 2025-10-08 | 10 | 40 | 0 |  | 0 | 50 |  |  |  | 15
2025-10-24 | 971 |  | L02_1600_RA_001 | A | DONE | 12 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 200 | 0 | 90 |  | 0 | 350 |  |  |  | 21
2025-10-24 | 972 | bth | L02_1600_RA_002 | A | DONE | 8 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 70 | 20 | 90 |  | 0 | 200 |  |  |  | 21
2025-10-22 | 973 | sp | L02_1600_RA_003 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 20 | 80 | 0 |  | 0 | 90 |  |  |  | 21
2025-10-24 | 974 | sp | L02_1600_RA_004 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 10 | 20 | 0 |  | 0 | 20 |  |  |  | 21
2025-10-24 | 976 | sp | L02_1600_RA_006 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 10 | 30 | 0 |  | 0 | 40 |  |  |  | 21
2025-10-24 | 979 | sp | L02_1600_RA_009 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 10 | 60 | 0 |  | 0 | 60 |  |  |  | 21
2025-10-24 | 980 | sp | L02_1600_RA_010 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 10 | 70 | 0 |  | 0 | 80 |  |  |  | 21
2025-10-24 | 982 |  | L02_1600_RAMP_002 | A | DONE | 4 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 80 | 0 | 0 |  | 0 | 160 |  |  |  | 21
2025-10-21 | 984 | bth | L02_10_902_MA_001 | A | DONE | 22 | M-L |  | PROJECT DOVE 6240041 | s.mates , VD | 2025-10-16 | Z | 2025-10-09 | 290 | 250 | 0 |  | 0 | 900 |  |  |  | 7
2025-10-21 | 985 | bth | L02_10_100_MA_001 | A | DONE | 11 | S-M |  | PROJECT DOVE 6240041 | s.mates , VD | 2025-10-16 | Z | 2025-10-09 | 60 | 210 | 0 |  | 0 | 480 |  |  |  | 7
2025-10-21 | 986 |  | L02_10_100_MA_002 | A | DONE | 7 | S-M |  | PROJECT DOVE 6240041 | VD's | 2025-10-16 | Z | 2025-10-09 | 110 | 0 | 50 | F | 0 | 210 |  |  |  | 7
2025-10-21 | 987 |  | L02_10_100_MA_003 | A | DONE | 16 | M |  | PROJECT DOVE 6240041 |  | 2025-10-16 | Z | 2025-10-09 | 330 | 0 | 50 | F | 0 | 660 |  |  |  | 7
2025-10-24 | 990 | sp | L01_600_EA_003 | A | DONE | 4 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 20 | 80 | 0 |  | 0 | 110 |  |  |  | 20 |  | 2025-11-20
2025-10-24 | 991 | sp | L01_600_EA_004 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 10 | 70 | 0 |  | 0 | 70 |  |  |  | 20 |  | 2025-10-16
2025-10-24 | 993 | bth | L01_600_MA_001 | A | DONE | 8 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 100 | 80 | 0 |  | 0 | 330 |  |  |  | 20 |  | 2025-10-16
2025-10-22 | 2417 |  | 76820-21 | A | DONE | 4 | S |  | ST BENARD 6230023 |  | 2025-10-28 | Z | 2025-10-15 | 100 | 0 | 0 |  | 0 | 150 |  | RF-1, RF-2 |  | 13
2025-10-22 | 541 |  | 81699 - 81700 | A | DONE | 22 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-27 | Z | 2025-09-18 | 390 | 0 | 160 | F | 0 | 1060 |  | RTU-1 SA main |  | 39
2025-10-22 | 542 |  | 81701 | A | DONE | 32 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-27 | Z | 2025-09-18 | 180 | 0 | 600 | F | 0 | 1150 |  | RTU-1 2nd Floor SA main |  | 39
2025-10-22 | 544 |  | 81702 - 81704 | A | DONE | 50 | M |  | SW HEALTH MOB 6250015 |  | 2025-10-27 | Z | 2025-09-18 | 310 | 0 | 920 | F | 0 | 1850 |  | RTU-1 SA West |  | 39
2025-10-22 | 545 |  | 81705 - 81706 | A | DONE | 22 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-27 | Z | 2025-09-18 | 130 | 0 | 410 | F | 0 | 650 |  | RTU-1 SA West |  | 39
2025-10-22 | 546 | sp | 81707 | A | DONE | 6 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-27 | Z | 2025-09-18 | 10 | 130 | 0 | F | 0 | 130 |  | RTU-1 SA West |  | 39
2025-10-22 | 547 |  | 81708 | A | DONE | 4 | S |  | SW HEALTH MOB 6250015 |  | 2025-10-27 | Z | 2025-09-19 | 50 | 0 | 40 | F | 0 | 110 |  | EF-4 |  | 38
2025-10-22 | 548 | sp | 81709 - 81710 | A | DONE | 6 | S-M |  | SW HEALTH MOB 6250015 |  | 2025-10-27 | Z | 2025-09-19 | 30 | 100 | 0 |  | 0 | 120 |  | EF-4 |  | 38
2025-10-21 | 549 |  | 81711 | A | DONE | 4 | S |  | SW HEALTH MOB 6250015 |  | 2025-10-27 | Z | 2025-09-19 | 20 | 0 | 60 |  | 0 | 90 |  | EF-3 EA |  | 38
2025-10-21 | 4699 |  | 82240 | A | DONE | 3 | S |  | TOMAH HEALTH 6250006 | 1" liner | 2025-10-27 | Z | 2025-10-15 | 50 | 0 | 0 |  | 40 | 70 |  | Bathroom trans. |  | 12
2025-10-22 | 2972 |  | 77357 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2025-10-28 | Z | 2025-10-23 | 20 | 0 | 0 |  | 0 | 70 |  | Infill |  | 5
2025-10-21 | 3125 |  | 54546 | A | DONE | 2 | S |  | UW VET MED 2250030 |  | 2025-10-22 | Z | 2025-10-20 | 20 | 0 | 0 |  | 0 | 40 |  | BSC 3 testing |  | 2
2025-10-21 | 3126 |  | 54547 | A | DONE | 2 | S |  | UW VET MED 6210014 | paint black | 2025-10-24 | Z | 2025-10-21 | 20 | 0 | 0 |  | 10 | 40 |  | 1st hall EA |  | 3
2025-10-20 | 1436 |  | MER-SAMP 5 | A | DONE | 28 | M-L |  | UW-LEVY HALL 6230028 |  | 2025-10-16 | Z | 2025-09-18 | 390 | 0 | 310 | F | 0 | 1380 |  |  |  | 28
2025-10-21 | 1437 |  | MER-EAMP 8 | A | DONE | 27 | M-L |  | UW-LEVY HALL 6230028 | MOD | 2025-10-16 | Z | 2025-09-19 | 460 | 0 | 200 |  | 0 | 1060 |  |  |  | 27
2025-10-21 | 1438 |  | MER-EAMP 9 | A | DONE | 5 | S |  | UW-LEVY HALL 6230028 | MOD | 2025-10-16 | Z | 2025-09-19 | 110 | 0 | 0 |  | 0 | 210 |  |  |  | 27
2025-10-21 | 1441 |  | MER-SAMP 6 | A | DONE | 8 | S-M |  | UW-LEVY HALL 6230028 | AFMS , MOD | 2025-10-16 | Z | 2025-09-19 | 200 | 0 | 0 |  | 0 | 390 |  |  |  | 27
2025-10-21 | 1442 |  | MER-SAMP 7 | A | DONE | 10 | S-M |  | UW-LEVY HALL 6230028 | MOD | 2025-10-16 | Z | 2025-09-19 | 140 | 0 | 100 |  | 0 | 540 |  |  |  | 27
2025-10-22 | 2179a |  | MER-SAMP 1 | A | DONE | 66 | L |  | UW-LEVY HALL 6230028 | partial | 2025-10-23 | Z | 2025-08-12 | 1380 | 0 | 0 |  | 0 | 3600 |  |  |  | 72 |  | 2025-11-20
2025-10-20 | 4817 |  | 78301 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2025-10-21 | Z | 2025-10-15 | 20 | 0 | 0 |  | 0 | 30 |  | cb144 |  | 6
2025-10-21 | 2201 | w | 77355 - 77356 | A | DONE | 7 | S-M |  | UW-STOUT 6250008 |  | 2025-10-21 | Z | 2025-10-09 | 160 | 0 | 0 |  | 0 | 550 |  | Pans |  | 12
2025-10-21 | 3120 |  | 54540 | A | DONE | 3 | S-M |  | UW-VET MED 6210014 | bird s. | 2025-10-22 | Z | 2025-09-22 | 70 | 0 | 0 |  | 0 | 200 |  | 7B OA Louver |  | 30
2025-10-22 | 3121 |  | 54541 - 54542 | A | DONE | 4 | M |  | UW-VET MED 6210014 | VD's | 2025-10-22 | Z | 2025-09-22 | 30 | 0 | 0 |  | 0 | 40 |  | 7B EA Louver |  | 30
2025-10-22 | 3124 |  | 54544-45 | A | DONE | 3 | S | ss | UW-VET MED 6210014 |  | 2025-10-24 | Z | 2025-10-14 | 20 | 40 | 0 |  | 0 | 80 |  |  |  | 10
2025-10-22 | 2370 |  | 75404-75361 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-10-24 | Z | 2025-10-21 | 40 | 0 | 0 |  | 0 | 70 |  | Grille box |  | 3 |  | 2025-11-20
2025-10-21 | 2366 |  | 75360 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-24 | Z | 2025-10-15 | 70 | 0 | 0 |  | 0 | 110 |  | Exhaust drop |  | 9
2025-10-21 | 2368 |  | 83397 | A | DONE | 6 | S |  | WAUNAKEE MS 6230013 |  | 2025-10-24 | Z | 2025-10-16 | 140 | 0 | 0 |  | 0 | 160 |  | 2nd A sect |  | 8
[6 empty] | 1194 | [13 empty] | 45260
WEEK OF 10-27-2025
2025-10-28 | 102 |  | 74026 | A | DONE | 2 | S | BI | BTC 6250020 |  | 2025-10-29 | Z | 2025-10-28 | 10 | 0 | 0 |  | 0 | 30 |  | Misc |  | 1
2025-10-27 | 100 |  | 79471 | A | DONE | 2 | S |  | CHFH 6240037 |  | 2025-10-28 | Z | 2025-10-27 | 10 | 0 | 0 |  | 0 | 20 |  | Grill box |  | 1
2025-10-30 | 3951 |  | 74010 | A | DONE | 23 | M |  | DELLSHIRE 6240017 |  | 2025-11-03 | Z | 2025-10-21 | 320 | 0 | 0 |  | 0 | 560 |  | Kitchen hood 1 plenum |  | 13
2025-10-28 | 3952 | bth | 74012 | A | DONE | 16 | M |  | DELLSHIRE 6240017 |  | 2025-11-03 | Z | 2025-10-21 | 70 | 390 | 0 |  | 0 | 390 |  | Misc. ex. |  | 13
2025-10-30 | 3955 | bth | 74014-15 | A | DONE | 66 | L | neal | DELLSHIRE 6240017 | spiralmate | 2025-11-03 | Z | 2025-10-22 | 410 | 310 | 120 |  | 40 | 1650 |  |  |  | 12
2025-10-30 | 3956 | sp | 74013 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2025-11-03 | Z | 2025-10-24 | 20 | 20 | 0 |  | 0 | 40 |  | Attic EA |  | 10
2025-10-30 | 3957 |  | 74018 | A | DONE | 22 | M |  | DELLSHIRE 6240017 |  | 2025-11-03 | Z | 2025-10-24 | 330 | 180 | 0 |  | 0 | 550 |  | Kitchen hood 2 |  | 10
2025-10-30 | 3958 |  | 75274 | A | DONE | 4 | S |  | DELLSHIRE 6240017 |  | 2025-11-03 | Z | 2025-10-24 | 60 | 0 | 0 |  | 0 | 100 |  | Kitchen SA |  | 10
2025-10-28 | 3960 |  | 74020 | A | DONE | 12 | S/M |  | DELLSHIRE 6240017 |  | 2025-10-30 | Z | 2025-10-24 | 100 | 0 | 0 |  | 0 | 280 |  | Kitchen louver |  | 6
2025-10-30 | 3962 |  | 74025 | A | DONE | 4 | S |  | DELLSHIRE 6240017 | paint black | 2025-11-03 | Z | 2025-10-28 | 120 | 0 | 0 |  | 0 | 100 |  | extra sliders |  | 6
2025-10-29 | 3192 |  | Z3-RA 30 | A | DONE | 29 | M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-09-18 | 330 | 0 | 240 |  | 0 | 710 |  |  |  | 42 |  | 2025-09-02
2025-10-29 | 3193 |  | Z3-RA 31 | A | DONE | 16 | M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-09-18 | 150 | 0 | 180 |  | 0 | 390 |  |  |  | 42 |  | 2025-09-02
2025-10-27 | 4783 |  | 56075 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-10-21 | 20 | 0 | 0 |  | 0 | 30 |  | Z3-EA-86 |  | 9
2025-10-29 | 4784 |  | 84387 | A | DONE | 25 | M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-10-22 | 220 | 0 | 0 |  | 0 | 620 |  |  |  | 8 |  | 2025-10-16
2025-10-28 | 674 | bth | Z1-EA 13 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | MOD | 2025-10-30 | Z | 2025-07-22 | 40 | 80 | 20 |  | 0 | 150 |  |  |  | 100 | 2025-10-23
2025-10-28 | 675 |  | Z1-EA 14 | A | DONE | 18 | M |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-22 | 230 | 0 | 80 |  | 0 | 430 |  |  |  | 100 | 2025-10-23
2025-10-28 | 676 |  | Z1-EA 15 | A | DONE | 20 | M |  | DOC JDC 6240023 | VD's | 2025-10-30 | Z | 2025-07-22 | 310 | 0 | 0 |  | 0 | 480 |  |  |  | 100 | 2025-10-23
2025-10-29 | 677 |  | Z1-EA 16 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-22 | 30 | 110 | 0 |  | 0 | 130 |  |  |  | 100 | 2025-10-23
2025-10-29 | 679 |  | Z1-EA 18 | A | DONE | 5 | S/M |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-22 | 40 | 0 | 50 |  | 0 | 110 |  |  |  | 100 | 2025-10-23
2025-10-28 | 689 | bth | Z1-EA 28 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | cable damper , MOD | 2025-10-30 | Z | 2025-07-22 | 110 | 10 | 0 |  | 0 | 150 |  |  |  | 100 | 2025-10-23
2025-10-28 | 690 |  | Z1-EA 29 | A | DONE | 2 | S |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-22 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 100 | 2025-10-23
2025-10-29 | 691 |  | Z1-EA 30 | A | DONE | 12 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-22 | 90 | 90 | 60 |  | 0 | 280 |  |  |  | 100 | 2025-10-23
2025-10-29 | 697 |  | Z2- OA 13 | A | DONE | 21 | M |  | DOC JDC 6240023 | VD's | 2025-10-30 | Z | 2025-07-30 | 270 | 0 | 150 |  | 0 | 520 |  |  |  | 92 | 2025-09-04
2025-10-28 | 704 |  | Z2-EA 35 | A | DONE | 19 | M |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-30 | 310 | 0 | 0 |  | 0 | 460 |  |  |  | 92 | 2025-09-04
2025-10-28 | 705 |  | Z2-EA 36 | A | DONE | 10 | S/M |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-30 | 180 | 0 | 40 |  | 0 | 250 |  |  |  | 92 | 2025-09-04
2025-10-27 | 727 |  | Z2-EA 58 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 50 | 0 | 130 |  |  | 210 |  |  |  | 92 | 2025-09-04
2025-10-27 | 728 | bth | Z2-EA 59 | A | DONE | 12 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 40 | 110 | 130 |  | 0 | 300 |  |  |  | 92 | 2025-09-04
2025-10-27 | 737 | bth | Z1-RA 4 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 80 | 20 | 70 |  |  | 210 |  |  |  | 92 | 2025-09-11
2025-10-28 | 738 | bth | Z1-RA 5 | A | DONE | 8 | S/M | pt.neal | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 110 | 40 | 30 |  | 0 | 180 |  |  |  | 92 | 2025-09-11
2025-10-28 | 739 | sp | Z1-RA 6 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 30 | 140 | 0 |  | 0 | 170 |  |  |  | 92 | 2025-09-11
2025-10-28 | 741 | bth | Z1-RA 8 | A | DONE | 21 | M |  | DOC JDC 6240023 | VD | 2025-11-06 | Z | 2025-07-30 | 290 | 0 | 150 |  | 0 | 520 |  |  |  | 99 | 2025-09-11 | 2025-11-13
2025-10-29 | 742 | bth | Z1-RA 9 | A | DONE | 12 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 90 | 100 | 60 |  | 0 | 300 |  |  |  | 92 | 2025-09-11 | 2025-09-02
2025-10-29 | 743 | bth | Z1-RA 10 | A | DONE | 2 | S |  | DOC JDC 6240023 | flex | 2025-10-30 | Z | 2025-07-30 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 92 | 2025-09-11
2025-10-28 | 744 | bth | Z1-RA 11 | A | DONE | 30 | M |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-30 | 300 | 30 | 50 |  | 0 | 730 |  |  |  | 92 | 2025-09-11
2025-10-28 | 745 |  | Z1-RA 12 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 110 | 0 | 30 |  | 0 | 190 |  |  |  | 92 | 2025-09-11 | 2025-11-20
2025-10-28 | 746 | bth | Z1-RA 13 | A | DONE | 18 | M |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-30 | 190 | 30 | 130 |  | 0 | 450 |  |  |  | 92 | 2025-09-11 | 2025-11-20
2025-10-28 | 747 | bth | Z1-RA 14 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 70 | 20 | 40 |  | 0 | 150 |  |  |  | 92 | 2025-09-11
2025-10-28 | 748 | bth | Z1-RA 15 | A | DONE | 13 | S/M |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-30 | 150 | 40 | 60 |  | 0 | 310 |  |  |  | 92 | 2025-09-11
2025-10-28 | 749 | bth | Z1-RA 16 | A | DONE | 28 | M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 460 | 30 | 110 |  | 0 | 690 |  |  |  | 92 | 2025-09-11
2025-10-28 | 750 | bth | Z1-RA 17 | A | DONE | 12 | S/M |  | DOC JDC 6240023 | VD | 2025-10-30 | Z | 2025-07-30 | 140 | 110 | 0 |  | 0 | 300 |  |  |  | 92 | 2025-09-11
2025-10-29 | 751 | bth | Z1-RA 18 | A | DONE | 16 | M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 160 | 190 | 0 |  | 0 | 400 |  |  |  | 92 | 2025-09-11
2025-10-28 | 752 | bth | Z1-RA 19 | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 230 | 50 | 60 |  | 0 | 440 |  |  |  | 92 | 2025-09-11
2025-10-29 | 753 | bth | Z1-RA 20 | A | DONE | 36 | M/L |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-07-30 | 220 | 20 | 270 |  | 0 | 900 |  |  |  | 92 | 2025-09-11
2025-10-29 | 761 | bth | Z2-RA 24 | A | DONE | 33 | M/L |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-08-05 | 350 | 120 | 130 |  | 0 | 810 |  |  |  | 86 | 2025-09-25
2025-10-29 | 762 | bth | Z2-RA 25 | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-08-05 | 150 | 10 | 150 |  | 0 | 430 |  |  |  | 86 | 2025-09-25
2025-10-29 | 763 | bth | Z2-RA 26 | A | DONE | 21 | M |  | DOC JDC 6240023 |  | 2025-10-30 | Z | 2025-08-05 | 200 | 100 | 100 |  | 0 | 520 |  |  |  | 86 | 2025-09-25
2025-10-29 | 1100 | bth | 81307 | A | DONE | 3 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 20 | 40 | 0 |  | 0 | 60 |  | VAV-1 |  | 10
2025-10-29 | 1101 | bth | 81308 | A | DONE | 2 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 20 | 10 | 0 |  | 0 | 20 |  | VAV-2 |  | 10
2025-10-30 | 1102 | bth | 81310 | A | DONE | 4 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 60 | 40 | 0 |  | 0 | 100 |  | VAV-3 |  | 10
2025-10-29 | 1103 | bth | 81311 | A | DONE | 3 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 20 | 50 | 0 |  | 0 | 70 |  | VAV-4 |  | 10
2025-10-30 | 1104 | bth | 81312 | A | DONE | 3 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 30 | 30 | 0 |  | 0 | 60 |  | VAV-5 |  | 10
2025-10-29 | 1105 | bth | 81313 | A | DONE | 2 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 10 | 10 | 0 |  | 0 | 20 |  | VAV-6 |  | 10
2025-10-29 | 1106 | bth | 81314 | A | DONE | 2 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 10 | 30 | 0 |  | 0 | 40 |  | VAV-7 |  | 10
2025-10-29 | 1107 | bth | 81315 | A | DONE | 2 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 10 | 10 | 0 |  | 0 | 20 |  | VAV-8 |  | 10
2025-10-29 | 1108 | bth | 81316 | A | DONE | 3 | S |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 10 | 50 | 0 |  | 0 | 60 |  | VAV-9 |  | 10
2025-10-28 | 1109 |  | 81317 | A | DONE | 9 | S/M |  | GRANT ELEM. 6250021 |  | 2025-11-03 | Z | 2025-10-24 | 130 | 0 | 0 |  | 0 | 210 |  |  |  | 10
2025-10-29 | 300 |  | 69060 | A | DONE | 3 | S | pcd | LABCORP 6240016 |  | 2025-11-03 | Z | 2025-10-23 | 20 | 50 | 0 |  | 0 | 70 |  | 1st fl fame |  | 11
2025-10-27 | 3919 |  | 83655 | A | DONE | 3 | S/M |  | MONROE HS 6240018 | 2" liner | 2025-10-28 | Z | 2025-10-15 | 70 | 0 | 0 |  | 60 | 110 |  | Outs |  | 13
2025-10-27 | 3921R |  | 85048 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-10-28 | Z | 2025-10-27 | 20 | 0 | 0 |  | 20 | 50 |  | Boiler caps |  | 1
2025-10-28 | 3922 |  | RA-L1E-06 | A | DONE | 18 | S |  | MONROE HS 6240018 | 1" liner | 2025-10-30 | Z | 2025-10-27 | 250 | 0 | 0 |  | 230 | 440 |  |  |  | 3
2025-10-30 | 1054 | sp | 76829-30 | A | DONE | 20 | M | neal | PEWAUKEE HS 6240030 |  | 2025-11-03 | Z | 2025-10-21 | 70 | 290 | 0 |  | 0 | 490 |  | Manufacturing room |  | 13
2025-10-27 | 1057 |  | 76833 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-10-28 | Z | 2025-10-23 | 30 | 0 | 0 |  | 0 | 50 |  | RA tie ins |  | 5
2025-10-28 | 1058 |  | 76851 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-10-29 | Z | 2025-10-27 | 10 | 0 | 0 |  | 0 | 20 |  | Hetos |  | 2
2025-10-29 | 1059 |  | 76853 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-11-04 | Z | 2025-10-28 | 10 | 0 | 0 |  | 0 | 20 |  | Pipe flashing |  | 7
2025-10-27 | 1000 | sp | L01_600_RA_002 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 0 | 30 | 0 |  | 0 | 40 |  |  |  | 20
2025-10-27 | 1002 | sp | L01_600_RAMP_001 | A | DONE | 5 | S/M |  | PROJECT DOVE 6240041 | spiral mate | 2025-10-30 | Z | 2025-10-10 | 20 | 100 | 0 |  | 0 | 170 |  |  |  | 20
2025-10-27 | 1003 |  | L01_600_RAMP_002 | A | DONE | 10 | M |  | PROJECT DOVE 6240041 | bird s. | 2025-10-30 | Z | 2025-10-10 | 50 | 0 | 190 |  | 0 | 430 |  |  |  | 20 |  | 2025-10-16
2025-10-27 | 1004 | bth | L01_600_SALP_001 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 40 | 20 | 0 |  | 0 | 60 |  |  |  | 20 |  | 2025-10-16
2025-10-27 | 1005 | bth | L01_600_SALP_002 | A | DONE | 5 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 40 | 70 | 0 |  | 0 | 120 |  |  |  | 20 |  | 2025-11-20
2025-10-27 | 1011 | sp | L01_600_SAMP_001 | A | DONE | 7 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 30 | 140 | 0 |  | 0 | 180 |  |  |  | 20 |  | 2025-11-20
2025-10-30 | 1013 |  | 76190 | A | DONE | 31 | M | ss | PROJECT DOVE 6240041 | flex | 2025-10-30 | Z | 2025-10-16 | 280 | 0 | 0 |  | 0 | 760 |  |  |  | 14
2025-10-27 | 1015w |  | L02_AREA_300_EA_002 | A | DONE | 4 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-10-28 | Z | 2025-10-20 | 90 | 0 | 0 |  | 0 | 240 |  |  |  | 8 | 2025-10-30
2025-10-28 | 1016w |  | L02_AREA_300_EA_003 | A | DONE | 14 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-10-28 | Z | 2025-10-20 | 140 | 0 | 0 |  | 0 | 330 |  |  |  | 8 | 2025-10-30
2025-10-30 | 1029 | w | L01_AREA_300_EA_004 | A | DONE | 8 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-23 | 60 | 0 | 0 |  | 0 | 200 |  |  |  | 7
2025-10-30 | 1030 | w | L01_AREA_300_EA_005 | A | DONE | 9 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-23 | 80 | 0 | 0 |  | 0 | 210 |  |  |  | 7
2025-10-28 | 1035 |  | 55141 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-28 | 40 | 0 | 0 |  | 0 | 50 |  | Angles |  | 2
2025-10-29 | 1609 |  | 76262 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-31 | Z | 2025-09-05 | 60 | 0 | 0 |  | 0 | 90 |  | Slot difusers |  | 56
2025-10-29 | 914r |  | 74808 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 | bird screen | 2025-10-30 | Z | 2025-10-28 | 20 | 0 | 0 |  | 0 | 60 |  | 400 tower |  | 2
2025-10-27 | 975 | sp | L02_1600_RA_005 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 20 | 60 | 0 |  | 0 | 90 |  |  |  | 21
2025-10-27 | 977 | bth | L02_1600_RA_007 | A | DONE | 10 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 190 | 10 | 40 |  | 0 | 270 |  |  |  | 21
2025-10-27 | 978 | bth | L02_1600_RA_008 | A | DONE | 8 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 50 | 40 | 90 |  | 0 | 210 |  |  |  | 21
2025-10-27 | 981 |  | L02_1600_RAMP_001 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 70 | 0 | 0 |  | 0 | 90 |  |  |  | 21
2025-10-27 | 983 |  | L02_1600_RAMP_003 | A | DONE | 6 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-09 | 140 | 0 | 0 |  | 0 | 230 |  |  |  | 21
2025-10-27 | 984r |  | Hand Drawn | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-28 | Z | 2025-10-24 | 10 | 0 | 0 |  | 0 | 60 |  | saddle hangers |  | 4
2025-10-27 | 988 |  | L01_600_EA_001 | A | DONE | 6 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 90 | 0 | 60 |  | 0 | 210 |  |  |  | 20
2025-10-27 | 989 |  | L01_600_EA_002 | A | DONE | 9 | M |  | PROJECT DOVE 6240041 | spiral mate | 2025-10-30 | Z | 2025-10-10 | 180 | 0 | 40 |  | 0 | 400 |  |  |  | 20
2025-10-27 | 992 |  | L01_600_EA_005 | A | DONE | 11 | M |  | PROJECT DOVE 6240041 | bird s. | 2025-10-30 | Z | 2025-10-10 | 30 | 0 | 240 |  | 0 | 380 |  |  |  | 20 |  | 2025-10-16
2025-10-27 | 994 |  | L01_600_MA_002 | A | DONE | 5 | S/M |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 50 | 0 | 70 |  | 0 | 190 |  |  |  | 20
2025-10-27 | 995 |  | L01_600_MA_003 | A | DONE | 15 | M |  | PROJECT DOVE 6240041 | VD's | 2025-10-30 | Z | 2025-10-10 | 180 | 0 | 190 |  | 0 | 640 |  |  |  | 20
2025-10-27 | 996 | sp | L01_600_MA_004 | A | DONE | 10 | S/M |  | PROJECT DOVE 6240041 | VD | 2025-10-30 | Z | 2025-10-10 | 40 | 200 | 0 |  | 0 | 280 |  |  |  | 20
2025-10-27 | 997 | bth | L01_600_MA_005 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 20
2025-10-27 | 998 | bth | L01_600_MA_006 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 20
2025-10-27 | 999 |  | L01_600_RA_001 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-10-30 | Z | 2025-10-10 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 20
2025-10-30 | 1375 | bth | 75868 - 75869 | A | DONE | 4 | S | semi | RICHLAND CTR. 6250011 | flex | 2026-01-26 | Z | 2025-10-01 | 20 | 80 | 0 |  | 0 | 90 |  | Art EA |  | 117
2025-10-28 | 862 |  | 68889 | A | DONE | 4 | S |  | SPH 6240039 |  | 2025-11-03 | Z | 2025-10-21 | 20 | 70 | 0 |  | 0 | 100 |  | Rau 4-38 |  | 13
2025-10-30 | 2100 |  | 81712 | A | DONE | 4 | S |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-23 | 40 | 0 | 40 |  | 0 | 100 |  | EF-1 EA |  | 41
2025-10-30 | 2101 |  | 81714 - 81715 | A | DONE | 7 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-23 | 50 | 30 | 70 |  | 0 | 160 |  | EF-2 |  | 41
2025-10-30 | 2102 |  | 81716 - 81718 | A | DONE | 21 | M |  | SW HEALTH MOB 6250015 | paint | 2025-11-03 | Z | 2025-09-24 | 180 | 0 | 210 |  | 10 | 520 |  | VAV 2-2 LPSA |  | 40
2025-10-29 | 2103 | sp | 81719 - 81720 | A | DONE | 11 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-24 | 30 | 250 | 0 |  | 0 | 260 |  | 2-2 , 2-3 LPSA |  | 40
2025-10-30 | 2104 |  | 81721 | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-24 | 30 | 0 | 0 |  | 0 | 50 |  | VAV 2-6 LPSA |  | 40
2025-10-29 | 2105 | sp | 81722 - 81723 | A | DONE | 6 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-24 | 30 | 110 | 0 |  | 0 | 130 |  | VAV 2-6 LPSA |  | 40
2025-10-29 | 2108 | sp | 81725 - 81726 | A | DONE | 12 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-26 | 30 | 270 | 0 |  | 0 | 280 |  | VAV 2-5 LPSA |  | 38
2025-10-28 | 2111 | sp | 81728 - 81729 | A | DONE | 6 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-26 | 20 | 140 | 0 |  | 0 | 140 |  | VAV - 2-1 LPSA |  | 38
2025-10-30 | 2112 |  | 69753 | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-29 | 30 | 0 | 0 |  | 0 | 50 |  | EF-2 |  | 35
2025-10-28 | 3144 |  | 69754 | A | DONE | 3 | S |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-10-20 | 10 | 60 | 0 |  | 0 | 70 |  |  |  | 14
2025-10-29 | 3148 |  | 69765 | A | DONE | 2 | S |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-10-22 | 10 | 0 | 0 |  | 0 | 20 |  | Rm 219 RA |  | 12 |  | 2025-10-16
2025-10-28 | 3116 |  | 69064 | A | DONE | 2 | S |  | UW AVRL 6240038 |  | 2025-10-30 | Z | 2025-10-27 | 10 | 0 | 0 |  | 0 | 20 |  | freezer farm |  | 3
2025-10-28 | 3117 |  | 6240038 | A | DONE | 5 | S |  | UW AVRL 6240038 |  | 2025-10-31 | Z | 2025-10-27 | 10 | 0 | 0 |  | 0 | 110 |  |  |  | 4
2025-10-27 | 4821 |  | 78306 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | flex | 2025-10-28 | Z | 2025-10-23 | 20 | 0 | 0 |  | 0 | 20 |  | flexes |  | 5
2025-10-28 | 4821r |  | 78306 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | flex | 2025-11-04 | Z | 2025-10-23 | 20 | 0 | 0 |  | 0 | 20 |  | LL FCU |  | 12
2025-10-29 | 4824 |  | 76123 | A | DONE | 4 | S |  | UW LEVY HALL 6230028 |  | 2025-11-04 | Z | 2025-10-28 | 30 | 0 | 0 |  | 0 | 90 |  |  |  | 7
2025-10-30 | 4825 |  | 78257 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | VD | 2025-11-04 | Z | 2025-10-28 | 10 | 0 | 0 |  | 0 | 30 |  | Misc dampers |  | 7
2025-10-27 | 2972 |  | 77357 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2025-10-28 | Z | 2025-10-23 | 20 | 0 | 0 |  | 0 | 50 |  | Infills |  | 5
2025-10-27 | 2973 |  | 77358 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2025-10-27 | Z | 2025-10-27 | 20 | 0 | 0 |  | 0 | 40 |  | flat stock |  | 0
2025-10-29 | 3127 |  | 54546-2 | A | DONE | 2 | S |  | UW VET MED 2250030 |  | 2025-11-03 | Z | 2025-10-29 | 10 | 0 | 0 |  | 0 | 20 |  | BSC 3 tesing |  | 5
2025-10-29 | 4819 |  | 78303 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 | VD | 2025-11-04 | Z | 2025-10-17 | 10 | 10 | 0 |  | 0 | 10 |  | L1 3-1-8 |  | 18
2025-10-29 | 4802 |  | MER-RAMP 6 | A | DONE | 117 | L |  | UW-LEVY HALL 6230028 |  | 2025-10-30 | Z | 2025-09-22 | 1270 | 0 | 0 |  | 0 | 2920 |  |  |  | 38
2025-10-27 | 4816 |  | 78051 - 78054 | A | DONE | 24 | M/L |  | UW-LEVY HALL 6230028 | paint , bird s.,1" liner | 2025-10-28 | Z | 2025-10-13 | 590 | 0 | 0 |  | 510 | 810 |  | TA |  | 15
2025-10-30 | 4818 |  | 78302 | A | DONE | 14 | S/M |  | UW-LEVY HALL 6230028 |  | 2025-11-04 | Z | 2025-10-16 | 380 | 0 | 0 |  | 0 | 350 |  |  |  | 19
2025-10-28 | 2202 |  | Pre-fab Hangers | A | DONE | 30 | M |  | UWS HERITAGE HALL 6250008 |  | 2025-11-04 | Z | 2025-10-15 | 280 | 0 | 0 |  | 0 | 750 |  | Tear drops |  | 20
2025-10-29 | 3275 |  | 61492 | A | DONE | 2 | S |  | UWSP-ALBERTON 6230016 |  | 2025-11-03 | Z | 2025-10-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2025-10-27 | 2371 |  | 82924 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-10-24 | Z | 2025-10-22 | 30 | 0 | 0 |  | 20 | 40 |  | 2nd a outs |  | 2 |  | 2025-10-16
2025-10-28 | 2372 |  | 82925 | A | DONE | 2 | S |  | WAUNAKEE 6230013 | flex | 2025-10-31 | Z | 2025-10-22 | 10 | 0 | 30 |  | 0 | 40 |  | 2nd a outs |  | 9 |  | 2025-10-16
2025-10-27 | 2373 |  | 75405 | A | DONE | 2 | S |  | WAUNAKEE 6230013 | 1" liner | 2025-10-31 | Z | 2025-10-22 | 10 | 0 | 0 |  | 10 | 30 |  | 2G grill box |  | 9 |  | 2025-10-16
2025-10-30 | 2374 |  | 83059-60,82926 | A | DONE | 8 | S/M |  | WAUNAKEE 6230013 | flex | 2025-10-31 | Z | 2025-10-27 | 70 | 0 | 0 |  | 110 | 190 |  | HP 218 2nd A |  | 4
2025-10-29 | 2375 |  | 82928 | A | DONE | 2 | S |  | WAUNAKEE 6230013 | VD | 2025-10-31 | Z | 2025-10-29 | 10 | 0 | 0 |  | 0 | 20 |  | 1st B |  | 2
2025-10-27 | 2367 |  | 75402-03 | A | DONE | 10 | M |  | WAUNAKEE MS 6230013 | CD | 2025-10-24 | Z | 2025-10-15 | 250 | 0 | 0 |  | 0 | 640 |  | Louver sleeves |  | 9
[6 empty] | 1296 | [13 empty] | 33060
WEEK OF 11-3-2025
2025-11-04 | 3050 |  | 74256 | A | DONE | 2 | S | ss | BARTILLION 6240024 | paint black, neal | 2025-11-10 | Z | 2025-11-03 | 10 | 0 | 0 |  | 10 | 40 |  | Gille box |  | 7
2025-11-05 | 2935 | bth | 58176-80 | A | DONE | 10 | S/M |  | BROOM ST 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 120 | 130 | 0 |  | 0 | 240 |  | Sleeves |  | 14
2025-11-04 | 2936 | bth | 79535-38 | A | DONE | 11 | S/M |  | BROOM ST 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 120 | 160 | 0 |  | 0 | 260 |  | L4/L5 East |  | 14
2025-11-03 | 1214 |  | 80409 | A | DONE | 16 | M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-30 | 140 | 0 | 0 |  | 0 | 380 |  | Sleeves |  | 6
2025-11-04 | 1237 |  | 80410 | A | DONE | 15 | M |  | BROOM ST. 6240033 |  | 2025-11-04 | Z | 2025-11-04 | 170 | 0 | 0 |  | 0 | 360 |  | Hpump angle |  | 0 | 2025-11-06
2025-11-03 | 2918 |  | M4.73 UNIT 240 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 70 | 0 | 20 |  | 0 | 100 |  |  |  | 14
2025-11-04 | 2921 |  | M4.76 UNIT 243 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 90 | 0 | 0 |  | 0 | 100 |  |  |  | 14 | 2025-11-06
2025-11-04 | 2922 |  | M4.77 UNIT 244 | A | DONE | 16 | M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 180 | 0 | 200 |  | 0 | 400 |  |  |  | 14 | 2025-11-06
2025-11-03 | 2923 |  | M4.78 UNIT 245 | A | DONE | 22 | M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 200 | 0 | 330 |  | 0 | 530 |  |  |  | 14
2025-11-03 | 2924 |  | M4.79 UNIT 246 | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 180 | 0 | 180 |  | 0 | 350 |  |  |  | 14
2025-11-04 | 2925 |  | M4.80 UNIT 247 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 70 | 0 | 70 |  | 0 | 140 |  |  |  | 14
2025-11-03 | 2926 |  | M4.81 UNIT 248 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 70 | 0 | 20 |  | 0 | 90 |  |  |  | 14 |  | 2025-10-16
2025-11-03 | 2927 |  | M4.82 UNIT 249 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 190 | 0 | 110 |  | 0 | 280 |  |  |  | 14 |  | 2025-10-16
2025-11-03 | 2928 |  | M4.83 UNIT 250 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 70 | 0 | 40 |  | 0 | 110 |  |  |  | 14
2025-11-03 | 2929 |  | M4.84 UNIT 251 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 70 | 0 | 40 |  | 0 | 110 |  |  |  | 14
2025-11-03 | 2930 |  | M4.85 UNIT 252 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 90 | 0 | 0 |  | 0 | 100 |  |  |  | 14
2025-11-03 | 2931 |  | M4.86 UNIT 253 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 60 | 0 | 40 |  | 0 | 100 |  |  |  | 14
2025-11-03 | 2932 |  | M4.87 UNIT 254 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 14
2025-11-03 | 2933 |  | M4.88 UNIT 255 | A | DONE | 16 | M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 220 | 0 | 200 |  | 0 | 400 |  |  |  | 14
2025-11-03 | 2934 |  | M4.89 UNIT 256 | A | DONE | 13 | S/M |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-22 | 140 | 0 | 190 |  | 0 | 320
2025-11-03 | 3954 | sp | 74054-55 | A | DONE | 17 | M | neal | DELLSHIRE 6240017 | spiralmate | 2025-11-03 | Z | 2025-10-22 | 50 | 300 | 0 |  | 0 | 410 |  |  |  | 12
2025-11-04 | 3959 | bth | 74016-17 | A | DONE | 78 | L |  | DELLSHIRE 6240017 |  | 2025-11-06 | Z | 2025-10-24 | 430 | 130 | 1000 |  | 0 | 1940 |  | 253 RA, Corr. 237 RA |  | 13
2025-11-05 | 3963 |  | 75276 | A | DONE | 3 | S |  | DELLSHIRE 6240017 |  | 2025-11-05 | Z | 2025-11-04 | 40 | 0 | 0 |  | 0 | 70 |  | Restaurant |  | 1
2025-11-03 | 4731 |  | ZP-EA 91 | A | DONE | 2 | S |  | DOC JDC 6240023 | bird s. , MOD-20 | 2025-11-06 | Z | 2025-09-30 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 37
2025-11-03 | 4732 |  | ZP-EA 92 | A | DONE | 2 | S |  | DOC JDC 6240023 | bird s. , MOD-19 | 2025-11-06 | Z | 2025-09-30 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 37
2025-11-04 | 4733 |  | ZP-EA 93 | A | DONE | 25 | M |  | DOC JDC 6240023 |  | 2025-11-06 | Z | 2025-09-30 | 190 | 0 | 240 |  | 0 | 620 |  |  |  | 37
2025-11-04 | 4734 |  | ZP-EA 94 | A | DONE | 19 | M |  | DOC JDC 6240023 |  | 2025-11-06 | Z | 2025-09-30 | 250 | 0 | 140 |  | 0 | 460 |  |  |  | 37
2025-11-05 | 4768 |  | ZP-RA 50 | A | DONE | 5 | S/M |  | DOC JDC 6240023 | partial | 2025-11-20 | Z | 2025-10-16 | 80 | 0 | 0 |  | 0 | 120 |  |  |  | 35
2025-11-03 | 4785 |  | 56076 | A | DONE | 11 | S/M |  | DOC JDC 6240023 |  | 2025-11-07 | Z | 2025-10-28 | 150 | 0 | 0 |  | 0 | 270 |  | Zone z |  | 10
2025-11-04 | 4786 | sp | 56077 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-11-06 | Z | 2025-10-30 | 10 | 90 | 0 |  | 0 | 90 |  | Extra spiral |  | 7
2025-11-04 | 4788 |  | 56078 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-11-06 | Z | 2025-11-04 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 2 |  |  | 2025-11-06
2025-11-05 | 655 |  | Z1-OA 5 | A | DONE | 16 | M |  | DOC JDC 6240023 | VD | 2025-11-06 | Z | 2025-07-22 | 150 | 0 | 80 |  | 0 | 380 |  |  |  | 107 | 2025-10-23 | 2025-11-20
2025-11-05 | 656 |  | Z1-OA 6 | A | DONE | 12 | S/M |  | DOC JDC 6240023 |  | 2025-11-06 | Z | 2025-07-22 | 220 | 0 | 40 |  | 0 | 300 |  |  |  | 107 | 2025-10-23 | 2025-11-20
2025-11-05 | 683 |  | Z1-EA 22 | A | DONE | 12 | S/M |  | DOC JDC 6240023 | MOD | 2025-11-06 | Z | 2025-07-22 | 70 | 0 | 170 |  | 0 | 280 |  |  |  | 107 | 2025-10-23 | 2025-11-24
2025-11-04 | 695 | bth | Z2- OA 11 | A | DONE | 13 | S/M |  | DOC JDC 6240023 | VD's | 2025-11-06 | Z | 2025-07-30 | 150 | 50 | 0 |  | 0 | 320 |  |  |  | 99
2025-11-05 | 696 |  | Z2- OA 12 | A | DONE | 22 | M |  | DOC JDC 6240023 | VD's | 2025-11-06 | Z | 2025-07-30 | 320 | 0 | 40 |  | 0 | 540 |  |  |  | 99 | 2025-09-04
2025-11-05 | 698 |  | Z2- OA 14.5 | A | DONE | 4 | S |  | DOC JDC 6240023 | VD | 2025-11-20 | Z | 2025-07-30 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 113 | 2025-09-04
2025-11-04 | 699 |  | Z2- OA 14 | A | DONE | 9 | S/M |  | DOC JDC 6240023 | VD's | 2025-11-20 | Z | 2025-07-30 | 110 | 0 | 40 |  | 0 | 210 |  |  |  | 113
2025-11-05 | 726 |  | Z2-EA 57 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2025-11-06 | Z | 2025-07-30 | 80 | 10 | 50 |  | 0 | 170 |  |  |  | 99 | 2025-09-04 | 2025-11-20
2025-11-03 | 740 | bth | Z1-RA 7 | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-07-30 | 110 | 110 | 170 |  | 0 | 440 |  |  |  | 113
2025-11-05 | 103 |  | 84745 | A | DONE | 2 | S |  | E386 |  | 2025-11-07 | Z | 2025-11-05 | 10 | 0 | 0 |  | 0 | 20 |  | Exposed |  | 2
2025-11-03 | 1321 |  | 77552-54 | A | DONE | 8 | S/M |  | EXACT SEQ 2250029 | flex | 2025-11-05 | Z | 2025-10-28 | 120 | 0 | 0 |  | 0 | 190 |  | BCU Outs |  | 8
2025-11-05 | 1110 |  | 77555 | A | DONE | 2 | S |  | EXACT SEQ. 2250029 |  | 2025-11-12 | Z | 2025-10-31 | 10 | 0 | 0 |  | 0 | 20 |  | Pump shelf |  | 12
2025-11-03 | 1320 |  | 77551 | A | DONE | 20 | M |  | EXACT SEQ. 2250029 |  | 2025-11-05 | Z | 2025-10-24 | 340 | 80 | 0 |  | 0 | 490 |  | Bcu 1893-3 RA |  | 12
2025-11-06 | 1321r |  | 77553 | A | DONE | 4 | S |  | EXACT SEQ. 2250029 | flex | 2025-11-06 | Z | 2025-11-05 | 30 | 0 | 0 |  | 0 | 100 |  | Bcu outs |  | 1
2025-11-06 | 3273 |  | 33539 | A | DONE | 7 | S/M |  | FOODHALL 6240037 | 2" dual wall | 2025-11-06 | Z | 2025-11-06 | 60 | 0 | 0 |  | 30 | 160 |  | End cap |  | 0
2025-11-03 | 3239 | sp | 74301 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-11-05 | Z | 2025-10-29 | 20 | 10 | 0 |  | 0 | 30 |  | Fume hood |  | 7
2025-11-06 | 3926 |  | 85049 | A | DONE | 6 | S/M |  | MONROE 6240018 | 1" liner | 2025-11-12 | Z | 2025-11-04 | 110 | 0 | 0 |  | 100 | 140 |  | Clearstory SG-9 Gym |  | 8
2025-11-06 | 3927 | sp | 85855 | A | DONE | 4 | S | neal | MONROE 6240018 |  | 2025-11-12 | Z | 2025-11-04 | 40 | 30 | 0 |  | 0 | 90 |  | SAMP-L2E-05 |  | 8
2025-11-06 | 3928 | sp | 85856 | A | DONE | 2 | S |  | MONROE 6240018 |  | 2025-11-12 | Z | 2025-11-04 | 30 | 20 | 0 |  | 0 | 50 |  | SAMP-L2E-01 |  | 8
2025-11-06 | 1595 |  | EA-L1C-01 | A | DONE | 20 | M |  | MONROE HS 6240018 | partial | 2025-11-11 | Z | 2025-04-28 | 80 | 0 | 310 |  | 0 | 480 |  |  |  | 197 | 2025-06-26 |  | 2025-11-18
2025-11-06 | 2758 |  | SALP-L1C-01 | A | DONE | 27 | M |  | MONROE HS 6240018 | flex , 2" liner , partial | 2025-11-11 | Z | 2025-04-28 | 170 | 0 | 320 |  | 390 | 670 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-06 | 2759 |  | SALP-L1C-02 | A | DONE | 20 | M |  | MONROE HS 6240018 | 2" liner | 2025-11-11 | Z | 2025-04-28 | 50 | 0 | 280 |  | 0 | 500 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-06 | 2764 | bth | SALP-L1C-07 | A | DONE | 19 | M | neal | MONROE HS 6240018 | flex , VD's | 2025-11-11 | Z | 2025-04-28 | 190 | 210 | 0 |  | 0 | 470 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-06 | 2766 | bth | SALP-L1C-09 | A | DONE | 13 | S/M | neal | MONROE HS 6240018 | flex , VD's | 2025-11-11 | Z | 2025-04-28 | 100 | 180 | 0 |  | 0 | 320 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-06 | 2768 | bth | SALP-L1C-11 | A | DONE | 14 | S/M |  | MONROE HS 6240018 | 2" liner | 2025-11-11 | Z | 2025-04-28 | 90 | 30 | 140 |  | 170 | 340 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-06 | 2769 | bth | SALP-L1C-12 | A | DONE | 14 | S/M |  | MONROE HS 6240018 | 2" liner | 2025-11-11 | Z | 2025-04-28 | 40 | 30 | 170 |  | 170 | 330 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-06 | 2774 | bth | SAMP-L1C-01 | A | DONE | 44 | M/L |  | MONROE HS 6240018 | oval , accuflange | 2025-11-11 | Z | 2025-04-28 | 220 | 470 | 0 |  | 0 | 1090 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-06 | 3923 |  | 83656 | A | DONE | 5 | S/M |  | MONROE HS 6240018 |  | 2025-11-11 | Z | 2025-10-31 | 80 | 0 | 0 |  | 0 | 110 |  | EA-L1E-04 |  | 11 |  |  | 2025-11-18
2025-11-05 | 3924 |  | 83658 | A | DONE | 2 | S |  | MONROE HS 6240018 | 1" liner | 2025-11-11 | Z | 2025-10-31 | 30 | 0 | 0 |  | 30 | 50 |  | L1-E-OUTS |  | 11
2025-11-06 | 3925 | bth | 83657 | A | DONE | 5 | S/M |  | MONROE HS 6240018 | 1" liner | 2025-11-11 | Z | 2025-10-31 | 40 | 30 | 60 |  | 70 | 120 |  | SALP-L1E-01 |  | 11 |  |  | 2025-11-18
2025-11-03 | 1060 |  | 76854 | A | DONE | 3 | S | neal | PEWAUKEE HS 6240030 |  | 2025-11-06 | Z | 2025-10-30 | 20 | 0 | 0 |  | 0 | 70 |  | flashing |  | 7
2025-11-04 | 1061 |  | 76855 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 | paint black | 2025-11-06 | Z | 2025-11-03 | 10 | 0 | 0 |  | 10 | 20 |  | Dark room grille box |  | 3
2025-11-05 | 1063 | bth | 76857 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-11-10 | Z | 2025-11-04 | 10 | 10 | 0 |  | 0 | 30 |  | Dust collector |  | 6
2025-11-03 | 101 |  | 75601 | A | DONE | 2 | S |  | PLACON 10065427 | damper | 2025-10-31 | Z | 2025-10-27 | 40 | 0 | 0 |  | 0 | 50 |  | exhaust |  | 4
2025-11-04 | 1023 |  | 76287-88 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 |  | 2025-11-04 | Z | 2025-10-23 | 60 | 0 | 0 |  | 0 | 100 |  | 052 lab |  | 12
2025-11-04 | 1032 | w | 76191 | A | DONE | 5 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-11-04 | Z | 2025-10-23 | 40 | 0 | 0 |  | 0 | 110 |  | 300 Roundbed RA |  | 12
2025-11-03 | 1033 |  | 76372 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-11-04 | Z | 2025-10-24 | 20 | 0 | 0 |  | 0 | 30 |  | L1NCMA1 |  | 11
2025-11-04 | 1034 |  | 76373 | A | DONE | 3 | S | ss | PROJECT DOVE 6240041 |  | 2025-11-06 | Z | 2025-10-27 | 50 | 0 | 0 |  | 0 | 70 |  | L02 AREA-300 |  | 10
2025-11-04 | 1036 |  | 55142 | A | DONE | 26 | S |  | PROJECT DOVE 6240041 |  | 2025-11-04 | Z | 2025-10-30 | 450 | 0 | 0 |  | 0 | 640 |  | Angles, flatstock |  | 5
2025-11-04 | 1037 | w | 76192 | A | DONE | 3 | S | ss | PROJECT DOVE 6240041 |  | 2025-11-03 | Z | 2025-11-03 | 20 | 0 | 0 |  | 0 | 70 |  | 700 outs |  | 0
2025-11-04 | 1385 |  | 75952 | A | DONE | 4 | S |  | RCIS 6250011 |  | 2025-11-10 | Z | 2025-10-27 | 10 | 50 | 0 |  | 0 | 80 |  | lobby |  | 14
2025-11-04 | 1386 |  | 75953 | A | DONE | 4 | S |  | RCIS 6250011 |  | 2025-11-10 | Z | 2025-10-27 | 10 | 80 | 0 |  | 0 | 90 |  | looby |  | 14 |  | 2025-10-16
2025-11-06 | 1388 |  | 74810 | A | DONE | 2 | S | neal | RCIS 6250011 |  | 2025-11-06 | Z | 2025-11-06 | 10 | 0 | 0 |  | 0 | 10 |  | Cab heater |  | 0
2025-11-05 | 1387 |  | 68892 | A | DONE | 2 | S |  | RICHLAND CTR. 6250011 |  | 2025-11-12 | Z | 2025-10-29 | 40 | 0 | 0 |  | 40 | 50 |  | Bathroom C plenum boxes |  | 14
2025-11-06 | 863 | bth | 68890-91 | A | DONE | 8 | S/M |  | SPH 6240039 |  | 2025-11-10 | Z | 2025-10-28 | 50 | 110 | 40 |  | 0 | 190 |  |  |  | 13
2025-11-03 | 2418 | bth | 85905,76852 | A | DONE | 3 | S |  | ST. BERNARD 6230023 | flex | 2025-11-05 | Z | 2025-10-29 | 50 | 20 | 0 |  | 0 | 60 |  | FCU-18, SA |  | 7
2025-11-03 | 2419 |  | 85904 | A | DONE | 4 | S |  | ST. BERNARD 6230023 | 1" liner | 2025-11-05 | Z | 2025-10-29 | 80 | 0 | 30 |  | 80 | 100 |  | FCU-return |  | 7
2025-11-05 | 1377 |  | 81738 - 81739 | A | DONE | 7 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-10-02 | 70 | 0 | 70 |  | 0 | 170 |  | VAV 1-34 LPSA |  | 39
2025-11-05 | 1378 | sp | 81740 - 81741 | A | DONE | 5 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-10-02 | 40 | 80 | 0 |  | 0 | 110 |  | VAV 1-34 LPSA |  | 39
2025-11-05 | 1379 | bth | 81742 - 81743 | A | DONE | 6 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-10-02 | 100 | 40 | 0 |  | 0 | 150 |  | VAV 1-35 LPSA |  | 39
2025-11-05 | 1380 | bth | 81744 - 81745 | A | DONE | 10 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-10-02 | 90 | 70 | 40 |  | 0 | 230 |  | VAV 1-36 LPSA |  | 39
2025-11-05 | 1381 |  | 81746 | A | DONE | 6 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-10-02 | 80 | 0 | 40 |  | 0 | 140 |  | VAV 1-37 LPSA |  | 39
2025-11-03 | 2107 |  | 81724 | A | DONE | 6 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-26 | 70 | 0 | 40 |  | 0 | 130 |  | VAV 2-5 |  | 38
2025-11-03 | 2110 |  | 81727 | A | DONE | 6 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-03 | Z | 2025-09-26 | 90 | 0 | 30 |  | 0 | 130 |  | VAV - 2-1 LPSA |  | 38
2025-11-05 | 2113 |  | 81730 | A | DONE | 7 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-09-29 | 80 | 0 | 60 |  | 0 | 160 |  | 2nd Floor VAV LPSA |  | 42
2025-11-05 | 2114 | sp | 81731 - 81733 | A | DONE | 6 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-09-29 | 30 | 110 | 0 |  | 0 | 130 |  | VAV 1-32 LPSA |  | 42
2025-11-05 | 2115 |  | 81734 - 81735 | A | DONE | 7 | S/M |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-09-29 | 70 | 0 | 60 |  | 0 | 160 |  | VAV 1-33 LPSA |  | 42
2025-11-04 | 2116 | sp | 81736 - 81737 | A | DONE | 4 | S |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-09-29 | 40 | 40 | 0 |  | 0 | 100 |  | 1-33 Round LPSA |  | 42
2025-11-03 | 2118 |  | 69752 | A | DONE | 6 | S/M |  | SW HEALTH MOB 6250015 | 1/2" liner | 2025-11-03 | Z | 2025-10-14 | 90 | 0 | 0 |  | 80 | 130 |  | CD-2 register boxes |  | 20 | 2025-09-04
2025-11-05 | 2119 |  | 69756 | A | DONE | 4 | S |  | SW HEALTH MOB 6250015 |  | 2025-11-10 | Z | 2025-10-14 | 40 | 0 | 50 |  | 0 | 100 |  | RTU-2 2nd floor |  | 27
2025-11-05 | 3149 |  | 69766 | A | DONE | 10 | S/M |  | SWH MOB 6250015 |  | 2025-11-10 | Z | 2025-10-29 | 180 | 0 | 0 |  | 0 | 230 |  | RTU-1 SA |  | 12 |  |  | 2025-11-24
2025-11-05 | 403 |  | 77057 | A | DONE | 2 | S |  | TOMAH 6250006 |  | 2025-11-07 | Z | 2025-11-05 | 10 | 0 | 0 |  | 0 | 20 |  | Return out |  | 2
2025-11-04 | 400 |  | 77052-56 | A | DONE | 37 | M/L |  | TOMAH HEALTH 6250006 |  | 2025-11-10 | Z | 2025-10-28 | 470 | 0 | 260 |  | 0 | 910 |  | FP-1701A |  | 13
2025-11-04 | 401 |  | 82245 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-11-10 | Z | 2025-10-29 | 20 | 0 | 0 |  | 0 | 40 |  | Return outs |  | 12 |  |  | 2025-11-06
2025-11-05 | 402 | sp | 82246 | A | DONE | 2 | S |  | TOMAH HEALTH 625006 |  | 2025-11-10 | Z | 2025-11-04 | 10 | 20 | 0 |  | 0 | 20 |  | Ex. Out |  | 6
2025-11-03 | 4700 |  | 82242-43 | A | DONE | 8 | S/M |  | TOMAH HEALTH 625006 |  | 2025-11-05 | Z | 2025-10-24 | 120 | 0 | 0 |  | 10 | 200 |  | Tab 1723 |  | 12 | 2025-09-04
2025-11-03 | 4701 |  | 82241,82244 | A | DONE | 5 | S/M |  | TOMAH HEALTH 625006 |  | 2025-11-05 | Z | 2025-10-24 | 50 | 60 | 0 |  | 0 | 110 |  | Tab 1729/1733 |  | 12 | 2025-09-11 | 2025-09-02 | 2025-11-18
2025-11-03 | 4820 |  | 78304-05 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | 1" liner | 2025-11-04 | Z | 2025-10-22 | 20 | 0 | 0 |  | 10 | 30 |  | ll transfer |  | 13
2025-11-03 | 4823 |  | 78056 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 |  | 2025-11-04 | Z | 2025-10-24 | 30 | 0 | 0 |  | 0 | 40 |  | LL el. Shaft tie nis |  | 11
2025-11-05 | 4826 |  | 78058 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | 1" liner | 2025-11-11 | Z | 2025-11-04 | 10 | 0 | 0 |  | 10 | 20 |  | LL transfer |  | 7
2025-11-06 | 1416r |  | Hand Drawn | A | DONE | 7 | S/M |  | UW LEVY HALL 6230033 |  | 2025-11-07 | Z | 2025-11-06 | 70 | 0 | 0 |  | 0 | 160 |  | Remake |  | 1
2025-11-04 | 2969 |  | L5-CEA SHAFT C1 | A | DONE | 5 | S/M | ss | UW STOUT 6250008 |  | 2025-11-11 | Z | 2025-10-22 | 50 | 0 | 0 |  | 0 | 120 |  |  |  | 20
2025-11-05 | 2970 |  | L5-SAMP SHAFT C1 | A | DONE | 12 | S/M |  | UW STOUT 6250008 |  | 2025-11-11 | Z | 2025-10-22 | 80 | 0 | 60 |  | 0 | 290 |  |  |  | 20
2025-11-05 | 2971 |  | L5-SAMP SHAFT F1 | A | DONE | 10 | S/M |  | UW STOUT 6250008 |  | 2025-11-11 | Z | 2025-10-22 | 50 | 0 | 60 |  | 0 | 250 |  |  |  | 20
2025-11-03 | 2992 |  | 82184 | A | DONE | 6 | S/M |  | UW STOUT 6250008 |  | 2025-11-04 | Z | 2025-10-30 | 40 | 0 | 0 |  | 0 | 150 |  | pans |  | 5
2025-11-04 | 2993 |  | 82183,82185 | A | DONE | 10 | S/M |  | UW STOUT 6250008 |  | 2025-11-04 | Z | 2025-10-30 | 120 | 0 | 0 |  | 0 | 230 |  | 4th test caps |  | 5
2025-11-05 | 3128 |  | 54548 | A | DONE | 2 | S | ss | UW VET MED 6210014 |  | 2025-11-10 | Z | 2025-11-04 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2025-11-04 | 1439 |  | MER-OA 2 | A | DONE | 16 | M |  | UW-LEVY HALL 6230028 | MOD | 2025-10-30 | Z | 2025-09-19 | 130 | 0 | 0 |  | 0 | 400 |  |  |  | 41
2025-11-04 | 1440 |  | MER-OA 3 | A | DONE | 16 | M |  | UW-LEVY HALL 6230028 | AFMS , MOD | 2025-10-30 | Z | 2025-09-19 | 130 | 0 | 0 |  | 0 | 380 |  |  |  | 41
2025-11-04 | 1447 |  | MER-EAMP 5 | A | DONE | 14 | S/M |  | UW-LEVY HALL 6230028 | MOD | 2025-11-06 | Z | 2025-09-22 | 130 | 0 | 0 |  | 0 | 350 |  |  |  | 45
2025-11-04 | 1448 |  | MER-EAMP 6 | A | DONE | 16 | M |  | UW-LEVY HALL 6230028 |  | 2025-11-06 | Z | 2025-09-22 | 190 | 0 | 120 |  | 0 | 390 |  |  |  | 45
2025-11-05 | 1449 |  | MER-EAMP 7 | A | DONE | 31 | M |  | UW-LEVY HALL 6230028 | MOD | 2025-11-06 | Z | 2025-09-22 | 340 | 0 | 150 |  | 0 | 760 |  |  |  | 45
2025-11-04 | 4800 |  | MER-OA 1 | A | DONE | 17 | M |  | UW-LEVY HALL 6230028 | AFMS , MOD | 2025-11-06 | Z | 2025-09-22 | 190 | 0 | 0 |  | 0 | 420 |  |  |  | 45
2025-11-03 | 1887 |  | 75723-24 | A | DONE | 4 | S |  | UWP 6240031 |  | 2025-11-05 | Z | 2025-10-20 | 60 | 0 | 0 |  | 0 | 100 |  | Supply AHU-4, roof |  | 16
2025-11-06 | 2887 |  | 84888 | A | DONE | 4 | S |  | UWRF 6230010 | flex | 2025-11-11 | Z | 2025-10-27 | 60 | 0 | 0 |  | 0 | 80 |  | Greenhouse |  | 15
2025-11-04 | 3275r |  | 61492 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2025-11-05 | Z | 2025-11-04 | 10 | 0 | 0 |  | 0 | 20 |  | Remake |  | 1
2025-11-04 | 2376 |  | 82929 | A | DONE | 10 | S/M |  | WAUNAKEE 6230013 |  | 2025-11-07 | Z | 2025-10-30 | 230 | 0 | 0 |  | 0 | 250 |  | 2nd flashing |  | 8
2025-11-04 | 2377 |  | 83327,83332 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-11-07 | Z | 2025-10-30 | 30 | 10 | 0 |  | 0 | 40 |  | G2 return, G1 outs |  | 8
2025-11-05 | 2378 |  | 83335,83333 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-11-07 | Z | 2025-11-04 | 40 | 0 | 0 |  | 0 | 50 |  | RA outs G1 |  | 3
2025-11-07 | 3964 |  | 75278-79 | A | DONE | 7 | S/M |  | DELLSHIRE 6240017 |  | 2025-11-10 | Z | 2025-11-07 | 90 | 0 | 0 |  | 0 | 160 |  | RA,SA Riser |  | 3
2025-11-07 | 767 | sp | Z2-RA 29 | A | DONE | 5 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-08-05 | 20 | 100 | 0 |  | 0 | 120 |  |  |  | 100 | 2025-09-25
2025-11-07 | 4704 | sp | Z3-SAT-2-1-3_2 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-09-18 | 20 | 150 | 0 |  | 0 | 160 |  |  |  | 56
2025-11-07 | 4789 |  | 74314 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-11-07 | 20 | 0 | 0 |  | 0 | 20 |  | Accu-1 |  | 6
2025-11-07 | 3240 |  | 74811 | A | DONE | 2 | S |  | HISTOSONICS 625009 |  | 2025-11-07 | Z | 2025-11-07 | 10 | 0 | 0 |  | 0 | 10 |  | Back draft damper |  | 0
2025-11-07 | 2760 | bth | SALP-L1C-03 | A | DONE | 20 | M | neal | MONROE HS 6240018 | VD's | 2025-11-11 | Z | 2025-04-28 | 150 | 280 | 0 |  | 0 | 500 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-07 | 2761 | bth | SALP-L1C-04 | L | DONE | 7 | S/M | neal | MONROE HS 6240018 | flex | 2025-11-11 | Z | 2025-04-28 | 30 | 100 | 0 |  | 0 | 170 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-07 | 2762 | sp | SALP-L1C-05 | A | DONE | 12 | S/M | neal | MONROE HS 6240018 | VD's | 2025-11-11 | Z | 2025-04-28 | 70 | 180 | 0 |  | 0 | 280 |  |  |  | 197 | 2025-07-02 | 2025-11-20 | 2025-11-18
2025-11-07 | 2763 | sp | SALP-L1C-06 | L | DONE | 11 | S/M | neal | MONROE HS 6240018 | VD's | 2025-11-11 | Z | 2025-04-28 | 80 | 140 | 0 |  | 0 | 270 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-07 | 1598 |  | EA-L1C-04 | A | DONE | 6 | S/M | neal | MONROE HS 6240018 | bird s. , 1" liner | 2025-11-11 | Z | 2025-04-28 | 80 | 0 | 50 |  | 40 | 150 |  |  |  | 197 | 2025-06-26 |  | 2025-11-18
2025-11-07 | 2750 | bth | EA-L1C-06 | A | DONE | 20 | M | neal | MONROE HS 6240018 | bird s. | 2025-11-11 | Z | 2025-04-28 | 160 | 250 | 0 |  | 0 | 490 |  |  |  | 197 | 2025-06-26 |  | 2025-11-18
2025-11-07 | 2752 |  | OA-L1C-01 | A | DONE | 20 | M | neal | MONROE HS 6240018 | flex , 1" liner | 2025-11-11 | Z | 2025-04-28 | 200 | 0 | 130 |  | 50 | 490 |  |  |  | 197 | 2025-06-26 |  | 2025-11-18
2025-11-07 | 2753 |  | OA-L1C-02 | A | DONE | 16 | M | neal | MONROE HS 6240018 | flex , 1" liner | 2025-11-11 | Z | 2025-04-28 | 260 | 0 | 50 |  | 40 | 380 |  |  |  | 197 | 2025-06-26 |  | 2025-11-18
2025-11-07 | 2755 |  | OA-L1C-04 | A | DONE | 14 | S/M | neal | MONROE HS 6240018 | CD , flex | 2025-11-11 | Z | 2025-04-28 | 220 | 0 | 70 |  | 0 | 350 |  |  |  | 197 | 2025-06-26
2025-11-07 | 105 |  | 74057 | A | DONE | 2 | S |  | OAKWOOD 4250047 |  | 2025-11-13 | Z | 2025-11-06 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2025-11-07 | 1064 | sp | 76859 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-11-07 | Z | 2025-11-07 | 0 | 30 | 0 |  | 0 | 30 |  | pulled spiral |  | 0
2025-11-07 | 1038 |  | 76289 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-11-13 | Z | 2025-11-04 | 10 | 0 | 0 |  | 0 | 20 |  | MAU-1 |  | 9
2025-11-07 | 1039 |  | 55143 | A | DONE | 5 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-14 | Z | 2025-11-05 | 80 | 0 | 0 |  | 0 | 110 |  | Angles |  | 9
2025-11-07 | 4822 | w | 76122 | A | DONE | 5 | S/M | BI | UW LEVY HALL 6230028 |  | 2025-11-06 | Z | 2025-10-23 | 30 | 0 | 0 |  | 10 | 110 |  | Steam relief |  | 14
[6 empty] | 1288 | [13 empty] | 30590
WEEK OF 11-10-2025
2025-11-12 | 107 |  | 76127 | A | DONE | 2 | S |  | 441 CHORRMANY 6240009 |  | 2025-11-13 | Z | 2025-11-12 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2025-11-14 | 3051 |  | 74257 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2025-11-17 | Z | 2025-11-14 | 10 | 0 | 0 |  | 0 | 20 |  | flashing |  | 3
2025-11-10 | 1211 | bth | 79470 | A | DONE | 5 | S/M | alum. | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-10-24 | 80 | 70 | 0 |  | 0 | 120 |  | L2 east roof |  | 12
2025-11-10 | 1213 | w | 79472 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 | 1" liner | 2025-11-11 | Z | 2025-10-28 | 70 | 0 | 0 |  | 50 | 160 |  | L2-East |  | 14
2025-11-10 | 1215 |  | 92832 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-11-05 | Z | 2025-11-03 | 10 | 0 | 0 |  | 0 | 30 |  | Sleeves |  | 2
2025-11-10 | 1238 | bth | 79473 | A | DONE | 9 | S/M |  | BROOM ST. 6240033 |  | 2025-11-13 | Z | 2025-11-10 | 60 | 10 | 170 |  | 0 | 220 |  | Mock up |  | 3
2025-11-13 | 1240 |  | 79476 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-12 | 10 | 0 | 0 |  | 0 | 10 |  | Unit 267 |  | 6
2025-11-13 | 1241 |  | 92833 | A | DONE | 2 | S |  | BROOM ST. 6240033 | pipe shop caps | 2025-11-26 | Z | 2025-11-12 | 20 | 0 | 0 |  | 0 | 40 |  | Caps for pipe shop |  | 14
2025-11-13 | 1242 |  | 79477 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-13 | 20 | 0 | 0 |  | 0 | 20 |  | Temp air |  | 5
2025-11-13 | 1243 |  | 80411 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-11-13 | Z | 2025-11-13 | 50 | 0 | 0 |  | 0 | 100 |  | S AND D |  | 0
2025-11-14 | 1244 |  | 79478 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-11-17 | Z | 2025-11-13 | 50 | 0 | 0 |  | 0 | 110 |  | L-3 roof curb |  | 4
2025-11-12 | 2937 |  | M4.75 UNIT 344 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 70 | 40 | 0 |  | 0 | 110 |  |  |  | 11
2025-11-12 | 2938 |  | M4.77 UNIT 347 | A | DONE | 16 | M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 140 | 0 | 230 |  | 0 | 390 |  |  |  | 11
2025-11-12 | 2939 |  | M4.93 UNIT 349 | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 170 | 0 | 160 |  | 0 | 330 |  |  |  | 11
2025-11-12 | 2940 |  | M4.94 UNIT 351 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 50 | 0 | 80 |  | 0 | 140 |  |  |  | 11
2025-11-12 | 2941 |  | M4.95 UNIT 353 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 180 | 0 | 120 |  | 0 | 300 |  |  |  | 11
2025-11-13 | 2942 |  | M4.96 UNIT 354 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 110 | 0 | 160 |  | 0 | 260 |  |  |  | 11
2025-11-12 | 2943 |  | M4.97 UNIT 355 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 80 | 80 | 0 |  | 0 | 170 |  |  |  | 11
2025-11-12 | 2944 |  | M4.98 UNIT 357 | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 170 | 0 | 190 |  | 0 | 340 |  |  |  | 11
2025-11-12 | 2945 |  | M4.99 UNIT 358 | A | DONE | 17 | M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 230 | 0 | 200 |  | 0 | 410 |  |  |  | 11
2025-11-12 | 2946 |  | M4.100 UNIT 360 | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 160 | 0 | 180 |  | 0 | 350 |  |  |  | 11
2025-11-12 | 2947 |  | M4.101 UNIT 362 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-07 | 120 | 0 | 0 |  | 0 | 130 |  |  |  | 11
2025-11-13 | 106 |  | 69999-70000 | A | DONE | 7 | S/M |  | CDIS 6220028 | VD, birdscreen | 2025-11-18 | Z | 2025-11-11 | 110 | 0 | 30 |  | 0 | 160 |  | RFI 1439 |  | 7
2025-11-10 | 3961 | w | 74023-24 | A | DONE | 60 | L | BI | DELLSHIRE 6240017 | BI Welded | 2025-11-10 | Z | 2025-10-27 | 470 | 0 | 0 |  | 0 | 1490 |  | Kitchen hood1,2 |  | 14
2025-11-14 | 3965 | bth | 74027-30 | A | DONE | 30 | M |  | DELLSHIRE 6240017 | VD | 2025-11-20 | Z | 2025-11-11 | 140 | 630 | 0 |  | 0 | 750 |  | VAV's |  | 9
2025-11-12 | 3165 | bth | Z2-SAT-3-1-8 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-11-14 | Z | 2025-09-17 | 30 | 10 | 0 |  | 20 | 40 |  |  |  | 58 | 2025-11-13 | 2025-11-06
2025-11-13 | 3169 | bth | Z2-SAT-4-1-26 | A | DONE | 9 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-11-14 | Z | 2025-09-17 | 60 | 160 | 0 |  | 20 | 220 |  |  |  | 58 | 2025-11-13 | 2025-11-06
2025-11-13 | 3170 | bth | Z2-SAT-4-1-27 | A | DONE | 13 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-11-14 | Z | 2025-09-17 | 90 | 190 | 30 |  | 60 | 320 |  |  |  | 58 | 2025-11-13 | 2025-11-06
2025-11-12 | 3171 | bth | Z2-SAT-4-1-28 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-11-14 | Z | 2025-09-17 | 30 | 10 | 0 |  | 20 | 40 |  |  |  | 58 | 2025-11-13 | 2025-11-06
2025-11-12 | 3172 | bth | Z2-SAT-4-1-29 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-11-14 | Z | 2025-09-17 | 30 | 10 | 0 |  | 20 | 40 |  |  |  | 58 | 2025-11-13 | 2025-11-06
2025-11-13 | 3174 |  | Z2-SAT-4-1-30_2 | A | DONE | 27 | M |  | DOC JDC 6240023 |  | 2025-11-14 | Z | 2025-09-17 | 160 | 190 | 230 |  | 0 | 670 |  |  |  | 58 | 2025-11-13 | 2025-11-06
2025-11-11 | 3194 | bth | Z3-RA 32 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-09-18 | 140 | 20 | 0 |  | 0 | 180 |  |  |  | 56
2025-11-13 | 3195 | bth | Z3-RA 33 | A | DONE | 10 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-09-18 | 100 | 20 | 50 |  | 0 | 230 |  |  |  | 56 |  | 2025-10-16
2025-11-11 | 4701 | bth | Z3-SAT-2-1-1 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 30 | 10 | 0 |  | 30 | 50 |  |  |  | 56
2025-11-12 | 4702 |  | Z3-SAT-2-1-2 | A | DONE | 15 | M |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 150 | 70 | 70 |  | 20 | 360 |  |  |  | 56 |  | 2025-10-16
2025-11-11 | 4703 | bth | Z3-SAT-2-1-3_1 | A | DONE | 17 | M |  | DOC JDC 6240023 | VD | 2025-11-13 | Z | 2025-09-18 | 260 | 0 | 0 |  | 0 | 420 |  |  |  | 56
2025-11-10 | 4705 |  | Z3-SAT-2-1-4_1 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 40 | 100 | 0 |  | 20 | 140 |  |  |  | 56
2025-11-11 | 4706 |  | Z3-SAT-2-1-4_2 | A | DONE | 15 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-09-18 | 180 | 90 | 60 |  | 0 | 360 |  |  |  | 56
2025-11-11 | 4707 | bth | Z3-SAT-2-1-5_1 | A | DONE | 10 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 100 | 70 | 30 |  | 40 | 240 |  |  |  | 56
2025-11-11 | 4708 | bth | Z3-SAT-2-1-5_2 | A | DONE | 19 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-09-18 | 230 | 80 | 110 |  | 0 | 470 |  |  |  | 56
2025-11-12 | 4709 | bth | Z3-SAT-2-1-6 | A | DONE | 23 | M |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 210 | 160 | 70 |  | 100 | 570 |  |  |  | 56
2025-11-11 | 4710 | bth | Z3-SAT-2-1-7_1 | A | DONE | 10 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 100 | 110 | 0 |  | 20 | 230 |  |  |  | 56
2025-11-11 | 4711 | bth | Z3-SAT-2-1-7_2 | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-09-18 | 160 | 70 | 160 |  | 0 | 440 |  |  |  | 56
2025-11-11 | 4712 | bth | Z3-SAT-2-1-8_1 | A | DONE | 5 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 30 | 90 | 0 |  | 20 | 120 |  |  |  | 56
2025-11-11 | 4713 | bth | Z3-SAT-2-1-8_2 | A | DONE | 14 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-09-18 | 180 | 80 | 60 |  | 0 | 350 |  |  |  | 56
2025-11-11 | 4714 | bth | Z3-SAT-4-1-1 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 20 | 10 | 0 |  | 20 | 40 |  |  |  | 56 |  |  | 2025-11-18
2025-11-11 | 4715 | bth | Z3-SAT-4-1-2 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-11-13 | Z | 2025-09-18 | 30 | 20 | 0 |  | 30 | 60 |  |  |  | 56 |  |  | 2025-11-18
2025-11-10 | 4753 |  | ZP-SAMP 46 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 90 | 0 | 0 |  | 0 | 140 |  | CH/RG-3 |  | 28 |  |  | 2025-11-18
2025-11-10 | 4754 |  | ZP-SAMP 47 | A | DONE | 12 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 210 | 0 | 40 |  | 0 | 300 |  |  |  | 28 |  |  | 2025-11-18
2025-11-11 | 4755 |  | ZP-SAMP 48 | A | DONE | 25 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 270 | 0 | 130 |  | 0 | 610 |  |  |  | 28 |  |  | 2025-11-18
2025-11-10 | 4756 |  | ZP-SAMP 49 | A | DONE | 14 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 140 | 0 | 60 |  | 0 | 350 |  |  |  | 28 |  |  | 2025-11-18
2025-11-10 | 4757 |  | ZP-SAMP 50 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 90 | 0 | 0 |  | 0 | 160 |  |  |  | 28
2025-11-10 | 4758 |  | ZP-SAMP 51 | A | DONE | 19 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 100 | 0 | 190 |  | 0 | 460 |  |  |  | 28
2025-11-11 | 4759 |  | ZP-SAMP 52 | A | DONE | 32 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 300 | 0 | 180 |  | 0 | 800 |  |  |  | 28
2025-11-10 | 4760 |  | ZP-SAMP 53 | A | DONE | 25 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 210 | 0 | 80 |  | 0 | 610 |  |  |  | 28
2025-11-10 | 4761 |  | ZP-SAMP 54 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 110 | 0 | 0 |  | 0 | 180 |  |  |  | 28
2025-11-11 | 4762 | sp | ZP-SAMP 54.5 | A | DONE | 23 | M | neal | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 80 | 350 | 0 |  | 0 | 570 |  |  |  | 28
2025-11-11 | 4763 | sp | ZP-SAMP 55 | A | DONE | 17 | M | neal | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 60 | 260 | 0 |  | 0 | 410 |  |  |  | 28
2025-11-11 | 4764 | sp | ZP-SAMP 56 | A | DONE | 15 | M | neal | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-16 | 80 | 230 | 0 |  | 0 | 370 |  |  |  | 28
2025-11-14 | 4765 |  | ZP-RA 47 | A | DONE | 22 | M |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-10-16 | 260 | 0 | 0 |  | 0 | 540 |  |  |  | 35 |  |  | 2025-11-24
2025-11-14 | 4766 |  | ZP-RA 48 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-10-16 | 70 | 0 | 50 |  | 0 | 180 |  |  |  | 35 |  |  | 2025-11-06
2025-11-13 | 4767 |  | ZP-RA 49 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-10-16 | 50 | 0 | 60 |  | 0 | 130 |  |  |  | 35 |  |  | 2025-11-06
2025-11-13 | 4771 |  | ZP-RA 53 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-10-16 | 90 | 0 | 30 |  | 0 | 140 |  |  |  | 35
2025-11-13 | 4782 |  | ZP-OA 32 | A | DONE | 17 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-22 | 120 | 0 | 140 |  | 0 | 410 |  |  |  | 22
2025-11-10 | 4787 |  | 84388 | A | DONE | 2 | S | neal | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-10-31 | 20 | 0 | 0 |  | 0 | 50 |  | Saddle hangers |  | 13
2025-11-13 | 4789 |  | 74314 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-11-10 | 10 | 0 | 0 |  | 0 | 70 |  | ACCU-1 |  | 3
2025-11-12 | 4790 |  | 56079 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-11-12 | Z | 2025-11-12 | 20 | 0 | 0 |  | 10 | 20 |  |  |  | 0
2025-11-13 | 4791 |  | 74315 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-11-12 | 80 | 0 | 0 |  | 0 | 180 |  | Louver angles |  | 8
2025-11-14 | 4793 |  | 56081 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-11-14 | Z | 2025-11-14 | 20 | 0 | 0 |  | 0 | 20 |  | zone 1 |  | 0
2025-11-14 | 4794 |  | 56082 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-11-14 | Z | 2025-11-14 | 60 | 0 | 0 |  | 0 | 80 |  | cb |  | 0
2025-11-13 | 653 |  | Z1-OA 2 | A | DONE | 26 | M |  | DOC JDC 6240023 | MOD | 2025-11-20 | Z | 2025-07-22 | 330 | 0 | 50 |  | 0 | 650 |  |  |  | 121 | 2025-10-23 | 2025-11-20
2025-11-14 | 701 |  | Z2-EA 32 | A | DONE | 10 | S/M |  | DOC JDC 6240023 | VD's | 2025-11-20 | Z | 2025-07-30 | 160 | 0 | 40 |  | 0 | 250 |  |  |  | 113 | 2025-09-04 |  | 2025-11-06
2025-11-14 | 703 |  | Z2-EA 34 | A | DONE | 10 | S/M |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-07-30 | 170 | 0 | 0 |  | 0 | 250 |  |  |  | 113 | 2025-09-04 |  | 2025-11-06
2025-11-14 | 731 | bth | Z2-EA 62 | C | DONE | 6 | S/M | pt.neal | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-07-30 | 40 | 90 | 0 |  | 0 | 130 |  |  |  | 113 | 2025-09-04 | 2025-11-20 | 2025-11-06
2025-11-13 | 751r |  | Z1-RA 18 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-11-13 | 20 | 50 | 0 |  | 0 | 80 |  |  |  | 0
2025-11-10 | 757 | bth | Z2-RA 20.5 | A | DONE | 16 | M |  | DOC JDC 6240023 | CD , VD's | 2025-11-13 | Z | 2025-08-05 | 200 | 30 | 60 |  | 0 | 380 |  |  |  | 100 | 2025-09-25
2025-11-12 | 758 | bth | Z2-RA 21 | A | DONE | 43 | M/L |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-08-05 | 560 | 10 | 190 |  | 0 | 1060 |  |  |  | 100 | 2025-09-25
2025-11-11 | 759 | bth | Z2-RA 22 | A | DONE | 16 | M |  | DOC JDC 6240023 | VD | 2025-11-13 | Z | 2025-08-05 | 160 | 30 | 130 |  | 0 | 380 |  |  |  | 100 | 2025-09-25
2025-11-13 | 760 | bth | Z2-RA 23 | A | DONE | 20 | M |  | DOC JDC 6240023 |  | 2025-11-13 | Z | 2025-08-05 | 180 | 210 | 30 |  | 0 | 500 |  |  |  | 100 | 2025-09-25
2025-11-12 | 764 | bth | Z2-RA 27 | A | DONE | 5 | S/M |  | DOC JDC 6240023 | flex | 2025-11-13 | Z | 2025-08-05 | 20 | 60 | 0 |  | 0 | 110 |  |  |  | 100 | 2025-09-25
2025-11-12 | 765 | bth | Z2-RA 28 | A | DONE | 29 | M |  | DOC JDC 6240023 | CD | 2025-11-13 | Z | 2025-08-05 | 260 | 20 | 310 |  | 0 | 710 |  |  |  | 100 | 2025-09-25
2025-11-10 | 766 |  | Z2-RA 29.5 | A | DONE | 5 | S/M |  | DOC JDC 6240023 | flex | 2025-11-13 | Z | 2025-08-05 | 60 | 0 | 0 |  | 0 | 110 |  |  |  | 100 | 2025-09-25
2025-11-11 | 1322 |  | 77556-57 | A | DONE | 8 | S/M |  | EXACT SEQ. 2250029 | flex | 2025-11-13 | Z | 2025-11-10 | 100 | 0 | 0 |  | 0 | 180 |  | BCU outs |  | 3
2025-11-11 | 1323 | bth | 77558 | A | DONE | 4 | S |  | EXACT SEQ. 2250029 |  | 2025-11-17 | Z | 2025-11-10 | 20 | 50 | 0 |  | 0 | 80 |  | TL-5 EA |  | 7
2025-11-14 | 1112 | sp | 81327,81329 | A | DONE | 3 | S |  | GRANT ELEM. 6250021 |  | 2025-11-24 | Z | 2025-11-11 | 10 | 80 | 0 |  | 0 | 70 |  | VAV 29,30 |  | 13
2025-11-10 | 1596 |  | EA-L1C-02 | A | DONE | 36 | M/L | pt.neal | MONROE HS 6240018 | VD's , 1" liner | 2025-11-11 | Z | 2025-04-28 | 350 | 0 | 310 |  | 50 | 900 |  |  |  | 197 | 2025-06-26
2025-11-10 | 1597 | bth | EA-L1C-03 | A | DONE | 10 | S/M | pt.neal | MONROE HS 6240018 | bird s. , 1" liner | 2025-11-11 | Z | 2025-04-28 | 110 | 60 | 0 |  | 40 | 230 |  |  |  | 197 | 2025-06-26
2025-11-10 | 1599 |  | EA-L1C-05 | A | DONE | 8 | S/M | neal | MONROE HS 6240018 | bird s. , 1" liner | 2025-11-11 | Z | 2025-04-28 | 120 | 0 | 0 |  | 30 | 200 |  |  |  | 197 | 2025-06-26 | 2025-10-16
2025-11-10 | 2751 |  | EA-L1C-07 | A | DONE | 10 | S/M | neal | MONROE HS 6240018 | bird s. | 2025-11-11 | Z | 2025-04-28 | 120 | 0 | 70 |  | 0 | 250 |  |  |  | 197 | 2025-06-26 | 2025-10-16
2025-11-10 | 2754 |  | OA-L1C-03 | A | DONE | 12 | S/M | neal | MONROE HS 6240018 | flex | 2025-11-11 | Z | 2025-04-28 | 200 | 0 | 0 |  | 0 | 290 |  |  |  | 197 | 2025-06-26
2025-11-10 | 2756 |  | OA-L1C-05 | A | DONE | 19 | M | neal | MONROE HS 6240018 | CD's , flex , 1" liner | 2025-11-11 | Z | 2025-04-28 | 140 | 0 | 170 |  | 50 | 470 |  |  |  | 197 | 2025-06-26
2025-11-10 | 2757 |  | OA-L1C-06 | A | DONE | 11 | S/M | neal | MONROE HS 6240018 | CD's , flex | 2025-11-11 | Z | 2025-04-28 | 160 | 0 | 50 |  | 0 | 260 |  |  |  | 197 | 2025-06-26
2025-11-10 | 2765 | bth | SALP-L1C-08 | A | DONE | 13 | S/M | neal | MONROE HS 6240018 | flex , VD's | 2025-11-11 | Z | 2025-04-28 | 80 | 180 | 0 |  | 0 | 320 |  |  |  | 197 | 2025-07-02
2025-11-11 | 2767 | bth | SALP-L1C-10 | A | DONE | 10 | S/M | neal | MONROE HS 6240018 | flex , VD's | 2025-11-11 | Z | 2025-04-28 | 80 | 100 | 0 |  | 0 | 230 |  |  |  | 197 | 2025-07-02 |  | 2025-11-18
2025-11-13 | 3932 |  | 83708 | A | DONE | 4 | S |  | MONROE HS 6240018 |  | 2025-11-13 | Z | 2025-11-13 | 30 | 0 | 0 |  | 0 | 90 |  | Mech room |  | 0
2025-11-11 | 104 |  | 84744 | A | DONE | 4 | S |  | OCTOPY 4250042 |  | 2025-11-17 | Z | 2025-11-05 | 30 | 70 | 0 |  | 0 | 100 |  | Exposed |  | 12
2025-11-10 | 1062 |  | 76856 | A | DONE | 3 | S |  | PEWAUKEE HS 6240030 | 2" board liner | 2025-11-17 | Z | 2025-11-04 | 30 | 0 | 0 |  | 30 | 60 |  | Curb Caps |  | 13
2025-11-12 | 1065 |  | 76861 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 | VD | 2025-11-17 | Z | 2025-11-11 | 20 | 0 | 0 |  | 0 | 40 |  | RFI 159 |  | 6
2025-11-13 | 1066 |  | 76870 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 | -12" wg | 2025-11-19 | Z | 2025-11-12 | 10 | 0 | 0 |  | 0 | 40 |  | Dust collector -12" |  | 7
2025-11-11 | 1040 |  | 76290 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-11-20 | Z | 2025-11-05 | 10 | 0 | 0 |  | 0 | 30 |  | L01-052 |  | 15
2025-11-10 | 1041 |  | 76223 | A | DONE | 17 | M |  | PROJECT DOVE 6240041 |  | 2025-11-13 | Z | 2025-11-06 | 290 | 0 | 0 |  | 0 | 410 |  | Flashing |  | 7
2025-11-11 | 1042 | w | 76193 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-11-13 | Z | 2025-11-10 | 20 | 0 | 0 |  | 0 | 40 |  | 2nd fl 300 outs |  | 3
2025-11-10 | 1043 | sp | 76194 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-11-13 | Z | 2025-11-10 | 0 | 30 | 0 |  | 0 | 30 |  | 600SALP |  | 3
2025-11-12 | 1044 | w | L01_AREA_300_EA_001 | A | DONE | 9 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-11-14 | Z | 2025-11-11 | 100 | 0 | 0 |  | 0 | 210 |  |  |  | 3
2025-11-13 | 1045 | w | L01_AREA_300_EA_002 | A | DONE | 9 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-11-14 | Z | 2025-11-11 | 90 | 0 | 0 |  | 0 | 220 |  |  |  | 3
2025-11-11 | 1047 |  | 55144 | A | DONE | 4 | S |  | PROJECT DOVE 6240041 | exposed | 2025-11-20 | Z | 2025-11-11 | 60 | 0 | 0 |  | 0 | 90 |  | Angles |  | 9
2025-11-12 | 864 |  | 68894 | A | DONE | 2 | S |  | SPH 6240039 |  | 2025-11-19 | Z | 2025-11-10 | 20 | 0 | 0 |  | 0 | 20 |  | Existing RAV |  | 9
2025-11-14 | 865 |  | 68895 | A | DONE | 3 | S |  | SPH SURGERY 6240039 | paint black | 2025-11-24 | Z | 2025-11-12 | 30 | 0 | 0 |  | 30 | 60 |  | Return boxes |  | 12
2025-11-11 | 1382 |  | 81747 | A | DONE | 8 | S/M |  | SWH MOB 6250015 |  | 2025-11-17 | Z | 2025-10-02 | 70 | 0 | 90 |  | 0 | 190 |  | VAV 1-38 LPSA |  | 46
2025-11-11 | 1383 | sp | 81748 | A | DONE | 3 | S |  | SWH MOB 6250015 |  | 2025-11-17 | Z | 2025-10-02 | 10 | 60 | 0 |  | 0 | 70 |  | VAV 1-39 LPSA |  | 46
2025-11-11 | 1384 |  | 81749 | A | DONE | 4 | S |  | SWH MOB 6250015 |  | 2025-11-17 | Z | 2025-10-02 | 20 | 0 | 40 |  | 0 | 80 |  | VAV 1-39 LPSA |  | 46
2025-11-11 | 510 | sp | 75552 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-11-17 | Z | 2025-11-05 | 10 | 10 | 0 |  | 0 | 10 |  | Misc |  | 12
2025-11-11 | 512 |  | 75553 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-11-17 | Z | 2025-11-06 | 20 | 0 | 0 |  | 0 | 30 |  | EF-1 tie in 2nd floor |  | 11
2025-11-13 | 520 |  | 75596 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-11-24 | Z | 2025-11-12 | 20 | 0 | 0 |  | 0 | 20 |  | Round Dampers |  | 12
2025-11-13 | 404 | sp | 81350 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-11-17 | Z | 2025-11-11 | 0 | 20 | 0 |  | 0 | 20 |  | Misc |  | 6
2025-11-10 | 3118 |  | 69068 | A | DONE | 2 | S |  | UW AVRL 6240038 |  | 2025-11-10 | Z | 2025-11-10 | 10 | 0 | 0 |  | 0 | 20 |  | Test reducer |  | 0
2025-11-14 | 4827 |  | 76125 | A | DONE | 8 | S/M |  | UW LEVY HALL 6230028 | 1" liner | 2025-11-18 | Z | 2025-11-04 | 90 | 0 | 0 |  | 80 | 190 |  | Penthouse |  | 14
2025-11-13 | 4830 |  | 78063 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | 1" liner | 2025-11-18 | Z | 2025-11-07 | 40 | 0 | 0 |  | 30 | 50 |  | L5 w bathroom |  | 11
2025-11-13 | 4831 |  | 76126 | A | DONE | 31 | M |  | UW LEVY HALL 6230028 |  | 2025-11-20 | Z | 2025-11-07 | 220 | 0 | 0 |  | 0 | 770 |  | Penthouse |  | 13
2025-11-13 | 4832 |  | LOUVER SECTIONAL | A | DONE | 7 | S/M |  | UW LEVY HALL 6230028 | paint black | 2025-11-18 | Z | 2025-11-10 | 60 | 0 | 0 |  | 60 | 170 |  | LL Generator |  | 8
2025-11-13 | 4833 |  | 78068 | A | DONE | 13 | S/M |  | UW LEVY HALL 6230028 |  | 2025-11-18 | Z | 2025-11-10 | 140 | 0 | 0 |  | 0 | 320 |  | LL Generator SA-1 |  | 8
2025-11-12 | 4834 |  | 78065,78067 | A | DONE | 13 | S/M |  | UW LEVY HALL 6230028 | flex | 2025-11-18 | Z | 2025-11-10 | 190 | 0 | 90 |  | 0 | 320 |  | L2 BCU-1 |  | 8
2025-11-10 | 4828 |  | 78060 | A | DONE | 2 | S |  | UW LEVY HALL 6230033 |  | 2025-11-18 | Z | 2025-11-06 | 10 | 0 | 0 |  | 0 | 10 |  | L5 west bathroom ex |  | 12
2025-11-13 | 4829 |  | 78059 | A | DONE | 5 | S/M |  | UW LEVY HALL 6230033 | flex | 2025-11-18 | Z | 2025-11-06 | 40 | 0 | 0 |  | 0 | 110 |  | FCU-5 |  | 12
2025-11-12 | 2951 | bth | L4-SAMP 1 | A | DONE | 41 | M/L |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 180 | 40 | 230 |  | 0 | 1020 |  |  |  | 27 | 2025-11-11
2025-11-12 | 2952 | bth | L4-SAMP 2 | A | DONE | 28 | M |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 90 | 50 | 230 |  | 0 | 680 |  |  |  | 27 | 2025-11-11
2025-11-12 | 2953 | bth | L4-SAMP 3 | A | DONE | 26 | M |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 50 | 70 | 230 |  | 0 | 650 |  |  |  | 27 | 2025-11-11
2025-11-12 | 2954 | bth | L4-SAMP 4 | A | DONE | 23 | M |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 50 | 60 | 170 |  | 0 | 560 |  |  |  | 27 | 2025-11-11
2025-11-13 | 2955 | bth | L4-SAMP 5 | A | DONE | 23 | M |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 30 | 30 | 300 |  | 0 | 570 |  |  |  | 27 | 2025-11-11
2025-11-12 | 2956 | bth | L4-SAMP 6 | A | DONE | 20 | M |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 80 | 40 | 190 |  | 0 | 480 |  |  |  | 27 | 2025-11-11
2025-11-13 | 2957 | bth | L4-SAMP 7 | A | DONE | 25 | M |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 130 | 30 | 190 |  | 0 | 610 |  |  |  | 27 | 2025-11-11
2025-11-13 | 2958 | bth | L4-SAMP 8 | A | DONE | 30 | M |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 200 | 70 | 170 |  | 0 | 750 |  |  |  | 27 | 2025-11-11
2025-11-14 | 2959 | bth | L4-SAMP 9 | A | DONE | 107 | L |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-10-22 | 430 | 30 | 840 |  | 0 | 2660 |  |  |  | 27 | 2025-11-11
2025-11-13 | 2994 |  | 82186-90 | A | DONE | 14 | S/M |  | UW STOUT 6250008 |  | 2025-11-18 | Z | 2025-11-12 | 110 | 0 | 0 |  | 0 | 350 |  | 3rd pans |  | 6
2025-11-10 | 3129 |  | 54549 | A | DONE | 2 | S |  | UW VET MED 6210014 | paint black | 2025-11-12 | Z | 2025-11-07 | 10 | 0 | 0 |  | 10 | 40 |  | 1st misc |  | 5
2025-11-11 | 2379 |  | 82930 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-11-14 | Z | 2025-11-05 | 20 | 0 | 0 |  | 0 | 40 |  | 1st A |  | 9
2025-11-11 | 2380 |  | 83410 | A | DONE | 2 | S | alum. | WAUNAKEE 6230013 |  | 2025-11-11 | Z | 2025-11-07 | 30 | 0 | 0 |  | 0 | 30 |  | Aluminum |  | 4
2025-11-10 | 2381 |  | 83338 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-11-11 | Z | 2025-11-07 | 20 | 0 | 0 |  | 0 | 30 |  | E2 outs |  | 4
2025-11-11 | 2382 |  | 75406 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-11-14 | Z | 2025-11-10 | 10 | 0 | 0 |  | 0 | 10 |  | DC 1 and 2 |  | 4
2025-11-12 | 2383 |  | 83339 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-11-14 | Z | 2025-11-12 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 2
[6 empty] | 1630 | [13 empty] | 38970 | [5 empty] | 42%
WEEK OF 11-17-2025
2025-11-18 | 1040 |  | 53952 | A | DONE | 2 | S |  | 121 E WILSON 6230024 |  | 2025-11-19 | Z | 2025-11-14 | 20 | 0 | 0 |  | 0 | 40 |  | Roof work |  | 5
2025-11-19 | 110 |  | 25614 | A | DONE | 8 | S/M |  | ALBERTSON 6230016 |  | 2025-11-25 | Z | 2025-11-19 | 140 | 0 | 0 |  | 0 | 190 |  | Outs |  | 6
2025-11-17 | 2452 |  | 70189 | A | DONE | 21 | M |  | ANITIGO E.S. 6250017 | 1" liner, pt black | 2025-11-24 | Z | 2025-11-12 | 240 | 0 | 0 |  | 200 | 510 |  | H2.1 Gym RA |  | 12
2025-11-20 | 2455 |  | 70194 | A | DONE | 4 | S |  | ANTIGO 6250017 |  | 2025-11-25 | Z | 2025-11-18 | 30 | 0 | 0 |  | 0 | 80 |  | 1st floor sleeve |  | 7
2025-11-19 | 2453 |  | 001 | A | DONE | 2 | S |  | ANTIGO E.S. 6250017 | pipe shop caps | 2025-11-25 | Z | 2025-11-13 | 10 | 0 | 0 |  | 0 | 20 |  | Sleeve caps |  | 12
2025-11-19 | 2454 |  | 70190 | A | DONE | 23 | M |  | ANTIGO E.S. 6250017 | foam board | 2025-11-25 | Z | 2025-11-13 | 210 | 0 | 0 |  | 0 | 560 |  | 2nd floor wall sleeve |  | 12
2025-11-18 | 3053 | w | 74259 | A | DONE | 2 | S | ss | BARTILLION 6240024 |  | 2025-12-01 | Z | 2025-11-17 | 10 | 0 | 0 |  | 0 | 20 |  | Kitchen enclosure |  | 14
2025-11-17 | 3052 |  | 74258 | A | DONE | 2 | S |  | BARTILLION 6420024 |  | 2025-11-18 | Z | 2025-11-17 | 10 | 0 | 0 |  | 0 | 20 |  | Tranfer fan |  | 1
2025-11-18 | 1200 |  | M4.75 UNIT 444 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 80 | 0 | 40 |  | 0 | 120 |  |  |  | 19
2025-11-19 | 1201 |  | M4.77 UNIT 447 | A | DONE | 16 | M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 140 | 0 | 230 |  | 0 | 400 |  |  |  | 19
2025-11-19 | 1202 |  | M4.93 UNIT 449 | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 140 | 0 | 160 |  | 0 | 330 |  |  |  | 19
2025-11-18 | 1203 |  | M4.94 UNIT 451 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 70 | 0 | 80 |  | 0 | 140 |  |  |  | 19
2025-11-19 | 1204 |  | M4.95 UNIT 453 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 180 | 0 | 120 |  | 0 | 300 |  |  |  | 19
2025-11-19 | 1205 |  | M4.96 UNIT 454 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 110 | 0 | 160 |  | 0 | 270 |  |  |  | 19
2025-11-19 | 1206 |  | M4.97 UNIT 455 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 80 | 80 | 0 |  | 0 | 170 |  |  |  | 19
2025-11-19 | 1207 |  | M4.98 UNIT 457 | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 140 | 0 | 190 |  | 0 | 340 |  |  |  | 19
2025-11-19 | 1208 |  | M4.99 UNIT 458 | A | DONE | 17 | M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 210 | 0 | 200 |  | 0 | 420 |  |  |  | 19
2025-11-19 | 1209 |  | M4.100 UNIT 460 | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 170 | 0 | 180 |  | 0 | 350 |  |  |  | 19
2025-11-19 | 1210 |  | M4.101 UNIT 462 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 120 | 0 | 0 |  | 0 | 140 |  |  |  | 19
2025-11-19 | 1212 |  | DOAS-4 RISER L2-L5 | A | DONE | 117 | L |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-07 | 170 | 0 | 90 |  | 0 | 2910 |  |  |  | 19
2025-11-20 | 1239 |  | 79474-75 | A | DONE | 17 | M |  | BROOM ST. 6240033 |  | 2025-11-18 | Z | 2025-11-11 | 170 | 0 | 0 |  | 0 | 420 |  | OA kits |  | 7
2025-11-17 | 1245 |  | 79479 | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-11-25 | Z | 2025-11-14 | 280 | 0 | 0 |  | 0 | 350 |  | flashing |  | 11
2025-11-20 | 74812 |  | 74812 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2025-11-20 | Z | 2025-11-20 | 80 | 0 | 0 |  | 0 | 180 |  | Wire baskets plates |  | 0
2025-11-20 | 79482 |  | 79482 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-11-26 | Z | 2025-11-20 | 80 | 0 | 0 |  | 0 | 80 |  | flat stock |  | 6
2025-11-20 | 79483 |  | 79483 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-11-21 | Z | 2025-11-20 | 10 | 0 | 0 |  | 0 | 10 |  |  |  | 1
2025-11-20 | 109 |  | 81863 | A | DONE | 4 | S |  | BTC 6250020 |  | 2025-12-01 | Z | 2025-11-18 | 10 | 0 | 0 |  | 0 | 90 |  | Misc |  | 13
2025-11-17 | 3966 | w | 75280 | A | DONE | 2 | S | bi | DELLSHIRE 6240017 |  | 2025-11-20 | Z | 2025-11-17 | 20 | 0 | 0 |  | 0 | 50 |  | KH-1 |  | 3
2025-11-18 | 3967 | bth | 74031 | A | DONE | 8 | S/M | neal | DELLSHIRE 6240017 | VD | 2025-11-20 | Z | 2025-11-17 | 80 | 100 | 0 |  | 0 | 190 |  | Misc. |  | 3
2025-11-18 | 3968 | bth | 74032 | A | DONE | 6 | S/M |  | DELLSHIRE 6240017 | VD | 2025-11-24 | Z | 2025-11-17 | 60 | 80 | 0 |  | 0 | 140 |  | EF-10 |  | 7
2025-11-19 | 3969 | bth | 74033 | A | DONE | 5 | S/M | alum | DELLSHIRE 6240017 |  | 2025-11-24 | Z | 2025-11-17 | 40 | 210 | 0 |  | 0 | 120 |  | Dryer venting |  | 7
2025-11-19 | 3970 |  | 74034-35,001 | A | DONE | 41 | M/L |  | DELLSHIRE 6240017 | VD | 2025-11-24 | Z | 2025-11-18 | 470 | 10 | 40 |  | 0 | 1020 |  | Retail 220, Mech |  | 6
2025-11-19 | 2208 | bth | Z1-SAT-4-1-24 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-11-20 | Z | 2025-07-31 | 30 | 10 | 0 |  | 20 | 40 |  |  |  | 112 | 2025-09-18 | 2025-11-06
2025-11-17 | 4769 |  | ZP-RA 51 | A | DONE | 38 | M/L |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-10-16 | 380 | 0 | 150 |  | 0 | 940 |  |  |  | 35
2025-11-17 | 4770 |  | ZP-RA 52 | A | DONE | 23 | M |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-10-16 | 230 | 0 | 140 |  | 0 | 560 |  |  |  | 35
2025-11-17 | 4792 | sp | 56080 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-11-13 | 10 | 70 | 0 |  | 0 | 70 |  | Extra spiral |  | 7
2025-11-18 | 4795 |  | 56083 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-11-17 | 10 | 0 | 0 |  | 0 | 10 |  | Z1-RA-15 out |  | 3
2025-11-18 | 4796 |  | 56084 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-11-17 | 20 | 0 | 0 |  | 0 | 20 |  | Zone 1 out |  | 3
2025-11-17 | 680 |  | Z1-EA 19 | A | DONE | 2 | S |  | DOC JDC 6240023 | MOD | 2025-11-20 | Z | 2025-07-22 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 121 | 2025-10-23 | 2025-11-24 | 2025-11-06
2025-11-17 | 681 |  | Z1-EA 20 | A | DONE | 10 | S/M | pt.neal | DOC JDC 6240023 | MOD | 2025-11-20 | Z | 2025-07-22 | 100 | 0 | 90 |  | 0 | 250 |  |  |  | 121 | 2025-10-23 | 2025-11-24 | 2025-11-24
2025-11-17 | 682 |  | Z1-EA 21 | A | DONE | 5 | S/M | neal | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-07-22 | 0 | 0 | 100 |  | 0 | 120 |  |  |  | 121 | 2025-10-23 | 2025-11-24 | 2025-11-24
2025-11-17 | 700 |  | Z2-EA 31 | A | DONE | 30 | M |  | DOC JDC 6240023 | VD | 2025-11-20 | Z | 2025-07-30 | 350 | 0 | 230 |  | 0 | 730 |  |  |  | 113 | 2025-09-04
2025-11-17 | 702 |  | Z2-EA 33 | A | DONE | 22 | M |  | DOC JDC 6240023 | VD | 2025-11-20 | Z | 2025-07-30 | 300 | 0 | 150 |  | 0 | 540 |  |  |  | 113 | 2025-09-04 |  | 2025-11-06
2025-11-17 | 729 | bth | Z2-EA 60 | A | DONE | 3 | S | pt.neal | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-07-30 | 30 | 40 | 0 |  | 0 | 70 |  |  |  | 113 | 2025-09-04 | 2025-11-20 | 2025-11-06
2025-11-17 | 730 | bth | Z2-EA 61 | A | DONE | 6 | S/M | pt.neal | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-07-30 | 90 | 20 | 20 |  | 0 | 140 |  |  |  | 113 | 2025-09-04 | 2025-11-20 | 2025-11-06
2025-11-19 | 786 | sp | Z1-SAT-3-1-7_2 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-11-20 | Z | 2025-07-31 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 112 | 2025-09-18 | 2025-11-06
2025-11-19 | 2500 | sp | 77560 | A | DONE | 8 | S/M |  | EXACT SEQ. |  | 2025-11-24 | Z | 2025-11-17 | 40 | 140 | 0 |  | 0 | 200 |  | SA duct |  | 7
2025-11-17 | 1324 |  | 77559 | A | DONE | 2 | S |  | EXACT SEQ. 2250029 |  | 2025-11-19 | Z | 2025-11-14 | 30 | 0 | 0 |  | 10 | 50 |  | BCU outs |  | 5
2025-11-18 | 1111 |  | 81326,28,30 | A | DONE | 11 | S/M |  | GRANT ELEM. 6250021 | VD | 2025-11-24 | Z | 2025-11-11 | 120 | 0 | 110 |  | 0 | 270 |  | VAV 29,30 break out |  | 13
2025-11-21 | 1113 |  | 81318,20,22,24-25 | A | DONE | 44 | M/L |  | GRANT ELEM. 6250021 | VD | 2025-11-24 | Z | 2025-11-11 | 130 | 90 | 680 |  | 0 | 1080 |  | Phrase 2 main |  | 13
2025-11-20 | 1114 | sp | 81319,21,23 | A | DONE | 16 | M |  | GRANT ELEM. 6250021 |  | 2025-11-24 | Z | 2025-11-11 | 70 | 340 | 0 |  | 0 | 380 |  | Phrase 2-3 |  | 13
2025-11-17 | 1115 |  | 25612-13 | A | DONE | 2 | S |  | GRANT ELEM. 6250021 |  | 2025-11-24 | Z | 2025-11-11 | 20 | 0 | 0 |  | 0 | 30 |  | VAV tie in |  | 13
2025-11-17 | 3241 | w | 77270 | A | DONE | 2 | S |  | HISTOSONICS 6250009 |  | 2025-11-18 | Z | 2025-11-17 | 10 | 0 | 0 |  | 0 | 30 |  | Roof cap |  | 1
2025-11-17 | 3242 |  | 77271 | A | DONE | 2 | S | pcd | HISTOSONICS 6250009 |  | 2025-11-18 | Z | 2025-11-17 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2025-11-17 | 3933 |  | 74351 | A | DONE | 8 | S/M |  | MONROE 6240018 |  | 2025-11-25 | Z | 2025-11-17 | 160 | 0 | 0 |  | 0 | 180 |  | flashing |  | 8
2025-11-19 | 3929 |  | 83701,83706-07 | A | DONE | 10 | S/M |  | MONROE HS 6240018 |  | 2025-11-25 | Z | 2025-11-10 | 160 | 0 | 0 |  | 0 | 230 |  | Football concessions OA |  | 15
2025-11-19 | 3930 | bth | 83702-03 | A | DONE | 16 | M |  | MONROE HS 6240018 |  | 2025-11-25 | Z | 2025-11-10 | 170 | 120 | 50 |  | 0 | 380 |  | Football concessions SA |  | 15
2025-11-19 | 3931 |  | 83704-05 | A | DONE | 7 | S/M |  | MONROE HS 6240018 | 1" liner | 2025-11-25 | Z | 2025-11-10 | 140 | 10 | 0 |  | 110 | 170 |  | Football concessions TA |  | 15
2025-11-19 | 111 |  | 74053 | A | DONE | 2 | S |  | OAKWOOD 4250047 |  | 2025-11-19 | Z | 2025-11-19 | 10 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2025-11-17 | 1067 | bth | 76871-72 | A | DONE | 4 | S | neal | PEWAUKEE HS 6240030 |  | 2025-11-19 | Z | 2025-11-13 | 50 | 40 | 0 |  | 0 | 90 |  | Plasma cutter, kiln drops |  | 6
2025-11-17 | 1068 |  | 74651 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-11-19 | Z | 2025-11-13 | 30 | 0 | 0 |  | 0 | 50 |  | Furnance hood |  | 6
2025-11-17 | 1069 |  | 76862 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-11-18 | Z | 2025-11-17 | 20 | 0 | 0 |  | 0 | 40 |  | Foundry hood |  | 1
2025-11-20 | 1024 |  | L01_AREA_1600_SALP_004 | A | DONE | 7 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 50 | 80 | 0 |  | 0 | 170 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-11-20 | 1025 |  | L01_AREA_1600_SAMP_001 | A | DONE | 8 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 90 | 0 | 40 |  | 0 | 180 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-11-17 | 1046 | w | L01_AREA_300_EA_003 | A | DONE | 9 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-11-14 | Z | 2025-11-11 | 100 | 0 | 0 |  | 0 | 220 |  |  |  | 3
2025-11-17 | 1048 |  | 76293-94 | A | DONE | 6 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-20 | Z | 2025-11-12 | 90 | 0 | 0 |  | 0 | 140 |  | NC shipping office |  | 8
2025-11-19 | 1049 |  | 55145 | A | DONE | 4 | S | neal | PROJECT DOVE 6240041 |  | 2025-11-20 | Z | 2025-11-18 | 60 | 0 | 0 |  | 0 | 90 |  | Angles |  | 2
2025-11-17 | 1376 |  | 75870 | A | DONE | 2 | S | semi | RICHLAND CTR. 6250011 | 1" liner | 2025-11-24 | Z | 2025-10-02 | 30 | 0 | 0 |  | 20 | 40 |  | Bathroom TA |  | 53 | 2025-11-24
2025-11-19 | 2420 |  | 76873 | A | DONE | 4 | S |  | SBC 6230023 | 1" liner, pt black | 2025-11-24 | Z | 2025-11-17 | 60 | 0 | 0 |  | 40 | 80 |  | Transfers |  | 7
2025-11-18 | 2421 |  | 76874 | A | DONE | 2 | S |  | SBC 6230023 | paint black | 2025-11-24 | Z | 2025-11-17 | 10 | 0 | 0 |  | 10 | 20 |  | Conf ex tie in |  | 7
2025-11-18 | 2115r |  | 81734 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-11-21 | Z | 2025-11-17 | 10 | 0 | 0 |  | 0 | 10 |  | Remake tap |  | 4
2025-11-17 | 2120 |  | 75600 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-11-24 | Z | 2025-11-07 | 30 | 0 | 0 |  | 0 | 40 |  | RA chase 2nd floor |  | 17
2025-11-19 | 3145 |  | 69757-60 | A | DONE | 40 | M/L |  | SWH MOB 6250015 |  | 2025-12-15 | Z | 2025-10-22 | 310 | 0 | 520 |  | 0 | 990 |  | RTU-1 1st floor |  | 54 | 2025-11-24
2025-11-17 | 3146 |  | 69761 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-15 | Z | 2025-10-22 | 10 | 20 | 0 |  | 0 | 30 |  | RTU-1 1st floor |  | 54
2025-11-19 | 3147 |  | 69762-64 | A | DONE | 41 | M/L |  | SWH MOB 6250015 |  | 2025-12-15 | Z | 2025-10-22 | 240 | 0 | 560 |  | 0 | 1010 |  | RTU-1 1st floor RA East |  | 54 | 2025-12-01 |  |  | 2025-11-06
2025-11-18 | 500 |  | 69767-70 | A | DONE | 90 | L |  | SWH MOB 6250015 |  | 2025-11-24 | Z | 2025-10-29 | 590 | 0 | 870 |  | 0 | 2250 |  | RTU-1 1st flr |  | 26 |  |  |  | 2025-11-06
2025-11-18 | 501 | sp | 69772-74 | A | DONE | 6 | S/M |  | SWH MOB 6250015 |  | 2025-11-24 | Z | 2025-10-29 | 40 | 110 | 0 |  | 0 | 150 |  | RTU-1 1st flr |  | 26
2025-11-18 | 502 |  | 69775 | A | DONE | 4 | S |  | SWH MOB 6250015 |  | 2025-11-24 | Z | 2025-10-29 | 60 | 0 | 0 |  | 0 | 80 |  | RTU-1 1st flr |  | 26
2025-11-20 | 503 |  | 69776-77 | A | DONE | 21 | S |  | SWH MOB 6250015 |  | 2025-12-01 | Z | 2025-10-30 | 110 | 0 | 320 |  | 0 | 510 |  | RTU-1 1st floor SA middle |  | 32
2025-11-20 | 504 | sp | 69778-79 | F | DONE | 4 | S |  | SWH MOB 6250015 |  | 2025-12-01 | Z | 2025-10-30 | 30 | 40 | 0 |  | 0 | 80 |  | RTU-1 1st floor SA middle |  | 32 |  |  |  | 2025-11-06
2025-11-17 | 505 |  | 69780 | A | DONE | 3 | S |  | SWH MOB 6250015 |  | 2025-11-24 | Z | 2025-10-30 | 0 | 0 | 50 |  | 0 | 60 |  | RTU-2 1st floor SA east |  | 25
2025-11-20 | 506 |  | 69781-85 | A | DONE | 45 | M/L |  | SWH MOB 6250015 |  | 2025-12-01 | Z | 2025-10-31 | 330 | 0 | 570 |  | 0 | 1120 |  | RTU-1 SA 1st floor |  | 31
2025-11-20 | 508 |  | 69790-91 | A | DONE | 9 | S/M |  | SWH MOB 6250015 |  | 2025-12-08 | Z | 2025-11-03 | 80 | 0 | 110 |  | 0 | 220 |  | RTU-2 1st floor SA |  | 35
2025-11-17 | 514 |  | 75599 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-11-24 | Z | 2025-11-11 | 30 | 0 | 0 |  | 0 | 50 |  | VAV 1-37 |  | 13
2025-11-20 | 515 |  | 75598 | A | DONE | 2 | S |  | SWH MOB 6250015 | VD | 2025-12-08 | Z | 2025-11-11 | 20 | 0 | 0 |  | 0 | 40 |  | Rm 132 RA |  | 27
2025-11-17 | 525 |  | 75595 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-11-24 | Z | 2025-11-13 | 30 | 0 | 0 |  | 0 | 40 |  | EF-1 chase |  | 11
2025-11-19 | 531 |  | 75593 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-01 | Z | 2025-11-14 | 30 | 0 | 0 |  | 0 | 30 |  | Misc |  | 17
2025-11-17 | 546 |  | 75562 | A | DONE | 2 | S |  | SWH MOB 6250015 | paint black | 2025-11-24 | Z | 2025-11-10 | 10 | 0 | 0 |  | 10 | 20 |  | Mech room RA box |  | 14
2025-11-19 | 405 |  | 82247 | A | DONE | 14 | S/M |  | TOMAH HEALTH 6250006 |  | 2025-12-01 | Z | 2025-11-17 | 160 | 0 | 130 |  | 0 | 340 |  | TAB-1701B |  | 14
2025-11-19 | 406 | sp | 82248 | A | DONE | 5 | S/M |  | TOMAH HEALTH 6250006 |  | 2025-12-01 | Z | 2025-11-17 | 50 | 70 | 0 |  | 0 | 120 |  | TAB-1701B |  | 14
2025-11-19 | 407 |  | 82249 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 | 1" liner | 2025-12-01 | Z | 2025-11-17 | 20 | 0 | 0 |  | 20 | 30 |  | Transfers |  | 14
2025-11-17 | 108 |  | 74059 | A | DONE | 2 | S |  | US BANK 20010005 |  | 2025-11-24 | Z | 2025-11-17 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2025-11-18 | 4829r |  | 78059 | A | DONE | 5 | S/M | neal | UW LEVY HALL 6230028 | flex | 2025-11-18 | Z | 2025-11-17 | 40 | 0 | 0 |  | 0 | 110 |  | FCU-5 |  | 1
2025-11-19 | 4836 |  | 76131 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 |  | 2025-12-02 | Z | 2025-11-18 | 30 | 0 | 0 |  | 0 | 50 |  | Penthouse |  | 14
2025-11-20 | 4837 |  | 78070 | A | DONE | 4 | S | neal | UW LEVY HALL 6230028 | flex | 2025-11-25 | Z | 2025-11-18 | 30 | 0 | 0 |  | 0 | 100 |  | FCU 5th floor |  | 7
2025-11-21 | 4838 |  | 76132 | A | DONE | 24 | M |  | UW LEVY HALL 6230028 |  | 2025-12-02 | Z | 2025-11-19 | 270 | 0 | 0 |  | 0 | 580 |  | Penthouse |  | 13
2025-11-20 | 78307 | sp | 78307 | A | DONE | 6 | S/M |  | UW LEVY HALL 6230028 |  | 2025-11-25 | Z | 2025-11-20 | 0 | 150 | 0 |  | 0 | 140 |  | misc |  | 5
2025-11-18 | 2960 | bth | L4-SAMP 10 | A | DONE | 45 | M/L |  | UW STOUT 6250008 |  | 2025-11-25 | Z | 2025-10-22 | 160 | 20 | 330 |  | 0 | 1110 |  |  |  | 34 | 2025-11-11
2025-11-17 | 2961 |  | L4-SAMP 11 | A | DONE | 18 | M |  | UW STOUT 6250008 |  | 2025-11-25 | Z | 2025-10-22 | 40 | 0 | 170 |  | 0 | 430 |  |  |  | 34 | 2025-11-11
2025-11-18 | 2962 | bth | L4-SAMP 12 | A | DONE | 26 | M |  | UW STOUT 6250008 |  | 2025-11-25 | Z | 2025-10-22 | 150 | 30 | 170 |  | 0 | 640 |  |  |  | 34 | 2025-11-11
2025-11-19 | 2963 | bth | L4-SAMP 13 | A | DONE | 46 | M/L |  | UW STOUT 6250008 |  | 2025-11-25 | Z | 2025-10-22 | 190 | 90 | 290 |  | 0 | 1130 |  |  |  | 34 | 2025-11-11
2025-11-19 | 2964 | bth | L4-SAMP 14 | A | DONE | 51 | M/L |  | UW STOUT 6250008 |  | 2025-11-25 | Z | 2025-10-22 | 230 | 40 | 380 |  | 0 | 1270 |  |  |  | 34 | 2025-11-11
2025-11-18 | 2965 |  | L4-SAMP 15 | A | DONE | 30 | M |  | UW STOUT 6250008 |  | 2025-11-25 | Z | 2025-10-22 | 210 | 0 | 110 |  | 0 | 740 |  |  |  | 34 | 2025-11-11 | 2025-11-25
2025-11-21 | 2974 | bth | L4-SAMP 19 | A | DONE | 17 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 120 | 50 | 140 |  | 0 | 420 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2975 | bth | L4-SAMP 20 | A | DONE | 8 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 30 | 20 | 90 |  | 0 | 180 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2976 | bth | L4-SAMP 21 | A | DONE | 8 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 20 | 40 | 90 |  | 0 | 180 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2977 | bth | L4-SAMP 22 | A | DONE | 14 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 110 | 60 | 90 |  | 0 | 330 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2978 | bth | L4-SAMP 23 | A | DONE | 10 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 90 | 20 | 100 |  | 0 | 240 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2979 | bth | L4-SAMP 24 | A | DONE | 3 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 10 | 60 | 0 |  | 0 | 60 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2981 | bth | L4-SAMP 26 | A | DONE | 11 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 120 | 60 | 50 |  | 0 | 260 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2982 | bth | L4-SAMP 27 | A | DONE | 5 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 50 | 40 | 30 |  | 0 | 120 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2983 | bth | L4-SAMP 28 | A | DONE | 26 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 200 | 60 | 80 |  | 0 | 640 |  |  |  | 33 | 2025-11-25
2025-11-21 | 2984 | bth | L4-SAMP 29 | A | DONE | 5 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 10 | 110 | 0 |  | 0 | 110 |  |  |  | 33 | 2025-11-25
2025-11-20 | 2995 |  | 82192-96 | A | DONE | 17 | M |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-11-18 | 130 | 0 | 0 |  | 0 | 410 |  | 2nd pans |  | 14
2025-11-21 | 82197 |  | 82197-82200 | A | DONE | 8 | S/M |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-11-20 | 90 | 0 | 0 |  | 0 | 200 |  | Pans |  | 12
2025-11-21 | 3130 | sp | 54550 | A | DONE | 2 | S | alum | VET MED 6210014 |  | 2025-11-24 | Z | 2025-11-20 | 10 | 10 | 0 |  | 0 | 10 |  | 3rd fl dryer |  | 4
2025-11-17 | 2384 |  | 83340-41 | A | DONE | 2 | S |  | WAUNAKEE 6230013 | paint black, VD | 2025-11-19 | Z | 2025-11-14 | 20 | 0 | 0 |  | 0 | 30 |  | C2 2217 |  | 5
2025-11-18 | 2385 | bth | 83411-16 | A | DONE | 4 | S | alum | WAUNAKEE 6230013 | VD | 2025-11-20 | Z | 2025-11-17 | 70 | 60 | 0 |  | 0 | 80 |  | 1st A |  | 3
2025-11-20 | 2386 |  | 76791-92,83417 | A | DONE | 6 | S/M |  | WAUNAKEE 6230013 |  | 2025-11-21 | Z | 2025-11-18 | 100 | 0 | 0 |  | 10 | 140 |  | D1 tie ins |  | 3
[6 empty] | 1451 | [13 empty] | 34710 | [5 empty] | 38% Short
WEEK OF 11-24-2025
2025-11-25 | 2456 |  | 70192 | A | DONE | 60 | L | neal | ANTIGO ES 6250017 | 1" liner | 2025-12-02 | Z | 2025-11-19 | 240 | 0 | 740 |  | 810 | 1480 |  | H2.1 AHU-1 RA |  | 13
2025-11-26 | 2457 |  | 70193,002 | A | DONE | 108 | L |  | ANTIGO ES 6250017 |  | 2025-12-02 | Z | 2025-11-19 | 230 | 1380 | 0 |  | 0 | 2680 |  | H2.1 AHU-1 SA |  | 13
2025-11-25 | 1246 |  | UNIT 544 M4.75 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 90 | 0 | 40 |  | 0 | 120 |  |  |  | 13
2025-11-26 | 1247 |  | UNIT 545 M4.76 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 70 | 0 | 20 |  | 0 | 80 |  |  |  | 13
2025-11-25 | 1248 |  | UNIT 547 M4.77 | A | DONE | 13 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 250 | 0 | 90 |  | 0 | 320 |  |  |  | 13
2025-11-25 | 1249 |  | UNIT 549 M4.93 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 200 | 0 | 110 |  | 0 | 300 |  |  |  | 13
2025-11-25 | 1250 |  | UNIT 551 M4.94 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 70 | 0 | 60 |  | 0 | 120 |  |  |  | 13
2025-11-25 | 1251 |  | UNIT 553 M4.95 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 200 | 0 | 110 |  | 0 | 280 |  |  |  | 13
2025-11-25 | 1252 |  | UNIT 554 M4.96 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 160 | 0 | 110 |  | 0 | 270 |  |  |  | 13
2025-11-26 | 1253 |  | UNIT 555 M4.97 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 80 | 80 | 0 |  | 0 | 160 |  |  |  | 13
2025-11-25 | 1254 |  | UNIT 557 M4.98 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 180 | 0 | 130 |  | 0 | 280 |  |  |  | 13
2025-11-25 | 1255 |  | UNIT 558 M4.99 | A | DONE | 15 | M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 280 | 0 | 110 |  | 0 | 360 |  |  |  | 13
2025-11-25 | 1256 |  | UNIT 560 M4.100 | A | DONE | 13 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 200 | 0 | 110 |  | 0 | 310 |  |  |  | 13
2025-11-25 | 1257 |  | UNIT 562 M4.101 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2025-12-02 | Z | 2025-11-19 | 130 | 0 | 20 |  | 0 | 160 |  |  |  | 13
2025-11-26 | 1258 |  | UNIT 131 M4.46 | A | DONE | 10 | S/M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 130 | 80 | 0 |  | 0 | 230 |  |  |  | 13
2025-11-26 | 1259 |  | LL1 UNIT 133 M4.47 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 100 | 0 | 0 |  | 0 | 100 |  |  |  | 13 |  | 2025-11-06
2025-11-26 | 1260 |  | UNIT 133 M4.47A | A | DONE | 14 | S/M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 240 | 0 | 130 |  | 0 | 340 |  |  |  | 13 |  | 2025-09-02
2025-11-26 | 1261 |  | LL1 UNIT 135 M4.48 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 130 | 0 | 30 |  | 0 | 260 |  |  |  | 13 |  | 2025-11-06
2025-11-26 | 1262 |  | UNIT 135 M4.48A | A | DONE | 10 | S/M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 190 | 0 | 50 |  | 0 | 250 |  |  |  | 13
2025-11-26 | 1263 |  | UNIT 136 M4.49 | A | DONE | 19 | M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 190 | 0 | 260 |  | 0 | 460 |  |  |  | 13
2025-11-26 | 1264 |  | UNIT 138 M4.50 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 200 | 0 | 130 |  | 0 | 300 |  |  |  | 13
2025-11-26 | 1265 |  | UNIT 139 M4.51 | A | DONE | 15 | M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 250 | 0 | 100 |  | 0 | 360 |  |  |  | 13
2025-11-26 | 1266 |  | UNIT 141 M4.52 | A | DONE | 10 | S/M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 180 | 0 | 80 |  | 0 | 240 |  |  |  | 13
2025-11-26 | 1267 |  | UNIT 143 M4.53 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-11-20 | 100 | 0 | 20 |  | 0 | 130 |  |  |  | 13
2025-11-25 | 1296 |  | S&D | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-11-25 | Z | 2025-11-25 | 20 | 0 | 0 |  | 0 | 50 |  | S&D |  | 0
2025-11-25 | 74037 |  | 74037 | A | DONE | 33 | M/L |  | DELLSHIRE 6240017 |  | 2025-12-01 | Z | 2025-11-20 | 410 | 0 | 130 |  | 0 | 820 |  | AHU-4 EA/OA |  | 11
2025-11-26 | 74038 |  | 74038 | A | DONE | 23 | M |  | DELLSHIRE 6240017 | 1" liner | 2025-12-03 | Z | 2025-11-20 | 330 | 0 | 100 |  | 300 | 570 |  | AHU-4 RA |  | 13
2025-11-24 | 74041 | bth | 74041 | A | DONE | 6 | S/M |  | DELLSHIRE 6240017 |  | 2025-11-25 | Z | 2025-11-24 | 20 | 120 | 0 |  | 0 | 150 |  | Misc |  | 1
2025-11-25 | 74058 |  | 74058 | A | DONE | 16 | M |  | DELLSHIRE 6240017 |  | 2025-12-01 | Z | 2025-11-21 | 310 | 0 | 0 |  | 0 | 400 |  | SA,RA chase |  | 10
2025-11-24 | 2209 | bth | Z1-SAT-4-1-25 | A | DONE | 12 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-11-25 | Z | 2025-07-31 | 290 | 0 | 0 |  | 0 | 300 |  |  |  | 117 | 2025-09-18
2025-11-24 | 735 | bth | Z1-RA 2 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-11-25 | Z | 2025-07-30 | 110 | 80 | 0 |  | 0 | 200 |  |  |  | 118 | 2025-09-11
2025-11-24 | 778 | bth | Z1-SAT-3-1-1_1 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | VD , 1" liner | 2025-11-25 | Z | 2025-07-31 | 80 | 40 | 20 |  | 20 | 150 |  |  |  | 117 | 2025-09-18
2025-11-24 | 2501 |  | 77561 | A | DONE | 4 | S |  | EXACT CONF. 2250051 | paint black | 2025-11-25 | Z | 2025-11-19 | 60 | 0 | 0 |  | 50 | 90 |  | Transfers |  | 6
2025-11-24 | 1116 |  | 77001 | A | DONE | 2 | S |  | GRANT ELEM. 6250021 | paint black | 2025-12-01 | Z | 2025-11-19 | 20 | 0 | 0 |  | 30 | 40 |  | Transfers |  | 12
2025-11-25 | 81335 |  | 81335 | A | DONE | 2 | S |  | GRANT ELEM. 6250021 |  | 2025-12-03 | Z | 2025-11-24 | 10 | 0 | 0 |  | 0 | 10 |  | Outs |  | 9
2025-11-26 | 3934 |  | 83711,83713-14 | A | DONE | 30 | M |  | MONROE 6240018 | BD damper | 2025-12-03 | Z | 2025-11-19 | 390 | 0 | 0 |  | 0 | 750 |  | L2E-OA, L2A-EA |  | 14
2025-11-25 | 3935 |  | 83710,83712 | A | DONE | 14 | S/M |  | MONROE 6240018 | 1" liner | 2025-12-03 | Z | 2025-11-19 | 240 | 0 | 0 |  | 120 | 350 |  | L2E-RA, SALP |  | 14
2025-11-26 | 55149 |  | 55149 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-12-04 | Z | 2025-11-25 | 10 | 0 | 0 |  | 0 | 20 |  | Riser clamp |  | 9
2025-11-25 | 2420r |  | 2420r | A | DONE | 2 | S |  | SBC 6230023 |  | 2025-11-25 | Z | 2025-11-25 | 30 | 0 | 0 |  | 20 | 40 |  | remake |  | 0
2025-11-25 | 85451 |  | 85451 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2025-12-03 | Z | 2025-11-24 | 10 | 0 | 0 |  | 0 | 30 |  | 3.5 Duct sleeves |  | 9
2025-11-26 | 2121 |  | 75555-61 | A | DONE | 42 | M/L |  | SWH MOB 6250015 | 24/22 MOD | 2025-12-08 | Z | 2025-11-07 | 450 | 0 | 430 |  | 0 | 1040 |  | RTU-1 RA 1st floor |  | 31
2025-11-24 | 507 |  | 69786-88 | A | DONE | 7 | S/M |  | SWH MOB 6250015 |  | 2025-12-01 | Z | 2025-10-31 | 50 | 110 | 0 |  | 0 | 160 |  | RTU-1 SA 1st floor |  | 31
2025-11-25 | 408 |  | 82232 | A | DONE | 2 | S | neal | TOMAH HEALTH 6250006 | paint grey | 2025-12-03 | Z | 2025-11-19 | 10 | 0 | 0 |  | 10 | 30 |  | RTU Sleeve |  | 14
2025-11-25 | 77002 |  | 77002-03 | A | DONE | 8 | S/M |  | TOMAH HEALTH 6250006 |  | 2025-12-03 | Z | 2025-11-24 | 150 | 0 | 0 |  | 0 | 180 |  | TAB-1746, flashing |  | 9
2025-11-26 | 3119 | w | 69069 | A | DONE | 2 | S |  | UW AVRL 6240038 |  | 2025-12-01 | Z | 2025-11-14 | 10 | 0 | 0 |  | 0 | 30 |  | EAT-583 |  | 17
2025-11-24 | 4835 |  | 76129-30,001 | A | DONE | 16 | M |  | UW LEVY HALL 6230028 |  | 2025-12-02 | Z | 2025-11-17 | 150 | 0 | 0 |  | 0 | 400 |  | Penthouse |  | 15
2025-11-25 | 78059 |  | 78059 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | flex | 2025-11-25 | Z | 2025-11-25 | 30 | 0 | 0 |  | 10 | 50 |  | Flex remake |  | 0
2025-11-26 | 78308 |  | 78308 | A | DONE | 14 | S/M | neal | UW LEVY HALL 6230028 |  | 2025-12-02 | Z | 2025-11-24 | 390 | 0 | 0 |  | 0 | 350 |  | L1 RAMP 10 |  | 8
2025-11-25 | 78309 |  | 78309 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | 1" liner | 2025-11-25 | Z | 2025-11-25 | 20 | 0 | 0 |  | 10 | 30 |  | Transfers |  | 0
2025-11-24 | 2980 | bth | L4-SAMP 25 | A | DONE | 20 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-10-30 | 50 | 170 | 200 |  | 0 | 490 |  |  |  | 33 | 2025-11-25
2025-11-26 | 77359 |  | 77359 | A | DONE | 3 | S |  | UW STOUT 6250008 |  | 2025-12-02 | Z | 2025-11-25 | 30 | 0 | 0 |  | 0 | 70 |  | 4th floor infill |  | 7
2025-11-25 | 2387 | sp | 75407-09 | A | DONE | 21 | M | neal | WAUNAKEE 6230013 |  | 2025-12-01 | Z | 2025-11-19 | 30 | 270 | 0 |  | 0 | 510 |  | Tech ed |  | 12
2025-11-24 | 2388 |  | 8293 | A | DONE | 4 | S |  | WAUNAKEE 6230013 |  | 2025-11-26 | Z | 2025-11-19 | 60 | 0 | 0 |  | 0 | 80 |  | 1st A-RA |  | 7
2025-11-24 | 76793 |  | 76793 | A | DONE | 2 | S |  | WAUNAKEE 6230013 | paint black | 2025-12-01 | Z | 2025-11-24 | 30 | 0 | 0 |  | 30 | 50 |  | E1 RA, TA |  | 7
2025-11-24 | 83420 |  | 83420 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-11-26 | Z | 2025-11-20 | 30 | 0 | 0 |  | 0 | 50 |  | 1st A |  | 6
2025-11-24 | 83421 |  | 83421 | A | DONE | 2 | S | neal | WAUNAKEE 6230013 |  | 2025-11-26 | Z | 2025-11-20 | 30 | 10 | 0 |  | 0 | 40 |  | 1st A |  | 6
2025-11-24 | 74757 |  | 74757 | A | DONE | 2 | S |  | WAUNAKEE HS 4250045 |  | 2025-11-24 | Z | 2025-11-24 | 10 | 10 | 0 |  | 0 | 20 |  |  |  | 0
2025-11-26 | 1009 |  | B-RAMP-01 | A | DONE | 16 | M |  | SHRINE 6240034 | 1" liner | 2025-12-08 | Z | 2025-11-19 | 60 | 0 | 160 |  | 0 | 390 |  |  |  | 19
[6 empty] | 726 | [13 empty] | 17530 | [5 empty] | 38% Short
WEEK OF 12-1-2025
2025-12-04 | 2456a |  | 2456a | A | DONE | 3 | S |  | ANTIGO 6250017 |  | 2025-12-04 | Z | 2025-12-04 | 30 | 0 | 0 |  | 0 | 70 |  | Remake |  | 0
2025-12-01 | 74261 |  | 74261 | A | DONE | 3 | S | alum | BARTILLION 6240024 |  | 2025-12-03 | Z | 2025-11-25 | 30 | 60 | 0 |  | 0 | 60 |  | Dryer vent |  | 8
2025-12-04 | 74262 |  | 74262 | A | DONE | 2 | S |  | BARTILLION 6240024 | paint black | 2025-12-09 | Z | 2025-12-02 | 10 | 0 | 0 |  | 10 | 20 |  | RA grille |  | 7
2025-12-04 | 1268 |  | UNIT 644 M4.75 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 70 | 0 | 40 |  | 0 | 120 |  |  |  | 19
2025-12-04 | 1269 |  | UNIT 645 M4.76 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 70 | 0 | 0 |  | 0 | 80 |  |  |  | 19
2025-12-04 | 1270 |  | UNIT 647 M4.77 | A | DONE | 13 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 240 | 0 | 80 |  | 0 | 320 |  |  |  | 19
2025-12-04 | 1271 |  | UNIT 649 M4.93 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 170 | 0 | 110 |  | 0 | 300 |  |  |  | 19
2025-12-04 | 1272 |  | UNIT 651 M4.94 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 60 | 0 | 60 |  | 0 | 130 |  |  |  | 19
2025-12-04 | 1273 |  | UNIT 653 M4.95 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 200 | 0 | 110 |  | 0 | 280 |  |  |  | 19
2025-12-04 | 1274 |  | UNIT 654 M4.96 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 180 | 0 | 80 |  | 0 | 260 |  |  |  | 19
2025-12-05 | 1275 |  | UNIT 655 M4.97 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 100 | 80 | 0 |  | 0 | 180 |  |  |  | 19
2025-12-05 | 1276 |  | UNIT 657 M4.98 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 180 | 0 | 100 |  | 0 | 280 |  |  |  | 19
2025-12-04 | 1277 |  | UNIT 658 M4.99 | A | DONE | 15 | M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 250 | 0 | 110 |  | 0 | 360 |  |  |  | 19
2025-12-04 | 1278 |  | UNIT 660 M4.100 | A | DONE | 13 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 200 | 0 | 103 |  | 0 | 310 |  |  |  | 19
2025-12-04 | 1279 |  | UNIT 662 M4.101 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 110 | 0 | 0 |  | 0 | 160 |  |  |  | 19
2025-12-03 | 1297 |  | 1297 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-12-03 | 10 | 0 | 0 |  | 0 | 20 |  | Temp return |  | 0
2025-12-04 | 58176 | sp | 58176-79 | A | DONE | 10 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-26 | 120 | 130 | 0 |  | 0 | 230 |  | Sleeves |  | 13
2025-12-02 | 58181 |  | 58181 | A | DONE | 3 | S |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-12-01 | 30 | 0 | 0 |  | 0 | 70 |  | SandD |  | 2
2025-12-04 | 79483r |  | 79483r | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-12-04 | Z | 2025-12-03 | 10 | 0 | 0 |  | 0 | 10 |  | Unit 245 |  | 1
2025-12-04 | 79484 |  | 79484-85 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-26 | 70 | 0 | 0 |  | 0 | 100 |  | L3/L4-A |  | 13
2025-12-05 | 79535 |  | 79535-39 | A | DONE | 12 | S/M | alum | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-20 | 140 | 170 | 0 |  | 0 | 290 |  | L6/L7 East WP |  | 19
2025-12-03 | 80412 | sp | 80412 | A | DONE | 3 | S |  | BROOM ST. 6240033 |  | 2025-12-03 | Z | 2025-12-02 | 30 | 50 | 0 |  | 0 | 70 |  | Temp return |  | 1
2025-12-01 | 74039 |  | 74039 | A | DONE | 11 | S/M |  | DELLSHIRE 6240017 | 1" liner | 2025-12-03 | Z | 2025-11-20 | 100 | 0 | 120 |  | 180 | 270 |  | AHU-4 RA |  | 13
2025-12-01 | 74040 | bth | 74040 | A | DONE | 11 | S/M |  | DELLSHIRE 6240017 | VD | 2025-12-04 | Z | 2025-11-21 | 210 | 110 | 0 |  | 0 | 270 |  | AHU-4 HP SA |  | 13
2025-12-03 | 74042 | bth | 74042 | A | DONE | 11 | S/M |  | DELLSHIRE 6240017 |  | 2025-12-08 | Z | 2025-12-01 | 1250 | 50 | 60 |  | 0 | 270 |  | 2nd D |  | 7
2025-12-01 | 74043 |  | 74043 | A | DONE | 22 | M |  | DELLSHIRE 6240017 |  | 2025-12-02 | Z | 2025-11-25 | 190 | 0 | 120 |  | 0 | 540 |  | AHU-1 OA |  | 7
2025-12-03 | 74044 | bth | 74044 | A | DONE | 10 | S/M |  | DELLSHIRE 6240017 |  | 2025-12-05 | Z | 2025-12-02 | 100 | 110 | 0 |  | 0 | 250 |  | AHU-3 tie-in |  | 3
2025-12-03 | 75281 |  | 75281-87 | A | DONE | 19 | M |  | DELLSHIRE 6240017 |  | 2025-12-08 | Z | 2025-11-25 | 290 | 0 | 0 |  | 0 | 470 |  | AHU-6,7 MAU-1,2 |  | 13
2025-12-04 | 4716r |  | 4716r | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-09 | Z | 2025-12-04 | 30 | 0 | 0 |  | 20 | 40 |  | Remake |  | 5
2025-12-04 | 4717r |  | 4717r | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-09 | Z | 2025-12-04 | 10 | 0 | 30 |  | 30 | 60 |  | Remake |  | 5
2025-12-04 | 4718r |  | 4718r | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-09 | Z | 2025-12-04 | 10 | 0 | 20 |  | 30 | 40 |  | Remake |  | 5
2025-12-02 | 4773 | sp | ZP-OA 23 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 10 | 170 | 0 |  | 0 | 170 |  |  |  | 43 | 2025-11-13
2025-12-02 | 4774 |  | ZP-OA 24 | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 200 | 0 | 40 |  | 0 | 430 |  |  |  | 43 | 2025-11-13
2025-12-03 | 4775 |  | ZP-OA 25 | A | DONE | 26 | M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 80 | 0 | 230 |  | 0 | 630 |  |  |  | 43 | 2025-11-13
2025-12-03 | 4776 |  | ZP-OA 26 | A | DONE | 10 | S/M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 130 | 0 | 40 |  | 0 | 240 |  |  |  | 43 | 2025-11-13
2025-12-01 | 4777 |  | ZP-OA 27 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 100 | 0 | 0 |  | 0 | 160 |  |  |  | 43 | 2025-11-13
2025-12-03 | 4778 |  | ZP-OA 28 | A | DONE | 40 | M/L |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 120 | 0 | 390 |  | 0 | 1000 |  |  |  | 43 | 2025-11-13
2025-12-02 | 4779 |  | ZP-OA 29 | A | DONE | 11 | S/M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 130 | 0 | 0 |  | 0 | 270 |  |  |  | 43 | 2025-11-13
2025-12-02 | 4780 |  | ZP-OA 30 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 43 | 2025-11-13
2025-12-01 | 4781 |  | ZP-OA 31 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-10-22 | 30 | 0 | 30 |  | 0 | 70 |  |  |  | 43 | 2025-11-13
2025-12-03 | 56085 | bth | 56085 | A | DONE | 12 | S/M | neal | DOC JDC 6240023 | VD | 2025-12-02 | Z | 2025-12-02 | 160 | 30 | 0 |  | 0 | 300 |  | Taps |  | 0
2025-12-03 | 56086 |  | 56086 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-12-02 | 80 | 0 | 0 |  | 0 | 90 |  | Flashing |  | 2
2025-12-03 | 56087 |  | 56087 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-04 | Z | 2025-12-02 | 10 | 0 | 30 |  | 30 | 50 |  | Outs |  | 2 |  |  | 2025-11-18
2025-12-04 | 56089 |  | 56089 | A | DONE | 24 | M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-12-03 | 20 | 0 | 30 |  | 0 | 580 |  | Changes |  | 1
2025-12-03 | 684 | sp | Z1-EA 23 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-07-22 | 20 | 110 | 0 |  | 0 | 130 |  |  |  | 135 | 2025-10-23 | 2025-09-02 | 2025-11-18
2025-12-03 | 736 |  | Z1-RA 3 | A | DONE | 10 | S/M |  | DOC JDC 6240023 |  | 2025-12-04 | Z | 2025-07-30 | 60 | 0 | 140 |  | 0 | 240 |  |  |  | 127 | 2025-09-11 | 2025-09-02 | 2025-11-18
2025-12-01 | 73930 |  | 73930-32 | A | DONE | 2 | S |  | DOC JDC 6240023 | flex | 2025-12-04 | Z | 2025-11-20 | 40 | 0 | 0 |  | 0 | 50 |  | Zone 1 fcu-1 RA,SA |  | 14
2025-12-01 | 84391 | bth | 84391 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner, birdscreen | 2025-12-04 | Z | 2025-11-20 | 30 | 10 | 0 |  | 10 | 60 |  | Curb cap |  | 14
2025-12-04 | 76051 |  | 76051 | A | DONE | 3 | S |  | GRANT ELEM. 6250021 |  | 2025-12-08 | Z | 2025-12-03 | 60 | 0 | 0 |  | 20 | 60 |  | 1st phase outs |  | 5
2025-12-05 | 76051r |  | 76051r | A | DONE | 2 | S |  | GRANT ES 6250021 |  | 2025-12-05 | Z | 2025-12-05 | 10 | 0 | 0 |  | 0 | 10 |  | A collars |  | 0
2025-12-03 | 74813 |  | 74813 | A | DONE | 2 | S | pcd | HISTOSONIC 6250009 | VD | 2025-12-04 | Z | 2025-12-03 | 10 | 0 | 0 |  | 0 | 10 |  | Damper |  | 1
2025-12-05 | 3949 |  | Pre-fab Hangers | A | DONE | 7 | S/M | neal | MONROE 6240018 |  | 2025-12-10 | Z | 2025-12-03 | 70 | 0 | 0 |  | 0 | 170 |  | L1C |  | 7
2025-12-01 | 74355 |  | 74355 | A | DONE | 2 | S |  | MONROE 6240018 |  | 2025-12-09 | Z | 2025-11-26 | 10 | 0 | 0 |  | 10 | 40 |  | Curb adapter |  | 13
2025-12-01 | 74354 |  | 74354 | A | DONE | 2 | S |  | MONROE 6240018 |  | 2025-12-03 | Z | 2025-11-26 | 20 | 0 | 0 |  | 0 | 20 |  | Rossi dampers |  | 7
2025-12-01 | 74356 |  | 74356 | A | DONE | 2 | S |  | MONROE 6240018 |  | 2025-12-03 | Z | 2025-12-01 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 2
2025-12-05 | 83623 | w | 83623 | A | DONE | 3 | S | ss | MONROE 6240018 |  | 2025-12-10 | Z | 2025-12-03 | 30 | 0 | 0 |  | 0 | 60 |  | FC's hood |  | 7
2025-12-04 | 83659 |  | 83659 | A | DONE | 4 | S |  | MONROE 6240018 |  | 2025-12-09 | Z | 2025-11-24 | 60 | 0 | 0 |  | 0 | 80 |  | Clear story |  | 15
2025-12-04 | 83660 |  | 83660 | A | DONE | 2 | S |  | MONROE 6240018 | 2" liner | 2025-12-09 | Z | 2025-11-24 | 20 | 0 | 0 |  | 20 | 30 |  | E-2 outs |  | 15
2025-12-05 | 83661 |  | 83661 | A | DONE | 3 | S |  | MONROE 6240018 |  | 2025-12-09 | Z | 2025-11-24 | 40 | 0 | 0 |  | 0 | 60 |  | EA L2E |  | 15
2025-12-02 | 83715 |  | 83715-17 | A | DONE | 7 | S/M | neal | MONROE 6240018 |  | 2025-12-03 | Z | 2025-11-21 | 110 | 0 | 0 |  | 0 | 170 |  | L2E-HRU2 |  | 12
2025-12-02 | 85857 |  | 85857 | A | DONE | 2 | S |  | MONROE 6240018 | 1" liner | 2025-12-09 | Z | 2025-11-21 | 20 | 0 | 0 |  | 10 | 20 |  | Kitchen |  | 18
2025-12-02 | 85858 |  | 85858 | A | DONE | 2 | S |  | MONROE 6240018 | VD | 2025-12-09 | Z | 2025-11-25 | 10 | 0 | 0 |  | 0 | 20 |  | B-104 |  | 14
2025-12-02 | 2770 |  | SALP-L1C-13 | A | DONE | 75 | L | neal | MONROE HS 6240018 | 1" liner | 2025-12-04 | Z | 2025-04-28 | 180 | 0 | 570 |  | 690 | 1860 |  |  |  | 220 | 2025-07-02
2025-12-02 | 2771 |  | SALP-L1C-14 | A | DONE | 59 | L | nl/ss | MONROE HS 6240018 | 1" liner | 2025-12-04 | Z | 2025-04-28 | 440 | 0 | 130 |  | 450 | 1460 |  |  |  | 220 | 2025-07-02
2025-12-02 | 2772 |  | SALP-L1C-15 | A | DONE | 24 | M | nl/ss | MONROE HS 6240018 | 1" liner | 2025-12-04 | Z | 2025-04-28 | 270 | 0 | 0 |  | 240 | 580 |  |  |  | 220 | 2025-07-02
2025-12-02 | 1017 |  | L01_AREA_1600_RA_001 | A | DONE | 8 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 50 | 330 | 0 |  | 0 | 200 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-12-04 | 1018 |  | L01_AREA_1600_RA_002 | A | DONE | 14 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 120 | 160 | 0 |  | 0 | 330 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-12-04 | 1019 |  | L01_AREA_1600_RA_003 | A | DONE | 11 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 70 | 100 | 0 |  | 0 | 260 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-12-04 | 1020 |  | L01_AREA_1600_RAMP_001 | A | DONE | 9 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 106 | 0 | 40 |  | 0 | 210 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-12-04 | 1021 |  | L01_AREA_1600_SALP_001 | A | DONE | 6 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 30 | 80 | 0 |  | 0 | 140 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-12-04 | 1022 |  | L01_AREA_1600_SALP_002 | A | DONE | 8 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 70 | 90 | 0 |  | 0 | 180 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-12-04 | 1023 |  | L01_AREA_1600_SALP_003 | A | DONE | 6 | S/M |  | PROJECT DOVE 6240041 |  | 2025-11-26 | Z | 2025-10-22 | 40 | 90 | 0 |  | 0 | 150 |  |  |  | 35 | 2025-11-06 | 2025-11-20
2025-12-03 | 1050r | w | 1050r | A | DONE | 11 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-12-11 | Z | 2025-12-01 | 90 | 0 | 0 |  | 0 | 270 |  | Remake |  | 10
2025-12-01 | 55146 | w | 55146 | A | DONE | 6 | S/M | ss | PROJECT DOVE 6240041 | flex | 2025-12-04 | Z | 2025-11-20 | 30 | 0 | 0 |  | 0 | 130 |  | EF-48 |  | 14
2025-12-01 | 55147 |  | 55147 | A | DONE | 10 | S/M |  | PROJECT DOVE 6240041 | birdscreen | 2025-12-04 | Z | 2025-11-20 | 60 | 0 | 0 |  | 0 | 250 |  | IH-8 |  | 14
2025-12-03 | 76195 |  | 76195 | A | DONE | 3 | S |  | PROJECT DOVE 6240041 |  | 2025-12-04 | Z | 2025-12-02 | 0 | 0 | 40 |  | 0 | 60 |  | 600 m/a |  | 2
2025-12-01 | 76298 | w | 76298-99 | A | DONE | 5 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-12-04 | Z | 2025-11-25 | 20 | 0 | 0 |  | 0 | 110 |  | Area 700 |  | 9
2025-12-01 | 76300 |  | 76300 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-12-04 | Z | 2025-12-01 | 10 | 0 | 0 |  | 0 | 20 |  | Brackets |  | 3
2025-12-02 | 76374 |  | 76374 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-12-04 | Z | 2025-12-02 | 10 | 0 | 0 |  | 0 | 10 |  | L2 600 |  | 2
2025-12-03 | 76376 |  | 76376 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-12-04 | Z | 2025-12-03 | 10 | 0 | 0 |  | 0 | 10 |  | L2 600 |  | 1
2025-12-05 | 76377 |  | 76377 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-12-08 | Z | 2025-12-05 | 20 | 0 | 0 |  | 0 | 30 |  | EF-8 |  | 3
2025-12-05 | 75954 |  | 75954-55 | A | DONE | 10 | S/M | semi | RICHLAND CTR. 6250011 | paint black | 2025-12-16 | Z | 2025-11-26 | 210 | 0 | 0 |  | 40 | 250 |  | Bathrooms C |  | 20
2025-12-04 | 76834 |  | 76834 | A | DONE | 2 | S |  | SBC 6230023 | paint black | 2025-12-05 | Z | 2025-11-26 | 20 | 0 | 0 |  | 20 | 20 |  | Grille extentions |  | 9
2025-12-03 | 1001 |  | B-EA-01 | A | DONE | 26 | M |  | SHRINE 6240034 |  | 2025-12-08 | Z | 2025-11-19 | 170 | 0 | 210 |  | 0 | 630 |  |  |  | 19
2025-12-03 | 1002 |  | B-EA-02 | A | DONE | 26 | M |  | SHRINE 6240034 | flex | 2025-12-08 | Z | 2025-11-19 | 260 | 0 | 190 |  | 0 | 650 |  |  |  | 19
2025-12-02 | 1003 |  | B-EA-03 | A | DONE | 18 | M |  | SHRINE 6240034 |  | 2025-12-08 | Z | 2025-11-19 | 180 | 0 | 170 |  | 0 | 430 |  |  |  | 19
2025-12-02 | 1004 |  | B-EA-04 | A | DONE | 10 | S/M |  | SHRINE 6240034 |  | 2025-12-08 | Z | 2025-11-19 | 140 | 30 | 50 |  | 0 | 250 |  |  |  | 19
2025-12-02 | 1005 |  | B-EA-05 | A | DONE | 13 | S/M |  | SHRINE 6240034 |  | 2025-12-08 | Z | 2025-11-19 | 240 | 0 | 40 |  | 0 | 320 |  |  |  | 19
2025-12-02 | 1006 |  | B-EA-06 | A | DONE | 5 | S/M |  | SHRINE 6240034 |  | 2025-12-08 | Z | 2025-11-19 | 60 | 50 | 0 |  | 0 | 110 |  |  |  | 19
2025-12-02 | 1007 |  | B-EA-07 | A | DONE | 3 | S |  | SHRINE 6240034 |  | 2025-12-08 | Z | 2025-11-19 | 10 | 50 | 0 |  | 0 | 60 |  |  |  | 19
2025-12-02 | 1008 |  | B-EA-08 | A | DONE | 6 | S/M |  | SHRINE 6240034 |  | 2025-12-08 | Z | 2025-11-19 | 100 | 0 | 0 |  | 0 | 140 |  |  |  | 19
2025-12-03 | 1010 |  | B-RAMP-02 | A | DONE | 43 | M/L |  | SHRINE 6240034 | 1" liner | 2025-12-08 | Z | 2025-11-19 | 390 | 0 | 0 |  | 340 | 1060 |  |  |  | 19
2025-12-04 | 1011 |  | B-RAMP-03 | A | DONE | 47 | M/L |  | SHRINE 6240034 | 1" liner | 2025-12-08 | Z | 2025-11-19 | 330 | 0 | 230 |  | 500 | 1170 |  |  |  | 19
2025-12-04 | 1012 |  | B-RAMP-04 | A | DONE | 28 | M |  | SHRINE 6240034 | 1" liner | 2025-12-08 | Z | 2025-11-19 | 320 | 0 | 130 |  | 320 | 700 |  |  |  | 19
2025-12-03 | 1013 |  | B-TA-01 | A | DONE | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2025-12-08 | Z | 2025-11-19 | 80 | 0 | 0 |  | 60 | 120 |  |  |  | 19
2025-12-03 | 1014 |  | B-TA-02 | A | DONE | 4 | S |  | SHRINE 6240034 | 1" liner | 2025-12-08 | Z | 2025-11-19 | 70 | 0 | 0 |  | 50 | 100 |  |  |  | 19
2025-12-02 | 866 | sp | 68899 | A | DONE | 5 | S/M |  | SPH 6240039 |  | 2025-12-08 | Z | 2025-11-19 | 20 | 110 | 0 | . | 0 | 120 |  | Blue phase |  | 19
2025-12-01 | 509 | sp | 69792 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-08 | Z | 2025-11-03 | 10 | 30 | 0 |  | 0 | 40 |  | RTU-2 1st floor SA |  | 35
2025-12-01 | 511 |  | 69795-97 | A | DONE | 59 | L |  | SWH MOB 6250015 |  | 2025-12-08 | Z | 2025-11-05 | 470 | 0 | 410 |  | 0 | 1470 |  | RTU 1 1st floor RA |  | 33
2025-12-02 | 513 |  | 69798-00,75554 | A | DONE | 42 | M/L |  | SWH MOB 6250015 |  | 2025-12-08 | Z | 2025-11-06 | 360 | 0 | 510 |  | 0 | 1040 |  | 1st Floor RTU-1 RA |  | 32
2025-12-02 | 535 |  | 76700 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-08 | Z | 2025-11-19 | 30 | 0 | 0 |  | 0 | 40 |  | VAV 2-4 |  | 19
2025-12-03 | 76687 |  | 76687 | A | DONE | 4 | S |  | SWH MOB 6250015 |  | 2025-12-08 | Z | 2025-12-01 | 70 | 0 | 0 |  | 0 | 90 |  | 1st floor RTU-1 tie ins |  | 7
2025-12-03 | 77058 |  | 77058 | A | DONE | 3 | S |  | TOMAH HEALTH 6250006 |  | 2025-12-08 | Z | 2025-11-25 | 40 | 0 | 0 |  | 40 | 60 |  | RA Grills |  | 13
2025-12-02 | 69070 |  | 69070 | A | DONE | 2 | S | ss | UW AVRL 6240038 | pipe shop | 2025-12-01 | Z | 2025-11-20 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 11
2025-12-03 | 69071 |  | 69071 | A | DONE | 2 | S | ss | UW AVRL 6240038 |  | 2025-12-03 | Z | 2025-12-02 | 10 | 0 | 0 |  | 0 | 20 |  | 5th floor |  | 1
2025-12-03 | 78310 |  | 78310 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | paint black | 2025-12-09 | Z | 2025-12-02 | 20 | 0 | 0 |  | 20 | 20 |  | L2 return |  | 7
2025-12-04 | 2985 | bth | L4-SAMP 30 | A | DONE | 6 | S |  | UW STOUT 6250008 |  | 2025-12-09 | Z | 2025-10-30 | 80 | 20 | 30 |  | 0 | 140 |  |  |  | 40 | 2025-11-25
2025-12-04 | 2986 | bth | L4-SAMP 31 | A | DONE | 6 | S |  | UW STOUT 6250008 |  | 2025-12-09 | Z | 2025-10-30 | 70 | 30 | 30 |  | 0 | 140 |  |  |  | 40 | 2025-11-25
2025-12-04 | 2987 | bth | L4-SAMP 32 | A | DONE | 6 | S |  | UW STOUT 6250008 |  | 2025-12-09 | Z | 2025-10-30 | 90 | 30 | 0 |  | 0 | 150 |  |  |  | 40 | 2025-11-25
2025-12-04 | 2988 | sp | L4-SAMP 33 | A | DONE | 6 | S |  | UW STOUT 6250008 |  | 2025-12-09 | Z | 2025-10-30 | 20 | 130 | 0 |  | 0 | 150 |  |  |  | 40 | 2025-11-25
2025-12-04 | 2989 |  | L4-SAMP 34 | A | DONE | 4 | S |  | UW STOUT 6250008 |  | 2025-12-09 | Z | 2025-10-30 | 40 | 0 | 40 |  | 0 | 90 |  |  |  | 40 | 2025-11-25
2025-12-04 | 76201 | sp | 76201 | A | DONE | 2 | S | alum | UW VET MED 6210014 |  | 2025-12-08 | Z | 2025-12-02 | 10 | 10 | 0 |  | 0 | 10 |  | Dryer vent |  | 6
2025-12-03 | 76202 |  | 76202 | A | DONE | 2 | S |  | UW VET MED 6210014 |  | 2025-12-08 | Z | 2025-12-02 | 10 | 0 | 0 |  | 0 | 10 |  | Misc |  | 6
2025-12-02 | 82931 | bth | 82931-32,82936 | A | DONE | 35 | M/L |  | WAUNAKEE 6230013 | flex, CD | 2025-12-05 | Z | 2025-11-20 | 400 | 20 | 0 |  | 10 | 870 |  | Generator room |  | 15
2025-12-01 | 83424 |  | 83424 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-12-05 | Z | 2025-12-01 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 4
2025-12-02 | 83425 |  | 83425 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-12-05 | Z | 2025-12-01 | 10 | 0 | 0 |  | 0 | 20 |  | 2nd D return |  | 4
[6 empty] | 1188 | [13 empty] | 28060 | [5 empty] | 35% Short
WEEK OF 12-8-2025
2025-12-10 | 74815 |  | 74815 | A | DONE | 2 | S |  | ANITGO 6250017 |  | 2025-12-12 | Z | 2025-12-10 | 50 | 0 | 0 |  | 0 | 50 |  | Bull nosing |  | 2
2025-12-08 | 70197 |  | 70197,003 | A | DONE | 12 | S/M | neal | ANTIGO 6250017 | 1" liner, VD | 2025-12-16 | Z | 2025-11-26 | 120 | 0 | 90 |  | 50 | 300 |  | H2.1 AHU-1 |  | 20
2025-12-11 | 74263 |  | 74263 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2025-12-15 | Z | 2025-12-10 | 10 | 0 | 0 |  | 0 | 30 |  | Misc |  | 5
2025-12-08 | 1280 |  | DOAS-2 L2-L5 | A | DONE | 10 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-24 | 60 | 0 | 170 |  | 0 | 230 |  |  |  | 15
2025-12-08 | 1281 |  | JC EXHAUST 1E-5E | A | DONE | 13 | S/M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-24 | 170 | 0 | 70 |  | 0 | 320 |  |  |  | 15
2025-12-08 | 1282 |  | STAIR 2 RISER L2-L5 | A | DONE | 16 | M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-24 | 60 | 0 | 250 |  | 0 | 400 |  |  |  | 15
2025-12-08 | 1283 |  | TRASH EXHAUST L1E-L5E | A | DONE | 23 | M |  | BROOM ST. 6240033 |  | 2025-12-09 | Z | 2025-11-24 | 100 | 0 | 340 |  | 0 | 560 |  |  |  | 15
2025-12-08 | 79480 |  | 79480 | A | DONE | 10 | S/M |  | BROOM ST. 6240033 | paint black/partial | 2025-12-09 | Z | 2025-11-25 | 160 | 0 | 0 |  | 140 | 250 |  | Grille boxes |  | 14
2025-12-10 | 79488 |  | 79488 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-12-11 | Z | 2025-12-09 | 50 | 0 | 0 |  | 0 | 50 |  | L2 CAD fixes |  | 2
2025-12-10 | 79489 |  | 79489 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-12-11 | Z | 2025-12-10 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 1
2025-12-08 | 74045 |  | 74045 | A | DONE | 6 | S/M | neal | DELLSHIRE 6240017 |  | 2025-12-09 | Z | 2025-12-04 | 70 | 0 | 0 |  | 0 | 130 |  | Misc 2nd C |  | 5
2025-12-11 | 74046 |  | 74046 | A | DONE | 4 | S | neal | DELLSHIRE 6240017 | spiral mate | 2025-12-14 | Z | 2025-12-09 | 60 | 0 | 0 |  | 0 | 100 |  | 2nd fec changes |  | 5
2025-12-08 | 74062 | bth | 74062 | A | DONE | 12 | S/M | neal | DELLSHIRE 6240017 | VD | 2025-12-10 | Z | 2025-12-01 | 110 | 130 | 0 |  | 0 | 280 |  | FEC |  | 9
2025-12-10 | 74063 |  | 74063 | A | DONE | 3 | S |  | DELLSHIRE 6240017 |  | 2025-12-14 | Z | 2025-12-09 | 40 | 0 | 0 |  | 0 | 60 |  | FEC RA chase |  | 5 |  | 2025-11-06
2025-12-09 | 12925 |  | 12925 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-09 | Z | 2025-12-09 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 0 |  | 2025-11-06
2025-12-10 | 3173 | bth | Z2-SAT-4-1-30_1 | A | DONE | 16 | M |  | DOC JDC 6240023 | 1" liner | 2025-12-11 | Z | 2025-09-17 | 150 | 80 | 90 |  | 50 | 400 |  |  |  | 85 | 2025-11-13 | 2025-11-06
2025-12-10 | 3175 |  | Z2-SAT-4-1-30_3 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-12-11 | Z | 2025-09-17 | 60 | 100 | 0 |  | 0 | 180 |  |  |  | 85 | 2025-11-13 | 2025-11-06
2025-12-09 | 3176 | bth | Z2-SAT-4-1-31 | A | DONE | 8 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-11 | Z | 2025-09-17 | 130 | 0 | 0 |  | 30 | 190 |  |  |  | 85 | 2025-11-13 | 2025-11-06
2025-12-08 | 3177 | bth | Z2-SAT-4-1-32 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-11 | Z | 2025-09-17 | 30 | 20 | 0 |  | 20 | 60 |  |  |  | 85 | 2025-11-13
2025-12-09 | 3178 | bth | Z2-SAT-4-1-33 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-11 | Z | 2025-09-17 | 50 | 30 | 20 |  | 30 | 130 |  |  |  | 85 | 2025-11-13 | 2025-11-06
2025-12-09 | 3179 | bth | Z2-SAT-4-1-34 | A | DONE | 10 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-11 | Z | 2025-09-17 | 110 | 90 | 0 |  | 20 | 240 |  |  |  | 85 | 2025-11-13
2025-12-09 | 706 |  | Z2-EA 37 | A | DONE | 32 | M |  | DOC JDC 6240023 | 601 caulk | 2025-12-11 | Z | 2025-07-30 | 200 | 0 | 380 |  | 0 | 780 |  |  |  | 134 | 2025-09-04 | 2025-11-06
2025-12-10 | 74814 |  | 74814 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2025-12-10 | Z | 2025-12-09 | 30 | 0 | 0 |  | 0 | 70 |  |  |  | 1 |  | 2025-11-06
2025-12-08 | 787 | bth | Z1-SAT-3-1-9 | A | DONE | 5 | S/M |  | DOC JDC 6240023 | VD , 1" liner | 2025-12-09 | Z | 2025-07-31 | 40 | 60 | 0 |  | 30 | 120 |  |  |  | 131 | 2025-09-18
2025-12-08 | 789 | bth | Z1-SAT-3-1-11 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-09 | Z | 2025-07-31 | 50 | 70 | 0 |  | 30 | 130 |  |  |  | 131 | 2025-09-18
2025-12-10 | 74752 | bth | 74752-55 | A | DONE | 25 | M |  | GREAT WOLF 4250055 |  | 2025-12-10 | Z | 2025-12-04 | 220 | 420 | 0 |  | 0 | 610 |  | FCU |  | 6
2025-12-11 | 74757 |  | 74757 | A | DONE | 5 | S/M |  | GREAT WOLF 4250055 |  | 2025-12-11 | Z | 2025-12-11 | 70 | 0 | 0 |  | 0 | 110 |  | fcu-2-06 |  | 0
2025-12-08 | 74062 |  | 74062 | A | DONE | 2 | S |  | HOLY NAME 4250051 | birdscreen | 2025-12-15 | Z | 2025-12-05 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 10
2025-12-11 | 3936 | sp | FE-L1C-01 | A | DONE | 25 | M | neal | MONROE 6240018 | 601 caulk | 2025-12-24 | Z | 2025-11-20 | 80 | 270 | 0 |  | 0 | 610 |  |  |  | 34 | 2025-12-11
2025-12-11 | 3944 | sp | FE-L1C-09 | A | DONE | 13 | S/M | neal | MONROE 6240018 | 601 caulk | 2025-12-24 | Z | 2025-11-20 | 30 | 170 | 0 |  | 0 | 310 |  |  |  | 34 | 2025-12-11
2025-12-09 | 74352 | w | 74352-53 | A | DONE | 11 | S/M | ss | MONROE 6240018 |  | 2025-12-09 | Z | 2025-11-21 | 100 | 0 | 0 |  | 0 | 270 |  | Kitchen hood |  | 18
2025-12-10 | 74816 |  | 74816 | A | DONE | 2 | S |  | MONROE 6240018 |  | 2025-12-11 | Z | 2025-12-10 | 10 | 0 | 0 |  | 0 | 20 |  | Reducer |  | 1
2025-12-09 | 83624 |  | 83624,26,27,664 | A | DONE | 12 | S/M |  | MONROE 6240018 |  | 2025-12-10 | Z | 2025-12-04 | 210 | 0 | 0 |  | 0 | 300 |  | Flashing |  | 6
2025-12-08 | 83662 | bth | 83662-63 | A | DONE | 5 | S/M | neal | MONROE 6240018 | flex | 2025-12-10 | Z | 2025-12-03 | 90 | 0 | 0 |  | 0 | 110 |  |  |  | 7
2025-12-08 | 74756 |  | 74756 | A | DONE | 2 | S |  | OCTOPY 4250042 |  | 2025-12-10 | Z | 2025-12-04 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2025-12-10 | 76691 |  | 76691 | A | DONE | 3 | S | neal | PECATONICA 6240005 |  | 2025-12-14 | Z | 2025-12-08 | 30 | 0 | 0 |  | 10 | 60 |  | Fl 1&2 warranty |  | 6 |  | 2025-09-02
2025-12-10 | 74063 |  | 74063 | A | DONE | 4 | S | neal | PLACON 10066019 | birdscreen, 1" liner | 2025-12-14 | Z | 2025-12-05 | 40 | 0 | 50 |  | 70 | 100 |  |  |  | 9 |  | 2025-09-02
2025-12-08 | 76196 |  | 76196 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-12-11 | Z | 2025-12-04 | 10 | 0 | 0 |  | 0 | 10 |  | 600 2nd fl EA |  | 7 |  | 2025-09-02
2025-12-09 | 76224 |  | 76224-25 | A | DONE | 7 | S/M |  | PROJECT DOVE 6240041 | flex | 2025-12-11 | Z | 2025-12-08 | 40 | 0 | 0 |  | 0 | 160 |  | L1 Shipping 052 |  | 3 |  | 2025-09-02
2025-12-08 | 76375 |  | 76375 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | bird screen | 2025-12-11 | Z | 2025-12-02 | 20 | 0 | 0 |  | 0 | 50 |  | L2 600 west |  | 9 |  | 2025-09-02
2025-12-09 | 1354 |  | 75856 - 75857 | A | DONE | 38 | M/L | semi | RICHLAND CTR. 6250011 |  | 2025-12-16 | Z | 2025-09-24 | 80 | 0 | 590 |  | 0 | 950 |  | B-Section East |  | 83 |  | 2025-09-02
2025-12-09 | 1355 |  | 81072 | A | DONE | 41 | M/L | semi | RICHLAND CTR. 6250011 |  | 2025-12-16 | Z | 2025-09-24 | 110 | 0 | 590 |  | 0 | 1010 |  | Café SA |  | 83
2025-12-10 | 1356 |  | 81075 - 81076 | A | DONE | 38 | M/L | semi | RICHLAND CTR. 6250011 |  | 2025-12-16 | Z | 2025-09-24 | 330 | 0 | 270 |  | 0 | 950 |  | Café SA |  | 83
2025-12-09 | 1357 |  | 81078 - 81080 | A | DONE | 84 | L | semi | RICHLAND CTR. 6250011 |  | 2025-12-16 | Z | 2025-09-24 | 500 | 0 | 720 |  | 0 | 2080 |  | Café SA |  | 83
2025-12-10 | 1358 |  | 81081 - 81082 | A | DONE | 20 | M | semi | RICHLAND CTR. 6250011 |  | 2025-12-16 | Z | 2025-09-24 | 170 | 0 | 260 |  | 0 | 500 |  | Café SA |  | 83
2025-12-10 | 1371 |  | 75859 - 75860 | A | DONE | 30 | M | semi | RICHLAND CTR. 6250011 |  | 2025-12-16 | Z | 2025-09-30 | 50 | 0 | 490 |  | 0 | 740 |  | Balcony / Storage |  | 77
2025-12-12 | 1015 |  | B-SA-01 | A | DONE | 4 | S | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 60 | 30 | 0 |  | 40 | 100 |  |  |  | 24
2025-12-11 | 1016 | bth | B-SA-02 | A | DONE | 6 | S/M | semi | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 70 | 10 | 30 |  | 70 | 140 |  |  |  | 24
2025-12-11 | 1017 |  | B-SA-03 | A | DONE | 5 | S/M | semi | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 70 | 0 | 30 |  | 70 | 120 |  |  |  | 24
2025-12-08 | 1018 |  | B-SA-04 | A | DONE | 3 | S |  | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 24
2025-12-08 | 1019 | bth | B-SA-05 | A | DONE | 3 | S |  | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 40 | 0 | 0 |  | 40 | 70 |  |  |  | 24
2025-12-11 | 1020 |  | B-SA-06 | A | DONE | 4 | S | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 70 | 0 | 0 |  | 60 | 100 |  |  |  | 24
2025-12-11 | 1021 |  | B-SA-07 | A | DONE | 5 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 80 | 0 | 0 |  | 70 | 110 |  |  |  | 24
2025-12-10 | 1022 |  | B-SA-08 | A | DONE | 4 | S | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 70 | 0 | 0 |  | 60 | 100 |  |  |  | 24
2025-12-09 | 1023 |  | B-SA-09 | A | DONE | 5 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 90 | 0 | 0 |  | 80 | 120 |  |  |  | 24
2025-12-11 | 1024 |  | B-SA-10 | A | DONE | 7 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 110 | 0 | 0 |  | 100 | 170 |  |  |  | 24
2025-12-11 | 1025 |  | B-SA-11 | A | DONE | 5 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 80 | 0 | 0 |  | 70 | 110 |  |  |  | 24
2025-12-11 | 1026 |  | B-SA-12 | A | DONE | 5 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 80 | 0 | 0 |  | 80 | 120 |  |  |  | 24
2025-12-11 | 1027 |  | B-SA-13 | A | DONE | 5 | S/M | semi | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 50 | 40 | 0 |  | 30 | 110 |  |  |  | 24
2025-12-11 | 1028 | sp | B-SA-14 | A | DONE | 4 | S | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 10 | 70 | 0 |  | 0 | 80 |  |  |  | 24
2025-12-11 | 1030 |  | B-SA-16 | A | DONE | 9 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 120 | 0 | 30 |  | 120 | 210 |  |  |  | 24
2025-12-12 | 1031 |  | B-SA-17 | A | DONE | 8 | S/M | semi | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 120 | 40 | 0 |  | 100 | 200 |  |  |  | 24
2025-12-11 | 1032 |  | B-SA-18 | A | DONE | 6 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 100 | 0 | 0 |  | 90 | 150 |  |  |  | 24
2025-12-11 | 1033 | bth | B-SA-19 | A | DONE | 4 | S | semi | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 40 | 50 | 0 |  | 20 | 90 |  |  |  | 24
2025-12-11 | 1034 |  | B-SA-20 | A | DONE | 4 | S | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 50 | 0 | 0 |  | 50 | 80 |  |  |  | 24
2025-12-11 | 1035 | bth | B-SAMP-01 | A | DONE | 4 | S | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 20 | 40 | 30 |  | 30 | 100 |  |  |  | 24
2025-12-11 | 1036 |  | B-SAMP-02 | A | DONE | 3 | S | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 24
2025-12-11 | 1037 |  | B-SAMP-03 | A | DONE | 24 | M | semi | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 280 | 0 | 0 |  | 220 | 590 |  |  |  | 24
2025-12-12 | 1038 | bth | B-SAMP-04 | A | DONE | 16 | M | semi | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 130 | 40 | 60 |  | 160 | 390 |  |  |  | 24
2025-12-12 | 1039 | bth | B-SAMP-05 | A | DONE | 17 | M | semi | SHRINE 6240034 | 1" liner, VD | 2025-12-15 | Z | 2025-11-21 | 90 | 20 | 110 |  | 170 | 420 |  |  |  | 24
2025-12-12 | 1040 |  | B-SAMP-06 | A | DONE | 29 | M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 260 | 0 | 160 |  | 370 | 710 |  |  |  | 24
2025-12-11 | 1044 | bth | B-SAMP-10 | A | DONE | 6 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-15 | Z | 2025-11-21 | 40 | 40 | 30 |  | 50 | 130 |  |  |  | 24
2025-12-11 | 1045 | sp | B-SAMP-11 | A | DONE | 3 | S | semi | SHRINE 6240034 |  | 2025-12-15 | Z | 2025-11-21 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 24
2025-12-12 | 1047 |  | B-SAMP-13 | A | DONE | 9 | S/M | semi | SHRINE 6240034 |  | 2025-12-15 | Z | 2025-11-21 | 110 | 0 | 50 |  | 0 | 210 |  |  |  | 24
2025-12-09 | 68900 |  | 68900 | A | DONE | 2 | S |  | SPH 6240039 |  | 2025-12-14 | Z | 2025-12-01 | 20 | 0 | 0 |  | 0 | 20 |  | Blue phase |  | 13
2025-12-10 | 68940 | sp | 68940 | A | DONE | 2 | S |  | SPH 6240039 | VD | 2025-12-14 | Z | 2025-12-02 | 20 | 0 | 0 |  | 0 | 20 |  | Ex/blue |  | 12
2025-12-10 | 68941 |  | 68941,68943 | A | DONE | 4 | S |  | SPH 6240039 |  | 2025-12-14 | Z | 2025-12-02 | 50 | 0 | 20 |  | 0 | 80 |  | Green phase |  | 12
2025-12-11 | 68942 | sp | 68942 | A | DONE | 17 | M |  | SPH 6240039 |  | 2025-12-14 | Z | 2025-12-02 | 40 | 400 | 0 |  | 0 | 410 |  | Green phase |  | 12
2025-12-09 | 68944 |  | 68944 | A | DONE | 2 | S |  | SPH 6240039 |  | 2025-12-15 | Z | 2025-12-03 | 10 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 12
2025-12-09 | 867 |  | 68896-98 | A | DONE | 5 | S/M |  | SPH 6240039 | VD | 2025-12-15 | Z | 2025-11-19 | 80 | 0 | 30 |  | 0 | 120 |  | Yellow phase |  | 26
2025-12-09 | 516 |  | 75563-65 | A | DONE | 19 | M |  | SWH MOB 6250015 | VD | 2025-12-15 | Z | 2025-11-11 | 280 | 0 | 110 |  | 0 | 460 |  | RTU 1 1st fl RA |  | 34
2025-12-12 | 517 | sp | 75566-69 | A | DONE | 11 | S/M |  | SWH MOB 6250015 | VD | 2025-12-15 | Z | 2025-11-11 | 60 | 210 | 0 |  | 0 | 270 |  | RTU 1 1st fl RA |  | 34
2025-12-09 | 518 |  | 75597 | A | DONE | 4 | S |  | SWH MOB 6250015 | VD | 2025-12-15 | Z | 2025-11-11 | 50 | 0 | 0 |  | 0 | 80 |  | 150/152 RA branch duct |  | 34
2025-12-10 | 76688 |  | 76688 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-14 | Z | 2025-12-02 | 10 | 0 | 0 |  | 0 | 10 |  | VAV 1-18 red |  | 12
2025-12-11 | 76689 | sp | 76689 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-14 | Z | 2025-12-03 | 10 | 10 | 0 |  | 0 | 10 |  | VAV 1-16 |  | 11
2025-12-09 | 76690 |  | 76690 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-15 | Z | 2025-12-04 | 20 | 0 | 0 |  | 0 | 20 |  | RTU-1 RA |  | 11
2025-12-11 | 76692 |  | 76692 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-14 | Z | 2025-12-09 | 30 | 0 | 0 |  | 0 | 40 |  | FC 1&2 warranty |  | 5
2025-12-12 | 76693 |  | 76693 | A | DONE | 4 | S |  | SWH MOB 6250015 |  | 2025-12-15 | Z | 2025-12-11 | 0 | 0 | 60 |  | 0 | 100 |  | RTU-1 RA tie in |  | 4
2025-12-09 | 77059 |  | 77059 | A | DONE | 3 | S |  | TOMAH HEALTH 6250006 | paint black | 2025-12-15 | Z | 2025-12-08 | 50 | 0 | 0 |  | 40 | 60 |  | Return soffit tie ins |  | 7
2025-12-11 | 77060 |  | 77060 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-12-14 | Z | 2025-12-09 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 5
2025-12-11 | 77061 |  | 77061 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2025-12-14 | Z | 2025-12-09 | 20 | 0 | 0 |  | 0 | 30 |  | Return soffit tie in |  | 5
2025-12-11 | 69072 | w | 69072 | A | DONE | 2 | S | ss | UW AVRL 6240038 | flanges | 2025-12-08 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 40 |  | 5th flr BSL-3 |  | 5
2025-12-08 | 76133 |  | 76133 | A | DONE | 15 | M |  | UW LEVY HALL 6230028 |  | 2025-12-09 | Z | 2025-12-03 | 200 | 0 | 0 |  | 0 | 360 |  | RAMP-6 Penthouse |  | 6
2025-12-09 | 76134 |  | 76134 | A | DONE | 8 | S/M |  | UW LEVY HALL 6230028 |  | 2025-12-09 | Z | 2025-12-05 | 80 | 0 | 0 |  | 0 | 190 |  | Penthouse |  | 4
2025-12-11 | 76135 |  | 76135 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 |  | 2025-12-16 | Z | 2025-12-09 | 20 | 0 | 0 |  | 0 | 30 |  | Penthouse |  | 7
2025-12-08 | 78311 |  | 78311 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | paint black | 2025-12-09 | Z | 2025-12-04 | 30 | 0 | 0 |  | 20 | 40 |  | L2 grille tie in |  | 5
2025-12-08 | 2990 |  | L4-SAMP 35 | A | DONE | 2 | S |  | UW STOUT 6250008 | flex | 2025-12-09 | Z | 2025-10-30 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 40 | 2025-11-25
2025-12-08 | 2991 |  | L4-SAMP 36 | A | DONE | 2 | S |  | UW STOUT 6250008 | flex | 2025-12-09 | Z | 2025-10-30 | 10 | 0 | 0 |  | 0 | 30 |  |  |  | 40 | 2025-11-25
2025-12-08 | 82196r |  | 82196r | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2025-12-08 | Z | 2025-12-08 | 20 | 0 | 0 |  | 0 | 30 |  | Remake |  | 0
2025-12-08 | 75725 |  | 75725 | A | DONE | 18 | M |  | UWP 6240031 | flex | 2025-12-11 | Z | 2025-11-20 | 340 | 0 | 40 |  | 0 | 440 |  | EF-3 |  | 21
2025-12-12 | 98991 |  | 98991 | A | DONE | 2 | S |  | UWP 6240031 |  | 2025-12-12 | Z | 2025-12-12 | 10 | 0 | 0 |  | 0 | 30 |  | Metal gaskets |  | 0
2025-12-10 | 83427 |  | 83427 | A | DONE | 2 | S |  | WAUNAKEE 6230013 | paint black | 2025-12-12 | Z | 2025-12-10 | 30 | 0 | 0 |  | 10 | 30 |  | 1st D |  | 2
2025-12-08 | 73819 |  | 73819 | A | DONE | 2 | S |  | WAUNAKEE 6230023 | 1" liner | 2025-12-12 | Z | 2025-12-05 | 30 | 0 | 0 |  | 30 | 50 |  | 1A dry storage |  | 7
2025-12-08 | 83426 |  | 83426 | A | DONE | 6 | S/M |  | WAUNAKEE 6230023 |  | 2025-12-12 | Z | 2025-12-05 | 130 | 0 | 0 |  | 0 | 150 |  | Angle |  | 7
2025-12-10 | 77272 |  | 77272 | A | DONE | 2 | S |  | WHC 6250007 |  | 2025-12-12 | Z | 2025-12-09 | 30 | 0 | 0 |  | 0 | 50 |  | Flashing |  | 3
[6 empty] | 946 | [13 empty] | 22290 | [5 empty] | 43% Short
WEEK OF 12-15-2025
2025-12-16 | 01215 |  | 01215 | A | DONE | 2 | S |  | ANTIGO 6250017 |  | 2025-12-15 | Z | 2025-12-15 | 10 | 0 | 0 |  | 0 | 20 |  | Elbows |  | 0
2025-12-15 | 70196 | sp | 70196,70198 | A | DONE | 27 | M |  | ANTIGO 6250017 | VD | 2025-12-16 | Z | 2025-11-26 | 160 | 440 | 0 |  | 0 | 670 |  | H2.1 AHU-1 |  | 20
2025-12-15 | 70199 |  | 70199 | A | DONE | 17 | M | neal | ANTIGO 6250017 | 1" liner, nosing | 2025-12-16 | Z | 2025-12-01 | 110 | 0 | 220 |  | 290 | 420 |  | BCU-1 |  | 15
2025-12-15 | 70200 |  | 70200 | A | DONE | 26 | M | neal | ANTIGO 6250017 | 2" liner, nosing | 2025-12-16 | Z | 2025-12-01 | 120 | 0 | 380 |  | 420 | 640 |  | BCU-1 |  | 15
2025-12-15 | 82751 | sp | 82751 | A | DONE | 10 | S/M |  | ANTIGO 6250017 |  | 2025-12-16 | Z | 2025-12-01 | 30 | 230 | 0 |  | 0 | 240 |  | BCU-1 |  | 15
2025-12-15 | 74264 |  | 74264 | A | DONE | 2 | S | ss | BARTILLION 6240024 |  | 2025-12-17 | Z | 2025-12-10 | 10 | 0 | 0 |  | 0 | 20 |  | Misc. |  | 7
2025-12-15 | 1284 |  | UNIT 744 M4.75 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 70 | 0 | 40 |  | 0 | 120 |  |  |  | 22
2025-12-15 | 1285 |  | UNIT 745 M4.76 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 70 | 0 | 0 |  | 0 | 80 |  |  |  | 22
2025-12-15 | 1286 |  | UNIT 747 M4.77 | A | DONE | 13 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 240 | 0 | 80 |  | 0 | 320 |  |  |  | 22
2025-12-15 | 1287 |  | UNIT 749 M4.93 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 170 | 0 | 110 |  | 0 | 300 |  |  |  | 22
2025-12-15 | 1288 |  | UNIT 751 M4.94 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 60 | 0 | 60 |  | 0 | 130 |  |  |  | 22
2025-12-16 | 1289 |  | UNIT 753 M4.95 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 170 | 0 | 110 |  | 0 | 280 |  |  |  | 22
2025-12-15 | 1290 |  | UNIT 754 M4.96 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 180 | 0 | 80 |  | 0 | 260 |  |  |  | 22
2025-12-15 | 1291 |  | UNIT 755 M4.97 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 80 | 80 | 0 |  | 0 | 170 |  |  |  | 22
2025-12-16 | 1292 |  | UNIT 757 M4.98 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 180 | 0 | 100 |  | 0 | 280 |  |  |  | 22
2025-12-16 | 1293 |  | UNIT 758 M4.99 | A | DONE | 15 | M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 250 | 0 | 110 |  | 0 | 360 |  |  |  | 22
2025-12-16 | 1294 |  | UNIT 760 M4.100 | A | DONE | 13 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 170 | 0 | 110 |  | 0 | 310 |  |  |  | 22
2025-12-16 | 1295 |  | UNIT 762 M4.101 | A | DONE | 7 | S/M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-11-24 | 110 | 0 | 0 |  | 0 | 160 |  |  |  | 22
2025-12-17 | 74819 |  | 74819 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-12-17 | Z | 2025-12-17 | 20 | 0 | 0 |  | 0 | 40 |  | Pan |  | 0
2025-12-18 | 79474 |  | 79474 | A | DONE | 26 | M |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-12-10 | 270 | 0 | 0 |  | 0 | 650 |  | OA Kits |  | 6
2025-12-15 | 79490 |  | 79490 | A | DONE | 2 | S |  | BROOM ST. 6240033 |  | 2025-12-16 | Z | 2025-12-12 | 20 | 0 | 0 |  | 0 | 20 |  | Plenum |  | 4 |  | 2025-09-02
2025-12-18 | 92840 |  | 92840 | A | DONE | 3 | S |  | BROOM ST. 6240033 | pipe shop caps | 2025-12-18 | Z | 2025-12-17 | 20 | 0 | 0 |  | 0 | 70 |  | Caps |  | 1
2025-12-18 | 74064 |  | 74064-67 | A | DONE | 88 | L |  | DELLSHIRE 6240017 |  | 2025-12-22 | Z | 2025-12-15 | 1030 | 0 | 400 |  | 0 | 2190 |  |  |  | 7
2025-12-18 | 74103 | sp | 74103 | A | DONE | 56 | L |  | DELLSHIRE 6240017 |  | 2025-12-18 | Z | 2025-12-17 | 80 | 1450 | 0 |  | 0 | 1380 |  | Spiral |  | 1
2025-12-16 | 75289 | bth | 75289-90,74101 | A | DONE | 9 | S/M | alum | DELLSHIRE 6240017 |  | 2025-12-17 | Z | 2025-12-15 | 160 | 40 | 0 |  | 0 | 220 |  |  |  | 2
2025-12-16 | 3164 | bth | Z2-SAT-3-1-4 | A | DONE | 9 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-09-17 | 80 | 80 | 20 |  | 30 | 220 |  |  |  | 92 | 2025-11-13 | 2025-11-06
2025-12-16 | 3167 | bth | Z2-SAT-3-1-17 | A | DONE | 12 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-09-17 | 110 | 80 | 60 |  | 30 | 290 |  |  |  | 92 | 2025-11-13 | 2025-11-06
2025-12-17 | 3168 | bth | Z2-SAT-3-1-18 | A | DONE | 5 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-09-17 | 50 | 60 | 0 |  | 20 | 110 |  |  |  | 92 | 2025-11-13 | 2025-10-16
2025-12-16 | 56090 |  | 56090 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-18 | Z | 2025-12-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2025-12-16 | 56091 |  | 56091 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-18 | Z | 2025-12-15 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 3
2025-12-16 | 56092 |  | 56092 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2025-12-18 | Z | 2025-12-15 | 100 | 0 | 0 |  | 0 | 140 |  | Chase changes |  | 3
2025-12-16 | 56092a | bth | 56092a | A | DONE | 9 | S/M |  | DOC JDC 6240023 |  | 2025-12-18 | Z | 2025-12-15 | 30 | 120 | 50 |  | 0 | 220 |  |  |  | 3
2025-12-17 | 56093 |  | 56093 | A | DONE | 3 | S |  | DOC JDC 6240023 |  | 2025-12-18 | Z | 2025-12-16 | 40 | 10 | 0 |  | 0 | 60 |  | Outs |  | 2
2025-12-17 | 785 | bth | Z1-SAT-3-1-7_1 | A | DONE | 8 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-07-31 | 50 | 130 | 0 |  | 30 | 190 |  |  |  | 140 | 2025-09-18 | 2025-11-06
2025-12-17 | 788 | bth | Z1-SAT-3-1-10 | A | DONE | 8 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-07-31 | 70 | 90 | 0 |  | 40 | 180 |  |  |  | 140 | 2025-09-18 | 2025-11-06
2025-12-16 | 790 | bth | Z1-SAT-3-1-12 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-07-31 | 20 | 10 | 0 |  | 20 | 30 |  |  |  | 140 | 2025-09-18 | 2025-11-06
2025-12-16 | 791 | bth | Z1-SAT-3-1-13 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-07-31 | 30 | 20 | 0 |  | 20 | 50 |  |  |  | 140 | 2025-09-18 | 2025-11-06
2025-12-16 | 792 | bth | Z1-SAT-3-1-14 | A | DONE | 7 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-07-31 | 70 | 40 | 40 |  | 0 | 170 |  |  |  | 140 | 2025-09-18 | 2025-11-06
2025-12-16 | 793 | bth | Z1-SAT-3-1-15 | A | DONE | 4 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-18 | Z | 2025-07-31 | 40 | 40 | 0 |  | 30 | 90 |  |  |  | 140 | 2025-09-18 | 2025-11-06
2025-12-18 | 84391r | w | 84391r | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-12-18 | 10 | 0 | 0 |  | 0 | 30 |  | Welded elbow |  | 11
2025-12-16 | 84392 |  | 84392-94 | A | DONE | 18 | M |  | DOC JDC 6240023 |  | 2025-12-18 | Z | 2025-12-12 | 220 | 0 | 0 |  | 0 | 450 |  | Outs |  | 6
2025-12-16 | 84395 |  | 84395 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-18 | Z | 2025-12-12 | 10 | 0 | 0 |  | 0 | 30 |  |  |  | 6
2025-12-19 | 76301 |  | 76301 | A | DONE | 6 | S/M |  | E381 |  | 2025-12-23 | Z | 2025-12-17 | 100 | 0 | 50 |  | 0 | 140 |  |  |  | 6
2025-12-15 | 77562 | w | 77562 | A | DONE | 2 | S | ss | EXACT 8250028 |  | 2025-12-17 | Z | 2025-12-08 | 10 | 0 | 0 |  | 0 | 10 |  | Coffee grind disposal |  | 9
2025-12-18 | 74758 | bth | 74758 | A | DONE | 3 | S |  | GREAT WOLF 4250055 |  | 2025-12-22 | Z | 2025-12-12 | 20 | 50 | 0 |  | 0 | 70 |  | Rm 209 |  | 10
2025-12-18 | 64657 | sp | 64657-58 | A | DONE | 7 | S/M |  | MAUSTON R 6250019 | VD | 2025-12-22 | Z | 2025-12-04 | 20 | 160 | 0 |  | 0 | 170 |  | SA HP |  | 18
2025-12-18 | 64662 | bth | 64662,65-67,69-70 | A | DONE | 46 | M/L |  | MAUSTON R 6250019 | 1" liner, VD | 2025-12-22 | Z | 2025-12-04 | 460 | 120 | 340 |  | 160 | 1140 |  | VAV's |  | 18
2025-12-19 | 64671 |  | 64671-72 | A | DONE | 70 | L |  | MAUSTON R 6250019 |  | 2025-12-22 | Z | 2025-12-04 | 340 | 0 | 910 |  | 0 | 1730 |  | SA HP |  | 18
2025-12-18 | 64673 |  | 64673,85 | A | DONE | 12 | S/M |  | MAUSTON R 6250019 | 1" liner,paint black | 2025-12-22 | Z | 2025-12-04 | 140 | 0 | 70 |  | 60 | 280 |  | RA |  | 18
2025-12-18 | 64684 |  | 64684,81,82 | A | DONE | 10 | S/M | alum | MAUSTON R 6250019 | VD | 2025-12-22 | Z | 2025-12-04 | 200 | 10 | 180 |  | 0 | 250 |  | EA |  | 18
2025-12-16 | 3937 | sp | FE-L1C-02 | A | DONE | 32 | M | neal | MONROE 6240018 | 601 caulk | 2025-12-24 | Z | 2025-11-20 | 100 | 370 | 0 |  | 0 | 790 |  |  |  | 34 | 2025-12-11
2025-12-16 | 3939 | sp | FE-L1C-04 | A | DONE | 9 | S/M | neal | MONROE 6240018 | 601 caulk | 2025-12-24 | Z | 2025-11-20 | 30 | 110 | 0 |  | 0 | 210 |  |  |  | 34 | 2025-12-11
2025-12-15 | 3940 | sp | FE-L1C-05 | A | DONE | 12 | S/M | neal | MONROE 6240018 | 601 caulk | 2025-12-24 | Z | 2025-11-20 | 30 | 150 | 0 |  | 0 | 280 |  |  |  | 34 | 2025-12-11
2025-12-18 | 3945 | sp | FE-L1C-10 | A | DONE | 19 | M | neal | MONROE 6240018 | 601 caulk | 2025-12-31 | Z | 2025-11-20 | 40 | 250 | 0 |  | 0 | 460 |  |  |  | 41 | 2025-12-11
2025-12-17 | 3947 | sp | FE-L1C-12 | A | DONE | 32 | M | neal | MONROE 6240018 | 601 caulk | 2025-12-24 | Z | 2025-11-20 | 120 | 320 | 0 |  | 0 | 800 |  |  |  | 34 | 2025-12-11
2025-12-16 | 83625 |  | 83625 | A | DONE | 3 | S |  | MONROE 6240018 |  | 2025-12-17 | Z | 2025-12-16 | 20 | 0 | 0 |  | 0 | 60 |  | A sectioin flashing 2nd |  | 1
2025-12-16 | 83665 | bth | 83665 | A | DONE | 4 | S | neal | MONROE 6240018 |  | 2025-12-17 | Z | 2025-12-10 | 50 | 20 | 0 |  | 0 | 80 |  | L2-E |  | 7
2025-12-15 | 83666 |  | 83666 | A | DONE | 2 | S |  | MONROE 6240018 |  | 2025-12-17 | Z | 2025-12-10 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2025-12-16 | 83667 |  | 83667,69 | A | DONE | 3 | S |  | MONROE 6240018 | 2" liner | 2025-12-17 | Z | 2025-12-12 | 50 | 0 | 0 |  | 10 | 70 |  |  |  | 5
2025-12-17 | 83670 |  | 83670,85859 | A | DONE | 2 | S |  | MONROE 6240018 | 1" liner | 2025-12-17 | Z | 2025-12-12 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 5
2025-12-16 | 83671 |  | 83671 | A | DONE | 2 | S | neal | MONROE 6240018 |  | 2025-12-17 | Z | 2025-12-15 | 10 | 0 | 0 |  | 0 | 10 |  | 1st floor E |  | 2
2025-12-16 | 83672 |  | 83672-73 | A | DONE | 13 | S/M | neal | MONROE 6240018 |  | 2025-12-17 | Z | 2025-12-15 | 160 | 0 | 0 |  | 0 | 310 |  | Flashing |  | 2
2025-12-17 | 83718 |  | 83718 | A | DONE | 4 | S |  | MONROE 6240018 |  | 2025-12-17 | Z | 2025-12-03 | 50 | 0 | 0 |  | 0 | 80 |  | EA-L1C |  | 14
2025-12-15 | 83719 |  | 83719 | A | DONE | 3 | S |  | MONROE 6240018 | 2" liner | 2025-12-17 | Z | 2025-12-03 | 40 | 0 | 0 |  | 0 | 60 |  | SALP-L1C |  | 14
2025-12-19 | 83720 | sp | 83720 | A | DONE | 2 | S | neal | MONROE 6240018 |  | 2025-12-24 | Z | 2025-12-17 | 30 | 20 | 0 |  | 0 | 50 |  | BCU-5A |  | 7
2025-12-18 | 95837 |  | 95837 | A | DONE | 5 | S/M |  | OAW 8250017 | Pipe Shop | 2025-12-19 | Z | 2025-12-18 | 50 | 0 | 0 |  | 0 | 120 |  | Send to pipe shop |  | 1
2025-12-19 | 95838 |  | 95838 | A | DONE | 2 | S |  | OAW 8250017 |  | 2025-12-19 | Z | 2025-12-19 | 10 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2025-12-18 | 005 | w | Stainless Repair | A | DONE | 2 |  | ss | OCTOPI 4250042 |  | 2025-12-18 | Z | 2025-12-18 | 0 | 0 | 0 |  | 0 | 30 |  |  |  | 0
2025-12-15 | 76837 |  | 76837 | A | DONE | 2 | S | neal | PEWAUKEE HS 6240030 |  | 2025-12-16 | Z | 2025-12-10 | 10 | 0 | 0 |  | 0 | 20 |  | Kiln 90 |  | 6
2025-12-16 | 74818 |  | 74818 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-12-18 | Z | 2025-12-16 | 10 | 0 | 0 |  | 0 | 20 |  | 700 Chem Storage |  | 2
2025-12-18 | 76197 |  | 76197 | A | DONE | 2 | S |  | PROJECT DOVE 6240041 |  | 2025-12-18 | Z | 2025-12-18 | 10 | 0 | 0 |  | 0 | 10 |  | Couplers |  | 0
2025-12-17 | 76226 |  | 76226-28,76232 | A | DONE | 10 | S/M |  | PROJECT DOVE 6240041 |  | 2025-12-18 | Z | 2025-12-10 | 120 | 0 | 0 |  | 20 | 230 |  | Flashing |  | 8
2025-12-19 | 76242 | w | 76242 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-12-24 | Z | 2025-12-15 | 10 | 0 | 0 |  | 0 | 30 |  | 052 lab |  | 9
2025-12-18 | 76378 |  | 76378 | A | DONE | 6 | S/M |  | PROJECT DOVE 6240041 |  | 2025-12-18 | Z | 2025-12-17 | 40 | 0 | 0 |  | 30 | 150 |  |  |  | 1
2025-12-17 | 76001 |  | 76001, 75956 | A | DONE | 2 | S |  | RCIS 6250011 |  | 2025-12-22 | Z | 2025-12-05 | 10 | 0 | 0 |  | 0 | 30 |  | Sleeves |  | 17
2025-12-17 | 1359 | sp | 81084 | A | DONE | 10 | S/M | semi | RICHLAND CTR. 6250011 |  | 2025-12-23 | Z | 2025-09-24 | 0 | 270 | 0 |  | 0 | 250 |  | Café SA |  | 90 |  | 2025-09-02
2025-12-16 | 1360 | sp | 75851 - 75853 | A | DONE | 29 | M | semi | RICHLAND CTR. 6250011 |  | 2025-12-23 | Z | 2025-09-24 | 290 | 420 | 0 |  | 0 | 720 |  | VAV take off / Spiral |  | 90 |  | 2025-09-02
2025-12-17 | 1361 | sp | 81098 - 8110 | A | DONE | 21 | M | semi | RICHLAND CTR. 6250011 |  | 2025-12-23 | Z | 2025-09-24 | 540 | 0 | 0 |  | 0 | 510 |  | VAV Spiral |  | 90 |  | 2025-09-02
2025-12-17 | 1365 | sp | 81089 | A | DONE | 6 | S/M | semi | RICHLAND CTR. 6250011 |  | 2025-12-23 | Z | 2025-09-24 | 20 | 130 | 0 |  | 0 | 140 |  | Office RA |  | 90 |  | 2025-09-02
2025-12-16 | 1372 |  | 75863 | A | DONE | 58 | L | semi | RICHLAND CTR. 6250011 |  | 2025-12-23 | Z | 2025-09-30 | 520 | 0 | 470 |  | 0 | 1450 |  | AHU-6 SA |  | 84 |  | 2025-09-02
2025-12-15 | 1373 |  | 75864 - 75865 | A | DONE | 15 | M | semi | RICHLAND CTR. 6250011 |  | 2025-12-19 | Z | 2025-10-01 | 190 | 0 | 130 |  | 0 | 370 |  | Art room north |  | 79
2025-12-17 | 1374 | sp | 75866 - 75867 | A | DONE | 12 | S/M | semi | RICHLAND CTR. 6250011 |  | 2025-12-23 | Z | 2025-10-01 | 20 | 310 | 0 |  | 0 | 300 |  | Art room north |  | 83
2025-12-16 | 76838 |  | 76838 | A | DONE | 2 | S |  | SBC 6230023 |  | 2025-12-18 | Z | 2025-12-15 | 10 | 0 | 0 |  | 0 | 30 |  | Brackets |  | 3
2025-12-15 | 1029 |  | B-SA-15 | A | DONE | 8 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-17 | Z | 2025-11-21 | 120 | 0 | 0 |  | 110 | 190 |  |  |  | 26
2025-12-16 | 1041 | bth | B-SAMP-07 | A | DONE | 18 | M | semi | SHRINE 6240034 | 1" liner | 2025-12-17 | Z | 2025-11-21 | 150 | 10 | 130 |  | 250 | 440 |  |  |  | 26
2025-12-16 | 1042 | bth | B-SAMP-08 | A | DONE | 10 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-17 | Z | 2025-11-21 | 170 | 20 | 0 |  | 140 | 250 |  |  |  | 26
2025-12-16 | 1043 | bth | B-SAMP-09 | A | DONE | 9 | S/M | semi | SHRINE 6240034 | 1" liner | 2025-12-17 | Z | 2025-11-21 | 160 | 30 | 0 |  | 120 | 210 |  |  |  | 26
2025-12-17 | 1046 |  | B-SAMP-12 | A | DONE | 21 | M | ss | SHRINE 6240034 | 1" liner | 2025-12-17 | Z | 2025-11-21 | 230 | 0 | 50 |  | 120 | 510 |  |  |  | 26
2025-12-17 | 1048 |  | B-SAMP-14 | A | DONE | 17 | M | semi | SHRINE 6240034 | 1" liner | 2025-12-17 | Z | 2025-11-21 | 210 | 0 | 80 |  | 220 | 410 |  |  |  | 26
2025-12-18 | 1049 |  | L2-EA-1O | A | DONE | 3 | S |  | SHRINE 6240034 |  | 2025-12-22 | Z | 2025-12-03 | 40 | 0 | 0 |  | 0 | 70 |  |  |  | 19
2025-12-18 | 1051 |  | L2-SAMP-11 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2025-12-22 | Z | 2025-12-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 19
2025-12-19 | 68945 |  | 68945 | A | DONE | 4 | S |  | SPH SURGERY 6240039 |  | 2025-12-29 | Z | 2025-12-09 | 30 | 0 | 0 |  | 20 | 80 |  | Roof curb caps |  | 20
2025-12-15 | 3145r |  | 3145r | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-15 | Z | 2025-12-15 | 0 | 0 | 40 |  | 0 | 50 |  |  |  | 0
2025-12-17 | 519 |  | 75570 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2025-12-22 | Z | 2025-11-12 | 20 | 0 | 0 |  | 0 | 30 |  | 1st floor RA |  | 40
2025-12-18 | 521 | sp | 75571-77 | A | DONE | 17 | M |  | SWH MOB 6250015 | VD | 2025-12-22 | Z | 2025-11-12 | 70 | 360 | 0 |  | 0 | 410 |  | 1st floor RA |  | 40
2025-12-18 | 522 |  | 75578-79 | A | DONE | 25 | M |  | SWH MOB 6250015 | paint black | 2025-12-22 | Z | 2025-11-12 | 190 | 0 | 310 |  | 10 | 610 |  | RTU-2 1st floor RA |  | 40
2025-12-18 | 523 |  | 75580-82 | A | DONE | 16 | M |  | SWH MOB 6250015 | VD | 2025-12-22 | Z | 2025-11-12 | 240 | 0 | 110 |  | 0 | 400 |  | EF-3 1st floor EA |  | 40
2025-12-17 | 524 | sp | 75583-84 | A | DONE | 5 | S/M |  | SWH MOB 6250015 | VD's | 2025-12-22 | Z | 2025-11-12 | 20 | 100 | 0 |  | 0 | 120 |  | EF-3 1st floor EA |  | 40
2025-12-18 | 526 |  | 75585-87 | A | DONE | 12 | S/M |  | SWH MOB 6250015 |  | 2025-12-22 | Z | 2025-11-13 | 180 | 0 | 70 |  | 0 | 300 |  | EF-3 south |  | 39
2025-12-17 | 527 | sp | 75588 | A | DONE | 6 | S/M |  | SWH MOB 6250015 |  | 2025-12-22 | Z | 2025-11-13 | 20 | 110 | 0 |  | 0 | 130 |  | EF-3 south |  | 39
2025-12-18 | 528 |  | 75589-90 | A | DONE | 14 | S/M |  | SWH MOB 6250015 |  | 2025-12-22 | Z | 2025-11-13 | 130 | 0 | 140 |  | 0 | 350 |  | EF-2 1st floor EA |  | 39
2025-12-18 | 529 | sp | 75591 | A | DONE | 5 | S/M |  | SWH MOB 6250015 |  | 2025-12-22 | Z | 2025-11-13 | 30 | 90 | 0 |  | 0 | 110 |  | EF-2 1st floor EA |  | 39
2025-12-18 | 530 |  | 75592 | A | DONE | 7 | S/M |  | SWH MOB 6250015 |  | 2025-12-22 | Z | 2025-11-13 | 60 | 0 | 90 |  | 0 | 170 |  | EF-1 EA |  | 39
2025-12-17 | 76694 | sp | 76694 | A | DONE | 4 | S |  | SWH MOB 6250015 |  | 2025-12-22 | Z | 2025-12-15 | 10 | 90 | 0 |  | 0 | 90 |  | Spiral |  | 7
2025-12-16 | 69074 |  | 69074 | A | DONE | 2 | S |  | UW AVRL 6240038 |  | 2025-12-17 | Z | 2025-12-09 | 50 | 10 | 0 |  | 20 | 50 |  | 5th fl BSL-3 |  | 8
2025-12-18 | 69075 | w | 69075 | A | DONE | 2 | S | ss | UW AVRL 6240038 |  | 2025-12-22 | Z | 2025-12-17 | 20 | 0 | 0 |  | 0 | 50 |  | 5th floor |  | 5
2025-12-19 | 69076 | w | 69076 | A | DONE | 2 | S | ss | UW AVRL 6240038 |  | 2025-12-22 | Z | 2025-12-18 | 30 | 0 | 0 |  | 0 | 50 |  | 5th floor |  | 4
2025-12-19 | 69077 | w | 69077 | A | DONE | 2 |  | ss | UW AVRL 6240038 |  | 2025-12-23 | Z | 2025-12-18 | 20 | 0 | 0 |  | 0 | 40 |  | 5th floor |  | 5
2025-12-17 | 4839 | bth | LL-SAMP 6 | A | DONE | 75 | L |  | UW LEVY HALL 6230028 | 1" liner | 2025-12-23 | Z | 2025-12-08 | 480 | 90 | 490 |  | 840 | 1860 |  |  |  | 15
2025-12-15 | 53954 |  | 53954 | A | DONE | 9 | S/M |  | UW LEVY HALL 6230028 |  | 2025-12-16 | Z | 2025-12-10 | 90 | 0 | 0 |  | 0 | 220 |  | Plenums |  | 6
2025-12-15 | 76136 |  | 76136,002 | A | DONE | 20 | M |  | UW LEVY HALL 6230028 |  | 2025-12-16 | Z | 2025-12-15 | 160 | 0 | 110 |  | 0 | 500 |  |  |  | 1
2025-12-15 | 78312 |  | 78312-13 | A | DONE | 4 | S |  | UW LEVY HALL 6230028 |  | 2025-12-16 | Z | 2025-12-08 | 60 | 0 | 0 |  | 0 | 90 |  | L2-BCU-1 |  | 8
2025-12-17 | 78314 |  | 78314 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 | paint black | 2025-12-23 | Z | 2025-12-11 | 20 | 0 | 0 |  | 20 | 20 |  | L2 return drops |  | 12
2025-12-19 | 78317 |  | 78317 | A | DONE | 2 | S |  | UW LEVY HALL 6230028 |  | 2025-12-30 | Z | 2025-12-17 | 10 | 0 | 0 |  | 0 | 10 |  | L5 SAT 3-5-19 |  | 13
2025-12-17 | 78352 |  | 78352 | A | DONE | 5 | S/M |  | UW LEVY HALL 6230028 | 1" liner strips | 2025-12-17 | Z | 2025-12-17 | 0 | 0 | 0 |  | 320 | 120 |  |  |  | 0
2025-12-16 | 77360 |  | 77360 | A | DONE | 2 | S |  | UW STOUT 6250008 |  | 2025-12-16 | Z | 2025-12-15 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2025-12-16 | 2389 |  | 2389 | A | DONE | 2 | S |  | WAUNAKEE 6230013 | pipe shop | 2025-12-17 | Z | 2025-12-08 | 10 | 0 | 0 |  | 0 | 40 |  | Gen. rain collar |  | 9
2025-12-16 | 73821 |  | 73821 | A | DONE | 3 | S |  | WAUNAKEE 6230013 | 1" liner, flex | 2025-12-19 | Z | 2025-12-10 | 40 | 0 | 0 |  | 30 | 70 |  | PE Offices |  | 9
2025-12-18 | 75409 |  | 75409 | A | DONE | 2 | S | neal | WAUNAKEE 6230013 |  | 2025-12-19 | Z | 2025-12-18 | 10 | 0 | 0 |  | 0 | 30 |  | Saddle remakes |  | 1
2025-12-16 | 75410 |  | 75410 | A | DONE | 2 | S |  | WAUNAKEE 6230013 | 2" liner | 2025-12-17 | Z | 2025-12-08 | 10 | 0 | 0 |  | 10 | 30 |  | Gen. Exh curb extention |  | 9
2025-12-17 | 75412 |  | 75412-14,73825 | A | DONE | 7 | S/M | neal | WAUNAKEE 6230013 |  | 2025-12-19 | Z | 2025-12-15 | 100 | 0 | 0 |  | 0 | 170 |  |  |  | 4
2025-12-17 | 75415 | sp | 75415 | A | DONE | 2 | S | alum | WAUNAKEE 6230013 |  | 2025-12-19 | Z | 2025-12-17 | 10 | 40 | 0 |  | 0 | 20 |  | Dryer vent |  | 2
2025-12-17 | 75451 |  | 75451-52,83429 | A | DONE | 13 | S/M | ss | WAUNAKEE 6230013 |  | 2025-12-19 | Z | 2025-12-15 | 200 | 0 | 0 |  | 0 | 320 |  |  |  | 4
2025-12-18 | 82939 |  | 82939 | A | DONE | 5 | S/M |  | WAUNAKEE 6230013 |  | 2025-12-19 | Z | 2025-12-17 | 70 | 0 | 0 |  | 0 | 110 |  | 2nd C RA |  | 2
2025-12-17 | 106876 |  | 106876 | A | DONE | 2 | S |  | WHC 6250007 | pipe shop caps | 2025-12-17 | Z | 2025-12-17 | 10 | 0 | 0 |  | 0 | 30 |  | Pipe shop |  | 0
2025-12-15 | 77273 |  | 77273 | A | DONE | 2 | S |  | WIS HISTORY 6250007 |  | 2025-12-16 | Z | 2025-12-15 | 20 | 0 | 0 |  | 0 | 50 |  | Decking covers |  | 1
[6 empty] | 1348 | [13 empty] | 32100 | [5 empty] | 47% short
WEEK OF 12-22-2025
2025-12-22 | 74265 | bi | 74265 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2025-12-23 | Z | 2025-12-19 | 0 | 0 | 0 |  | 0 | 10 |  | Grille stiffener |  | 4
2025-12-22 | 58176 | sp | 58716-78 | A | DONE | 8 | S/M | alum | BROOM ST 6240033 |  | 2026-01-06 | Z | 2025-12-18 | 20 | 20 | 0 |  | 0 | 200 |  | Sleeves |  | 19
2025-12-23 | 79492 |  | 79492 | A | DONE | 4 | S |  | BROOM ST 6240033 |  | 2025-12-24 | Z | 2025-12-22 | 70 | 0 | 0 |  | 0 | 80 |  | X58 |  | 2
2025-12-23 | 2910 |  | M4.65 UNIT 232 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 70 | 80 | 0 |  | 0 | 180 |  |  |  | 69 |  | 2025-10-16
2025-12-23 | 2912 |  | M4.67 UNIT 234 | A | DONE | 18 | M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 390 | 0 | 40 |  | 0 | 450 |  |  |  | 69 |  | 2025-10-16
2025-12-23 | 2915 |  | M4.70 UNIT 237 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 260 | 0 | 30 |  | 0 | 290 |  |  |  | 69 |  | 2025-10-16
2025-12-23 | 2916 |  | M4.71 UNIT 238 | A | DONE | 12 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 270 | 0 | 0 |  | 0 | 280 |  |  |  | 69 |  | 2025-10-16
2025-12-23 | 2917 |  | M4.72 UNIT 239 | A | DONE | 11 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 240 | 0 | 40 |  | 0 | 260 |  |  |  | 69 |  | 2025-10-16
2025-12-23 | 2919 |  | M4.74 UNIT 241 | A | DONE | 9 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 210 | 0 | 0 |  | 0 | 220 |  |  |  | 69 |  | 2025-10-16
2025-12-23 | 58176 |  | 58176-78 | A | DONE | 8 | S/M | alum | BROOM ST. 6240033 |  | 2025-12-24 | Z | 2025-12-11 | 100 | 120 | 0 |  | 0 | 200 |  | Sleeves |  | 13
2025-12-23 | 79474a |  | 79474-75,79486 | A | DONE | 34 | M/L |  | BROOM ST. 6240033 |  | 2025-12-29 | Z | 2025-12-15 | 340 | 0 | 0 |  | 0 | 840 |  | OA kits |  | 14
2025-12-23 | 79487 |  | 79487 | A | DONE | 21 | M |  | BROOM ST. 6240033 |  | 2025-12-23 | Z | 2025-12-08 | 490 | 0 | 0 |  | 0 | 520 |  | East tower corridor D |  | 15
2025-12-22 | 79491 |  | 79491 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-12-24 | Z | 2025-12-18 | 30 | 0 | 80 |  | 0 | 120 |  | L6 East |  | 6
2025-12-22 | 74820 |  | 74820 | A | DONE | 2 | S |  | COLUMBUS HS 10065248 | 1" liner | 2025-12-29 | Z | 2025-12-18 | 10 | 0 | 0 |  | 10 | 20 |  | Cap |  | 11
2025-12-23 | 74070 | bth | 74070 | A | DONE | 4 | S |  | DELLSHIRE 6240017 |  | 2025-12-29 | Z | 2025-12-19 | 50 | 50 | 0 |  | 0 | 100 |  | 4th floor housekeeping |  | 10
2025-12-23 | 122325 |  | 122325 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-23 | Z | 2025-12-23 | 30 | 0 | 0 |  | 0 | 40 |  | Elbows |  | 0
2025-12-23 | 2222 |  | Z3-OA 22 | A | DONE | 10 | S/M |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-09-10 | 150 | 0 | 30 |  | 0 | 250 |  |  |  | 110 | 2025-10-23 | 2025-11-20
2025-12-23 | 3166 | bth | Z2-SAT-3-1-16 | A | DONE | 12 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-29 | Z | 2025-09-17 | 170 | 10 | 40 |  | 20 | 290 |  |  |  | 103 | 2025-11-13 | 2025-11-06
2025-12-23 | 4768 |  | ZP-RA 50 partial | A | DONE | 30 | M |  | DOC JDC 6240023 |  | 2025-12-18 | Z | 2025-12-09 | 350 | 0 | 60 |  | 0 | 750 |  |  |  | 9
2025-12-23 | 56094 |  | 56094 | A | DONE | 7 | S/M |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-12-22 | 30 | 0 | 90 |  | 0 | 170 |  | Misc |  | 7
2025-12-23 | 657 |  | Z1-OA 7 | A | DONE | 5 | S/M |  | DOC JDC 6240023 | bird s. , MOD | 2025-12-29 | Z | 2025-07-22 | 70 | 0 | 0 |  | 0 | 120 |  |  |  | 160 | 2025-10-23 | 2025-11-20
2025-12-23 | 660 |  | Z1-OA 10 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-07-22 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 160 | 2025-10-23 | 2025-11-20
2025-12-23 | 665 |  | Z1-EA 5 | A | DONE | 14 | S/M | pt.neal | DOC JDC 6240023 | MOD | 2025-12-29 | Z | 2025-07-22 | 130 | 0 | 160 |  | 0 | 350 |  |  |  | 160 | 2025-10-23
2025-12-23 | 667 | bth | Z1-EA 6 | A | DONE | 2 | S |  | DOC JDC 6240023 | MOD | 2025-12-29 | Z | 2025-07-22 | 20 | 10 | 20 |  | 0 | 40 |  |  |  | 160 | 2025-10-23
2025-12-23 | 671 |  | Z1-EA 10 | A | DONE | 7 | S/M | neal | DOC JDC 6240023 | VD | 2025-12-29 | Z | 2025-07-22 | 50 | 0 | 100 |  | 0 | 170 |  |  |  | 160 | 2025-10-23
2025-12-22 | 707 |  | Z2-EA 38 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-07-30 | 130 | 0 | 0 |  | 0 | 190 |  |  |  | 152 | 2025-09-04
2025-12-23 | 708 |  | Z2-EA 39 | A | DONE | 19 | M |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-07-30 | 190 | 0 | 140 |  | 0 | 470 |  |  |  | 152 | 2025-09-04 | 2025-11-20
2025-12-23 | 709 |  | Z2-EA 40 | A | DONE | 11 | S/M |  | DOC JDC 6240023 | VD's | 2025-12-29 | Z | 2025-07-30 | 70 | 0 | 140 |  | 0 | 270 |  |  |  | 152 | 2025-09-04 | 2025-11-20
2025-12-22 | 733 |  | Z1-TA 1 | A | DONE | 5 | S/M |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-07-30 | 80 | 0 | 0 |  | 70 | 110 |  |  |  | 152 | 2025-09-11 | 2025-09-02
2025-12-22 | 734 | sp | Z1-RA 1 | A | DONE | 6 | S/M |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-07-30 | 10 | 130 | 0 |  | 0 | 130 |  |  |  | 152 | 2025-09-11 | 2025-11-06
2025-12-22 | 74821 | w | 74821 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-19 | Z | 2025-12-19 | 20 | 0 | 0 |  | 10 | 50 |  | remake goose neck |  | 0
2025-12-22 | 779 | bth | Z1-SAT-3-1-1_2 | A | DONE | 8 | S/M |  | DOC JDC 6240023 | VD's | 2025-12-29 | Z | 2025-07-31 | 100 | 30 | 50 |  | 0 | 200 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-22 | 780 | bth | Z1-SAT-3-1-2 | A | DONE | 8 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-29 | Z | 2025-07-31 | 50 | 100 | 0 |  | 30 | 190 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-22 | 781 | bth | Z1-SAT-3-1-3 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-29 | Z | 2025-07-31 | 20 | 30 | 30 |  | 30 | 70 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-23 | 782 | bth | Z1-SAT-3-1-5 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | VD , 1" liner | 2025-12-29 | Z | 2025-07-31 | 70 | 50 | 0 |  | 20 | 130 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-23 | 783 | bth | Z1-SAT-3-1-6_1 | A | DONE | 6 | S/M |  | DOC JDC 6240023 | 1" liner | 2025-12-29 | Z | 2025-07-31 | 30 | 80 | 0 |  | 30 | 130 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-22 | 784 | bth | Z1-SAT-3-1-6_2 | A | DONE | 8 | S/M |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-07-31 | 100 | 20 | 30 |  | 0 | 190 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-23 | 794 | bth | Z1-SAT-3-1-19 | A | DONE | 3 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-29 | Z | 2025-07-31 | 40 | 30 | 0 |  | 20 | 70 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-23 | 795 |  | Z1-SAT-3-1-20 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-29 | Z | 2025-07-31 | 20 | 10 | 0 |  | 20 | 30 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-23 | 796 |  | Z1-SAT-3-1-21 | A | DONE | 2 | S |  | DOC JDC 6240023 | 1" liner | 2025-12-29 | Z | 2025-07-31 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 151 | 2025-09-18 | 2025-11-06
2025-12-22 | 84396 |  | 84396 | A | DONE | 20 | M |  | DOC JDC 6240023 |  | 2025-12-29 | Z | 2025-12-15 | 190 | 0 | 0 |  | 0 | 500 |  | HRU 1,2 |  | 14
2025-12-22 | 77062 | sp | 77062 | A | DONE | 2 | S |  | GRANT ELEM. 6250021 |  | 2025-12-29 | Z | 2025-12-18 | 20 | 0 | 0 |  | 0 | 30 |  | Supply Diff. |  | 11
2025-12-22 | 3943 | sp | FE-L1C-08 | A | DONE | 27 | M | neal | MONROE 6240018 | 601 caulk | 2025-12-31 | Z | 2025-11-20 | 70 | 310 | 0 |  | 0 | 660 |  |  |  | 41 | 2025-12-11
2025-12-23 | 83676 |  | 83676 | A | DONE | 5 | S/M |  | MONROE 6240018 |  | 2025-12-24 | Z | 2025-12-18 | 40 | 0 | 0 |  | 0 | 110 |  | E mech |  | 6
2025-12-23 | 83724 | w | 83724-26 | A | DONE | 8 |  | ss | MONROE 6240018 |  | 2025-12-24 | Z | 2025-12-18 | 120 | 0 | 0 |  | 0 | 190 |  | Dishwasher, kitchen hood |  | 6
2025-12-22 | 74654 |  | 74654 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-12-23 | Z | 2025-12-19 | 10 | 0 | 0 |  | 0 | 20 |  | Filter rack door |  | 4
2025-12-23 | 74656 |  | 746565 | A | DONE | 2 | S |  | PEWAUKEE HS 6240030 |  | 2025-12-29 | Z | 2025-12-22 | 20 | 0 | 0 |  | 0 | 30 |  | Kiln hood |  | 7
2025-12-22 | 100 |  | 100 | A | DONE | 2 | S | neal | PLACON 10066019 |  | 2025-12-22 | Z | 2025-12-22 | 10 | 0 | 0 |  | 0 | 20 |  | Flat stock |  | 0
2025-12-22 | 76198 | w | 76198 | A | DONE | 3 | S | ss | PROJECT DOVE 6240041 |  | 2025-12-24 | Z | 2025-12-18 | 20 | 0 | 0 |  | 0 | 60 |  | 700 Bottling |  | 6
2025-12-23 | 76229 |  | 76229-31 | A | DONE | 8 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-12-24 | Z | 2025-12-10 | 110 | 0 | 0 |  | 0 | 200 |  | SS Flashing |  | 14
2025-12-23 | 76233 |  | 76233-35,37-39 | A | DONE | 13 | S/M | ss | PROJECT DOVE 6240041 | paint black | 2025-12-24 | Z | 2025-12-11 | 160 | 0 | 0 |  | 40 | 320 |  | Flashing, angle, outs |  | 13
2025-12-23 | 76240 |  | 76240-41 | A | DONE | 7 | S/M | ss | PROJECT DOVE 6240041 |  | 2025-12-24 | Z | 2025-12-12 | 70 | 0 | 0 |  | 0 | 160 |  |  |  | 12
2025-12-22 | 76243 |  | 76243 | A | DONE | 5 | S/M |  | PROJECT DOVE 6240041 |  | 2025-12-24 | Z | 2025-12-16 | 50 | 0 | 0 |  | 0 | 110 |  |  |  | 8
2025-12-22 | 76244 | w | 76244 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-12-24 | Z | 2025-12-19 | 10 | 0 | 0 |  | 0 | 40 |  | 700 RAMP 4 |  | 5
2025-12-22 | 3815 | bth | LG-RA-01 | A | DONE | 52 | M/L |  | PROMEGA BTC 6250020 |  | 2025-12-22 | Z | 2025-12-10 | 470 | 10 | 330 |  | 0 | 1280 |  |  |  | 12
2025-12-23 | 69072r | w | 69072r | A | DONE | 2 | S | ss | UW AVRL 6240038 |  | 2025-12-29 | Z | 2025-12-22 | 10 | 0 | 0 |  | 0 | 30 |  | BSL-3 |  | 7
2025-12-23 | 69077r | w | 69077r | A | DONE | 2 | S | ss | UW AVRL 6240038 |  | 2025-12-23 | Z | 2025-12-22 | 10 | 0 | 0 |  | 0 | 20 |  | Remake |  | 1
2025-12-22 | 69078 | w | 69078-79 | A | DONE | 2 | S | ss | UW AVRL 6240038 |  | 2025-12-23 | Z | 2025-12-19 | 20 | 0 | 0 |  | 0 | 50 |  | 5th floor |  | 4
2025-12-22 | 69082 | w | 69082 | A | DONE | 2 | S | ss | UW AVRL 6240038 |  | 2025-12-24 | Z | 2025-12-22 | 10 | 0 | 0 |  | 0 | 10 |  | 5th floor |  | 2
2025-12-23 | 69083 |  | 69083 | A | DONE | 2 | S | alum | UW AVRL 6240038 |  | 2025-12-29 | Z | 2025-12-22 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2025-12-22 | 4840 | bth | LL-SAMP 7 | A | DONE | 48 | M/L |  | UW LEVY HALL 6230028 | 1" liner | 2025-12-23 | Z | 2025-12-08 | 400 | 50 | 240 |  | 550 | 1190 |  |  |  | 15
2025-12-23 | 83429r |  | 83429r | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2025-12-24 | Z | 2025-12-23 | 10 | 0 | 0 |  | 0 | 10 |  | remake |  | 1
2025-12-23 | 77274 |  | 77274 | A | DONE | 2 | S |  | WHC 6250007 |  | 2025-12-30 | Z | 2025-12-22 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 8
2025-12-24 | 2909 |  | M4.65 UNIT 231 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 70 | 80 | 0 |  | 0 | 180 |  |  |  | 69 |  | 2025-10-16
2025-12-24 | 2911 |  | M4.66 UNIT 233 | A | DONE | 10 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 210 | 0 | 0 |  | 0 | 230 |  |  |  | 69 |  | 2025-10-16
2025-12-24 | 2913 |  | M4.68 UNIT 235 | A | DONE | 4 | S |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 90 | 0 | 0 |  | 0 | 100 |  |  |  | 69 |  | 2025-10-16
2025-12-24 | 2914 |  | M4.69 UNIT 236 | A | DONE | 6 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 110 | 0 | 0 |  | 0 | 130 |  |  |  | 69 |  | 2025-10-16
2025-12-24 | 2920 |  | M4.75 UNIT 242 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2025-12-30 | Z | 2025-10-22 | 110 | 0 | 0 |  | 0 | 120 |  |  |  | 69
2025-12-24 | 74201 | bth | 74201,03-04,74068-69 | A | DONE | 26 | M | neal | DELLSHIRE 6240017 |  | 2025-12-29 | Z | 2025-12-18 | 310 | 160 | 60 |  | 0 | 640 |  | Outs |  | 11
2025-12-24 | 2221 |  | Z3-OA 21 | A | DONE | 11 | S/M |  | DOC JDC 6240023 | VD's | 2025-12-29 | Z | 2025-09-10 | 180 | 0 | 0 |  | 0 | 260 |  |  |  | 110 | 2025-10-23 | 2025-11-20
2025-12-24 | 672 |  | Z1-EA 11 | A | DONE | 2 | S | neal | DOC JDC 6240023 | bird s. , MOD | 2025-12-29 | Z | 2025-07-22 | 10 | 0 | 20 |  | 0 | 30 |  |  |  | 160 | 2025-10-23
2025-12-24 | 673 |  | Z1-EA 12 | A | DONE | 12 | S/M | neal | DOC JDC 6240023 | MOD | 2025-12-29 | Z | 2025-07-22 | 80 | 0 | 150 |  | 0 | 290 |  |  |  | 160 | 2025-10-23
2025-12-24 | 76052 | bth | 76052-53 | A | DONE | 4 | S |  | GRANT ELEM. 6250021 |  | 2025-12-23 | Z | 2025-12-17 | 40 | 60 | 0 |  | 0 | 100 |  | Library |  | 6
2025-12-24 | 53955 |  | 53955-57,001 | A | DONE | 37 | M/L |  | UW LEVY HALL 6230028 | paint black | 2025-12-30 | Z | 2025-12-22 | 330 | 0 | 0 |  | 80 | 920 |  | Gen room |  | 8
2025-12-24 | 69080 |  | 69080-81 | A | DONE | 8 | S/M |  | UW AVRL 6240038 |  | 2025-12-29 | Z | 2025-12-22 | 120 | 10 | 0 |  | 30 | 200 |  | RFI 594 |  | 7
[6 empty] | 699 | [13 empty] | 16550 | [5 empty] | 42% short
WEEK OF 12-29-2025
2025-12-30 | 300 | w | 300 | A | DONE | 13 | S/M | ss | 121 E WILSON 6230024 | 3" liner | 2026-01-05 | Z | 2025-12-17 | 130 | 0 | 0 |  | 70 | 310 |  |  |  | 19
2025-12-30 | 004 |  | 004-005 | A | DONE | 2 | S |  | ANTIGO 6250017 |  | 2026-01-05 | Z | 2025-12-23 | 20 | 0 | 0 |  | 0 | 40 |  | Hangers |  | 13
2025-12-31 | 82753 | sp | 82753-54 | A | DONE | 40 | M/L |  | ANTIGO 6250017 | oval rings | 2026-01-05 | Z | 2025-12-22 | 170 | 580 | 0 |  | 0 | 1000 |  | H2.1 SA |  | 14
2025-12-30 | 82755 |  | 82755 | A | DONE | 2 | S | neal | ANTIGO 6250017 | 1" liner, nosing | 2026-01-05 | Z | 2025-12-22 | 30 | 0 | 0 |  | 10 | 50 |  |  |  | 14
2025-12-30 | 82756 |  | 82756 | A | DONE | 3 | S |  | ANTIGO 6250017 |  | 2026-01-05 | Z | 2025-12-23 | 40 | 0 | 0 |  | 0 | 60 |  | RE-1A,1B |  | 13
2025-12-29 | 58180 | sp | 58180 | A | DONE | 2 | S |  | BROOM ST 6240033 |  | 2025-12-30 | Z | 2025-12-19 | 10 | 0 | 0 |  | 0 | 20 |  | Sleeves |  | 11
2025-12-30 | 1500 |  | UNIT 331 M4.65 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 70 | 80 | 0 |  | 0 | 180 |  |  |  | 25
2025-12-30 | 1501 |  | UNIT 332 M4.65 | A | DONE | 8 | S/M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 70 | 80 | 0 |  | 0 | 180 |  |  |  | 25
2025-12-31 | 1502 |  | UNIT 333 M4.66 | A | DONE | 10 | S/M |  | BROOM ST. 6240033 |  | 2026-01-06 | Z | 2025-12-12 | 210 | 0 | 0 |  | 0 | 230 |  |  |  | 25
2025-12-30 | 58185 |  | 58185 | A | DONE | 5 | S/M |  | BROOM ST. 6240033 |  | 2026-01-13 | Z | 2025-12-29 | 0 | 0 | 0 |  | 0 | 110 |  | S and D |  | 15
2025-12-29 | 74103 | sp | 74103 | A | DONE | 12 | S/M |  | DELLSHIRE 6240017 |  | 2025-12-30 | Z | 2025-12-24 | 20 | 320 | 0 |  | 0 | 300 |  | 4" spiral |  | 6
2026-01-02 | 74108 |  | 74108 | A | DONE | 14 | S/M |  | DELLSHIRE 6240017 |  | 2026-01-05 | Z | 2025-12-24 | 280 | 0 | 0 |  | 0 | 330 |  | Kitchen hood tie in |  | 12
2025-12-31 | 74109 | w | 74109 | A | DONE | 8 | S/M | bi | DELLSHIRE 6240017 |  | 2026-01-05 | Z | 2025-12-24 | 70 | 0 | 0 |  | 0 | 180 |  | KH1/2 final connections |  | 12
2025-12-30 | 75289r |  | 75289r | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2026-01-05 | Z | 2025-12-24 | 30 | 0 | 0 |  | 0 | 40 |  | offset remake |  | 12
2025-12-30 | 56097 |  | 56097 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-31 | Z | 2025-12-29 | 30 | 0 | 0 |  | 0 | 40 |  | Change |  | 2
2025-12-30 | 56098 |  | 56098 | A | DONE | 2 | S |  | DOC JDC 6240023 |  | 2025-12-31 | Z | 2025-12-30 | 20 | 0 | 0 |  | 0 | 20 |  | Sally port 1406 |  | 1
2025-12-31 | 56099 |  | 56099 | A | DONE | 5 | S/M |  | DOC JDC 6240023 |  | 2025-12-31 | Z | 2025-12-31 | 100 | 0 | 0 |  | 0 | 120 |  | Taps |  | 0
2025-12-31 | 662 |  | Z1-EA 2 | A | DONE | 2 | S | neal | DOC JDC 6240023 | bird s. , MOD | 2026-01-08 | Z | 2025-07-22 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 170 | 2025-10-23 | 2025-11-20
2025-12-31 | 663 |  | Z1-EA 3 | A | DONE | 11 | S/M | pt.neal | DOC JDC 6240023 | VD | 2026-01-08 | Z | 2025-07-22 | 130 | 0 | 90 |  | 0 | 260 |  |  |  | 170 | 2025-10-23 | 2025-11-20
2025-12-31 | 664 |  | Z1-EA 4 | A | DONE | 14 | S/M | pt.neal | DOC JDC 6240023 | VD , MOD | 2026-01-08 | Z | 2025-07-22 | 170 | 0 | 120 |  | 0 | 340 |  |  |  | 170 | 2025-10-23
2025-12-31 | 668 |  | Z1-EA 7 | A | DONE | 4 | S |  | DOC JDC 6240023 |  | 2026-01-08 | Z | 2025-07-22 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 170 | 2025-10-23
2025-12-30 | 678 | bth | Z1-EA 17 | A | DONE | 10 | S/M | pt.neal | DOC JDC 6240023 |  | 2025-12-31 | Z | 2025-07-22 | 90 | 20 | 80 |  | 0 | 240 |  |  |  | 162 | 2025-10-23 | 2025-09-02
2025-12-30 | 3938 | sp | FE-L1C-03 | A | DONE | 42 | M/L | neal | MONROE 6240018 | 601 caulk | 2026-01-07 | Z | 2025-11-20 | 120 | 240 | 0 |  | 0 | 1050 |  |  |  | 48 | 2025-12-11
2025-12-30 | 3941 | sp | FE-L1C-06 | A | DONE | 7 | S/M | neal | MONROE 6240018 | 601 caulk | 2026-01-07 | Z | 2025-11-20 | 30 | 80 | 0 |  | 0 | 170 |  |  |  | 48 | 2025-12-11
2025-12-30 | 3942 | sp | FE-L1C-07 | A | DONE | 14 | S/M | neal | MONROE 6240018 | 601 caulk | 2026-01-07 | Z | 2025-11-20 | 40 | 170 | 0 |  | 0 | 330 |  |  |  | 48 | 2025-12-11
2025-12-30 | 3946 | sp | FE-L1C-11 | A | DONE | 27 | M | neal | MONROE 6240018 | 601 caulk | 2026-01-07 | Z | 2025-11-20 | 80 | 130 | 0 |  | 0 | 670 |  |  |  | 48 | 2025-12-11
2025-12-30 | 83727 |  | 83727 | A | DONE | 2 | S |  | MONROE 6240018 | paint black | 2025-12-30 | Z | 2025-12-30 | 40 | 0 | 0 |  | 10 | 50 |  | Register boxes |  | 0
2025-12-29 | 95837x |  | 95837 | A | DONE | 4 | S |  | OAW 8250017 | pipe shop | 2025-12-29 | Z | 2025-12-29 | 20 | 0 | 0 |  | 0 | 90 |  |  |  | 0
2026-01-02 | 88750 |  | 88749-51 | A | DONE | 5 | S/M | neal | PECATONICA 6240005 |  | 2026-01-05 | Z | 2025-12-24 | 50 | 0 | 0 |  | 0 | 110 |  |  |  | 12
2025-12-29 | 76840 |  | 76840 | A | DONE | 12 | S/M |  | PEWAUKEE HS 6240030 |  | 2026-01-02 | Z | 2025-12-23 | 120 | 0 | 0 |  | 0 | 280 |  | OA gooseneck |  | 10
2025-12-29 | 76235r |  | 76235r | A | DONE | 2 | S |  | PROJECT DOVE 6240041 | flex | 2025-12-30 | Z | 2025-12-24 | 0 | 0 | 0 |  | 0 | 20 |  | flex remake |  | 6
2025-12-29 | 76245 |  | 76245-46 | A | DONE | 4 | S | ss | PROJECT DOVE 6240041 |  | 2025-12-30 | Z | 2025-12-23 | 50 | 0 | 0 |  | 0 | 90 |  | Angles |  | 7
2025-12-29 | 76247 | w | 76247 | A | DONE | 2 | S | ss | PROJECT DOVE 6240041 |  | 2025-12-30 | Z | 2025-12-24 | 20 | 0 | 0 |  | 0 | 50 |  | 700 |  | 6
2025-12-31 | 74067 | bth | 74067-69,74071 | A | DONE | 7 | S/M |  | QBE 4250054 |  | 2026-01-05 | Z | 2025-12-22 | 60 | 100 | 0 |  | 0 | 160 |  | VAV-321-324 |  | 14
2026-01-02 | 74072 | bth | 74072-75 | A | DONE | 6 | S/M |  | QBE 4250054 |  | 2026-01-05 | Z | 2025-12-22 | 50 | 90 | 0 |  | 0 | 140 |  | VAV-325-328 |  | 14
2026-01-02 | 74076 | bth | 74076-79 | A | DONE | 13 | S/M |  | QBE 4250054 |  | 2026-01-05 | Z | 2025-12-22 | 160 | 160 | 0 |  | 0 | 320 |  | VAV-318-329 |  | 14
2025-12-31 | 74080 | bth | 74080,74082-83 | A | DONE | 13 | S/M |  | QBE 4250054 |  | 2026-01-05 | Z | 2025-12-22 | 90 | 230 | 0 |  | 0 | 310 |  | VAV-316-317 |  | 14
2025-12-30 | 74100 |  | 74100-01 | A | DONE | 27 | M |  | QBE 4250054 | 1" liner | 2025-12-31 | Z | 2025-12-30 | 700 | 0 | 0 |  | 450 | 660 |  | Transfers |  | 1
2025-12-29 | 1362 |  | 75854 - 75855 | A | DONE | 49 | M/L | semi | RICHLAND CTR. 6250011 |  | 2026-01-02 | Z | 2025-09-24 | 130 | 0 | 700 |  | 0 | 1210 |  | Music wing main |  | 100 |  | 2025-09-02
2025-12-29 | 1363 |  | 75858 | A | DONE | 6 | S/M | semi | RICHLAND CTR. 6250011 |  | 2026-01-02 | Z | 2025-09-24 | 90 | 0 | 0 |  | 0 | 130 |  | Band Room |  | 100 |  | 2025-09-02
2025-12-29 | 1364 |  | 81085 - 81087 | A | DONE | 28 | M | semi | RICHLAND CTR. 6250011 |  | 2026-01-02 | Z | 2025-09-24 | 190 | 0 | 300 |  | 0 | 700 |  | Office RA |  | 100 |  | 2025-09-02
2025-12-29 | 1366 |  | 81090 - 81091 | A | DONE | 26 | M | semi | RICHLAND CTR. 6250011 |  | 2026-01-02 | Z | 2025-09-24 | 210 | 0 | 340 |  | 0 | 650 |  | Office SA |  | 100 |  | 2025-09-02
2025-12-29 | 1367 |  | 81092 - 81094 | A | DONE | 30 | M | semi | RICHLAND CTR. 6250011 |  | 2026-01-02 | Z | 2025-09-24 | 490 | 0 | 140 |  | 0 | 730 |  | VAV Duct Area B |  | 100 |  | 2025-09-02
2025-12-29 | 1368 |  | 81096 | A | DONE | 10 | S/M | semi | RICHLAND CTR. 6250011 |  | 2026-01-02 | Z | 2025-09-24 | 90 | 0 | 90 |  | 0 | 230 |  | VAV Duct Area B |  | 100
2025-12-30 | 1052 |  | L1-EA-01 | A | DONE | 4 | S |  | SHRINE 6240034 | CD | 2026-01-05 | Z | 2025-12-23 | 70 | 10 | 0 |  | 0 | 100 |  |  |  | 13
2025-12-30 | 1053 |  | L1-EA-02 | A | DONE | 6 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 80 | 0 | 20 |  | 0 | 130 |  |  |  | 13
2025-12-30 | 1054 |  | L1-EA-03 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 20 | 0 | 20 |  | 0 | 40 |  |  |  | 13
2025-12-30 | 1055 |  | L1-EA-04 | A | DONE | 6 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 110 | 0 | 0 |  | 0 | 150 |  |  |  | 13
2025-12-30 | 1056 |  | L1-EA-05 | A | DONE | 5 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 80 | 0 | 20 |  | 0 | 120 |  |  |  | 13
2025-12-31 | 1057 |  | L1-SALP-01 | A | DONE | 11 | S/M |  | SHRINE 6240034 | 1" liner | 2026-01-05 | Z | 2025-12-23 | 190 | 0 | 0 |  | 140 | 270 |  |  |  | 13
2026-01-02 | 1058 |  | L1-SALP-02 | A | DONE | 4 | S |  | SHRINE 6240034 | 1" liner | 2026-01-05 | Z | 2025-12-23 | 40 | 40 | 0 |  | 30 | 90 |  |  |  | 13
2025-12-31 | 1059 |  | L1-SALP-03 | A | DONE | 5 | S/M |  | SHRINE 6240034 | 1" liner | 2026-01-05 | Z | 2025-12-23 | 50 | 0 | 30 |  | 70 | 110 |  |  |  | 13
2025-12-30 | 1060 |  | L1-SALP-04 | A | DONE | 2 | S |  | SHRINE 6240034 | 1" liner | 2026-01-05 | Z | 2025-12-23 | 10 | 0 | 30 |  | 30 | 50 |  |  |  | 13
2026-01-02 | 1061 | bth | L1-SAMP-01 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 10 | 10 | 0 |  | 0 | 30 |  |  |  | 13
2026-01-02 | 1062 | bth | L1-SAMP-02 | A | DONE | 2 | S |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 10 | 10 | 0 |  | 0 | 30 |  |  |  | 13
2025-12-31 | 1063 |  | L1-SAMP-03 | A | DONE | 4 | S |  | SHRINE 6240034 | 1" liner, CD | 2026-01-05 | Z | 2025-12-23 | 50 | 0 | 0 |  | 50 | 80 |  |  |  | 13
2026-01-02 | 1064 |  | L1-RA-01 | A | DONE | 8 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 100 | 0 | 50 |  | 0 | 200 |  |  |  | 13
2026-01-02 | 1065 |  | L1-RA-02 | A | DONE | 9 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 120 | 0 | 40 |  | 0 | 210 |  |  |  | 13
2026-01-02 | 1067 |  | L1-RA-04 | A | DONE | 9 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 40 | 0 | 140 |  | 0 | 210 |  |  |  | 13
2026-01-02 | 1069 |  | L1-RA-06 | A | DONE | 26 | M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 160 | 0 | 250 |  | 0 | 640 |  |  |  | 13
2026-01-02 | 1072 |  | L1-RA-09 | A | DONE | 10 | S/M |  | SHRINE 6240034 |  | 2026-01-05 | Z | 2025-12-23 | 100 | 0 | 40 |  | 0 | 250 |  |  |  | 13
2025-12-30 | 68948 |  | 68948 | A | DONE | 2 | S |  | SPH 6240039 |  | 2026-01-05 | Z | 2025-12-19 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 17
2026-01-02 | 68949 |  | 68949 | A | DONE | 9 | S/M |  | SPH 6240039 | 1" liner | 2026-01-05 | Z | 2025-12-22 | 100 | 0 | 0 |  | 20 | 220 |  | Roof curb |  | 14
2025-12-30 | 68950 |  | 68950 | A | DONE | 2 | S |  | SPH 6240039 |  | 2026-01-05 | Z | 2025-12-23 | 20 | 0 | 0 |  | 0 | 30 |  | Grille boxes |  | 13
2026-01-02 | 532 | sp | 76655,76657,76659 | A | DONE | 12 | S/M |  | SWH MOB 6250015 | VD | 2026-01-05 | Z | 2025-11-18 | 50 | 260 | 0 |  | 0 | 280 |  | 1st floor Vav LPSA |  | 48
2025-12-30 | 533 |  | 76653 | A | DONE | 2 | S |  | SWH MOB 6250015 | 1/2" liner | 2026-01-05 | Z | 2025-11-18 | 40 | 0 | 0 |  | 0 | 50 |  | 1st floor Vav LPSA |  | 48
2025-12-30 | 534 |  | 76651-52,54,56,58 | A | DONE | 31 | M |  | SWH MOB 6250015 | VD | 2026-01-05 | Z | 2025-11-18 | 330 | 0 | 310 |  | 0 | 760 |  | 1st floor Vav LPSA |  | 48
2026-01-02 | 76660 |  | 76660-62,64,66,68 | A | DONE | 23 | M |  | SWH MOB 6250015 | VD | 2026-01-05 | Z | 2025-11-21 | 320 | 100 | 90 |  | 0 | 570 |  | 1st flr vav lpsa |  | 45
2026-01-02 | 76663 | sp | 76663,65,67 | A | DONE | 8 | S/M |  | SWH MOB 6250015 | VD | 2026-01-05 | Z | 2025-11-21 | 70 | 130 | 0 |  | 0 | 200 |  | 1st flr vav lpsa |  | 45
2025-12-31 | 76695 |  | 76695 | A | DONE | 7 | S/M |  | SWH MOB 6250015 | 1/2" liner | 2026-01-05 | Z | 2025-12-17 | 80 | 0 | 0 |  | 40 | 170 |  | RG-3 |  | 19
2025-12-30 | 76696 |  | 76696 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2026-01-05 | Z | 2025-12-22 | 10 | 0 | 0 |  | 0 | 20 |  | Rm 190 RA |  | 14
2025-12-31 | 76697 |  | 76697 | A | DONE | 2 | S |  | SWH MOB 6250015 |  | 2026-01-05 | Z | 2025-12-29 | 10 | 0 | 30 |  | 0 | 40 |  | EF-3 |  | 7
2025-12-30 | 77063 |  | 77063 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2026-01-05 | Z | 2025-12-24 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 12
2025-12-30 | 77064 | sp | 77064 | A | DONE | 2 | S |  | TOMAH HEALTH 6250006 |  | 2026-01-05 | Z | 2025-12-24 | 20 | 0 | 0 |  | 0 | 20 |  | Linear neck extentions |  | 12
2025-12-29 | 78315 |  | 78315-16 | A | DONE | 41 | M/L |  | UW LEVY HALL 6230028 |  | 2025-12-30 | Z | 2025-12-16 | 340 | 0 | 0 |  | 0 | 1010 |  |  |  | 14
2025-12-29 | 78353 |  | 78353 | A | DONE | 4 | S |  | UW LEVY HALL 6230028 | 1" liner | 2025-12-30 | Z | 2025-12-24 | 0 | 0 | 0 |  | 250 | 100 |  | Liner strips |  | 6
2025-12-30 | 75416 | sp | 75416 | A | DONE | 14 | S/M | neal | WAUNAKEE 6230013 |  | 2026-01-02 | Z | 2025-12-22 | 10 | 230 | 0 |  | 0 | 330 |  | DC runouts |  | 11
2025-12-29 | 75418 |  | 75418 | A | DONE | 2 | S |  | WAUNAKEE 6230013 |  | 2026-01-02 | Z | 2025-12-24 | 20 | 0 | 0 |  | 0 | 20 |  | Filter racks |  | 9
2025-12-31 | 74823 |  | 74823 | A | DONE | 2 | S |  | WHC 6250007 |  | 2025-12-31 | Z | 2025-12-31 | 10 | 0 | 0 |  | 0 | 20 |  | Pipe shop |  | 0
[6 empty] | 797 | [13 empty] | 18910

## Completed TO# List 2024
COMPLETED TO#'s | [10 empty] | SHEET SHOP - 2024
| TO#'S |  | SKETCH/SPOOL #'S | STATUS | DONE | SIZE |  | Metal | JOB NAME |  |  |  | DATE | PLASMA | SPIRAL | C.LINE | C.LINE | INSU | LBS.
COMPLETED | [6 empty] | EST. |  |  | SPECIAL | NEED | Priority | RCVD | SQ FT | SQ FT | SQ FT | STATUS | SQ FT
DATE | [6 empty] | SIZE | ETC. |  | NOTES | DATE | 0.5 | Pounds completed to date this week = | [5 empty] | 1874570 |  | Description | Semi / # | Lead Time | Original need date
WEEK OF 1-2-2024
2024-01-02 | 1703 | sp | 71890 - 71891 | A | DONE | 11 | S-M | neal | BLACKHAWK BTC 6230025 - spiral mates |  | 2024-01-02 | Z | 2023-12-19 | 50 | 220 | 0 |  | 0 | 320 |  |  |  | 14
2024-01-04 | 170 |  | 67870 | A | DONE | 2 | S |  | CODY STANDO 1000370 - Furnace |  | 2024-01-04 | Z | 2024-01-04 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2024-01-04 | 1125 | w | 56649 | A | DONE | 3 | S-M | ss | DANE CO. AIRPORT 6210011 - EF-27 |  | 2024-01-08 | Z | 2023-12-22 | 60 | 0 | 0 |  | 0 | 60 |  |  |  | 17
2024-01-04 | 1124 | w | 56647 | A | DONE | 2 | S-M | ss | DANE CO. AIRPORT 6210011 - EF-28 |  | 2024-01-08 | Z | 2023-12-22 | 60 | 0 | 0 |  | 0 | 60 |  |  |  | 17
2024-01-04 | 2330 |  | 58163 | A | DONE | 2 | S |  | DEWITT 6230021 - PUNCH LIST |  | 2024-01-05 | Z | 2024-01-04 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-01-05 | 168 | bth | 69365 | A | DONE | 3 | S |  | EVCO 10052975 |  | 2024-01-10 | Z | 2024-01-03 | 60 | 20 | 0 |  | 0 | 90 |  |  |  | 7
2024-01-02 | 1682 | bth | 72493 - 72494 | A | DONE | 9 | S-M | flex | EXACT BIOSAFE 6230005 - FCU-1 SA |  | 2024-01-04 | Z | 2023-12-22 | 40 | 130 | 50 | F | 0 | 260 |  |  |  | 13
2024-01-02 | 1680 |  | 42182 | A | DONE | 6 | S-M | alum | EXACT NEXUS 6210003 - Thaw Cooler |  | 2024-01-04 | Z | 2023-12-18 | 150 | 0 | 0 |  | 0 | 120 |  |  |  | 17
2024-01-03 | 1686 |  | 72495 | A | DONE | 2 | S |  | EXACT SCIENCE 2230044 - 1-EL |  | 2024-01-09 | Z | 2024-01-02 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 7
2024-01-04 | 1687 | sp | 72496 | A | DONE | 2 | S |  | EXACT SCIENCE 2230051 - EA |  | 2024-01-09 | Z | 2024-01-02 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-01-05 | 2664 |  | 57935 | A | DONE | 11 | S-M |  | HEALTH SERV. 6230004 - 1st Floor |  | 2024-01-09 | Z | 2023-12-27 | 260 | 0 | 0 |  | 180 | 340 |  |  |  | 13
2024-01-04 | 2666 |  | 42633 | A | DONE | 2 | S-M | neal | HEALTH SERV. 6230004 - Basement |  | 2024-01-09 | Z | 2023-12-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 13
2024-01-04 | 2667 |  | 42634 | A | DONE | 7 | S-M |  | HEALTH SERV. 6230004 - Mech Rm. |  | 2024-01-09 | Z | 2023-12-27 | 160 | 0 | 0 |  | 0 | 370 |  |  |  | 13
2024-01-04 | 2668 |  | 42635 | A | DONE | 2 | S-M |  | HEALTH SERV. 6230004 - Basement |  | 2024-01-09 | Z | 2023-12-27 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 13
2024-01-05 | 2669 |  | 68440 | A | DONE | 8 | S |  | HEALTH SERV. 6230004 - CB-21 |  | 2024-01-09 | Z | 2024-01-03 | 200 | 0 | 0 |  | 0 | 280 |  |  |  | 6
2024-01-05 | 167 | bth | 70205-08 | A | DONE | 39 | M | neal | JOHNSON HEALTH 4230080 - HP/VAV/RETURN |  | 2024-01-08 | Z | 2024-01-02 | 380 | 520 | 0 |  | 70 | 940 |  |  |  | 6
2024-01-04 | 166 | sp | 70259 | A | DONE | 3 | S |  | LAB CORP 10052661 - W182 EXH |  | 2024-01-09 | Z | 2024-01-02 | 20 | 50 | 0 |  | 0 | 50 |  |  |  | 7
2024-01-03 | 721 |  | 69459 | A | DONE | 2 | S |  | OLIV 6210030 - C-DOAS |  | 2024-01-03 | Z | 2024-01-02 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 1
2024-01-02 | 720 |  | 69458 | A | DONE | 2 | S |  | OLIV 6210030 - L1 |  | 2024-01-04 | Z | 2023-12-29 | 90 | 0 | 0 |  | 0 | 120 |  |  |  | 6
2024-01-03 | 3759 | bth | BSMT-A-SAMP-024 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-01-05 | Z | 2023-12-12 | 140 | 20 | 80 | F | 0 | 280 |  |  |  | 24
2024-01-03 | 3760 | bth | BSMT-A-SAMP-025 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-01-05 | Z | 2023-12-12 | 50 | 30 | 30 | F | 0 | 150 |  |  |  | 24
2024-01-02 | 3761 |  | BSMT-A-SAMP-026 | A | DONE | 16 | S-M |  | CDIS 6220028 |  | 2024-01-05 | Z | 2023-12-12 | 280 | 0 | 120 | F | 0 | 520 |  |  |  | 24
2024-01-03 | 3762 |  | BSMT-A-SALP-050 | A | DONE | 3 | S | pt.neal | CDIS 6220028 - paint 1" liner |  | 2024-01-05 | Z | 2023-12-12 | 60 | 0 | 0 |  | 30 | 70 |  |  |  | 24
2024-01-02 | 3763 |  | BSMT-A-SALP-051 | A | DONE | 5 | S | pt.neal | CDIS 6220028 - paint 1" liner |  | 2024-01-05 | Z | 2023-12-12 | 90 | 20 | 0 |  | 40 | 120 |  |  |  | 24
2024-01-03 | 3764 |  | BSMT-A-EAD-046 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-01-05 | Z | 2023-12-12 | 90 | 0 | 60 | F | 0 | 190 |  |  |  | 24
2024-01-03 | 3765 | bth | BSMT-A-EAD-047 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-01-05 | Z | 2023-12-12 | 90 | 20 | 0 |  | 0 | 150 |  |  |  | 24
2024-01-03 | 3766 |  | BSMT-A-EAD-048 | A | DONE | 6 | S | pt.neal | CDIS 6220028 - paint |  | 2024-01-05 | Z | 2023-12-12 | 40 | 50 | 50 | F | 20 | 160 |  |  |  | 24
2024-01-03 | 3767 |  | BSMT-A-EAD-049 | A | DONE | 6 | S | pt.neal | CDIS 6220028 - paint |  | 2024-01-05 | Z | 2023-12-12 | 70 | 30 | 30 | F | 20 | 150 |  |  |  | 24
2024-01-02 | 3882 | w | 61354 | A | DONE | 2 | S |  | CDIS 6220028 - Sleeves 1" FB |  | 2024-01-04 | Z | 2023-12-28 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 7
2024-01-03 | 1222 | w | 62919 - 62920 | A | DONE | 2 | S-M | ss | PROMEGA FEYNMAN 6220014 - Rood Drop |  | 2024-01-03 | Z | 2023-12-21 | 50 | 0 | 0 |  | 0 | 160 |  |  |  | 13
2024-01-04 | 635 |  | 70652 | A | DONE | 2 | S |  | RAMC 6230009 - Corr. L100 1" wrap |  | 2024-01-08 | Z | 2023-12-28 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 11
2024-01-04 | 636 |  | 70653 | A | DONE | 2 | S |  | RAMC 6230009 - Existing Corr. 1" wrap |  | 2024-01-08 | Z | 2023-12-28 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 11
2024-01-02 | 1193 |  | 71895 - 71896 | A | DONE | 20 | M | pt.pcd | ROCK CO. JAIL 6220018 - AHU-3 OA / RH-3 flex |  | 2024-01-04 | Z | 2023-12-27 | 500 | 0 | 0 |  | 0 | 1090 |  |  |  | 8
2024-01-02 | 1195 |  | 71899 - 71900 | A | DONE | 21 | M | pt.pcd | ROCK CO. JAIL 6220018 - AHU-1 OA / RH-1 flex |  | 2024-01-04 | Z | 2023-12-27 | 510 | 0 | 0 |  | 0 | 920 |  |  |  | 8
2024-01-02 | 1196 |  | 78753 | A | DONE | 12 | M | pt.pcd | ROCK CO. JAIL 6220018 - AHU-4 OA flex |  | 2024-01-04 | Z | 2023-12-27 | 230 | 0 | 70 | F | 0 | 500 |  |  |  | 8
2024-01-05 | 1199 | bth | 78757 | A | DONE | 4 | S | pt.alum | ROCK CO. JAIL 6220018 - Min. Chase |  | 2024-01-11 | Z | 2023-12-28 | 20 | 40 | 30 | F | 0 | 80 |  |  |  | 14
2024-01-05 | 2050 |  | 78758 | A | DONE | 6 | S |  | ROCK CO. JAIL 6220018 - EF-4J |  | 2024-01-11 | Z | 2023-12-28 | 140 | 0 | 0 |  | 0 | 160 |  |  |  | 14
2024-01-03 | 2051 |  | 72358 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Fleet Garage |  | 2024-01-11 | Z | 2023-12-28 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 14
2024-01-05 | 2052 |  | 72359 | A | DONE | 2 | S | flex | ROCK CO. JAIL 6220018 - FG vehicle EA |  | 2024-01-11 | Z | 2023-12-29 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 13
2024-01-04 | 2054 |  | 72362 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - B-weap. Cleaning |  | 2024-01-11 | Z | 2023-12-29 | 50 | 0 | 0 |  | 0 | 50 |  |  |  | 13
2024-01-04 | 2055 | sp | 72363 | A | DONE | 2 | S |  | ROCK CO JAIL 6220018 - FLEET GARAGE |  | 2024-01-11 | Z | 2024-01-02 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 9
2024-01-04 | 2712 |  | 73386 | A | DONE | 2 | S |  | UWL-HSC 6230018 - VAV 96 |  | 2024-01-08 | Z | 2024-01-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 5
2024-01-04 | 1510 |  | 68162 - 38164 | A | DONE | 7 | S-M |  | WAUSHARA CO. GOV. 6220010 - Basement |  | 2024-01-09 | Z | 2023-12-27 | 160 | 0 | 0 |  | 0 | 230 |  |  |  | 13
2024-01-03 | 864 | bth | 2C-SALP-1 | A | DONE | 10 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 140 | 90 | 0 |  | 0 | 290 |  |  |  | 23
2024-01-03 | 865 | bth | 2C-SALP-2 | A | DONE | 9 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 140 | 70 | 0 |  | 0 | 250 |  |  |  | 23
2024-01-03 | 866 | bth | 2C-SALP-3 | A | DONE | 8 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 100 | 50 | 50 | F | 0 | 230 |  |  |  | 23
2024-01-04 | 867 | bth | 2C-SALP-4 | A | DONE | 5 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 50 | 50 | 20 | F | 0 | 150 |  |  |  | 23
2024-01-03 | 868 | bth | 2C-SALP-5 | A | DONE | 12 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 140 | 90 | 50 | F | 0 | 330 |  |  |  | 23
2024-01-04 | 869 | bth | 2C-SALP-6 | A | DONE | 17 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 110 | 90 | 220 | F | 0 | 510 |  |  |  | 23
2024-01-03 | 870 | bth | 2C-SALP-7 | A | DONE | 8 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 90 | 50 | 50 | F | 0 | 220 |  |  |  | 23
2024-01-03 | 871 | bth | 2C-SALP-8 | A | DONE | 15 | S-M | pt.neal | WCSD HERITAGE 6220024 - flex |  | 2024-01-05 | Z | 2023-12-13 | 240 | 50 | 70 | F | 0 | 410 |  |  |  | 23
2024-01-03 | 872 | bth | 2C-SALP-9 | A | DONE | 10 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 160 | 40 | 50 | F | 0 | 290 |  |  |  | 23
2024-01-04 | 873 | bth | 2C-SALP-10 | A | DONE | 8 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 60 | 120 | 0 |  | 0 | 220 |  |  |  | 23
2024-01-03 | 874 | bth | 2C-SALP-11 | A | DONE | 19 | M | neal | WCSD HERITAGE 6220024 - flex |  | 2024-01-05 | Z | 2023-12-13 | 190 | 110 | 170 | F | 0 | 550 |  |  |  | 23
2024-01-04 | 875 | bth | 2C-SALP-12 | A | DONE | 15 | S-M | neal | WCSD HERITAGE 6220024 - flex |  | 2024-01-05 | Z | 2023-12-13 | 200 | 30 | 140 | F | 0 | 440 |  |  |  | 23
2024-01-03 | 876 | sp | 2C-SALP-13 | A | DONE | 10 | S |  | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 20 | 210 | 0 |  | 0 | 270 |  |  |  | 23
2024-01-04 | 877 | sp | 2C-SALP-14 | A | DONE | 2 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 23
2024-01-04 | 879 | bth | 2C-SALP-16 | A | DONE | 3 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 30 | 30 | 0 |  | 0 | 60 |  |  |  | 23
2024-01-04 | 880 |  | 2C-SALP-17 | A | DONE | 2 | S | neal | WCSD HERITAGE 6220024 - flex |  | 2024-01-05 | Z | 2023-12-13 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 23
2024-01-04 | 881 | sp | 2C-SALP-18 | A | DONE | 2 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 23
2024-01-04 | 883 |  | 2C-RA-1 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 100 | 0 | 0 |  | 70 | 120 |  |  |  | 22
2024-01-04 | 884 |  | 2C-RA-2 | A | DONE | 5 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 120 | 0 | 0 |  | 110 | 160 |  |  |  | 22
2024-01-04 | 885 |  | 2C-RA-3 | A | DONE | 8 | S-M | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 140 | 0 | 40 | F | 170 | 250 |  |  |  | 22
2024-01-04 | 886 |  | 2C-RA-4 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 90 | 0 | 0 |  | 100 | 140 |  |  |  | 22
2024-01-04 | 887 | bth | 2C-RA-5 | A | DONE | 3 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 50 | 20 | 0 |  | 20 | 80 |  |  |  | 22
2024-01-04 | 888 |  | 2C-RA-6 | A | DONE | 7 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 130 | 0 | 40 | F | 160 | 190 |  |  |  | 22
2024-01-04 | 889 |  | 2C-RA-7 | A | DONE | 8 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 140 | 0 | 40 | F | 120 | 210 |  |  |  | 22
2024-01-04 | 890 |  | 2C-RA-8 | A | DONE | 2 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 50 | 0 | 0 |  | 50 | 90 |  |  |  | 22
2024-01-04 | 891 |  | 2C-RA-9 | A | DONE | 3 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 70 | 0 | 0 |  | 90 | 120 |  |  |  | 22
2024-01-04 | 892 |  | 2C-RA-10 | A | DONE | 2 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 22
2024-01-04 | 893 |  | 2C-RA-11 | A | DONE | 6 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 130 | 0 | 0 |  | 80 | 160 |  |  |  | 22
2024-01-04 | 894 |  | 2C-RA-12 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 90 | 0 | 0 |  | 50 | 130 |  |  |  | 22
2024-01-04 | 895 | bth | 2C-RA-13 | A | DONE | 2 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 20 | 20 | 0 |  | 20 | 40 |  |  |  | 22
2024-01-04 | 896 | bth | 2C-RA-14 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 30 | 60 | 0 |  | 20 | 120 |  |  |  | 22
2024-01-04 | 897 | bth | 2C-RA-15 | A | DONE | 3 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 40 | 20 | 0 |  | 30 | 50 |  |  |  | 22
2024-01-04 | 898 | bth | 2C-RA-16 | A | DONE | 3 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 40 | 20 | 0 |  | 20 | 70 |  |  |  | 22
2024-01-02 | 1068 | sp | 1A-EA-2 | A | DONE | 8 | S |  | WCSD HERITAGE 6220024 |  | 2023-12-29 | Z | 2023-11-29 | 30 | 150 | 0 |  | 0 | 210 |  |  |  | 30
2024-01-03 | 1078 | sp | 1A-OA-1 | A | DONE | 10 | S-M |  | WCSD HERITAGE 6220024 |  | 2023-12-29 | Z | 2023-11-30 | 40 | 190 | 0 |  | 0 | 670 |  |  |  | 29
2024-01-03 | 1081 | bth | 1A-OA-4 | A | DONE | 16 | S-M |  | WCSD HERITAGE 6220024 |  | 2023-12-29 | Z | 2023-11-30 | 90 | 90 | 210 | F | 0 | 480 |  |  |  | 29
2024-01-03 | 1082 | bth | 1A-OA-5 | A | DONE | 13 | S-M | neal | WCSD HERITAGE 6220024 |  | 2023-12-29 | Z | 2023-11-30 | 140 | 140 | 40 | F | 0 | 410 |  |  |  | 29
2024-01-02 | 1086 | bth | 1A-OA-9 | A | DONE | 16 | S-M | pt.neal | WCSD HERITAGE 6220024 |  | 2023-12-29 | Z | 2023-11-30 | 150 | 40 | 210 | F | 0 | 500 |  |  |  | 29
2024-01-04 | 1750 |  | 2C-RA-18 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 90 | 0 | 0 |  | 80 | 130 |  |  |  | 22
2024-01-03 | 1756 |  | 34148 | A | DONE | 2 | S | pt.neal | WCSD HERITAGE 6220024 - 1-E EA |  | 2024-01-05 | Z | 2023-12-29 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-01-02 | 1757 |  | 34149 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - 1st Floor area C EA |  | 2024-01-05 | Z | 2023-12-29 | 40 | 0 | 0 |  | 0 | 70 |  |  |  | 7
2024-01-05 | 1784 |  | 69151 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - 2C-OA NORTH |  | 2024-01-12 | Z | 2024-01-04 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 8
[6 empty] | 564 | [13 empty] | 17340 |  |  |  | 6810 | 39.27%
WEEK OF 1-8-2024
2024-01-09 | 1705 | sp | 6230025 | A | DONE | 2 | S |  | BLACKHAWK 6230025 |  | 2024-01-11 | Z | 2024-01-05 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 6
2024-01-11 | 4649 |  | 73198 | A | DONE | 2 | S |  | CBOC 6220026 - Misc |  | 2024-01-15 | Z | 2024-01-11 | 20 | 20 | 0 |  | 20 | 30 |  |  |  | 4
2024-01-09 | 3228 | pt | SC-EAD-001 | A | DONE | 10 | S-M |  | CDIS 6220028 - DROPS partial |  | 2024-01-12 | Z | 2024-01-05 | 0 | 0 | 250 | F | 0 | 560 |  |  |  | 7
2024-01-08 | 3230 | pt | SC-RAD-001 | A | DONE | 8 | S-M |  | CDIS 6220028 - DROPS partial |  | 2024-01-12 | Z | 2024-01-05 | 60 | 0 | 120 |  | 0 | 350 |  |  |  | 7
2024-01-09 | 3768 | bth | BSMT-A-SALP-057 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 180 | 70 | 0 | F | 40 | 240 |  |  |  | 30
2024-01-09 | 3769 | bth | BSMT-A-SALP-060 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 50 | 50 | 60 | F | 0 | 170 |  |  |  | 30
2024-01-09 | 3770 | bth | BSMT-A-SAMP-027 | A | DONE | 21 | S-M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 170 | 50 | 300 | F | 0 | 720 |  |  |  | 30
2024-01-10 | 3771 |  | BSMT-A-RAD-002 | A | DONE | 51 | M |  | CDIS 6220028 - 1" DW |  | 2024-01-12 | Z | 2023-12-13 | 740 | 0 | 520 | F | 1060 | 1730 |  |  |  | 30
2024-01-10 | 3772 |  | BSMT-A-RAD-003 | A | DONE | 49 | M |  | CDIS 6220028 - 1" DW |  | 2024-01-12 | Z | 2023-12-13 | 630 | 0 | 150 | F | 440 | 1130 |  |  |  | 30
2024-01-09 | 3773 |  | BSMT-A-RAD-004 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 190 | 0 | 100 | F | 0 | 520 |  |  |  | 30
2024-01-10 | 3774 |  | BSMT-A-EAD-027 | A | DONE | 38 | M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 400 | 0 | 530 | F | 0 | 1570 |  |  |  | 30
2024-01-10 | 3775 |  | BSMT-A-EAD-030 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 140 | 20 | 20 | F | 0 | 210 |  |  |  | 30
2024-01-10 | 3776 |  | BSMT-A-EAD-031 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 240 | 0 | 40 | F | 0 | 330 |  |  |  | 30
2024-01-10 | 3777 |  | BSMT-A-EAD-033 | A | DONE | 22 | M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 360 | 0 | 190 | F | 0 | 910 |  |  |  | 30
2024-01-10 | 3778 | bth | BSMT-A-EAD-034 | A | DONE | 9 | S |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 40 | 80 | 120 | F | 0 | 280 |  |  |  | 30
2024-01-10 | 3779 |  | BSMT-A-EAD-035 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 150 | 0 | 50 | F | 0 | 230 |  |  |  | 30
2024-01-10 | 3780 | bth | BSMT-A-EAD-036 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 10 | 10 | 70 | F | 0 | 100 |  |  |  | 30
2024-01-10 | 3781 | bth | BSMT-A-EAD-037 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 30 | 20 | 50 | F | 0 | 100 |  |  |  | 30
2024-01-10 | 3782 | bth | BSMT-A-EAD-038 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 20 | 20 | 70 | F | 0 | 120 |  |  |  | 30
2024-01-10 | 3783 | bth | BSMT-A-EAD-039 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 40 | 10 | 30 | F | 0 | 100 |  |  |  | 30
2024-01-10 | 3784 |  | BSMT-A-EAD-040 | A | DONE | 9 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-01-12 | Z | 2023-12-13 | 140 | 0 | 70 | F | 10 | 300 |  |  |  | 30
2024-01-10 | 3785 |  | BSMT-A-EAD-042 | A | DONE | 8 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-01-12 | Z | 2023-12-13 | 110 | 0 | 80 | F | 10 | 220 |  |  |  | 30
2024-01-10 | 3786 | bth | BSMT-A-EAD-043 | A | DONE | 17 | S-M |  | CDIS 6220028 - 1" DW , 1" liner |  | 2024-01-12 | Z | 2023-12-13 | 110 | 220 | 0 |  | 110 | 340 |  |  |  | 30
2024-01-11 | 3787 | sp | BSMT-A-EAD-044 | A | DONE | 9 | S-M |  | CDIS 6220028 - 1" DW |  | 2024-01-12 | Z | 2023-12-13 | 40 | 0 | 130 | F | 40 | 160 |  |  |  | 30
2024-01-10 | 3788 | bth | BSMT-A-EAD-045 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-01-12 | Z | 2023-12-13 | 70 | 0 | 90 | F | 0 | 220 |  |  |  | 30
2024-01-08 | 3884 | w | 61406-08 | A | DONE | 5 | S |  | CDIS 6220028 - SLEEVES |  | 2024-01-17 | Z | 2024-01-03 | 110 | 0 | 0 |  | 0 | 250 |  |  |  | 14
2024-01-09 | 1126 |  | 56551 | A | DONE | 2 | S-M |  | DANE CO. AIRPORT 6210011 - 5K-157 |  | 2024-01-10 | Z | 2024-01-08 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 2
2024-01-09 | 2331 | sp | 58164 | A | DONE | 3 | S |  | DEWITT LAW 6230021 - VAV Rework |  | 2024-01-12 | Z | 2024-01-09 | 20 | 40 | 0 |  | 0 | 40 |  |  |  | 3
2024-01-10 | 2332 |  | 58166 | A | DONE | 2 | S |  | DEWITT LAW 6230021 - VAV Rework |  | 2024-01-12 | Z | 2024-01-09 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-01-08 | 1554 |  | 62410-13 | A | DONE | 14 | S-M |  | EMBASSY SUITES 6220012 - 1st FL-Lobby |  | 2024-01-09 | Z | 2024-01-03 | 250 | 30 | 70 | F | 0 | 400 |  |  |  | 6
2024-01-10 | 1688 | sp | 62508-11 | A | DONE | 13 | S-M |  | EXACT BIO 6230005 - Misc-EF |  | 2024-01-16 | Z | 2024-01-04 | 60 | 260 | 0 |  | 0 | 370 |  |  |  | 12
2024-01-08 | 2665 | bth | 57936 | A | DONE | 5 | S-M | flex | HEALTH SERV. 6230004 - Roof |  | 2024-01-09 | Z | 2023-12-27 | 80 | 30 | 0 |  | 0 | 120 |  |  |  | 13
2024-01-09 | 2670 |  | 68441-42 | A | DONE | 17 | S-M | pt neal | HEALTH SERV. 6230004 - EAST/WEST CHASE |  | 2024-01-16 | Z | 2024-01-03 | 430 | 0 | 0 |  | 0 | 650 |  |  |  | 13
2024-01-08 | 2671 |  | 68443 | A | DONE | 3 | S | neal | HEALTH SERV. 6230004 - TIE INS |  | 2024-01-16 | Z | 2024-01-03 | 70 | 0 | 0 |  | 0 | 90 |  |  |  | 13
2024-01-08 | 2672 |  | 68444 | A | DONE | 2 | S |  | HEALTH SERV. 6230004 - MISC OUTS |  | 2024-01-16 | Z | 2024-01-03 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 13
2024-01-08 | 2673 |  | 72149 | A | DONE | 8 | S |  | HEALTH SERV. 6230004 - MECH B33 |  | 2024-01-16 | Z | 2024-01-03 | 200 | 0 | 0 |  | 0 | 270 |  |  |  | 13
2024-01-08 | 2674 |  | 68445 | A | DONE | 5 | S |  | HEALTH SERV. 6230004 - AHU-6-1-REL |  | 2024-01-09 | Z | 2024-01-04 | 110 | 0 | 0 |  | 0 | 160 |  |  |  | 5
2024-01-09 | 2675 |  | 68446-47 | A | DONE | 9 | S |  | HEALTH SERV. 6230004 - AHU-6-1/6-3 |  | 2024-01-16 | Z | 2024-01-04 | 210 | 0 | 0 |  | 0 | 320 |  |  |  | 12
2024-01-08 | 2676 |  | 42636 | A | DONE | 2 | S |  | HEALTH SERV. 6230004 - Basement |  | 2024-01-09 | Z | 2024-01-08 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-01-11 | 2679 |  | 68450 | A | DONE | 5 | S-M |  | HEALTH SERV. 6230004 - B3-MECH |  | 2024-01-16 | Z | 2024-01-09 | 110 | 0 | 0 |  | 0 | 230 |  |  |  | 7
2024-01-09 | 764 |  | 68525 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 - Flashing |  | 2024-01-23 | Z | 2024-01-08 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 15
2024-01-08 | 1929 |  | 67402 | A | DONE | 2 | S-M | exp. m | MENDOTA FOODS 6220027 - Fan guard paint |  | 2024-01-11 | Z | 2023-12-26 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 16
2024-01-08 | 1931 |  | 67406-08 | A | DONE | 7 | S-M |  | MENDOTA FOODS 6220027 - LOUVER TIE IN |  | 2024-01-11 | Z | 2024-01-03 | 180 | 0 | 0 |  | 0 | 240 |  |  |  | 8
2024-01-08 | 1932 |  | 67411-12 | A | DONE | 11 | S |  | MENDOTA FOOD 6220027 - TIE INS 1"liner |  | 2024-01-11 | Z | 2024-01-03 | 170 | 0 | 0 |  | 90 | 160 |  |  |  | 8
2024-01-08 | 1933 |  | 67413 | A | DONE | 3 | S |  | MENDOTA FOOD 6220027 - TG-2 Restroom 1"liner |  | 2024-01-11 | Z | 2024-01-04 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 7
2024-01-11 | 1934 |  | 67414 | A | DONE | 6 | S |  | MENDOTA FOOD 6220027 - 1st Floor |  | 2024-01-18 | Z | 2024-01-09 | 60 | 0 | 70 | F | 0 | 140 |  |  |  | 9
2024-01-08 | 172 | sp | 70263 | A | DONE | 9 | S |  | MIDDLETON CLINIC 4230086 - FURNACE |  | 2024-01-10 | Z | 2024-01-04 | 110 | 130 | 0 |  | 0 | 220 |  |  |  | 6
2024-01-08 | 173 |  | 70264 | A | DONE | 3 | S |  | MIDDLETON CLINIC 4230086 - PATCH |  | 2024-01-10 | Z | 2024-01-04 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 6
2024-01-09 | 722 | bth | 61115-17 | A | DONE | 2 | S-M |  | OLIV 6210030 - 1st FL-AMEN-Misc |  | 2024-01-11 | Z | 2024-01-05 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 6
2024-01-09 | 723 |  | 69460 | A | DONE | 2 | S |  | OLIV 6210030 - L 10 MISC |  | 2024-01-11 | Z | 2024-01-09 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 2
2024-01-10 | 724 |  | 69461 | F | DONE | 2 | S |  | OLIV 6210030 - Unit 1022 |  | 2024-01-11 | Z | 2024-01-10 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-01-11 | 1617 | sp | 66901 | A | DONE | 5 | S |  | PROMEGA CMC 6230019 - Hood tie in |  | 2024-01-12 | Z | 2024-01-10 | 30 | 90 | 0 |  | 0 | 110 |  |  |  | 2
2024-01-08 | 1226 | bth | 56210 - 56212 | A | DONE | 9 | S-M |  | PROMEGA FEYNMAN 6220014 - VVS-3-37 / RAMP 4 |  | 2024-01-10 | Z | 2023-12-29 | 150 | 20 | 40 | F | 0 | 280 |  |  |  | 12
2024-01-11 | 1227 |  | 62651,55-56 | A | DONE | 13 | S-M |  | PROMEGA FEYNMAN 6220014 - 2ND FLOOR |  | 2024-01-17 | Z | 2024-01-05 | 240 | 0 | 70 | F | 0 | 490 |  |  |  | 12
2024-01-11 | 1228 | bth | 62652-54 | A | DONE | 9 | S-M | ss/pcd | PROMEGA FEYNMAN 6220014 - 2ND FLOOR |  | 2024-01-17 | Z | 2024-01-05 | 90 | 70 | 50 | F | 0 | 260 |  |  |  | 12
2024-01-11 | 1229 | sp | 62657 | A | DONE | 3 | S | ss | PROMEGA FEYNMAN 6220014 - EF 14-2 |  | 2024-01-17 | Z | 2024-01-05 | 40 | 20 | 0 |  | 0 | 50 |  |  |  | 12
2024-01-11 | 1230 | sp | 62658 | A | DONE | 3 | S | pcd | PROMEGA FEYNMAN 6220014 - EA |  | 2024-01-17 | Z | 2024-01-10 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 7
2024-01-08 | 2053 | sp | 72360 - 72361 | A | DONE | 9 | M |  | ROCK CO. JAIL 6220018 - FG vehicle EA |  | 2024-01-11 | Z | 2023-12-29 | 60 | 150 | 0 |  | 0 | 250 |  |  |  | 13
2024-01-11 | 2059 | bth | 78805 - 78806 | A | DONE | 9 | S-M |  | ROCK CO. JAIL 6220018 - Kitchen Remodel 1" liner |  | 2024-01-18 | Z | 2024-01-08 | 40 | 170 | 0 |  | 20 | 210 |  |  |  | 10
2024-01-09 | 2056 |  | 78801 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - OUTS |  | 2024-01-11 | Z | 2024-01-05 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 6
2024-01-11 | 169 | sp | 70262 | A | DONE | 3 | S |  | THERMO FISHER 10053022 - 2303 EXH |  | 2024-01-17 | Z | 2024-01-03 | 20 | 60 | 0 |  | 0 | 70 |  |  |  | 14
2024-01-08 | 171 | sp | 23906 | A | DONE | 2 | S |  | UW-CHEMISTRY 6180020 - CB 1510 |  | 2024-01-11 | Z | 2024-01-04 | 10 | 30 | 0 |  | 0 | 40 |  |  |  | 7
2024-01-08 | 2713 |  | 73387 | A | DONE | 2 | S |  | UWL-HSC 6230018 - L5 |  | 2024-01-16 | Z | 2024-01-04 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 12
2024-01-09 | 2714 |  | 73388 | A | DONE | 2 | S |  | UWL-HSC 6230018 - MISC RD EC's |  | 2024-01-16 | Z | 2024-01-05 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 11
2024-01-11 | 2715 |  | 73389 | A | DONE | 2 | S |  | UWL-HSC 6230018 - L4 |  | 2024-01-16 | Z | 2024-01-11 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 5
2024-01-10 | 580 | sp | 70563 | A | DONE | 2 | S | alum | UW-MITCHELL HALL 6220009 |  | 2024-01-10 | Z | 2024-01-10 | 20 | 30 | 0 |  | 0 | 30 |  |  |  | 0
2024-01-09 | 2768 |  | 72657 | A | DONE | 8 | S-M | neal | UW-VET MED 6210014 - 2nd Floor D |  | 2024-01-15 | Z | 2023-12-28 | 190 | 0 | 0 |  | 0 | 270 |  |  |  | 18
2024-01-08 | 878 | bth | 2C-SALP-15 | A | DONE | 2 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-05 | Z | 2023-12-13 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 23
2024-01-08 | 899 |  | 2C-RA-17 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-01-05 | Z | 2023-12-14 | 100 | 0 | 0 |  | 70 | 120 |  |  |  | 22
2024-01-08 | 1752 |  | 2C-DOAS 2-EA3 | A | DONE | 29 | M-L | pt.neal | WCSD HERITAGE 6220024 |  | 2024-01-12 | Z | 2023-12-27 | 500 | 0 | 210 | F | 0 | 1290 |  |  |  | 16
2024-01-08 | 1753 |  | 2C-DOAS 2-OA1 | A | DONE | 63 | L | pt.neal | WCSD HERITAGE 6220024 |  | 2024-01-12 | Z | 2023-12-27 | 1080 | 0 | 490 | F | 0 | 3270 |  |  |  | 16
2024-01-11 | 1754 |  | 2C-DOAS 1-EA-4 | A | DONE | 35 | M-L |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2023-12-27 | 560 | 0 | 330 | F | 0 | 1760 |  |  |  | 22
2024-01-11 | 1755 |  | 2C-DOAS 1-OA-2 | A | DONE | 51 | L |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2023-12-27 | 740 | 0 | 540 | F | 0 | 2830 |  |  |  | 22
2024-01-11 | 1785 |  | 67960 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - OA OUTS |  | 2024-01-18 | Z | 2024-01-05 | 30 | 0 | 0 |  | 0 | 80 |  |  |  | 13
2024-01-08 | 1786 |  | 70562 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - Couplings |  | 2024-01-08 | Z | 2024-01-08 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 0
2024-01-11 | 1790 | bth | 2D-EA-4 | A | DONE | 15 | S-M |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 140 | 40 | 180 | F | 0 | 430 |  |  |  | 9
2024-01-11 | 1791 | bth | 2D-EA-5 | A | DONE | 7 | S |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 30 | 60 | 70 | F | 0 | 200 |  |  |  | 9
2024-01-11 | 1794 |  | 2D-OA-3 | A | DONE | 8 | S |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 130 | 0 | 70 | F | 0 | 250 |  |  |  | 9
[6 empty] | 778 | [13 empty] | 27360 |  |  |  | 7670 | 28.03%
WEEK OF 1-15-2024
2024-01-16 | 3792 |  | BSMT-A-SALP-055 | A | DONE | 5 | S |  | CDIS 6220028 - 1" liner |  | 2024-01-19 | Z | 2023-12-18 | 120 | 0 | 0 |  | 70 | 140 |  |  |  | 32
2024-01-17 | 3793 | bth | BSMT-A-SALP-056 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 70 | 80 | 30 | F | 0 | 180 |  |  |  | 32
2024-01-17 | 3794 | bth | BSMT-A-SALP-058 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 70 | 30 | 70 | F | 0 | 180 |  |  |  | 32
2024-01-17 | 3795 | bth | BSMT-A-SALP-059 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 30 | 50 | 90 | F | 0 | 180 |  |  |  | 32
2024-01-17 | 3796 |  | BSMT-A-SALP-066 | A | DONE | 3 | S |  | CDIS 6220028 - 1" liner |  | 2024-01-19 | Z | 2023-12-18 | 30 | 0 | 30 | F | 30 | 60 |  |  |  | 32
2024-01-17 | 3797 | bth | BSMT-A-SALP-067 | A | DONE | 9 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-01-19 | Z | 2023-12-18 | 60 | 150 | 0 |  | 30 | 220 |  |  |  | 32
2024-01-17 | 3798 |  | BSMT-A-SAMP-028 | A | DONE | 36 | M |  | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 440 | 0 | 460 | F | 0 | 1590 |  |  |  | 32
2024-01-17 | 3799 |  | BSMT-A-SAMP-029 | A | DONE | 32 | M |  | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 280 | 0 | 510 | F | 0 | 1320 |  |  |  | 32
2024-01-17 | 3850 |  | BSMT-A-SAMP-036 | A | DONE | 20 | S-M |  | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 310 | 20 | 160 | F | 0 | 860 |  |  |  | 32
2024-01-18 | 3851 | bth | BSMT-A-SAMP-037 | A | DONE | 27 | S-M |  | CDIS 6220028 - 1" DW |  | 2024-01-19 | Z | 2023-12-18 | 330 | 30 | 310 | F | 130 | 900 |  |  |  | 32
2024-01-17 | 3852 | bth | BSMT-A-SAMP-038 | A | DONE | 14 | S |  | CDIS 6220028 - 1" DW |  | 2024-01-19 | Z | 2023-12-18 | 90 | 30 | 210 | F | 80 | 450 |  |  |  | 32
2024-01-17 | 3853 |  | BSMT-A-SAMP-043 | A | DONE | 24 | S-M |  | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 220 | 0 | 370 | F | 0 | 1130 |  |  |  | 32
2024-01-17 | 3854 |  | BSMT-A-SAMP-044 | A | DONE | 16 | S-M |  | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 230 | 0 | 150 | F | 0 | 550 |  |  |  | 32
2024-01-18 | 3855 |  | BSMT-A-SAMP-068 | A | DONE | 13 | S | s.mates | CDIS 6220028 |  | 2024-01-19 | Z | 2023-12-18 | 180 | 140 | 0 |  | 0 | 530 |  |  |  | 32
2024-01-18 | 3857 |  | BSMT-A-SAMP-045 | A | DONE | 18 | M |  | CDIS 6220028 |  | 2024-01-23 | Z | 2023-12-28 | 280 | 0 | 150 | F | 0 | 630 |  |  |  | 26
2024-01-18 | 3858 | bth | BSMT-A-SAMP-046 | A | DONE | 33 | M |  | CDIS 6220028 - 1" DW |  | 2024-01-23 | Z | 2023-12-28 | 330 | 20 | 470 | F | 200 | 1290 |  |  |  | 26
2024-01-18 | 3859 |  | BSMT-A-SAMP-030 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-01-23 | Z | 2023-12-28 | 80 | 0 | 30 | F | 0 | 140 |  |  |  | 26
2024-01-18 | 3860 | bth | BSMT-A-SAMP-031 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-01-23 | Z | 2023-12-28 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 26
2024-01-18 | 3861 | bth | BSMT-A-SAMP-032 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-01-23 | Z | 2023-12-28 | 40 | 20 | 100 | F | 0 | 180 |  |  |  | 26
2024-01-18 | 3862 | bth | BSMT-A-SAMP-033 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-01-23 | Z | 2023-12-28 | 40 | 20 | 40 | F | 0 | 100 |  |  |  | 26
2024-01-18 | 3863 | bth | BSMT-A-SAMP-034 | A | DONE | 27 | M | pt.neal | CDIS 6220028 - 1" DW |  | 2024-01-23 | Z | 2023-12-28 | 310 | 210 | 140 | F | 80 | 890 |  |  |  | 26
2024-01-18 | 3885 |  | 64109-10 | A | DONE | 4 | S-M |  | CDIS 6220028 - Test pc's AHU-2&9 |  | 2024-01-23 | Z | 2024-01-09 | 80 | 0 | 0 |  | 0 | 160 |  |  |  | 14
2024-01-17 | 3918 | w | 61417 | A | DONE | 2 | S |  | CDIS 6220028 - Sleeves |  | 2024-01-17 | Z | 2024-01-17 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-01-16 | 1555 |  | 62414 - 62416 | A | DONE | 2 | S-M |  | EMBASSY SUITES 6220012 - Roof |  | 2024-01-18 | Z | 2024-01-15 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 3
2024-01-16 | 1556 |  | 62417 | A | DONE | 5 | S-M |  | EMBASSY SUITES 6220012 - Shaft |  | 2024-01-18 | Z | 2024-01-15 | 110 | 0 | 0 |  | 20 | 170 |  |  |  | 3
2024-01-18 | 1689 |  | 72497 | A | DONE | 2 | S |  | EXACT SCIENCE 2230051 - QCNGS EAT1662-D |  | 2024-01-23 | Z | 2024-01-17 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-01-18 | 2677 |  | 68448 | A | DONE | 7 | S-M | flex | HEALTH SERV. 6230004 - B-30 Mech. Rm. bird.s |  | 2024-01-23 | Z | 2024-01-08 | 160 | 0 | 0 |  | 0 | 310 |  |  |  | 15
2024-01-16 | 2678 |  | 68449 | A | DONE | 3 | S-M | neal | HEALTH SERV. 6230004 - W. Basement open office |  | 2024-01-23 | Z | 2024-01-08 | 70 | 0 | 0 |  | 0 | 140 |  |  |  | 15
2024-01-15 | 2680 |  | 42638 - 42639 | A | DONE | 8 | S-M |  | HEALTH SERV. 6230004 - B 30 Mech Rm. |  | 2024-01-16 | Z | 2024-01-11 | 190 | 0 | 0 |  | 0 | 250 |  |  |  | 5
2024-01-18 | 2681 |  | 42637 | A | DONE | 4 | S-M |  | HEALTH SERV. 6230004 - B 30 Mech Rm. |  | 2024-01-23 | Z | 2024-01-11 | 90 | 0 | 0 |  | 0 | 170 |  |  |  | 12
2024-01-18 | 2682 | sp | 42640 | A | DONE | 2 | S |  | HEALTH SERV. 6230004 - EX / VAV |  | 2024-01-23 | Z | 2024-01-11 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 12
2024-01-18 | 2683 |  | 42641 - 42642 | A | DONE | 7 | S-M | flex | HEALTH SERV. 6230004 - Rm. B-15 |  | 2024-01-23 | Z | 2024-01-11 | 130 | 0 | 30 | F | 0 | 190 |  |  |  | 12
2024-01-17 | 2684 |  | 42643 | A | DONE | 2 | S-M |  | HEALTH SERV. 6230004 - AHU 6-1 RA |  | 2024-01-18 | Z | 2024-01-16 | 40 | 0 | 0 |  | 0 | 70 |  |  |  | 2
2024-01-18 | 2685 |  | 72150 | A | DONE | 2 | S-M | neal | HEALTH SERV. 6230004 - LL |  | 2024-01-23 | Z | 2024-01-16 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-01-16 | 3706 |  | 63338 | A | DONE | 4 | S-M |  | KOHL CENTER 6210034 - Boxes |  | 2024-01-19 | Z | 2024-01-15 | 90 | 0 | 0 |  | 0 | 100 |  |  |  | 4
2024-01-16 | 3707 |  | 63339 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Finishes |  | 2024-01-19 | Z | 2024-01-15 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 4
2024-01-18 | 3708 |  | 63340 | A | DONE | 2 | S-M |  | KOHL CENTER 6210034 - Upper Con. paint |  | 2024-01-19 | Z | 2024-01-17 | 20 | 0 | 0 |  | 20 | 60 |  |  |  | 2
2024-01-18 | 3709 |  | 55183 | A | DONE | 2 | S-M |  | KOHL CENTER 6210034 - RET paint |  | 2024-01-19 | Z | 2024-01-18 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 1
2024-01-15 | 765 |  | 68526 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 - Flat Stock |  | 2024-01-23 | Z | 2024-01-09 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 14
2024-01-16 | 766 |  | 70517 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 - Angle |  | 2024-01-16 | Z | 2024-01-16 | 20 | 0 | 0 |  | 0 | 80 |  |  |  | 0
2024-01-17 | 767 |  | 68527 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 - Roof Caps 1" liner |  | 2024-01-18 | Z | 2024-01-17 | 50 | 0 | 0 |  | 20 | 130 |  |  |  | 1
2024-01-18 | 768 |  | 70564 | A | DONE | 2 | S-M |  | MEMORIAL HS 6210024 - Cap 1" liner |  | 2024-01-18 | Z | 2024-01-18 | 20 | 0 | 0 |  | 20 | 50 |  |  |  | 0
2024-01-15 | 1935 |  | 67415 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 - SF Mech Rm. |  | 2024-01-18 | Z | 2024-01-11 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-01-17 | 1936 | bth | 67417 | A | DONE | 7 | S |  | MENDOTA FOODS 6220027 - 42' Linear |  | 2024-01-18 | Z | 2024-01-16 | 140 | 20 | 0 |  | 0 | 180 |  |  |  | 2
2024-01-17 | 725 |  | 61118 | A | DONE | 5 | S-M | flex | OLIV 6210030 - 1st Fl. Tie-Ins |  | 2024-01-18 | Z | 2024-01-16 | 120 | 0 | 0 |  | 0 | 140 |  |  |  | 2
2024-01-17 | 726 |  | 61119 | A | DONE | 2 | S-M | neal | OLIV 6210030 - 1st Fl outs paint |  | 2024-01-18 | Z | 2024-01-17 | 40 | 0 | 0 |  | 20 | 80 |  |  |  | 1
2024-01-18 | 727 |  | 61120 | A | DONE | 2 | S | flex | OLIV 6210030 - Misc |  | 2024-01-22 | Z | 2024-01-18 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 4
2024-01-18 | 728 |  | 69462 | A | DONE | 2 | S |  | OLIV 6210030 - L10 Misc paint |  | 2024-01-22 | Z | 2024-01-18 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 4
2024-01-17 | 308 | w | 11624 | A | DONE | 2 | S-M |  | PP 10053337 - Gen. JBox |  | 2024-01-18 | Z | 2024-01-16 | 50 | 0 | 0 |  | 0 | 160 |  |  |  | 2
2024-01-18 | 1234 |  | 62661 | A | DONE | 6 | S |  | PROMEGA FEYNMAN 6220014 - AHU-13 |  | 2024-01-24 | Z | 2024-01-15 | 140 | 0 | 0 |  | 0 | 300 |  |  |  | 9
2024-01-18 | 1235 |  | 62662 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 - Floor Sleeve |  | 2024-01-24 | Z | 2024-01-17 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 7
2024-01-15 | 176 |  | PL2-1 | A | DONE | 2 | S |  | QUAD CAPITAL 6230024 - Caps |  | 2024-01-16 | Z | 2024-01-11 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 5
2024-01-16 | 637 |  | 70654 | A | DONE | 9 | S |  | RAMC 6230009 - AHU-13-OA |  | 2024-01-22 | Z | 2024-01-05 | 220 | 0 | 0 |  | 0 | 320 |  |  |  | 17
2024-01-15 | 2057 |  | 78759 | A | DONE | 11 | S-M |  | ROCK CO. JAIL 6220018 - Cell chases |  | 2024-01-18 | Z | 2024-01-08 | 190 | 80 | 0 |  | 0 | 300 |  |  |  | 10
2024-01-15 | 2058 |  | 78803 - 78804 | A | DONE | 5 | S-M |  | ROCK CO. JAIL 6220018 - Kitchen Remodel |  | 2024-01-18 | Z | 2024-01-08 | 120 | 0 | 0 |  | 0 | 160 |  |  |  | 10
2024-01-15 | 2060 |  | 78807 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - SALP 18 1" liner |  | 2024-01-18 | Z | 2024-01-09 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 9
2024-01-16 | 2061 |  | 78808 - 78809 | A | DONE | 6 | S-M | flex | ROCK CO. JAIL 6220018 - Hallway / AHU-2 |  | 2024-01-18 | Z | 2024-01-10 | 140 | 0 | 0 |  | 0 | 290 |  |  |  | 8
2024-01-15 | 2062 |  | 78760 | A | DONE | 2 | S | bird.s | ROCK CO. JAIL 6220018 - AHU 1-K |  | 2024-01-18 | Z | 2024-01-10 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 8
2024-01-16 | 2063 |  | J2F-SALP-035 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-10 | 40 | 0 | 0 |  | 40 | 70 |  |  |  | 8
2024-01-16 | 2064 | bth | J2F-SALP-036 | A | DONE | 3 | S |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-10 | 40 | 20 | 0 |  | 20 | 50 |  |  |  | 8
2024-01-16 | 2065 |  | J2F-SALP-037 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-10 | 40 | 0 | 0 |  | 40 | 60 |  |  |  | 8
2024-01-16 | 2066 |  | J2F-SALP-038 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-10 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 8
2024-01-16 | 2067 |  | J2F-SALP-016 | A | DONE | 4 | S-M |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-11 | 60 | 0 | 20 | F | 30 | 90 |  |  |  | 7
2024-01-16 | 2068 |  | J2F-SALP-017 | A | DONE | 4 | S-M |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-11 | 100 | 0 | 0 |  | 30 | 150 |  |  |  | 7
2024-01-16 | 2069 |  | J2F-SALP-029 | A | DONE | 4 | S-M |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-11 | 100 | 0 | 0 |  | 30 | 150 |  |  |  | 7
2024-01-16 | 2070 |  | J2F-SALP-039 | A | DONE | 7 | S-M |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-11 | 170 | 0 | 0 |  | 50 | 200 |  |  |  | 7
2024-01-16 | 2071 |  | J2F-SALP-043 | A | DONE | 6 | S-M |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-11 | 80 | 0 | 50 | F | 20 | 140 |  |  |  | 7
2024-01-16 | 2072 |  | J2F-SALP-079 | A | DONE | 6 | S-M |  | ROCK CO. JAIL 6220018 - 1" liner |  | 2024-01-18 | Z | 2024-01-11 | 120 | 0 | 30 | F | 20 | 160 |  |  |  | 7
2024-01-16 | 2074 |  | 78762 | A | DONE | 6 | S-M | pt.neal | ROCK CO. JAIL 6220018 - C/D section misc paint |  | 2024-01-18 | Z | 2024-01-15 | 140 | 0 | 0 |  | 30 | 230 |  |  |  | 3
2024-01-17 | 2075 |  | 78763 | A | DONE | 12 | S-M |  | ROCK CO. JAIL 6220018 - Kitchen Flashing |  | 2024-01-25 | Z | 2024-01-16 | 280 | 0 | 0 |  | 0 | 330 |  |  |  | 9
2024-01-16 | 175 |  | 71337 | A | DONE | 2 | S |  | ST.BERNARDS 6230023 - Altar SA |  | 2024-01-22 | Z | 2024-01-10 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 12
2024-01-17 | r2715 |  | 73389 | A | DONE | 2 | S |  | UWL-HSC 6230018 - L-4 |  | 2024-01-23 | Z | 2024-01-16 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-01-16 | 2769 |  | 72658 | A | DONE | 2 | S | ss | UW-VET MED 6210014 - 2nd Fl. |  | 2024-01-22 | Z | 2024-01-15 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-01-17 | 2770 | sp | 72659 | A | DONE | 2 | S |  | UW-VET MED 6210014- L2-D |  | 2024-01-22 | Z | 2024-01-16 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 6
2024-01-17 | 182 |  | call in | A | DONE | 2 | S |  | VERONA ICE ARENA 4230034 - St Collar |  | 2024-01-17 | Z | 2024-01-17 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-01-18 | 1751 | w | 1C-Dishwasher duct-1 | A | DONE | 8 | S-M | ss | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2023-12-21 | 150 | 0 | 0 |  | 0 | 320 |  |  |  | 28
2024-01-16 | 1787 |  | 2D-EA-1 | A | DONE | 56 | L | pt.neal | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 410 | 0 | 980 | F | 0 | 2620 |  |  |  | 9
2024-01-15 | 1788 | bth | 2D-EA-2 | A | DONE | 17 | S-M |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 210 | 70 | 130 | F | 0 | 470 |  |  |  | 9
2024-01-15 | 1789 | bth | 2D-EA-3 | F | DONE | 28 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 330 | 130 | 230 | F | 0 | 790 |  |  |  | 9
2024-01-16 | 1792 | bth | 2D-OA-1 | A | DONE | 45 | M-L | neal | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 430 | 130 | 550 | F | 0 | 1420 |  |  |  | 9
2024-01-16 | 1793 | bth | 2D-OA-2 | A | DONE | 20 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 180 | 40 | 270 | F | 0 | 600 |  |  |  | 9
2024-01-15 | 1795 | bth | 2D-OA-4 | A | DONE | 8 | S |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 70 | 50 | 60 | F | 0 | 200 |  |  |  | 9
2024-01-16 | 1796 | bth | 2D-OA-5 | A | DONE | 31 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 230 | 20 | 510 | F | 0 | 900 |  |  |  | 9
2024-01-15 | 1797 | bth | 2D-OA-6 | A | DONE | 25 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 200 | 170 | 240 | F | 0 | 690 |  |  |  | 9
2024-01-17 | 1798 | bth | 2D-OA-7 | A | DONE | 20 | M |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 120 | 170 | 210 | F | 0 | 590 |  |  |  | 9
2024-01-16 | 1799 | bth | 2D-OA-8 | A | DONE | 10 | S |  | WCSD HERITAGE 6220024 |  | 2024-01-18 | Z | 2024-01-09 | 50 | 120 | 60 | F | 0 | 250 |  |  |  | 9
2024-01-15 | 1812 |  | 69008 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - HP-169 1" liner paint |  | 2024-01-18 | Z | 2024-01-10 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 8
2024-01-17 | 1845 |  | 69009 | A | DONE | 2 | S | ss | WCSD HERITAGE 6220024 - Dishwasher duct |  | 2024-01-23 | Z | 2024-01-16 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 7
[6 empty] | 792 | [13 empty] | 26670 |  |  |  | 13830 | 51.86%
WEEK OF 1-22-2024
2024-01-24 | 193 |  | PL2-2 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 - Caps |  | 2024-01-24 | Z | 2024-01-24 | 0 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-01-22 | 3864 |  | BSMT-A-SAMP-035 | A | DONE | 37 | M |  | CDIS 6220028 |  | 2024-01-23 | Z | 2023-12-28 | 450 | 0 | 470 | F | 0 | 1550 |  |  |  | 26
2024-01-22 | 3865 | bth | BSMT-A-EAD-032 | A | DONE | 3 | S | neal | CDIS 6220028 - paint |  | 2024-01-23 | Z | 2023-12-28 | 50 | 20 | 0 |  | 0 | 80 |  |  |  | 26
2024-01-22 | 3866 |  | BSMT-A-EAD-020 | A | DONE | 20 | S-M |  | CDIS 6220028 |  | 2024-01-23 | Z | 2023-12-28 | 330 | 0 | 170 | F | 0 | 1080 |  |  |  | 26
2024-01-22 | 3867 | bth | BSMT-A-EAD-021 | A | DONE | 17 | S | pt.neal | CDIS 6220028 - 1" DW , 1" liner , paint |  | 2024-01-23 | Z | 2023-12-28 | 200 | 180 | 40 | F | 230 | 450 |  |  |  | 26
2024-01-22 | 3868 |  | BSMT-A-EAD-022 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-01-23 | Z | 2023-12-28 | 80 | 0 | 70 | F | 0 | 180 |  |  |  | 26
2024-01-24 | 3869 |  | BSMT-A-SAMP-069 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-01-26 | Z | 2023-12-28 | 110 | 0 | 0 |  | 0 | 140 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3870 |  | BSMT-A-SALP-061 | A | DONE | 4 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-01-26 | Z | 2023-12-28 | 80 | 0 | 20 | F | 70 | 120 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3871 | bth | BSMT-A-SALP-062 | A | DONE | 4 | S |  | CDIS 6220028 - 1" liner |  | 2024-01-26 | Z | 2023-12-28 | 70 | 20 | 0 |  | 40 | 90 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3872 | bth | BSMT-A-SALP-063 | A | DONE | 4 | S |  | CDIS 6220028 - 1" liner |  | 2024-01-26 | Z | 2023-12-28 | 60 | 20 | 0 |  | 30 | 80 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3873 | bth | BSMT-A-SALP-064 | A | DONE | 4 | S |  | CDIS 6220028 - 1" liner |  | 2024-01-26 | Z | 2023-12-28 | 70 | 20 | 0 |  | 40 | 90 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3874 |  | BSMT-A-SALP-065 | A | DONE | 4 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-01-26 | Z | 2023-12-28 | 50 | 0 | 30 | F | 10 | 90 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3875 |  | BSMT-A-RAD-011 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-01-26 | Z | 2023-12-28 | 80 | 0 | 0 |  | 0 | 100 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3876 |  | BSMT-A-RAD-006 | A | DONE | 17 | M |  | CDIS 6220028 |  | 2024-01-26 | Z | 2023-12-28 | 310 | 0 | 100 | F | 0 | 580 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3877 |  | BSMT-A-RAD-007 | A | DONE | 13 | S-M | neal | CDIS 6220028 |  | 2024-01-26 | Z | 2023-12-28 | 180 | 0 | 140 | F | 0 | 470 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3878 | bth | BSMT-A-EAD-023 | A | DONE | 5 | S-M |  | CDIS 6220028 - 1" sp.accoustic |  | 2024-01-26 | Z | 2023-12-28 | 70 | 50 | 0 |  | 70 | 130 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3879 |  | BSMT-A-EAD-024 | A | DONE | 37 | M-L |  | CDIS 6220028 |  | 2024-01-26 | Z | 2023-12-28 | 390 | 0 | 530 | F | 0 | 1920 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3880 | bth | BSMT-A-EAD-025 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-01-26 | Z | 2023-12-28 | 70 | 30 | 40 | F | 0 | 150 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3881 | bth | BSMT-A-EAD-026 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-01-26 | Z | 2023-12-28 | 20 | 30 | 80 | F | 0 | 140 |  |  |  | 29 |  | 2024-02-09
2024-01-25 | 3888 |  | BSMT-C-SAMP-010 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 120 | 0 | 120 | F | 0 | 300 |  |  |  | 20 |  | 2024-02-16
2024-01-24 | 3916 |  | 61413 - 61414 | A | DONE | 18 | M |  | CDIS 6220028 - SC RAD |  | 2024-01-26 | Z | 2024-01-11 | 310 | 0 | 120 | F | 0 | 740 |  |  |  | 15 |  | 2024-02-09
2024-01-24 | 3917 |  | 61415 - 61416 | A | DONE | 20 | M |  | CDIS 6220028 - SC EAD |  | 2024-01-26 | Z | 2024-01-11 | 0 | 0 | 500 | F | 0 | 1090 |  |  |  | 15 |  | 2024-02-09
2024-01-22 | 3929 |  | 61311 | A | DONE | 2 | S |  | CDIS 6220028 - RA |  | 2024-01-23 | Z | 2024-01-19 | 0 | 0 | 50 | F | 0 | 90 |  |  |  | 4
2024-01-25 | 3930 |  | 61419 | A | DONE | 4 | S-M |  | CDIS 6220028 - Angle |  | 2024-01-30 | Z | 2024-01-23 | 100 | 0 | 0 |  | 0 | 170 |  |  |  | 7
2024-01-22 | 1557 |  | 62362 | A | DONE | n/a | S |  | EMBASSY SUITES 6220012 - Linear Plenum BG's |  | 2024-01-23 | Z | 2024-01-16 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 7
2024-01-24 | 1677 | sp | 62505 | A | DONE | 18 | M |  | EXACT BIOSAFE 6230005 - Phase 2 |  | 2024-01-30 | Z | 2023-12-13 | 70 | 360 | 0 |  | 0 | 500 |  |  |  | 48 |  | 2023-01-02
2024-01-22 | 1690 | sp | 62512 | A | DONE | 2 | S |  | EXACT QC 2230051 - Misc |  | 2024-01-23 | Z | 2024-01-19 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 4
2024-01-23 | 1691 |  | 76118 | A | DONE | 2 | S | ss | EXACT SCIENCE 8230019 - Buffer guard |  | 2024-01-29 | Z | 2024-01-22 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 7
2024-01-25 | 2686 |  | 42644 | A | DONE | 20 | S-M |  | HEALTH SERV. 6230004 - B-3 |  | 2024-01-30 | Z | 2024-01-17 | 330 | 0 | 160 | F | 0 | 710 |  |  |  | 13
2024-01-25 | 2687 |  | 42645 | A | DONE | 2 | S |  | HEALTH SERV. 6230004 - Basement vav tie in |  | 2024-01-30 | Z | 2024-01-17 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 13
2024-01-26 | 2688 |  | 42646 | A | DONE | 2 | S-M | neal | HEALTH SERV. 6230004 - Paint Rm. RA |  | 2024-01-30 | Z | 2024-01-18 | 50 | 0 | 0 |  | 0 | 70 |  |  |  | 12
2024-01-26 | 2689 |  | 57937 | A | DONE | 2 | S-M | alum | HEALTH SERV. 6230004 - PT / Activity |  | 2024-01-30 | Z | 2024-01-18 | 30 | 0 | 0 |  | 0 | 20 |  |  |  | 12
2024-01-23 | 2690 |  | 41834 | A | DONE | 2 | S |  | HEALTH SERV. 6230004 - B30 |  | 2024-01-24 | Z | 2024-01-23 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 1
2024-01-24 | 2691 |  | 42647 | A | DONE | 9 | S-M | neal | HEALTH SERV. 6230004 - Basement |  | 2024-01-30 | Z | 2024-01-24 | 220 | 0 | 0 |  | 0 | 250 |  |  |  | 6
2024-01-23 | 2802 |  | 70801 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 - IF-1 |  | 2024-02-01 | Z | 2024-01-17 | 50 | 0 | 0 |  | 0 | 90 |  |  |  | 15
2024-01-23 | 184 | bth | 69369 - 69371 | A | DONE | 13 | S-M |  | KL ENGINEERING 4240002 - FCU's |  | 2024-01-26 | Z | 2024-01-19 | 90 | 220 | 0 |  | 0 | 320 |  |  |  | 7
2024-01-23 | 185 | bth | 69372 - 69373 | A | DONE | 12 | S-M |  | KL ENGINEERING 4240002 - FCU's |  | 2024-01-26 | Z | 2024-01-19 | 130 | 170 | 0 |  | 0 | 320 |  |  |  | 7
2024-01-24 | 186 | bth | 69366 , 69368 | A | DONE | 12 | S-M |  | KL ENGINEERING 4240002 - FCU's |  | 2024-01-26 | Z | 2024-01-19 | 80 | 200 | 0 |  | 20 | 270 |  |  |  | 7
2024-01-25 | 188 | bth | 69374 - 69375 | A | DONE | 10 | S-M | neal | KL ENGINEERING 4240002 - FCU's |  | 2024-01-29 | Z | 2024-01-23 | 130 | 90 | 30 | F | 0 | 300 |  |  |  | 6
2024-01-25 | 189 |  | 69376 - 69377 | A | DONE | 6 | S-M | neal | KL ENGINEERING 4240002 - FCU's |  | 2024-01-29 | Z | 2024-01-23 | 130 | 0 | 0 |  | 0 | 210 |  |  |  | 6
2024-01-25 | 190 | sp | 69378 - 69379 | A | DONE | 17 | S-M | neal | KL ENGINEERING 4240002 - FCU's |  | 2024-01-29 | Z | 2024-01-23 | 140 | 270 | 0 |  | 0 | 470 |  |  |  | 6
2024-01-25 | 192 |  | 69383 | A | DONE | 2 | S |  | KL ENGINEERING 4240002 - TA 1"liner |  | 2024-01-29 | Z | 2024-01-23 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 6
2024-01-22 | 3710 |  | 63341 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - E. upper |  | 2024-01-22 | Z | 2024-01-22 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 0
2024-01-24 | 3711 |  | 63342 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Finish paint |  | 2024-01-26 | Z | 2024-01-24 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 2
2024-01-25 | 3712 |  | 63343 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Mezz finishes paint |  | 2024-01-26 | Z | 2024-01-24 | 40 | 0 | 0 |  | 20 | 40 |  |  |  | 2
2024-01-25 | 174 | sp | 70267 | A | DONE | 8 | S | ss | LABCORP 4230039 - Cage wash |  | 2024-01-30 | Z | 2024-01-09 | 90 | 90 | 0 |  | 0 | 200 |  |  |  | 21
2024-01-24 | 177 |  | 70268 | L | delete | 8 | S-M | ss | LABCORP 4230039 - Cage wash |  | 2024-01-22 | Z | 2024-01-15 | 90 | 110 | 0 |  | 0 | 200 |  |  |  | 7
2024-01-22 | 181 |  | 70269 | A | DONE | 4 | S | ss | LAB CORP. 4230039 - Extra EA |  | 2024-01-22 | Z | 2024-01-16 | 40 | 50 | 0 |  | 0 | 90 |  |  |  | 6
2024-01-22 | 183 |  | 70270 | A | DONE | 6 | S-M | ss | LABCORP 4230039 - Fresh air |  | 2024-01-23 | Z | 2024-01-18 | 80 | 70 | 0 |  | 0 | 150 |  |  |  | 5
2024-01-25 | 769 |  | 68528 | A | DONE | 16 | S-M | alum | MEMORIAL HS 6210024 - CB 41.1 |  | 2024-01-30 | Z | 2024-01-18 | 160 | 0 | 220 | F | 0 | 240 |  |  |  | 12
2024-01-23 | 191 |  | 70271 | A | DONE | 2 | S |  | MIDDLETON WEST 4230086 - Coupler |  | 2024-01-25 | Z | 2024-01-23 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-01-24 | 3805 |  | 66065 | A | DONE | 2 | S-M |  | MOXY 6210032 - PH |  | 2024-01-26 | Z | 2024-01-24 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 2
2024-01-22 | 729 |  | 61121 | A | DONE | n/a | S | flex | OLIV 6210030 - L1 |  | 2024-01-25 | Z | 2024-01-19 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 6
2024-01-24 | 730 |  | 69463 - 69465 | A | DONE | 6 | S-M | neal | OLIV 6210030 - L1 Louver tie in / L2 paint |  | 2024-01-25 | Z | 2024-01-24 | 150 | 0 | 0 |  | 20 | 190 |  |  |  | 1
2024-01-24 | 731 | bth | 69466 | A | DONE | 4 | S-M | pt.alum | OLIV 6210030 - L2 |  | 2024-01-25 | Z | 2024-01-24 | 30 | 50 | 0 |  | 0 | 70 |  |  |  | 1
2024-01-24 | 732 |  | 61123 | A | DONE | 2 | S-M | neal | OLIV 6210030 - L1 Corridor |  | 2024-01-25 | Z | 2024-01-24 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2024-01-24 | 733 |  | 61122 | A | DONE | 2 | S-M | flex | OLIV 6210030 - 1st Fl. |  | 2024-01-25 | Z | 2024-01-24 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-01-22 | 309 | w | 11625 | A | DONE | 2 | S-M |  | PP 10053337 - MV. JBox |  | 2024-01-23 | Z | 2024-01-16 | 50 | 0 | 0 |  | 0 | 220 |  |  |  | 7
2024-01-25 | 1619 |  | 66903 | A | DONE | 2 | S |  | PROMEGA CMC 6230019 - Hood tie in |  | 2024-01-26 | Z | 2024-01-25 | 40 | 0 | 0 |  | 0 | 80 |  |  |  | 1
2024-01-23 | 1618 | sp | 66902 | A | DONE | 3 | S |  | PROMEGA CMC 6230019 - Hood tie-in |  | 2024-01-25 | Z | 2024-01-23 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 2
2024-01-22 | 1231 | w | 62922 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 - Roof stack |  | 2024-01-31 | Z | 2024-01-12 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 19
2024-01-22 | 1232 | w | 62921 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 - Roof stack |  | 2024-01-31 | Z | 2024-01-12 | 50 | 0 | 0 |  | 0 | 100 |  |  |  | 19
2024-01-22 | 1233 |  | 62659 - 62660 | A | DONE | 8 | S-M |  | PROMEGA FEYNMAN 6220014 - RF-13 / AHU-13 |  | 2024-01-24 | Z | 2024-01-15 | 200 | 0 | 0 |  | 0 | 530 |  |  |  | 9
2024-01-22 | 1241 |  | 62887 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 - 1st floor out |  | 2024-01-24 | Z | 2024-01-19 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 5
2024-01-22 | 2073 | w | 78761 | A | DONE | 2 | S-M | ss | ROCK CO. JAIL 6220018 - Kitchen Duct |  | 2024-01-25 | Z | 2024-01-15 | 50 | 0 | 0 |  | 0 | 130 |  |  |  | 10
2024-01-24 | 2076 |  | 78810 | A | DONE | 2 | S | pcd | ROCK CO. JAIL 6220018 - Mech room |  | 2024-01-25 | Z | 2024-01-16 | 50 | 0 | 0 |  | 0 | 100 |  |  |  | 9
2024-01-23 | 2077 |  | 78811 | A | DONE | 4 | S-M |  | ROCK CO. JAIL 6220018 - Mech room |  | 2024-01-25 | Z | 2024-01-16 | 40 | 0 | 40 | F | 0 | 80 |  |  |  | 9
2024-01-22 | 2078 |  | 72364 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - F.G grille boxes paint |  | 2024-01-25 | Z | 2024-01-17 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 8
2024-01-22 | 2079 |  | 78812 | A | DONE | 4 | S-M |  | ROCK CO. JAIL 6220018 - Kitchen |  | 2024-01-25 | Z | 2024-01-17 | 30 | 0 | 70 | F | 0 | 130 |  |  |  | 8
2024-01-22 | 2080 |  | 78764 | A | DONE | 2 | S | neal | ROCK CO. JAIL 6220018 - Fitness Flashing |  | 2024-01-25 | Z | 2024-01-22 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 3
2024-01-22 | 2081 | w | 78813 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Sleeve Ext. |  | 2024-01-25 | Z | 2024-01-22 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 3
2024-01-23 | 2082 |  | 78814 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Cell chases |  | 2024-01-25 | Z | 2024-01-22 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 3
2024-01-24 | 170 |  | 71065 | A | DONE | 7 | S-M |  | UWL-CHILLER 6230008 - L-3 |  | 2024-01-26 | Z | 2023-09-08 | 170 | 0 | 0 |  | 0 | 370 |  |  |  | 140 |  | 2023-10-13 | 2023-11-10
2024-01-26 | 2771 |  | 72662 - 72663 | A | DONE | 4 | S-M | neal | UW-VET MED 6210014 - Arena tray |  | 2024-01-29 | Z | 2024-01-24 | 80 | 0 | 0 |  | 0 | 180 |  |  |  | 5
2024-01-22 | 1511 |  | 38165 | A | DONE | 2 | S |  | WAUSHARA CO. GOV. 6220010 - 1st Fl C. |  | 2024-01-23 | Z | 2024-01-17 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-01-22 | 1512 | bth | 38166 | A | DONE | 3 | S |  | WAUSHARA CO. GOV. 6220010 - 1st Fl C. |  | 2024-01-23 | Z | 2024-01-18 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 5
2024-01-23 | 1758 |  | 2D-RA-1 | A | DONE | 5 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 120 | 0 | 0 |  | 80 | 150 |  |  |  | 23
2024-01-23 | 1759 |  | 2D-RA-2 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 40 | 0 | 40 | F | 70 | 110 |  |  |  | 23
2024-01-23 | 1760 |  | 2D-RA-3 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 90 | 0 | 0 |  | 60 | 110 |  |  |  | 23
2024-01-23 | 1761 |  | 2D-RA-4 | A | DONE | 9 | S-M | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 220 | 0 | 70 | F | 200 | 360 |  |  |  | 23
2024-01-23 | 1762 |  | 2D-RA-5 | A | DONE | 6 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 130 | 0 | 0 |  | 130 | 190 |  |  |  | 23
2024-01-24 | 1763 |  | 2D-RA-6 | A | DONE | 5 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 80 | 0 | 40 | F | 70 | 150 |  |  |  | 23
2024-01-23 | 1764 |  | 2D-RA-7 | A | DONE | 5 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 100 | 20 | 0 |  | 0 | 130 |  |  |  | 23
2024-01-23 | 1765 |  | 2D-RA-8 | A | DONE | 8 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 150 | 0 | 40 | F | 200 | 240 |  |  |  | 23
2024-01-23 | 1766 |  | 2D-RA-9 | A | DONE | 12 | S-M | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 260 | 0 | 40 | F | 280 | 400 |  |  |  | 23
2024-01-23 | 1767 | bth | 2D-RA-10 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 80 | 20 | 0 |  | 40 | 100 |  |  |  | 23
2024-01-23 | 1768 |  | 2D-RA-11 | A | DONE | 9 | S | flex | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 220 | 0 | 0 |  | 150 | 280 |  |  |  | 23
2024-01-23 | 1769 |  | 2D-RA-12 | A | DONE | 6 | S | flex/neal | WCSD HERITAGE 6220024 1"liner |  | 2024-01-25 | Z | 2024-01-02 | 110 | 0 | 30 | F | 110 | 160 |  |  |  | 23
2024-01-23 | 1770 | bth | 2D-SA-1 | A | DONE | 19 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 140 | 190 | 130 | F | 0 | 530 |  |  |  | 23
2024-01-23 | 1771 | bth | 2D-SA-2 | A | DONE | 13 | S-M | flex/neal | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 180 | 40 | 90 | F | 0 | 280 |  |  |  | 23
2024-01-23 | 1772 | bth | 2D-SA-3 | A | DONE | 12 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 140 | 90 | 50 | F | 0 | 320 |  |  |  | 23
2024-01-23 | 1773 | bth | 2D-SA-4 | A | DONE | 10 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 140 | 90 | 0 |  | 0 | 270 |  |  |  | 23
2024-01-24 | 1774 | bth | 2D-SA-5 | A | DONE | 18 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 100 | 90 | 250 | F | 0 | 520 |  |  |  | 23
2024-01-24 | 1775 | bth | 2D-SA-6 | A | DONE | 10 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 120 | 100 | 30 | F | 0 | 290 |  |  |  | 23
2024-01-24 | 1776 | bth | 2D-SA-7 | A | DONE | 7 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 90 | 40 | 40 | F | 0 | 210 |  |  |  | 23
2024-01-24 | 1777 | bth | 2D-SA-8 | A | DONE | 11 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 140 | 60 | 70 | F | 0 | 320 |  |  |  | 23
2024-01-24 | 1778 | bth | 2D-SA-9 | A | DONE | 8 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 70 | 40 | 70 | F | 0 | 210 |  |  |  | 23
2024-01-24 | 1779 | bth | 2D-SA-10 | A | DONE | 13 | S-M | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 200 | 80 | 30 | F | 0 | 350 |  |  |  | 23
2024-01-24 | 1780 | bth | 2D-SA-11 | A | DONE | 8 | S | flex | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 80 | 70 | 40 | F | 0 | 210 |  |  |  | 23
2024-01-24 | 1781 | bth | 2D-SA-12 | A | DONE | 16 | S-M | flex/neal | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 170 | 40 | 170 | F | 0 | 460 |  |  |  | 23
2024-01-24 | 1782 | bth | 2D-SA-13 | A | DONE | 19 | S-M | flex/neal | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 140 | 100 | 230 | F | 0 | 550 |  |  |  | 23
2024-01-24 | 1783 |  | 2D-SA-14 | A | DONE | 2 | S | flex/neal | WCSD HERITAGE 6220024 |  | 2024-01-25 | Z | 2024-01-02 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 23
2024-01-22 | 1846 |  | 57764 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - D-Section OA |  | 2024-01-25 | Z | 2024-01-17 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 8
2024-01-23 | 1847 |  | 69152 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - 2C-OA-1 |  | 2024-01-25 | Z | 2024-01-22 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-01-24 | 1848 |  | 69154 - 69155 | A | DONE | 5 | S-M | flex | WCSD HERITAGE 6220024 - HP TA 1" liner |  | 2024-01-25 | Z | 2024-01-22 | 120 | 0 | 0 |  | 40 | 140 |  |  |  | 3
2024-01-22 | 1849 |  | 70565 | A | DONE | 2 | S | pt.neal | WCSD HERITAGE 6220024 - Misc |  | 2024-01-22 | Z | 2024-01-22 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-01-23 | 1850 |  | 68972 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - Misc |  | 2024-01-25 | Z | 2024-01-22 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 3
[6 empty] | 764 | [13 empty] | 24390 |  |  |  | 6540 | 26.81%
WEEK OF 1-29-2024
2024-01-30 | 179 |  | PL2-3 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 - Caps |  | 2024-01-30 | Z | 2024-01-30 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-02-01 | 201 |  | 70568 | A | DONE | 49 | M |  | 121 E. WILSON 6230024 - Flat stock |  | 2024-02-01 | Z | 2024-02-01 | 1210 | 0 | 0 |  | 0 | 1100 |  |  |  | 0
2024-02-01 | 178 |  | 70041 | A | DONE | 3 | S |  | ALDEVRON 1ST FL 2230053 - VAV 140 paint |  | 2024-02-05 | Z | 2024-01-16 | 60 | 0 | 0 |  | 20 | 60 |  |  |  | 20
2024-02-01 | 179 | sp | 70042 - 70043 | A | DONE | 4 | S-M |  | ALDEVRON 1ST FL 2230053 - VAV 136 , 140 |  | 2024-02-05 | Z | 2024-01-16 | 20 | 60 | 0 |  | 0 | 70 |  |  |  | 20
2024-02-01 | 180 |  | 70044 | A | DONE | 2 | S |  | ALDEVRON 1ST FL 2230053 - Office TA 1/2" liner |  | 2024-02-05 | Z | 2024-01-16 | 40 | 0 | 0 |  | 30 | 40 |  |  |  | 20
2024-01-30 | 1719 |  | 78952 | A | DONE | 2 | S |  | BLACKHAWK BTC 6230025 - Angle |  | 2024-02-01 | Z | 2024-01-29 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 3
2024-01-30 | 1718 | w | 78951 | A | DONE | 3 | S |  | BLACKHAWK BTC 6230025 - Wall sleeve 2" FB |  | 2024-02-01 | Z | 2024-01-24 | 70 | 0 | 0 |  | 40 | 160 |  |  |  | 8
2024-01-29 | 3886 |  | BSMT-C-SAMP-008 | A | DONE | 53 | M-L |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 970 | 0 | 340 | F | 0 | 2870 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3887 |  | BSMT-C-SAMP-009 | A | DONE | 34 | M-L |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 560 | 0 | 290 | F | 0 | 1720 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3889 |  | BSMT-C-SAMP-011 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 150 | 0 | 50 | F | 0 | 240 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3890 | sp | BSMT-C-SAMP-012 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3891 | sp | BSMT-C-SAMP-013 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3892 | bth | BSMT-C-SAMP-014 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 100 | 20 | 30 | F | 0 | 160 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3893 | bth | BSMT-C-SAMP-015 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 120 | 30 | 0 |  | 0 | 170 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3894 | bth | BSMT-C-SAMP-016 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 30 | 50 | 0 |  | 0 | 80 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3895 |  | BSMT-C-EAD-007 | A | DONE | 31 | M-L | neal | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 590 | 0 | 170 | F | 0 | 1660 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3896 |  | BSMT-C-EAD-008 | A | DONE | 22 | M | neal | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 460 | 0 | 90 | F | 0 | 1000 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3897 |  | BSMT-C-EAD-009 | A | DONE | 16 | S-M | neal | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 190 | 0 | 210 | F | 0 | 590 |  |  |  | 20 |  | 2024-02-16
2024-01-30 | 3898 | bth | BSMT-C-EAD-010 | A | DONE | 6 | S | alum | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 70 | 50 | 30 | F | 0 | 100 |  |  |  | 20 |  | 2024-02-16
2024-01-30 | 3899 | bth | BSMT-C-EAD-011 | A | DONE | 8 | S | alum | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 120 | 20 | 50 | F | 0 | 120 |  |  |  | 20 |  | 2024-02-16
2024-01-30 | 3900 | bth | BSMT-C-EAD-012 | A | DONE | 6 | S | alum | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 40 | 40 | 50 | F | 0 | 90 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3901 |  | BSMT-C-EAD-013 | A | DONE | 8 | S | neal | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 150 | 0 | 30 | F | 0 | 200 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3902 | bth | BSMT-C-EAD-014 | A | DONE | 5 | S | neal | CDIS 6220028 - paint |  | 2024-01-30 | Z | 2024-01-10 | 70 | 20 | 30 | F | 20 | 130 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3903 | bth | BSMT-C-EAD-015 | A | DONE | 5 | S | neal | CDIS 6220028 - paint |  | 2024-01-30 | Z | 2024-01-10 | 60 | 20 | 40 | F | 20 | 130 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3904 | bth | BSMT-C-EAD-016 | A | DONE | 3 | S | neal | CDIS 6220028 - paint |  | 2024-01-30 | Z | 2024-01-10 | 30 | 40 | 0 |  | 20 | 80 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3905 | sp | BSMT-C-EAD-017 | A | DONE | 3 | S | neal | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3906 | sp | BSMT-C-EAD-018 | A | DONE | 4 | S | neal | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 20 | 60 | 0 |  | 0 | 90 |  |  |  | 20 |  | 2024-02-16
2024-01-29 | 3907 | sp | BSMT-C-EAD-019 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-01-30 | Z | 2024-01-10 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 20 |  | 2024-02-16
2024-02-02 | 3909 |  | BSMT-C-SALP-017 | A | DONE | 4 | S | neal | CDIS 6220028 - paint |  | 2024-02-06 | Z | 2024-01-10 | 90 | 0 | 0 |  | 40 | 140 |  |  |  | 27 |  | 2024-02-22
2024-02-02 | 3910 |  | BSMT-C-SALP-018 | A | DONE | 2 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-06 | Z | 2024-01-10 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 27 |  | 2024-02-22
2024-01-31 | 3975 |  | 61420 | A | DONE | 24 | M |  | CDIS 6220028 - Flashing |  | 2024-02-06 | Z | 2024-01-29 | 590 | 0 | 0 |  | 0 | 970 |  |  |  | 8
2024-01-31 | 3999 |  | 61421 | A | DONE | 2 | S |  | CDIS 6220028 - Sleeves |  | 2024-02-02 | Z | 2024-01-31 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-02-02 | 2333 |  | 71506 | A | DONE | 3 | S-M |  | DEWITT LAW 6230021 - 9th floor |  | 2024-02-05 | Z | 2024-01-31 | 60 | 0 | 0 |  | 0 | 90 |  |  |  | 5
2024-02-02 | 1258 |  | 70033 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 - EAT 111 paint |  | 2024-02-05 | Z | 2023-12-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 55 |  | 2024-02-12
2024-02-02 | 1260 | sp | 70036 - 70037 | A | DONE | 14 | S-M |  | EGENESIS PH2 6230026 - RTU-1 RA |  | 2024-02-05 | Z | 2023-12-13 | 280 | 50 | 0 |  | 0 | 480 |  |  |  | 54 |  | 2024-02-12
2024-02-01 | 1261 | sp | 70038 | A | DONE | 7 | S-M |  | EGENESIS PH2 6230026 - RTU-1 SA |  | 2024-02-05 | Z | 2023-12-13 | 0 | 170 | 0 |  | 0 | 250 |  |  |  | 54 |  | 2024-02-12
2024-01-31 | 1262 | w | 70039 - 70040 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 - Detail Flashing |  | 2024-02-05 | Z | 2023-12-15 | 50 | 0 | 0 |  | 0 | 110 |  |  |  | 52 |  | 2024-02-12
2024-01-31 | 1263 |  | 61843 | A | DONE | n/a | S | flex | EGENESIS PH2 6230026 - Office area |  | 2024-02-05 | Z | 2023-12-19 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 48 |  | 2024-02-12
2024-01-31 | 1264 |  | DH-0002 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 - Hangers |  | 2024-02-05 | Z | 2023-12-19 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 48
2024-02-02 | 1265 |  | 70062 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 - Office TA 1/2" liner |  | 2024-02-05 | Z | 2023-12-27 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 40
2024-02-02 | 1560 |  | 62364 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 - Angle |  | 2024-02-02 | Z | 2024-02-01 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2024-01-30 | 1558 |  | 62418 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 - E. Shaft |  | 2024-01-31 | Z | 2024-01-25 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 6
2024-01-29 | 1559 | w | 62363 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 - Roof Curb portal 1" DB |  | 2024-01-31 | Z | 2024-01-25 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 6
2024-02-01 | 1692 | sp | 62516 | A | DONE | 4 | S-M | pt.alum | EXACT BIOSAFE 6230005 - FCU |  | 2024-02-06 | Z | 2024-01-24 | 20 | 70 | 0 |  | 20 | 80 |  |  |  | 13
2024-01-29 | 1675 | sp | 62501 - 62502 | A | DONE | 27 | M |  | EXACT BIOSAFE 6230005 - RTU-1 |  | 2024-01-30 | Z | 2023-12-13 | 140 | 530 | 0 |  | 0 | 770 |  |  |  | 48 |  | 2023-01-02
2024-01-29 | 1676 | sp | 62503 - 62504 | A | DONE | 24 | M |  | EXACT BIOSAFE 6230005 - RTU-2 |  | 2024-01-30 | Z | 2023-12-13 | 80 | 520 | 0 |  | 0 | 730 |  |  |  | 48 |  | 2024-01-02
2024-02-02 | 2692 |  | 42648 | A | DONE | 2 | S-M |  | HEALTH SERV. 6230004 - Ceiling finish |  | 2024-02-06 | Z | 2024-01-30 | 50 | 0 | 0 |  | 0 | 50 |  |  |  | 7
2024-01-31 | 200 |  | 69385 | A | DONE | 2 | S | neal | KL ENGINEERING 4240002 - Misc |  | 2024-02-01 | Z | 2024-01-31 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-01-30 | 3705 | sp | 63335 | A | DONE | 2 | S | neal | KOHL CENTER 6210034 - Misc |  | 2024-02-02 | Z | 2024-01-08 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 25
2024-01-30 | 3713 |  | 55185 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Mezz finishes |  | 2024-02-02 | Z | 2024-01-25 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 8
2024-01-30 | 3714 | sp | 63344 | A | DONE | 2 | S | neal | KOHL CENTER 6210034 - Misc |  | 2024-02-02 | Z | 2024-01-30 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-01-31 | 3715 |  | 55186 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Main K Lid |  | 2024-02-02 | Z | 2024-01-30 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-02-01 | 3716 |  | 63345 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Shaft |  | 2024-02-02 | Z | 2024-01-31 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-01-31 | 771 |  | 70518 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 - Misc |  | 2024-02-02 | Z | 2024-01-31 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-02-01 | 770 |  | 68529 | A | DONE | 3 | S |  | MEMORIAL HS 6210024 - Shower stadium |  | 2024-02-05 | Z | 2024-01-30 | 70 | 0 | 0 |  | 0 | 80 |  |  |  | 6
2024-01-31 | 194 |  | 70215 | A | DONE | 5 | S-M | bird.s | MPI W-90926 - EA flex |  | 2024-02-02 | Z | 2024-01-24 | 120 | 0 | 0 |  | 0 | 140 |  |  |  | 9
2024-01-30 | 738 |  | 66424 | A | DONE | 14 | S-M |  | OLIV 6210030 - LV-11 |  | 2024-02-01 | Z | 2024-01-26 | 90 | 0 | 260 | F | 0 | 410 |  |  |  | 6
2024-01-30 | 739 | bth | 61124 - 61125 | A | DONE | 6 | S-M |  | OLIV 6210030 - Outs paint |  | 2024-02-01 | Z | 2024-01-26 | 120 | 20 | 0 |  | 20 | 160 |  |  |  | 6
2024-01-30 | 740 |  | 69467 | A | DONE | 2 | S |  | OLIV 6210030 - L2 Amenities |  | 2024-02-01 | Z | 2024-01-30 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-01-31 | 741 |  | 87749 | A | DONE | 2 | S |  | OLIV 6210030 - Pans |  | 2024-02-01 | Z | 2024-01-31 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-01-31 | 310 | w | 12924 | A | DONE | 2 | S |  | PP 10053746 - JBOX |  | 2024-02-05 | Z | 2024-01-29 | 50 | 0 | 0 |  | 0 | 160 |  |  |  | 7
2024-01-30 | 1236 |  | 62663 - 62665 | A | DONE | 13 | M |  | PROMEGA FEYNMAN 6220014 - AHU-14 / DH-A |  | 2024-01-31 | Z | 2024-01-19 | 320 | 0 | 0 |  | 0 | 690 |  |  |  | 12
2024-01-30 | 1237 |  | 62666 - 62668 | A | DONE | 9 | S-M | flex | PROMEGA FEYNMAN 6220014 - DH-B / RF-13 |  | 2024-01-31 | Z | 2024-01-19 | 180 | 0 | 30 | F | 0 | 230 |  |  |  | 12
2024-01-30 | 1238 |  | 62669 | A | DONE | 12 | S-M | pcd | PROMEGA FEYNMAN 6220014 - DH-A SA ss.flex |  | 2024-01-31 | Z | 2024-01-19 | 230 | 0 | 50 | F | 0 | 430 |  |  |  | 12
2024-01-30 | 1239 |  | 62670 - 62671 | A | DONE | 20 | M |  | PROMEGA FEYNMAN 6220014 - AHU-14 / DH-A |  | 2024-01-31 | Z | 2024-01-19 | 450 | 0 | 50 | F | 0 | 880 |  |  |  | 12
2024-01-30 | 1240 |  | 62672 | A | DONE | 13 | M |  | PROMEGA FEYNMAN 6220014 - DH-A |  | 2024-01-31 | Z | 2024-01-19 | 270 | 0 | 50 | F | 0 | 460 |  |  |  | 12
2024-01-30 | 2083 |  | 78815 | A | DONE | 6 | M |  | ROCK CO. JAIL 6220018 - Jail Admin. grille box paint |  | 2024-02-01 | Z | 2024-01-23 | 130 | 0 | 0 |  | 130 | 220 |  |  |  | 9
2024-01-30 | 2084 |  | 78816 | A | DONE | 4 | S |  | ROCK CO. JAIL 6220018 - Mech room 1" liner |  | 2024-02-01 | Z | 2024-01-24 | 80 | 0 | 0 |  | 20 | 140 |  |  |  | 8
2024-01-30 | 2085 |  | 78817 - 78818 | A | DONE | 27 | M |  | ROCK CO. JAIL 6220018 - Min. security / cell chase |  | 2024-02-01 | Z | 2024-01-24 | 140 | 0 | 530 | F | 0 | 1080 |  |  |  | 8
2024-01-29 | 2089 |  | 78824 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Tear drop hangers |  | 2024-02-01 | Z | 2024-01-29 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 3
2024-01-30 | 2094 |  | 78825 | A | DONE | 2 | S | BI | ROCK CO. JAIL 6220018 - Cooling tower |  | 2024-02-01 | Z | 2024-01-29 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 3
2024-01-30 | r2073 | w | 78761 | A | DONE | 2 | S | ss | ROCK CO. JAIL 6220018 - Kitchen Duct |  | 2024-02-08 | Z | 2024-01-29 | 30 | 0 | 0 |  | 0 | 110 |  |  |  | 10
2024-01-31 | 187 | bth | 70212 - 70214 | A | DONE | 15 | S-M |  | UBS 4230090 - VAV 4-1,2,3 1" liner |  | 2024-02-02 | Z | 2024-01-22 | 110 | 100 | 160 | F | 180 | 350 |  |  |  | 11
2024-01-30 | 2716 |  | 73390 | A | DONE | 2 | S |  | UWL-HSC 6230018 - VAV-41 LVL 3 |  | 2024-02-01 | Z | 2024-01-24 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 8
2024-01-29 | 5000 |  | 96536 | A | DONE | 2 | S | BI | UWSP ALBERTSON 6230016 - Caps |  | 2024-01-30 | Z | 2024-01-26 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 4
2024-02-01 | 1800 | bth | 2A-RA-1 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 40 | 40 | 0 |  | 20 | 90 |  |  |  | 23
2024-02-01 | 1801 | bth | 2A-RA-2 | A | DONE | 8 | S-M | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 180 | 20 | 0 |  | 130 | 230 |  |  |  | 23
2024-02-01 | 1802 |  | 2A-RA-3 | A | DONE | 21 | M | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 410 | 0 | 110 | F | 500 | 630 |  |  |  | 23
2024-02-01 | 1803 | bth | 2A-RA-4 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 50 | 50 | 0 |  | 40 | 120 |  |  |  | 23
2024-02-01 | 1804 | bth | 2A-RA-5 | A | DONE | 5 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 90 | 20 | 0 |  | 70 | 120 |  |  |  | 23
2024-02-01 | 1805 | bth | 2A-RA-6 | A | DONE | 2 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 20 | 20 | 0 |  | 20 | 40 |  |  |  | 23
2024-02-01 | 1806 | bth | 2A-RA-7 | A | DONE | 10 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 120 | 120 | 0 |  | 50 | 260 |  |  |  | 23
2024-02-01 | 1807 |  | 2A-RA-8 | A | DONE | 6 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 150 | 0 | 0 |  | 120 | 190 |  |  |  | 23
2024-02-01 | 1808 |  | 2A-RA-9 | A | DONE | 6 | S | flex | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 90 | 0 | 40 | F | 90 | 160 |  |  |  | 23
2024-02-01 | 1809 |  | 2A-RA-10 | A | DONE | 8 | S | neal | WCSD HERITAGE 6220024 - 1" liner |  | 2024-02-02 | Z | 2024-01-10 | 130 | 0 | 50 | F | 160 | 220 |  |  |  | 23
2024-02-01 | 1810 |  | 2A-RA-11 | A | DONE | 4 | S | neal | WCSD HERITAGE 6220024 - 1" liner , flex |  | 2024-02-02 | Z | 2024-01-10 | 100 | 0 | 0 |  | 70 | 120 |  |  |  | 23
2024-02-01 | 1811 |  | 2A-RA-12 | A | DONE | 10 | S | neal | WCSD HERITAGE 6220024 - 1" liner , flex |  | 2024-02-02 | Z | 2024-01-10 | 180 | 0 | 60 | F | 190 | 300 |  |  |  | 23
2024-01-31 | 1813 | bth | 2A-SA-1 | A | DONE | 12 | S-M |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 120 | 140 | 30 | F | 0 | 330 |  |  |  | 18
2024-01-31 | 1814 | bth | 2A-SA-2 | A | DONE | 16 | S-M |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 120 | 160 | 100 | F | 0 | 460 |  |  |  | 18
2024-01-31 | 1815 | bth | 2A-SA-3 | A | DONE | 12 | S-M | pt.neal | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 120 | 20 | 160 | F | 0 | 350 |  |  |  | 18
2024-01-31 | 1816 | bth | 2A-SA-4 | A | DONE | 16 | M | neal | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 170 | 70 | 160 | F | 0 | 490 |  |  |  | 18
2024-02-01 | 1817 | bth | 2A-SA-5 | A | DONE | 23 | M | neal | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 270 | 90 | 210 | F | 0 | 680 |  |  |  | 18
2024-02-01 | 1818 | bth | 2A-SA-6 | A | DONE | 6 | S |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 70 | 60 | 0 |  | 0 | 160 |  |  |  | 18
2024-01-31 | 1819 |  | 2A-SA-7 | A | DONE | 13 | S-M | neal | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 150 | 0 | 160 | F | 0 | 370 |  |  |  | 18
2024-01-31 | 1820 | bth | 2A-SA-8 | A | DONE | 7 | S-M |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 80 | 50 | 40 | F | 0 | 180 |  |  |  | 18
2024-01-31 | 1821 | bth | 2A-SA-9 | A | DONE | 5 | S |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 50 | 50 | 20 | F | 0 | 140 |  |  |  | 18
2024-02-01 | 1822 | bth | 2A-SA-10 | A | DONE | 4 | S |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 50 | 50 | 0 |  | 0 | 120 |  |  |  | 18
2024-02-01 | 1823 | bth | 2A-SA-11 | A | DONE | 10 | S |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 80 | 120 | 30 | F | 0 | 260 |  |  |  | 18
2024-02-01 | 1824 | bth | 2A-SA-12 | A | DONE | 5 | S |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 50 | 60 | 0 |  | 0 | 140 |  |  |  | 18
2024-01-31 | 1825 | bth | 2A-SA-13 | A | DONE | 12 | S-M |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 80 | 170 | 30 | F | 0 | 320 |  |  |  | 18
2024-02-01 | 1826 | bth | 2A-SA-14 | A | DONE | 3 | S |  | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 40 | 30 | 0 |  | 0 | 80 |  |  |  | 18
2024-02-01 | 1827 | bth | 2A-SA-15 | A | DONE | 9 | S | pt.neal | WCSD HERITAGE 6220024 - flex |  | 2024-02-02 | Z | 2024-01-15 | 120 | 70 | 30 | F | 0 | 260 |  |  |  | 18
2024-02-01 | 1828 | bth | 2A-SA-16 | A | DONE | 12 | S-M | neal | WCSD HERITAGE 6220024 |  | 2024-02-02 | Z | 2024-01-15 | 80 | 90 | 120 | F | 0 | 350 |  |  |  | 18
2024-02-01 | 1829 | bth | 2A-SA-17 | A | DONE | 16 | M | neal | WCSD HERITAGE 6220024 |  | 2024-02-02 | Z | 2024-01-15 | 170 | 130 | 100 | F | 0 | 460 |  |  |  | 18
2024-01-30 | 1851 |  | 68973 - 68974 | A | DONE | 3 | S | pt.neal | WCSD HERITAGE 6220024 - 1A-OA-7 , HP 160 RA |  | 2024-01-31 | Z | 2024-01-24 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 7
2024-01-31 | 1852 |  | 57765 | A | DONE | 3 | S-M |  | WCSD HERITAGE 6220024 - E. Sect. TA 1" liner paint |  | 2024-02-02 | Z | 2024-01-25 | 60 | 0 | 0 |  | 30 | 80 |  |  |  | 8
2024-01-31 | 1853 |  | 57766 | A | DONE | 3 | S-M | flex | WCSD HERITAGE 6220024 - Misc MOD |  | 2024-02-02 | Z | 2024-01-25 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 8
2024-01-30 | 1854 | sp | 57767 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - 1A Bathroom |  | 2024-02-02 | Z | 2024-01-25 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 8
2024-01-30 | 1855 | w | 34150 | A | DONE | n/a | S |  | WCSD HERITAGE 6220024 - A-section OA |  | 2024-02-02 | Z | 2024-01-26 | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 7
2024-02-01 | 1858 |  | 70521 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - Taps |  | 2024-02-02 | Z | 2024-01-31 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 2
[6 empty] | 888 | [13 empty] | 28990 |  |  |  | 8790 | 30.32%
WEEK OF 2-5-2024
2024-02-09 | 207 |  | 70601 | A | DONE | 2 | S |  | ACADIA 8230013 - Flashing |  | 2024-02-13 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-02-05 | 3908 |  | BSMT-C-RAD-010 | A | DONE | 13 | M | neal | CDIS 6220028 - bird.s |  | 2024-02-06 | Z | 2024-01-10 | 310 | 0 | 0 |  | 0 | 650 |  |  |  | 27 |  | 2024-02-22
2024-02-05 | 3911 |  | BSMT-C-SALP-019 | A | DONE | 2 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-06 | Z | 2024-01-10 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 27 |  | 2024-02-22
2024-02-05 | 3912 |  | BSMT-C-SALP-020 | A | DONE | 2 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-06 | Z | 2024-01-10 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 27 |  | 2024-02-22
2024-02-05 | 3913 |  | BSMT-C-SALP-021 | A | DONE | 2 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-06 | Z | 2024-01-10 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 27 |  | 2024-02-22
2024-02-05 | 3914 |  | BSMT-C-SALP-022 | A | DONE | 2 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-06 | Z | 2024-01-10 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 27 |  | 2024-02-22
2024-02-05 | 3915 | bth | BSMT-C-SALP-023 | A | DONE | 3 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-06 | Z | 2024-01-10 | 40 | 20 | 0 |  | 20 | 50 |  |  |  | 27 |  | 2024-02-22
2024-02-06 | 3919 |  | L1-B-RAD-001 | A | DONE | 41 | M-L |  | CDIS 6220028 - 1" DW |  | 2024-02-06 | Z | 2024-01-18 | 1020 | 0 | 0 |  | 430 | 1450 |  |  |  | 19 |  | 2024-02-22
2024-02-05 | 3920 | bth | L1-B-RAD-002 | A | DONE | 17 | M |  | CDIS 6220028 |  | 2024-02-06 | Z | 2024-01-18 | 270 | 70 | 80 | F | 0 | 570 |  |  |  | 19 |  | 2024-02-22
2024-02-06 | 3921 | bth | L1-B-RAD-003 | A | DONE | 26 | S-M |  | CDIS 6220028 - 1" DW |  | 2024-02-06 | Z | 2024-01-18 | 500 | 20 | 110 | F | 270 | 690 |  |  |  | 19 |  | 2024-02-22
2024-02-05 | 3922 | bth | L1-B-RAD-004 | A | DONE | 10 | S |  | CDIS 6220028 |  | 2024-02-06 | Z | 2024-01-18 | 70 | 30 | 150 | F | 0 | 390 |  |  |  | 19 |  | 2024-02-22
2024-02-06 | 3923 |  | L1-B-SAMP-001 | A | DONE | 34 | M-L |  | CDIS 6220028 - 1" DW |  | 2024-02-06 | Z | 2024-01-18 | 740 | 0 | 110 | F | 250 | 1270 |  |  |  | 19 |  | 2024-02-22
2024-02-06 | 3924 |  | L1-B-SAMP-002 | A | DONE | 22 | M |  | CDIS 6220028 - 1" DW |  | 2024-02-06 | Z | 2024-01-18 | 400 | 0 | 150 | F | 100 | 820 |  |  |  | 19 |  | 2024-02-22
2024-02-05 | 3925 | bth | L1-B-SAMP-003 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-02-06 | Z | 2024-01-18 | 130 | 30 | 160 | F | 0 | 430 |  |  |  | 19 |  | 2024-02-22
2024-02-05 | 3926 | bth | L1-B-SAMP-004 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-02-06 | Z | 2024-01-18 | 230 | 40 | 40 | F | 0 | 370 |  |  |  | 19 |  | 2024-02-22
2024-02-05 | 3927 | bth | L1-B-SAMP-005 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-02-06 | Z | 2024-01-18 | 210 | 40 | 120 | F | 0 | 490 |  |  |  | 19 |  | 2024-02-22
2024-02-05 | 3928 | bth | L1-B-SAMP-006 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-02-06 | Z | 2024-01-18 | 160 | 30 | 100 | F | 0 | 350 |  |  |  | 19 |  | 2024-02-22
2024-02-07 | 3932 |  | L1-B-EAD-001 | A | DONE | 20 | M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 500 | 0 | 0 |  | 0 | 1000 |  |  |  | 16 |  | 2024-02-29
2024-02-07 | 3933 |  | L1-B-EAD-002 | A | DONE | 20 | M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 280 | 0 | 200 | F | 0 | 680 |  |  |  | 16 |  | 2024-02-29
2024-02-07 | 3934 |  | L1-B-EAD-005 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 50 | 0 | 140 | F | 0 | 240 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3935 | bth | L1-B-EAD-006 | A | DONE | 5 | S | pt.neal | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 90 | 20 | 0 |  | 0 | 160 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3936 |  | L1-B-EAD-007 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 120 | 0 | 50 | F | 0 | 260 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3937 | bth | L1-B-EAD-008 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 180 | 40 | 30 | F | 0 | 290 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3938 | bth | L1-B-EAD-010 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 190 | 40 | 0 |  | 0 | 280 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3939 | bth | L1-B-EAD-013 | A | DONE | 16 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 260 | 20 | 120 | F | 0 | 460 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3940 |  | L1-B-EAD-015 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 100 | 0 | 110 | F | 0 | 250 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3941 | bth | L1-B-EAD-016 | A | DONE | 7 | S | neal | CDIS 6220028 - paint |  | 2024-02-09 | Z | 2024-01-24 | 80 | 20 | 70 | F | 0 | 250 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3942 |  | L1-B-SAMP-008 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 40 | 20 | 40 | F | 0 | 160 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3943 | bth | L1-B-SAMP-009 | A | DONE | 16 | M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 340 | 20 | 40 | F | 0 | 590 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3944 |  | L1-B-SAMP-010 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 70 | 0 | 40 | F | 0 | 130 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3945 | bth | L1-B-SAMP-011 | A | DONE | 4 | S-M | neal | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 40 | 20 | 40 | F | 0 | 120 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3946 | bth | L1-B-SAMP-012 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 100 | 50 | 40 | F | 0 | 250 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3947 |  | L1-B-SAMP-013 | A | DONE | 32 | M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 650 | 20 | 120 | F | 0 | 1300 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3948 |  | L1-B-SAMP-014 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 250 | 0 | 40 | F | 0 | 410 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3949 | bth | L1-B-SAMP-015 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 210 | 30 | 80 | F | 0 | 560 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3950 | bth | L1-B-SAMP-016 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 180 | 20 | 120 | F | 0 | 430 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3951 | bth | L1-B-SAMP-017 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 80 | 20 | 40 | F | 0 | 180 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3952 | bth | L1-B-SAMP-018 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-24 | 20 | 20 | 110 | F | 0 | 160 |  |  |  | 16 |  | 2024-02-29
2024-02-09 | 3976 |  | L1-B-SAMP-007 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-02-09 | Z | 2024-01-29 | 140 | 0 | 80 | F | 0 | 260 |  |  |  | 11 |  | 2024-02-29
2024-02-05 | 2334 | sp | 70522 | A | DONE | 2 | S |  | DEWITT LAW 6230021 - Misc |  | 2024-02-05 | Z | 2024-02-05 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 0
2024-02-09 | 1693 |  | 62513 - 62514 | A | DONE | 7 | S-M |  | EXACT BIOSAFE 6230005 - RTU Drop |  | 2024-02-13 | Z | 2024-01-24 | 160 | 0 | 0 |  | 0 | 330 |  |  |  | 20
2024-02-05 | 2693 | bth | 42649 | A | DONE | 3 | S-M | pt.neal | HEALTH SERV. 6230004 - Misc |  | 2024-02-06 | Z | 2024-02-02 | 50 | 20 | 0 |  | 0 | 70 |  |  |  | 4
2024-02-09 | 2694 |  | 42650 | A | DONE | 2 | S-M |  | HEALTH SERV. 6230004 - Basement finishes paint |  | 2024-02-13 | Z | 2024-02-02 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 11
2024-02-05 | 2695 |  | 66652 | A | DONE | 2 | S |  | HEALTH SERV. 6230004 - AHU 6-1 SA tie in |  | 2024-02-06 | Z | 2024-02-05 | 20 | 0 | 0 |  | 0 | 70 |  |  |  | 1
2024-02-09 | 2696 |  | 66653 | A | DONE | 2 | S |  | HEALTH SERV. 6230004 - LL Misc |  | 2024-02-13 | Z | 2024-02-06 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 7
2024-02-09 | 2698 |  | 66655 | A | DONE | 2 | S | neal | HEALTH SERV. 6230004 - Angles |  | 2024-02-13 | Z | 2024-02-08 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 5
2024-02-09 | 2803 |  | 70805 - 70806 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 - Pool RA , SA 1" liner |  | 2024-02-15 | Z | 2024-01-29 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 17
2024-02-05 | 199 | bth | 69384 | A | DONE | 7 | S-M |  | KL ENGINEERING 4240002 - Misc |  | 2024-02-07 | Z | 2024-01-31 | 140 | 20 | 0 |  | 0 | 140 |  |  |  | 7
2024-02-07 | 3718 |  | 63346 - 63347 | A | DONE | 2 | S-M |  | KOHL CENTER 6210034 - Finishes paint |  | 2024-02-08 | Z | 2024-02-07 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 1
2024-02-05 | 3717 |  | 67652 | A | DONE | 2 | S |  | KOHL CENTER 8210034 - Sleeve |  | 2024-02-07 | Z | 2024-02-02 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 5
2024-02-06 | 203 |  | 70523 | A | DONE | 6 | S | ss | MCPASD WEST CLINIC 8230023 - Misc |  | 2024-02-06 | Z | 2024-02-06 | 150 | 0 | 0 |  | 0 | 200 |  |  |  | 0
2024-02-09 | 772 |  | 68530 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 - Stadium bathroom flex |  | 2024-02-13 | Z | 2024-02-07 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-02-09 | 202 | bth | 70272 - 70273 | A | DONE | 18 | S-M |  | NATE K. E363 - Furnace |  | 2024-02-09 | Z | 2024-02-05 | 100 | 120 | 230 | F | 0 | 410 |  |  |  | 4
2024-02-07 | 742 | bth | 69468 , 69470 | A | DONE | 8 | S | flex | OLIV 6210030 - Maintenance office |  | 2024-02-08 | Z | 2024-02-05 | 60 | 120 | 0 |  | 0 | 160 |  |  |  | 3
2024-02-07 | 743 | bth | 69469 | A | DONE | 5 | S | flex | OLIV 6210030 - Maintenance SA |  | 2024-02-08 | Z | 2024-02-05 | 40 | 70 | 0 |  | 0 | 120 |  |  |  | 3
2024-02-06 | 744 |  | 61126 | A | DONE | 5 | S |  | OLIV 6210030 - Misc |  | 2024-02-08 | Z | 2024-02-05 | 40 | 0 | 70 | F | 0 | 120 |  |  |  | 3
2024-02-06 | 745 |  | 69471 | A | DONE | 2 | S |  | OLIV 6210030 - L10 C-corridor |  | 2024-02-08 | Z | 2024-02-06 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 2
2024-02-05 | 1620 | sp | 66905 | A | DONE | 2 | S | neal | PROMEGA CMC 6230010 - Hood tie in |  | 2024-02-05 | Z | 2024-02-05 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 0
2024-02-06 | 1242 |  | 62673 - 62674 | A | DONE | 3 | S-M |  | PROMEGA FEYNMAN 6220014 - DH-B OA / RA |  | 2024-02-07 | Z | 2024-01-23 | 60 | 0 | 0 |  | 0 | 90 |  |  |  | 15
2024-02-06 | 1243 |  | 62676 - 62677 | A | DONE | 6 | S-M |  | PROMEGA FEYNMAN 6220014 - DH-B SA / Relief |  | 2024-02-07 | Z | 2024-01-23 | 100 | 30 | 0 |  | 0 | 140 |  |  |  | 15
2024-02-06 | 1244 | w | 62678 , 62680 | A | DONE | 4 | S-M | ss | PROMEGA FEYNMAN 6220014 - DH-A,B EA |  | 2024-02-07 | Z | 2024-01-23 | 100 | 0 | 0 |  | 0 | 250 |  |  |  | 15
2024-02-05 | 1245 | sp | 62679 | A | DONE | 4 | S-M |  | PROMEGA FEYNMAN 6220014 - DH-A Relief |  | 2024-02-07 | Z | 2024-01-23 | 60 | 40 | 0 |  | 0 | 120 |  |  |  | 15
2024-02-05 | 1246 |  | 62681 | A | DONE | 9 | S-M |  | PROMEGA FEYNMAN 6220014 - AHU 13 SA |  | 2024-02-07 | Z | 2024-01-30 | 220 | 0 | 0 |  | 0 | 470 |  |  |  | 8
2024-02-06 | 1247 |  | 62683 | A | DONE | 4 | S-M |  | PROMEGA FEYNMAN 6220014 - RF |  | 2024-02-07 | Z | 2024-01-30 | 180 | 0 | 0 |  | 0 | 460 |  |  |  | 8
2024-02-05 | 2241 |  | 66904 | A | DONE | 2 | S | neal | PROMEGA KEPLER 6210031 - Misc |  | 2024-02-07 | Z | 2024-02-05 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 2
2024-02-06 | 2086 |  | 78819 - 78821 | A | DONE | 7 | S-M |  | ROCK CO. JAIL 6220018 - Mech room VAV |  | 2024-02-08 | Z | 2024-01-25 | 90 | 0 | 70 | F | 0 | 210 |  |  |  | 14
2024-02-06 | 2087 |  | 78822 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Cell chase 1" liner |  | 2024-02-08 | Z | 2024-01-25 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 14
2024-02-06 | 2088 |  | 78823 | A | DONE | 5 | S |  | ROCK CO. JAIL 6220018 - Mech room EA |  | 2024-02-08 | Z | 2024-01-25 | 120 | 0 | 0 |  | 0 | 210 |  |  |  | 14
2024-02-05 | 2090 | w | 22342 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Roof Cap |  | 2024-02-08 | Z | 2024-01-29 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 10
2024-02-06 | 2091 |  | 72365 - 72366 | A | DONE | 5 | S |  | ROCK CO. JAIL 6220018 - B-section exh |  | 2024-02-08 | Z | 2024-01-29 | 120 | 0 | 0 |  | 0 | 160 |  |  |  | 10
2024-02-06 | 2092 |  | 72367 - 72368 | A | DONE | 8 | S-M |  | ROCK CO. JAIL 6220018 - B-section exh |  | 2024-02-08 | Z | 2024-01-29 | 200 | 0 | 0 |  | 0 | 240 |  |  |  | 10
2024-02-06 | 2093 |  | 37400 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Jail admin. |  | 2024-02-08 | Z | 2024-01-29 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 10
2024-02-06 | 2095 |  | 78826 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Mech room |  | 2024-02-08 | Z | 2024-01-30 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 9
2024-02-06 | 2096 |  | AHU-6J-7J OA | A | DONE | 14 | S-M |  | ROCK CO. JAIL 6220018 |  | 2024-02-08 | Z | 2024-01-30 | 330 | 0 | 0 |  | 0 | 430 |  |  |  | 9
2024-02-07 | 2097 | bth | AHU-6J-7J SA | A | DONE | 18 | S-M |  | ROCK CO. JAIL 6220018 |  | 2024-02-08 | Z | 2024-01-30 | 220 | 220 | 0 |  | 0 | 530 |  |  |  | 9
2024-02-06 | 2098 |  | 72369 | A | DONE | 2 | S | neal | ROCK CO. JAIL 6220018 - FG Flashing |  | 2024-02-08 | Z | 2024-02-01 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-02-06 | 2099 | sp | 78827 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Misc |  | 2024-02-08 | Z | 2024-02-05 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 3
2024-02-06 | 4700 |  | 78852 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Jail admin. paint |  | 2024-02-08 | Z | 2024-02-05 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 3
2024-02-06 | 4701 |  | 78828 | A | DONE | 2 | S | alum | ROCK CO. JAIL 6220018 - Cell chase |  | 2024-02-07 | Z | 2024-02-05 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-02-07 | 195 | sp | 78704 - 78705 | A | DONE | 10 | M |  | THERMO FISHER 10053401 - Lab 4101 , snorkel 2,3 |  | 2024-02-09 | Z | 2024-01-29 | 50 | 180 | 0 |  | 0 | 200 |  |  |  | 11
2024-02-07 | 196 | sp | 78706 - 78707 | A | DONE | 6 | M |  | THERMO FISHER 10053401 - Snorkel 5-6 , Hood |  | 2024-02-09 | Z | 2024-01-29 | 20 | 130 | 0 |  | 0 | 130 |  |  |  | 11
2024-02-06 | 204 |  | 70216 | A | DONE | 2 | S |  | UBS 4230090 - Misc |  | 2024-02-07 | Z | 2024-02-06 | 20 | 0 | 0 |  | 0 | 80 |  |  |  | 1
2024-02-05 | 198 |  | 67871 | A | DONE | 2 | S |  | UW-CHILLER 6230008 - Roof Flashing |  | 2024-02-07 | Z | 2024-01-30 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 8
2024-02-09 | 2772 | w | 72664 - 72665 | A | DONE | 2 | S-M | ss | UW-VET MED 2230012 - BSL-3 |  | 2024-02-12 | Z | 2024-01-29 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 14
2024-02-09 | 2775 | w | 72670 - 72672 | A | DONE | 2 | S | ss | UW-VET MED 2230012 - BSL-6 |  | 2024-02-12 | Z | 2024-01-29 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 14
2024-02-07 | 2776 |  | 72673 | A | DONE | 2 | S |  | UW-VET MED 2230012 - Flashing |  | 2024-02-12 | Z | 2024-01-31 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 12
2024-02-09 | 2777 |  | 72674 | A | DONE | 2 | S-M | pcd | UW-VET MED 6210014 - 3rd Floor |  | 2024-02-12 | Z | 2024-02-01 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 11
2024-02-09 | 2778 | bth | 72675 | A | DONE | 3 | S-M |  | UW-VET MED 2230012 - RM 3937 1" liner |  | 2024-02-12 | Z | 2024-02-05 | 30 | 40 | 0 |  | 20 | 70 |  |  |  | 7
2024-02-09 | 2779 |  | 72676 | A | DONE | 2 | S |  | UW-VET MED 6210014 - 3rd Floor 1" liner |  | 2024-02-12 | Z | 2024-02-08 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 4
2024-02-06 | 1830 |  | 2A-DOAS-3 | A | DONE | 22 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 390 | 0 | 150 | F | 0 | 690 |  |  |  | 25
2024-02-07 | 1831 | bth | 2A-EA-1 | A | DONE | 4 | S |  | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 30 | 30 | 40 | F | 0 | 120 |  |  |  | 25
2024-02-07 | 1832 | bth | 2A-EA-2 | A | DONE | 23 | M | neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 160 | 50 | 360 | F | 0 | 690 |  |  |  | 25
2024-02-07 | 1833 | sp | 2A-EA-3 | A | DONE | 22 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 70 | 460 | 0 |  | 0 | 620 |  |  |  | 25
2024-02-07 | 1834 | bth | 2A-EA-4 | A | DONE | 21 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 90 | 220 | 200 | F | 0 | 600 |  |  |  | 25
2024-02-07 | 1835 | bth | 2A-EA-5 | A | DONE | 8 | S | neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 20 | 120 | 50 | F | 0 | 200 |  |  |  | 25
2024-02-07 | 1836 | bth | 2A-OA-1 | A | DONE | 26 | M | neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 110 | 230 | 290 | F | 0 | 770 |  |  |  | 25
2024-02-07 | 1837 | bth | 2A-OA-2 | A | DONE | 29 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 230 | 180 | 300 | F | 0 | 870 |  |  |  | 25
2024-02-09 | 1838 | bth | 2A-OA-3 | A | DONE | 20 | S-M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 140 | 200 | 140 | F | 0 | 570 |  |  |  | 25
2024-02-09 | 1839 | bth | 2A-OA-4 | A | DONE | 22 | M | pt.neal | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 150 | 290 | 100 | F | 0 | 640 |  |  |  | 25
2024-02-07 | 1840 |  | 2A-OA-5 | A | DONE | 30 | M-L |  | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 480 | 0 | 260 | F | 0 | 1320 |  |  |  | 25
2024-02-07 | 1841 |  | 2A-OA-6 | A | DONE | 6 | S |  | WCSD HERITAGE 6220024 |  | 2024-02-09 | Z | 2024-01-15 | 150 | 0 | 0 |  | 0 | 240 |  |  |  | 25
2024-02-09 | 1842 | sp | 2B-SALP-1 | A | DONE | 42 | M-L | neal | WCSD HERITAGE 6220024 - s.mates |  | 2024-02-09 | Z | 2024-01-16 | 200 | 830 | 0 |  | 0 | 1370 |  |  |  | 24
2024-02-09 | 1843 | sp | 2B-SALP-2 | A | DONE | 44 | M-L | neal | WCSD HERITAGE 6220024 - s.mates |  | 2024-02-09 | Z | 2024-01-16 | 190 | 910 | 0 |  | 0 | 1480 |  |  |  | 24
2024-02-06 | 1856 | bth | 57768 - 57769 | A | DONE | 4 | S-M |  | WCSD HERITAGE 6220024 - 1D 1" liner |  | 2024-02-09 | Z | 2024-01-29 | 100 | 0 | 0 |  | 70 | 110 |  |  |  | 11
2024-02-06 | 1857 | bth | 57770 - 57771 | A | DONE | 6 | S-M |  | WCSD HERITAGE 6220024 - 1C 1" liner |  | 2024-02-09 | Z | 2024-01-29 | 110 | 20 | 0 |  | 80 | 150 |  |  |  | 11
2024-02-06 | 1859 | bth | 57775 | A | DONE | 2 | S | neal | WCSD HERITAGE 6220024 - OA-5 |  | 2024-02-09 | Z | 2024-02-01 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 8
2024-02-06 | 1860 | bth | 57776 | A | DONE | 3 | S |  | WCSD HERITAGE 6220024 - Misc |  | 2024-02-09 | Z | 2024-02-01 | 60 | 0 | 0 |  | 0 | 110 |  |  |  | 8
[6 empty] | 1023 | [13 empty] | 33070 |  |  |  | 5470 | 16.54%
WEEK OF 2-12-2024
2024-02-14 | 1901 |  | 70048 | A | DONE | 2 | S |  | ALDEVRON 2230053 - sq. to rounds |  | 2024-02-26 | Z | 2024-01-25 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 32
2024-02-13 | 1720 |  | 78953 | A | DONE | 2 | S |  | BLACKHAWK BTC 6230025 - Fin tube louver |  | 2024-02-15 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-02-12 | 3953 | bth | L1-B-EAD-003 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 60 | 20 | 0 |  | 0 | 90 |  |  |  | 15
2024-02-12 | 3954 | bth | L1-B-EAD-004 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 40 | 20 | 0 |  | 0 | 60 |  |  |  | 15
2024-02-12 | 3955 | bth | L1-B-EAD-009 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 180 | 20 | 120 | F | 0 | 380 |  |  |  | 15
2024-02-12 | 3956 | bth | L1-B-EAD-011 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 170 | 20 | 140 | F | 0 | 370 |  |  |  | 15
2024-02-12 | 3957 | bth | L1-B-EAD-012 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 140 | 20 | 30 | F | 0 | 220 |  |  |  | 15
2024-02-12 | 3958 |  | L1-B-EAD-014 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 190 | 0 | 110 | F | 0 | 360 |  |  |  | 15
2024-02-12 | 3959 |  | L1-B-SALP-019 | A | DONE | 3 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-13 | Z | 2024-01-29 | 70 | 0 | 0 |  | 40 | 90 |  |  |  | 15
2024-02-12 | 3960 |  | L1-B-SALP-020 | A | DONE | 4 | S |  | CDIS 6220028 - 1" liner |  | 2024-02-13 | Z | 2024-01-29 | 100 | 0 | 0 |  | 60 | 120 |  |  |  | 15
2024-02-12 | 3961 |  | L1-B-SALP-021 | A | DONE | 7 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-13 | Z | 2024-01-29 | 130 | 0 | 40 | F | 0 | 200 |  |  |  | 15
2024-02-12 | 3962 |  | L1-B-SALP-022 | A | DONE | 2 | S | neal | CDIS 6220028 - 1" liner paint |  | 2024-02-13 | Z | 2024-01-29 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 15
2024-02-12 | 3963 | bth | L1-B-SALP-023 | A | DONE | 9 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-13 | Z | 2024-01-29 | 130 | 20 | 70 | F | 60 | 240 |  |  |  | 15
2024-02-12 | 3964 |  | L1-B-SALP-024 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 100 | 0 | 70 | F | 0 | 210 |  |  |  | 15
2024-02-12 | 3965 | bth | L1-B-SALP-025 | A | DONE | 8 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-13 | Z | 2024-01-29 | 120 | 20 | 50 | F | 50 | 200 |  |  |  | 15
2024-02-12 | 3966 |  | L1-B-SALP-026 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 130 | 0 | 50 | F | 0 | 200 |  |  |  | 15
2024-02-12 | 3967 |  | L1-B-SALP-027 | A | DONE | 6 | S |  | CDIS 6220028 - 1" liner |  | 2024-02-13 | Z | 2024-01-29 | 80 | 0 | 70 | F | 30 | 180 |  |  |  | 15
2024-02-13 | 3968 | bth | L1-B-SALP-028 | A | DONE | 8 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-13 | Z | 2024-01-29 | 120 | 70 | 0 |  | 30 | 200 |  |  |  | 15
2024-02-12 | 3969 |  | L1-B-SALP-029 | A | DONE | 6 | S |  | CDIS 6220028 - 1" liner |  | 2024-02-13 | Z | 2024-01-29 | 130 | 0 | 20 | F | 30 | 180 |  |  |  | 15
2024-02-12 | 3970 |  | L1-B-SALP-030 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 100 | 0 | 140 | F | 0 | 290 |  |  |  | 15
2024-02-12 | 3971 |  | L1-B-SALP-031 | A | DONE | 8 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-13 | Z | 2024-01-29 | 200 | 0 | 0 |  | 40 | 240 |  |  |  | 15
2024-02-12 | 3972 |  | L1-B-SALP-032 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 70 | 0 | 100 | F | 0 | 200 |  |  |  | 15
2024-02-12 | 3973 |  | L1-B-SALP-033 | A | DONE | 10 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-13 | Z | 2024-01-29 | 140 | 0 | 100 | F | 70 | 280 |  |  |  | 15
2024-02-13 | 3974 |  | L1-B-SALP-034 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-02-13 | Z | 2024-01-29 | 180 | 0 | 160 | F | 0 | 400 |  |  |  | 15
2024-02-14 | 3977 |  | L1-A-EAD-017 | A | DONE | 17 | M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 300 | 0 | 120 | F | 0 | 840 |  |  |  | 17
2024-02-14 | 3978 | bth | L1-A-EAD-018 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 - paint |  | 2024-02-16 | Z | 2024-01-30 | 50 | 40 | 20 | F | 0 | 120 |  |  |  | 17
2024-02-13 | 3979 | sp | L1-A-EAD-019 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 20 | 70 | 0 |  | 0 | 70 |  |  |  | 17
2024-02-14 | 3980 | bth | L1-A-EAD-020 | A | DONE | 3 | S-M | pt.neal | CDIS 6220028 - paint |  | 2024-02-16 | Z | 2024-01-30 | 30 | 30 | 0 |  | 0 | 70 |  |  |  | 17
2024-02-14 | 3981 | bth | L1-A-EAD-023 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 130 | 80 | 70 | F | 0 | 320 |  |  |  | 17
2024-02-14 | 3982 | bth | L1-A-EAD-027 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 190 | 30 | 0 |  | 0 | 280 |  |  |  | 17
2024-02-14 | 3983 |  | L1-A-EAD-031 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 240 | 0 | 0 |  | 0 | 350 |  |  |  | 17
2024-02-14 | 3984 | bth | L1-A-EAD-033 | A | DONE | 13 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-16 | Z | 2024-01-30 | 120 | 90 | 100 | F | 0 | 370 |  |  |  | 17
2024-02-14 | 3985 | bth | L1-A-EAD-034 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 130 | 20 | 40 | F | 0 | 230 |  |  |  | 17
2024-02-13 | 3986 | sp | L1-A-EAD-038 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 20 | 100 | 0 |  | 0 | 130 |  |  |  | 17
2024-02-14 | 3987 | bth | L1-A-EAD-041 | A | DONE | 18 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 280 | 40 | 120 | F | 0 | 520 |  |  |  | 17
2024-02-14 | 3988 | bth | L1-A-EAD-042 | A | DONE | 16 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 340 | 40 | 0 |  | 0 | 460 |  |  |  | 17
2024-02-14 | 3989 | bth | L1-A-EAD-043 | A | DONE | 20 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 330 | 30 | 120 | F | 0 | 640 |  |  |  | 17
2024-02-13 | 3990 | sp | L1-A-EAD-044 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 20 | 130 | 0 |  | 0 | 160 |  |  |  | 17
2024-02-14 | 3991 | bth | L1-A-SAMP-035 | A | DONE | 23 | M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 480 | 30 | 60 | F | 0 | 850 |  |  |  | 17
2024-02-14 | 3992 | sp | L1-A-SAMP-036 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 20 | 80 | 0 |  | 0 | 100 |  |  |  | 17
2024-02-14 | 3993 | bth | L1-A-SAMP-037 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 120 | 50 | 0 |  | 0 | 190 |  |  |  | 17
2024-02-14 | 3994 | bth | L1-A-SAMP-038 | A | DONE | 24 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 290 | 20 | 280 | F | 0 | 1070 |  |  |  | 17
2024-02-15 | 3995 | bth | L1-A-SAMP-039 | A | DONE | 20 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 170 | 70 | 240 | F | 0 | 710 |  |  |  | 17
2024-02-15 | 3996 |  | L1-A-SAMP-040 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 200 | 0 | 0 |  | 0 | 340 |  |  |  | 17
2024-02-15 | 3997 | bth | L1-A-SAMP-041 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 120 | 20 | 40 | F | 0 | 230 |  |  |  | 17
2024-02-14 | 3998 | sp | L1-A-SAMP-042 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-02-16 | Z | 2024-01-30 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 17
2024-02-16 | 4001 |  | L1-A-EAD-022 | A | DONE | 31 | M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 530 | 0 | 230 | F | 0 | 1360 |  |  |  | 18
2024-02-12 | 4031 |  | 61422 | A | DONE | 4 | S-M |  | CDIS 6220028 - 2nd Floor B sleeves |  | 2024-02-16 | Z | 2024-02-06 | 80 | 0 | 0 |  | 0 | 130 |  |  |  | 10
2024-02-12 | 4052 |  | 61456 | A | DONE | 2 | S |  | CDIS 6220028 - Sleeves |  | 2024-02-12 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-02-15 | 4053 |  | 57938 | A | DONE | 2 | S |  | CDIS 6220028 - Basement outs |  | 2024-02-23 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 11
2024-02-13 | 4054 |  | 96541 | A | DONE | 2 | S | BI | CDIS 6220028 - Caps |  | 2024-02-15 | Z | 2024-02-13 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 2
2024-02-15 | 4094 |  | 61424 | A | DONE | 2 | S-M |  | CDIS 6220028 - End caps |  | 2024-02-19 | Z | 2024-02-14 | 50 | 0 | 0 |  | 0 | 120 |  |  |  | 5
2024-02-14 | 1266 |  | 70049 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 - CB-1 Register box paint |  | 2024-02-19 | Z | 2024-02-13 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 6
2024-02-15 | 1561 |  | 21524 | A | DONE | 2 | S |  | EMBASSY SUITES - Panel cover |  | 2024-02-16 | Z | 2024-02-14 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-02-12 | 1694 |  | 62515 | A | DONE | 4 | S-M |  | EXACT BIOSAFE 6230005 - EF Drop BD dampers |  | 2024-02-13 | Z | 2024-01-24 | 90 | 0 | 0 |  | 0 | 140 |  |  |  | 20
2024-02-15 | 1695 |  | 72498 | A | DONE | 2 | S | flex | EXACT BIO SAFE 6230005 - EF-2 |  | 2024-02-20 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 8
2024-02-16 | 1696 |  | 61023 | A | DONE | 8 | S |  | EXACT BIO SAFE 6230005 - TL-2 |  | 2024-02-20 | Z | 2024-02-12 | 180 | 0 | 0 |  | 0 | 260 |  |  |  | 8
2024-02-15 | 1697 |  | 72499 - 724500 | A | DONE | 10 | S-M | flex | EXACT BIO SAFE 6230005 - BCU 1662 |  | 2024-02-20 | Z | 2024-02-12 | 250 | 0 | 0 |  | 0 | 310 |  |  |  | 8
2024-02-15 | 1383 |  | 73392 | A | DONE | 2 | S |  | GTCH 6220003 - Misc |  | 2024-02-20 | Z | 2024-02-06 | 30 | 0 | 0 |  | 0 | 100 |  |  |  | 14
2024-02-12 | 2697 | sp | 66654 | A | DONE | 2 | S | ss | HEALTH SERV. 6230004 - Kitchen hood EA bird.s |  | 2024-02-13 | Z | 2024-02-06 | 30 | 20 | 0 |  | 0 | 40 |  |  |  | 7
2024-02-12 | 2699 |  | 68392 - 68393 | A | DONE | 2 | S | ss | HEALTH SERV. 6230004 - Misc |  | 2024-02-13 | Z | 2024-02-12 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 1
2024-02-15 | 3820 |  | 68394 | A | DONE | 2 | S | ss | HEALTH SERV. 6230004 - Corner trim |  | 2024-02-20 | Z | 2024-02-14 | 30 | 0 | 0 |  | 0 | 70 |  |  |  | 6
2024-02-15 | 3719 |  | 55187 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Flat stock |  | 2024-02-16 | Z | 2024-02-15 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-02-15 | 1937 |  | 67418 | A | DONE | 15 | S-M | vav's | MENDOTA FOOD 6220027 - Basement VAV 1" liner |  | 2024-02-22 | Z | 2024-01-22 | 360 | 0 | 0 |  | 230 | 430 |  |  |  | 31
2024-02-13 | 1939 |  | 67420 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 - TG-3 Elec. 1" liner |  | 2024-02-22 | Z | 2024-01-25 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 28
2024-02-13 | 206 | sp | 70276 | A | DONE | 3 | S |  | OAK WOOD WEST 10050055 - Heat pump RA |  | 2024-02-14 | Z | 2024-02-08 | 30 | 30 | 0 |  | 0 | 60 |  |  |  | 6
2024-02-13 | 746 |  | 69472 | A | DONE | 3 | S |  | OLIV 6210030 - DOAS |  | 2024-02-15 | Z | 2024-02-07 | 70 | 0 | 0 |  | 0 | 120 |  |  |  | 8
2024-02-13 | 747 |  | 69473 - 69474 | A | DONE | 18 | S-M |  | OLIV 6210030 - Roof |  | 2024-02-15 | Z | 2024-02-07 | 270 | 0 | 180 | F | 0 | 610 |  |  |  | 8
2024-02-13 | 748 |  | 61127 | A | DONE | 2 | S | flex | OLIV 6210030 - SF-5 |  | 2024-02-15 | Z | 2024-02-07 | 50 | 0 | 0 |  | 0 | 80 |  |  |  | 8
2024-02-15 | 2600 |  | 69477 | A | DONE | 6 | S-M |  | OLIV 6210030 - Stair pressurization |  | 2024-02-22 | Z | 2024-02-12 | 150 | 0 | 0 |  | 0 | 180 |  |  |  | 10
2024-02-16 | 2601 | sp | 69478 | A | DONE | 23 | S-M |  | OLIV 6210030 - Stair pressurization |  | 2024-02-22 | Z | 2024-02-12 | 210 | 350 | 0 |  | 0 | 660 |  |  |  | 10
2024-02-14 | 2602 | bth | 69479 | A | DONE | 4 | S | neal | OLIV 6210030 - L1 Amen. |  | 2024-02-15 | Z | 2024-02-13 | 100 | 0 | 0 |  | 0 | 170 |  |  |  | 2
2024-02-16 | 2603 |  | 69482 | A | DONE | 4 | S-M |  | OLIV 6210030 - LV-17 , 18 |  | 2024-02-22 | Z | 2024-02-14 | 80 | 0 | 0 |  | 20 | 120 |  |  |  | 8
2024-02-15 | 1621 |  | 66906 | A | DONE | 2 | S |  | PROMEGA CMC 6230019 - Punch list |  | 2024-02-16 | Z | 2024-02-14 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-02-13 | 1248 | w | 62923 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 - Roof cap |  | 2024-02-14 | Z | 2024-01-30 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 15
2024-02-13 | 1249 |  | 62684 | A | DONE | 2 | S | pcd | PROMEGA FEYNMAN 6220014 - EX Fan |  | 2024-02-14 | Z | 2024-02-07 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-02-13 | 1950 |  | 62685 - 62688 | A | DONE | 5 | S-M |  | PROMEGA FEYNMAN 6220014 - Misc |  | 2024-02-14 | Z | 2024-02-07 | 120 | 0 | 0 |  | 0 | 140 |  |  |  | 7
2024-02-13 | 1951 |  | 62689 | A | DONE | 5 | S |  | PROMEGA FEYNMAN 6220014 - AHU-13 SA |  | 2024-02-14 | Z | 2024-02-07 | 120 | 0 | 0 |  | 0 | 300 |  |  |  | 7
2024-02-13 | 1952 |  | 62690 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 - DH-B OA |  | 2024-02-14 | Z | 2024-02-07 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-02-12 | 1953 |  | 62691 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 - 2nd Floor |  | 2024-02-14 | Z | 2024-02-07 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-02-13 | 1954 |  | 62692 | F | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 - AHU-14 SA |  | 2024-02-14 | Z | 2024-02-07 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 7
2024-02-12 | 1955 | sp | 62693 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 - Grilles |  | 2024-02-14 | Z | 2024-02-07 | 20 | 30 | 0 |  | 0 | 30 |  |  |  | 7
2024-02-16 | 549 |  | 70658 | A | DONE | 15 | M | neal | RAMC 6230009 - OA Duct birdscreen |  | 2024-02-19 | Z | 2024-02-13 | 250 | 0 | 120 | F | 0 | 500 |  |  |  | 6
2024-02-16 | 208 | sp | 69387 - 69388 | A | DONE | 11 | S-M |  | RISK STRATEGIES 4240006 - FCU 3-17 |  | 2024-02-19 | Z | 2024-02-12 | 80 | 190 | 0 |  | 0 | 250 |  |  |  | 7
2024-02-15 | 209 | bth | 69389 - 69390 | A | DONE | 12 | S-M |  | RISK STRATEGIES 4240006 - FCU 3-17 |  | 2024-02-19 | Z | 2024-02-12 | 150 | 130 | 0 |  | 0 | 330 |  |  |  | 7
2024-02-15 | 210 | bth | 69391 - 69393 | A | DONE | 14 | S-M |  | RISK STRATEGIES 4240006 - FCU 3-3 |  | 2024-02-19 | Z | 2024-02-12 | 120 | 160 | 70 | F | 0 | 330 |  |  |  | 7
2024-02-15 | 211 | sp | 69394 | A | DONE | 17 | S-M |  | RISK STRATEGIES 4240006 - OA |  | 2024-02-19 | Z | 2024-02-12 | 50 | 360 | 0 |  | 0 | 370 |  |  |  | 7
2024-02-15 | 212 |  | 69396 | A | DONE | 2 | S |  | RISK STRATEGIES 4240006 - TA 1" liner |  | 2024-02-19 | Z | 2024-02-12 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 7
2024-02-16 | 213 | sp | 69397 | A | DONE | 10 | S-M |  | RISK STRATEGIES 4240006 - EA |  | 2024-02-19 | Z | 2024-02-12 | 30 | 210 | 0 |  | 0 | 230 |  |  |  | 7
2024-02-15 | 214 |  | 69398 | A | DONE | 2 | S |  | RISK STRATEGIES 4240006 - FCU 3-3 |  | 2024-02-19 | Z | 2024-02-12 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-02-13 | 4702 |  | 55742 - 55743 | A | DONE | 6 | S |  | ROCK CO. JAIL 6220018 - SALP misc |  | 2024-02-15 | Z | 2024-02-06 | 140 | 0 | 0 |  | 0 | 220 |  |  |  | 9
2024-02-13 | 4703 |  | 78853 | A | DONE | 2 | S | flex | ROCK CO. JAIL 6220018 - A-section / kitchen paint |  | 2024-02-15 | Z | 2024-02-07 | 50 | 0 | 0 |  | 20 | 70 |  |  |  | 8
2024-02-15 | 4704 |  | 78854 | A | DONE | 3 | S-M | ss | ROCK CO. JAIL 6220018 - Kitchen Exh |  | 2024-02-22 | Z | 2024-02-07 | 60 | 0 | 0 |  | 0 | 60 |  |  |  | 15
2024-02-13 | 4705 |  | 78829 | A | DONE | 6 | S-M |  | ROCK CO. JAIL 6220018 - Grille boxes paint |  | 2024-02-15 | Z | 2024-02-08 | 150 | 0 | 0 |  | 140 | 260 |  |  |  | 7
2024-02-13 | 4706 |  | 78830 | A | DONE | 9 | S-M |  | ROCK CO. JAIL 6220018 - Mech room |  | 2024-02-15 | Z | 2024-02-12 | 220 | 0 | 0 |  | 0 | 420 |  |  |  | 3
2024-02-13 | 4707 | bth | 78831 | A | DONE | 12 | S-M |  | ROCK CO. JAIL 6220018 - Max Security |  | 2024-02-15 | Z | 2024-02-12 | 220 | 60 | 0 |  | 0 | 340 |  |  |  | 3
2024-02-13 | 4708 |  | 78832 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - D-Section FG |  | 2024-02-15 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-02-15 | 4709 |  | 78833 | A | DONE | 3 | S-M | pcd | ROCK CO. JAIL 6220018 - Indoor Rec. |  | 2024-02-22 | Z | 2024-02-12 | 60 | 0 | 0 |  | 0 | 90 |  |  |  | 10
2024-02-12 | 4710 |  | 78834 | delete |  |  | S-M | flex | ROCK CO. JAIL 6220018 - Indoor Rec. |  | 2024-02-22 | Z | 2024-02-12 | [9 empty] | 10
2024-02-15 | 4711 |  | 78835 | A | DONE | 2 | S | flex | ROCK CO. JAIL 6220018 - EF-5J |  | 2024-02-22 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 10
2024-02-14 | 4712 |  | 78836 | A | DONE | 5 | S |  | ROCK CO. JAIL 6220018 - Guard |  | 2024-02-15 | Z | 2024-02-13 | 110 | 0 | 0 |  | 0 | 150 |  |  |  | 2
2024-02-15 | 4713 |  | 78837 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Weapons hood hanger |  | 2024-02-22 | Z | 2024-02-15 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-02-16 | 4714 |  | 78838 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Mech Rm. |  | 2024-02-22 | Z | 2024-02-15 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-02-12 | 4800 |  | 96540 | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 - Rings |  | 2024-02-14 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 2
2024-02-14 | 2717 |  | 73391 , 73536 | A | DONE | 2 | S |  | UWL-HSC 6230018 - 1st floor , VAV 112 |  | 2024-02-20 | Z | 2024-02-02 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 18
2024-02-15 | 2718 |  | 73393 | A | DONE | 6 | S |  | UWL-HSC 6230018 - L-2 |  | 2024-02-20 | Z | 2024-02-07 | 140 | 0 | 40 | F | 0 | 190 |  |  |  | 13
2024-02-12 | 5001 |  | 96539 | A | DONE | 2 | S | BI | UWSP ALBERTSON 6230016 - Caps |  | 2024-02-14 | Z | 2024-02-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-02-13 | 2773 | w | 72666 - 72667 | A | DONE | 2 | S | ss | UW-VET MED 2230012 - BSL-4 |  | 2024-02-12 | Z | 2024-01-29 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 14
2024-02-12 | 2774 | w | 72668 - 72269 | A | DONE | 2 | S | ss | UW-VET MED 2230012 - BSL-5 |  | 2024-02-12 | Z | 2024-01-29 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 14
2024-02-14 | 2780 |  | 72677 | A | DONE | 2 | S-M |  | UW-VET MED 2230012 - Angle |  | 2024-02-19 | Z | 2024-02-13 | 50 | 0 | 0 |  | 0 | 140 |  |  |  | 6
2024-02-13 | 2781 |  | 70528 | A | DONE | 2 | S |  | UW-VET MED 2230012 - Heto |  | 2024-02-13 | Z | 2024-02-13 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-02-15 | 2782 |  | 72678 | A | DONE | 2 | S | pcd | UW-VET MED 2230012 - 3rd floor |  | 2024-02-19 | Z | 2024-02-14 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 5
2024-02-12 | 1844 | sp | 2B-SALP-3 | A | DONE | 38 | M-L | neal | WCSD HERITAGE 6220024 - s.mates |  | 2024-02-09 | Z | 2024-01-16 | 240 | 700 | 0 |  | 0 | 1200 |  |  |  | 24
2024-02-13 | 1861 |  | 57777 | A | DONE | 4 | S |  | WCSD HERITAGE 6220024 - MAU-tie ins |  | 2024-02-16 | Z | 2024-02-05 | 100 | 0 | 0 |  | 0 | 120 |  |  |  | 11
2024-02-13 | 1862 |  | 69157 - 69159 | A | DONE | 4 | S | flex | WCSD HERITAGE 6220024 - HP 232 , 236 1" liner |  | 2024-02-16 | Z | 2024-02-06 | 100 | 0 | 0 |  | 70 | 140 |  |  |  | 10
2024-02-13 | 1863 |  | 69160 - 69163 | A | DONE | 6 | S |  | WCSD HERITAGE 6220024 - HP 224 ,229 ,230 ,233 |  | 2024-02-16 | Z | 2024-02-06 | 130 | 0 | 0 |  | 30 | 150 |  |  |  | 10
2024-02-13 | 1864 |  | 69164 - 69165 | A | DONE | 3 | S-M | neal | WCSD HERITAGE 6220024 - OA , EA Corridor outs |  | 2024-02-16 | Z | 2024-02-06 | 70 | 0 | 0 |  | 0 | 120 |  |  |  | 10
2024-02-13 | 1865 |  | 69010 | A | DONE | 8 | S-M |  | WCSD HERITAGE 6220024 - Grille box paint |  | 2024-02-16 | Z | 2024-02-07 | 200 | 0 | 0 |  | 200 | 420 |  |  |  | 9
2024-02-15 | 1866 | w | 57778 | A | DONE | 2 | S-M | ss | WCSD HERITAGE 6220024 - 1st Dishwasher |  | 2024-02-16 | Z | 2024-02-07 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 9
2024-02-13 | 1867 |  | 57779 - 57780 | A | DONE | 13 | S-M |  | WCSD HERITAGE 6220024 - 2-C DOAS 1 |  | 2024-02-16 | Z | 2024-02-07 | 320 | 0 | 0 |  | 0 | 720 |  |  |  | 9
2024-02-14 | 1868 | w | 57781 | A | DONE | 2 | S-M | BI | WCSD HERITAGE 6220024 - Kitchen hood tie in |  | 2024-02-16 | Z | 2024-02-07 | 40 | 0 | 0 |  | 0 | 100 |  |  |  | 9
2024-02-13 | 1869 |  | 69166 | A | DONE | 3 | S-M |  | WCSD HERITAGE 6220024 - 2nd D outs |  | 2024-02-16 | Z | 2024-02-12 | 70 | 0 | 0 |  | 0 | 120 |  |  |  | 4
2024-02-14 | 1870 |  | 57783 - 57785 | A | DONE | 7 | S-M |  | WCSD HERITAGE 6220024 - Roof - RH 1 / Drops |  | 2024-02-16 | Z | 2024-02-12 | 160 | 0 | 0 |  | 0 | 310 |  |  |  | 4
2024-02-16 | 1871 |  | 69011 | A | DONE | 24 | S-M |  | WCSD HERITAGE 6220024 - Grille box 1C / 1D |  | 2024-02-23 | Z | 2024-02-12 | 600 | 0 | 0 |  | 0 | 1420 |  |  |  | 11
2024-02-15 | 1876 |  | 68980 | A | DONE | 4 | S |  | WCSD HERITAGE 6220024 - DOAS-2 Drop |  | 2024-02-19 | Z | 2024-02-15 | 100 | 0 | 0 |  | 0 | 140 |  |  |  | 4
2024-02-16 | 1877 |  | 69018 | A | DONE | 2 | S | neal | WCSD HERITAGE 6220024 - Gym hangers |  | 2024-02-23 | Z | 2024-02-15 | 40 | 0 | 0 |  | 0 | 100 |  |  |  | 8
2024-02-15 | 215 |  | 70279 | A | DONE | 2 | S |  | WEST MIDDLETON 4230086 - Misc paint |  | 2024-02-16 | Z | 2024-02-14 | 30 | 0 | 0 |  | 30 | 40 |  |  |  | 2
[6 empty] | 884 | [13 empty] | 28340 |  |  |  | 11960 | 42.2%
WEEK OF 2-19-2024
2024-02-23 | 221 |  | 22224 | A | DONE | 2 | S |  | ACADIA 8230013 - Plate |  | 2024-02-22 | Z | 2024-02-22 | 30 | 0 | 0 |  | 0 | 90 |  |  |  | 0
2024-02-19 | 1900 | sp | 70045 - 70047 | A | DONE | 5 | S-M |  | ALDEVRON 2230053 - FPVAV's |  | 2024-02-26 | Z | 2024-01-25 | 30 | 90 | 0 |  | 0 | 120 |  |  |  | 32
2024-02-20 | 4000 | sp | L1-A-EAD-021 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 18
2024-02-20 | 4002 | bth | L1-A-EAD-032 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 120 | 130 | 40 | F | 0 | 320 |  |  |  | 18
2024-02-20 | 4003 | bth | L1-A-EAD-035 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 - paint |  | 2024-02-23 | Z | 2024-02-05 | 30 | 80 | 20 | F | 0 | 140 |  |  |  | 18
2024-02-20 | 4004 | bth | L1-A-EAD-036 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 50 | 150 | 20 | F | 0 | 230 |  |  |  | 18
2024-02-20 | 4005 | sp | L1-A-EAD-037 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 18
2024-02-20 | 4006 | bth | L1-A-EAD-039 | A | DONE | 4 | S-M |  | CDIS 6220028 - paint |  | 2024-02-23 | Z | 2024-02-05 | 50 | 30 | 20 | F | 0 | 120 |  |  |  | 18
2024-02-20 | 4007 | bth | L1-A-EAD-040 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 50 | 20 | 0 |  | 0 | 70 |  |  |  | 18
2024-02-20 | 4008 | sp | L1-A-EAD-045 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 20 | 140 | 0 |  | 0 | 160 |  |  |  | 18
2024-02-19 | 4009 |  | L1-A-RAD-005 | A | DONE | 63 | S-M |  | CDIS 6220028 - 1" DW |  | 2024-02-23 | Z | 2024-02-05 | 920 | 0 | 640 | F | 590 | 2930 |  |  |  | 18
2024-02-20 | 4010 |  | L1-A-RAD-006 | A | DONE | 62 | S-M |  | CDIS 6220028 - 1" DW |  | 2024-02-23 | Z | 2024-02-05 | 770 | 0 | 770 | F | 560 | 2740 |  |  |  | 18
2024-02-20 | 4011 |  | L1-A-RAD-007 | A | DONE | 34 | S-M |  | CDIS 6220028 - 1" DW |  | 2024-02-23 | Z | 2024-02-05 | 530 | 0 | 300 | F | 380 | 1250 |  |  |  | 18
2024-02-20 | 4012 |  | L1-A-RAD-008 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 180 | 0 | 100 | F | 0 | 450 |  |  |  | 18
2024-02-20 | 4013 | bth | L1-A-SALP-053 | A | DONE | 8 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-23 | Z | 2024-02-05 | 120 | 20 | 60 | F | 50 | 230 |  |  |  | 18
2024-02-20 | 4014 | bth | L1-A-SALP-054 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 60 | 60 | 60 | F | 0 | 220 |  |  |  | 18
2024-02-21 | 4015 |  | L1-A-SALP-055 | A | DONE | 13 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-23 | Z | 2024-02-05 | 230 | 0 | 90 | F | 60 | 390 |  |  |  | 18
2024-02-21 | 4016 |  | L1-A-SALP-056 | A | DONE | 10 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-23 | Z | 2024-02-05 | 200 | 0 | 40 | F | 50 | 340 |  |  |  | 18
2024-02-20 | 4017 |  | L1-A-SALP-057 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 90 | 0 | 250 | F | 0 | 570 |  |  |  | 18
2024-02-21 | 4018 |  | L1-A-SALP-058 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 210 | 0 | 160 | F | 0 | 470 |  |  |  | 18
2024-02-21 | 4019 |  | L1-A-SALP-059 | A | DONE | 4 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-23 | Z | 2024-02-05 | 90 | 0 | 0 |  | 30 | 110 |  |  |  | 18
2024-02-21 | 4020 |  | L1-A-SALP-060 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 40 | 0 | 150 | F | 0 | 230 |  |  |  | 18
2024-02-21 | 4021 |  | L1-A-SALP-061 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 50 | 0 | 80 | F | 0 | 160 |  |  |  | 18
2024-02-21 | 4022 |  | L1-A-SALP-062 | A | DONE | 3 | S-M |  | CDIS 6220028 - 1" liner paint |  | 2024-02-23 | Z | 2024-02-05 | 60 | 0 | 0 |  | 40 | 100 |  |  |  | 18
2024-02-21 | 4023 | bth | L1-A-SALP-063 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 - 1" liner paint |  | 2024-02-23 | Z | 2024-02-05 | 130 | 30 | 30 | F | 20 | 210 |  |  |  | 18
2024-02-21 | 4024 |  | L1-A-SALP-064 | A | DONE | 9 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-23 | Z | 2024-02-05 | 170 | 0 | 40 | F | 70 | 270 |  |  |  | 18
2024-02-21 | 4025 |  | L1-A-SALP-065 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 70 | 0 | 110 | F | 0 | 240 |  |  |  | 18
2024-02-21 | 4026 | bth | L1-A-SALP-066 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 90 | 20 | 30 | F | 0 | 160 |  |  |  | 18
2024-02-21 | 4027 | bth | L1-A-SALP-067 | A | DONE | 12 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-23 | Z | 2024-02-05 | 80 | 220 | 0 |  | 30 | 300 |  |  |  | 18
2024-02-21 | 4028 | bth | L1-A-SALP-068 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 |  | 2024-02-23 | Z | 2024-02-05 | 50 | 190 | 0 |  | 0 | 240 |  |  |  | 18
2024-02-21 | 4029 |  | L1-A-TA-001 | A | DONE | 2 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-23 | Z | 2024-02-05 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 18
2024-02-21 | 4030 |  | L1-A-TA-002 | A | DONE | 4 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-23 | Z | 2024-02-05 | 100 | 0 | 0 |  | 70 | 120 |  |  |  | 18
2024-02-23 | 4038 |  | L1-A-RAD-009 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 20
2024-02-21 | 4050 |  | 61423 | A | DONE | 8 | S-M |  | CDIS 6220028 - 2nd Floor A sleeves |  | 2024-02-27 | Z | 2024-02-08 | 190 | 0 | 0 |  | 0 | 370 |  |  |  | 19
2024-02-19 | 4157 | w | 61355 | A | DONE | 2 | S |  | CDIS 6220028 - Sleeves |  | 2024-02-22 | Z | 2024-02-16 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-02-21 | 4209 |  | 56623 | A | DONE | 6 | S-M |  | CDIS 6220028 - B2660 Mech room |  | 2024-02-22 | Z | 2024-02-21 | 150 | 0 | 0 |  | 0 | 400 |  |  |  | 1
2024-02-20 | 3229a |  | SC-EAD-002 | A | DONE | 2 | S |  | CDIS 6220028 - partial |  | 2024-02-21 | Z | 2024-02-19 | 50 | 0 | 0 |  | 0 | 160 |  |  |  | 2
2024-02-20 | 1127 |  | 59477 | A | DONE | 3 | S |  | DANE CO. AIRPORT 6210011 - Elec. Rm EA paint |  | 2024-02-22 | Z | 2024-02-19 | 70 | 0 | 0 |  | 20 | 80 |  |  |  | 3
2024-02-22 | 1562 |  | 62419 - 62420 | A | DONE | 5 | S-M |  | EMBASSY SUITES 6220012 - 1st flooor paint |  | 2024-02-26 | Z | 2024-02-20 | 110 | 0 | 0 |  | 80 | 150 |  |  |  | 6
2024-02-23 | 1699 |  | 61027 | A | DONE | 26 | M |  | EXACT BIOSAFE 6230005 - RTU-1 RA |  | 2024-02-27 | Z | 2024-02-16 | 520 | 0 | 130 | F | 0 | 1110 |  |  |  | 11
2024-02-23 | 2551 |  | 61030 | A | DONE | 3 | S-M | flex | EXACT BIOSAFE 6230005 - XF-1 , XF-2, EF-3 |  | 2024-02-27 | Z | 2024-02-16 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 11
2024-02-19 | 3821 |  | 68395 | A | DONE | 2 | S |  | HEALTH SERV. 6230004 - Firestop |  | 2024-02-19 | Z | 2024-02-19 | 40 | 0 | 0 |  | 0 | 100 |  |  |  | 0
2024-02-21 | 3720 |  | 63348 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Main con. |  | 2024-02-26 | Z | 2024-02-19 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 7
2024-02-21 | 3721 |  | 55188 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - Flat stock |  | 2024-02-26 | Z | 2024-02-20 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-02-23 | 3723 |  | 55189 | A | DONE | 2 | S | flex | KOHL CENTER 6210034 - Main con. |  | 2024-02-26 | Z | 2024-02-22 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 4
2024-02-22 | 443 |  | 68514 | A | DONE | 4 | S-M |  | MEMORIAL HS 6210024 - A-B- Patches |  | 2024-03-01 | Z | 2023-12-06 | 80 | 0 | 0 |  | 0 | 90 |  |  |  | 86 |  | 2024-06-25
2024-02-19 | 1938 |  | 67419 | A | DONE | 6 | S-M | vav's | MENDOTA FOOD 6220027 - 1st floor VAV 1" liner |  | 2024-02-22 | Z | 2024-01-22 | 150 | 0 | 0 |  | 150 | 320 |  |  |  | 31
2024-02-21 | 1941 |  | 22124 | A | DONE | 2 | S |  | MENDOTA FOOD 8220036 - Plates |  | 2024-02-23 | Z | 2024-02-21 | 30 | 0 | 0 |  | 0 | 90 |  |  |  | 2
2024-02-22 | 3806 |  | 66078 | A | DONE | 2 | S |  | MOXY 6210032 - FSD's |  | 2024-02-26 | Z | 2024-02-19 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-02-21 | 216 |  | 70277 - 70278 | A | DONE | 14 | M |  | NATE K. E363 - Furnace |  | 2024-02-23 | Z | 2024-02-16 | 100 | 0 | 240 | F | 0 | 310 |  |  |  | 7
2024-02-19 | 734 | sp | 71115 - 71116 | A | DONE | 9 | S-M |  | OLIV 6210030 - Stair # 4 |  | 2024-02-22 | Z | 2024-01-25 | 50 | 170 | 0 |  | 0 | 230 |  |  |  | 28 |  | 2024-03-07
2024-02-19 | 735 | sp | 71117 - 71118 | A | DONE | 17 | M |  | OLIV 6210030 - Stair # 3 |  | 2024-02-22 | Z | 2024-01-25 | 80 | 340 | 0 |  | 0 | 430 |  |  |  | 28 |  | 2024-03-07
2024-02-19 | 749 | sp | 69475 - 69476 | A | DONE | 6 | S-M |  | OLIV 6210030 - Stair pressurization |  | 2024-02-22 | Z | 2024-02-12 | 130 | 0 | 0 |  | 0 | 210 |  |  |  | 10
2024-02-19 | 2605 | bth | 69483 | A | DONE | 2 | S | pt.neal | OLIV 6210030 - Basement / LVL 1 flex |  | 2024-02-22 | Z | 2024-02-16 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 6
2024-02-20 | 2607 |  | 61129 - 61130 | A | DONE | 4 | S | flex | OLIV 6210030 - 1st Ammen |  | 2024-02-22 | Z | 2024-02-19 | 70 | 0 | 30 | F | 0 | 100 |  |  |  | 3
2024-02-21 | 2608 |  | 69487 | A | DONE | 4 | S |  | OLIV 6210030 - IDF Rm |  | 2024-02-22 | Z | 2024-02-21 | 90 | 0 | 0 |  | 0 | 130 |  |  |  | 1
2024-02-23 | 2609 |  | 69489 | A | DONE | 4 | S | pt.neal | OLIV 6210030 - STAIR DUCT |  | 2024-02-26 | Z | 2024-02-23 | 80 | 0 | 0 |  | 0 | 120 |  |  |  | 3
2024-02-20 | 1956 | bth | 62888 - 62890 | A | DONE | 12 | M |  | PROMEGA FEYNMAN 6220014 - RA tie ins |  | 2024-02-23 | Z | 2024-02-14 | 210 | 90 | 0 |  | 0 | 350 |  |  |  | 9
2024-02-20 | 1957 |  | 62694 - 62695 | A | DONE | 3 | S-M |  | PROMEGA FEYNMAN 6220014 - AHU-13 / DH A |  | 2024-02-23 | Z | 2024-02-14 | 60 | 0 | 0 |  | 0 | 180 |  |  |  | 9
2024-02-19 | 1958 | w | 62696 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 - DH-A Relief |  | 2024-02-23 | Z | 2024-02-14 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 9
2024-02-19 | 1959 |  | 62698 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 - AHU SA |  | 2024-02-23 | Z | 2024-02-14 | 50 | 0 | 0 |  | 0 | 140 |  |  |  | 9
2024-02-19 | 1960 |  | 62926 | A | DONE | 2 | S | pcd | PROMEGA FEYNMAN 6220014 - Misc birdsceen |  | 2024-02-23 | Z | 2024-02-14 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 9
2024-02-22 | 1961 | bth | 62891 | A | DONE | 3 | S-M |  | PROMEGA FEYNMAN 6220014 - RA tie ins |  | 2024-02-26 | Z | 2024-02-16 | 60 | 0 | 0 |  | 0 | 100 |  |  |  | 10
2024-02-22 | 505 | bth | L1-SAMP-6 | A | DONE | 74 | L | semi 2 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 1020 | 150 | 670 | F | 0 | 3690 |  |  |  | 26
2024-02-22 | 535 | sp | L1-RA-1 | A | DONE | 16 | S-M | semi 2 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 70 | 330 | 0 |  | 0 | 470 |  |  |  | 26
2024-02-22 | 536 | sp | L1-RA-2 | A | DONE | 16 | S-M | semi 1 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 120 | 280 | 0 |  | 0 | 480 |  |  |  | 26
2024-02-23 | 537 | bth | L1-RA-3 | A | DONE | 17 | S-M | semi 1 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 170 | 250 | 0 |  | 0 | 560 |  |  |  | 26
2024-02-22 | 539 | bth | L1-RA-5 | A | DONE | 51 | L | semi 1 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 960 | 30 | 280 | F | 0 | 1970 |  |  |  | 26
2024-02-21 | 550 | sp | 70661 | A | DONE | 5 | S |  | RAMC 6230009 - Reheat Coil |  | 2024-02-26 | Z | 2024-02-13 | 20 | 100 | 0 |  | 0 | 130 |  |  |  | 13
2024-02-21 | 220 |  | 69400 | A | DONE | 3 | S |  | RISK STRATEGIES 4240006 - EA paint |  | 2024-02-23 | Z | 2024-02-21 | 70 | 0 | 0 |  | 30 | 80 |  |  |  | 2
2024-02-20 | 218 |  | 69399 | A | DONE | 2 | S |  | RISK STRATEGIES 4240006 - Misc |  | 2024-02-20 | Z | 2024-02-20 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 0
2024-02-19 | 4715 |  | 78839 | A | DONE | 5 | S-M |  | ROCK CO. JAIL 6220018 - Max Security |  | 2024-02-22 | Z | 2024-02-16 | 120 | 0 | 0 |  | 0 | 160 |  |  |  | 6
2024-02-22 | 4716 |  | 78840 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Flashing |  | 2024-02-29 | Z | 2024-02-19 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 10
2024-02-23 | 4718 |  | 72370 | A | DONE | 2 | S | neal | ROCK CO. JAIL 6220018 - LES finish birdscreen |  | 2024-02-29 | Z | 2024-02-21 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 8
2024-02-21 | 2783 |  | 72679 | A | DONE | 2 | S | pcd | UW-VET MED 2230012 - 3rd BSL-2 |  | 2024-02-26 | Z | 2024-02-20 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-02-19 | 1872 |  | 69012 - 69014 | A | DONE | 4 | S-M |  | WCSD HERITAGE 6220024 - Tie ins 1" liner paint |  | 2024-02-23 | Z | 2024-02-14 | 90 | 0 | 0 |  | 40 | 130 |  |  |  | 9
2024-02-19 | 1873 |  | 69015 - 69016 | A | DONE | 4 | S-M |  | WCSD HERITAGE 6220024 - Tie ins 1" liner paint |  | 2024-02-23 | Z | 2024-02-14 | 90 | 0 | 0 |  | 70 | 140 |  |  |  | 9
2024-02-19 | 1874 | bth | 69017 | A | DONE | 2 | S-M |  | WCSD HERITAGE 6220024 - Tie ins paint |  | 2024-02-23 | Z | 2024-02-14 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 9
2024-02-21 | 1875 |  | 68976 - 68977 | A | DONE | 13 | M | flex | WCSD HERITAGE 6220024 - DOAS |  | 2024-02-23 | Z | 2024-02-14 | 320 | 0 | 0 |  | 0 | 790 |  |  |  | 9
2024-02-20 | 1878 |  | 69019 - 69020 | A | DONE | 10 | S-M |  | WCSD HERITAGE 6220024 - Misc |  | 2024-02-23 | Z | 2024-02-19 | 240 | 0 | 0 |  | 0 | 340 |  |  |  | 4
2024-02-20 | 1879 |  | 69201 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - Louver sleeve |  | 2024-02-23 | Z | 2024-02-19 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 4
2024-02-21 | 1880 |  | 57786 | A | DONE | 2 | S | BI | WCSD HERITAGE 6220024 - Misc |  | 2024-02-23 | Z | 2024-02-20 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-02-22 | 3722 |  | 68981 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - RA Gym office |  | 2024-02-23 | Z | 2024-02-22 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
[6 empty] | 772 | [13 empty] | 27920 |  |  |  | 6150 | 22.03%
WEEK OF 2-26-2024
2024-02-27 | 1721 |  | 68015 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 - Fin Tube Cover |  | 2024-02-29 | Z | 2024-02-26 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-02-28 | 1714 |  | 78917 | A | DONE | 7 | S-M |  | BLACKHAWK BTC 6230025 - Stairway |  | 2024-02-29 | Z | 2024-01-19 | 70 | 0 | 90 | F | 120 | 160 |  |  |  | 41 |  | 2024-03-14
2024-02-26 | 4032 | bth | L1-A-EAD-024 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 100 | 30 | 200 | F | 0 | 380 |  |  |  | 20
2024-02-26 | 4033 | bth | L1-A-EAD-025 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 80 | 20 | 100 | F | 0 | 220 |  |  |  | 20
2024-02-26 | 4034 | bth | L1-A-EAD-026 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 90 | 20 | 0 |  | 0 | 110 |  |  |  | 20
2024-02-26 | 4035 | bth | L1-A-EAD-028 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 140 | 50 | 40 | F | 0 | 250 |  |  |  | 20
2024-02-26 | 4036 | bth | L1-A-EAD-029 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 100 | 20 | 110 | F | 0 | 250 |  |  |  | 20
2024-02-26 | 4037 | bth | L1-A-EAD-030 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 110 | 20 | 0 |  | 0 | 140 |  |  |  | 20
2024-02-26 | 4039 |  | L1-A-SALP-047 | A | DONE | 13 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-27 | Z | 2024-02-07 | 190 | 0 | 130 | F | 40 | 370 |  |  |  | 20
2024-02-26 | 4040 | bth | L1-A-SALP-048 | A | DONE | 17 | S |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 50 | 80 | 280 | F | 0 | 470 |  |  |  | 20
2024-02-26 | 4041 |  | L1-A-SALP-049 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 90 | 0 | 70 | F | 0 | 190 |  |  |  | 20
2024-02-26 | 4042 |  | L1-A-SALP-050 | A | DONE | 9 | S-M |  | CDIS 6220028 - 1" liner |  | 2024-02-27 | Z | 2024-02-07 | 140 | 0 | 70 | F | 40 | 250 |  |  |  | 20
2024-02-26 | 4043 | bth | L1-A-SALP-051 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 50 | 20 | 110 | F | 0 | 200 |  |  |  | 20
2024-02-26 | 4044 | bth | L1-A-SALP-052 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 80 | 20 | 90 | F | 0 | 210 |  |  |  | 20
2024-02-26 | 4045 |  | L1-A-SAMP-043 | A | DONE | 17 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 130 | 0 | 290 | F | 0 | 570 |  |  |  | 20
2024-02-26 | 4046 |  | L1-A-SAMP-044 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 120 | 0 | 180 | F | 0 | 400 |  |  |  | 20
2024-02-26 | 4047 |  | L1-A-SAMP-045 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 160 | 0 | 170 | F | 0 | 420 |  |  |  | 20
2024-02-27 | 4048 | sp | L1-A-SAMP-046 | A | DONE | 9 | S-M | neal | CDIS 6220028 - s.mates |  | 2024-02-28 | Z | 2024-02-07 | 90 | 120 | 0 |  | 0 | 300 |  |  |  | 21
2024-02-26 | 4049 |  | L1-A-SAMP-069 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-02-27 | Z | 2024-02-07 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 20
2024-03-01 | 4093 |  | L2-B-TAD-002 | A | DONE | 4 | S |  | CDIS 6220028 - 1" liner |  | 2024-03-05 | Z | 2024-02-14 | 80 | 0 | 0 |  | 60 | 100 |  |  |  | 20
2024-02-26 | 4095 |  | 61425 | A | DONE | 2 | S | pt.neal | CDIS 6220028 - S/D |  | 2024-02-28 | Z | 2024-02-15 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 13
2024-02-29 | 4101 |  | L2-B-RAD-001 | A | DONE | 2 | S | pt.neal | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-15 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 19
2024-03-01 | 4104 |  | L2-A-SAMP-063 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-15 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 19
2024-02-27 | 4210 |  | 61426 - 61427 | A | DONE | 19 | M |  | CDIS 6220028 - SC RAD / EAD |  | 2024-02-28 | Z | 2024-02-21 | 160 | 0 | 310 | F | 0 | 930 |  |  |  | 7
2024-03-01 | 4218 |  | 94234 | A | DONE | 2 | S |  | CDIS 6220028 - Caps |  | 2024-03-04 | Z | 2024-03-01 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-02-26 | 217 | sp | 79551 | A | DONE | 6 | S-M |  | CULVER PARK 2240010 - RTU SA |  | 2024-02-27 | Z | 2024-02-20 | 40 | 90 | 0 |  | 0 | 120 |  |  |  | 7
2024-02-26 | 1563 |  | 62421 | A | DONE | 2 | S-M |  | EMBASSY SUITES 6220012 - 2nd flooor |  | 2024-02-28 | Z | 2024-02-21 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 7
2024-02-26 | 1564 |  | 62422 | A | DONE | 4 | S | flex | EMBASSY SUITES 6220012 - Roof birdscreen |  | 2024-02-28 | Z | 2024-02-21 | 90 | 0 | 0 |  | 0 | 120 |  |  |  | 7
2024-02-27 | 1565 |  | 62424 | A | DONE | 4 | S-M |  | EMBASSY SUITES 6220012 - TG 3-9 1" liner |  | 2024-02-28 | Z | 2024-02-22 | 100 | 0 | 0 |  | 20 | 120 |  |  |  | 6
2024-02-29 | 1566 |  | 62365 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 - Lineset sleeves |  | 2024-03-05 | Z | 2024-02-27 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 7
2024-02-26 | 1698 | sp | 62517 - 62519 | A | DONE | 22 | M |  | EXACT BIO SAFE 6230005 - XF-1,2 / EF-1 |  | 2024-02-27 | Z | 2024-02-12 | 100 | 450 | 0 |  | 0 | 630 |  |  |  | 15
2024-02-26 | 2550 | bth | 61029 | A | DONE | 17 | M | s.mates | EXACT BIOSAFE 6230005 - RTU-1 SA |  | 2024-02-27 | Z | 2024-02-16 | 340 | 80 | 0 |  | 0 | 570 |  |  |  | 11
2024-02-28 | 2552 |  | 61032 - 61033 | A | DONE | 2 | S-M | flex | EXACT SCIENCE 2230051 - Finishes paint |  | 2024-03-04 | Z | 2024-02-27 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 6
2024-03-01 | 1485 |  | 65369-71 | A | DONE | 13 | M | flex | GRAND AVE. ES 6230012 - RTU-1 SA / RA 1" liner |  | 2024-03-25 | Z | 2023-08-16 | 320 | 0 | 0 |  | 240 | 640 |  |  |  | 222
2024-02-28 | 2650 |  | 69488 | A | DONE | 2 | S | neal | HARMONICS 6240010 - Oval Hangers |  | 2024-03-07 | Z | 2024-02-22 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 14
2024-02-27 | 227 |  | 79401 - 79402 | A | DONE | 2 | S-M |  | KL ENGINERRING 4240002 - Misc |  | 2024-02-28 | Z | 2024-02-27 | 40 | 0 | 0 |  | 0 | 70 |  |  |  | 1
2024-02-27 | 3724 |  | 63349 | A | DONE | 2 | S-M |  | KOHL CENTER 6210034 - E-Main paint |  | 2024-02-29 | Z | 2024-02-26 | 30 | 0 | 0 |  | 20 | 60 |  |  |  | 3
2024-03-01 | 1110 |  | 98574 | A | DONE | 32 | M-L |  | LAPCORP 6230014 - OA |  | 2024-03-04 | Z | 2024-02-16 | 780 | 0 | 0 |  | 0 | 1980 |  |  |  | 17
2024-03-01 | 415 | sp | 63041 - 63042 | A | DONE | 4 | S-M | neal | MEMORIAL HS 6210024 - G2 - 12 |  | 2024-03-05 | Z | 2023-12-06 | 30 | 60 | 0 |  | 0 | 120 |  |  |  | 90
2024-03-01 | 416 |  | 63043 - 63044 | A | DONE | 14 | S-M |  | MEMORIAL HS 6210024 - Exhaust |  | 2024-03-05 | Z | 2023-12-06 | 110 | 0 | 240 | F | 0 | 450 |  |  |  | 90
2024-03-01 | 418 | sp | 63047 | A | DONE | 3 | S-M | alum | MEMORIAL HS 6210024 - Exhaust |  | 2024-03-05 | Z | 2023-12-06 | 20 | 40 | 0 |  | 0 | 40 |  |  |  | 90
2024-02-28 | 425 |  | 68751 - 68753 | A | DONE | 21 | S-M |  | MEMORIAL HS 6210024 - D -1st SA E. |  | 2024-03-01 | Z | 2023-12-06 | 170 | 340 | 0 |  | 0 | 810 |  |  |  | 86 |  | 2024-06-18
2024-02-26 | 426 |  | 68754 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 - D -1st SA SE. |  | 2024-03-01 | Z | 2023-12-06 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 427 |  | 68755 - 68756 | A | DONE | 30 | M |  | MEMORIAL HS 6210024 - D -1st SA W. |  | 2024-03-01 | Z | 2023-12-06 | 50 | 0 | 700 | F | 0 | 990 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 428 | sp | 68757 - 68758 | A | DONE | 8 | S-M |  | MEMORIAL HS 6210024 - VAV D2-08 |  | 2024-03-01 | Z | 2023-12-06 | 50 | 140 | 0 |  | 0 | 200 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 429 | sp | 68759 - 68760 | A | DONE | 3 | S |  | MEMORIAL HS 6210024 - VAV D2-10 |  | 2024-03-01 | Z | 2023-12-06 | 30 | 40 | 0 |  | 0 | 70 |  |  |  | 86 |  | 2024-06-18
2024-02-27 | 430 | bth | 68761 - 68763 | A | DONE | 14 | S-M |  | MEMORIAL HS 6210024 - VAV D2-09 |  | 2024-03-01 | Z | 2023-12-06 | 80 | 150 | 120 | F | 0 | 370 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 431 | sp | 68764 - 68766 | A | DONE | 10 | S-M |  | MEMORIAL HS 6210024 - VAV D2-05 |  | 2024-03-01 | Z | 2023-12-06 | 40 | 190 | 0 |  | 0 | 210 |  |  |  | 86 |  | 2024-06-18
2024-02-29 | 432 | sp | 68767 - 68768 | A | DONE | 5 | S |  | MEMORIAL HS 6210024 - VAV D2-07 |  | 2024-03-01 | Z | 2023-12-06 | 30 | 90 | 0 |  | 0 | 130 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 433 | sp | 68769 | A | DONE | 7 | S |  | MEMORIAL HS 6210024 - N. TA |  | 2024-03-01 | Z | 2023-12-06 | 0 | 170 | 0 |  | 0 | 160 |  |  |  | 86 |  | 2024-06-18
2024-02-29 | 434 | bth | 68770 - 68772 | A | DONE | 12 | S-M |  | MEMORIAL HS 6210024 - VAV D2-04 |  | 2024-03-01 | Z | 2023-12-06 | 90 | 150 | 50 | F | 0 | 290 |  |  |  | 86 |  | 2024-06-18
2024-02-27 | 435 | bth | 68773 - 68775 | A | DONE | 6 | S |  | MEMORIAL HS 6210024 - VAV D2-03 |  | 2024-03-01 | Z | 2023-12-06 | 60 | 20 | 70 | F | 0 | 160 |  |  |  | 86 |  | 2024-06-18
2024-02-29 | 436 | sp | 68776 - 68777 | A | DONE | 7 | S-M |  | MEMORIAL HS 6210024 - VAV D2-04 |  | 2024-03-01 | Z | 2023-12-06 | 30 | 130 | 0 |  | 0 | 140 |  |  |  | 86 |  | 2024-06-18
2024-02-27 | 437 |  | 68778 | A | DONE | 16 | M |  | MEMORIAL HS 6210024 - D 1st RA S. |  | 2024-03-01 | Z | 2023-12-06 | 0 | 0 | 390 | F | 0 | 840 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 438 |  | 63613 - 63614 | A | DONE | 33 | M-L |  | MEMORIAL HS 6210024 - D SA E. |  | 2024-03-01 | Z | 2023-12-06 | 310 | 0 | 500 | F | 0 | 1380 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 439 |  | 63615 - 63616 | A | DONE | 32 | M-L |  | MEMORIAL HS 6210024 - D SA W. |  | 2024-03-01 | Z | 2023-12-06 | 240 | 0 | 550 | F | 0 | 1680 |  |  |  | 86 |  | 2024-06-18
2024-02-29 | 440 | bth | 63617 - 61618 | A | DONE | 9 | S-M |  | MEMORIAL HS 6210024 - VAV D2-01 , 02 |  | 2024-03-01 | Z | 2023-12-06 | 100 | 80 | 30 | F | 0 | 220 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 441 | bth | 63619 - 63620 | A | DONE | 9 | S-M |  | MEMORIAL HS 6210024 - VAV D2-02 |  | 2024-03-01 | Z | 2023-12-06 | 120 | 90 | 0 |  | 0 | 220 |  |  |  | 86 |  | 2024-06-18
2024-02-28 | 442 | sp | 68515 | A | DONE | 23 | S-M |  | MEMORIAL HS 6210024 - EA/RA A-B |  | 2024-03-01 | Z | 2023-12-06 | 30 | 530 | 0 |  | 0 | 510 |  |  |  | 86 |  | 2024-06-25
2024-02-27 | 444 | bth | 68785 - 68787 | A | DONE | 5 | S-M |  | MEMORIAL HS 6210024 - VAV A5-11 |  | 2024-03-01 | Z | 2023-12-06 | 80 | 40 | 0 |  | 0 | 140 |  |  |  | 86 |  | 2024-06-25
2024-02-28 | 445 | bth | 68788 - 68790 | A | DONE | 4 | S-M |  | MEMORIAL HS 6210024 - VAV A5-10 |  | 2024-03-01 | Z | 2023-12-06 | 30 | 50 | 0 |  | 0 | 100 |  |  |  | 86 |  | 2024-06-25
2024-02-28 | 446 | sp | 68791 - 68793 | A | DONE | 4 | S-M |  | MEMORIAL HS 6210024 - VAV A5-05 |  | 2024-03-01 | Z | 2023-12-06 | 40 | 40 | 0 |  | 0 | 100 |  |  |  | 86 |  | 2024-06-25
2024-02-28 | 447 | sp | 68794 - 68795 | A | DONE | 9 | S-M |  | MEMORIAL HS 6210024 - VAV A5-03 , 02 |  | 2024-03-01 | Z | 2023-12-06 | 40 | 170 | 0 |  | 0 | 200 |  |  |  | 86 |  | 2024-06-25
2024-02-29 | 448 | bth | 68796 - 68798 | A | DONE | 6 | S-M |  | MEMORIAL HS 6210024 - VAV A5-01 |  | 2024-03-01 | Z | 2023-12-06 | 50 | 60 | 20 | F | 0 | 160 |  |  |  | 86 |  | 2024-06-25
2024-02-28 | 449 | bth | 68799 - 68800 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 - VAV A5-13 |  | 2024-03-01 | Z | 2023-12-06 | 20 | 40 | 0 |  | 0 | 80 |  |  |  | 86 |  | 2024-06-25
2024-02-29 | 750 | sp | 61649 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 - VAV A5-21 |  | 2024-03-01 | Z | 2023-12-06 | 30 | 30 | 0 |  | 0 | 80 |  |  |  | 86 |  | 2024-06-25
2024-02-29 | 751 | bth | 68501 - 68502 | A | DONE | 4 | S-M |  | MEMORIAL HS 6210024 - VAV A5-22 |  | 2024-03-01 | Z | 2023-12-06 | 50 | 30 | 0 |  | 0 | 80 |  |  |  | 86 |  | 2024-06-25
2024-02-29 | 752 | bth | 68503 - 68505 | A | DONE | 4 | S-M |  | MEMORIAL HS 6210024 - VAV A5-20 |  | 2024-03-01 | Z | 2023-12-06 | 50 | 30 | 0 |  | 0 | 90 |  |  |  | 86 |  | 2024-06-25
2024-02-28 | 753 | bth | 68506 - 68507 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 - VAV A5-14 , 15 |  | 2024-03-01 | Z | 2023-12-06 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 86 |  | 2024-06-25
2024-02-27 | 754 | bth | 68508 - 68509 | A | DONE | 3 | S |  | MEMORIAL HS 6210024 - VAV A5-18 |  | 2024-03-01 | Z | 2023-12-06 | 50 | 20 | 0 |  | 0 | 80 |  |  |  | 86 |  | 2024-06-25
2024-02-28 | 755 | bth | 68510 - 68511 | A | DONE | 4 | S |  | MEMORIAL HS 6210024 - VAV A5-19 |  | 2024-03-01 | Z | 2023-12-06 | 40 | 40 | 20 | F | 0 | 90 |  |  |  | 86 |  | 2024-06-25
2024-02-29 | 756 | bth | 68512 - 68513 | A | DONE | 4 | S |  | MEMORIAL HS 6210024 - VAV A5-20 |  | 2024-03-01 | Z | 2023-12-06 | 40 | 60 | 0 |  | 0 | 100 |  |  |  | 86 |  | 2024-06-25
2024-02-29 | 757 | sp | 68779 - 68780 | A | DONE | 22 | S-M | neal | MEMORIAL HS 6210024 - GYM ez flange |  | 2024-03-01 | Z | 2023-12-06 | 260 | 270 | 0 |  | 0 | 750 |  |  |  | 86 |  | 2024-05-21
2024-02-27 | 758 | sp | 68781 | A | DONE | 2 | S-M | neal | MEMORIAL HS 6210024 - GYM ez flange |  | 2024-03-01 | Z | 2023-12-06 | 50 | 0 | 0 |  | 0 | 120 |  |  |  | 86 |  | 2024-05-21
2024-02-29 | 759 | sp | 68782 - 68783 | A | DONE | 17 | S-M | neal | MEMORIAL HS 6210024 - GYM ez flange |  | 2024-03-01 | Z | 2023-12-06 | 30 | 380 | 0 |  | 0 | 500 |  |  |  | 86 |  | 2024-05-21
2024-02-26 | 760 |  | 68784 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 - GYM Hangers |  | 2024-03-01 | Z | 2023-12-06 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 86 |  | 2024-05-21
2024-03-01 | 775 | sp | 68533 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 - Solder bay |  | 2024-03-05 | Z | 2024-02-28 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 6
2024-03-01 | 776 |  | 68534 | A | DONE | 2 | S | ss | MEMORIAL HS 6210024 - Solder bay |  | 2024-03-05 | Z | 2024-02-28 | 30 | 0 | 0 |  | 0 | 60 |  |  |  | 6
2024-03-01 | 778 |  | 68536 | A | DONE | 8 | S | neal | MEMORIAL HS 6210024 - Rings |  | 2024-03-05 | Z | 2024-03-01 | 180 | 0 | 0 |  | 0 | 310 |  |  |  | 4
2024-02-27 | 1940 | sp | 67422 | A | DONE | 5 | S |  | MENDOTA FOOD 6220027 - Misc |  | 2024-02-29 | Z | 2024-02-20 | 120 | 0 | 0 |  | 0 | 130 |  |  |  | 9
2024-02-27 | 2606 |  | 69485 | A | DONE | 2 | S | bird.s | OLIV 6210030 - LV-5 paint |  | 2024-02-29 | Z | 2024-02-19 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 10
2024-02-27 | 311 |  | 70569 | A | DONE | 3 | S |  | PP 10054214 - Flat stock |  | 2024-02-27 | Z | 2024-02-27 | 70 | 0 | 0 |  | 0 | 150 |  |  |  | 0
2024-02-28 | 1622 | sp | 79552 | A | DONE | 2 | S |  | PROMEGA CMC 6230019 - 4" heto |  | 2024-02-29 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-02-27 | 538 | sp | L1-RA-4 | A | DONE | 25 | M | semi 1 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 170 | 450 | 0 |  | 0 | 890 |  |  |  | 26
2024-02-27 | 540 | sp | L1-RA-6 | A | DONE | 12 | S-M | semi 1 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 40 | 250 | 0 |  | 0 | 420 |  |  |  | 26
2024-02-27 | 541 | sp | L1-RA-7 | A | DONE | 19 | M | semi 1 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 180 | 280 | 0 |  | 0 | 690 |  |  |  | 26
2024-02-27 | 542 | sp | L1-RA-8 | A | DONE | 19 | M | semi 1 | RAMC 6230009 - oval |  | 2024-02-26 | Z | 2024-01-31 | 40 | 440 | 0 |  | 0 | 670 |  |  |  | 26
2024-02-26 | 4719 |  | 78842 | A | DONE | 2 | S | neal | ROCK CO. JAIL 6220018 - Cab Unit heater |  | 2024-02-29 | Z | 2024-02-22 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-02-28 | 4717 | w | 78841 | A | DONE | 2 | S-M |  | ROCK CO. JAIL 6220018 - Generator curb 1-1/2" DB |  | 2024-02-29 | Z | 2024-02-21 | 30 | 0 | 0 |  | 20 | 90 |  |  |  | 8
2024-02-28 | 4720 | w | 78854 | A | DONE | 2 | S | ss | ROCK CO.JAIL 6220018 |  | 2024-02-29 | Z | 2024-02-23 | 50 | 0 | 0 |  | 0 | 160 |  |  |  | 6
2024-02-26 | 219 | w | 64021 | A | DONE | 2 | S |  | ST.BERNARDS 6230023 - Floor sleeves |  | 2024-02-27 | Z | 2024-02-21 | 50 | 0 | 0 |  | 0 | 100 |  |  |  | 6
2024-02-27 | 226 |  | 78712 | A | DONE | 2 | S | bird.s | THERMO FISHER 10053401 - 4104 Rm EA |  | 2024-02-28 | Z | 2024-02-26 | 50 | 0 | 0 |  | 0 | 50 |  |  |  | 2
2024-02-27 | 223 |  | 70217 | A | DONE | 6 | S-M |  | TOMAH HEALTH 4240011 - Phase 1 SA |  | 2024-02-28 | Z | 2024-02-26 | 70 | 60 | 0 |  | 0 | 120 |  |  |  | 2
2024-02-29 | 2719 |  | 73394 | A | DONE | 2 | S |  | UWL-HSC 6230018 - 2nd floor VAV-124 |  | 2024-03-05 | Z | 2024-02-29 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 5
2024-03-01 | 2784 | w | 72680 - 72681 | A | DONE | 2 | S-M | ss | UW-VET MED 2230012 - BSL-3 |  | 2024-03-04 | Z | 2024-02-22 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 11
2024-03-01 | 2785 | w | 72682 - 72683 | A | DONE | 2 | S-M | ss | UW-VET MED 2230012 - BSL-3 |  | 2024-03-04 | Z | 2024-02-22 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 11
2024-03-01 | 2786 | w | 72684 - 72685 | A | DONE | 2 | S-M | ss | UW-VET MED 2230012 - BSL-3 |  | 2024-03-04 | Z | 2024-02-22 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 11
2024-02-29 | 2787 | w | 72686 - 72688 | A | DONE | 2 | S-M | ss | UW-VET MED 2230012 - BSL-3 |  | 2024-03-04 | Z | 2024-02-22 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 11
2024-02-28 | 2788 |  | 72689 | A | DONE | 2 | S |  | UW-VET MED 6210014 - 3rd |  | 2024-03-04 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-02-29 | 2789 | w | 72690 | A | DONE | 2 | S | ss | UW-VET MED 6210014 - Rm 3975B |  | 2024-03-04 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-02-29 | 2790 | w | 72691 | A | DONE | 2 | S | ss | UW-VET MED 2230012 - Misc |  | 2024-03-04 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 6
2024-02-28 | 1881 | w | 57790 | A | DONE | 2 | S | ss | WCSD HERITAGE 6220024 - 1C Dishwasher |  | 2024-03-01 | Z | 2024-02-22 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 8
2024-02-28 | 1882 | w | 68982 | A | DONE | 7 | S-M | bird.s | WCSD HERITAGE 6220024 - 2F Mech Rm MAU |  | 2024-03-01 | Z | 2024-02-22 | 30 | 130 | 0 |  | 0 | 190 |  |  |  | 8
2024-02-27 | 1883 |  | 69024 | A | DONE | 5 | S-M |  | WCSD HERITAGE 6220024 - 2nd Mech Rm outs |  | 2024-03-01 | Z | 2024-02-22 | 120 | 0 | 0 |  | 0 | 220 |  |  |  | 8
2024-02-27 | 1884 |  | 57791 | A | DONE | 2 | S-M |  | WCSD HERITAGE 6220024 - Rm 2046 RA tie-ins |  | 2024-03-01 | Z | 2024-02-22 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 8
2024-02-28 | 1885 |  | 69022 | A | DONE | 6 | S-M | flex | WCSD HERITAGE 6220024 - 2nd Mech Rm outs |  | 2024-03-01 | Z | 2024-02-22 | 130 | 0 | 0 |  | 0 | 290 |  |  |  | 8
2024-02-26 | 1886 |  | 68983-84 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - MISC |  | 2024-02-27 | Z | 2024-02-23 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 4
2024-02-28 | 1887 |  | 57793 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - Angles |  | 2024-03-01 | Z | 2024-02-26 | 80 | 0 | 0 |  | 0 | 90 |  |  |  | 4
2024-02-29 | 1888 |  | 68985 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - FD Flashing |  | 2024-03-01 | Z | 2024-02-28 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
[6 empty] | 844 | [13 empty] | 27630 |  |  |  | 4730 | 17.12%
WEEK OF 3-4-2024
2024-03-06 | 1707 |  | 78905 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 - Hangers |  | 2024-03-07 | Z | 2024-01-19 | 30 | 0 | 0 |  | 0 | 80 |  |  |  | 48
2024-03-06 | 1711 |  | 78912 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 - Hangers |  | 2024-03-07 | Z | 2024-01-19 | 30 | 0 | 0 |  | 20 | 80 |  |  |  | 48
2024-03-04 | 3229 |  | SC-EAD-002 | A | DONE | 36 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2023-11-13 | 410 | 0 | 480 | F | 0 | 1900 |  |  |  | 113
2024-03-06 | 4055 | bth | L2-B-EAD-001 | A | DONE | 20 | S-M |  | CDIS 6220028 | 1" spiral accu. paint | 2024-03-06 | Z | 2024-02-14 | 170 | 70 | 260 | F | 30 | 780 |  |  |  | 21
2024-03-04 | 4056 | bth | L2-B-EAD-003 | A | DONE | 21 | S-M | pt.neal | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 280 | 20 | 220 | F | 0 | 840 |  |  |  | 20
2024-03-06 | 4057 | bth | L2-B-EAD-011 | A | DONE | 14 | S-M | pt.neal | CDIS 6220029 | 1" spiral accu. 1" liner | 2024-03-06 | Z | 2024-02-14 | 240 | 60 | 40 | F | 130 | 390 |  |  |  | 21
2024-03-04 | 4058 | bth | L2-B-EAD-012 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 210 | 20 | 0 |  | 0 | 270 |  |  |  | 20
2024-03-05 | 4059 | bth | L2-B-EAD-013 | A | DONE | 10 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 120 | 50 | 70 | F | 140 | 290 |  |  |  | 20
2024-03-04 | 4060 |  | L2-B-EAD-014 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 120 | 0 | 120 | F | 0 | 280 |  |  |  | 20
2024-03-04 | 4061 | bth | L2-B-EAD-016 | A | DONE | 7 | S | pt.neal | CDIS 6220028 | paint | 2024-03-05 | Z | 2024-02-14 | 80 | 80 | 0 |  | 20 | 170 |  |  |  | 20
2024-03-04 | 4062 |  | L2-B-EAD-017 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 100 | 20 | 60 | F | 0 | 190 |  |  |  | 20
2024-03-04 | 4063 | sp | L2-B-EAD-018 | A | DONE | 10 | S |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 30 | 210 | 0 |  | 0 | 220 |  |  |  | 20
2024-03-04 | 4064 | sp | L2-B-EAD-019 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 20 | 170 | 0 |  | 0 | 180 |  |  |  | 20
2024-03-04 | 4065 | sp | L2-B-EAD-020 | A | DONE | 4 | S-M | pt.neal | CDIS 6220028 | paint | 2024-03-05 | Z | 2024-02-14 | 40 | 30 | 30 | F | 20 | 100 |  |  |  | 20
2024-03-05 | 4066 |  | L2-B-EAD-021 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 30 | 170 | 0 |  | 0 | 190 |  |  |  | 20
2024-03-05 | 4067 |  | L2-B-SALP-017 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 70 | 50 | 0 |  | 40 | 130 |  |  |  | 20
2024-03-04 | 4068 | bth | L2-B-SALP-018 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner paint | 2024-03-05 | Z | 2024-02-14 | 80 | 20 | 20 | F | 40 | 140 |  |  |  | 20
2024-03-05 | 4069 | bth | L2-B-SALP-019 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 60 | 40 | 0 |  | 30 | 110 |  |  |  | 20
2024-03-04 | 4070 | bth | L2-B-SALP-020 | A | DONE | 8 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 170 | 20 | 0 |  | 110 | 220 |  |  |  | 20
2024-03-04 | 4071 |  | L2-B-SALP-021 | A | DONE | 7 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 90 | 0 | 80 | F | 50 | 210 |  |  |  | 20
2024-03-05 | 4072 | bth | L2-B-SALP-022 | A | DONE | 8 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 60 | 20 | 100 | F | 40 | 200 |  |  |  | 20
2024-03-04 | 4073 |  | L2-B-SALP-023 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 40 | 20 | 80 | F | 40 | 160 |  |  |  | 20
2024-03-05 | 4074 |  | L2-B-SALP-024 | A | DONE | 12 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 180 | 100 | 0 |  | 110 | 320 |  |  |  | 20
2024-03-05 | 4075 | bth | L2-B-SALP-025 | A | DONE | 12 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 160 | 40 | 80 | F | 30 | 310 |  |  |  | 20
2024-03-04 | 4076 | bth | L2-B-SALP-026 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 100 | 20 | 120 | F | 0 | 280 |  |  |  | 20
2024-03-05 | 4077 | bth | L2-B-SALP-027 | A | DONE | 8 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 140 | 40 | 0 |  | 70 | 300 |  |  |  | 20
2024-03-05 | 4078 | bth | L2-B-SALP-028 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 130 | 120 | 0 |  | 0 | 250 |  |  |  | 20
2024-03-04 | 4079 | bth | L2-B-SALP-029 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 30 | 20 | 100 | F | 0 | 160 |  |  |  | 20
2024-03-05 | 4080 |  | L2-B-SALP-030 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 70 | 0 | 110 | F | 0 | 210 |  |  |  | 20
2024-03-05 | 4081 | bth | L2-B-SALP-031 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 50 | 60 | 0 |  | 30 | 120 |  |  |  | 20
2024-03-05 | 4082 |  | L2-B-SAMP-001 | A | DONE | 23 | M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 430 | 0 | 130 | F | 0 | 920 |  |  |  | 20
2024-03-05 | 4083 | bth | L2-B-SAMP-007 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 50 | 70 | 120 | F | 0 | 280 |  |  |  | 20
2024-03-04 | 4084 | bth | L2-B-SAMP-008 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 20 | 20 | 80 | F | 0 | 150 |  |  |  | 20
2024-03-04 | 4085 | bth | L2-B-SAMP-009 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 20 | 40 | 70 | F | 0 | 150 |  |  |  | 20
2024-03-05 | 4086 | bth | L2-B-SAMP-011 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 190 | 20 | 100 | F | 0 | 460 |  |  |  | 20
2024-03-05 | 4087 | bth | L2-B-SAMP-012 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 50 | 50 | 60 | F | 0 | 180 |  |  |  | 20
2024-03-05 | 4088 | bth | L2-B-SAMP-013 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 180 | 30 | 60 | F | 0 | 410 |  |  |  | 20
2024-03-05 | 4089 | bth | L2-B-SAMP-014 | A | DONE | 18 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 100 | 50 | 300 | F | 0 | 850 |  |  |  | 20
2024-03-05 | 4090 | bth | L2-B-SAMP-015 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 70 | 40 | 250 | F | 0 | 700 |  |  |  | 20
2024-03-05 | 4091 | bth | L2-B-SAMP-016 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-14 | 90 | 20 | 130 | F | 0 | 290 |  |  |  | 20
2024-03-05 | 4092 |  | L2-B-TAD-001 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-03-05 | Z | 2024-02-14 | 70 | 0 | 40 | F | 80 | 140 |  |  |  | 20
2024-03-05 | 4096 |  | L2-B-EAD-022 | A | DONE | 18 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-15 | 170 | 0 | 260 | F | 0 | 600 |  |  |  | 19
2024-03-05 | 4097 | bth | L2-B-EAD-029 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-15 | 40 | 20 | 130 | F | 0 | 230 |  |  |  | 19
2024-03-04 | 4098 | sp | L2-B-EAD-043 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-15 | 20 | 60 | 0 |  | 0 | 60 |  |  |  | 19
2024-03-05 | 4099 | bth | L2-B-EAD-055 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-15 | 40 | 20 | 20 | F | 0 | 90 |  |  |  | 19
2024-03-05 | 4100 | bth | L2-B-EAD-058 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-15 | 20 | 80 | 40 | F | 0 | 160 |  |  |  | 19
2024-03-05 | 4102 | bth | L2-A-SAMP-060 | A | DONE | 22 | S-M | pt.neal | CDIS 6220028 | s.mates | 2024-03-05 | Z | 2024-02-15 | 200 | 350 | 0 |  | 0 | 850 |  |  |  | 19
2024-03-05 | 4103 |  | L2-A-SAMP-061 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-03-05 | Z | 2024-02-15 | 150 | 0 | 100 | F | 0 | 430 |  |  |  | 19
2024-03-06 | 4105 | bth | L2-B-EAD-002 | A | DONE | 23 | M |  | CDIS 6220030 | 1" spiral accu. 1" liner | 2024-03-06 | Z | 2024-02-15 | 330 | 30 | 200 | F | 60 | 920 |  |  |  | 20 |  | 2024-03-12
2024-03-08 | 4107 | sp | L2-B-EAD-024 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-03-12 | Z | 2024-02-15 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 26 |  | 2024-03-12
2024-03-08 | 4108 | sp | L2-B-EAD-025 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-03-12 | Z | 2024-02-15 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 26 |  | 2024-03-12
2024-03-08 | 4109 | bth | L2-B-SALP-018 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner paint | 2024-03-12 | Z | 2024-02-15 | 100 | 20 | 0 |  | 40 | 140 |  |  |  | 26 |  | 2024-03-12
2024-03-08 | 4110 | bth | L2-B-SALP-034 | A | DONE | 10 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-12 | Z | 2024-02-15 | 160 | 30 | 50 | F | 20 | 250 |  |  |  | 26 |  | 2024-03-12
2024-03-08 | 4111 | bth | L2-B-SALP-035 | A | DONE | 9 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-12 | Z | 2024-02-15 | 130 | 30 | 60 | F | 80 | 280 |  |  |  | 26 |  | 2024-03-12
2024-03-08 | 4112 |  | L2-A-SALP-0104 | A | DONE | 14 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-12 | Z | 2024-02-15 | 300 | 0 | 40 | F | 50 | 480 |  |  |  | 26 |  | 2024-03-12
2024-03-06 | 4211 |  | 61428 | A | DONE | 3 | S-M |  | CDIS 6220028 - Sleeves |  | 2024-03-11 | Z | 2024-02-26 | 70 | 0 | 0 |  | 0 | 130 |  |  |  | 14
2024-03-06 | 4212 |  | 61429 | A | DONE | 4 | S-M |  | CDIS 6220028 - Sleeves |  | 2024-03-11 | Z | 2024-02-26 | 80 | 0 | 0 |  | 0 | 150 |  |  |  | 14
2024-03-08 | 4214 |  | 85994 | A | DONE | 2 | S | alum | CDIS 6220028 - Misc |  | 2024-03-14 | Z | 2024-02-26 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 17
2024-03-07 | 4215 |  | 61430 - 61431 | A | DONE | 2 | S |  | CDIS 6220028 - Test cap |  | 2024-03-12 | Z | 2024-02-27 | 30 | 0 | 0 |  | 0 | 80 |  |  |  | 14
2024-03-08 | 4216 |  | 61431 | A | DONE | 2 | S | alum | CDIS 6220028 - BSMT-C-EAD-12 |  | 2024-03-12 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 14
2024-03-07 | 4217 |  | 61462 | A | DONE | 3 | S |  | CDIS 6220028 - Sleeves / test caps |  | 2024-03-12 | Z | 2024-02-28 | 60 | 0 | 0 |  | 0 | 110 |  |  |  | 13
2024-03-04 | 4222 |  | 94235 - 94236 | A | DONE | 2 | S |  | CDIS 6220028 - Caps |  | 2024-03-05 | Z | 2024-03-04 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-03-08 | 4225 |  | 69801 | A | DONE | 2 | S |  | CDIS 6220028 - Hangers |  | 2024-03-12 | Z | 2024-03-07 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 5
2024-03-07 | 228 |  | 78708 - 7879 | A | DONE | 36 | S-M |  | EGENESIS RTU 4230083 - Outside / Inside |  | 2024-03-08 | Z | 2024-02-28 | 240 | 0 | 660 | F | 0 | 860 |  |  |  | 9
2024-03-07 | 229 | bth | 78710 - 78711 | A | DONE | 7 | S-M |  | EGENESIS RTU 4230083 - Inside |  | 2024-03-08 | Z | 2024-02-28 | 120 | 50 | 0 |  | 0 | 140 |  |  |  | 9
2024-03-08 | 1268 | sp | 70066 | A | DONE | 6 | S |  | EGENESIS PH2 6230026 - CB-3 DOAS-1 SA |  | 2024-03-11 | Z | 2024-02-20 | 80 | 70 | 0 |  | 0 | 170 |  |  |  | 20
2024-03-07 | 1269 | w | 70067 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 - CD-3 curb cap 2" DB |  | 2024-03-11 | Z | 2024-02-20 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 20
2024-03-07 | 1270 | w | 70068 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 - CD-3 roof curb 1-1/2" DB |  | 2024-03-11 | Z | 2024-02-20 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 20
2024-03-08 | 1271 | w | 70069 | A | DONE | 4 | S-M |  | EGENESIS PH2 6230026 - CB-3 equipment rails |  | 2024-03-11 | Z | 2024-02-21 | 100 | 0 | 0 |  | 0 | 230 |  |  |  | 19
2024-03-06 | 1276 |  | 70099 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 - CB-3 |  | 2024-03-11 | Z | 2024-03-04 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-03-05 | 1567 |  | 92400 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 - Bands |  | 2024-03-07 | Z | 2024-03-04 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 3
2024-03-07 | 1568 |  | 62366 - 62367 | A | DONE | 5 | S-M |  | EMBASSY SUITES 6220012 - 1st Floor / Roof |  | 2024-03-11 | Z | 2024-03-04 | 110 | 0 | 0 |  | 0 | 180 |  |  |  | 7
2024-03-08 | 1569 |  | 62425 - 62426 | A | DONE | 10 | S-M |  | EMBASSY SUITES 6220012 - Roof |  | 2024-03-11 | Z | 2024-03-04 | 230 | 0 | 0 |  | 0 | 380 |  |  |  | 7
2024-03-08 | 1570 |  | 62368 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 - DOAS-4 |  | 2024-03-12 | Z | 2024-03-07 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 5
2024-03-07 | 2554 |  | 62520 | A | DONE | 2 | S |  | EXACT BIOSAFE 6230005 - Ceiling EA paint |  | 2024-03-12 | Z | 2024-03-06 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 6
2024-03-07 | 2651 | sp | DT-SALP-01 | A | DONE | 15 | S-M | neal | HARMONICS 6240010 | oval accu | 2024-03-07 | Z | 2024-02-27 | 70 | 300 | 0 |  | 0 | 430 |  |  |  | 9
2024-03-07 | 2652 | sp | DT-SALP-02 | A | DONE | 12 | S-M | neal | HARMONICS 6240010 | oval accu | 2024-03-07 | Z | 2024-02-27 | 50 | 250 | 0 |  | 0 | 340 |  |  |  | 9
2024-03-07 | 2653 | bth | DT-SALP-03 | A | DONE | 11 | S-M | neal | HARMONICS 6240010 | oval accu | 2024-03-07 | Z | 2024-02-27 | 80 | 190 | 0 |  | 0 | 380 |  |  |  | 9
2024-03-06 | 2654 |  | DT-EA-01 | A | DONE | 5 | S-M |  | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 50 | 30 | 30 | F | 0 | 110 |  |  |  | 9
2024-03-06 | 2655 |  | DT-EA-02 | A | DONE | 3 | S | flex | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 60 | 0 | 0 |  | 0 | 70 |  |  |  | 9
2024-03-06 | 2656 |  | DT-EA-03 | A | DONE | 13 | S-M |  | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 170 | 0 | 140 | F | 0 | 360 |  |  |  | 9
2024-03-07 | 2657 |  | DT-EA-04 | A | DONE | 14 | S-M |  | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 140 | 0 | 210 | F | 0 | 420 |  |  |  | 9
2024-03-07 | 2658 |  | DT-OA-01 | A | DONE | 11 | S-M |  | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 200 | 0 | 70 | F | 0 | 310 |  |  |  | 9
2024-03-07 | 2659 |  | DT-OA-02 | A | DONE | 22 | M |  | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 390 | 0 | 160 | F | 0 | 640 |  |  |  | 9
2024-03-07 | 2660 |  | DT-OA-03 | A | DONE | 2 | S |  | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 9
2024-03-07 | 2661 |  | DT-RA-01 | A | DONE | 6 | S-M | flex | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 140 | 0 | 0 |  | 0 | 180 |  |  |  | 9
2024-03-07 | 2662 |  | DT-RA-02 | A | DONE | 6 | S | flex | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 100 | 0 | 40 | F | 0 | 160 |  |  |  | 9
2024-03-07 | 2663 |  | DT-RA-03 | A | DONE | 2 | S | flex | HARMONICS 6240010 |  | 2024-03-07 | Z | 2024-02-27 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 9
2024-03-08 | 222 |  | 66080 | A | DONE | 4 | S-M |  | HILLDALE 6240003 - RTU-10,11 | 3" DB | 2024-03-12 | Z | 2024-02-22 | 80 | 0 | 0 |  | 40 | 130 |  |  |  | 19
2024-03-04 | 412 | sp | 63031 - 63033 | A | DONE | 13 | S-M | pt.alum | MEMORIAL HS 6210024 - W. Exhaust |  | 2024-03-05 | Z | 2023-12-06 | 60 | 250 | 0 |  | 0 | 330 |  |  |  | 90
2024-03-04 | 413 | bth | 63034 - 63036 | A | DONE | 18 | S-M |  | MEMORIAL HS 6210024 - M Supply |  | 2024-03-05 | Z | 2023-12-06 | 100 | 120 | 220 | F | 0 | 500 |  |  |  | 90
2024-03-04 | 414 | sp | 63037 - 63040 | A | DONE | 10 | M |  | MEMORIAL HS 6210024 - ERU |  | 2024-03-05 | Z | 2023-12-06 | 80 | 160 | 0 |  | 0 | 270 |  |  |  | 90
2024-03-04 | 417 | sp | 63045 - 63046 | A | DONE | 8 | S-M |  | MEMORIAL HS 6210024 - Exhaust |  | 2024-03-05 | Z | 2023-12-06 | 40 | 160 | 0 |  | 0 | 230 |  |  |  | 90
2024-03-07 | 419 | sp | 68841 - 68842 | A | DONE | 16 | S-M |  | MEMORIAL HS 6210024 - AHU P1 SA South |  | 2024-03-08 | Z | 2023-12-06 | 80 | 300 | 0 |  | 0 | 400 |  |  |  | 93 |  | 2024-04-02
2024-03-07 | 420 | sp | 68843 - 68845 | A | DONE | 16 | S-M |  | MEMORIAL HS 6210024 - AHU P1 SA North |  | 2024-03-08 | Z | 2023-12-06 | 80 | 300 | 0 |  | 0 | 420 |  |  |  | 93 |  | 2024-04-02
2024-03-07 | 421 |  | 68846 | A | DONE | 5 | S-M |  | MEMORIAL HS 6210024 - AHU P1 RA 1" liner |  | 2024-03-08 | Z | 2023-12-06 | 110 | 0 | 0 |  | 60 | 120 |  |  |  | 93 |  | 2024-04-02
2024-03-07 | 422 | bth | 68847- 68848 | A | DONE | 25 | S-M |  | MEMORIAL HS 6210024 - FCU ERV 1-1 , 1-2 |  | 2024-03-08 | Z | 2023-12-06 | 220 | 280 | 110 | F | 0 | 880 |  |  |  | 93 |  | 2024-04-02
2024-03-08 | 774 |  | 68532 | A | DONE | 3 | S |  | MEMORIAL HS 6210024 | flex | 2024-03-12 | Z | 2024-02-23 | 60 | 0 | 0 |  | 0 | 70 |  |  |  | 18
2024-03-08 | 777 |  | 68535 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 - Roof caps | 1" DB | 2024-03-12 | Z | 2024-02-29 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 12
2024-03-06 | 1942 |  | 59927 | A | DONE | 22 | M |  | MENDOTA FOODS 6220027 - 1st floor RA |  | 2024-03-07 | Z | 2024-02-29 | 180 | 0 | 360 | F | 0 | 790 |  |  |  | 7
2024-03-06 | 1943 | sp | 59928 - 59929 | A | DONE | 6 | S-M |  | MENDOTA FOODS 6220027 - EA / SA |  | 2024-03-07 | Z | 2024-02-29 | 20 | 120 | 0 |  | 0 | 130 |  |  |  | 7
2024-03-06 | 1944 |  | 59930 - 59931 | A | DONE | 23 | M |  | MENDOTA FOODS 6220027 - 1st floor SA |  | 2024-03-07 | Z | 2024-02-29 | 200 | 0 | 370 | F | 0 | 790 |  |  |  | 7
2024-03-06 | 1945 |  | 59932 - 59933 | A | DONE | 32 | M |  | MENDOTA FOODS 6220027 - Basement |  | 2024-03-07 | Z | 2024-02-29 | 180 | 20 | 580 | F | 0 | 960 |  |  |  | 7
2024-03-06 | 1946 | sp | 59934 | A | DONE | 5 | S-M |  | MENDOTA FOODS 6220027 - Basement |  | 2024-03-07 | Z | 2024-02-29 | 30 | 90 | 0 |  | 0 | 120 |  |  |  | 7
2024-03-06 | 1947 |  | 59935 - 59936 | A | DONE | 26 | M |  | MENDOTA FOODS 6220027 - Basement RA East |  | 2024-03-07 | Z | 2024-03-04 | 70 | 0 | 570 | F | 0 | 780 |  |  |  | 3
2024-03-06 | 1948 |  | 59937 | A | DONE | 3 | S-M |  | MENDOTA FOODS 6220027 - Basement RA East |  | 2024-03-07 | Z | 2024-03-04 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 3
2024-03-06 | 1949 |  | 59938 - 59939 | A | DONE | 30 | M |  | MENDOTA FOODS 6220027 - Basement RA West |  | 2024-03-07 | Z | 2024-03-04 | 190 | 0 | 550 | F | 0 | 880 |  |  |  | 3
2024-03-06 | 2500 |  | 59940 | A | DONE | 20 | S-M |  | MENDOTA FOODS 6220027 - Basement SA East |  | 2024-03-07 | Z | 2024-03-04 | 40 | 0 | 450 | F | 0 | 590 |  |  |  | 3
2024-03-05 | 2501 |  | 67425 | A | DONE | 2 | S | bird.s | MENDOTA FOODS 6220027 - Misc |  | 2024-03-07 | Z | 2024-03-04 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 3
2024-03-08 | 3807 | w | 66081 | A | DONE | 2 | S |  | MOXY 6210032 - 2nd fl pan |  | 2024-03-11 | Z | 2024-03-07 | 20 | 0 | 0 |  | 0 | 70 |  |  |  | 4
2024-03-06 | 736 | sp | 71119 - 71120 | A | DONE | 18 | M |  | OLIV 6210030 - Stair # 2 , 3 |  | 2024-03-07 | Z | 2024-01-25 | 80 | 360 | 0 |  | 0 | 460 |  |  |  | 42
2024-03-06 | 737 | sp | 71121 - 71122 | A | DONE | 22 | M |  | OLIV 6210030 - Stair # 1 |  | 2024-03-07 | Z | 2024-01-25 | 90 | 450 | 0 |  | 0 | 570 |  |  |  | 42
2024-03-05 | 2604 |  | 69480 - 69481 | A | DONE | 3 | S-M |  | OLIV 6210030 - Stair 1 |  | 2024-03-07 | Z | 2024-02-15 | 60 | 0 | 0 |  | 0 | 130 |  |  |  | 21
2024-03-06 | 2610 |  | 61131 | A | DONE | 2 | S |  | OLIV 6210030 - Outs |  | 2024-03-07 | Z | 2024-02-29 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-03-08 | 2612 |  | 69491 | A | DONE | 2 | S |  | OLIV 6210030 - LV-3 |  | 2024-03-14 | Z | 2024-03-05 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 9
2024-03-05 | 1962 | w | 62924 | A | DONE | 2 | S-M | ss | PROMEGA FEYNMAN 6220014 - Roof drop |  | 2024-02-29 | Z | 2024-02-16 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 13
2024-03-05 | 1963 | w | 62925 | A | DONE | 2 | S-M | ss | PROMEGA FEYNMAN 6220014 - Roof stack |  | 2024-02-29 | Z | 2024-02-16 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 13
2024-03-05 | 1964 | w | 62927 , 62699 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 - Penthouse |  | 2024-03-06 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 70 |  |  |  | 8
2024-03-05 | 1965 | bth | 62700 | A | DONE | 4 | S-M |  | PROMEGA FEYNMAN 6220014 - Penthouse |  | 2024-03-06 | Z | 2024-02-27 | 60 | 30 | 0 |  | 0 | 100 |  |  |  | 8
2024-03-05 | 1966 |  | 62892 - 62893 | A | DONE | 8 | S-M |  | PROMEGA FEYNMAN 6220014 - RA |  | 2024-03-06 | Z | 2024-02-28 | 180 | 0 | 0 |  | 0 | 230 |  |  |  | 7
2024-03-05 | 1967 | bth | 62894 - 62895 | A | DONE | 10 | S-M |  | PROMEGA FEYNMAN 6220014 - RA |  | 2024-03-06 | Z | 2024-02-28 | 180 | 70 | 0 |  | 0 | 310 |  |  |  | 7
2024-03-06 | 504 | bth | L1-SAMP-5 | A | DONE | 65 | L | semi 3 | RAMC 6230009 |  | 2024-03-18 | Z | 2024-01-31 | 690 | 370 | 560 | F | 0 | 2760 |  |  |  | 47
2024-03-06 | 4722 |  | 78843 - 78846 | A | DONE | 39 | S-M | pcd | ROCK CO. JAIL 6220018 - Generator | flex | 2024-03-07 | Z | 2024-02-28 | 960 | 0 | 0 |  | 0 | 1460 |  |  |  | 8
2024-03-06 | 4721 | w | 72371 | A | DONE | 3 | S-M | ss | ROCK CO. JAIL 6220018 - Kitchen Hood |  | 2024-03-07 | Z | 2024-02-27 | 70 | 0 | 0 |  | 0 | 170 |  |  |  | 9
2024-03-08 | 4728 |  | 78856 | A | DONE | 2 | S | alum | ROCK CO. JAIL 6220018 - Remodel |  | 2024-03-14 | Z | 2024-03-06 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 8
2024-03-08 | 224 | w | 70570 | A | DONE | 2 | S |  | TOMAH HEALTH 4240011 - Box |  | 2024-03-08 | Z | 2024-02-26 | 30 | 0 | 0 |  | 0 | 100 |  |  |  | 11
2024-03-07 | 2000 | bth | 58907 | A | DONE | 69 | M |  | UWL-GRAFF 6230017 - Pent. Temp |  | 2024-03-11 | Z | 2023-12-28 | 340 | 1400 | 0 |  | 0 | 2080 |  |  |  | 74
2024-03-07 | 2001 | w | 58927 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 - Curb cap | 1" poly | 2024-03-11 | Z | 2024-02-14 | 60 | 0 | 0 |  | 40 | 170 |  |  |  | 26
2024-03-07 | 2002 |  | 67961 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 - Pent. Temp |  | 2024-03-11 | Z | 2024-02-14 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 26
2024-03-07 | 2003 |  | 58920 - 58921 | A | DONE | 52 | L |  | UWL-GRAFF 6230017 - AHU-4 SA |  | 2024-03-11 | Z | 2024-02-20 | 430 | 0 | 860 | F | 0 | 2170 |  |  |  | 20
2024-03-07 | 2004 |  | 58922 - 58923 | A | DONE | 104 | M-L |  | UWL-GRAFF 6230017 - AHU-4 RA |  | 2024-03-11 | Z | 2024-02-20 | 1390 | 0 | 1210 | F | 0 | 4220 |  |  |  | 20
2024-03-07 | 2007 |  | 58924 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 - AHU-4 RA |  | 2024-03-11 | Z | 2024-02-20 | 50 | 0 | 90 | F | 0 | 210 |  |  |  | 20
2024-03-06 | 2792 | w | 72696 | A | DONE | 2 | S | ss | UW-VET MED 2230012 - BSL |  | 2024-03-11 | Z | 2024-03-06 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 5
2024-03-07 | 2791 | w | 72692 | A | DONE | 2 | S | ss | UW-VET MED 2230012 - BSL-3 |  | 2024-03-11 | Z | 2024-03-05 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 6
2024-03-07 | 2793 | sp | 72695 | A | DONE | 3 | S |  | UW-VET MED 6210014 - FO #69 |  | 2024-03-11 | Z | 2024-03-06 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 5
2024-03-05 | 1889 |  | 57794 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - |  | 2024-03-08 | Z | 2024-03-01 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 7
2024-03-05 | 1890 |  | 57796 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - |  | 2024-03-08 | Z | 2024-03-01 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-03-07 | 1891 |  | 68986 - 68987 | A | DONE | 5 | S | flex | WCSD HERITAGE 6220024 - |  | 2024-03-08 | Z | 2024-03-01 | 120 | 0 | 0 |  | 0 | 290 |  |  |  | 7
2024-03-06 | 1892 |  | 69025 - 69027 | A | DONE | 2 | S | neal | WCSD HERITAGE 6220024 - |  | 2024-03-08 | Z | 2024-03-01 | 50 | 0 | 0 |  | 20 | 80 |  |  |  | 7
2024-03-07 | 1898 |  | 70531 | A | DONE | 4 | S | neal | WCSD HERITAGE 6220024 - Misc |  | 2024-03-11 | Z | 2024-03-07 | 30 | 70 | 0 |  | 0 | 110 |  |  |  | 4
2024-03-07 | 230 |  | 67076 | A | DONE | 2 | S | bird.s | WHA 10054247 - Squirrel guard |  | 2024-03-08 | Z | 2024-03-04 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 4
[6 empty] | 1509 | [13 empty] | 49250 |  |  |  | 13960 | 28.35%
WEEK OF 3-11-2024
2024-03-14 | 2200 |  | 1STFL-1 / PL-1 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-03-15 | Z | 2024-03-14 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeve caps |  | 1
2024-03-14 | 2201 |  | SM-1 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-03-15 | Z | 2024-03-14 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeve caps |  | 1
2024-03-12 | 231 |  | 70602 | A | DONE | 2 | S |  | ACADIA 8230013 - Plate |  | 2024-03-19 | Z | 2024-03-07 | 30 | 0 | 0 |  | 0 | 100 |  |  |  | 12
2024-03-13 | 1902 | sp | 79601 - 79602 | A | DONE | 5 | S-M |  | ALDEVRON 2230053 |  | 2024-03-14 | Z | 2024-03-12 | 60 | 60 | 0 |  | 0 | 110 |  | LPSA |  | 2
2024-03-14 | 1722 |  | 78923 - 78924 | A | DONE | 8 | S-M | neal | BLACKHAWK BTC 6230025 | flex , bird.s | 2024-03-18 | Z | 2024-03-04 | 180 | 0 | 0 |  | 0 | 320 |  | Lower Lab |  | 14
2024-03-14 | 1723 |  | 78925 - 78926 | A | DONE | 7 | S-M | neal | BLACKHAWK BTC 6230025 | flex , 1" liner | 2024-03-18 | Z | 2024-03-04 | 170 | 0 | 0 |  | 110 | 230 |  | Lower Lab |  | 14
2024-03-13 | 1725 |  | 78928 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-03-18 | Z | 2024-03-04 | 20 | 0 | 0 |  | 20 | 50 |  | Hangers |  | 14
2024-03-12 | 1726 | w | 68013 | A | DONE | 2 | S |  | BLACKHAWK BTC 6230025 - Roof caps 1" DB |  | 2024-03-18 | Z | 2024-03-04 | 50 | 0 | 0 |  | 20 | 130 |  |  |  | 14
2024-03-12 | 2101 |  | 73200 | A | DONE | 10 | S-M |  | CBOC 6220026 - AHU-1 OA | flex | 2024-03-13 | Z | 2024-03-05 | 240 | 0 | 0 |  | 0 | 590 |  |  |  | 8
2024-03-12 | 2100 |  | 73199 | A | DONE | 5 | S-M |  | CBOC 6220026 - AHU-1 SA | 1" liner , flex | 2024-03-13 | Z | 2024-03-05 | 120 | 0 | 0 |  | 70 | 260 |  |  |  | 8
2024-03-11 | 4106 | bth | L2-B-EAD-023 | A | DONE | 24 | S-M |  | CDIS 6220028 | 1" spiral accu. | 2024-03-12 | Z | 2024-02-15 | 260 | 120 | 220 | F | 110 | 730 |  |  |  | 26
2024-03-11 | 4113 |  | L2-A-SALP-0105 | A | DONE | 13 | S-M | neal | CDIS 6220028 |  | 2024-03-12 | Z | 2024-02-15 | 270 | 0 | 40 | F | 0 | 430 |  |  |  | 26
2024-03-11 | 4114 |  | L2-A-SALP-0106 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-03-12 | Z | 2024-02-15 | 80 | 0 | 80 | F | 0 | 200 |  |  |  | 26
2024-03-11 | 4115 |  | L2-A-SALP-0107 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-03-12 | Z | 2024-02-15 | 130 | 0 | 60 | F | 0 | 290 |  |  |  | 26
2024-03-15 | 4128 | bth | L2-A-SAMP-049 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 110 | 70 | 110 | F | 0 | 500 |  |  |  | 33
2024-03-15 | 4135 | bth | L2-A-SAMP-056 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 220 | 20 | 0 |  | 0 | 340 |  |  |  | 33
2024-03-14 | 4136 | bth | L2-A-SAMP-057 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 150 | 20 | 140 | F | 0 | 410 |  |  |  | 33
2024-03-15 | 4137 |  | L2-A-SAMP-058 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 150 | 0 | 0 |  | 0 | 270 |  |  |  | 33
2024-03-15 | 4138 | bth | L2-A-SAMP-059 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 50 | 90 | 40 | F | 0 | 190 |  |  |  | 33
2024-03-12 | 4213 |  | 61459 , 61461 | A | DONE | 15 | S-M | alum | CDIS 6220028 - Pit 167-10 relief |  | 2024-03-14 | Z | 2024-02-26 | 280 | 0 | 80 | F | 0 | 210 |  |  |  | 17
2024-03-12 | 4219 | bth | 69951 - 69952 | A | DONE | 7 | S-M | neal | CDIS 6220028 - EAD 008 |  | 2024-03-14 | Z | 2024-03-04 | 120 | 30 | 20 | F | 0 | 190 |  |  |  | 10
2024-03-12 | 4220 | bth | 69953 - 69954 | A | DONE | 7 | S-M |  | CDIS 6220028 - SA Mezz |  | 2024-03-14 | Z | 2024-03-04 | 70 | 30 | 70 | F | 0 | 190 |  |  |  | 10
2024-03-11 | 4221 |  | SC-EAD-004 | A | DONE | 59 | L |  | CDIS 6220028 | partial | 2024-03-12 | Z | 2024-03-04 | 1100 | 0 | 370 | F | 0 | 3800 |  |  |  | 8
2024-03-12 | 4226 |  | 61435 | A | DONE | 3 | S |  | CDIS 6220028 - A SAMP 037 |  | 2024-03-14 | Z | 2024-03-08 | 60 | 0 | 0 |  | 0 | 70 |  |  |  | 6
2024-03-14 | 4228 |  | 61438 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-03-12 | 20 | 0 | 80 | F | 0 | 130 |  | SAMP-43 |  | 7
2024-03-13 | 4229 |  | 61439 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-03-12 | 30 | 0 | 0 |  | 0 | 50 |  | Test caps |  | 7
2024-03-13 | 4232 | w | 85998 - 85999 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-15 | Z | 2024-03-13 | 40 | 0 | 0 |  | 0 | 40 |  | Rod oven divider |  | 2
2024-03-14 | 4232 |  | 61440 | A | DONE | 2 | S | alum | CDIS 6220028 |  | 2024-03-19 | Z | 2024-03-13 | 20 | 0 | 0 |  | 0 | 20 |  | Draw band |  | 6
2024-03-15 | 255 |  | 70280 | A | DONE | 3 | S |  | COMPASS ESSER 4240010 |  | 2024-03-18 | Z | 2024-03-14 | 70 | 0 | 0 |  | 0 | 80 |  | HP Swap |  | 4
2024-03-12 | 244 |  | 67150 | A | DONE | 2 | S |  | EGENESIS 4230083 |  | 2024-03-12 | Z | 2024-03-12 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-03-13 | 245 |  | 78713 | A | DONE | 2 | S |  | EGENESIS 4230083 |  | 2024-03-13 | Z | 2024-03-13 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 0
2024-03-13 | 252 |  | 78714 | A | DONE | 2 | S |  | EGENESIS 4230083 |  | 2024-03-13 | Z | 2024-03-13 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-03-14 | 254 | bth | 78715 - 78716 | A | DONE | 9 | S-M |  | EGENESIS 4230083 |  | 2024-03-14 | Z | 2024-03-14 | 110 | 20 | 90 | F | 0 | 190 |  | Misc |  | 0
2024-03-11 | 2553 |  | 61034 | A | DONE | 10 | S-M |  | EXACT BIOSAFE 6230005 - RTU-1 | spiral mates | 2024-03-12 | Z | 2024-03-05 | 70 | 160 | 0 |  | 0 | 350 |  |  |  | 7
2024-03-15 | 2555 |  | 78447 - 78448 | A | DONE | 2 | S | pt.ss | EXACT BIOSAFE 8230004 |  | 2024-03-21 | Z | 2024-03-07 | 20 | 0 | 0 |  | 0 | 20 |  | Floor sink covers |  | 14
2024-03-14 | 2556 |  | 42199 - 421200 | A | DONE | 4 | S-M |  | EXACT BIOSAFE 6230005 |  | 2024-03-19 | Z | 2024-03-11 | 100 | 0 | 0 |  | 0 | 120 |  | F-1 , 2 |  | 8
2024-03-14 | 650 |  | 70100 | A | DONE | 3 | S |  | GRAND AVE. ES 6230012 |  | 2024-03-25 | Z | 2024-02-16 | 60 | 0 | 0 |  | 0 | 100 |  | Storage Rm wall blank off |  | 38
2024-03-13 | 2664 |  | 69404 | A | DONE | 2 | S | neal | HARMONICS 6240010 |  | 2024-03-14 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 30 |  | Hangers |  | 16
2024-03-13 | 2665 |  | SO-EA-01 | A | DONE | 6 | S-M |  | HARMONICS 6240010 | flex | 2024-03-14 | Z | 2024-02-29 | 110 | 0 | 40 | F | 0 | 170 |  |  |  | 14
2024-03-13 | 2666 | bth | SO-EA-02 | A | DONE | 4 | S-M |  | HARMONICS 6240010 | flex | 2024-03-14 | Z | 2024-02-29 | 60 | 20 | 0 |  | 0 | 80 |  |  |  | 14
2024-03-13 | 2667 |  | SO-OA-01 | A | DONE | 10 | S-M |  | HARMONICS 6240010 | flex | 2024-03-14 | Z | 2024-02-29 | 170 | 0 | 70 | F | 0 | 280 |  |  |  | 14
2024-03-13 | 2668 |  | SO-OA-02 | A | DONE | 2 | S-M |  | HARMONICS 6240010 |  | 2024-03-14 | Z | 2024-02-29 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 14
2024-03-13 | 2669 |  | SO-OA-03 | A | DONE | 2 | S-M |  | HARMONICS 6240010 |  | 2024-03-14 | Z | 2024-02-29 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 14
2024-03-13 | 2670 |  | SO-RA-01 | A | DONE | 6 | S-M |  | HARMONICS 6240010 | flex | 2024-03-14 | Z | 2024-02-29 | 150 | 0 | 0 |  | 0 | 170 |  |  |  | 14
2024-03-13 | 2671 | bth | SO-RA-02 | A | DONE | 9 | S-M |  | HARMONICS 6240010 | flex | 2024-03-14 | Z | 2024-02-29 | 200 | 20 | 0 |  | 0 | 250 |  |  |  | 14
2024-03-12 | 2672 | sp | SO-SALP-01 | A | DONE | 9 | S-M | neal | HARMONICS 6240010 | oval | 2024-03-14 | Z | 2024-02-29 | 60 | 160 | 0 |  | 0 | 260 |  |  |  | 14
2024-03-13 | 2673 |  | SO-SALP-02 | A | DONE | 15 | S-M |  | HARMONICS 6240010 |  | 2024-03-14 | Z | 2024-02-29 | 210 | 0 | 160 | F | 0 | 430 |  |  |  | 14
2024-03-15 | 256 |  | 70105 | A | DONE | 2 | S | ss | INVENRA 6230001 |  | 2024-03-18 | Z | 2024-03-14 | 20 | 20 | 0 |  | 0 | 30 |  | Fume Hood |  | 4
2024-03-14 | 2804 |  | 66066 - 66067 | A | DONE | 12 | S-M |  | JANESVILLE ESSR 6230011 | flex , 2" liner | 2024-03-18 | Z | 2024-01-31 | 170 | 0 | 120 | F | 210 | 340 |  | Storage 120 |  | 47
2024-03-14 | 2805 |  | 66068 - 66069 | A | DONE | 16 | S-M |  | JANESVILLE ESSR 6230011 | flex , 1" liner | 2024-03-18 | Z | 2024-01-31 | 190 | 0 | 210 | F | 250 | 470 |  | Storage 120 |  | 47
2024-03-14 | 2806 |  | 66070 - 66071 | A | DONE | 10 | S-M |  | JANESVILLE ESSR 6230011 | flex , 1" liner | 2024-03-18 | Z | 2024-01-31 | 200 | 0 | 30 | F | 50 | 260 |  | Storage 120 |  | 47
2024-03-15 | 2812 |  | 70810 - 70811 | A | DONE | 3 | S |  | JANESVILLE ESSR 6230011 | 2" liner | 2024-03-18 | Z | 2024-03-14 | 70 | 0 | 0 |  | 60 | 100 |  | BCU 2,3 SA |  | 4
2024-03-11 | 3725 |  | 63350 | A | DONE | 2 | S |  | KOHL CENTER 6210034 - channel | paint | 2024-03-11 | Z | 2024-03-11 | 30 | 0 | 0 |  | 30 | 50 |  |  |  | 0
2024-03-14 | 779 |  | 68537 - 68358 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-03-19 | Z | 2024-03-05 | 60 | 0 | 0 |  | 30 | 120 |  | Pipe dog house |  | 14
2024-03-13 | 780 |  | 68539 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-03-19 | Z | 2024-03-05 | 30 | 0 | 0 |  | 30 | 80 |  | End caps |  | 14
2024-03-11 | 781 | w | 68540 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 - Duct wall supports |  | 2024-03-12 | Z | 2024-03-07 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 5
2024-03-15 | 783 |  | 68542 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-03-26 | Z | 2024-03-12 | 30 | 0 | 0 |  | 0 | 60 |  | Stadium |  | 14
2024-03-12 | 2502 |  | 59941 | A | DONE | 15 | S-M |  | MENDOTA FOODS 6220027 - Basement SA |  | 2024-03-14 | Z | 2024-03-04 | 130 | 0 | 230 | F | 0 | 430 |  |  |  | 10
2024-03-12 | 2503 | sp | 59942 - 59943 | A | DONE | 6 | S-M |  | MENDOTA FOODS 6220027 - Basement SA |  | 2024-03-14 | Z | 2024-03-04 | 40 | 110 | 0 |  | 0 | 140 |  |  |  | 10
2024-03-12 | 2504 |  | 59944 - 59945 | A | DONE | 20 | S-M | alum | MENDOTA FOODS 6220027 - Basement EA |  | 2024-03-14 | Z | 2024-03-04 | 170 | 0 | 330 | F | 0 | 330 |  |  |  | 10
2024-03-11 | 2505 | bth | 59946 - 59947 | A | DONE | 7 | S-M | alum | MENDOTA FOODS 6220027 - Basement EA |  | 2024-03-14 | Z | 2024-03-04 | 90 | 50 | 30 | F | 0 | 110 |  |  |  | 10
2024-03-12 | 2506 | bth | 59948 - 59949 | A | DONE | 16 | S-M |  | MENDOTA FOODS 6220027 - Basement SALP |  | 2024-03-14 | Z | 2024-03-04 | 120 | 40 | 240 | F | 0 | 460 |  |  |  | 10
2024-03-12 | 2507 | sp | 67427 | A | DONE | 8 | S-M |  | MENDOTA FOODS 6220027 - Basement SALP |  | 2024-03-14 | Z | 2024-03-04 | 30 | 170 | 0 |  | 0 | 190 |  |  |  | 10
2024-03-13 | 2508 |  | 67428 | A | DONE | 5 | S-M |  | MENDOTA FOODS 6220027 | paint | 2024-03-14 | Z | 2024-03-04 | 60 | 0 | 50 | F | 30 | 140 |  | Basement Duct |  | 10
2024-03-12 | 2527 |  | 67454 | A | DONE | 5 | S-M |  | MENDOTA FOODS 6220027 - Basement SA East |  | 2024-03-14 | Z | 2024-03-08 | 60 | 0 | 60 | F | 0 | 160 |  |  |  | 6
2024-03-13 | 2528 |  | 67455 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | 1" liner, paint | 2024-03-14 | Z | 2024-03-11 | 20 | 0 | 0 |  | 20 | 20 |  | TA |  | 3
2024-03-15 | 2544 |  | 67456 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 | paint | 2024-03-21 | Z | 2024-03-13 | 20 | 0 | 0 |  | 20 | 40 |  | Grille Finish |  | 8
2024-03-14 | 2546 |  | 67459 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-03-14 | Z | 2024-03-14 | 20 | 0 | 0 |  | 0 | 20 |  | HP tap |  | 0
2024-03-13 | 2611 |  | 69490 | A | DONE | 10 | S-M |  | OLIV 6210030 | birdscreen , paint | 2024-03-14 | Z | 2024-03-05 | 240 | 0 | 0 |  | 50 | 530 |  | LV-3 |  | 9
2024-03-15 | 2613 |  | 61132 | A | DONE | 4 | S-M |  | OLIV 6210030 | flex , paint | 2024-03-21 | Z | 2024-03-12 | 90 | 0 | 0 |  | 20 | 150 |  | MAU-1 |  | 9
2024-03-11 | 312 |  | 70571 | A | DONE | 16 | S-M |  | PP 10054214 - Flat metal |  | 2024-03-11 | Z | 2024-03-11 | 400 | 0 | 0 |  | 0 | 870 |  |  |  | 0
2024-03-12 | 1968 | bth | 62928 - 62929 | A | DONE | 14 | M |  | PROMEGA FEYNMAN 6220014 - 1st floor |  | 2024-03-13 | Z | 2024-03-05 | 170 | 160 | 0 |  | 0 | 380 |  |  |  | 8
2024-03-12 | 1970 |  | 62930 | A | DONE | 5 | S |  | PROMEGA FEYNMAN 6220014 - 1st floor |  | 2024-03-13 | Z | 2024-03-07 | 40 | 70 | 0 |  | 0 | 120 |  |  |  | 6
2024-03-14 | 500 | sp | L1-SAMP-1 | A | DONE | 16 | S-M | semi 4 | RAMC 6230009 | oval | 2024-03-18 | Z | 2024-01-31 | 110 | 290 | 0 |  | 0 | 490 |  |  |  | 47
2024-03-14 | 501 | bth | L1-SAMP-2 | A | DONE | 19 | M | semi 4 | RAMC 6230009 | oval | 2024-03-18 | Z | 2024-01-31 | 130 | 330 | 0 |  | 0 | 500 |  |  |  | 47
2024-03-14 | 502 | sp | L1-SAMP-3 | A | DONE | 28 | M | semi 3 | RAMC 6230009 | oval | 2024-03-18 | Z | 2024-01-31 | 150 | 550 | 0 |  | 0 | 860 |  |  |  | 47
2024-03-14 | 503 | sp | L1-SAMP-4 | A | DONE | 18 | M | semi 3 | RAMC 6230009 | oval | 2024-03-18 | Z | 2024-01-31 | 20 | 410 | 0 |  | 0 | 560 |  |  |  | 47
2024-03-15 | 506 | sp | L1-SAMP-7 | A | DONE | 26 | M | semi 4 | RAMC 6230009 | oval | 2024-03-18 | Z | 2024-01-31 | 100 | 530 | 0 |  | 0 | 750 |  |  |  | 47
2024-03-11 | 4533 | w | 72373 | A | DONE | 2 | S |  | RAMC 6230009 - Roof Curb | 1" DB | 2024-03-12 | Z | 2024-03-07 | 50 | 0 | 0 |  | 20 | 130 |  |  |  | 5
2024-03-15 | 4534 |  | 72372 | A | DONE | 4 | S |  | RAMC 6230009 |  | 2024-03-18 | Z | 2024-03-07 | 100 | 0 | 0 |  | 0 | 180 |  | Roof Cap / Drop |  | 11
2024-03-13 | 4723 |  | 78848 | A | DONE | 5 | S-M |  | ROCK CO. JAIL 6220018 | paint | 2024-03-14 | Z | 2024-03-04 | 110 | 0 | 0 |  | 70 | 130 |  | Area F1 |  | 10
2024-03-12 | 4724 | bth | 78847 | A | DONE | 8 | S-M | pt.alum | ROCK CO. JAIL 6220018 - Area F1 |  | 2024-03-14 | Z | 2024-03-04 | 50 | 140 | 0 |  | 0 | 180 |  |  |  | 10
2024-03-13 | 4725 |  | 78849 | A | DONE | 5 | S-M |  | ROCK CO. JAIL 6220018 | birdscreen | 2024-03-14 | Z | 2024-03-04 | 120 | 0 | 0 |  | 0 | 290 |  | Generator |  | 10
2024-03-13 | 4726 |  | 78850 | A | DONE | 3 | S-M |  | ROCK CO. JAIL 6220018 |  | 2024-03-14 | Z | 2024-03-04 | 60 | 0 | 0 |  | 0 | 70 |  | Misc |  | 10
2024-03-13 | 4727 |  | 78855 | A | DONE | 11 | S | alum | ROCK CO. JAIL 6220018 |  | 2024-03-14 | Z | 2024-03-06 | 120 | 150 | 0 |  | 0 | 150 |  | Locker Rm |  | 8
2024-03-15 | 4729 |  | 78857 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 | flex | 2024-03-21 | Z | 2024-03-07 | 20 | 0 | 0 |  | 0 | 20 |  | Fan |  | 14
2024-03-12 | 4731 |  | 78859 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 - Generator |  | 2024-03-14 | Z | 2024-03-12 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 2
2024-03-11 | 2005 |  | 58913 - 58914 | A | DONE | 69 | L |  | UWL-GRAFF 6230017 - AHU-5 RA |  | 2024-03-13 | Z | 2024-02-20 | 1710 | 0 | 0 |  | 0 | 5110 |  |  |  | 22
2024-03-11 | 2006 |  | 58910 - 58912 | A | DONE | 30 | M-L |  | UWL-GRAFF 6230017 - AHU-5 SA |  | 2024-03-13 | Z | 2024-02-20 | 420 | 0 | 310 | F | 0 | 1210 |  |  |  | 22
2024-03-11 | 2008 |  | 58915 - 58916 | A | DONE | 47 | M-L |  | UWL-GRAFF 6230017 - AHU-5 RA |  | 2024-03-13 | Z | 2024-02-20 | 410 | 0 | 750 | F | 0 | 1760 |  |  |  | 22
2024-03-12 | 2009 |  | 58917 - 58918 | A | DONE | 37 | M-L |  | UWL-GRAFF 6230017 - AHU-5 RA |  | 2024-03-13 | Z | 2024-02-20 | 530 | 0 | 380 | F | 0 | 1910 |  |  |  | 22
2024-03-12 | 2010 |  | 58919 | A | DONE | 53 | L |  | UWL-GRAFF 6230017 - AHU-5 OA |  | 2024-03-13 | Z | 2024-02-20 | 1320 | 0 | 0 |  | 0 | 3370 |  |  |  | 22
2024-03-15 | 4850 |  | 70574 | A | DONE | 2 | S | BI | UWRF 6230010 |  | 2024-03-15 | Z | 2024-03-15 | 20 | 0 | 0 |  | 0 | 40 |  | Gasket |  | 0
2024-03-13 | 2794 | w | 72697 - 72699 | A | DONE | 2 | S-M | ss | UW-VET MED 2230012 |  | 2024-03-18 | Z | 2024-03-08 | 30 | 0 | 0 |  | 0 | 80 |  | BSL-3 |  | 10
2024-03-12 | 1893 |  | 68988 | A | DONE | 5 | S-M | neal | WCSD HERITAGE 6220024 - Gym Grilles |  | 2024-03-13 | Z | 2024-03-05 | 120 | 0 | 0 |  | 0 | 150 |  |  |  | 8
2024-03-13 | 1894 |  | 57797 | A | DONE | 4 | S-M | neal | WCSD HERITAGE 6220024 |  | 2024-03-14 | Z | 2024-03-07 | 90 | 0 | 0 |  | 0 | 170 |  | Gym Duct |  | 7
2024-03-13 | 1895 |  | 69202 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 |  | 2024-03-15 | Z | 2024-03-07 | 30 | 0 | 0 |  | 0 | 50 |  | Ceiling tie-ins |  | 8
2024-03-13 | 1896 |  | 69203 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 | 1" liner | 2024-03-15 | Z | 2024-03-07 | 50 | 0 | 0 |  | 30 | 80 |  | Ceiling tie-ins |  | 8
2024-03-13 | 1897 |  | 69204 - 69206 | A | DONE | 4 | S-M |  | WCSD HERITAGE 6220024 |  | 2024-03-15 | Z | 2024-03-07 | 80 | 0 | 0 |  | 0 | 120 |  | Ceiling tie-ins |  | 8
2024-03-13 | 1899 |  | 69207 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 |  | 2024-03-15 | Z | 2024-03-07 | 30 | 0 | 0 |  | 0 | 50 |  | Ceiling tie-ins |  | 8
2024-03-13 | 2250 |  | 69208 - 69209 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 |  | 2024-03-15 | Z | 2024-03-08 | 40 | 0 | 0 |  | 0 | 50 |  | 1st fl plenum boxes |  | 7
2024-03-13 | 2251 |  | 57798 - 57799 | A | DONE | 2 | S | pt.neal | WCSD HERITAGE 6220024 |  | 2024-03-15 | Z | 2024-03-08 | 40 | 0 | 0 |  | 0 | 60 |  |  |  | 7
2024-03-11 | 2252 |  | 68989 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 - HP |  | 2024-03-13 | Z | 2024-03-11 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 2
2024-03-14 | 2253 |  | 70572 | A | DONE | 2 | S | neal | WCSD HERITAGE 6220024 |  | 2024-03-14 | Z | 2024-03-14 | 20 | 0 | 0 |  | 0 | 60 |  | Tear drop hangers |  | 0
2024-03-15 | 257 | bth | 70101 | A | DONE | 2 | S |  | WICELL 2230040 | 1/2" liner | 2024-03-18 | Z | 2024-03-14 | 40 | 20 | 0 |  | 20 | 60 |  | TA |  | 4
2024-03-15 | 258 | sp | 70104 | A | DONE | 2 | S | pt.pcd | WICELL 2230040 |  | 2024-03-18 | Z | 2024-03-14 | 20 | 20 | 0 |  | 0 | 40 |  | EA |  | 4
[6 empty] | 959 | [13 empty] | 36940 |  |  |  | 12890 | 34.89%
WEEK OF 3-18-2024
2024-03-21 | 1715 | sp | 78918 | A | DONE | 3 | S |  | BLACKHAWK BTC 6230025 |  | 2024-03-28 | Z | 2024-01-19 | 0 | 60 | 0 |  | 0 | 60 |  | Stairway |  | 69 |  | 2024-03-14
2024-03-22 | 1716 |  | 78919 - 78920 | A | DONE | 27 | S-M | neal | BLACKHAWK BTC 6230025 | 1" liner | 2024-03-28 | Z | 2024-01-19 | 90 | 0 | 570 | F | 570 | 930 |  | Welding lab |  | 69 |  | 2024-03-14
2024-03-19 | 1724 | sp | 78927 | A | DONE | 9 | S-M | neal | BLACKHAWK BTC 6230025 | 1" spiral accu | 2024-03-18 | Z | 2024-03-04 | 40 | 170 | 0 |  | 180 | 250 |  | Lower Lab |  | 14
2024-03-20 | 1727 | sp | 78929 | A | DONE | 9 | S-M | neal | BLACKHAWK BTC 6230025 | birdscreen | 2024-03-21 | Z | 2024-03-08 | 110 | 110 | 0 |  | 0 | 250 |  | Intake |  | 13
2024-03-18 | 263 |  | 78717 | A | DONE | 2 | S |  | BROWNPOINT 10054346 |  | 2024-03-20 | Z | 2024-03-18 | 30 | 0 | 0 |  | 0 | 70 |  | Misc |  | 2
2024-03-18 | 3514 |  | 94242 | A | DONE | 2 | S | BI | CDIS 6220028 |  | 2024-03-18 | Z | 2024-03-18 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 0
2024-03-18 | 4116 | bth | L2-A-EAD-044 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 50 | 60 | 120 | F | 0 | 300 |  |  |  | 33
2024-03-18 | 4117 | bth | L2-A-EAD-045 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 20 | 60 | 40 | F | 0 | 140 |  |  |  | 33
2024-03-18 | 4118 | bth | L2-A-EAD-047 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 20 | 90 | 40 | F | 0 | 170 |  |  |  | 33
2024-03-18 | 4119 | sp | L2-A-EAD-048 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 30 | 120 | 40 | F | 0 | 200 |  |  |  | 33
2024-03-18 | 4120 | bth | L2-A-EAD-049 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 50 | 40 | 120 | F | 0 | 280 |  |  |  | 33
2024-03-18 | 4121 | bth | L2-A-EAD-050 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 20 | 80 | 160 | F | 0 | 320 |  |  |  | 33
2024-03-18 | 4122 | bth | L2-A-EAD-052 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 210 | 20 | 70 | F | 0 | 410 |  |  |  | 33
2024-03-18 | 4123 | bth | L2-A-EAD-053 | A | DONE | 8 | S-M |  | CDIS 6220028 | paint | 2024-03-19 | Z | 2024-02-15 | 50 | 90 | 40 | F | 20 | 190 |  |  |  | 33
2024-03-18 | 4124 | bth | L2-A-EAD-054 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 | paint | 2024-03-19 | Z | 2024-02-15 | 90 | 40 | 70 | F | 20 | 250 |  |  |  | 33
2024-03-18 | 4125 | bth | L2-A-EAD-057 | A | DONE | 15 | S-M | pt.neal | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 230 | 20 | 110 | F | 0 | 500 |  |  |  | 33
2024-03-18 | 4126 | bth | L2-A-SAMP-043 | A | DONE | 20 | M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 240 | 40 | 220 | F | 0 | 900 |  |  |  | 33
2024-03-18 | 4127 | bth | L2-A-SAMP-048 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 130 | 80 | 110 | F | 0 | 570 |  |  |  | 33
2024-03-18 | 4129 | bth | L2-A-SAMP-050 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 20 | 80 | 220 | F | 0 | 570 |  |  |  | 33
2024-03-18 | 4130 | bth | L2-A-SAMP-051 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 30 | 60 | 170 | F | 0 | 450 |  |  |  | 33
2024-03-18 | 4131 | bth | L2-A-SAMP-052 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 80 | 60 | 60 | F | 0 | 290 |  |  |  | 33
2024-03-18 | 4132 | bth | L2-A-SAMP-053 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 120 | 40 | 40 | F | 0 | 250 |  |  |  | 33
2024-03-18 | 4133 | bth | L2-A-SAMP-054 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 40 | 40 | 70 | F | 0 | 180 |  |  |  | 33
2024-03-18 | 4134 | sp | L2-A-SAMP-055 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-03-19 | Z | 2024-02-15 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 33
2024-03-21 | 4139 | bth | L2-A-EAD-026 | A | DONE | 28 | M | neal | CDIS 6220028 | paint | 2024-03-26 | Z | 2024-02-15 | 530 | 20 | 130 | F | 0 | 1030 |  |  |  | 40
2024-03-21 | 4140 |  | L2-A-EAD-027 | A | DONE | 20 | M | neal | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 350 | 0 | 150 | F | 0 | 780 |  |  |  | 40
2024-03-22 | 4141 | bth | L2-A-EAD-032 | A | DONE | 18 | S-M | pt.neal | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 240 | 80 | 110 | F | 0 | 670 |  |  |  | 40
2024-03-21 | 4142 |  | L2-A-EAD-033 | A | DONE | 32 | M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 680 | 0 | 100 | F | 0 | 1260 |  |  |  | 40
2024-03-22 | 4143 | bth | L2-A-EAD-037 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 60 | 60 | 0 |  | 0 | 140 |  |  |  | 40
2024-03-21 | 4144 | bth | L2-A-EAD-038 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 50 | 20 | 0 |  | 0 | 80 |  |  |  | 40
2024-03-22 | 4145 | sp | L2-A-EAD-039 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 40
2024-03-21 | 4146 | sp | L2-A-EAD-040 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 40
2024-03-21 | 4147 | bth | L2-A-SAMP-038 | A | DONE | 22 | S-M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 140 | 30 | 370 | F | 0 | 1020 |  |  |  | 40
2024-03-21 | 4148 | bth | L2-A-SAMP-039 | A | DONE | 28 | M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 440 | 20 | 240 | F | 0 | 1290 |  |  |  | 40
2024-03-21 | 4149 | bth | L2-A-SAMP-040 | A | DONE | 21 | M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 310 | 20 | 190 | F | 0 | 870 |  |  |  | 40
2024-03-21 | 4150 | bth | L2-A-SAMP-041 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 60 | 20 | 40 | F | 0 | 130 |  |  |  | 40
2024-03-22 | 4151 | bth | L2-A-SAMP-042 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 170 | 30 | 170 | F | 0 | 660 |  |  |  | 40
2024-03-21 | 4152 |  | L2-A-SAMP-044 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 200 | 0 | 150 | F | 0 | 520 |  |  |  | 40
2024-03-21 | 4153 | bth | L2-A-SAMP-045 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 170 | 30 | 40 | F | 0 | 270 |  |  |  | 40
2024-03-21 | 4154 | bth | L2-A-SAMP-046 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 60 | 20 | 40 | F | 0 | 140 |  |  |  | 40
2024-03-21 | 4155 | bth | L2-A-SAMP-047 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 100 | 20 | 20 | F | 0 | 150 |  |  |  | 40
2024-03-18 | 4224 |  | 61432 | A | DONE | 2 | S |  | CDIS 6220028 | 1" spiral accu | 2024-03-19 | Z | 2024-03-05 | 20 | 20 | 0 |  | 20 | 30 |  | Basement EAD 43 |  | 14
2024-03-20 | 4227 |  | 61436 - 61437 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-03-25 | Z | 2024-03-11 | 160 | 0 | 0 |  | 0 | 300 |  | Sleeves |  | 14
2024-03-19 | 4233 | bth | 61442 - 61443 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-03-21 | Z | 2024-03-13 | 30 | 20 | 0 |  | 0 | 50 |  | AHU-3 , SAMP 38 |  | 8
2024-03-21 | 4234 |  | 61441 | A | DONE | 3 | S |  | CDIS 6220028 | flex | 2024-03-26 | Z | 2024-03-13 | 60 | 0 | 0 |  | 0 | 140 |  | AHU-2 SA |  | 13
2024-03-18 | 4293 |  | 86124 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-18 | Z | 2024-03-18 | 20 | 0 | 0 |  | 0 | 30 |  | Cap |  | 0
2024-03-18 | 4294 |  | 69851 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-21 | Z | 2024-03-18 | 50 | 0 | 0 |  | 0 | 110 |  | 1st floor |  | 3
2024-03-21 | 4230 |  | 69803 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-03-12 | 40 | 0 | 0 |  | 0 | 80 |  | Hangers |  | 14
2024-03-22 | 276 |  | 70220 | A | DONE | 7 | S-M |  | COMPASS ESSER 4240010 |  | 2024-03-28 | Z | 2024-03-20 | 170 | 0 | 0 |  | 0 | 170 |  | Misc |  | 8
2024-03-18 | 1571 | w | 70532 | A | DONE | 2 | S | ss | EMBASSY SUITES 6220012 |  | 2024-03-20 | Z | 2024-03-07 | 20 | 0 | 0 |  | 0 | 40 |  | Elbows |  | 13
2024-03-18 | 1572 |  | 62369 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 |  | 2024-03-20 | Z | 2024-03-14 | 50 | 0 | 0 |  | 0 | 60 |  | Roof |  | 6
2024-03-22 | 1573 |  | 62370 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 |  | 2024-03-26 | Z | 2024-03-21 | 30 | 0 | 0 |  | 0 | 30 |  | Angles |  | 5
2024-03-22 | 2557 | w | 42198 | A | DONE | 2 | S-M |  | EXACT BIOSAFE 6230005 |  | 2024-03-26 | Z | 2024-03-11 | 50 | 0 | 0 |  | 0 | 130 |  | Pipe Portal |  | 15
2024-03-21 | 269 |  | 41925 | A | DONE | 3 | S |  | FAIRCHILD 20008537 | paint | 2024-03-28 | Z | 2024-03-19 | 60 | 0 | 0 |  | 60 | 70 |  | Grille boxes |  | 9
2024-03-19 | 4600 |  | 69495 | A | DONE | 12 | S |  | HARMONICS 6240010 |  | 2024-03-21 | Z | 2024-03-15 | 300 | 0 | 0 |  | 0 | 310 |  | Double tap SA |  | 6
2024-03-22 | 4601 | w | 87749 | A | DONE | 2 | S-M |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-03-18 | 20 | 0 | 0 |  | 0 | 50 |  | Condensate pans |  | 10
2024-03-20 | 2254 |  | 69210 | A | DONE | 2 | S | neal | HERITAGE 6220024 |  | 2024-03-22 | Z | 2024-03-15 | 20 | 0 | 0 |  | 0 | 30 |  | 2A-EA |  | 7
2024-03-18 | 2809 |  | 67653 - 67654 | A | DONE | 26 | M | semi | JANESVILLE ESSR 6230011 | 1" liner | 2024-03-20 | Z | 2024-03-08 | 580 | 0 | 70 | F | 290 | 890 |  | AHU-6 |  | 12 |  | 2024-06-20
2024-03-18 | 2810 |  | 67655 | A | DONE | 15 | M | semi | JANESVILLE ESSR 6230011 | 2" liner | 2024-03-20 | Z | 2024-03-08 | 230 | 0 | 130 | F | 280 | 510 |  | AHU-6 |  | 12 |  | 2024-06-20
2024-03-19 | 2811 |  | 67656 - 67657 | A | DONE | 12 | S-M | semi | JANESVILLE ESSR 6230011 | 1" liner | 2024-03-20 | Z | 2024-03-08 | 200 | 0 | 90 | F | 110 | 360 |  | Rm 240A |  | 12 |  | 2024-06-20
2024-03-21 | 1111 | w | 72901 - 72902 | A | DONE | 2 | S-M |  | LABCORP 6230014 |  | 2024-03-26 | Z | 2024-03-12 | 20 | 0 | 0 |  | 0 | 50 |  | Cone Flashing |  | 14
2024-03-22 | 277 |  | EMAIL | A | DONE | 2 | S | ss | MCDS 4230075 |  | 2024-03-22 | Z | 2024-03-22 | 20 | 0 | 0 |  | 0 | 20 |  | storm collars |  | 0
2024-03-18 | 264 |  | 78718 | A | DONE | 2 | S |  | MCDS 4230075 | birdscreen | 2024-03-21 | Z | 2024-03-18 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 3
2024-03-18 | 784 |  | 68543 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 | 1" DB | 2024-03-19 | Z | 2024-03-12 | 70 | 0 | 0 |  | 60 | 180 |  | AHU-P1 |  | 7
2024-03-20 | 785 |  | 68544 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-03-26 | Z | 2024-03-14 | 30 | 0 | 20 | F | 0 | 50 |  | VAV G2-12 |  | 12
2024-03-21 | 786 | sp | 68545 | A | DONE | 4 | S-M |  | MEMORIAL HS 6210024 |  | 2024-03-26 | Z | 2024-03-14 | 0 | 100 | 0 |  | 0 | 100 |  | VAV G2-13 |  | 12
2024-03-20 | 787 |  | 68552 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-03-20 | Z | 2024-03-20 | 20 | 0 | 0 |  | 20 | 20 |  | ERV Dog house |  | 0
2024-03-21 | 1140 |  | 67501 - 67502 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-21 | 50 | 0 | 0 |  | 0 | 60 |  | 1st Fl. RA |  | 0
2024-03-19 | 2509 |  | 67431 - 67432 | A | DONE | 45 | M-L |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-05 | 160 | 0 | 960 | F | 0 | 1350 |  | Conference Rm 140 |  | 16
2024-03-19 | 2510 | sp | 67433 | A | DONE | 22 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-05 | 70 | 470 | 0 |  | 0 | 500 |  | Conference Rm 140 |  | 16
2024-03-19 | 2511 |  | 67434 - 67435 | A | DONE | 29 | M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-05 | 210 | 0 | 510 | F | 0 | 1000 |  | Conference Rm 140 |  | 16
2024-03-19 | 2512 |  | 67429 | A | DONE | 8 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-06 | 50 | 0 | 140 | F | 0 | 230 |  | AT 4-14 / 4-22 2nd fl |  | 15
2024-03-19 | 2513 | sp | 67430 | A | DONE | 12 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-06 | 60 | 240 | 0 |  | 0 | 290 |  | 2nd fl SALP |  | 15
2024-03-19 | 2514 |  | 67436 | A | DONE | 12 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-06 | 40 | 0 | 240 | F | 0 | 400 |  | Washing Rm 132 |  | 15
2024-03-19 | 2515 |  | 67437 - 67438 | A | DONE | 45 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-06 | 330 | 0 | 780 | F | 0 | 1500 |  | Conference Rm 140 RA |  | 15
2024-03-19 | 2516 |  | 67439 | A | DONE | 22 | S-M | alum | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-06 | 130 | 0 | 400 | F | 0 | 340 |  | 2nd fl bathroom EA |  | 15
2024-03-19 | 2517 |  | 67440 - 67441 | A | DONE | 41 | M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-06 | 120 | 0 | 890 | F | 0 | 1570 |  | 2nd fl corridor SA main |  | 15
2024-03-19 | 2518 | sp | 67451 | A | DONE | 6 | S |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-06 | 50 | 90 | 0 |  | 0 | 130 |  | 2nd fl corridor |  | 15
2024-03-19 | 2519 |  | 67443 - 67444 | A | DONE | 34 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-07 | 70 | 0 | 770 | F | 0 | 1020 |  | 2nd fl RA East |  | 14
2024-03-19 | 2520 | sp | 67445 | A | DONE | 4 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-07 | 20 | 80 | 0 |  | 0 | 100 |  | 2nd fl RA East |  | 14
2024-03-19 | 2521 |  | 67447 | A | DONE | 13 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-07 | 40 | 0 | 270 | F | 0 | 510 |  | 2nd fl RA West |  | 14
2024-03-21 | 2522 |  | 67442 | A | DONE | 4 | S |  | MENDOTA FOODS 6220027 |  | 2024-03-28 | Z | 2024-03-07 | 50 | 0 | 130 | F | 0 | 210 |  | SALP |  | 21
2024-03-21 | 2523 |  | 67446 , 67448 | A | DONE | 29 | S-M | pt.alum | MENDOTA FOODS 6220027 |  | 2024-03-28 | Z | 2024-03-07 | 150 | 0 | 560 | F | 0 | 760 |  | 2nd Fl EA Corridor EF-3-2 |  | 21
2024-03-22 | 2524 | sp | 67452 | A | DONE | 2 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-28 | Z | 2024-03-07 | 20 | 50 | 0 |  | 0 | 70 |  | SALP |  | 21
2024-03-21 | 2525 |  | 67449 - 67450 | A | DONE | 8 | S-M |  | MENDOTA FOODS 6220027 | flex | 2024-03-28 | Z | 2024-03-07 | 120 | 0 | 70 | F | 0 | 220 |  | 1st Fl SF-3 / EF-3 |  | 21
2024-03-21 | 2526 |  | 67453 | A | DONE | 4 | S |  | MENDOTA FOODS 6220027 | flex | 2024-03-28 | Z | 2024-03-07 | 100 | 0 | 0 |  | 0 | 120 |  | EF-5 |  | 21
2024-03-19 | 2545 |  | 67457 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-13 | 40 | 0 | 0 |  | 0 | 60 |  | Misc |  | 8
2024-03-19 | 2548 |  | 67461 | A | DONE | 4 | S-M |  | MENDOTA FOODS 6220027 | 1" liner | 2024-03-21 | Z | 2024-03-15 | 90 | 0 | 0 |  | 70 | 100 |  | TA |  | 6
2024-03-20 | 2549 | bth | 67462 - 67463 | A | DONE | 6 | S-M | pt.alum | MENDOTA FOODS 6220027 |  | 2024-03-21 | Z | 2024-03-19 | 90 | 20 | 30 | F | 0 | 110 |  | Misc |  | 2
2024-03-19 | 2614 |  | 69494 | A | DONE | 4 | S |  | OLIV 6210030 |  | 2024-03-21 | Z | 2024-03-12 | 90 | 0 | 0 |  | 0 | 280 |  | Generator |  | 9
2024-03-19 | 2615 |  | 69496 | A | DONE | 2 | S-M |  | OLIV 6210030 | birdscreen | 2024-03-21 | Z | 2024-03-15 | 40 | 0 | 0 |  | 0 | 50 |  | Electrical Rm |  | 6
2024-03-18 | 2616 |  | 69497 | A | DONE | 5 | S-M |  | OLIV 6210030 | paint | 2024-03-20 | Z | 2024-03-18 | 110 | 0 | 0 |  | 20 | 110 |  | 220 / 620 |  | 2
2024-03-20 | 2617 | bth | 69498 | A | DONE | 3 | S-M | pt.neal | OLIV 6210030 |  | 2024-03-21 | Z | 2024-03-20 | 40 | 30 | 0 |  | 0 | 80 |  | Yogo Room |  | 1
2024-03-19 | 265 |  | 31825 | A | DONE | 2 | S | ss | PORTAGE ES 10053789 |  | 2024-03-19 | Z | 2024-03-18 | 20 | 0 | 0 |  | 0 | 20 |  | Wall cover |  | 1
2024-03-19 | 268 |  | 31925 | A | DONE | 2 | S | ss | PORTAGE ES 10053789 |  | 2024-03-19 | Z | 2024-03-19 | 20 | 0 | 0 |  | 0 | 20 |  | Wall cover |  | 0
2024-03-18 | 262 |  | 31824 | A | DONE | 2 | S |  | PRAIRIE RIDGE 8230018 |  | 2024-03-19 | Z | 2024-03-18 | 30 | 0 | 0 |  | 0 | 60 |  | Angles |  | 1
2024-03-20 | 507 |  | L1-TA-1 | A | DONE | 2 | S | semi 4 | RAMC 6230009 | 1" liner | 2024-03-25 | Z | 2024-01-31 | 40 | 0 | 0 |  | 30 | 70 |  |  |  | 54
2024-03-20 | 508 |  | L1-TA-2 | A | DONE | 2 | S | semi 4 | RAMC 6230009 | 1" liner | 2024-03-25 | Z | 2024-01-31 | 40 | 0 | 0 |  | 30 | 50 |  |  |  | 54
2024-03-20 | 509 |  | L1-TA-3 | A | DONE | 4 | S | semi 4 | RAMC 6230009 | 1" liner | 2024-03-25 | Z | 2024-01-31 | 50 | 0 | 50 | F | 70 | 110 |  |  |  | 54
2024-03-21 | 510 | bth | L1-SALP-VAV01 | A | DONE | 3 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 40 | 0 |  | 0 | 70 |  |  |  | 54
2024-03-20 | 511 | bth | L1-SALP-VAV02 | A | DONE | 3 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 40 | 0 |  | 0 | 80 |  |  |  | 54
2024-03-20 | 512 | bth | L1-SALP-VAV03 | A | DONE | 4 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 60 | 0 |  | 0 | 100 |  |  |  | 54
2024-03-20 | 513 | bth | L1-SALP-VAV04 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 54
2024-03-20 | 514 | bth | L1-SALP-VAV05 | A | DONE | 4 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 50 | 0 |  | 0 | 90 |  |  |  | 54
2024-03-20 | 515 | bth | L1-SALP-VAV06 | A | DONE | 4 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 60 | 0 |  | 0 | 100 |  |  |  | 54
2024-03-20 | 516 | bth | L1-SALP-VAV07 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 54
2024-03-21 | 517 | bth | L1-SALP-VAV08 | A | DONE | 8 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 170 | 0 |  | 0 | 240 |  |  |  | 54
2024-03-20 | 518 | bth | L1-SALP-VAV09 | A | DONE | 7 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 80 | 90 | 0 |  | 0 | 190 |  |  |  | 54
2024-03-21 | 519 | bth | L1-SALP-VAV10 | A | DONE | 9 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 60 | 160 | 0 |  | 0 | 240 |  |  |  | 54
2024-03-20 | 520 | bth | L1-SALP-VAV11 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 54
2024-03-20 | 521 | bth | L1-SALP-VAV12 | A | DONE | 12 | S-M | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 50 | 230 | 0 |  | 0 | 320 |  |  |  | 54
2024-03-20 | 522 | bth | L1-SALP-VAV13 | A | DONE | 12 | S-M | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 40 | 250 | 0 |  | 0 | 340 |  |  |  | 54
2024-03-20 | 523 | bth | L1-SALP-VAV14 | A | DONE | 4 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 70 | 0 |  | 0 | 110 |  |  |  | 54
2024-03-20 | 524 | bth | L1-SALP-VAV15 | A | DONE | 6 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 110 | 0 |  | 0 | 160 |  |  |  | 54
2024-03-20 | 525 | bth | L1-SALP-VAV16 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 54
2024-03-20 | 526 | bth | L1-SALP-VAV17 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 54
2024-03-20 | 527 | bth | L1-SALP-VAV18 | A | DONE | 10 | S-M | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 80 | 170 | 0 |  | 0 | 290 |  |  |  | 54
2024-03-20 | 528 | bth | L1-SALP-VAV19 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 54
2024-03-20 | 529 | bth | L1-SALP-VAV19A | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 54
2024-03-20 | 530 | bth | L1-SALP-VAV20 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 54
2024-03-20 | 531 | bth | L1-SALP-VAV21 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 54
2024-03-20 | 532 | bth | L1-SALP-VAV22 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 20 | 0 |  | 0 | 60 |  |  |  | 54
2024-03-20 | 533 | bth | L1-SALP-VAV23 | A | DONE | 3 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 40 | 0 |  | 0 | 80 |  |  |  | 54
2024-03-20 | 534 | bth | L1-SALP-VAV24 | A | DONE | 2 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 54
2024-03-21 | 543 | bth | L1-EA-1 | A | DONE | 10 | S-M | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 120 | 100 | 30 | F | 0 | 260 |  |  |  | 54
2024-03-20 | 544 | sp | L1-EA-2 | A | DONE | 10 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 220 | 0 |  | 0 | 290 |  |  |  | 54
2024-03-21 | 545 | sp | L1-EA-3 | A | DONE | 4 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 80 | 0 |  | 0 | 100 |  |  |  | 54
2024-03-21 | 546 | sp | L1-EA-4 | A | DONE | 8 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 30 | 160 | 0 |  | 0 | 220 |  |  |  | 54
2024-03-21 | 547 | sp | L1-EA-5 | A | DONE | 5 | S | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 20 | 90 | 0 |  | 0 | 120 |  |  |  | 54
2024-03-20 | 548 | bth | L1-EA-6 | A | DONE | 8 | S-M | semi 4 | RAMC 6230009 |  | 2024-03-25 | Z | 2024-01-31 | 70 | 30 | 100 | F | 0 | 240 |  |  |  | 54
2024-03-20 | 4535 |  | 72374 | A | DONE | 10 | S-M |  | RAMC 6230009 | flex , 1" liner | 2024-03-25 | Z | 2024-03-15 | 240 | 0 | 0 |  | 110 | 590 |  | AHU-1 Drops |  | 10
2024-03-20 | 4730 |  | 78858 | A | DONE | 37 | S-M | neal | ROCK CO. JAIL 6220018 | birdscreen | 2024-03-21 | Z | 2024-03-11 | 910 | 0 | 0 |  | 0 | 1180 |  |  |  | 10
2024-03-20 | 4732 |  | 78860 | A | DONE | 4 | S-M | pcd | ROCK CO. JAIL 6220018 |  | 2024-03-21 | Z | 2024-03-13 | 80 | 0 | 0 |  | 0 | 150 |  |  |  | 8
2024-03-20 | 4733 |  | 78861 | A | DONE | 7 | S-M |  | ROCK CO. JAIL 6220018 | flex | 2024-03-21 | Z | 2024-03-13 | 170 | 0 | 0 |  | 0 | 290 |  |  |  | 8
2024-03-20 | 4734 |  | 78862 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-03-21 | Z | 2024-03-15 | 20 | 0 | 0 |  | 0 | 20 |  | Jail |  | 6
2024-03-20 | 4735 | w | 78863 | A | DONE | 2 | S | ss | ROCK CO. JAIL 6220018 |  | 2024-03-21 | Z | 2024-03-15 | 30 | 0 | 0 |  | 0 | 60 |  | Dishwasher |  | 6
2024-03-21 | 4736 |  | 78864 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-03-28 | Z | 2024-03-19 | 20 | 0 | 0 |  | 0 | 20 |  | Cell chase |  | 9
2024-03-18 | 1414 |  | 67872 | A | DONE | 2 | S |  | SOUTHSIDE ES 6210025 |  | 2024-03-22 | Z | 2024-03-18 | 20 | 0 | 0 |  | 0 | 20 |  | Warranty repair |  | 4
2024-03-20 | 225 | sp | 70075 | A | DONE | 2 | S |  | SPH ERP 2240001 |  | 2024-03-25 | Z | 2024-02-26 | 20 | 20 | 0 |  | 0 | 30 |  | R-3-10K RA |  | 28
2024-03-20 | 272 |  | 70314 | A | DONE | 2 | S |  | ST.BERNARD 2220037 |  | 2024-03-21 | Z | 2024-03-19 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeve |  | 2
2024-03-20 | 260 | bth | 79406 - 79407 | A | DONE | 12 | S-M |  | TOMAH HEALTH 4240011 |  | 2024-03-22 | Z | 2024-03-15 | 60 | 170 | 60 | F | 0 | 340 |  | TAB-1012E , 1013 |  | 7
2024-03-20 | 261 | bth | 70218 - 70219 | A | DONE | 21 | S-M |  | TOMAH HEALTH 4240011 |  | 2024-03-22 | Z | 2024-03-15 | 90 | 390 | 30 | F | 0 | 570 |  | Misc, Corridor RA |  | 7
2024-03-20 | 2011 | w | 58930 | A | DONE | 2 | S |  | UWL GRAFF 6230017 |  | 2024-03-25 | Z | 2024-03-14 | 40 | 0 | 0 |  | 0 | 100 |  | Pipe Sleeves |  | 11
2024-03-21 | 2795 |  | 72700 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-03-25 | Z | 2024-03-20 | 30 | 0 | 0 |  | 0 | 30 |  | Grille boxes |  | 5
2024-03-19 | 267 |  | 78720 | A | DONE | 4 | S-M |  | VERONA ICE 4230034 | 1" liner | 2024-03-19 | Z | 2024-03-19 | 90 | 0 | 0 |  | 80 | 130 |  | DH-2 |  | 0
2024-03-19 | 270 |  | 78722 | A | DONE | 2 | S |  | VERONA ICE 4230034 | 1" liner | 2024-03-19 | Z | 2024-03-19 | 30 | 0 | 0 |  | 0 | 80 |  | End caps |  | 0
2024-03-20 | 1513 | sp | 60699 | A | DONE | 2 | S-M |  | WAUSHARA CO. GOV 6220010 |  | 2024-03-21 | Z | 2024-03-18 | 20 | 20 | 0 |  | 0 | 30 |  | Basement |  | 3
2024-03-18 | 1514 |  | 38164 | A | DONE | 3 | S |  | WAUSHARA CO. GOV 6220010 |  | 2024-03-21 | Z | 2024-03-18 | 70 | 0 | 0 |  | 0 | 100 |  | Angles |  | 3
2024-03-19 | 259 | bth | 70102 - 70103 | A | DONE | 14 | M |  | WICELL 2230040 |  | 2024-03-21 | Z | 2024-03-14 | 110 | 210 | 30 | F | 0 | 320 |  | VAV-128 A,B |  | 7
[6 empty] | 1259 | [13 empty] | 40200 |  |  |  | 8580 | 21.34%
WEEK OF 3-25-2024
2024-03-26 | 1706 |  | 68014 | A | DONE | 78 | L | neal | BLACKHAWK BTC 6230025 | 1" spiral accu | 2024-04-11 | Z | 2024-01-19 | 1940 | 0 | 0 |  | 1890 | 5400 |  | Menu Lab |  | 83
2024-03-26 | 1708 | sp | 78906 - 78907 | A | DONE | 15 | S-M |  | BLACKHAWK BTC 6230025 |  | 2024-03-28 | Z | 2024-01-19 | 80 | 290 | 0 |  | 0 | 390 |  | Clean Lab |  | 69 |  | 2024-03-14
2024-03-25 | 1717 |  | 78921 - 78922 | A | DONE | 36 | S-M | neal | BLACKHAWK BTC 6230025 | 1" liner | 2024-03-28 | Z | 2024-01-19 | 700 | 0 | 180 | F | 610 | 1220 |  | Welding lab |  | 69 |  | 2024-03-14
2024-03-27 | 1728 |  | 78930 | A | DONE | 2 | S | pt.neal | BLACKHAWK BTC 6230025 | 1" DB | 2024-04-04 | Z | 2024-03-25 | 30 | 0 | 0 |  | 20 | 50 |  | Roof caps |  | 10
2024-03-25 | 1712 |  | 78914 | A | DONE | 9 | S-M | neal | BLACKHAWK BTC 6230025 | 1" spiral accu | 2024-03-28 | Z | 2024-01-19 | 130 | 0 | 90 | F | 150 | 290 |  | Lab |  | 69 |  | 2024-03-14
2024-03-25 | 1713 | sp | 78915 - 78916 | A | DONE | 17 | M | neal | BLACKHAWK BTC 6230025 | 1" spiral accu | 2024-03-28 | Z | 2024-01-19 | 160 | 250 | 0 |  | 380 | 490 |  | Lab |  | 69 |  | 2024-03-14
2024-03-27 | 3231 |  | SC-SAMP-001 | A | DONE | 44 | S-M |  | CDIS 6220028 |  | 2024-03-29 | Z | 2023-11-13 | 90 | 0 | 1000 | F | 0 | 2390 |  |  |  | 137
2024-03-27 | 3234 |  | SC-SAMP-004 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-03-29 | Z | 2023-11-13 | 40 | 0 | 320 | F | 0 | 530 |  |  |  | 137
2024-03-25 | 3549 |  | 61444 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-03-21 | 20 | 0 | 0 |  | 0 | 20 |  | SAMP 37 |  | 5
2024-03-27 | 3551 |  | 61448 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-04-02 | Z | 2024-03-25 | 20 | 0 | 0 |  | 0 | 30 |  | Tear drop hangers |  | 8
2024-03-26 | 3552 |  | 92171 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-03-25 | 30 | 0 | 0 |  | 0 | 40 |  | Angles |  | 8
2024-03-25 | 4156 |  | L2-A-SAMP-062 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-26 | Z | 2024-02-15 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 40
2024-03-28 | 4158 | sp | L2-A-EAD-040 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 43
2024-03-28 | 4159 | sp | L2-A-EAD-041 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 43
2024-03-29 | 4160 | sp | L2-A-EAD-042 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 20 | 80 | 0 |  | 0 | 90 |  |  |  | 43
2024-03-28 | 4161 | sp | L2-A-EAD-046 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 20 | 90 | 0 |  | 0 | 110 |  |  |  | 43
2024-03-28 | 4162 | sp | L2-A-EAD-051 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 20 | 60 | 0 |  | 0 | 90 |  |  |  | 43
2024-03-29 | 4163 | bth | L2-A-EAD-053 | A | DONE | 7 | S-M |  | CDIS 6220028 | paint | 2024-04-02 | Z | 2024-02-19 | 40 | 90 | 40 | F | 20 | 180 |  |  |  | 43
2024-03-28 | 4164 | sp | L2-A-EAD-056 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 43
2024-03-27 | 4165 | bth | L2-A-SALP-064 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 70 | 30 | 220 | F | 0 | 370 |  |  |  | 43
2024-03-28 | 4166 | bth | L2-A-SALP-077 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 50 | 0 |  | 30 | 100 |  |  |  | 43
2024-03-28 | 4167 | sp | L2-A-SALP-078 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 43
2024-03-27 | 4168 | bth | L2-A-SALP-084 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 90 | 20 | 0 |  | 60 | 140 |  |  |  | 43
2024-03-27 | 4169 | bth | L2-A-SALP-085 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 70 | 20 | 0 |  | 40 | 110 |  |  |  | 43
2024-03-29 | 4170 | bth | L2-A-SALP-086 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 90 | 0 |  | 20 | 160 |  |  |  | 43
2024-03-29 | 4171 | bth | L2-A-SALP-087 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 90 | 0 |  | 20 | 160 |  |  |  | 43
2024-03-28 | 4172 | bth | L2-A-SALP-088 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 60 | 80 | 0 |  | 30 | 150 |  |  |  | 43
2024-03-28 | 4173 | bth | L2-A-SALP-089 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 80 | 20 | 0 |  | 50 | 110 |  |  |  | 43
2024-03-29 | 4174 | bth | L2-A-SALP-090 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 50 | 0 |  | 30 | 130 |  |  |  | 43
2024-03-29 | 4175 | bth | L2-A-SALP-091 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 60 | 0 |  | 30 | 120 |  |  |  | 43
2024-03-28 | 4176 | bth | L2-A-SALP-092 | A | DONE | 3 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 20 | 0 |  | 30 | 80 |  |  |  | 43
2024-03-28 | 4177 | bth | L2-A-SALP-093 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 30 | 0 |  | 30 | 90 |  |  |  | 43
2024-03-28 | 4178 | bth | L2-A-SALP-094 | A | DONE | 4 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 50 | 0 |  | 20 | 110 |  |  |  | 43
2024-03-28 | 4179 | bth | L2-A-SALP-095 | A | DONE | 7 | S | neal | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 140 | 20 | 0 |  | 30 | 180 |  |  |  | 43
2024-03-29 | 4180 | bth | L2-A-SALP-096 | A | DONE | 7 | S | neal | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 80 | 90 | 0 |  | 0 | 200 |  |  |  | 43
2024-03-29 | 4181 | bth | L2-A-SALP-097 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 40 | 80 | 0 |  | 0 | 140 |  |  |  | 43
2024-03-29 | 4182 | sp | L2-A-SALP-098 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-04-02 | Z | 2024-02-19 | 30 | 80 | 0 |  | 0 | 120 |  |  |  | 43
2024-03-28 | 4183 | bth | L2-A-SALP-099 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-04-02 | Z | 2024-02-19 | 50 | 30 | 20 | F | 20 | 110 |  |  |  | 43
2024-03-26 | 4235 | sp | L3-B-EALP-001 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 15
2024-03-27 | 4236 | sp | L3-B-EALP-002 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 15
2024-03-26 | 4237 | sp | L3-B-EALP-003 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 15
2024-03-26 | 4238 | sp | L3-B-EALP-004 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 15
2024-03-26 | 4239 | bth | L3-B-EALP-005 | A | DONE | 4 | S | neal | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 80 | 20 | 0 |  | 0 | 90 |  |  |  | 15
2024-03-26 | 4240 | bth | L3-B-EALP-006 | A | DONE | 3 | S | pt.neal | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 40 | 20 | 0 |  | 0 | 60 |  |  |  | 15
2024-03-28 | 4241 | bth | L3-B-EALP-007 | A | DONE | 3 | S | pt.neal | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 30 | 30 | 0 |  | 0 | 70 |  |  |  | 15
2024-03-27 | 4242 | sp | L3-B-EALP-008 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 70 | 0 |  | 0 | 110 |  |  |  | 15
2024-03-27 | 4243 | sp | L3-B-EALP-009 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 80 | 0 |  | 0 | 110 |  |  |  | 15
2024-03-26 | 4244 | sp | L3-B-EALP-010 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 90 | 0 |  | 0 | 110 |  |  |  | 15
2024-03-27 | 4245 | sp | L3-B-EALP-011 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 15
2024-03-28 | 4246 | bth | L3-B-EALP-012 | A | DONE | 3 | S | pt.neal | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 30 | 50 | 0 |  | 0 | 100 |  |  |  | 15
2024-03-27 | 4247 | sp | L3-B-EALP-013 | A | DONE | 3 | S | pt.neal | CDIS 6220028 | 1" spiral accu | 2024-03-29 | Z | 2024-03-14 | 30 | 30 | 0 |  | 20 | 80 |  |  |  | 15
2024-03-26 | 4248 | bth | L3-B-EALP-014 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 90 | 20 | 30 | F | 0 | 150 |  |  |  | 15
2024-03-27 | 4249 | bth | L3-B-EALP-016 | A | DONE | 3 | S | neal | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 30 | 20 | 20 | F | 0 | 60 |  |  |  | 15
2024-03-26 | 4250 | sp | L3-B-EALP-017 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 20 | 100 | 0 |  | 0 | 140 |  |  |  | 15
2024-03-26 | 4251 | sp | L3-B-EALP-018 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 30 | 100 | 0 |  | 0 | 120 |  |  |  | 15
2024-03-26 | 4252 | bth | L3-B-SALP-001 | A | DONE | 3 | S |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 15
2024-03-27 | 4253 | bth | L3-B-SALP-002 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 60 | 60 | 0 |  | 30 | 140 |  |  |  | 15
2024-03-27 | 4254 | bth | L3-B-SALP-003 | A | DONE | 7 | S |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 70 | 100 | 0 |  | 30 | 190 |  |  |  | 15
2024-03-26 | 4255 | bth | L3-B-SALP-004 | A | DONE | 12 | S-M |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 220 | 30 | 30 | F | 60 | 320 |  |  |  | 15
2024-03-27 | 4256 | bth | L3-B-SALP-005 | A | DONE | 7 | S | neal | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 80 | 20 | 60 | F | 20 | 180 |  |  |  | 15
2024-03-27 | 4257 | bth | L3-B-SALP-006 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 50 | 60 | 0 |  | 30 | 120 |  |  |  | 15
2024-03-27 | 4258 |  | L3-B-SALP-007 | A | DONE | 9 | S-M | neal | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 170 | 0 | 40 | F | 30 | 250 |  |  |  | 15
2024-03-26 | 4259 | bth | L3-B-SALP-008 | A | DONE | 4 | S | neal | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 40 | 50 | 0 |  | 20 | 90 |  |  |  | 15
2024-03-28 | 4260 | sp | L3-B-SALP-009 | A | DONE | 6 | S | neal | CDIS 6220028 |  | 2024-03-29 | Z | 2024-03-14 | 40 | 100 | 0 |  | 0 | 170 |  |  |  | 15
2024-03-27 | 4261 | bth | L3-B-SALP-010 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 90 | 60 | 0 |  | 50 | 150 |  |  |  | 15
2024-03-28 | 4262 | bth | L3-B-SALP-011 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 40 | 50 | 0 |  | 20 | 100 |  |  |  | 15
2024-03-27 | 4263 | bth | L3-B-SALP-012 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 40 | 100 | 0 |  | 20 | 180 |  |  |  | 15
2024-03-28 | 4264 | bth | L3-B-SALP-013 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 50 | 100 | 0 |  | 20 | 150 |  |  |  | 15
2024-03-27 | 4265 |  | L3-B-SALP-018 | A | DONE | 3 | S | neal | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 70 | 0 | 0 |  | 20 | 100 |  |  |  | 15
2024-03-27 | 4266 |  | L3-B-SALP-019 | A | DONE | 3 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-03-29 | Z | 2024-03-14 | 50 | 20 | 0 |  | 30 | 60 |  |  |  | 15
2024-03-25 | 4292 | w | 61310 | A | DONE | 2 | S-M |  | CDIS 6220028 | 1-1/2 DB | 2024-03-29 | Z | 2024-03-18 | 50 | 0 | 0 |  | 20 | 110 |  | Roof curb |  | 11
2024-03-28 | a3909 |  | BSMT-C-SALP-017 | A | DONE | 4 | S | neal | CDIS 6220028 | paint , 1" liner | 2024-03-29 | Z | 2024-03-27 | 90 | 0 | 0 |  | 40 | 140 |  |  |  | 2
2024-03-27 | 1277 |  | 70098 | A | DONE | 6 | S-M |  | EGENESIS PH2 6230026 | flex | 2024-04-01 | Z | 2024-03-04 | 130 | 0 | 0 |  | 0 | 240 |  | RTU-1 Relief Fan |  | 28
2024-03-27 | 1278 | w | 79609 | A | DONE | 2 | S-M |  | EGENESIS PH2 6230026 |  | 2024-04-01 | Z | 2024-03-13 | 20 | 0 | 0 |  | 0 | 60 |  | Equipment rail caps |  | 19
2024-03-27 | 1267 | bth | 70064 - 70065 | A | DONE | 9 | S-M |  | EGENESIS PH2 6230026 | paint | 2024-04-01 | Z | 2024-02-16 | 120 | 60 | 40 | F | 30 | 250 |  | CB 3 EAT 001 |  | 45
2024-03-28 | 1272 | sp | 70070 | A | DONE | 7 | S-M |  | EGENESIS PH2 6230026 |  | 2024-04-01 | Z | 2024-02-22 | 60 | 110 | 0 |  | 0 | 160 |  | CB-3 VAV 104 |  | 39
2024-03-25 | 1574 |  | 62371 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 |  | 2024-03-28 | Z | 2024-03-25 | 20 | 0 | 0 |  | 0 | 20 |  | Added Bedrooms |  | 3
2024-03-25 | 2674 |  | ROXXY-EA-01 | A | DONE | 8 | S-M |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 90 | 0 | 110 | F | 0 | 250 |  |  |  | 28
2024-03-26 | 2675 | sp | ROXXY-EA-02 | A | DONE | 5 | S-M | neal | HARMONICS 6240010 | oval | 2024-03-28 | Z | 2024-02-29 | 50 | 70 | 0 |  | 0 | 180 |  |  |  | 28
2024-03-25 | 2676 |  | ROXXY-EA-03 | A | DONE | 25 | S-M |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 170 | 0 | 450 | F | 0 | 740 |  |  |  | 28
2024-03-25 | 2677 |  | ROXXY-EA-04 | A | DONE | 16 | S-M |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 240 | 0 | 140 | F | 0 | 470 |  |  |  | 28
2024-03-25 | 2678 |  | ROXXY-OA-01 | A | DONE | 14 | S-M |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 230 | 0 | 120 | F | 0 | 420 |  |  |  | 28
2024-03-25 | 2679 | bth | ROXXY-OA-02 | A | DONE | 10 | S-M |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 130 | 80 | 20 | F | 0 | 270 |  |  |  | 28
2024-03-25 | 2680 |  | ROXXY-OA-03 | A | DONE | 8 | S-M |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 200 | 0 | 0 |  | 0 | 280 |  |  |  | 28
2024-03-25 | 2681 |  | ROXXY-OA-04 | A | DONE | 3 | S-M |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 60 | 0 | 0 |  | 0 | 70 |  |  |  | 28
2024-03-25 | 2682 |  | ROXXY-OA-05 | A | DONE | 2 | S-M |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 40 | 0 | 0 |  | 0 | 50 |  |  |  | 28
2024-03-25 | 2683 |  | ROXXY-OA-06 | A | DONE | 6 | S |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 150 | 0 | 0 |  | 0 | 180 |  |  |  | 28
2024-03-25 | 2684 |  | ROXXY-OA-07 | A | DONE | 6 | S |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 150 | 0 | 0 |  | 0 | 220 |  |  |  | 28
2024-03-25 | 2685 |  | ROXXY-OA-08 | A | DONE | 5 | S |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 90 | 0 | 20 | F | 0 | 130 |  |  |  | 28
2024-03-26 | 2686 |  | ROXXY-RA-01 | A | DONE | 4 | S |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 80 | 0 | 0 |  | 0 | 100 |  |  |  | 28
2024-03-25 | 2687 |  | ROXXY-RA-02 | A | DONE | 2 | S |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 50 | 0 | 0 |  | 0 | 60 |  |  |  | 28
2024-03-26 | 2688 |  | ROXXY-RA-03 | A | DONE | 2 | S |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 30 | 0 | 0 |  | 0 | 50 |  |  |  | 28
2024-03-25 | 2689 |  | ROXXY-RA-04 | A | DONE | 2 | S |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 28
2024-03-26 | 2690 |  | ROXXY-RA-05 | A | DONE | 4 | S |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 100 | 0 | 0 |  | 0 | 150 |  |  |  | 28
2024-03-26 | 2691 |  | ROXXY-RA-06 | A | DONE | 9 | S-M |  | HARMONICS 6240010 | flex | 2024-03-28 | Z | 2024-02-29 | 210 | 0 | 0 |  | 0 | 260 |  |  |  | 28
2024-03-26 | 2692 |  | ROXXY-RA-07 | A | DONE | 4 | S |  | HARMONICS 6240010 |  | 2024-03-28 | Z | 2024-02-29 | 90 | 0 | 0 |  | 0 | 110 |  |  |  | 28
2024-03-28 | 4602 |  | 69500 | A | DONE | 5 | S-M |  | HARMONICS 6240010 |  | 2024-04-04 | Z | 2024-03-25 | 70 | 0 | 50 | F | 0 | 140 |  | Stair 4 outs |  | 10
2024-03-27 | 2255 |  | 69029 | A | DONE | 12 | S-M |  | HERITAGE 6220024 |  | 2024-03-29 | Z | 2024-03-21 | 220 | 0 | 70 | F | 0 | 490 |  | 2A R Shaft |  | 8
2024-03-26 | 2256 |  | 57800 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-03-29 | Z | 2024-03-21 | 40 | 0 | 0 |  | 0 | 60 |  | 2A E Shaft |  | 8
2024-03-26 | 2257 |  | 68990 | A | DONE | 5 | S-M |  | HERITAGE 6220024 |  | 2024-03-29 | Z | 2024-03-21 | 110 | 0 | 0 |  | 0 | 220 |  | AHU-1 Gym RA |  | 8
2024-03-26 | 2258 |  | 69213 | A | DONE | 2 | S | neal | HERITAGE 6220024 |  | 2024-03-29 | Z | 2024-03-25 | 30 | 0 | 0 |  | 0 | 30 |  | 2nd Floor tie-ins |  | 4
2024-03-26 | 2259 |  | 68991 | A | DONE | 5 | S-M |  | HERITAGE 6220024 |  | 2024-03-29 | Z | 2024-03-25 | 110 | 0 | 0 |  | 0 | 160 |  | OA 2A |  | 4
2024-03-27 | 2260 |  | 68992 - 68993 | A | DONE | 4 | S |  | HERITAGE 6220024 | 1" liner | 2024-03-29 | Z | 2024-03-26 | 90 | 0 | 0 |  | 20 | 110 |  | AHU-1 HP , HP RA |  | 3
2024-03-27 | 2261 | bth | 2D-EA-6 | A | DONE | 13 | S-M |  | HERITAGE 6220024 |  | 2024-03-29 | Z | 2024-03-26 | 140 | 50 | 130 | F | 0 | 370 |  |  |  | 3
2024-03-28 | 2262 |  | 69030 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-04-05 | Z | 2024-03-27 | 30 | 0 | 0 |  | 0 | 40 |  | D-ceiling tie-ins |  | 9
2024-03-28 | 2807 |  | 66072 - 66073 | A | DONE | 18 | S-M | alum | JANESVILLE ESSR 6230011 |  | 2024-04-01 | Z | 2024-02-02 | 150 | 0 | 290 | F | 0 | 280 |  | Pool Mech Rm. |  | 59
2024-03-28 | 2808 |  | 66074 - 66076 | A | DONE | 49 | S-M | alum | JANESVILLE ESSR 6230011 |  | 2024-04-01 | Z | 2024-02-02 | 630 | 0 | 590 | F | 0 | 910 |  | Pool Mech Rm. |  | 59
2024-03-29 | 278 |  | EMAIL | A | DONE | 2 | S | neal | KEVIN D. 1000372 |  | 2024-03-29 | Z | 2024-03-29 | 20 | 0 | 0 |  | 0 | 30 |  | Pan |  | 0
2024-03-27 | 1112 |  | 72903 | A | DONE | 2 | S |  | LABCORP 6230014 |  | 2024-04-01 | Z | 2024-03-25 | 20 | 0 | 0 |  | 0 | 20 |  | Adj. storm collars |  | 7
2024-03-27 | 773 |  | 68531 | A | DONE | 14 | S-M | alum | MEMORIAL HS 6210024 |  | 2024-04-02 | Z | 2024-02-16 | 340 | 0 | 0 |  | 0 | 250 |  | Pool SA |  | 46
2024-03-26 | 782 |  | 68541 | A | DONE | 3 | S | alum | MEMORIAL HS 6210024 |  | 2024-04-02 | Z | 2024-03-07 | 60 | 0 | 0 |  | 0 | 90 |  | Pool Caps |  | 26
2024-03-27 | 792 |  | 68554 | A | DONE | 2 | S | ss | MEMORIAL HS 6210024 |  | 2024-03-28 | Z | 2024-03-20 | 50 | 0 | 0 |  | 0 | 100 |  | Conecessions pass though |  | 8
2024-03-28 | 797 |  | 68590 | A | DONE | 2 | S | alum | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-25 | 20 | 0 | 0 |  | 0 | 30 |  | P-locker room |  | 15
2024-03-29 | 1145 |  | 67509 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 | flex | 2024-04-04 | Z | 2024-03-28 | 30 | 0 | 0 |  | 0 | 60 |  | Fan Basement |  | 7
2024-03-26 | 1141 |  | 67503 | A | DONE | 6 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-28 | Z | 2024-03-25 | 130 | 0 | 0 |  | 0 | 150 |  | AT-4-7 |  | 3
2024-03-25 | 1142 |  | 67504 - 67505 | A | DONE | 4 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-03-25 | Z | 2024-03-25 | 90 | 0 | 0 |  | 0 | 150 |  | Basement RA |  | 0
2024-03-27 | 1143 |  | 67507 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-03-28 | Z | 2024-03-26 | 20 | 0 | 0 |  | 0 | 20 |  | Basement RA East |  | 2
2024-03-27 | 2547 | w | 67458 | A | DONE | 2 | S-M |  | MENDOTA FOODS 6220027 | 1" DB , wood nailer | 2024-04-04 | Z | 2024-03-14 | 20 | 0 | 0 |  | 20 | 50 |  | Curbs |  | 21
2024-03-28 | 2619 | bth | 69405 | A | DONE | 5 | S-M | pt.alum | OLIV 6210030 | birdscreen | 2024-04-04 | Z | 2024-03-25 | 120 | 0 | 0 |  | 0 | 280 |  | Duplex Roof |  | 10
2024-03-27 | 2620 |  | 69406 - 69407 | A | DONE | 2 | S |  | OLIV 6210030 |  | 2024-03-28 | Z | 2024-03-26 | 60 | 0 | 0 |  | 0 | 80 |  | C-DOAS , Delux Roof |  | 2
2024-03-25 | 1977 |  | 37553 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2024-04-01 | Z | 2024-03-21 | 80 | 0 | 0 |  | 0 | 120 |  | Misc |  | 11
2024-03-29 | 1973 | w | 62933 | A | DONE | 3 | S | ss | PROMEGA FEYNMAN 6220014 |  | 2024-04-01 | Z | 2024-03-18 | 30 | 0 | 0 |  | 0 | 70 |  | DH-B |  | 14
2024-03-25 | 1974 |  | 62934 | C | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 |  | 2024-04-01 | Z | 2024-03-18 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 14
2024-03-27 | 1975 | bth | 62935 - 62937 | A | DONE | 8 | S-M |  | PROMEGA FEYNMAN 6220014 |  | 2024-04-01 | Z | 2024-03-20 | 160 | 30 | 0 |  | 0 | 230 |  | 1st floor |  | 12
2024-03-27 | 1976 | bth | 62938 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 |  | 2024-04-01 | Z | 2024-03-21 | 30 | 20 | 0 |  | 0 | 60 |  | 1st floor |  | 11
2024-03-28 | 1978 |  | 37554 | A | DONE | 5 | S |  | PROMEGA FEYNMAN 6220014 |  | 2024-04-03 | Z | 2024-03-21 | 110 | 0 | 0 |  | 0 | 280 |  | Relief |  | 13
2024-03-27 | 1979 | sp | 37555 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 |  | 2024-04-01 | Z | 2024-03-21 | 0 | 50 | 0 |  | 0 | 50 |  | Misc |  | 11
2024-03-29 | 1980 | w | 62896 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 |  | 2024-04-03 | Z | 2024-03-21 | 20 | 0 | 0 |  | 0 | 20 |  | EA out |  | 13
2024-03-29 | 1969 | sp | 37551 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 |  | 2024-04-03 | Z | 2024-03-06 | 30 | 0 | 0 |  | 0 | 30 |  | Misc |  | 28
2024-03-27 | 1971 |  | 62931 | A | DONE | 6 | S-M |  | PROMEGA FEYNMAN 6220014 | flex | 2024-04-01 | Z | 2024-03-18 | 150 | 0 | 0 |  | 0 | 290 |  | Exh fan |  | 14
2024-03-27 | 1972 |  | 62932 | A | DONE | 2 | S | pcd | PROMEGA FEYNMAN 6220014 | flex | 2024-04-01 | Z | 2024-03-18 | 50 | 0 | 0 |  | 0 | 80 |  | Exh fan |  | 14
2024-03-25 | 4737 |  | 78865 - 78866 | A | DONE | 2 | S-M |  | ROCK CO. JAIL 6220018 | VD's | 2024-03-28 | Z | 2024-03-20 | 50 | 0 | 0 |  | 0 | 60 |  | Cell chase grilles |  | 8
2024-03-25 | 4738 |  | 78867 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 | birdscreen | 2024-03-28 | Z | 2024-03-21 | 50 | 0 | 0 |  | 0 | 80 |  | Elec switch room |  | 7
2024-03-25 | 4739 |  | 78868 - 78869 | A | DONE | 11 | S-M |  | ROCK CO. JAIL 6220018 |  | 2024-03-28 | Z | 2024-03-21 | 190 | 0 | 80 | F | 0 | 310 |  | Boiler room |  | 7
2024-03-29 | 4740 |  | 78870 | A | DONE | 5 | S |  | ROCK CO. JAIL 6220018 | VD's | 2024-04-04 | Z | 2024-03-25 | 110 | 0 | 0 |  | 0 | 150 |  | Indoor Rec. |  | 10
[6 empty] | 888 | [13 empty] | 28900 |  |  |  | 4230 | 14.64%
WEEK OF 4-1-2024
2024-04-01 | 280 |  | 70577 | A | DONE | 2 | S |  | 43 N. AVIATION 4230079 |  | 2024-04-01 | Z | 2024-04-01 | 30 | 0 | 0 |  | 0 | 60 |  | Misc |  | 0
2024-04-01 | 1709 | sp | 78908 - 78909 | A | DONE | 44 | M-L | neal | BLACKHAWK BTC 6230025 | 1" spiral accu | 2024-04-04 | Z | 2024-01-19 | 130 | 950 | 0 |  | 1010 | 1320 |  | Mezz Lab |  | 76 |  | 2024-03-14
2024-04-02 | 1710 | sp | 78910 - 78911 | A | DONE | 41 | M-L | neal | BLACKHAWK BTC 6230025 | 1" spiral accu | 2024-04-04 | Z | 2024-01-19 | 80 | 930 | 0 |  | 200 | 1180 |  | Mezz Lab |  | 76 |  | 2024-03-14
2024-04-01 | 1729 |  | 78931 - 78932 | A | DONE | 4 | S-M | neal | BLACKHAWK BTC 6230025 | flex , spiralmates | 2024-04-04 | Z | 2024-03-25 | 100 | 0 | 0 |  | 20 | 130 |  | Lower lab |  | 10
2024-04-04 | 2102 |  | 70108 | A | DONE | 2 | S |  | CBOC 6220026 |  | 2024-04-08 | Z | 2024-04-03 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 5
2024-04-05 | 2103 |  | 70110 | A | DONE | 2 | S |  | CBOC 6220026 |  | 2024-04-08 | Z | 2024-04-04 | 20 | 0 | 0 |  | 0 | 20 |  | Kitchen hood |  | 4
2024-04-03 | 3579 |  | 61449 | A | DONE | 2 | S |  | CDIS 6220028 | flex | 2024-04-09 | Z | 2024-03-28 | 50 | 0 | 0 |  | 0 | 80 |  | 1st floor EA |  | 12
2024-04-01 | 3580 |  | 61450 , 61452 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-03-28 | 370 | 0 | 0 |  | 0 | 690 |  | BSMT Splitter vanes |  | 5
2024-04-01 | 3581 |  | EMAIL | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-04-02 | Z | 2024-03-28 | 200 | 0 | 0 |  | 0 | 360 |  | 2nd floor splitter vanes |  | 5
2024-04-03 | 3582 |  | 61504 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-04-09 | Z | 2024-03-29 | 20 | 0 | 0 |  | 0 | 20 |  | LV-8 , 9 |  | 11
2024-04-03 | 3583 |  | 69804 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-03-29 | 60 | 0 | 0 |  | 0 | 120 |  |  |  | 11
2024-04-02 | 3609 |  | 69853 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-04-01 | 150 | 0 | 0 |  | 0 | 410 |  | BSMT-C-SAMP-008 |  | 4
2024-04-03 | 3658 |  | 69854 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-04-04 | Z | 2024-04-03 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 1
2024-04-04 | 3659 |  | 69856 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-04-03 | 20 | 0 | 0 |  | 0 | 20 |  | SAMP 30 out |  | 6
2024-04-05 | 3695 |  | 72200 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-04-04 | 40 | 0 | 0 |  | 0 | 60 |  | Basement AH |  | 5
2024-04-04 | 4184 | bth | L2-A-EAD-028 | A | DONE | 13 | S-M | neal | CDIS 6220028 | paint | 2024-04-09 | Z | 2024-02-19 | 250 | 20 | 40 | F | 0 | 360 |  |  |  | 50
2024-04-04 | 4185 |  | L2-A-EAD-030 | A | DONE | 4 | S-M |  | CDIS 6220028 | paint | 2024-04-09 | Z | 2024-02-19 | 60 | 0 | 30 | F | 20 | 100 |  |  |  | 50
2024-04-04 | 4186 | bth | L2-A-EAD-031 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 110 | 50 | 0 |  | 0 | 190 |  |  |  | 50
2024-04-04 | 4187 | bth | L2-A-EAD-034 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 230 | 20 | 70 | F | 0 | 360 |  |  |  | 50
2024-04-04 | 4188 | bth | L2-A-EAD-035 | A | DONE | 21 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 60 | 20 | 430 | F | 0 | 620 |  |  |  | 50
2024-04-04 | 4189 | bth | L2-A-EAD-036 | A | DONE | 17 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 160 | 20 | 230 | F | 0 | 480 |  |  |  | 50
2024-04-04 | 4190 | bth | L2-A-SALP-063 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 80 | 20 | 140 | F | 0 | 270 |  |  |  | 50
2024-04-04 | 4191 |  | L2-A-SALP-065 | A | DONE | 7 | S-M | neal | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 140 | 0 | 20 | F | 30 | 190 |  |  |  | 50
2024-04-05 | 4193 | bth | L2-A-SALP-067 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 90 | 60 | 0 |  | 0 | 170 |  |  |  | 50
2024-04-01 | 4267 |  | L3-B-EALP-015 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 100 | 0 | 20 | F | 0 | 140 |  |  |  | 21
2024-04-04 | 4268 | bth | L3-B-SALP-014 | A | DONE | 5 | S | neal | CDIS 6220028 | 1" liner | 2024-04-05 | Z | 2024-03-15 | 50 | 60 | 0 |  | 20 | 120 |  |  |  | 21
2024-04-01 | 4269 |  | L3-B-SALP-015 | A | DONE | 2 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-04-05 | Z | 2024-03-15 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 21
2024-04-03 | 4270 | bth | L3-B-SALP-016 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-04-05 | Z | 2024-03-15 | 80 | 20 | 0 |  | 40 | 100 |  |  |  | 21
2024-04-04 | 4271 | bth | L3-B-SALP-017 | A | DONE | 4 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-04-05 | Z | 2024-03-15 | 80 | 20 | 0 |  | 40 | 120 |  |  |  | 21
2024-04-04 | 4272 | bth | L3-B-EAD-016 | A | DONE | 12 | S-M | neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 250 | 50 | 0 |  | 0 | 470 |  |  |  | 21
2024-04-03 | 4273 | bth | L3-B-SAMP-001 | A | DONE | 18 | M |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 230 | 70 | 130 | F | 0 | 580 |  |  |  | 21
2024-04-02 | 4274 | bth | L3-B-SAMP-002 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 140 | 20 | 90 | F | 0 | 280 |  |  |  | 21
2024-04-01 | 4275 | bth | L3-B-SAMP-003 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 40 | 20 | 170 | F | 0 | 280 |  |  |  | 21
2024-04-04 | 4276 | bth | L3-B-SAMP-004 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 100 | 40 | 100 | F | 0 | 280 |  |  |  | 21
2024-04-04 | 4277 | bth | L3-B-SAMP-005 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 60 | 20 | 0 |  | 0 | 90 |  |  |  | 21
2024-04-03 | 4278 | bth | L3-B-SAMP-006 | A | DONE | 19 | M |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 260 | 30 | 180 | F | 0 | 700 |  |  |  | 21
2024-04-04 | 4279 | bth | L3-B-SAMP-007 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 120 | 50 | 0 |  | 0 | 180 |  |  |  | 21
2024-04-02 | 4280 | bth | L3-B-SAMP-008 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 100 | 20 | 210 | F | 0 | 530 |  |  |  | 21
2024-04-03 | 4281 | bth | L3-B-SAMP-009 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 80 | 30 | 180 | F | 0 | 430 |  |  |  | 21
2024-04-04 | 4282 | bth | L3-B-SAMP-010 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 70 | 40 | 80 | F | 0 | 220 |  |  |  | 21
2024-04-02 | 4283 | bth | L3-B-EAMP-001 | A | DONE | 18 | M | pt.neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 430 | 20 | 0 |  | 0 | 740 |  |  |  | 21
2024-04-04 | 4284 | bth | L3-B-EAMP-002 | A | DONE | 11 | S-M | neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 200 | 20 | 40 | F | 0 | 400 |  |  |  | 21
2024-04-04 | 4285 | bth | L3-B-EAMP-003 | A | DONE | 12 | S-M | neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 170 | 50 | 80 | F | 0 | 430 |  |  |  | 21
2024-04-04 | 4286 | bth | L3-B-EAMP-004 | A | DONE | 14 | S-M | neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 270 | 20 | 40 | F | 0 | 430 |  |  |  | 21
2024-04-04 | 4287 | bth | L3-B-EAMP-005 | A | DONE | 9 | S | neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 110 | 70 | 30 | F | 0 | 240 |  |  |  | 21
2024-04-04 | 4288 | bth | L3-B-EAMP-006 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 60 | 110 | 60 | F | 0 | 270 |  |  |  | 21
2024-04-04 | 4289 | bth | L3-B-EAMP-007 | A | DONE | 10 | S-M |  | CDIS 6220028 | 1" spiral accu. | 2024-04-05 | Z | 2024-03-15 | 100 | 30 | 110 | F | 20 | 360 |  |  |  | 21
2024-04-02 | 4290 | bth | L3-B-EAMP-008 | A | DONE | 6 | S | pt.neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 110 | 20 | 0 |  | 0 | 130 |  |  |  | 21
2024-04-03 | 4291 | bth | L3-B-EAMP-009 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 |  | 2024-04-05 | Z | 2024-03-15 | 150 | 30 | 70 | F | 0 | 360 |  | Outs |  | 21
2024-04-01 | 2621 |  | 69408 | A | DONE | 6 | S |  | HARMONICS 6240010 | paint | 2024-04-04 | Z | 2024-03-29 | 100 | 0 | 30 | F | 70 | 160 |  | TA |  | 6
2024-04-03 | 2693 | sp | ROXXY-SALP-01 | A | DONE | 16 | S-M | neal | HARMONICS 6240010 | oval | 2024-04-04 | Z | 2024-02-29 | 160 | 250 | 0 |  | 0 | 480 |  | Flashing |  | 35
2024-04-03 | 2694 | sp | ROXXY-SALP-02 | A | DONE | 12 | S-M | neal | HARMONICS 6240010 | oval | 2024-04-04 | Z | 2024-02-29 | 70 | 230 | 0 |  | 0 | 350 |  |  |  | 35
2024-04-03 | 2695 | sp | ROXXY-SALP-03 | A | DONE | 12 | S-M | neal | HARMONICS 6240010 | oval | 2024-04-04 | Z | 2024-02-29 | 50 | 230 | 0 |  | 0 | 360 |  |  |  | 35
2024-04-03 | 2696 | sp | ROXXY-SALP-04 | A | DONE | 10 | S-M | neal | HARMONICS 6240010 | oval | 2024-04-04 | Z | 2024-02-29 | 40 | 210 | 0 |  | 0 | 280 |  |  |  | 35
2024-04-02 | 2697 | sp | ROXXY-SALP-05 | A | DONE | 11 | S-M | neal | HARMONICS 6240010 | oval | 2024-04-04 | Z | 2024-02-29 | 50 | 210 | 0 |  | 0 | 300 |  |  |  | 35
2024-04-03 | 2698 | sp | ROXXY-SALP-06 | A | DONE | 13 | S-M | neal | HARMONICS 6240010 | oval | 2024-04-04 | Z | 2024-02-29 | 40 | 270 | 0 |  | 0 | 350 |  |  |  | 35
2024-04-03 | 2699 | bth | ROXXY-SALP-07 | A | DONE | 10 | S-M |  | HARMONICS 6240010 |  | 2024-04-04 | Z | 2024-02-29 | 160 | 20 | 70 | F | 0 | 280 |  |  |  | 35
2024-04-01 | 4603 |  | 69409 | A | DONE | 4 | S |  | HARMONICS 6240010 |  | 2024-04-04 | Z | 2024-03-29 | 90 | 0 | 0 |  | 0 | 150 |  | Roof Drops |  | 6
2024-04-01 | 2263 |  | 69031 - 69032 | A | DONE | 4 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-04-05 | Z | 2024-03-27 | 90 | 0 | 0 |  | 40 | 130 |  | D-ceiling tie-ins |  | 9
2024-04-01 | 2264 |  | 69033 - 69034 | A | DONE | 4 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-04-05 | Z | 2024-03-27 | 80 | 0 | 0 |  | 30 | 110 |  | D-ceiling tie-ins |  | 9
2024-04-04 | 2265 | w | 69036 | A | DONE | 2 | S-M | ss | HERITAGE 6220024 |  | 2024-04-05 | Z | 2024-03-27 | 50 | 0 | 0 |  | 0 | 110 |  | Misc |  | 9
2024-04-01 | 2266 |  | 68994 - 68995 | A | DONE | 2 | S | neal | HERITAGE 6220024 | flex , paint | 2024-04-05 | Z | 2024-03-27 | 40 | 0 | 0 |  | 0 | 50 |  | HP 166 RA |  | 9
2024-04-02 | 2267 | bth | 68996 | A | DONE | 2 | S | neal | HERITAGE 6220024 | flex | 2024-04-05 | Z | 2024-03-27 | 20 | 30 | 0 |  | 0 | 60 |  | HP 104 RA |  | 9
2024-04-01 | 2268 |  | 69038 | A | DONE | 3 | S |  | HERITAGE 6220024 |  | 2024-04-02 | Z | 2024-03-29 | 30 | 0 | 0 |  | 0 | 40 |  | E-section kitchen hood |  | 4
2024-04-03 | 2269 |  | 69301 - 69302 | A | DONE | 4 | S |  | HERITAGE 6220024 | 1" liner | 2024-04-05 | Z | 2024-04-02 | 100 | 0 | 0 |  | 20 | 180 |  | 1st SA |  | 3
2024-04-02 | 2270 |  | 69039 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-04-05 | Z | 2024-04-02 | 20 | 0 | 0 |  | 0 | 30 |  | Outs |  | 3
2024-04-03 | 2271 |  | 68997 | A | DONE | 8 | S-M |  | HERITAGE 6220024 |  | 2024-04-05 | Z | 2024-04-02 | 180 | 0 | 0 |  | 0 | 200 |  | Roof cap |  | 3
2024-04-03 | 2272 | sp | 69304 | A | DONE | 3 | S |  | HERITAGE 6220024 |  | 2024-04-05 | Z | 2024-04-03 | 0 | 60 | 0 |  | 0 | 70 |  | P-locker room |  | 2
2024-04-04 | 2273 |  | 69040 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-04-09 | Z | 2024-04-03 | 20 | 0 | 0 |  | 0 | 30 |  | C-OA |  | 6
2024-04-01 | 3726 |  | 67659 | A | DONE | 2 | S |  | KOHL CENTER 6210034 |  | 2024-04-02 | Z | 2024-04-01 | 20 | 0 | 0 |  | 0 | 20 |  | Fan |  | 1
2024-04-04 | 1113 |  | 72904 | A | DONE | 2 | S |  | LABCORP 6240011 |  | 2024-04-08 | Z | 2024-04-03 | 20 | 0 | 0 |  | 0 | 30 |  | Flat stock |  | 5
2024-04-01 | 423 | sp | 68516 - 68517 | A | DONE | 28 | S-M | alum | MEMORIAL HS 6210024 |  | 2024-04-02 | Z | 2023-12-06 | 290 | 390 | 0 |  | 0 | 350 |  | Pool Duct |  | 118
2024-04-01 | 424 |  | 68518 - 68519 | A | DONE | 44 | S-M | alum | MEMORIAL HS 6210024 |  | 2024-04-02 | Z | 2023-12-06 | 560 | 0 | 540 | F | 0 | 680 |  | Pool Duct |  | 118
2024-04-05 | 789 |  | 68549 - 68550 | A | DONE | 12 | S-M | alum | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-20 | 300 | 0 | 0 |  | 0 | 420 |  | Pool AHU |  | 20
2024-04-01 | 790 |  | 68551 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-04-09 | Z | 2024-03-20 | 50 | 0 | 0 |  | 30 | 110 |  | Pool room EC's |  | 20
2024-04-01 | 791 |  | 68553 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-20 | 30 | 0 | 0 |  | 0 | 70 |  | Fume Hood |  | 20
2024-04-03 | 796 |  | 68559 | A | DONE | 4 | S |  | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-25 | 40 | 0 | 40 | F | 0 | 90 |  | AHU-3 Tie ins |  | 15
2024-04-01 | 798 |  | 68561 - 68562 | A | DONE | 4 | S-M |  | MEMORIAL HS 6210024 | 1" liner | 2024-04-09 | Z | 2024-03-26 | 80 | 0 | 0 |  | 50 | 200 |  | AHU-P1 SA |  | 14
2024-04-01 | 799 |  | 68563 | A | DONE | 3 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-04-09 | Z | 2024-03-26 | 60 | 0 | 0 |  | 50 | 140 |  | P-1 RA , CB 43 |  | 14
2024-04-04 | 2150 |  | 68564 - 68565 | A | DONE | 14 | S-M |  | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-26 | 150 | 0 | 180 | F | 0 | 390 |  | P-1 RA , CB 43 |  | 14
2024-04-01 | 2151 | w | 68566 | A | DONE | 2 | S | ss | MEMORIAL HS 6210024 |  | 2024-04-02 | Z | 2024-03-28 | 30 | 0 | 0 |  | 0 | 50 |  | Misc |  | 5
2024-04-01 | 1144 |  | 67508 | A | DONE | 8 | S |  | MENDOTA FOOD 6220027 |  | 2024-04-04 | Z | 2024-03-27 | 180 | 0 | 0 |  | 0 | 320 |  | Line set angles |  | 8
2024-04-01 | 1146 |  | 67466 | A | DONE | 5 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-04 | Z | 2024-03-29 | 120 | 0 | 0 |  | 0 | 180 |  | 1st floor RA/EA |  | 6
2024-04-03 | 1147 |  | 67467 | A | DONE | 2 | S | alum | MENDOTA FOOD 6220027 |  | 2024-04-04 | Z | 2024-03-29 | 30 | 0 | 0 |  | 0 | 30 |  | BSMT SALP 51 |  | 6
2024-04-03 | 1148 | bth | 67468 | A | DONE | 10 | S-M | pt.alum | MENDOTA FOOD 6220027 |  | 2024-04-04 | Z | 2024-04-03 | 90 | 160 | 0 |  | 0 | 230 |  | End caps |  | 1
2024-04-03 | 2618 |  | 69499 | A | DONE | 12 | S-M |  | OLIV 6210030 | MOD , paint | 2024-04-04 | Z | 2024-03-25 | 340 | 0 | 0 |  | 0 | 570 |  | 1st floor B |  | 10
2024-04-03 | 2622 |  | 70578 | A | DONE | 2 | S |  | OLIV 6210030 |  | 2024-04-04 | Z | 2024-04-03 | 40 | 0 | 0 |  | 0 | 190 |  | Misc |  | 1
2024-04-04 | 1981 |  | 37558 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 | paint | 2024-04-08 | Z | 2024-04-03 | 40 | 0 | 0 |  | 20 | 60 |  | TA |  | 5
2024-04-03 | 4536 |  | 72375 | A | DONE | 3 | S-M |  | RAMC 6230009 |  | 2024-04-08 | Z | 2024-03-21 | 60 | 0 | 0 |  | 0 | 70 |  | Splitter vanes |  | 18
2024-04-04 | 4537 | sp | 72376 | A | DONE | 6 | S |  | RAMC 6230009 |  | 2024-04-08 | Z | 2024-03-21 | 20 | 110 | 0 |  | 0 | 130 |  | 1st SA Misc |  | 18
2024-04-03 | 4538 |  | 72377 | A | DONE | 27 | M |  | RAMC 6230009 |  | 2024-04-08 | Z | 2024-03-25 | 670 | 0 | 0 |  | 0 | 1860 |  | Basement outs |  | 14
2024-04-02 | 4741 | sp | 78871 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-04-04 | Z | 2024-04-01 | 30 | 0 | 0 |  | 0 | 50 |  | Jail |  | 3
2024-04-05 | 4650 | sp | 70304 | delete |  |  | S |  | ST.BERNARD 2230056 |  | 2024-04-15 | Z | 2024-03-25 | [7 empty] | Rm 118 SA |  | 21
2024-04-05 | 4651 | sp | 70306 - 70307 | delete |  |  | S-M |  | ST.BERNARD 2230056 |  | 2024-04-15 | Z | 2024-03-25 | [7 empty] | F-6 SA Rm 114 113 SA |  | 21
2024-04-05 | 4652 | sp | 70308 | delete |  |  | S |  | ST.BERNARD 2230056 |  | 2024-04-15 | Z | 2024-03-25 | [7 empty] | 1st Fl SA |  | 21
2024-04-05 | 4653 | bth | 70309 - 70310 | delete |  |  | S-M |  | ST.BERNARD 2230056 |  | 2024-04-15 | Z | 2024-03-25 | [7 empty] | 2nd Fl SA , Hallway 108 |  | 21
2024-04-01 | 279 |  | 70221 | A | DONE | 2 | S |  | TOMAH HEALTH 4240011 | paint | 2024-04-02 | Z | 2024-03-29 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 4
2024-04-04 | 284 |  | 70222 | A | DONE | 2 | S |  | TOMAH HEALTH 4240011 | paint | 2024-04-04 | Z | 2024-04-04 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 0
2024-04-01 | 2796 |  | 72408 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-04-08 | Z | 2024-03-26 | 20 | 0 | 0 |  | 0 | 30 |  | 3rd floor |  | 13
2024-04-04 | 2797 |  | 72409 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-04-08 | Z | 2024-03-27 | 20 | 0 | 0 |  | 0 | 20 |  | Arena |  | 12
2024-04-04 | 2798 | w | 72410 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-04-08 | Z | 2024-03-28 | 20 | 0 | 0 |  | 0 | 20 |  | BSL-3 |  | 11
2024-04-03 | 1515 | sp | 58863 | A | DONE | 2 | S |  | WAUSHARA CO. GOV 6220010 |  | 2024-04-04 | Z | 2024-04-03 | 20 | 0 | 0 |  | 0 | 20 |  | Extra |  | 1
2024-04-04 | 282 |  | 70109 | A | DONE | 2 | S |  | WICELL 2230040 |  | 2024-04-08 | Z | 2024-04-03 | 20 | 0 | 0 |  | 0 | 20 |  | VAV-128A |  | 5
[6 empty] | 821 | [13 empty] | 25310 |  |  |  | 5220 | 20.62%
WEEK OF 4-8-2024
2024-04-10 | 2202 |  | 3RDFL-1 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-04-10 | Z | 2024-04-10 | 20 | 0 | 0 |  | 0 | 30 |  | Caps |  | 0
2024-04-09 | 281 | sp | 78723 | A | DONE | 4 | S-M |  | ALDEVRON 10054760 |  | 2024-04-11 | Z | 2024-04-03 | 20 | 60 | 0 |  | 0 | 80 |  | EA snorkel |  | 8
2024-04-09 | 1730 | sp | 78944 - 78945 | A | DONE | 3 | S-M | neal | BLACKHAWK BTC 6230025 | 1" spiral accu. | 2024-04-11 | Z | 2024-04-03 | 50 | 20 | 0 |  | 30 | 90 |  | Menu lab |  | 8
2024-04-11 | 750 |  | 69805 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-04-09 | 20 | 0 | 0 |  | 0 | 20 |  | GET-1-2-45 |  | 7
2024-04-10 | 776 | sp | 69858 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-04-09 | 20 | 0 | 0 |  | 0 | 20 |  | Extra 6" |  | 3
2024-04-11 | 778 | sp | 69859 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-04-12 | Z | 2024-04-11 | 0 | 20 | 0 |  | 0 | 20 |  | EA Tie in |  | 1
2024-04-10 | 3500 | bth | L3-A-SAMP-023 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 50 | 20 | 200 | F | 0 | 370 |  |  |  | 25
2024-04-10 | 3501 | bth | L3-A-SAMP-024 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 110 | 30 | 200 | F | 0 | 450 |  |  |  | 25
2024-04-10 | 3502 | bth | L3-A-SAMP-025 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 50 | 20 | 250 | F | 0 | 380 |  |  |  | 25
2024-04-10 | 3503 | bth | L3-A-SAMP-026 | A | DONE | 17 | S-M |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 160 | 70 | 180 | F | 0 | 470 |  |  |  | 25
2024-04-10 | 3504 | bth | L3-A-SAMP-027 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 70 | 30 | 70 | F | 0 | 190 |  |  |  | 25
2024-04-11 | 3554 | bth | L4-B-EALP-12 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 30 | 40 | 70 | F | 0 | 150 |  |  |  | 19
2024-04-11 | 3555 | bth | L4-B-EALP-13 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 40 | 20 | 50 | F | 0 | 130 |  |  |  | 19
2024-04-12 | 3556 | sp | L4-B-EALP-14 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 19
2024-04-11 | 3558 | sp | L4-B-EALP-17 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 19
2024-04-11 | 3560 | sp | L4-B-EALP-19 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 20 | 60 | 0 |  | 0 | 70 |  |  |  | 19
2024-04-11 | 3561 | sp | L4-B-EALP-20 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 20 | 80 | 0 |  | 0 | 100 |  |  |  | 19
2024-04-11 | 3563 | sp | L4-B-EALP-23 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 19
2024-04-11 | 3564 | bth | L4-B-SALP-13 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 50 | 70 | 0 |  | 20 | 130 |  |  |  | 19
2024-04-12 | 3566 |  | L4-B-SALP-16 | A | DONE | 3 | S | neal | CDIS 6220028 | 1" liner , paint | 2024-04-16 | Z | 2024-03-28 | 50 | 0 | 20 | F | 40 | 80 |  |  |  | 19
2024-04-12 | 3569 | bth | L4-B-SALP-20 | A | DONE | 10 | S | neal | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 130 | 100 | 0 |  | 20 | 260 |  |  |  | 19
2024-04-11 | 3572 | bth | L4-B-SALP-24 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 50 | 30 | 30 | F | 20 | 150 |  |  |  | 19
2024-04-08 | 3696 |  | 69857 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-04-09 | Z | 2024-04-05 | 20 | 0 | 0 |  | 0 | 20 |  | BSMT-B-EAD-2 |  | 4
2024-04-10 | 3697 |  | 12345 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-04-08 | 200 | 0 | 0 |  | 0 | 370 |  | Splitter vanes |  | 4
2024-04-10 | 3698 |  | 12346 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-04-08 | 90 | 0 | 0 |  | 0 | 180 |  | Splitter vanes |  | 4
2024-04-10 | 3699 |  | 59482 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-04-09 | 30 | 0 | 0 |  | 0 | 40 |  | 3rd floor |  | 3
2024-04-08 | 4192 | bth | L2-A-SALP-066 | A | DONE | 4 | S-M | neal | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 30 | 30 | 20 | F | 0 | 90 |  |  |  | 50
2024-04-08 | 4194 | bth | L2-A-SALP-068 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 50 | 20 | 70 | F | 0 | 160 |  |  |  | 50
2024-04-08 | 4195 | bth | L2-A-SALP-069 | A | DONE | 7 | S-M | neal | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 90 | 20 | 60 | F | 0 | 210 |  |  |  | 50
2024-04-08 | 4196 | bth | L2-A-SALP-070 | A | DONE | 7 | S-M | neal | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 130 | 30 | 0 |  | 30 | 190 |  |  |  | 50
2024-04-08 | 4197 | bth | L2-A-SALP-071 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 70 | 160 | 0 |  | 0 | 260 |  |  |  | 50
2024-04-08 | 4198 | bth | L2-A-SALP-072 | A | DONE | 6 | S-M | neal | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 60 | 70 | 0 |  | 30 | 150 |  |  |  | 50
2024-04-08 | 4199 | sp | L2-A-SALP-073 | A | DONE | 5 | S-M | neal | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 20 | 90 | 0 |  | 0 | 130 |  |  |  | 50
2024-04-08 | 4200 |  | L2-A-SALP-074 | A | DONE | 3 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 50 | 0 | 20 | F | 20 | 90 |  |  |  | 50
2024-04-08 | 4201 | bth | L2-A-SALP-075 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 50 | 50 | 0 |  | 20 | 110 |  |  |  | 50
2024-04-08 | 4202 | bth | L2-A-SALP-076 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 50 | 50 | 0 |  | 0 | 110 |  |  |  | 50
2024-04-08 | 4203 | bth | L2-A-SALP-079 | A | DONE | 16 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 170 | 110 | 110 | F | 50 | 430 |  |  |  | 50
2024-04-08 | 4204 | bth | L2-A-SALP-080 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 80 | 30 | 200 | F | 0 | 370 |  |  |  | 50
2024-04-08 | 4205 | bth | L2-A-SALP-081 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-04-09 | Z | 2024-02-19 | 70 | 20 | 70 | F | 0 | 180 |  |  |  | 50
2024-04-08 | 4206 |  | L2-A-SALP-082 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner , paint | 2024-04-09 | Z | 2024-02-19 | 80 | 0 | 30 | F | 20 | 120 |  |  |  | 50
2024-04-08 | 4207 | bth | L2-A-SALP-083 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 100 | 30 | 0 |  | 30 | 160 |  |  |  | 50
2024-04-08 | 4208 | bth | L2-A-SALP-0108 | A | DONE | 10 | S-M | neal | CDIS 6220028 | 1" liner | 2024-04-09 | Z | 2024-02-19 | 70 | 20 | 140 | F | 30 | 260 |  |  |  | 50
2024-04-10 | 4295 | bth | L3-A-EAMP-029 | A | DONE | 30 | M-L | neal | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 390 | 40 | 310 | F | 0 | 1310 |  |  |  | 25
2024-04-10 | 4296 | bth | L3-A-EAMP-030 | A | DONE | 33 | M-L | neal | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 380 | 30 | 400 | F | 0 | 1160 |  |  |  | 25
2024-04-10 | 4297 | bth | L3-A-EAMP-031 | A | DONE | 16 | M | neal | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 190 | 20 | 190 | F | 0 | 560 |  |  |  | 25
2024-04-10 | 4298 | bth | L3-A-EAMP-032 | A | DONE | 13 | S-M | neal | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 120 | 60 | 140 | F | 0 | 450 |  |  |  | 25
2024-04-10 | 4299 | bth | L3-A-SAMP-022 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-18 | 120 | 30 | 120 | F | 0 | 350 |  |  |  | 25
2024-04-09 | 4231 |  | 59480 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-04-12 | Z | 2024-03-13 | 70 | 0 | 0 |  | 0 | 120 |  | 3rd Fl Tear Drop |  | 30
2024-04-11 | 293 |  | 79413 | A | DONE | 2 | S |  | CHR HANSEN INC. 30004306 | flex | 2024-04-12 | Z | 2024-04-10 | 40 | 0 | 0 |  | 0 | 70 |  | EA |  | 2
2024-04-08 | 1575 |  | 62372 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 |  | 2024-04-10 | Z | 2024-04-05 | 30 | 0 | 0 |  | 0 | 30 |  | Angles |  | 5
2024-04-11 | 1576 |  | 62374 - 62375 | A | DONE | 2 | S-M |  | EMBASSY SUITES 6220012 | 1" liner , paint | 2024-04-12 | Z | 2024-04-10 | 50 | 0 | 0 |  | 40 | 70 |  | TA |  | 2
2024-04-11 | 1577 |  | 62376 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 | paint | 2024-04-15 | Z | 2024-04-10 | 20 | 0 | 0 |  | 20 | 30 |  | EA Boxes |  | 5
2024-04-10 | 283 |  | 62701 | A | DONE | n/a | S |  | EVCO 2240014 | flex | 2024-04-15 | Z | 2024-04-04 | 0 | 0 | 0 |  | 0 | 0 |  | Misc |  | 11
2024-04-11 | 2624 |  | 79453 | A | DONE | 2 | S |  | HARMONICS 6240010 |  | 2024-04-12 | Z | 2024-04-11 | 20 | 30 | 0 |  | 0 | 30 |  | Kitchen |  | 1
2024-04-10 | 4604 |  | 69410 - 69411 | A | DONE | 8 | S-M |  | HARMONICS 6240010 | paint | 2024-04-11 | Z | 2024-03-29 | 120 | 0 | 60 | F | 20 | 210 |  | Louver tie-ins / DT EA |  | 13
2024-04-10 | 2274 |  | 69303 | A | DONE | 10 | S-M |  | HERITAGE 6220024 |  | 2024-04-12 | Z | 2024-04-03 | 250 | 0 | 0 |  | 0 | 400 |  | DOAS-1 OA |  | 9
2024-04-09 | 2275 |  | 69305 | A | DONE | 2 | S |  | HERITAGE 6220024 | birdscreen | 2024-04-12 | Z | 2024-04-03 | 20 | 0 | 0 |  | 0 | 80 |  | AHU-1 RA gym |  | 9
2024-04-09 | 2276 |  | 69216 | A | DONE | 2 | S | neal | HERITAGE 6220024 |  | 2024-04-12 | Z | 2024-04-04 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor misc |  | 8
2024-04-11 | 2813 |  | 78552 - 78553 | A | DONE | 14 | S-M |  | JANESVILLE ESSR 6230011 | flex , 2" liner | 2024-04-15 | Z | 2024-04-01 | 120 | 0 | 230 | F | 280 | 490 |  | BCU-1 SA |  | 14
2024-04-10 | 2814 |  | 78556 , 78558 | A | DONE | 14 | S-M |  | JANESVILLE ESSR 6230011 | flex , 1" liner | 2024-04-15 | Z | 2024-04-01 | 210 | 0 | 120 | F | 80 | 470 |  | BCU-1 RA |  | 14
2024-04-11 | 2815 |  | 78559 | A | DONE | 3 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-04-15 | Z | 2024-04-01 | 70 | 0 | 0 |  | 0 | 100 |  | BCU-1 OA |  | 14
2024-04-11 | 2816 |  | 78562 - 78563 | A | DONE | 10 | S-M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-04-15 | Z | 2024-04-01 | 200 | 0 | 50 | F | 130 | 300 |  | RE-11 EA |  | 14
2024-04-11 | 2817 |  | 70813 - 70814 | A | DONE | 56 | S-M | alum | JANESVILLE ESSR 6230011 |  | 2024-04-15 | Z | 2024-04-02 | 210 | 0 | 1170 | F | 0 | 950 |  | Pool SA / EA |  | 13
2024-04-10 | 2818 |  | 70815 | A | DONE | 2 | S-M | alum | JANESVILLE ESSR 6230011 |  | 2024-04-15 | Z | 2024-04-03 | 40 | 0 | 0 |  | 0 | 30 |  | Pool RA |  | 12
2024-04-10 | 3727 |  | 67661 | A | DONE | 2 | S | alum | KOHL CENTER 6210034 |  | 2024-04-12 | Z | 2024-04-10 | 20 | 0 | 0 |  | 0 | 20 |  | Angle |  | 2
2024-04-10 | 3728 |  | 67662 | A | DONE | 2 | S-M |  | KOHL CENTER 6210034 |  | 2024-04-12 | Z | 2024-04-10 | 30 | 0 | 0 |  | 0 | 180 |  | Miron |  | 2
2024-04-08 | 788 |  | 68546 - 68548 | A | DONE | 45 | S-M | alum | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-20 | 810 | 0 | 300 | F | 0 | 980 |  | Pool AHU |  | 20
2024-04-08 | 793 |  | 68555 - 68556 | A | DONE | 15 | S-M | alum | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-25 | 370 | 0 | 0 |  | 0 | 420 |  | Pool AHU |  | 15
2024-04-08 | 794 |  | 68557 | A | DONE | 4 | S | alum | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-25 | 100 | 0 | 0 |  | 0 | 140 |  | Pool AHU OA |  | 15
2024-04-08 | 795 |  | 68558 | A | DONE | 5 | S-M |  | MEMORIAL HS 6210024 |  | 2024-04-09 | Z | 2024-03-25 | 110 | 0 | 0 |  | 0 | 140 |  | Pool AHU OA west |  | 15
2024-04-11 | 2152 |  | 68567 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-04-16 | Z | 2024-03-29 | 40 | 0 | 0 |  | 30 | 90 |  | End caps - Fan room |  | 18
2024-04-12 | 2153 | sp | 68568 - 68569 | A | DONE | 4 | S |  | MEMORIAL HS 6210024 |  | 2024-04-16 | Z | 2024-03-29 | 30 | 60 | 0 |  | 0 | 80 |  | EF-G2-1 |  | 18
2024-04-11 | 2154 |  | 68570 , 68572 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 |  | 2024-04-16 | Z | 2024-03-29 | 60 | 0 | 0 |  | 0 | 100 |  | EF-G3-1 |  | 18
2024-04-12 | 2155 | sp | 68571 , 68573 | A | DONE | 15 | S-M |  | MEMORIAL HS 6210024 |  | 2024-04-16 | Z | 2024-03-29 | 150 | 210 | 0 |  | 0 | 420 |  | EF-G3-2 |  | 18
2024-04-10 | 2156 |  | 68574 | A | DONE | 2 | S-M |  | MEMORIAL HS 6210024 |  | 2024-04-16 | Z | 2024-04-03 | 50 | 0 | 0 |  | 0 | 110 |  | Rain guard ERV Door |  | 13
2024-04-12 | 2157 |  | 68575 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-04-16 | Z | 2024-04-11 | 20 | 0 | 0 |  | 0 | 30 |  | Panel cover |  | 5
2024-04-08 | 1149 |  | 67512 - 67513 | A | DONE | 3 | S |  | MENDOTA FOOD 6220027 |  | 2024-04-09 | Z | 2024-04-05 | 30 | 0 | 40 | F | 0 | 80 |  | Basement |  | 4
2024-04-09 | 2529 |  | PHSM-SAMP-1 | A | DONE | 8 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 150 | 0 | 40 | F | 0 | 230 |  |  |  | 31
2024-04-09 | 2530 |  | PHSM-SAMP-3 | A | DONE | 7 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 170 | 0 | 0 |  | 0 | 200 |  |  |  | 31
2024-04-09 | 2531 |  | PHSM-SAMP-4 | A | DONE | 11 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 200 | 0 | 60 | F | 0 | 360 |  |  |  | 31
2024-04-09 | 2532 |  | PHSM-SAMP-5 | A | DONE | 12 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 280 | 0 | 0 |  | 0 | 460 |  |  |  | 31
2024-04-09 | 2533 |  | PHSM-SAMP-6 | A | DONE | 11 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 200 | 0 | 60 | F | 0 | 360 |  |  |  | 31
2024-04-09 | 2534 |  | PHSM-RA-1 | A | DONE | 16 | S |  | MENDOTA FOOD 6220027 | spiral mates | 2024-04-11 | Z | 2024-03-11 | 380 | 0 | 0 |  | 0 | 470 |  |  |  | 31
2024-04-09 | 2535 |  | PHSM-RAMP-2 | A | DONE | 17 | M |  | MENDOTA FOOD 6220027 | spiral mates | 2024-04-11 | Z | 2024-03-11 | 240 | 0 | 180 | F | 0 | 730 |  |  |  | 31
2024-04-09 | 2536 |  | PHSM-RAMP-3 | A | DONE | 14 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 270 | 0 | 60 | F | 0 | 370 |  |  |  | 31
2024-04-09 | 2537 |  | PHSM-RAMP-4 | A | DONE | 12 | S-M |  | MENDOTA FOOD 6220027 | spiral mates | 2024-04-11 | Z | 2024-03-11 | 220 | 0 | 80 | F | 0 | 430 |  |  |  | 31
2024-04-09 | 2538 |  | PHSM-RAMP-5 | A | DONE | 13 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 270 | 0 | 40 | F | 0 | 430 |  |  |  | 31
2024-04-09 | 2539 |  | PHSM-OA-1 | A | DONE | 16 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 330 | 0 | 60 | F | 0 | 500 |  |  |  | 31
2024-04-09 | 2540 |  | PHSM-OA-2 | A | DONE | 5 | S |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 120 | 0 | 0 |  | 0 | 330 |  |  |  | 31
2024-04-09 | 2541 |  | PHSM-OA-3 | A | DONE | 11 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 260 | 0 | 0 |  | 0 | 490 |  |  |  | 31
2024-04-09 | 2542 |  | PHSM-EA-1 | A | DONE | 11 | S |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 220 | 0 | 50 | F | 0 | 360 |  |  |  | 31
2024-04-09 | 2543 |  | PHSM-EA-2 | A | DONE | 16 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-11 | Z | 2024-03-11 | 300 | 0 | 90 | F | 0 | 490 |  |  |  | 31
2024-04-08 | 3830 |  | 67469 - 67470 | A | DONE | 3 | S |  | MENDOTA FOOD 6220027 |  | 2024-04-09 | Z | 2024-04-05 | 60 | 0 | 0 |  | 0 | 90 |  | Basement / 1st floor |  | 4
2024-04-12 | 3831 |  | 67514 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 |  | 2024-04-15 | Z | 2024-04-11 | 50 | 0 | 0 |  | 0 | 60 |  | Basement RA |  | 4
2024-04-10 | 3250 | sp | 62521 - 62522 | A | DONE | 8 | S-M | neal | NIC 6240004 | spiral mates | 2024-04-16 | Z | 2024-04-01 | 70 | 120 | 0 |  | 0 | 270 |  |  |  | 15
2024-04-11 | 3251 | sp | 62523 - 62524 | A | DONE | 18 | S-M | neal | NIC 6240004 | spiral mates | 2024-04-16 | Z | 2024-04-01 | 100 | 350 | 0 |  | 0 | 690 |  |  |  | 15
2024-04-10 | 2623 |  | 79451 - 79452 | A | DONE | 9 | S-M |  | OLIV 6210030 | birdscreen , flex | 2024-04-12 | Z | 2024-04-09 | 210 | 0 | 0 |  | 0 | 260 |  | SF-5 / Gen |  | 3
2024-04-09 | 4395 | bth | 37556 - 37557 | A | DONE | 9 | S-M | neal | PROMEGA BTC 6230022 | VD's | 2024-04-10 | Z | 2024-04-04 | 110 | 100 | 0 |  | 0 | 250 |  | Engineering |  | 6
2024-04-09 | 1982 | bth | 62939 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 |  | 2024-04-10 | Z | 2024-04-04 | 30 | 20 | 0 |  | 0 | 60 |  | Clean room |  | 6
2024-04-10 | 4539 |  | 72379 | A | DONE | 4 | S-M |  | RAMC 6230009 | oval | 2024-04-15 | Z | 2024-04-05 | 60 | 20 | 0 |  | 0 | 110 |  | RA 1st floor |  | 10
2024-04-09 | 4541 |  | 70664 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-04-09 | Z | 2024-04-09 | 50 | 0 | 0 |  | 0 | 70 |  | Curb flashing |  | 0
2024-04-09 | 4742 |  | 78872 | A | DONE | 2 | S-M |  | ROCK CO. JAIL 6220018 | VD's | 2024-04-11 | Z | 2024-04-04 | 40 | 0 | 0 |  | 0 | 60 |  | Jail |  | 7
2024-04-11 | 4656 |  | 70316 | A | DONE | 5 | S |  | ST.BERNARD 2230056 |  | 2024-04-15 | Z | 2024-03-27 | 110 | 0 | 0 |  | 0 | 100 |  | 2nd fl RA drops |  | 19
2024-04-11 | 4654 |  | 70311 - 70312 | A | DONE | 16 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-04-15 | Z | 2024-03-25 | 260 | 0 | 120 | F | 280 | 590 |  | Sacristy 111 RA |  | 21
2024-04-11 | 4655 |  | 70313 | A | DONE | 10 | S-M |  | ST.BERNARD 6230023 |  | 2024-04-15 | Z | 2024-03-25 | 120 | 0 | 130 | F | 0 | 370 |  | Sacristy 111 RA |  | 21
2024-04-12 | 4657 |  | 70319 | A | DONE | 2 | S |  | ST.BERNARD 6230023 | 1" liner , paint | 2024-04-19 | Z | 2024-04-05 | 30 | 0 | 0 |  | 0 | 50 |  | FCU mock up |  | 14
2024-04-11 | 2012 |  | 67987 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2024-04-15 | Z | 2024-03-28 | 160 | 0 | 0 |  | 0 | 330 |  | AHU-5 RA |  | 18
2024-04-09 | 2799 | w | 72411 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-04-15 | Z | 2024-04-05 | 40 | 0 | 0 |  | 0 | 140 |  | BSL-3 |  | 10
2024-04-11 | 3200 | bth | 72412 - 72413 | A | DONE | 3 | S-M | ss | UW-VET MED 6210014 |  | 2024-04-15 | Z | 2024-04-05 | 40 | 20 | 0 |  | 0 | 60 |  | 3rd floor hoods |  | 10
2024-04-11 | 3201 |  | 72414 | A | DONE | 4 | S |  | UW-VET MED 6210014 |  | 2024-04-15 | Z | 2024-04-05 | 100 | 0 | 0 |  | 0 | 120 |  | 3rd floor |  | 10
2024-04-10 | 3202 | sp | 72415 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-04-15 | Z | 2024-04-09 | 20 | 20 | 0 |  | 0 | 30 |  | 3rd floor EA |  | 6
2024-04-09 | 285 |  | 70603 | A | DONE | 2 | S | ss | WICELL 8230015 |  | 2024-04-12 | Z | 2024-04-08 | 20 | 0 | 0 |  | 0 | 20 |  | Box |  | 4
[6 empty] | 888 | [13 empty] | 26930 |  |  |  | 4540 | 16.86%
WEEK OF 4-15-2024
2024-04-17 | 155 |  | 32496 | A | DONE | 2 | S |  | ACADIA 8230013 |  | 2024-04-18 | Z | 2024-04-17 | 50 | 0 | 0 |  | 0 | 30 |  | COVERS |  | 1
2024-04-17 | 1731 | sp | 78946 | A | DONE | 12 | S-M | neal | BLACKHAWK BTC 6230025 | spiral mates | 2024-04-18 | Z | 2024-04-04 | 120 | 160 | 0 |  | 0 | 400 |  | Weld EA East |  | 14
2024-04-17 | 1732 | sp | 78947 - 78950 | A | DONE | 18 | M | neal | BLACKHAWK BTC 6230025 |  | 2024-04-18 | Z | 2024-04-04 | 60 | 390 | 0 |  | 0 | 570 |  | Weld EA East |  | 14
2024-04-17 | 1733 | sp | 68016 - 68018 | A | DONE | 18 | S-M | neal | BLACKHAWK BTC 6230025 | spiral mates | 2024-04-18 | Z | 2024-04-04 | 70 | 360 | 0 |  | 0 | 560 |  | Weld EA West |  | 14
2024-04-17 | 1734 | sp | 68019 | A | DONE | 12 | S-M | neal | BLACKHAWK BTC 6230025 | spiral mates | 2024-04-18 | Z | 2024-04-04 | 300 | 0 | 0 |  | 0 | 550 |  | Weld EA |  | 14
2024-04-15 | 1735 |  | 78943 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-04-18 | Z | 2024-04-04 | 40 | 0 | 0 |  | 0 | 70 |  | Weld EA hangers |  | 14
2024-04-15 | 1736 |  | 68020 | A | DONE | 11 | S-M | neal | BLACKHAWK BTC 6230025 | birdscreen | 2024-04-18 | Z | 2024-04-05 | 260 | 0 | 0 |  | 0 | 570 |  | EF 4-5 Drops |  | 13
2024-04-18 | 3505 | bth | L3-A-SALP-056 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-04-19 | Z | 2024-03-18 | 110 | 120 | 0 |  | 40 | 260 |  |  |  | 32
2024-04-18 | 3506 | bth | L3-A-SALP-057 | A | DONE | 9 | S-M | neal | CDIS 6220028 | 1" liner | 2024-04-19 | Z | 2024-03-18 | 110 | 110 | 0 |  | 50 | 260 |  |  |  | 32
2024-04-18 | 3507 | bth | L3-A-SALP-058 | A | DONE | 11 | S-M | neal | CDIS 6220028 | 1" liner | 2024-04-19 | Z | 2024-03-18 | 150 | 120 | 0 |  | 60 | 310 |  |  |  | 32
2024-04-18 | 3508 | bth | L3-A-SALP-061 | A | DONE | 9 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-04-19 | Z | 2024-03-18 | 120 | 90 | 0 |  | 30 | 250 |  |  |  | 32
2024-04-18 | 3509 | bth | L3-A-SALP-062 | A | DONE | 9 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-04-19 | Z | 2024-03-18 | 90 | 120 | 0 |  | 30 | 250 |  |  |  | 32
2024-04-17 | 3510 | bth | L3-A-SALP-063 | A | DONE | 12 | S-M | neal | CDIS 6220028 | 1" liner | 2024-04-19 | Z | 2024-03-18 | 200 | 20 | 80 | F | 50 | 320 |  |  |  | 32
2024-04-17 | 3511 | bth | L3-A-EALP-046 | A | DONE | 11 | S-M | neal | CDIS 6220028 |  | 2024-04-19 | Z | 2024-03-18 | 150 | 30 | 80 | F | 0 | 320 |  |  |  | 32
2024-04-17 | 3512 | bth | L3-A-EALP-047 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-04-19 | Z | 2024-03-18 | 140 | 30 | 60 | F | 0 | 280 |  |  |  | 32
2024-04-18 | 3513 | bth | L3-A-EALP-048 | A | DONE | 18 | S-M | pt.neal | CDIS 6220028 |  | 2024-04-19 | Z | 2024-03-18 | 290 | 80 | 60 | F | 0 | 500 |  |  |  | 32
2024-04-15 | 3550 |  | 61445 - 61446 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-21 | 160 | 0 | 0 |  | 0 | 320 |  | Sleeves |  | 26
2024-04-15 | 3553 | bth | L4-B-EALP-11 | A | DONE | 6 | S | neal | CDIS 6220028 | paint | 2024-04-16 | Z | 2024-03-28 | 90 | 40 | 0 |  | 20 | 160 |  |  |  | 19
2024-04-15 | 3557 | sp | L4-B-EALP-16 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 19
2024-04-15 | 3559 | bth | L4-B-EALP-18 | A | DONE | 4 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 70 | 20 | 0 |  | 0 | 90 |  |  |  | 19
2024-04-15 | 3562 | bth | L4-B-EALP-21 | A | DONE | 6 | S | neal | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 50 | 70 | 30 | F | 0 | 180 |  |  |  | 19
2024-04-15 | 3565 | bth | L4-B-SALP-14 | A | DONE | 7 | S |  | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 60 | 100 | 0 |  | 30 | 160 |  |  |  | 19
2024-04-15 | 3567 | bth | L4-B-SALP-17 | A | DONE | 14 | S-M |  | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 110 | 50 | 170 | F | 20 | 390 |  |  |  | 19
2024-04-15 | 3568 | bth | L4-B-SALP-19 | A | DONE | 9 | S |  | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 60 | 160 | 0 |  | 20 | 230 |  |  |  | 19
2024-04-15 | 3570 | bth | L4-B-SALP-22 | A | DONE | 4 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 40 | 40 | 0 |  | 20 | 80 |  |  |  | 19
2024-04-15 | 3571 | bth | L4-B-SALP-23 | A | DONE | 6 | S | pt.neal | CDIS 6220028 | 1" liner , paint | 2024-04-16 | Z | 2024-03-28 | 130 | 20 | 0 |  | 40 | 160 |  |  |  | 19
2024-04-15 | 3573 | bth | L4-B-SALP-25 | A | DONE | 6 | S | neal | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 60 | 90 | 0 |  | 30 | 180 |  |  |  | 19
2024-04-15 | 3574 | bth | L4-B-SALP-26 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner,1" spiral accu | 2024-04-16 | Z | 2024-03-28 | 50 | 80 | 0 |  | 80 | 180 |  |  |  | 19
2024-04-15 | 3575 | bth | L4-B-SALP-27 | A | DONE | 7 | S |  | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 70 | 50 | 40 | F | 20 | 170 |  |  |  | 19
2024-04-15 | 3576 | bth | L4-B-SALP-28 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 60 | 40 | 50 | F | 20 | 180 |  |  |  | 19
2024-04-15 | 3577 | bth | L4-B-SALP-29 | A | DONE | 5 | S | neal | CDIS 6220028 | 1" liner | 2024-04-16 | Z | 2024-03-28 | 90 | 30 | 0 |  | 20 | 140 |  |  |  | 19
2024-04-15 | 3578 | bth | L4-B-SALP-30 | A | DONE | 6 | S | neal | CDIS 6220028 |  | 2024-04-16 | Z | 2024-03-28 | 70 | 70 | 0 |  | 0 | 160 |  |  |  | 19
2024-04-18 | 3584 |  | L4-B-EAMP-001 | A | DONE | 23 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 400 | 0 | 180 | F | 0 | 1180 |  |  |  | 22
2024-04-18 | 3590 |  | L4-B-EAMP-007 | A | DONE | 7 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 0 | 0 | 170 | F |  | 210 |  |  |  | 22
2024-04-19 | 3595 |  | L4-B-RAD-001 | A | DONE | 2 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 22
2024-04-19 | 3597 |  | L4-B-SAMP-002 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 140 | 0 | 120 | F | 0 | 310 |  |  |  | 22
2024-04-19 | 3599 |  | L4-B-SAMP-004 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 170 | 0 | 120 | F | 0 | 420 |  |  |  | 22
2024-04-15 | 777 |  | 59483 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-04-16 | Z | 2024-04-11 | 60 | 0 | 0 |  | 0 | 90 |  | 3rd floor test caps |  | 5
2024-04-18 | 779 |  | 69901 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-12 | 0 | 0 | 70 |  |  | 100 |  | Flashing |  | 11
2024-04-15 | 780 |  | 61313 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-15 | Z | 2024-04-15 | 20 | 0 | 0 |  | 0 | 40 |  | Sleeves |  | 0
2024-04-17 | 781 |  | 59484 | A | DONE | 3 | S |  | CDIS 6220028 | 1"liner | 2024-04-19 | Z | 2024-04-16 | 20 | 0 | 0 |  | 10 | 20 |  | L3-B-SALP-3 EC |  | 3
2024-04-18 | 156 |  | 79752 | A | DONE | 2 | S |  | COMPASS HP 4230088 |  | 2024-04-19 | Z | 2024-04-18 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 1
2024-04-15 | 286 |  | 70282 | A | DONE | 6 | S-M |  | COMPASS HP 4230088 |  | 2024-04-17 | Z | 2024-04-09 | 140 | 0 | 0 |  | 130 | 260 |  | RTU Drops |  | 8
2024-04-18 | 287 | sp | 70283 - 70284 | A | DONE | 35 | M |  | COMPASS HP 4230088 | oval , accuflange | 2024-04-17 | Z | 2024-04-09 | 270 | 0 | 590 | F | 0 | 1000 |  | SA High side |  | 8
2024-04-16 | 288 | sp | 70285 - 70286 | A | DONE | 10 | S-M |  | COMPASS HP 4230088 |  | 2024-04-17 | Z | 2024-04-09 | 160 | 90 | 0 |  | 0 | 280 |  | VAV-10 , 18 |  | 8
2024-04-15 | 289 | sp | 70287 - 70288 | A | DONE | 6 | S-M |  | COMPASS HP 4230088 |  | 2024-04-17 | Z | 2024-04-09 | 40 | 90 | 0 |  | 0 | 120 |  | VAV-11 , 14 |  | 8
2024-04-16 | 290 | sp | 70289 - 70290 | A | DONE | 12 | S-M |  | COMPASS HP 4230088 |  | 2024-04-17 | Z | 2024-04-09 | 90 | 210 | 0 |  | 0 | 330 |  | VAV-12 , 13 |  | 8
2024-04-16 | 291 | sp | 70291 - 70292 | A | DONE | 10 | S-M |  | COMPASS HP 4230088 |  | 2024-04-17 | Z | 2024-04-09 | 150 | 80 | 0 |  | 0 | 250 |  | VAV-17 |  | 8
2024-04-15 | 295 |  | 70295 | A | DONE | 14 | S-M |  | COMPASS HP 4230088 | 1" liner | 2024-04-17 | Z | 2024-04-10 | 280 | 0 | 70 | F | 80 | 540 |  | RTU RA |  | 7
2024-04-15 | 1128 |  | 59478 - 59479 | A | DONE | 7 | S-M |  | DANE CO. AIRPORT 6210011 |  | 2024-04-18 | Z | 2024-04-08 | 170 | 0 | 0 |  | 0 | 290 |  | CB-41 |  | 10
2024-04-17 | 1129 |  | 59481 | A | DONE | 2 | S-M |  | DANE CO. AIRPORT 6210011 |  | 2024-04-18 | Z | 2024-04-08 | 40 | 0 | 0 |  | 0 | 130 |  | RFI-362 |  | 10
2024-04-15 | 1279 |  | 79618 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 | birdscreen | 2024-04-17 | Z | 2024-04-10 | 20 | 0 | 0 |  | 0 | 40 |  | Relief fan |  | 7
2024-04-16 | 1280 | sp | 79619 | A | DONE | 3 | S |  | EGENESIS PH2 6230026 |  | 2024-04-17 | Z | 2024-04-12 | 40 | 20 | 0 |  | 0 | 60 |  | Soft wall lab tie ins |  | 5
2024-04-17 | 1578 |  | 62377 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 |  | 2024-04-23 | Z | 2024-04-16 | 40 | 0 | 0 |  | 0 | 40 |  | Plenum angle |  | 7
2024-04-15 | 2559 |  | 62526 | A | DONE | 2 | S |  | EXACT QC 2230051 |  | 2024-04-16 | Z | 2024-04-12 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 4
2024-04-17 | 154 | bth | 62427 | A | DONE | 5 | S | pt alum | HEATH SERV 6230004 |  | 2024-04-18 | Z | 2024-04-16 | 50 | 70 | 0 |  | 10 | 70 |  | RM 163 |  | 2
2024-04-15 | 2277 |  | 69306 | A | DONE | 6 | S-M |  | HERITAGE 6220024 |  | 2024-04-19 | Z | 2024-04-15 | 50 | 0 | 100 | F | 0 | 180 |  | Elevator EA |  | 4
2024-04-16 | 2278 |  | 69307 | A | DONE | 4 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-04-19 | Z | 2024-04-15 | 100 | 0 | 0 |  | 50 | 160 |  | Kitchen tie-in |  | 4
2024-04-17 | 3729 |  | 67663 | A | DONE | 2 | S |  | KOHL CENTER 6210034 |  | 2024-04-17 | Z | 2024-04-17 | 20 | 0 | 0 |  | 0 | 50 |  | FLAT STOCK |  | 0.5
2024-04-17 | 2900 | bth | 72905 | A | DONE | 13 | S-M |  | LABCORP SAMPLE 6240011 |  | 2024-04-22 | Z | 2024-04-12 | 130 | 180 | 0 |  | 0 | 350 |  | HPSA |  | 10
2024-04-19 | 2901 | bth | 72906 - 72907 | A | DONE | 23 | S-M |  | LABCORP SAMPLE 6240011 |  | 2024-04-22 | Z | 2024-04-12 | 170 | 320 | 70 | F | 0 | 500 |  | VAV-PH104 A/B |  | 10
2024-04-18 | 2902 | bth | 72908 | A | DONE | 14 | S-M |  | LABCORP SAMPLE 6240011 |  | 2024-04-22 | Z | 2024-04-12 | 60 | 240 | 30 | F | 0 | 290 |  | VAV-PH110 |  | 10
2024-04-17 | 2903 |  | 72909 | A | DONE | 3 | S |  | LABCORP SAMPLE 6240011 | 1" liner | 2024-04-22 | Z | 2024-04-12 | 70 | 0 | 0 |  | 60 | 80 |  | TA |  | 10
2024-04-17 | 2904 |  | 72910 - 72911 | A | DONE | 7 | S-M |  | LABCORP SAMPLE 6240011 |  | 2024-04-22 | Z | 2024-04-12 | 40 | 0 | 130 | F | 0 | 160 |  | In wall EA |  | 10
2024-04-15 | 298 |  | 70533 | A | DONE | 2 | S |  | MULLET ICE ARENA 10054815 | 1" liner | 2024-04-15 | Z | 2024-04-15 | 20 | 0 | 0 |  | 20 | 50 |  | EC |  | 0
2024-04-17 | 299 |  | 78724 - 78725 | A | DONE | 35 | M |  | MULLET ICE ARENA 10054815 | 1" liner , 1" DW | 2024-04-17 | Z | 2024-04-15 | 550 | 0 | 310 | F | 660 | 1130 |  | DH1 SA |  | 2
2024-04-15 | 2625 |  | 79454 | A | DONE | 2 | S |  | OLIV 6210030 | flex | 2024-04-15 | Z | 2024-04-12 | 20 | 0 | 0 |  | 0 | 20 |  | Gen EA |  | 3
2024-04-19 | 294 | sp | 70294 | A | DONE | 2 | S-M |  | PLACON 10054853 |  | 2024-04-22 | Z | 2024-04-10 | 0 | 40 | 0 |  | 0 | 50 |  | Low loss stack |  | 12
2024-04-17 | 4396 | sp | 62702 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-04-22 | Z | 2024-04-16 | 10 | 0 | 0 |  | 0 | 20 |  | MISC |  | 6
2024-04-15 | 1983 |  | 62898 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 |  | 2024-04-17 | Z | 2024-04-12 | 50 | 0 | 0 |  | 0 | 60 |  | TA |  | 5
2024-04-18 | 1984 | w | 62941 | A | DONE | 3 | S |  | PROMEGA RDC 6210033 | 1" liner | 2024-04-24 | Z | 2024-04-16 | 20 | 0 | 0 |  | 10 | 30 |  | Curb Cap |  | 8
2024-04-16 | 4540 |  | 72378 | A | DONE | 10 | S-M |  | RAMC 6230009 |  | 2024-04-19 | Z | 2024-04-05 | 230 | 0 | 0 |  | 0 | 340 |  | 1st flashing |  | 14
2024-04-15 | 4743 | w | 78956 | A | DONE | 4 | S |  | ROCK CO. JAIL 6220018 |  | 2024-04-18 | Z | 2024-04-05 | 100 | 0 | 0 |  | 0 | 310 |  | Curb cap |  | 13
2024-04-19 | 292 |  | 70293 | A | DONE | 2 | S |  | SIERRA SPACE 10054754 |  | 2024-04-24 | Z | 2024-04-10 | 20 | 0 | 0 |  | 0 | 20 |  | Furnace |  | 14
2024-04-17 | 4662 |  | 64022 - 640023 | A | DONE | 9 | S-M |  | ST.BERNARD 2230056 |  | 2024-04-22 | Z | 2024-04-10 | 90 | 0 | 130 | F | 0 | 220 |  | Basement RA Shaft |  | 12
2024-04-17 | 4663 |  | 64024 - 64025 | A | DONE | 7 | S-M |  | ST.BERNARD 2230056 |  | 2024-04-22 | Z | 2024-04-10 | 110 | 0 | 60 | F | 0 | 150 |  | Basement RA Tie-ins |  | 12
2024-04-17 | 4664 |  | 64029 - 64030 | A | DONE | 7 | S-M |  | ST.BERNARD 2230056 | 1" liner | 2024-04-22 | Z | 2024-04-10 | 80 | 0 | 90 | F | 130 | 160 |  | F-7 SA |  | 12
2024-04-17 | 4665 |  | 70325 | A | DONE | 4 | S-M |  | ST.BERNARD 2230056 | 1" liner | 2024-04-22 | Z | 2024-04-10 | 60 | 0 | 40 | F | 80 | 90 |  | Basement RA |  | 12
2024-04-17 | 4666 |  | 70326 | A | DONE | 5 | S-M |  | ST.BERNARD 2230056 |  | 2024-04-22 | Z | 2024-04-10 | 60 | 0 | 50 | F | 0 | 100 |  | Basement RA |  | 12
2024-04-17 | 241 |  | 70089 | A | DONE | 6 | S |  | UPLAND HILLS 2240008 |  | 2024-04-22 | Z | 2024-03-12 | 110 | 0 | 30 | F | 0 | 200 |  | 1305 Inlet |  | 41 |  | 2024-04-29
2024-04-17 | 242 |  | 70090 - 70092 | A | DONE | 12 | S-M |  | UPLAND HILLS 2240008 |  | 2024-04-22 | Z | 2024-03-12 | 220 | 0 | 80 | F | 0 | 280 |  | 1305 LPSA |  | 41 |  | 2024-05-06
2024-04-19 | 248 | sp | 79603 | A | DONE | 4 | S |  | UPLAND HILLS 2240008 |  | 2024-04-22 | Z | 2024-03-13 | 20 | 80 | 0 |  | 0 | 100 |  | RAT 1307 |  | 40 |  | 2024-05-13
2024-04-19 | 249 | bth | 79604 - 79605 | A | DONE | 6 | S-M |  | UPLAND HILLS 2240008 |  | 2024-04-22 | Z | 2024-03-13 | 70 | 30 | 50 | F | 0 | 170 |  | AT 1307 MPSA |  | 40 |  | 2024-05-13
2024-04-19 | 3207 | w | 72421 | A | DONE | 2 | S | ss | UW VET MED 2230012 |  | 2024-04-22 | Z | 2024-04-16 | 20 | 0 | 0 |  | 0 | 20 |  | OFFSET |  | 6
2024-04-18 | 3206 |  | 72420 | A | DONE | 2 | S |  | UW VET MED 2230013 |  | 2024-04-22 | Z | 2024-04-16 | 30 | 0 | 0 |  | 0 | 40 |  | Testing |  | 6
2024-04-18 | 3208 |  | 72422 | A | DONE | 2 | S |  | UW VET MED 6210014 |  | 2024-04-22 | Z | 2024-04-18 | 20 | 0 | 0 |  | 0 | 20 |  | 3RD |  | 4
2024-04-18 | 4833 | bth | L2Z1-SAMP-7 | A | DONE | 30 | M-L |  | UWRF 6230010 |  | 2024-04-24 | Z | 2024-03-13 | 540 | 20 | 190 | F | 0 | 1220 |  |  | L-2 Zone 1A | 42
2024-04-17 | 3203 |  | 72416 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-04-22 | Z | 2024-04-12 | 20 | 0 | 0 |  | 0 | 20 |  | AHU caps |  | 10
2024-04-15 | 3204 |  | 72417 - 72418 | A | DONE | 2 | S | neal | UW-VET MED 6210014 |  | 2024-04-22 | Z | 2024-04-12 | 20 | 0 | 0 |  | 0 | 30 |  | AHU caps , Arena |  | 10
2024-04-15 | 3205 |  | 72419 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-04-22 | Z | 2024-04-12 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor A3 |  | 10
2024-04-18 | 2280 |  | 68998 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 |  | 2024-04-19 | Z | 2024-04-18 | 0 | 0 | 20 | F |  | 20 |  | ANGLES |  | 1
2024-04-19 | 297 | bth | 70111 | A | DONE | 2 | S |  | WICELL 2230040 | paint | 2024-04-22 | Z | 2024-04-15 | 20 | 20 | 0 |  | 20 | 30 |  | Misc |  | 7
[6 empty] | 701 | [13 empty] | 20890 |  |  |  | 8660 | #DIV/0!
WEEK OF 4-22-2024
2024-04-23 | 1737 |  | 68021 - 68022 | A | DONE | 18 | S-M |  | BLACKHAWK BTC 6230025 | 1" liner | 2024-04-25 | Z | 2024-04-08 | 270 | 0 | 0 |  | 180 | 590 |  | RTU-2/3 Drops |  | 17
2024-04-22 | 1738 |  | 68023 | A | DONE | 3 | S-M |  | BLACKHAWK BTC 6230025 | 1" liner | 2024-04-25 | Z | 2024-04-10 | 40 | 0 | 0 |  | 40 | 60 |  | RTU-4 drop |  | 15
2024-04-22 | 1739 |  | 68024 | A | DONE | 11 | S-M | neal | BLACKHAWK BTC 6230025 | 1" liner | 2024-04-25 | Z | 2024-04-11 | 100 | 0 | 60 |  | 120 | 200 |  | Welding |  | 14
2024-04-24 | 1740 | bth | 68025 - 68026 | A | DONE | 36 | M |  | BLACKHAWK BTC 6230025 | 1" liner , 1" s. accu | 2024-04-25 | Z | 2024-04-12 | 140 | 40 | 310 |  | 410 | 690 |  | Welding , Menu Lab |  | 13
2024-04-23 | 1741 |  | 68027 | A | DONE | 3 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-04-24 | Z | 2024-04-17 | 30 | 0 | 0 |  | 0 | 80 |  | OVAL HANGERS |  | 7
2024-04-23 | 782 | bth | L-2B-SALP-037 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-04-24 | Z | 2024-04-17 | 80 | 10 | 0 |  | 40 | 100 |  |  |  | 7
2024-04-24 | 784 |  | 59485 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-04-22 | 20 | 0 | 0 |  | 0 | 20 |  | 3RD FL TEAR DROP |  | 7
2024-04-25 | 787 |  | 59486 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-04-23 | 20 | 0 | 0 |  | 0 | 40 |  | 3RD FL FD TAP |  | 6
2024-04-26 | 3515 | bth | L3-A-EAMP-028 | A | DONE | 39 | M-L | pt.neal | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 550 | 90 | 340 |  | 0 | 1570 |  |  |  | 41
2024-04-26 | 3516 | bth | L3-A-EAMP-033 | A | DONE | 13 | S-M | neal | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 140 | 20 | 170 |  | 0 | 380 |  |  |  | 41
2024-04-26 | 3517 | bth | L3-A-EAMP-034 | A | DONE | 11 | S-M | pt.neal | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 40 | 20 | 200 |  | 0 | 310 |  |  |  | 41
2024-04-26 | 3518 | bth | L3-A-EAMP-035 | A | DONE | 11 | S-M | pt.neal | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 160 | 10 | 110 |  | 0 | 360 |  |  |  | 41
2024-04-26 | 3519 | bth | L3-A-EAMP-036 | A | DONE | 6 | S | neal | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 10 | 20 | 120 |  | 0 | 170 |  |  |  | 41
2024-04-25 | 3520 | bth | L3-A-EAMP-037 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 10 | 10 | 100 |  | 0 | 150 |  |  |  | 41
2024-04-25 | 3521 | bth | L3-A-EAMP-040 | A | DONE | 10 | S | neal | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 20 | 40 | 180 |  | 0 | 280 |  |  |  | 41
2024-04-26 | 3522 | bth | L3-A-EAMP-041 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 10 | 20 | 120 |  | 0 | 170 |  |  |  | 41
2024-04-26 | 3523 | bth | L3-A-EAMP-042 | A | DONE | 5 | S | pt.neal | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 30 | 20 | 60 |  | 0 | 130 |  |  |  | 41
2024-04-25 | 3524 |  | L3-A-SAMP-011 | A | DONE | 17 | M |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 210 | 0 | 230 |  | 0 | 760 |  |  |  | 41
2024-04-26 | 3525 | bth | L3-A-SAMP-012 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 110 | 10 | 90 |  | 0 | 250 |  |  |  | 41
2024-04-25 | 3526 | bth | L3-A-SAMP-013 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 20 | 20 | 150 |  | 0 | 220 |  |  |  | 41
2024-04-26 | 3527 | bth | L3-A-SAMP-014 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 20 | 20 | 130 |  | 0 | 200 |  |  |  | 41
2024-04-26 | 3528 | bth | L3-A-SAMP-015 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 100 | 40 | 120 |  | 0 | 290 |  |  |  | 41
2024-04-26 | 3529 | bth | L3-A-SAMP-016 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 90 | 30 | 70 |  | 0 | 230 |  |  |  | 41
2024-04-26 | 3530 | sp | L3-A-SAMP-017 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 41
2024-04-26 | 3531 | bth | L3-A-SAMP-018 | A | DONE | 23 | M |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 480 | 40 | 60 |  | 0 | 960 |  |  |  | 41
2024-04-25 | 3532 | bth | L3-A-SAMP-019 | A | DONE | 18 | M |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 230 | 20 | 200 |  | 0 | 830 |  |  |  | 41
2024-04-26 | 3533 |  | L3-A-SAMP-020 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 180 | 0 | 150 |  | 0 | 390 |  |  |  | 41
2024-04-26 | 3534 | bth | L3-A-SAMP-021 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-04-29 | Z | 2024-03-19 | 230 | 50 | 90 |  | 0 | 420 |  |  |  | 41
2024-04-23 | 3585 | bth | L4-B-EAMP-002 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 90 | 30 | 120 | F | 0 | 370 |  |  |  | 22
2024-04-23 | 3586 | bth | L4-B-EAMP-003 | A | DONE | 14 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 220 | 70 | 80 | F | 0 | 560 |  |  |  | 22
2024-04-23 | 3587 | bth | L4-B-EAMP-004 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 160 | 10 | 40 | F | 0 | 340 |  |  |  | 22
2024-04-23 | 3588 | bth | L4-B-EAMP-005 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 70 | 10 | 120 | F | 0 | 240 |  |  |  | 22
2024-04-23 | 3589 | bth | L4-B-EAMP-006 | A | DONE | 9 | S-M | pt.neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 50 | 20 | 170 | F | 0 | 280 |  |  |  | 22
2024-04-23 | 3591 | bth | L4-B-EAMP-008 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 100 | 20 | 30 |  | 0 | 160 |  |  |  | 22
2024-04-23 | 3592 | bth | L4-B-EAMP-009 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 40 | 10 | 140 |  | 0 | 220 |  |  |  | 22
2024-04-23 | 3593 | bth | L4-B-EAMP-010 | A | DONE | 11 | S-M | neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 80 | 60 | 120 | F | 0 | 300 |  |  |  | 22
2024-04-23 | 3594 | bth | L4-B-EAMP-024 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 40 | 50 | 30 | F | 0 | 130 |  |  |  | 22
2024-04-23 | 3596 | bth | L4-B-SAMP-001 | A | DONE | 19 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 380 | 10 | 180 | F | 0 | 1020 |  |  |  | 22
2024-04-23 | 3598 | bth | L4-B-SAMP-003 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 110 | 30 | 90 | F | 0 | 290 |  |  |  | 22
2024-04-23 | 3600 | bth | L4-B-SAMP-005 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 220 | 20 | 40 | F | 0 | 360 |  |  |  | 22
2024-04-23 | 3601 | bth | L4-B-SAMP-006 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 110 | 20 | 0 |  | 0 | 140 |  |  |  | 22
2024-04-23 | 3602 | bth | L4-B-SAMP-007 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 80 | 50 | 120 | F | 0 | 280 |  |  |  | 22
2024-04-23 | 3603 | sp | L4-B-SAMP-008 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 10 | 30 | 0 |  | 0 | 30 |  |  |  | 22
2024-04-23 | 3604 | bth | L4-B-SAMP-009 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 100 | 30 | 90 | F | 0 | 250 |  |  |  | 22
2024-04-23 | 3605 | bth | L4-B-SAMP-010 | A | DONE | 17 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 220 | 30 | 170 | F | 0 | 690 |  |  |  | 22
2024-04-23 | 3606 | bth | L4-B-SAMP-011 | A | DONE | 17 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 210 | 30 | 170 | F | 0 | 600 |  |  |  | 22
2024-04-23 | 3607 | bth | L4-B-SAMP-012 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 50 | 40 | 140 | F | 0 | 260 |  |  |  | 22
2024-04-22 | 3608 |  | L4-B-SAMP-103 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-04-23 | Z | 2024-04-01 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 22
2024-04-24 | 153 | w | 79751 | A | DONE | 16 | S-M |  | COMPASS HP 4230088 | 1" liner | 2024-04-26 | Z | 2024-04-16 | 220 | 0 | 0 |  | 180 | 360 |  | Curb Cap |  | 10
2024-04-26 | 157 |  | 79753 | A | DONE | 2 | S |  | COMPASS HP 4230088 |  | 2024-04-29 | Z | 2024-04-22 | 30 | 0 | 0 |  | 0 | 30 |  | OFFSET |  | 7
2024-04-26 | 1579 |  | 62378 | A | DONE | 2 | S | ss | EMBASSY 6220012 | T & M | 2024-04-30 | Z | 2024-04-22 | 30 | 0 | 0 |  | 0 | 30 |  | AIR CURTAIN COVERS |  | 8
2024-04-24 | 4605 |  | 69412 | A | DONE | 5 | S |  | HARMONIC 6240010 |  | 2024-04-26 | Z | 2024-04-23 | 110 | 0 | 0 |  | 0 | 130 |  | DT Vestibule |  | 3
2024-04-26 | 4606 |  | call in | A | DONE | 2 | S |  | HARMONICS 6240010 |  | 2024-04-29 | Z | 2024-04-26 | 20 | 0 | 0 |  | 0 | 20 |  | VD & Pressed elbow |  | 3
2024-04-23 | 159 |  | 66702 | A | DONE | 2 | S |  | HEALTH SERV 6230004 |  | 2024-04-24 | Z | 2024-04-22 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 2
2024-04-24 | 700 |  | 71507 - 71508 | A | DONE | 17 | M |  | HILLDALE 6240003 |  | 2024-04-29 | Z | 2024-04-08 | 370 | 0 | 60 |  | 0 | 640 |  | RTU drops |  | 21
2024-04-24 | 702 |  | 71510 , 71512 | A | DONE | 16 | M |  | HILLDALE 6240003 |  | 2024-04-29 | Z | 2024-04-08 | 410 | 0 | 0 |  | 0 | 520 |  | RTU drops |  | 21
2024-04-25 | 703 | w | 71513 | A | DONE | 5 | S |  | HILLDALE 6240003 |  | 2024-04-29 | Z | 2024-04-08 | 110 | 0 | 0 |  | 0 | 190 |  | Curb cap |  | 21
2024-04-25 | 704 | w | 66082 | A | DONE | 2 | S |  | HILLDALE 6240003 |  | 2024-04-29 | Z | 2024-04-08 | 40 | 0 | 0 |  | 0 | 70 |  | Future EA |  | 21
2024-04-24 | 710 |  | 71510 | A | DONE | 9 | S-M |  | HILLDALE 6240003 | flex | 2024-04-29 | Z | 2024-04-09 | 230 | 0 | 0 |  | 0 | 340 |  | RTU Drops |  | 20
2024-04-26 | 711 |  | 71507 - 71508 | A | DONE | 15 | M |  | HILLDALE 6240003 | flex | 2024-04-29 | Z | 2024-04-09 | 360 | 0 | 0 |  | 0 | 500 |  | RTU Drops |  | 20
2024-04-26 | 712 |  | 71532 | A | DONE | 4 | S-M |  | HILLDALE 6240003 | flex | 2024-04-29 | Z | 2024-04-09 | 100 | 0 | 0 |  | 0 | 120 |  | RTU-4 Drop |  | 20
2024-04-23 | 2819 |  | 78605 | A | DONE | 6 | S-M | alum | JANESVILLE ESSR 6230011 |  | 2024-04-25 | Z | 2024-04-11 | 150 | 0 | 0 |  | 0 | 110 |  | Pool EA |  | 14
2024-04-24 | 2820 | w | 78566 - 78567 | A | DONE | 12 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-04-25 | Z | 2024-04-11 | 290 | 0 | 0 |  | 0 | 640 |  | Welded curb adapters |  | 14
2024-04-22 | 3730 |  | 67665 | A | DONE | 2 | S |  | KOHL CENTER 6210034 |  | 2024-04-25 | Z | 2024-04-19 | 20 | 0 | 0 |  | 0 | 20 |  | MEZZ |  | 6
2024-04-24 | 3731 |  | 67660 | A | DONE | 2 | S |  | KOHL CENTER 6210034 |  | 2024-04-25 | Z | 2024-04-24 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 1
2024-04-25 | 2905 | bth | 72912-17 | A | DONE | 34 | M |  | LABCORP SAMPLE 6240011 |  | 2024-04-29 | Z | 2024-04-18 | 400 | 0 | 450 |  | 0 | 860 |  |  |  | 11
2024-04-24 | 3834 |  | 67519-22 | A | DONE | 51 | M |  | MEDOTA FOOD 6220027 |  | 2024-04-25 | Z | 2024-04-18 | 550 | 0 | 730 |  | 0 | 1860 |  |  |  | 7
2024-04-23 | 3832 |  | 67517-18 | A | DONE | 25 | S-M | pt alum | MENDOTA FOOD 6220027 |  | 2024-04-25 | Z | 2024-04-16 | 330 | 0 | 310 |  | 0 | 830 |  | 1st FL / Conf SA |  | 9
2024-04-23 | 3833 | w | 67471 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 |  | 2024-04-25 | Z | 2024-04-18 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-04-23 | 3835 |  | 67523 | A | DONE | 7 | S |  | MENDOTA FOOD 6220027 |  | 2024-04-25 | Z | 2024-04-19 | 40 | 0 | 120 |  | 0 | 190 |  | 1ST FL - EA |  | 6
2024-04-24 | 3836 |  | 67524 | A | DONE | 7 | S-M |  | MENDOTA FOOD 6220027 |  | 2024-04-25 | Z | 2024-04-24 | 160 | 0 | 0 |  | 0 | 270 |  | AHU-Blank Offs |  | 1
2024-04-24 | 160 |  | 78726 | A | DONE | 8 | S-M |  | MULLET ICE ARENA 10054815 | 1"liner | 2024-04-26 | Z | 2024-04-23 | 150 | 0 | 0 |  | 50 | 200 |  | RELIEF DAMPER |  | 3
2024-04-22 | 3252 |  | 62525 | A | DONE | 3 | S-M |  | NIC 6240004 | VD's | 2024-04-30 | Z | 2024-04-05 | 60 | 0 | 0 |  | 0 | 100 |  | Bypass |  | 25
2024-04-26 | 4398 |  | 62943 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-01 | Z | 2024-04-25 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 7
2024-04-23 | 1985 | sp | 62942 | A | DONE | 2 | S |  | PROMEGA RDC 6210033 |  | 2024-04-24 | Z | 2024-04-16 | 10 | 10 | 0 |  | 0 | 20 |  | EA |  | 8
2024-04-23 | 560 | bth | LL-RA-01 | A | DONE | 34 | M-L |  | RAMC 6230009 | oval | 2024-04-19 | Z | 2024-02-27 | 370 | 320 | 150 | F | 0 | 1290 |  |  | Semi 5 | 52
2024-04-23 | 561 | sp | LL-RA-02 | A | DONE | 15 | S-M |  | RAMC 6230009 |  | 2024-04-19 | Z | 2024-02-27 | 140 | 230 | 0 |  | 0 | 440 |  |  | Semi 5 | 52
2024-04-23 | 562 | sp | LL-RA-03 | A | DONE | 12 | S-M |  | RAMC 6230009 |  | 2024-04-19 | Z | 2024-02-27 | 40 | 250 | 0 |  | 0 | 340 |  |  | Semi 5 | 52
2024-04-23 | 563 | bth | LL-RA-04 | A | DONE | 34 | M-L |  | RAMC 6230009 | oval | 2024-04-19 | Z | 2024-02-27 | 210 | 440 | 180 | F | 0 | 1370 |  |  | Semi 5 | 52
2024-04-23 | 564 | sp | LL-RA-05 | A | DONE | 14 | S-M |  | RAMC 6230009 |  | 2024-04-19 | Z | 2024-02-27 | 60 | 280 | 0 |  | 0 | 400 |  |  | Semi 5 | 52
2024-04-23 | 565 | sp | LL-RA-06 | A | DONE | 34 | M-L |  | RAMC 6230009 | oval | 2024-04-19 | Z | 2024-02-27 | 130 | 720 | 0 |  | 0 | 1270 |  |  | Semi 5 | 52
2024-04-23 | 566 | sp | LL-RA-07 | A | DONE | 20 | M |  | RAMC 6230009 | oval | 2024-04-19 | Z | 2024-02-27 | 100 | 380 | 0 |  | 0 | 560 |  |  | Semi 5 | 52
2024-04-23 | 4542 |  | 72380 | A | DONE | 7 | S-M |  | RAMC 6230009 | oval , accuflange | 2024-04-19 | Z | 2024-04-11 | 150 | 20 | 0 |  | 0 | 290 |  | SA/RA main |  | 8
2024-04-23 | 4543 | sp | 72381 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-04-29 | Z | 2024-04-17 | 0 | 20 | 0 |  | 0 | 20 |  | 1st SAMP-7 |  | 12
2024-04-24 | 4744 |  | 61156-57 | A | DONE | 8 | S-M |  | ROCK CO. JAIL 6220018 |  | 2024-04-24 | Z | 2024-04-17 | 120 | 0 | 30 |  | 40 | 210 |  | RETURN DROPS |  | 7
2024-04-22 | 4745 | w | 78873-74 | A | DONE | 4 | S | pt ss | ROCK CO. JAIL 6220018 | 1.5 " DB | 2024-04-24 | Z | 2024-04-17 | 80 | 0 | 0 |  | 20 | 150 |  | Kitchen / Curb Adapt |  | 7
2024-04-22 | 4746 |  | 78875-77 | A | DONE | 7 | S-M |  | ROCK CO. JAIL 6220018 | paint | 2024-04-24 | Z | 2024-04-17 | 100 | 0 | 50 |  | 10 | 190 |  | BOILER RM / CURB |  | 7
2024-04-26 | 158 |  | 79754 | A | DONE | 2 | S |  | SIERRA SPACE 10054773 |  | 2024-04-29 | Z | 2024-04-22 | 40 | 0 | 0 |  | 0 | 40 |  | FURNACE |  | 7
2024-04-26 | 4677 | sp | email | A | DONE | 2 | S |  | ST BERNARD 6230023 |  | 2024-05-01 | Z | 2024-04-17 | 20 | 0 | 0 |  | 0 | 20 |  | 12"rd-90s |  | 14
2024-04-26 | 4672 |  | Pre-fab hangers | A | DONE | 2 | S |  | ST.BERNARD 2220037 |  | 2024-04-29 | Z | 2024-04-11 | 20 | 0 | 0 |  | 0 | 30 |  | Hangers |  | 18
2024-04-24 | 4667 | sp | 70304 | A | DONE | 6 | S-M |  | ST.BERNARD 2230056 |  | 2024-04-25 | Z | 2024-04-11 | 50 | 100 | 0 |  | 0 | 130 |  | Room 118 SA |  | 14
2024-04-24 | 4668 | bth | 70320 - 70321 | A | DONE | 11 | S-M |  | ST.BERNARD 2230056 |  | 2024-04-25 | Z | 2024-04-11 | 50 | 240 | 0 |  | 0 | 260 |  | 114 / 117 SA |  | 14
2024-04-24 | 4669 | bth | 70322 - 70324 | A | DONE | 13 | S-M |  | ST.BERNARD 2230056 |  | 2024-04-25 | Z | 2024-04-11 | 170 | 60 | 80 |  | 0 | 280 |  | Rm 103 , 112 , 113 |  | 14
2024-04-23 | 4670 |  | 64026 - 64027 | A | DONE | 15 | S-M |  | ST.BERNARD 2230056 |  | 2024-04-25 | Z | 2024-04-11 | 130 | 0 | 230 |  | 0 | 350 |  | 1st floor RA |  | 14
2024-04-24 | 4671 | sp | 64028 | A | DONE | 3 | S-M |  | ST.BERNARD 2230056 |  | 2024-04-25 | Z | 2024-04-11 | 20 | 50 | 0 |  | 0 | 60 |  | 1nd floor RA |  | 14
2024-04-26 | 4661 | sp | 71350 | A | DONE | 3 | S |  | ST.BERNARD 6230023 |  | 2024-04-29 | Z | 2024-04-09 | 0 | 80 | 0 | F | 0 | 70 |  | VAV-2,3 |  | 20
2024-04-26 | 296 | w | 70297 - 70298 | A | DONE | 6 | S-M | ss | THERMO FISHER 10054818 |  | 2024-04-29 | Z | 2024-04-15 | 160 | 0 | 0 |  | 0 | 380 |  | Switch gear cap |  | 14
2024-04-26 | 152 |  | 70300 | A | DONE | 2 | S |  | THERMO FISHER 10054820 |  | 2024-04-29 | Z | 2024-04-15 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 14
2024-04-26 | 3211 | w | 72424 | A | DONE | 2 | S | ss | UW VET MED 2230012 |  | 2024-04-29 | Z | 2024-04-23 | 20 | 0 | 0 |  | 0 | 20 |  | BSL-3-3969B |  | 6
2024-04-26 | 3213 |  | 72427 | A | DONE | 2 | S-M |  | UW VET MED 2230013 |  | 2024-04-29 | Z | 2024-04-24 | 40 | 0 | 0 |  | 0 | 90 |  | 3RD FL ANGLES |  | 5
2024-04-26 | 3209 |  | 72423 | A | DONE | 2 | S | alum | UW VET MED 6210014 |  | 2024-04-29 | Z | 2024-04-23 | 20 | 0 | 0 |  | 0 | 20 |  | Wall Sleeve |  | 6
2024-04-23 | 4800 | bth | L2Z1-EAMP-1 | A | DONE | 49 | L | pt.neal | UWRF 6230010 |  | 2024-04-24 | Z | 2024-03-12 | 430 | 50 | 740 |  | 0 | 2010 |  |  | L-2 Zone 1A | 43
2024-04-23 | 4801 | bth | L2Z1-EAMP-2 | A | DONE | 13 | S-M |  | UWRF 6230010 |  | 2024-04-24 | Z | 2024-03-12 | 130 | 50 | 150 |  | 0 | 490 |  |  | L-2 Zone 1A | 43
2024-04-23 | 4802 | bth | L2Z1-EAMP-3 | A | DONE | 26 | M-L |  | UWRF 6230010 |  | 2024-04-24 | Z | 2024-03-12 | 190 | 40 | 420 |  | 0 | 1050 |  |  | L-2 Zone 1A | 43
2024-04-23 | 4803 | bth | L2Z1-EAMP-4 | A | DONE | 15 | M |  | UWRF 6230010 |  | 2024-04-24 | Z | 2024-03-12 | 220 | 30 | 130 |  | 0 | 520 |  |  | L-2 Zone 1A | 43 |  |  | 2023-10-05
2024-04-23 | 4804 | bth | L2Z1-EAMP-5 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-04-24 | Z | 2024-03-12 | 170 | 30 | 0 |  | 0 | 250 |  |  | L-2 Zone 1A | 43 |  |  | 2023-10-05
2024-04-23 | 4834 | bth | L2Z1-SAMP-8 | A | DONE | 17 | M |  | UWRF 6230010 |  | 2024-04-24 | Z | 2024-03-13 | 230 | 50 | 140 | F | 0 | 830 |  |  | L-2 Zone 1A | 42
2024-04-23 | 4835 | bth | L2Z1-SAMP-9 | A | DONE | 15 | M |  | UWRF 6230010 |  | 2024-04-24 | Z | 2024-03-13 | 80 | 50 | 240 | F | 0 | 560 |  |  | L-2 Zone 1A | 42
2024-04-23 | 4931 |  | 73395 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-04-24 | Z | 2024-04-09 | 190 | 0 | 0 | F | 0 | 220 |  | L-2 Hangers |  | 15
2024-04-24 | 2279 |  | 69308-09 | A | DONE | 17 | M | flex | WCSD HERITAGE 6220024 |  | 2024-04-26 | Z | 2024-04-18 | 410 | 0 | 0 |  | 0 | 630 |  | DOAS-3 |  | 8
2024-04-22 | 2281 |  | 69000 | A | DONE | 3 | S |  | WCSD HERITAGE 6220024 |  | 2024-04-23 | Z | 2024-04-18 | 30 | 0 | 0 |  | 0 | 30 |  | STEM SLEEVES |  | 5
2024-04-24 | 2283 |  | 69251 | A | DONE | 12 | S |  | WCSD HERITAGE 6220024 |  | 2024-04-26 | Z | 2024-04-19 | 290 | 0 | 0 |  | 0 | 350 |  |  |  | 7
2024-04-24 | 2284 |  | 69310-12 | A | DONE | 6 | S-M |  | WCSD HERITAGE 6220024 |  | 2024-04-26 | Z | 2024-04-19 | 130 | 0 | 10 |  | 10 | 160 |  | A-CEILING TIE IN |  | 7
2024-04-24 | 2286 |  | 69254 | A | DONE | 2 | S | neal | WCSD HERITAGE 6220024 |  | 2024-04-26 | Z | 2024-04-23 | 20 | 0 | 0 |  | 0 | 30 |  | Flashing |  | 3
2024-04-24 | 161 |  | 70114 | A | DONE | 2 | S |  | WICELL 2230040 | 1/2"liner | 2024-04-25 | Z | 2024-04-23 | 30 | 0 | 0 |  | 30 | 30 |  | TA |  | 2
2024-04-25 | 150 | sp | 70112 | A | DONE | 17 | M |  | WICELL 2230040 |  | 2024-04-29 | Z | 2024-04-15 | 90 | 320 | 0 |  | 0 | 470 |  | SA |  | 14
2024-04-24 | 151 |  | 70113 | A | DONE | 3 | S |  | WICELL 2230040 | 1/2" liner | 2024-04-29 | Z | 2024-04-15 | 40 | 0 | 0 |  | 30 | 40 |  | TA |  | 14
[6 empty] | 1246 | [13 empty] | 40650 |  |  |  | 8110 | 19.95%
WEEK OF 4-29-2024
2024-05-01 | 166 | sp | 70224 | A | DONE | 3 | S |  | 8020 10055253 |  | 2024-05-03 | Z | 2024-04-30 | 20 | 50 | 0 |  | 0 | 50 |  | Misc |  | 3
2024-05-01 | 167 | w | 70604 - 70605 | A | DONE | 2 | S |  | ACADIA 8230013 |  | 2024-05-03 | Z | 2024-04-30 | 20 | 0 | 0 |  | 0 | 60 |  | Pans |  | 3
2024-05-01 | 1742 | sp | 68028 | A | DONE | 8 | S | neal | BLACKHAWK BTC 6230025 | 1" s. accu | 2024-05-02 | Z | 2024-04-19 | 30 | 80 | 0 |  | 80 | 120 |  | MEZZ LAB |  | 13
2024-04-30 | 1743 | sp | 68029 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 | 1" s. accu | 2024-05-02 | Z | 2024-04-23 | 20 | 0 | 0 |  | 10 | 20 |  | Manu Lab |  | 9
2024-04-29 | 1744 |  | 68031 | A | DONE | 2 | S |  | BLACKHAWK BTC 6230025 |  | 2024-05-02 | Z | 2024-04-25 | 20 | 0 | 0 |  | 0 | 50 |  |  |  | 8
2024-04-29 | 783 |  | 69902 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-05-02 | Z | 2024-04-18 | 130 | 0 | 0 |  | 0 | 230 |  |  |  | 14
2024-05-01 | 785 |  | 69860 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-05-06 | Z | 2024-04-22 | 30 | 0 | 0 |  | 0 | 70 |  | TEAR DROP |  | 14
2024-04-29 | 786 |  | 69861 | A | DONE | 2 | S |  | CDIS 6220028 | flex | 2024-05-02 | Z | 2024-04-22 | 30 | 0 | 0 |  | 0 | 50 |  | AHU-2-RETURN TIE IN |  | 10
2024-05-03 | 789 | sp | 59487 | A | DONE | 4 | S | neal | CDIS 6220028 |  | 2024-05-06 | Z | 2024-04-25 | 30 | 50 | 0 |  | 0 | 90 |  | 3RD FL-B |  | 11
2024-04-29 | 790 |  | SC-SAMP-005 | A | DONE | 30 | M-L |  | CDIS 6220028 |  | 2024-05-01 | Z | 2024-04-24 | 750 | 0 | 0 |  | 0 | 1660 |  |  |  | 7
2024-04-29 | 791 |  | SC-SAMP-008 | A | DONE | 17 | M |  | CDIS 6220028 |  | 2024-05-01 | Z | 2024-04-24 | 50 | 0 | 370 | F | 0 | 610 |  |  |  | 7
2024-05-04 | 793 |  | 69903 | A | DONE | 4 | S |  | CDIS 6220028 | 1' DW | 2024-05-07 | Z | 2024-04-29 | 80 | 0 | 0 |  | 20 | 70 |  | SAMP 001 1st floor |  | 8
2024-05-02 | 794 | sp | 59488 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-06 | Z | 2024-04-30 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd fl A-Section |  | 6
2024-05-04 | 828 |  | 61505 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-07 | Z | 2024-05-02 | 20 | 0 | 0 |  | 0 | 50 |  | BSMT-EAD-27 |  | 5
2024-05-04 | 829 |  | 69863 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-07 | Z | 2024-05-02 | 40 | 0 | 0 |  | 0 | 80 |  | End caps |  | 5
2024-05-03 | 3535 | bth | L3-A-SALP-051 | A | DONE | 9 | S-M | pt.neal | CDIS 6220028 | 1" s.accu ,1" liner | 2024-05-06 | Z | 2024-03-20 | 120 | 100 | 0 |  | 40 | 250 |  |  |  | 47
2024-05-03 | 3536 | bth | L3-A-SALP-052 | A | DONE | 17 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-05-06 | Z | 2024-03-20 | 320 | 80 | 20 | F | 90 | 490 |  |  |  | 47
2024-05-03 | 3537 | bth | L3-A-SALP-053 | A | DONE | 15 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-06 | Z | 2024-03-20 | 170 | 200 | 0 |  | 50 | 380 |  |  |  | 47
2024-05-03 | 3538 | bth | L3-A-SALP-054 | A | DONE | 10 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-06 | Z | 2024-03-20 | 110 | 130 | 0 |  | 40 | 250 |  |  |  | 47
2024-05-03 | 3539 | bth | L3-A-SALP-055 | A | DONE | 13 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-06 | Z | 2024-03-20 | 200 | 80 | 40 | F | 50 | 370 |  |  |  | 47
2024-05-03 | 3540 | bth | L3-A-SALP-059 | A | DONE | 16 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-05-06 | Z | 2024-03-20 | 240 | 50 | 100 | F | 50 | 440 |  |  |  | 47
2024-05-02 | 3541 |  | L3-A-SALP-060 | A | DONE | 9 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-05-06 | Z | 2024-03-20 | 200 | 0 | 20 | F | 50 | 250 |  |  |  | 47
2024-05-03 | 3542 | bth | L3-A-EALP-038 | A | DONE | 4 | S-M | pt.neal | CDIS 6220028 | 1" s.accu ,1" liner | 2024-05-06 | Z | 2024-03-20 | 70 | 30 | 0 |  | 20 | 120 |  |  |  | 47
2024-05-03 | 3543 | sp | L3-A-EALP-039 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-05-06 | Z | 2024-03-20 | 30 | 120 | 0 |  | 0 | 150 |  |  |  | 47
2024-05-03 | 3544 | bth | L3-A-EALP-043 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-06 | Z | 2024-03-20 | 50 | 50 | 20 | F | 0 | 130 |  |  |  | 47
2024-05-03 | 3545 | sp | L3-A-EALP-044 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-05-06 | Z | 2024-03-20 | 30 | 90 | 0 |  | 0 | 120 |  |  |  | 47
2024-05-03 | 3546 | bth | L3-A-EALP-045 | A | DONE | 8 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-06 | Z | 2024-03-20 | 100 | 100 | 0 |  | 30 | 230 |  |  |  | 47
2024-05-02 | 3547 | bth | L3-A-EALP-049 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-05-06 | Z | 2024-03-20 | 130 | 30 | 30 | F | 0 | 220 |  |  |  | 47
2024-05-03 | 3548 | sp | L3-A-EALP-050 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-05-06 | Z | 2024-03-20 | 40 | 130 | 0 |  | 0 | 170 |  |  |  | 47
2024-04-30 | 3610 | bth | L4-A-EAMP-034 | A | DONE | 20 | S-M | neal | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 270 | 0 | 220 | F | 0 | 810 |  |  |  | 37
2024-04-29 | 162 | bth | 79755 | A | DONE | 5 | S |  | COMPASS HP 4230088 |  | 2024-04-30 | Z | 2024-04-24 | 80 | 30 | 0 |  | 0 | 130 |  | CURB |  | 6
2024-04-29 | 1281 |  | 79657 | A | DONE | 2 | S |  | EGENESIS PH2 6230026 |  | 2024-04-30 | Z | 2024-04-26 | 20 | 0 | 0 |  | 0 | 20 |  | Temp RTU - 12"rd ec |  | 4
2024-05-01 | 2558 | sp | 56684 | A | DONE | 12 | S-M | alum | EXACT BIOSAFE 6230005 | angle rings | 2024-04-30 | Z | 2024-04-01 | 120 | 180 | 0 |  | 0 | 190 |  | EA roof vents |  | 29
2024-04-29 | 701 | w | 71509 , 71511 | SENT | OUT | n/a | M |  | HILLDALE 6240003 | 2" DB | 2024-04-29 | Z | 2024-04-08 | 0 | 0 | 0 |  | 0 | 0 |  | Curb adapters |  | 21
2024-05-01 | 713 |  | 71530 | A | DONE | 2 | S |  | HILLDALE 6240003 | 1/2" liner | 2024-05-06 | Z | 2024-04-10 | 30 | 0 | 0 |  | 20 | 30 |  | 2nd fl TA |  | 26
2024-05-03 | 714 | sp | 71531 | A | DONE | 4 | S-M |  | HILLDALE 6240003 |  | 2024-05-06 | Z | 2024-04-10 | 30 | 60 | 0 |  | 0 | 80 |  | Elevator SA |  | 26
2024-05-01 | 2822 |  | 78568-70 | A | DONE | 25 | S-M | alum | JANESVILLE ESSR 6230011 |  | 2024-05-02 | Z | 2024-04-19 | 450 | 0 | 180 | F | 0 | 630 |  | AHU-SA/EXH |  | 13
2024-05-04 | 2906 | bth | 72919 | A | DONE | 2 | S |  | LABCORP 6240011 |  | 2024-05-09 | Z | 2024-05-02 | 20 | 0 | 0 |  | 0 | 20 |  | LPSA |  | 7
2024-04-29 | 2158 |  | 68576 | A | DONE | 3 | S | alum | MEMORIAL HS 6210024 |  | 2024-04-30 | Z | 2024-04-16 | 60 | 0 | 0 |  | 0 | 50 |  | Pool SA |  | 14
2024-04-29 | 2159 |  | 68577 - 68578 | A | DONE | 9 | S-M |  | MEMORIAL HS 6210024 |  | 2024-04-30 | Z | 2024-04-16 | 210 | 0 | 0 |  | 0 | 350 |  | OA pool unit |  | 14
2024-04-29 | 2160 |  | 68579 | A | DONE | 5 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-04-30 | Z | 2024-04-16 | 70 | 0 | 0 |  | 50 | 80 |  | AHU-P1 |  | 14
2024-04-29 | 2161 |  | 68580 - 68581 | A | DONE | 9 | S-M | alum | MEMORIAL HS 6210024 |  | 2024-04-30 | Z | 2024-04-16 | 210 | 0 | 0 |  | 0 | 150 |  | Pool AHU |  | 14
2024-04-29 | 2162 |  | 68582 | A | DONE | 2 | S | ss | MEMORIAL HS 6210024 | partial | 2024-04-30 | Z | 2024-04-17 | 30 | 0 | 0 |  | 0 | 50 |  | Concessions |  | 13
2024-04-29 | 2163 |  | 68584 | A | DONE | 2 | S | flex | MEMORIAL HS 6210024 | flex only | 2024-04-30 | Z | 2024-04-18 | 20 | 0 | 0 |  | 0 | 20 |  | Round Flex Connection |  | 12
2024-05-04 | 2164 |  | 68585 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-05-07 | Z | 2024-04-24 | 20 | 0 | 0 |  | 0 | 30 |  | LOCKER ROOM OUT |  | 13
2024-04-30 | 3837 | w | 67472 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | 1-1/2" DB | 2024-05-01 | Z | 2024-04-29 | 20 | 0 | 0 |  | 20 | 50 |  | Curb |  | 2
2024-05-02 | 3838 |  | 67474 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-05-09 | Z | 2024-04-30 | 30 | 0 | 0 |  | 0 | 30 |  | Flashing |  | 9
2024-05-04 | 3839 |  | 67515 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-05-09 | Z | 2024-05-01 | 20 | 0 | 0 |  | 0 | 50 |  | Basement |  | 8
2024-05-01 | 168 |  | 78728 | A | DONE | 2 | S |  | MULLET ICE ARENA 10054815 | 1" liner | 2024-05-02 | Z | 2024-04-30 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 2
2024-04-29 | 3253 | w | 62526.1 - .2 | A | DONE | 8 | M |  | NIC 6240004 | 1-1/2" DB | 2024-04-30 | Z | 2024-04-08 | 180 | 0 | 0 |  | 170 | 520 |  | Curb Extensions |  | 22
2024-04-29 | 3254 | w | 62526.3 | A | DONE | 2 | S-M |  | NIC 6240004 | 1-1/2" DB | 2024-04-30 | Z | 2024-04-08 | 50 | 0 | 0 |  | 50 | 150 |  | Curb Extensions |  | 22
2024-04-30 | 3255 | w | 62526.5 - .6 | A | DONE | 10 | M |  | NIC 6240004 | 1-1/2" DB | 2024-04-30 | Z | 2024-04-08 | 140 | 0 | 0 |  | 110 | 300 |  | Curb Extensions |  | 22
2024-04-29 | 3256 |  | 41224 A | A | DONE | 7 | S-M |  | NIC 6240004 |  | 2024-04-30 | Z | 2024-04-15 | 160 | 0 | 0 |  | 0 | 340 |  | Curb drop |  | 15
2024-04-29 | 3257 |  | 41224 B ,C | A | DONE | 6 | S-M |  | NIC 6240004 |  | 2024-04-30 | Z | 2024-04-15 | 150 | 0 | 0 |  | 0 | 320 |  | Curb drop |  | 15
2024-04-29 | 3258 |  | 41224 D,E | A | DONE | 5 | S-M |  | NIC 6240004 |  | 2024-04-30 | Z | 2024-04-15 | 120 | 0 | 0 |  | 0 | 260 |  | Curb drop |  | 15
2024-04-30 | 2626 |  | 69413 | A | DONE | 2 | S |  | OLIV 6210030 |  | 2024-05-02 | Z | 2024-04-30 | 20 | 0 | 0 |  | 20 | 20 |  | Retail Trash |  | 2
2024-05-01 | 2627 |  | 69414 | A | DONE | 2 | S |  | OLIV 6210030 | paint | 2024-05-02 | Z | 2024-04-30 | 20 | 0 | 0 |  | 20 | 30 |  | L1 amenities |  | 2
2024-05-01 | 1986 | sp | 37560 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-03 | Z | 2024-05-01 | 20 | 20 | 0 |  | 0 | 20 |  | Misc |  | 2
2024-05-01 | 1987 |  | 62946 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-03 | Z | 2024-05-01 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 2
2024-05-02 | 573 | sp | LL-SAMP-03 | A | DONE | 12 | S-M |  | RAMC 6230009 | oval | 2024-05-03 | Z | 2024-02-27 | 70 | 220 | 0 |  | 0 | 360 |  |  | Semi 7 | 66
2024-05-01 | 574 | sp | LL-SAMP-04 | A | DONE | 12 | S-M |  | RAMC 6230009 | oval | 2024-05-03 | Z | 2024-02-27 | 80 | 200 | 0 |  | 0 | 330 |  |  | Semi 7 | 66
2024-05-02 | 575 | sp | LL-SAMP-05 | A | DONE | 25 | M |  | RAMC 6230009 | oval | 2024-05-03 | Z | 2024-02-27 | 130 | 480 | 0 |  | 0 | 790 |  |  | Semi 7 | 66
2024-05-02 | 576 | sp | LL-SAMP-06 | A | DONE | 39 | M-L |  | RAMC 6230009 | oval | 2024-05-03 | Z | 2024-02-27 | 150 | 810 | 0 |  | 0 | 1340 |  |  | Semi 7 | 66
2024-05-02 | 577 | sp | LL-SAMP-07 | A | DONE | 27 | M |  | RAMC 6230009 | oval | 2024-05-03 | Z | 2024-02-27 | 130 | 530 | 0 |  | 0 | 860 |  |  | Semi 7 | 66
2024-05-02 | 578 | sp | LL-SAMP-08 | A | DONE | 15 | S-M |  | RAMC 6230009 | oval | 2024-05-03 | Z | 2024-02-27 | 100 | 260 | 0 |  | 0 | 490 |  |  | Semi 7 | 66
2024-05-02 | 579 | sp | LL-SAMP-09 | A | DONE | 10 | S-M |  | RAMC 6230009 |  | 2024-05-03 | Z | 2024-02-27 | 30 | 220 | 0 |  | 0 | 290 |  |  | Semi 7 | 66
2024-05-01 | 580 | sp | LL-SAMP-10 | A | DONE | 16 | M |  | RAMC 6230009 |  | 2024-05-03 | Z | 2024-02-27 | 40 | 350 | 0 |  | 0 | 440 |  |  | Semi 7 | 66
2024-04-29 | 4747 |  | 78878 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-05-02 | Z | 2024-04-18 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 14
2024-04-30 | 4748 |  | 78879 | A | DONE | 3 | S |  | ROCK CO. JAIL 6220018 | paint | 2024-05-02 | Z | 2024-04-23 | 70 | 0 | 0 |  | 0 | 90 |  | JAIL |  | 9
2024-05-02 | 4750 |  | 33241 | A | DONE | 2 | S |  | ROCK CO. JAIL 8220022 |  | 2024-05-07 | Z | 2024-05-01 | 20 | 0 | 0 |  | 0 | 20 |  | Plates |  | 6
2024-04-30 | 4679 |  | 64046 | A | DONE | 2 | S |  | ST BERNARD 2230056 |  | 2024-05-06 | Z | 2024-04-25 | 20 | 0 | 0 |  | 0 | 20 |  | 2ND FL RECTORY |  | 11
2024-05-01 | 4678 |  | 64039-44 | A | DONE | 33 | M-L |  | ST BERNARD 6230023 |  | 2024-05-06 | Z | 2024-04-22 | 660 | 0 | 150 | F | 440 | 1130 |  | MISC |  | 14
2024-04-29 | 4658 | bth | 70301 - 70303 | A | DONE | 61 | M |  | ST.BERNARD 6230023 |  | 2024-04-29 | Z | 2024-04-09 | 270 | 270 | 970 | F | 0 | 1970 |  | AHU-2 SA |  | 20
2024-04-29 | 4659 |  | 71346 | A | DONE | 7 | S |  | ST.BERNARD 6230023 | 1" liner , bird screen | 2024-04-29 | Z | 2024-04-09 | 40 | 0 | 50 | F | 70 | 90 |  | VAV-3 LP |  | 20
2024-04-29 | 4660 |  | 71348 , 71349 | A | DONE | 27 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-04-29 | Z | 2024-04-09 | 270 | 0 | 130 | F | 290 | 370 |  | VAV-2 LP / TA |  | 20
2024-05-01 | 4673 |  | 64031 | A | DONE | 6 | S |  | ST.BERNARD 6230023 |  | 2024-05-06 | Z | 2024-04-15 | 90 | 0 | 40 | F | 0 | 180 |  | AHU-1 SA |  | 21
2024-05-04 | 4674 | bth | 64033 - 64034 | A | DONE | 7 | S-M |  | ST.BERNARD 6230023 |  | 2024-05-06 | Z | 2024-04-15 | 100 | 70 | 0 |  | 0 | 180 |  | AHU-1 SA |  | 21
2024-05-04 | 4675 | bth | 64035 - 64036 | A | DONE | 12 | S-M |  | ST.BERNARD 6230023 |  | 2024-05-06 | Z | 2024-04-15 | 130 | 60 | 100 | F | 0 | 310 |  | AHU-1 SA |  | 21
2024-05-04 | 4676 | sp | 64037 | A | DONE | 10 | S-M |  | ST.BERNARD 6230023 |  | 2024-05-06 | Z | 2024-04-15 | 20 | 210 | 0 |  | 0 | 220 |  | AHU-1 SA |  | 21
2024-05-01 | 246 |  | 70095 - 70096 | A | DONE | 22 | S-M |  | UPLAND HILLS 2240008 | VD | 2024-06-10 | Z | 2024-03-13 | 300 | 0 | 250 | F | 0 | 510 |  | RAT 1305 LPRA |  | 89 |  | 2024-05-06 | 2024-06-13
2024-05-02 | 247 |  | 70097 | A | DONE | 3 | S |  | UPLAND HILLS 2240008 | paint | 2024-06-10 | Z | 2024-03-13 | 60 | 0 | 30 | F | 20 | 70 |  | RAT 1305 LPRA |  | 89 |  | 2024-05-06 | 2024-06-13
2024-04-30 | 3214 | w | 72428 | A | DONE | 2 | S | ss | UW VET MED 2230012 |  | 2024-05-06 | Z | 2024-04-24 | 20 | 0 | 0 |  | 0 | 20 |  | BSL-TA |  | 12
2024-05-01 | 3210 |  | 72425 | A | DONE | 2 | S |  | UW VET MED 6210014 | paint | 2024-05-06 | Z | 2024-04-23 | 20 | 0 | 0 |  | 20 | 30 |  | 3rd RA |  | 13
2024-04-30 | 3212 | sp | 72426 | A | DONE | 2 | S |  | UW VET MED 6210014 |  | 2024-05-06 | Z | 2024-04-23 | 20 | 0 | 0 |  | 0 | 20 |  | 3RD |  | 13
2024-04-29 | 2013 |  | 67988 | A | DONE | 5 | S-M |  | UWL GRAFF 6230017 |  | 2024-04-29 | Z | 2024-04-23 | 110 | 0 | 0 |  | 0 | 240 |  | END CAPS |  | 6
2024-05-01 | 2014 |  | 67989 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2024-05-06 | Z | 2024-04-25 | 100 | 0 | 0 |  | 0 | 190 |  | AHU-4-RA |  | 11
2024-04-29 | 4812 |  | L2Z1-FEMP-1 | A | DONE | 11 | S-M | pcd | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-12 | 210 | 0 | 80 | F | 0 | 430 |  |  | L-2 Zone 1B | 50
2024-04-30 | 4813 | bth | L2Z1-FEMP-2 | A | DONE | 13 | S-M | pcd | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-12 | 110 | 20 | 180 | F | 0 | 450 |  |  | L-2 Zone 1B | 50
2024-04-30 | 4814 |  | L2Z1-FEMP-3 | A | DONE | 16 | M | pcd | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-12 | 40 | 0 | 360 | F | 0 | 600 |  |  | L-2 Zone 1B | 50
2024-04-30 | 4815 | bth | L2Z1-FEMP-4 | A | DONE | 13 | S-M | pcd | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-12 | 140 | 110 | 80 | F | 0 | 430 |  |  | L-2 Zone 1B | 50
2024-04-29 | 4816 |  | L2Z1-FEMP-5 | A | DONE | 9 | S-M | pcd | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-12 | 20 | 0 | 210 | F | 0 | 290 |  |  | L-2 Zone 1B | 50
2024-04-30 | 4817 | bth | L2Z1-FEMP-6 | A | DONE | 13 | S-M | pcd | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-12 | 100 | 60 | 180 | F | 0 | 430 |  |  | L-2 Zone 1B | 50
2024-04-30 | 4827 | bth | L2Z1-SAMP-1 | A | DONE | 49 | L |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-13 | 600 | 80 | 540 | F | 0 | 2530 |  |  | L-2 Zone 1B | 49
2024-04-30 | 4828 | bth | L2Z1-SAMP-2 | A | DONE | 20 | M |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-13 | 90 | 70 | 340 | F | 0 | 760 |  |  | L-2 Zone 1B | 49
2024-04-30 | 4829 | bth | L2Z1-SAMP-3 | A | DONE | 11 | S-M |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-13 | 100 | 30 | 130 | F | 0 | 360 |  |  | L-2 Zone 1B | 49
2024-04-30 | 4830 | bth | L2Z1-SAMP-4 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-13 | 100 | 20 | 160 | F | 0 | 390 |  |  | L-2 Zone 1B | 49
2024-04-30 | 4831 | bth | L2Z1-SAMP-5 | A | DONE | 7 | S |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-13 | 50 | 30 | 80 | F | 0 | 210 |  |  | L-2 Zone 1B | 49
2024-04-30 | 4832 | bth | L2Z1-SAMP-6 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-13 | 40 | 80 | 0 |  | 0 | 120 |  |  | L-2 Zone 1B | 49
2024-04-30 | 4836 | bth | L2Z1-SAMP-10 | A | DONE | 23 | M-L |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-13 | 430 | 60 | 90 | F | 0 | 1060 |  |  | L-2 Zone 1B | 49
2024-04-29 | 4851 |  | L2Z1-RAMP-1 | A | DONE | 6 | S | pt.neal | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-21 | 160 | 0 | 0 |  | 0 | 190 |  |  | L-2 Zone 1B | 41
2024-04-29 | 4852 |  | L2Z1-RAMP-2 | A | DONE | 11 | S-M |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-21 | 80 | 0 | 190 | F | 0 | 330 |  |  | L-2 Zone 1B | 41
2024-04-29 | 4853 |  | L2Z1-RAMP-3 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-21 | 50 | 0 | 80 | F | 0 | 160 |  |  | L-2 Zone 1B | 41
2024-04-29 | 4854 |  | L2Z1-RAMP-4 | A | DONE | 8 | S | neal | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-21 | 40 | 0 | 140 | F | 0 | 210 |  |  | L-2 Zone 1B | 41
2024-04-30 | 4855 | bth | L2Z1-RAMP-5 | A | DONE | 6 | S | neal | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-21 | 30 | 10 | 100 | F | 0 | 170 |  |  | L-2 Zone 1B | 41
2024-04-29 | 4856 |  | L2Z1-RAMP-6 | A | DONE | 11 | S | pt.neal | UWRF 6230010 |  | 2024-05-01 | Z | 2024-03-21 | 180 | 0 | 90 | F | 0 | 310 |  |  | L-2 Zone 1B | 41
2024-05-03 | 4805 |  | L2Z2-EAMP-6 | A | DONE | 42 | M-L | pt.neal | UWRF 6230010 |  | 2024-05-06 | Z | 2024-03-12 | 630 | 0 | 420 | F | 0 | 1780 |  |  | L2 Zone 2 A/B | 55
2024-05-03 | 4806 | bth | L2Z2-EAMP-7 | A | DONE | 27 | M |  | UWRF 6230010 |  | 2024-05-06 | Z | 2024-03-12 | 210 | 50 | 400 | F | 0 | 970 |  |  | L2 Zone 2 A/B | 55
2024-05-03 | 4807 | bth | L2Z2-EAMP-8 | A | DONE | 8 | S-M |  | UWRF 6230010 |  | 2024-05-06 | Z | 2024-03-12 | 90 | 30 | 80 | F | 0 | 240 |  |  | L2 Zone 2 A/B | 55
2024-05-03 | 4808 | bth | L2Z2-EAMP-9 | A | DONE | 29 | M |  | UWRF 6230010 |  | 2024-05-06 | Z | 2024-03-12 | 240 | 40 | 430 | F | 0 | 1080 |  |  | L2 Zone 2 A/B | 55
2024-05-03 | 4837 | bth | L2Z2-SAMP-11 | A | DONE | 30 | M-L |  | UWRF 6230010 |  | 2024-05-06 | Z | 2024-03-13 | 210 | 90 | 450 | F | 0 | 1210 |  |  | L2 Zone 2 A/B | 54
2024-05-03 | 4838 | bth | L2Z2-SAMP-12 | A | DONE | 15 | M |  | UWRF 6230010 |  | 2024-05-06 | Z | 2024-03-13 | 30 | 90 | 240 | F | 0 | 520 |  |  | L2 Zone 2 A/B | 54
2024-05-03 | 4839 | bth | L2Z2-SAMP-13 | A | DONE | 22 | M |  | UWRF 6230010 |  | 2024-05-06 | Z | 2024-03-13 | 100 | 100 | 330 | F | 0 | 820 |  |  | L2 Zone 2 A/B | 54
2024-05-03 | 4840 | bth | L2Z2-SAMP-14 | A | DONE | 28 | M-L |  | UWRF 6230010 |  | 2024-05-06 | Z | 2024-03-13 | 240 | 40 | 410 | F | 0 | 1130 |  |  | L2 Zone 2 A/B | 54
2024-05-04 | 4809 | bth | L2Z2-EAMP-10 | A | DONE | 28 | M-L | pt.neal | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-12 | 220 | 50 | 430 | F | 0 | 1370 |  |  | L2 Zone 2 C | 57
2024-05-04 | 4847 |  | L2Z2-SAMP-21 | A | DONE | 20 | M |  | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-13 | 270 | 0 | 210 | F | 0 | 780 |  |  | L2 Zone 2 C | 56
2024-05-04 | 4848 |  | L2Z2-SAMP-22 | A | DONE | 18 | M |  | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-13 | 250 | 0 | 190 | F | 0 | 700 |  |  | L2 Zone 2 C | 56
2024-04-29 | 4932 |  | 73397 | A | DONE | 8 | S-M |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-04-11 | 190 | 0 | 0 |  | 0 | 220 |  | L-3 hangers |  | 20
2024-04-30 | 4933 |  | 73398 | A | DONE | 13 | M |  | UWRF 6230010 |  | 2024-05-01 | Z | 2024-04-11 | 320 | 0 | 0 |  | 0 | 470 |  | Test caps |  | 20
2024-05-02 | 3215 | w | 72429 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-05-06 | Z | 2024-05-01 | 20 | 0 | 0 |  | 0 | 40 |  | BSL-3 |  | 5
2024-05-01 | 2282 | sp | 68999 | A | DONE | 4 | S | alum | WCSD HERITAGE 6220024 |  | 2024-05-03 | Z | 2024-04-18 | 20 | 70 | 0 |  | 0 | 50 |  | DRYER DUCT |  | 15
2024-05-01 | 2285 |  | 69252-53 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 |  | 2024-05-03 | Z | 2024-04-19 | 20 | 0 | 0 |  | 0 | 30 |  | Dishwasher / Dampers |  | 14
2024-04-30 | 2287 |  | 69255 | A | DONE | 6 | S-M |  | WCSD HERITAGE 6220024 |  | 2024-05-01 | Z | 2024-04-24 | 140 | 0 | 0 |  | 0 | 200 |  | 2ND FL PLENUM |  | 7
2024-04-30 | 2288 |  | 69315 | A | DONE | 3 | S | neal | WCSD HERITAGE 6220024 |  | 2024-05-03 | Z | 2024-04-24 | 70 | 0 | 0 |  | 0 | 80 |  | DOAS-3-EA |  | 9
2024-04-30 | 2289 |  | 69049 | A | DONE | 2 | S |  | WCSD HERITAGE 6220024 |  | 2024-05-03 | Z | 2024-04-24 | 20 | 0 | 0 |  | 0 | 20 |  | 1ST FL CEILING |  | 9
2024-04-30 | 2290 |  | 69316 | A | DONE | 2 | S | neal | WCSD HERITAGE 6220024 |  | 2024-05-03 | Z | 2024-04-26 | 30 | 0 | 0 |  | 0 | 40 |  | 2ND FL HP-201-SA |  | 7
2024-05-04 | 170 |  | 23907 | A | DONE | 2 | S |  | WICELL 2230040 |  | 2024-05-07 | Z | 2024-05-03 | 20 | 0 | 0 |  | 0 | 20 |  | Hallway SA couplings |  | 4
[6 empty] | 1305 | [13 empty] | 43360 |  |  |  | 5100 | 11.76%
WEEK OF 5-6-2024
2024-05-07 | 2203 |  | 2NDFL / 2NDFL-2 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-05-14 | Z | 2024-05-07 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 7
2024-05-06 | 165 | bth | 70223 | A | DONE | 10 | S-M |  | ACCURAY 4240021 |  | 2024-05-07 | Z | 2024-04-30 | 130 | 120 | 0 |  | 0 | 220 |  | Misc |  | 7
2024-05-07 | 1750 |  | 68040 | A | DONE | 6 | S-M |  | BLACKHAWK BTC 6230025 |  | 2024-05-09 | Z | 2024-05-07 | 130 | 0 | 0 |  | 0 | 240 |  | Curb caps |  | 2
2024-05-11 | 177 |  | 70581 | A | DONE | 2 | S |  | CAMBRIDGE MS 10055437 |  | 2024-05-10 | Z | 2024-05-10 | 20 | 0 | 0 |  | 0 | 20 |  | End cap |  | 0
2024-05-06 | 788 | sp | 69862 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-05-07 | Z | 2024-04-24 | 20 | 20 | 0 |  | 0 | 40 |  | B-EAD-2-Basement |  | 13
2024-05-11 | 792 |  | 61035 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-29 | 70 | 0 | 0 |  | 0 | 130 |  | 2nd floor EA Chase |  | 15
2024-05-06 | 819 |  | NC-RAD-001 | A | DONE | 20 | M-L |  | CDIS 6220028 | partial 1-3 floors | 2024-05-09 | Z | 2024-05-01 | 80 | 0 | 400 | F | 0 | 1010 |  |  |  | 8
2024-05-07 | 821 |  | NC-SAMP-001 | A | DONE | 38 | M-L |  | CDIS 6220028 | partial 1-3 floors | 2024-05-09 | Z | 2024-05-01 | 80 | 0 | 400 | F | 0 | 1000 |  |  |  | 8
2024-05-08 | 3611 | bth | L4-A-EAMP-038 | A | DONE | 16 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 50 | 50 | 290 | F | 0 | 610 |  |  |  | 37
2024-05-08 | 3612 | bth | L4-A-EAMP-039 | A | DONE | 16 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 110 | 30 | 250 | F | 0 | 650 |  |  |  | 37
2024-05-08 | 3613 | bth | L4-A-EAMP-040 | A | DONE | 14 | S-M | neal | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 170 | 40 | 130 | F | 0 | 490 |  |  |  | 37
2024-05-08 | 3614 | bth | L4-A-EAMP-041 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 60 | 60 | 70 | F | 0 | 220 |  |  |  | 37
2024-05-08 | 3615 | bth | L4-A-EAMP-042 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 50 | 20 | 140 | F | 0 | 250 |  |  |  | 37
2024-05-06 | 3616 | bth | L4-A-SAMP-041 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 90 | 30 | 170 | F | 0 | 410 |  |  |  | 37
2024-05-08 | 3617 | bth | L4-A-SAMP-042 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 140 | 20 | 30 | F | 0 | 220 |  |  |  | 37
2024-05-07 | 3618 |  | L4-A-SAMP-043 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 140 | 0 | 100 | F | 0 | 320 |  |  |  | 37
2024-05-08 | 3619 | bth | L4-A-SAMP-045 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 30 | 60 | 130 | F | 0 | 270 |  |  |  | 37
2024-05-08 | 3620 | bth | L4-A-SAMP-046 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 50 | 20 | 220 | F | 0 | 450 |  |  |  | 37
2024-05-08 | 3621 | bth | L4-A-SAMP-047 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 37
2024-05-08 | 3622 | bth | L4-A-SAMP-048 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 140 | 60 | 110 | F | 0 | 440 |  |  |  | 37
2024-05-08 | 3623 | bth | L4-A-SAMP-049 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 110 | 20 | 150 | F | 0 | 440 |  |  |  | 37
2024-05-08 | 3624 | bth | L4-A-SAMP-050 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 120 | 40 | 30 | F | 0 | 220 |  |  |  | 37
2024-05-08 | 3625 | bth | L4-A-SAMP-051 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 37
2024-05-08 | 3626 | bth | L4-A-SAMP-052 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 37
2024-05-08 | 3627 | bth | L4-A-SAMP-053 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 37
2024-05-07 | 3628 | bth | L4-A-SAMP-054 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 20 | 0 | 100 | F | 0 | 140 |  |  |  | 37
2024-05-08 | 3629 | bth | L4-A-SAMP-055 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-05-09 | Z | 2024-04-02 | 50 | 30 | 20 | F | 0 | 110 |  |  |  | 37
2024-05-11 | 3637 |  | L4-A-SALP-015 | A | DONE | 3 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 70 | 0 | 0 |  | 20 | 80 |  |  |  | 42
2024-05-11 | 3642 |  | L4-A-SALP-068 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 80 | 0 | 80 | F | 0 | 200 |  |  |  | 42
2024-05-11 | 3651 | bth | L4-A-SALP-084 | A | DONE | 4 | S-M | pt.neal | CDIS 6220028 | 1" liner , paint | 2024-05-14 | Z | 2024-04-02 | 80 | 0 | 20 | F | 30 | 120 |  |  |  | 42
2024-05-08 | 3958a |  | L1-B-EAD-014 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-05-08 | 80 | 0 | 60 | F | 0 | 160 |  | Remake |  | 6
2024-05-07 | 172 |  | 79756 | A | DONE | 4 | S |  | COMPASS HP 4230088 |  | 2024-05-10 | Z | 2024-05-06 | 80 | 0 | 0 |  | 0 | 150 |  | SA/RA drops |  | 4
2024-05-08 | 1130 |  | 59489 | A | DONE | 2 | S |  | DANE CO. AIRPORT 6210011 |  | 2024-05-08 | Z | 2024-05-08 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-05-09 | 2335 | sp | 58802 | A | DONE | 3 | S-M |  | DEWITT 2240019 |  | 2024-05-10 | Z | 2024-04-30 | 50 | 20 | 0 |  | 0 | 60 |  | Chilled Beam |  | 10
2024-05-07 | 1580 |  | 62379 - 62380 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 | birdscreen | 2024-05-09 | Z | 2024-05-06 | 30 | 0 | 0 |  | 0 | 40 |  | Flashing / Shroud |  | 3
2024-05-10 | 174 |  | 37562 | A | DONE | 2 | S |  | EVCO 2240015 | flex | 2024-05-13 | Z | 2024-05-09 | 50 | 0 | 0 |  | 0 | 50 |  | Misc |  | 4
2024-05-09 | 4607 |  | 69416 | A | DONE | 2 | S-M |  | HARMONICS 6240010 | VD , oval flange | 2024-05-13 | Z | 2024-05-03 | 50 | 0 | 0 |  | 20 | 80 |  | S.O outs |  | 10
2024-05-07 | 2291 |  | 69317 - 69318 | A | DONE | 3 | S-M |  | HERITAGE 6220024 |  | 2024-05-10 | Z | 2024-05-02 | 70 | 0 | 0 |  | 0 | 80 |  | 2nd C-Section tie-ins |  | 8
2024-05-07 | 2292 |  | 69320 - 69321 | A | DONE | 4 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-05-10 | Z | 2024-05-02 | 90 | 0 | 0 |  | 60 | 140 |  | 2nd C-Section tie-ins |  | 8
2024-05-07 | 2293 |  | 69322 | A | DONE | 2 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-05-10 | Z | 2024-05-02 | 40 | 0 | 0 |  | 30 | 60 |  | 2nd C-Section TA |  | 8
2024-05-07 | 2294 |  | 69327 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-05-10 | Z | 2024-05-02 | 20 | 0 | 0 |  | 0 | 30 |  | 1st A room 1126 |  | 8
2024-05-07 | 2295 |  | 69256 | A | DONE | 4 | S | pt.neal | HERITAGE 6220024 | paint | 2024-05-10 | Z | 2024-05-06 | 100 | 0 | 0 |  | 20 | 110 |  | Stem EA |  | 4
2024-05-07 | 2296 |  | 69326 | A | DONE | 2 | S | neal | HERITAGE 6220024 | 1" liner | 2024-05-10 | Z | 2024-05-06 | 20 | 0 | 0 |  | 20 | 30 |  | 1st Floor outs |  | 4
2024-05-06 | 2823 |  | 78606-08 | A | DONE | 6 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-05-07 | Z | 2024-04-23 | 150 | 0 | 0 |  | 0 | 140 |  | POOL Supply/Exhaust |  | 14
2024-05-08 | 2824 |  | 78609 - 78610 | A | DONE | 24 | S-M | alum | JANESVILLE ESSR 6230011 |  | 2024-05-09 | Z | 2024-04-29 | 490 | 0 | 110 | F | 0 | 430 |  | AHU-RA / EA |  | 10
2024-05-08 | 2834 |  | 70820 | A | DONE | n/a | S | alum | JANESVILLE ESSR 6230011 |  | 2024-05-09 | Z | 2024-05-08 | 0 | 0 | 0 |  | 0 | 0 |  | Ductmate |  | 1
2024-05-07 | 171 |  | 70225 | A | DONE | 2 | S |  | JOHNSON HEALTH 10055308 |  | 2024-05-08 | Z | 2024-05-06 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2024-05-06 | 169 |  | 62944 - 62945 | A | DONE | 9 | S-M |  | LINDSEY M. 1000373 |  | 2024-05-08 | Z | 2024-05-01 | 220 | 0 | 0 |  | 0 | 230 |  | Furnace |  | 7
2024-05-07 | 3840 |  | 67525 - 67527 | A | DONE | 18 | M |  | MENDOTA FOODS 6220027 |  | 2024-05-09 | Z | 2024-05-06 | 220 | 0 | 220 | F | 0 | 620 |  | Tie-ins |  | 3
2024-05-07 | 164 |  | 69807-08 | A | DONE | 4 | S | alum | MSN 2240006 |  | 2024-05-10 | Z | 2024-04-26 | 80 | 0 | 0 |  | 0 | 100 |  | DR-5 |  | 14
2024-05-08 | 2628 |  | 69415 | A | DONE | 3 | S-M | pt.alum | OLIV 6210030 | paint , birdscreen | 2024-05-13 | Z | 2024-05-03 | 60 | 0 | 0 |  | 20 | 60 |  | 11th |  | 10
2024-05-11 | 2629 |  | 69417 | A | DONE | 2 | S |  | OLIV 6210030 | paint | 2024-05-13 | Z | 2024-05-10 | 20 | 0 | 0 |  | 20 | 20 |  | L1 Amenities |  | 3
2024-05-06 | 163 |  | email | A | DONE | 16 | S |  | PP 10055216 |  | 2024-05-07 | Z | 2024-04-24 | 0 | 0 | 400 | F | 0 | 870 |  | FLAT STOCK |  | 13
2024-05-06 | 4397 |  | 37559 | A | DONE | 3 | S |  | PROMEGA BTC 6230022 |  | 2024-05-08 | Z | 2024-04-24 | 50 | 0 | 30 | F | 0 | 80 |  | ENGINEERING |  | 14
2024-05-06 | 4399 |  | 37561 | A | DONE | 2 | S |  | PROMEGA BTC 2230052 |  | 2024-05-08 | Z | 2024-05-02 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2024-05-08 | 1800 |  | 62948 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-09 | Z | 2024-05-07 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 2
2024-05-09 | 551 | bth | LL-EA-01 | A | DONE | 12 | S-M |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 190 | 30 | 80 | F | 0 | 350 |  |  | Semi 8 | 73
2024-05-09 | 552 | bth | LL-EA-02 | A | DONE | 10 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 90 | 150 | 0 |  | 0 | 240 |  |  | Semi 8 | 73
2024-05-09 | 553 | sp | LL-EA-03 | A | DONE | 7 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 30 | 140 | 0 |  | 0 | 170 |  |  | Semi 8 | 73
2024-05-09 | 554 | sp | LL-EA-04 | A | DONE | 9 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 50 | 170 | 0 |  | 0 | 250 |  |  | Semi 8 | 73
2024-05-09 | 555 | bth | LL-EA-05 | A | DONE | 12 | S-M |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 130 | 160 | 0 |  | 0 | 330 |  |  | Semi 8 | 73
2024-05-09 | 556 | sp | LL-EA-06 | A | DONE | 4 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 80 | 0 |  | 0 | 110 |  |  | Semi 8 | 73
2024-05-09 | 557 | sp | LL-EA-07 | A | DONE | 13 | S-M |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 290 | 0 |  | 0 | 350 |  |  | Semi 8 | 73
2024-05-09 | 558 | sp | LL-EA-08 | A | DONE | 10 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 220 | 0 |  | 0 | 270 |  |  | Semi 8 | 73
2024-05-09 | 559 | sp | LL-EA-09 | A | DONE | 8 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 30 | 160 | 0 |  | 0 | 220 |  |  | Semi 8 | 73
2024-05-07 | 567 | sp | LL-RA-08 | A | DONE | 22 | M |  | RAMC 6230009 | oval | 2024-05-08 | Z | 2024-02-27 | 160 | 390 | 0 |  | 0 | 680 |  |  | Semi 6 | 71
2024-05-07 | 568 | sp | LL-RA-09 | A | DONE | 47 | M-L |  | RAMC 6230009 | oval | 2024-05-08 | Z | 2024-02-27 | 220 | 940 | 0 |  | 0 | 1820 |  |  | Semi 6 | 71
2024-05-07 | 569 | sp | LL-RA-10 | A | DONE | 13 | S-M |  | RAMC 6230009 |  | 2024-05-08 | Z | 2024-02-27 | 70 | 260 | 0 |  | 0 | 390 |  |  | Semi 6 | 71
2024-05-07 | 570 | sp | LL-RA-11 | A | DONE | 24 | M |  | RAMC 6230009 | oval | 2024-05-08 | Z | 2024-02-27 | 160 | 440 | 0 |  | 0 | 750 |  |  | Semi 6 | 71
2024-05-07 | 571 | bth | LL-SAMP-01 | A | DONE | 41 | L |  | RAMC 6230009 | oval | 2024-05-08 | Z | 2024-02-27 | 520 | 440 | 80 | F | 0 | 2030 |  |  | Semi 6 | 71
2024-05-07 | 572 | sp | LL-SAMP-02 | A | DONE | 23 | M |  | RAMC 6230009 | oval | 2024-05-08 | Z | 2024-02-27 | 90 | 470 | 0 |  | 0 | 840 |  |  | Semi 6 | 71
2024-05-08 | 581 |  | LL-TA-01 | A | DONE | 8 | S-M |  | RAMC 6230009 | 1" liner | 2024-05-10 | Z | 2024-02-27 | 180 | 0 | 0 |  | 110 | 220 |  |  | Semi 8 | 73
2024-05-08 | 582 |  | LL-TA-02 | A | DONE | 2 | S |  | RAMC 6230009 | 1" liner | 2024-05-10 | Z | 2024-02-27 | 40 | 0 | 0 |  | 30 | 50 |  |  | Semi 8 | 73
2024-05-09 | 583 | bth | LL-VAV-25 | A | DONE | 6 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 120 | 0 |  | 0 | 150 |  |  | Semi 8 | 73
2024-05-09 | 584 | bth | LL-VAV-26 | A | DONE | 21 | M |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 320 | 20 | 170 | F | 0 | 600 |  |  | Semi 8 | 73
2024-05-09 | 585 | bth | LL-VAV-27 | A | DONE | 8 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 40 | 140 | 0 |  | 0 | 200 |  |  | Semi 8 | 73
2024-05-08 | 586 | bth | LL-VAV-28 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 30 | 20 | 0 |  | 0 | 60 |  |  | Semi 8 | 73
2024-05-09 | 587 | bth | LL-VAV-29 | A | DONE | 3 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 50 | 30 | 0 |  | 0 | 90 |  |  | Semi 8 | 73
2024-05-09 | 588 | bth | LL-VAV-30 | A | DONE | 4 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 40 | 50 | 0 |  | 0 | 100 |  |  | Semi 8 | 73
2024-05-09 | 589 | bth | LL-VAV-31 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 8 | 73
2024-05-09 | 590 | bth | LL-VAV-32 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 40 |  |  | Semi 8 | 73
2024-05-09 | 591 | bth | LL-VAV-33 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 40 |  |  | Semi 8 | 73
2024-05-09 | 592 | bth | LL-VAV-34 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 8 | 73
2024-05-09 | 593 | bth | LL-VAV-35 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 50 |  |  | Semi 8 | 73
2024-05-09 | 594 | bth | LL-VAV-36 | A | DONE | 4 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 40 | 60 | 0 |  | 0 | 120 |  |  | Semi 8 | 73
2024-05-09 | 595 | bth | LL-VAV-37 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 30 |  |  | Semi 8 | 73
2024-05-09 | 596 | bth | LL-VAV-38 | A | DONE | 9 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 80 | 130 | 0 |  | 0 | 240 |  |  | Semi 8 | 73
2024-05-09 | 597 | bth | LL-VAV-39 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 30 |  |  | Semi 8 | 73
2024-05-09 | 598 | bth | LL-VAV-40 | A | DONE | 10 | S-M |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 50 | 200 | 0 |  | 0 | 290 |  |  | Semi 8 | 73
2024-05-09 | 599 | bth | LL-VAV-41 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 30 | 20 | 0 |  | 0 | 50 |  |  | Semi 8 | 73
2024-05-09 | 4500 | bth | LL-VAV-42 | A | DONE | 11 | S-M |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 50 | 210 | 0 |  | 0 | 300 |  |  | Semi 8 | 73
2024-05-09 | 4501 | bth | LL-VAV-43 | A | DONE | 3 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 50 | 0 |  | 0 | 70 |  |  | Semi 8 | 73
2024-05-09 | 4502 |  | LL-VAV-44 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 8 | 73
2024-05-09 | 4503 |  | LL-VAV-44A | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 8 | 73
2024-05-09 | 4504 | bth | LL-VAV-45 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 8 | 73
2024-05-09 | 4505 | bth | LL-VAV-46 | A | DONE | 11 | S-M |  | RAMC 6230009 |  | 2024-05-10 | Z | 2024-02-27 | 50 | 210 | 0 |  | 0 | 300 |  |  | Semi 8 | 73
2024-05-07 | 4749 |  | 78880 - 78881 | A | DONE | 4 | S-M |  | ROCK CO. JAIL 6220018 | VD's , paint | 2024-05-09 | Z | 2024-04-30 | 80 | 0 | 0 |  | 40 | 140 |  | Car garage |  | 9
2024-05-06 | 4751 |  | 78957 | A | DONE | 2 | S-M | ss | ROCK CO. JAIL 6220018 |  | 2024-05-08 | Z | 2024-05-03 | 30 | 0 | 0 |  | 0 | 70 |  | Pipe enclosure |  | 5
2024-05-08 | 4680 |  | 64045 | A | DONE | 2 | S |  | ST BERNARD 2230056 |  | 2024-05-13 | Z | 2024-04-25 | 20 | 0 | 0 |  | 0 | 20 |  | Basement Rectory |  | 18
2024-05-08 | 4681 |  | 64047 | A | DONE | 3 | S |  | ST.BERNARD 2230056 |  | 2024-05-13 | Z | 2024-04-30 | 30 | 0 | 0 |  | 0 | 40 |  | 1st floor RA |  | 13
2024-05-08 | 2015 |  | 67990 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2024-05-13 | Z | 2024-04-30 | 100 | 0 | 0 |  | 0 | 210 |  | AHU-5 RA |  | 13
2024-05-08 | 3982 |  | 66882 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-05-10 | Z | 2024-05-08 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeve |  | 2
2024-05-11 | 4818 |  | L2Z2-FEMP-7 | A | DONE | 6 | S | pcd | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-12 | 100 | 0 | 50 | F | 0 | 190 |  |  | L2 Zone 2 A/B | 62
2024-05-10 | 4819 | bth | L2Z2-FEMP-8 | A | DONE | 6 | S | pcd | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-12 | 40 | 90 | 0 |  | 0 | 150 |  |  | L2 Zone 2 A/B | 62
2024-05-10 | 4820 | sp | L2Z2-FEMP-9 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-12 | 20 | 70 | 0 |  | 0 | 100 |  |  | L2 Zone 2 A/B | 62
2024-05-10 | 4821 | bth | L2Z2-FEMP-10 | A | DONE | 14 | S-M | pcd | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-12 | 180 | 110 | 50 | F | 0 | 430 |  |  | L2 Zone 2 A/B | 62
2024-05-11 | 4841 | bth | L2Z2-SAMP-15 | A | DONE | 29 | M |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-13 | 560 | 30 | 120 | F | 0 | 1150 |  |  | L2 Zone 2 A/B | 61
2024-05-11 | 4842 | bth | L2Z2-SAMP-16 | A | DONE | 27 | M-L |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-13 | 330 | 90 | 250 | F | 0 | 980 |  |  | L2 Zone 2 A/B | 61
2024-05-11 | 4843 | bth | L2Z2-SAMP-17 | A | DONE | 8 | S-M |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-13 | 40 | 40 | 100 | F | 0 | 240 |  |  | L2 Zone 2 A/B | 61
2024-05-11 | 4844 | bth | L2Z2-SAMP-18 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-13 | 70 | 30 | 40 | F | 0 | 160 |  |  | L2 Zone 2 A/B | 61
2024-05-09 | 4857 |  | L2Z2-RAMP-7 | A | DONE | 12 | S-M | neal | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-21 | 130 | 0 | 170 | F | 0 | 360 |  |  | L2 Zone 2 A/B | 53
2024-05-09 | 4858 |  | L2Z2-RAMP-8 | A | DONE | 17 | S-M | neal | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-21 | 80 | 0 | 330 | F | 0 | 510 |  |  | L2 Zone 2 A/B | 53
2024-05-09 | 4859 |  | L2Z2-RAMP-9 | A | DONE | 9 | S-M | neal | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-21 | 130 | 0 | 90 | F | 0 | 250 |  |  | L2 Zone 2 A/B | 53
2024-05-10 | 4860 | bth | L2Z2-RAMP-10 | A | DONE | 9 | S | neal | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-21 | 140 | 40 | 30 | F | 0 | 240 |  |  | L2 Zone 2 A/B | 53
2024-05-06 | 4810 | bth | L2Z2-EAMP-11 | A | DONE | 18 | M | pt.neal | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-12 | 130 | 140 | 160 | F | 0 | 700 |  |  | L2 Zone 2 C | 57
2024-05-06 | 4811 | bth | L2Z2-EAMP-12 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-12 | 130 | 80 | 80 | F | 0 | 390 |  |  | L2 Zone 2 C | 57
2024-05-06 | 4822 | bth | L2Z2-FEMP-11 | A | DONE | 10 | S-M | pcd | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-12 | 150 | 20 | 70 | F | 0 | 310 |  |  | L2 Zone 2 C | 57
2024-05-06 | 4823 | bth | L2Z2-FEMP-12 | A | DONE | 11 | S-M | pcd | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-12 | 70 | 20 | 180 | F | 0 | 320 |  |  | L2 Zone 2 C | 57
2024-05-06 | 4824 | bth | L2Z2-FEMP-13 | A | DONE | 10 | S-M | pcd | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-12 | 150 | 60 | 30 | F | 0 | 290 |  |  | L2 Zone 2 C | 57
2024-05-06 | 4825 | bth | L2Z2-FEMP-14 | A | DONE | 7 | S | pcd | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-12 | 70 | 20 | 80 | F | 0 | 190 |  |  | L2 Zone 2 C | 57
2024-05-06 | 4826 | bth | L2Z2-FEMP-15 | A | DONE | 9 | S-M | pcd | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-12 | 100 | 20 | 100 | F | 0 | 260 |  |  | L2 Zone 2 C | 57
2024-05-06 | 4845 | bth | L2Z2-SAMP-19 | A | DONE | 28 | M-L |  | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-13 | 190 | 80 | 430 | F | 0 | 1120 |  |  | L2 Zone 2 C | 56
2024-05-06 | 4846 | bth | L2Z2-SAMP-20 | A | DONE | 29 | M-L |  | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-13 | 190 | 50 | 480 | F | 0 | 1190 |  |  | L2 Zone 2 C | 56
2024-05-06 | 4849 | bth | L2Z2-SAMP-23 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-05-08 | Z | 2024-03-13 | 30 | 20 | 160 | F | 0 | 300 |  |  | L2 Zone 2 C | 56
2024-05-10 | 4885 | bth | L3Z1-EAMP-1 | A | DONE | 26 | M-L | pt.neal | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-26 | 190 | 50 | 410 | F | 0 | 1030 |  |  | L3 Zone 1 A/B | 48
2024-05-10 | 4886 | bth | L3Z1-EAMP-2 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-26 | 150 | 40 | 110 | F | 0 | 370 |  |  | L3 Zone 1 A/B | 48
2024-05-10 | 4887 | bth | L3Z1-EAMP-3 | A | DONE | 18 | M | pt.neal | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-26 | 140 | 20 | 290 | F | 0 | 620 |  |  | L3 Zone 1 A/B | 48
2024-05-08 | 4888 |  | L3Z1-EAMP-4 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-26 | 120 | 0 | 210 | F | 0 | 470 |  |  | L3 Zone 1 A/B | 48
2024-05-10 | 4889 | bth | L3Z1-EAMP-5 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-26 | 100 | 80 | 170 | F | 0 | 470 |  |  | L3 Zone 1 A/B | 48
2024-05-10 | 4890 | sp | L3Z1-EAMP-6 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-26 | 40 | 140 | 0 |  | 0 | 210 |  |  | L3 Zone 1 A/B | 48
2024-05-10 | 4905 | bth | L3Z1-SAMP-4 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-26 | 160 | 30 | 110 | F | 0 | 470 |  |  | L3 Zone 1 A/B | 48
2024-05-10 | 4906 | bth | L3Z1-SAMP-5 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-05-13 | Z | 2024-03-26 | 90 | 30 | 160 | F | 0 | 410 |  |  | L3 Zone 1 A/B | 48
2024-05-10 | 3217 | w | 72431 | A | DONE | 2 | S | ss | UW-VET MED 2230012 |  | 2024-05-13 | Z | 2024-05-02 | 20 | 0 | 0 |  | 0 | 30 |  | BSL-3 |  | 11
2024-05-06 | 3216 |  | 72430 | A | DONE | 2 | S |  | UW-VET MED 2230013 |  | 2024-05-13 | Z | 2024-05-02 | 40 | 0 | 0 |  | 0 | 90 |  | 3rd |  | 11
2024-05-06 | 3218 |  | 72433 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-05-08 | Z | 2024-05-02 | 20 | 0 | 0 |  | 0 | 20 |  | Pipe cover |  | 6
2024-05-07 | 173 |  | 70580 | A | DONE | 2 | S |  | WICELL 2230040 |  | 2024-05-07 | Z | 2024-05-07 | 20 | 0 | 0 |  | 0 | 20 |  | Reducer |  | 0
[6 empty] | 1211 | [13 empty] | 38710 |  |  |  | 6490 | 16.77%
WEEK OF 5-13-2024
2024-05-15 | 1745 | bth | 68032 , 68035 | A | DONE | 12 | S-M | neal | BLACKHAWK BTC 6230025 | 1" s. accu | 2024-05-16 | Z | 2024-05-02 | 260 | 20 | 0 |  | 180 | 340 |  | Mezz lab |  | 14
2024-05-15 | 1746 |  | 68033 - 68034 | A | DONE | 37 | S-M | neal | BLACKHAWK BTC 6230025 | 1" liner | 2024-05-16 | Z | 2024-05-02 | 800 | 0 | 120 | F | 360 | 660 |  | Mezz lab |  | 14
2024-05-13 | 1747 |  | 68036 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 | flex | 2024-05-16 | Z | 2024-05-02 | 20 | 0 | 0 |  | 0 | 30 |  | EF-6 |  | 14
2024-05-15 | 1748 | sp | 68037 | A | DONE | 5 | S-M | neal | BLACKHAWK BTC 6230025 | birdscreen | 2024-05-16 | Z | 2024-05-02 | 30 | 80 | 0 |  | 0 | 130 |  | EF-6 |  | 14
2024-05-14 | 1749 | bth | 68038 - 68039 | A | DONE | 2 | S |  | BLACKHAWK BTC 6230025 |  | 2024-05-16 | Z | 2024-05-07 | 30 | 0 | 0 |  | 0 | 60 |  | VAV-03 / Flashing |  | 9
2024-05-15 | 795 | bth | L2-B-EAD-004 | A | DONE | 4 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 40 | 60 | 0 |  | 0 | 110 |  |  |  | 16
2024-05-15 | 796 | bth | L2-B-EAD-005 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 60 | 20 | 70 | F | 0 | 170 |  |  |  | 16
2024-05-15 | 797 | bth | L2-B-EAD-006 | A | DONE | 7 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 20 | 50 | 90 | F | 0 | 170 |  |  |  | 16
2024-05-15 | 798 | bth | L2-B-EAD-007 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 40 | 40 | 70 | F | 0 | 160 |  |  |  | 16
2024-05-15 | 799 | bth | L2-B-EAD-008 | A | DONE | 21 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 310 | 40 | 170 | F | 30 | 670 |  |  |  | 16
2024-05-15 | 800 |  | L2-B-EAD-009 | A | DONE | 28 | S-M | neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 290 | 0 | 400 | F | 0 | 1180 |  |  |  | 16
2024-05-15 | 801 | bth | L2-B-EAD-010 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 130 | 20 | 30 | F | 0 | 200 |  |  |  | 16
2024-05-15 | 802 | bth | L2-B-EAD-015 | A | DONE | 9 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 40 | 70 | 110 | F | 0 | 250 |  |  |  | 16
2024-05-15 | 803 | bth | L2-B-SALP-032 | A | DONE | 14 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-16 | Z | 2024-04-30 | 150 | 0 | 190 | F | 40 | 470 |  |  |  | 16
2024-05-15 | 804 | bth | L2-B-SALP-033 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 40 | 0 | 270 | F | 0 | 380 |  |  |  | 16
2024-05-15 | 805 | bth | L2-B-SAMP-002 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 40 | 40 | 40 | F | 0 | 120 |  |  |  | 16
2024-05-15 | 806 | bth | L2-B-SAMP-003 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 50 | 40 | 60 | F | 0 | 160 |  |  |  | 16
2024-05-15 | 807 | bth | L2-B-SAMP-004 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 160 | 30 | 130 | F | 0 | 390 |  |  |  | 16
2024-05-15 | 808 |  | L2-B-SAMP-005 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 100 | 0 | 210 | F | 0 | 370 |  |  |  | 16
2024-05-15 | 809 | bth | L2-B-SAMP-006 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 190 | 50 | 0 |  | 0 | 270 |  |  |  | 16
2024-05-15 | 810 | bth | L2-B-SAMP-010 | A | DONE | 27 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 260 | 30 | 370 | F | 0 | 1010 |  |  |  | 16
2024-05-15 | 811 | bth | L2-A-EAD-059 | A | DONE | 6 | S-M | neal | CDIS 6220028 | paint | 2024-05-16 | Z | 2024-04-30 | 90 | 20 | 30 | F | 20 | 150 |  |  |  | 16
2024-05-15 | 812 | bth | L2-A-EAD-060 | A | DONE | 8 | S-M | neal | CDIS 6220028 | paint | 2024-05-16 | Z | 2024-04-30 | 70 | 60 | 70 | F | 0 | 230 |  |  |  | 16
2024-05-15 | 813 | sp | L2-A-EAD-061 | A | DONE | 7 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 20 | 140 | 0 |  | 0 | 200 |  |  |  | 16
2024-05-15 | 814 |  | L2-A-SALP-0100 | A | DONE | 6 | S-M | neal | CDIS 6220028 | 1" liner , paint | 2024-05-16 | Z | 2024-04-30 | 90 | 0 | 60 | F | 20 | 180 |  |  |  | 16
2024-05-15 | 815 | bth | L2-A-SALP-0101 | A | DONE | 14 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-16 | Z | 2024-04-30 | 130 | 140 | 70 | F | 30 | 400 |  |  |  | 16
2024-05-15 | 816 |  | L2-A-SALP-0102 | A | DONE | 4 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-16 | Z | 2024-04-30 | 80 | 0 | 0 |  | 20 | 90 |  |  |  | 16
2024-05-15 | 817 | bth | L2-A-SALP-0103 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-04-30 | 100 | 20 | 70 | F | 0 | 220 |  |  |  | 16
2024-05-14 | 818 |  | L3-A-STAIR-3-RISER-100 | A | DONE | 24 | M-L |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-05-01 | 110 | 0 | 490 | F | 0 | 1040 |  |  |  | 15
2024-05-13 | 830 | sp | 68501 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-05-07 | 60 | 0 | 0 |  | 0 | 80 |  | 2nd Floor |  | 7
2024-05-14 | 831 |  | Hand Drawn | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-05-08 | 30 | 0 | 0 |  | 0 | 60 |  | Splitter vanes |  | 8
2024-05-13 | 832 | sp | 69864 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-05-16 | Z | 2024-05-09 | 20 | 0 | 0 |  | 0 | 20 |  | SALP-023 |  | 7
2024-05-13 | 833 |  | 69865 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-16 | Z | 2024-05-09 | 20 | 0 | 0 |  | 0 | 20 |  | Test Heto |  | 7
2024-05-16 | 842 |  | 69502 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-05-21 | Z | 2024-05-15 | 100 | 0 | 0 |  | 0 | 150 |  | Flashing |  | 6
2024-05-16 | 843 |  | 59490 | A | DONE | 2 | S | pt.neal | CDIS 6220028 | 1" s. accu | 2024-05-17 | Z | 2024-05-15 | 20 | 30 | 0 |  | 20 | 50 |  | 3rd floor |  | 2
2024-05-14 | 3630 | sp | L4-A-EALP-015 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 30 | 120 | 0 |  | 0 | 160 |  |  |  | 42
2024-05-14 | 3631 | bth | L4-A-EALP-022 | A | DONE | 2 | S-M | neal | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 30 | 20 | 0 |  | 0 | 60 |  |  |  | 42
2024-05-13 | 3632 | sp | L4-A-EALP-060 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 42
2024-05-14 | 3633 | sp | L4-A-EALP-061 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 42
2024-05-13 | 3634 | sp | L4-A-EALP-062 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 42
2024-05-13 | 3635 | sp | L4-A-EALP-063 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 30 | 40 | 0 |  | 0 | 60 |  |  |  | 42
2024-05-14 | 3636 | bth | L4-A-EALP-064 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 60 | 30 | 0 |  | 0 | 100 |  |  |  | 42
2024-05-13 | 3638 | bth | L4-A-SALP-018 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 60 | 80 | 0 |  | 20 | 160 |  |  |  | 42
2024-05-14 | 3639 | bth | L4-A-SALP-021 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 50 | 70 | 20 | F | 0 | 180 |  |  |  | 42
2024-05-14 | 3640 | bth | L4-A-SALP-059 | A | DONE | 4 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 70 | 30 | 0 |  | 20 | 120 |  |  |  | 42
2024-05-13 | 3641 | bth | L4-A-SALP-062 | A | DONE | 5 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 90 | 20 | 0 |  | 30 | 150 |  |  |  | 42
2024-05-13 | 3643 | bth | L4-A-SALP-072 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 50 | 80 | 0 |  | 20 | 130 |  |  |  | 42
2024-05-13 | 3644 |  | L4-A-SALP-077 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 | 1" liner , paint | 2024-05-14 | Z | 2024-04-02 | 160 | 20 | 50 | F | 50 | 260 |  |  |  | 42
2024-05-13 | 3645 | bth | L4-A-SALP-078 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 90 | 20 | 0 |  | 40 | 120 |  |  |  | 42
2024-05-13 | 3646 | bth | L4-A-SALP-079 | A | DONE | 3 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 50 | 20 | 0 |  | 20 | 70 |  |  |  | 42
2024-05-13 | 3647 | bth | L4-A-SALP-080 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 40 | 100 | 0 |  | 20 | 140 |  |  |  | 42
2024-05-14 | 3648 | bth | L4-A-SALP-081 | A | DONE | 3 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 40 | 20 | 0 |  | 20 | 70 |  |  |  | 42
2024-05-14 | 3649 | bth | L4-A-SALP-082 | A | DONE | 4 | S-M | neal | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 30 | 50 | 0 |  | 20 | 90 |  |  |  | 42
2024-05-13 | 3650 | bth | L4-A-SALP-083 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 42
2024-05-13 | 3652 | bth | L4-A-SALP-085 | A | DONE | 7 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 90 | 20 | 50 | F | 20 | 180 |  |  |  | 42
2024-05-13 | 3653 | sp | L4-A-SALP-086 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-05-14 | Z | 2024-04-02 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 42
2024-05-13 | 3654 | bth | L4-A-SALP-087 | A | DONE | 7 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 110 | 30 | 30 | F | 20 | 180 |  |  |  | 42
2024-05-14 | 3655 | bth | L4-A-SALP-088 | A | DONE | 7 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 50 | 110 | 0 |  | 0 | 180 |  |  |  | 42
2024-05-13 | 3656 | bth | L4-A-SALP-089 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 50 | 50 | 0 |  | 20 | 120 |  |  |  | 42
2024-05-13 | 3657 | bth | L4-A-SALP-090 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-14 | Z | 2024-04-02 | 40 | 50 | 0 |  | 20 | 90 |  |  |  | 42
2024-05-13 | 819a |  | NC-RAD-001 | A | DONE | 20 | M-L |  | CDIS 6220028 | partial 3-5 floors | 2024-05-16 | Z | 2024-05-01 | 80 | 0 | 400 | F | 0 | 1010 |  |  |  | 15
2024-05-13 | 821a |  | NC-SAMP-001 | A | DONE | 20 | M-L |  | CDIS 6220028 | partial 3-5 floors | 2024-05-16 | Z | 2024-05-01 | 80 | 0 | 400 | F | 0 | 1000 |  |  |  | 15
2024-05-16 | 179 |  | 79757 | A | DONE | 6 | S-M |  | COMPASS HIGH 4230088 | paint | 2024-05-17 | Z | 2024-05-13 | 130 | 0 | 0 |  | 120 | 270 |  | TA |  | 4
2024-05-14 | 1581 |  | 62381 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 | paint | 2024-05-16 | Z | 2024-05-13 | 20 | 0 | 0 |  | 20 | 20 |  | Ceiling misc |  | 3
2024-05-14 | 1582 |  | 70582 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 | VD's | 2024-05-14 | Z | 2024-05-13 | 60 | 0 | 0 |  | 0 | 80 |  | Damper |  | 1
2024-05-16 | 1583 |  | 62383 | A | DONE | 2 | S | ss | EMBASSY SUITES 6220012 | birdscreen | 2024-05-17 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 30 |  | Ex. caps |  | 2
2024-05-16 | 1584 |  | 62384 | A | DONE | 2 | S | alum | EMBASSY SUITES 6220012 |  | 2024-05-17 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | Dryer vent - removable |  | 2
2024-05-18 | 2560 |  | 56685 | A | DONE | 2 | S |  | EXACT BIO 6230004 | birdscreen | 2024-05-21 | Z | 2024-05-03 | 20 | 0 | 0 |  | 0 | 20 |  | Cap |  | 18
2024-05-17 | 4608 |  | 69418 | A | DONE | 2 | S |  | HARMONICS 6240010 |  | 2024-05-20 | Z | 2024-05-14 | 20 | 0 | 0 |  | 0 | 40 |  | Kitchen |  | 6
2024-05-17 | 4609 |  | 69419 | A | DONE | 2 | S |  | HARMONICS 6240010 | flex | 2024-05-20 | Z | 2024-05-15 | 0 | 0 | 0 |  | 0 | 0 |  | Misc |  | 5
2024-05-16 | 2297 |  | 69331 | A | DONE | 6 | S |  | HERITAGE 6220024 |  | 2024-05-17 | Z | 2024-05-08 | 60 | 0 | 70 | F | 0 | 160 |  | Elevator EA |  | 9
2024-05-15 | 2298 | sp | 69332 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-05-17 | Z | 2024-05-09 | 20 | 30 | 0 |  | 0 | 50 |  | Hood tie in |  | 8
2024-05-16 | 2952 |  | 69257 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-05-17 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | Dryer sleeve |  | 2
2024-05-17 | 2953 |  | 69258 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-05-20 | Z | 2024-05-16 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 4
2024-05-15 | 2821 |  | 78555 | A | DONE | 8 | S-M |  | JANESVILLE ESSR 6230011 | 2" liner | 2024-05-16 | Z | 2024-04-15 | 30 | 0 | 160 | F | 150 | 230 |  | BCU-1 SA |  | 31
2024-05-14 | 2825 |  | 78571 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-05-16 | Z | 2024-05-06 | 20 | 0 | 0 |  | 0 | 20 |  | Pool duct |  | 10
2024-05-15 | 2826 | bth | 78573 - 78575 | A | DONE | 9 | S-M | alum | JANESVILLE ESSR 6230011 | VD's | 2024-05-16 | Z | 2024-05-06 | 130 | 90 | 0 |  | 0 | 120 |  | Pool duct |  | 10
2024-05-16 | 3732 | w | 55190 | A | DONE | 2 | S | BI | KOHL CENTER 6210034 | shut down | 2024-05-20 | Z | 2024-05-14 | 40 | 0 | 0 |  | 0 | 170 |  | Grease duct |  | 6
2024-05-16 | 3733 | sp | 55191 | A | DONE | 3 | S |  | KOHL CENTER 6210034 | shut down | 2024-05-20 | Z | 2024-05-14 | 30 | 30 | 0 |  | 0 | 80 |  | EA |  | 6
2024-05-13 | 1114 |  | 72920 , 72923 | A | DONE | 3 | S |  | LABCORP 6240011 |  | 2024-05-15 | Z | 2024-05-07 | 60 | 0 | 0 |  | 0 | 80 |  | EAV-109 |  | 8
2024-05-13 | 1115 |  | 72921 - 72922 | A | DONE | 3 | S |  | LABCORP 6240011 |  | 2024-05-15 | Z | 2024-05-07 | 60 | 0 | 0 |  | 0 | 80 |  | EAV-110A/B |  | 8
2024-05-18 | 2165 |  | 68601 | A | DONE | 4 | S | alum | MEMORIAL HS 6210024 |  | 2024-05-21 | Z | 2024-05-08 | 80 | 0 | 0 |  | 0 | 90 |  | Pool Mech Rm. |  | 13
2024-05-14 | 2167 | bth | 68587 - 68588 | A | DONE | 4 | S-M |  | MEMORIAL HS 6210024 |  | 2024-05-14 | Z | 2024-05-13 | 80 | 20 | 0 |  | 0 | 100 |  | Locker Rm outs |  | 1
2024-05-14 | 2162a | w | 68582 | A | DONE | 2 | S-M | ss | MEMORIAL HS 6210024 | partial | 2024-05-15 | Z | 2024-05-02 | 30 | 0 | 0 |  | 0 | 130 |  | Concessions |  | 13
2024-05-14 | 3841 |  | 67528 | A | DONE | 11 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-05-16 | Z | 2024-05-07 | 150 | 0 | 110 | F | 0 | 340 |  | 1st Floor |  | 9
2024-05-14 | 3842 |  | 67529 - 67530 | A | DONE | 26 | S-M |  | MENDOTA FOODS 6220027 | 1" liner | 2024-05-16 | Z | 2024-05-07 | 420 | 0 | 210 | F | 500 | 740 |  | 1st Floor TA |  | 9
2024-05-13 | 3843 |  | 67531 - 67532 | A | DONE | 8 | S-M | pt.alum | MENDOTA FOODS 6220027 |  | 2024-05-16 | Z | 2024-05-07 | 180 | 0 | 20 | F | 0 | 210 |  | 1st Floor / Misc |  | 9
2024-05-14 | 3844 |  | 67533 - 67534 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | VD | 2024-05-16 | Z | 2024-05-09 | 50 | 0 | 0 |  | 0 | 90 |  | Tie-ins / Janitor |  | 7
2024-05-14 | 3846 |  | 67538 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-05-15 | Z | 2024-05-14 | 30 | 0 | 0 |  | 0 | 50 |  | Flashing |  | 1
2024-05-15 | 178 |  | 69808 | A | DONE | 3 | S | alum | MSN 2240006 |  | 2024-05-17 | Z | 2024-05-13 | 30 | 0 | 0 |  | 0 | 30 |  | DR-5 |  | 4
2024-05-17 | 2630 |  | 79501 | A | DONE | 2 | S | neal | OLIV 6210030 | flex | 2024-05-20 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | L2 |  | 5
2024-05-16 | 2631 |  | 79503 | A | DONE | 2 | S |  | OLIV 6210030 | paint | 2024-05-20 | Z | 2024-05-15 | 20 | 0 | 0 |  | 20 | 20 |  | Study rooms |  | 5
2024-05-16 | 4506 | bth | LL-SALP-47 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 30 |  |  | Semi 9 | 80
2024-05-16 | 4507 | bth | LL-SALP-48 | A | DONE | 11 | S-M |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 50 | 210 | 0 |  | 0 | 300 |  |  | Semi 9 | 80
2024-05-17 | 4508 | bth | LL-SALP-49 | A | DONE | 11 | S-M |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 50 | 210 | 0 |  | 0 | 300 |  |  | Semi 9 | 80
2024-05-16 | 4509 | bth | LL-SALP-50 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 30 |  |  | Semi 9 | 80
2024-05-16 | 4510 |  | LL-SALP-51 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 9 | 80
2024-05-16 | 4511 |  | LL-SALP-51A | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 9 | 80
2024-05-16 | 4512 | bth | LL-SALP-52 | A | DONE | 10 | S-M |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 50 | 190 | 0 |  | 0 | 280 |  |  | Semi 9 | 80
2024-05-16 | 4513 | bth | LL-SALP-53 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 30 |  |  | Semi 9 | 80
2024-05-17 | 4514 | bth | LL-SALP-54 | A | DONE | 11 | S-M |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 50 | 210 | 0 |  | 0 | 300 |  |  | Semi 9 | 80
2024-05-17 | 4515 | bth | LL-SALP-55 | A | DONE | 11 | S-M |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 50 | 210 | 0 |  | 0 | 300 |  |  | Semi 9 | 80
2024-05-16 | 4516 | bth | LL-SALP-56 | A | DONE | 3 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 50 | 0 |  | 0 | 70 |  |  | Semi 9 | 80
2024-05-16 | 4517 |  | LL-SALP-57 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 9 | 80
2024-05-16 | 4518 |  | LL-SALP-57A | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 9 | 80
2024-05-16 | 4519 |  | LL-SALP-58 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 9 | 80
2024-05-16 | 4520 |  | LL-SALP-59 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 20 |  |  | Semi 9 | 80
2024-05-16 | 4521 | bth | LL-SALP-60 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 50 |  |  | Semi 9 | 80
2024-05-17 | 4522 | bth | LL-SALP-61 | A | DONE | 11 | S-M |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 50 | 210 | 0 |  | 0 | 300 |  |  | Semi 9 | 80
2024-05-16 | 4523 | bth | LL-SALP-62 | A | DONE | 6 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 40 | 90 | 0 |  | 0 | 150 |  |  | Semi 9 | 80
2024-05-17 | 4524 | bth | LL-SALP-63 | A | DONE | 3 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 50 | 0 |  | 0 | 80 |  |  | Semi 9 | 80
2024-05-16 | 4525 | bth | LL-SALP-64 | A | DONE | 4 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 60 | 0 |  | 0 | 100 |  |  | Semi 9 | 80
2024-05-16 | 4526 | bth | LL-SALP-65 | A | DONE | 3 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 40 | 0 |  | 0 | 70 |  |  | Semi 9 | 80
2024-05-16 | 4527 | bth | LL-SALP-66 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 20 |  |  | Semi 9 | 80
2024-05-17 | 4528 | bth | LL-SALP-67 | A | DONE | 12 | S-M |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 80 | 220 | 0 |  | 0 | 340 |  |  | Semi 9 | 80
2024-05-16 | 4529 | bth | LL-SALP-68 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 0 | 0 |  | 0 | 30 |  |  | Semi 9 | 80
2024-05-16 | 4530 | bth | LL-SALP-69 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 30 |  |  | Semi 9 | 80
2024-05-16 | 4531 | bth | LL-SALP-70 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 40 |  |  | Semi 9 | 80
2024-05-16 | 4532 | bth | LL-SALP-71 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-02-27 | 20 | 20 | 0 |  | 0 | 40 |  |  | Semi 9 | 80
2024-05-16 | 4544 |  | 72382 | A | DONE | 4 | S |  | RAMC 6230009 |  | 2024-05-17 | Z | 2024-05-03 | 100 | 0 | 0 |  | 0 | 210 |  | 1st floor misc |  | 14
2024-05-16 | 4545 | bth | 72383 | A | DONE | 4 | S |  | RAMC 6230009 | VD , bird screen | 2024-05-17 | Z | 2024-05-03 | 60 | 20 | 0 |  | 0 | 110 |  | 1st floor RA / VAV |  | 14
2024-05-14 | 3000 |  | 62527 | A | DONE | 2 | S |  | RETRO CX 6240004 |  | 2024-05-16 | Z | 2024-05-10 | 20 | 0 | 0 |  | 0 | 20 |  | MD AHU-1,4 |  | 6
2024-05-14 | 4753 |  | 78882 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 | paint | 2024-05-16 | Z | 2024-05-09 | 40 | 0 | 0 |  | 40 | 60 |  | Misc |  | 7
2024-05-17 | 4684 |  | 70331 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-05-20 | Z | 2024-05-03 | 30 | 0 | 0 |  | 0 | 30 |  | Beam offset |  | 17
2024-05-14 | 4682 |  | 70327 | A | DONE | 6 | S-M |  | ST.BERNARD 6230023 |  | 2024-05-16 | Z | 2024-05-02 | 150 | 0 | 0 |  | 0 | 220 |  | AHU-2 SA |  | 14
2024-05-15 | 4683 |  | 70328 - 70329 | A | DONE | 21 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-05-16 | Z | 2024-05-02 | 230 | 0 | 290 | F | 420 | 620 |  | AHU-2 SA |  | 14
2024-05-16 | 4685 | bth | 70332 | A | DONE | 4 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-05-20 | Z | 2024-05-09 | 70 | 20 | 0 |  | 20 | 100 |  | VAV-2 outs |  | 11
2024-05-14 | 176 | sp | 78729 | A | DONE | 2 | S-M |  | THERMO FISHER 10055296 |  | 2024-05-15 | Z | 2024-05-10 | 20 | 20 | 0 |  | 0 | 20 |  | Lab 4112 |  | 5
2024-05-13 | 175 | bth | 70226 - 70227 | A | DONE | 8 | S-M |  | TST 4240017 | VD's , birdscreen | 2024-05-14 | Z | 2024-05-10 | 100 | 80 | 0 |  | 0 | 180 |  | HP SA |  | 4
2024-05-16 | 2016 |  | 79251 - 79252 | A | DONE | 3 | S-M |  | UW-GRAFF 6230017 |  | 2024-06-03 | Z | 2024-05-09 | 60 | 0 | 0 |  | 0 | 120 |  | End Caps |  | 25 |  | 2024-05-20
2024-05-16 | 3978 |  | 70116 | A | DONE | 6 | S-M |  | UWRF 6230010 |  | 2024-05-22 | Z | 2024-05-07 | 140 | 0 | 0 |  | 0 | 380 |  | Shaft 194N |  | 15
2024-05-18 | 4862 | bth | L3Z1-FEMP-2 | A | DONE | 11 | S-M | pcd | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 170 | 20 | 80 | F | 0 | 320 |  |  | L3 Zone 1 A/B | 55
2024-05-18 | 4863 | bth | L3Z1-FEMP-3 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 90 | 20 | 0 |  | 0 | 130 |  |  | L3 Zone 1 A/B | 55
2024-05-18 | 4865 | bth | L3Z1-FEMP-5 | A | DONE | 8 | S | pcd | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 70 | 50 | 80 | F | 0 | 240 |  |  | L3 Zone 1 A/B | 55
2024-05-17 | 4867 | bth | L3Z1-FEMP-7 | A | DONE | 19 | M | pcd | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 190 | 90 | 190 | F | 0 | 730 |  |  | L3 Zone 1 A/B | 55
2024-05-18 | 4875 |  | L3Z1-RAMP-1 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 100 | 0 | 30 | F | 0 | 150 |  |  | L3 Zone 1 A/B | 55
2024-05-18 | 4876 |  | L3Z1-RAMP-2 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 70 | 0 | 120 | F | 0 | 230 |  |  | L3 Zone 1 A/B | 55
2024-05-18 | 4877 |  | L3Z1-RAMP-3 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 50 | 0 | 140 | F | 0 | 230 |  |  | L3 Zone 1 A/B | 55
2024-05-18 | 4878 |  | L3Z1-RAMP-4 | A | DONE | 5 | S | pt.neal | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 60 | 0 | 60 | F | 0 | 140 |  |  | L3 Zone 1 A/B | 55
2024-05-18 | 4879 | bth | L3Z1-RAMP-5 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 90 | 20 | 120 | F | 0 | 260 |  |  | L3 Zone 1 A/B | 55
2024-05-18 | 4880 |  | L3Z2-RAMP-6 | A | DONE | 12 | S-M | neal | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 80 | 0 | 210 | F | 0 | 370 |  |  | L3 Zone 1 A/B | 55
2024-05-17 | 4881 | bth | L3Z2-RAMP-7 | A | DONE | 10 | S-M | pt.neal | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 160 | 30 | 60 | F | 0 | 300 |  |  | L3 Zone 2 A/B | 55
2024-05-17 | 4882 | bth | L3Z2-RAMP-8 | A | DONE | 11 | S-M | neal | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 40 | 20 | 200 | F | 0 | 320 |  |  | L3 Zone 2 A/B | 55
2024-05-17 | 4883 |  | L3Z2-RAMP-9 | A | DONE | 10 | S-M | neal | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 20 | 210 | 0 |  | 0 | 270 |  |  | L3 Zone 2 A/B | 55
2024-05-17 | 4884 | bth | L3Z2-RAMP-10 | A | DONE | 8 | S-M | neal | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 140 | 30 | 30 | F | 0 | 250 |  |  | L3 Zone 2 A/B | 55
2024-05-17 | 4891 | bth | L3Z2-EAMP-7 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 30 | 80 | 70 | F | 0 | 190 |  |  | L3 Zone 2 A/B | 55
2024-05-17 | 4892 | sp | L3Z2-EAMP-8 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 30 | 80 | 0 |  | 0 | 110 |  |  | L3 Zone 2 A/B | 55
2024-05-17 | 4893 | bth | L3Z2-EAMP-9 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 140 | 20 | 130 | F | 0 | 400 |  |  | L3 Zone 2 A/B | 55
2024-05-17 | 4894 | bth | L3Z2-EAMP-10 | A | DONE | 14 | S-M | pt.neal | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 120 | 20 | 200 | F | 0 | 390 |  |  | L3 Zone 2 A/B | 55
2024-05-14 | 4902 | bth | L3Z1-SAMP-1 | A | DONE | 35 | L |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 290 | 60 | 520 | F | 0 | 1810 |  |  | L3 Zone 1 A/B | 50
2024-05-14 | 4903 | bth | L3Z1-SAMP-2 | A | DONE | 27 | M-L |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 330 | 40 | 300 | F | 0 | 1260 |  |  | L3 Zone 1 A/B | 50
2024-05-14 | 4904 | bth | L3Z1-SAMP-3 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 100 | 50 | 180 | F | 0 | 500 |  |  | L3 Zone 1 A/B | 50
2024-05-14 | 4907 | bth | L3Z1-SAMP-6 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 70 | 40 | 70 | F | 0 | 210 |  |  | L3 Zone 1 A/B | 50
2024-05-14 | 4908 | bth | L3Z1-SAMP-7 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 50 | 80 | 0 |  | 0 | 130 |  |  | L3 Zone 1 A/B | 50
2024-05-14 | 4909 | bth | L3Z1-SAMP-8 | A | DONE | 42 | L |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 710 | 20 | 300 | F | 0 | 2220 |  |  | L3 Zone 1 A/B | 50
2024-05-14 | 4910 | bth | L3Z1-SAMP-9 | A | DONE | 26 | M-L |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 240 | 30 | 370 | F | 0 | 1070 |  |  | L3 Zone 1 A/B | 50
2024-05-14 | 4911 | bth | L3Z1-SAMP-10 | A | DONE | 24 | M-L |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 280 | 50 | 260 | F | 0 | 1190 |  |  | L3 Zone 1 A/B | 50
2024-05-14 | 4912 |  | L3Z1-SAMP-11 | A | DONE | 20 | M-L |  | UWRF 6230010 |  | 2024-05-15 | Z | 2024-03-26 | 150 | 20 | 310 | F | 0 | 970 |  |  | L3 Zone 1 A/B | 50
2024-05-13 | 5002 |  | 58794 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-05-14 | Z | 2024-04-26 | 50 | 0 | 0 |  | 0 | 90 |  | Parts bin |  | 18
2024-05-17 | 3219 |  | 72433 - 72435 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-05-20 | Z | 2024-05-14 | 20 | 0 | 0 |  | 0 | 20 |  | Pipe cover |  | 6
2024-05-17 | 3220 | w | 72436 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-05-20 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 5
2024-05-16 | 3221 |  | 72437 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-05-20 | Z | 2024-05-15 | 40 | 0 | 0 |  | 0 | 40 |  | 3rd |  | 5
2024-05-18 | 3222 | w | 72438 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-05-22 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | BSL-TA |  | 7
2024-05-15 | 180 |  | 51524 - 51525 | A | DONE | 2 | S-M | BI | WINDSOR MUNICIPAL 6240012 |  | 2024-05-15 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 30 |  | Caps |  | 0
[6 empty] | 1200 | [13 empty] | 38140 |  |  |  | 4030 | 10.57%
WEEK OF 5-20-2024
2024-05-21 | 1751 |  | 68041 | A | DONE | 4 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-05-23 | Z | 2024-05-13 | 80 | 0 | 0 |  | 0 | 120 |  | Flashing |  | 10
2024-05-22 | 820 |  | NC-RAD-002 | A | DONE | 12 | M-L |  | CDIS 6220028 | partial 5-7 floors | 2024-05-23 | Z | 2024-05-01 | 140 | 0 | 160 | F | 0 | 550 |  |  |  | 22
2024-05-22 | 822 |  | NC-SAMP-002 | A | DONE | 11 | M-L |  | CDIS 6220028 | partial 5-7 floors | 2024-05-23 | Z | 2024-05-01 | 140 | 0 | 120 | F | 0 | 480 |  |  |  | 22
2024-05-20 | 834 | bth | L2-B-SALP-036 | A | DONE | 7 | S-M |  | CDIS 6220028 | 1" liner | 2024-05-21 | Z | 2024-05-09 | 90 | 80 | 0 |  | 0 | 180 |  |  |  | 12
2024-05-22 | 835 |  | 69906 | A | DONE | 10 | M |  | CDIS 6220028 | paint | 2024-05-23 | Z | 2024-05-10 | 230 | 0 | 0 |  | 50 | 620 |  | 1st floor louver |  | 13
2024-05-22 | 836 |  | 69907 - 69908 | A | DONE | 7 | S-M |  | CDIS 6220028 | paint | 2024-05-23 | Z | 2024-05-10 | 170 | 0 | 0 |  | 0 | 240 |  | 1st floor grille 1,2,3 |  | 13
2024-05-22 | 837 |  | 69909 - 69910 | A | DONE | 2 | S-M |  | CDIS 6220028 | paint | 2024-05-23 | Z | 2024-05-10 | 50 | 0 | 0 |  | 0 | 70 |  | 1st floor grille 4,5,6,7 |  | 13
2024-05-22 | 838 |  | 69911 - 69912 | A | DONE | 2 | S-M |  | CDIS 6220028 | paint | 2024-05-23 | Z | 2024-05-10 | 40 | 0 | 0 |  | 0 | 60 |  | 1st floor grille 8,9,10,11 |  | 13
2024-05-22 | 839 |  | 69913 | A | DONE | 2 | S-M |  | CDIS 6220028 | paint | 2024-05-23 | Z | 2024-05-10 | 40 | 0 | 0 |  | 0 | 60 |  | 1st floor grille 12,13 |  | 13
2024-05-22 | 840 |  | 69866 - 69867 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-05-28 | Z | 2024-05-13 | 290 | 0 | 0 |  | 0 | 480 |  | Dry wall sleeves 6th-7th |  | 15
2024-05-21 | 841 |  | 69868 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-23 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | B-Basement tie in |  | 8
2024-05-22 | 845 |  | L2-B-TAD-002 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-05-28 | Z | 2024-05-15 | 80 | 0 | 0 |  | 50 | 100 |  |  |  | 13
2024-05-22 | 848 |  | 94258 , 94259 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-05-23 | Z | 2024-05-16 | 40 | 0 | 0 |  | 0 | 100 |  | Angles |  | 7
2024-05-23 | 893 | sp | 59491 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-28 | Z | 2024-05-22 | 20 | 20 | 0 |  | 0 | 20 |  | 3rd floor |  | 6
2024-05-23 | 903 |  | 59492 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-05-28 | Z | 2024-05-23 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor |  | 5
2024-05-22 | 820a |  | NC-RAD-002 | A | DONE | 12 | M-L |  | CDIS 6220028 | partial 7-8 floors | 2024-05-30 | Z | 2024-05-01 | 140 | 0 | 160 | F | 0 | 550 |  |  |  | 29
2024-05-22 | 822a |  | NC-SAMP-002 | A | DONE | 11 | M-L |  | CDIS 6220028 | partial 7-8 floors | 2024-05-30 | Z | 2024-05-01 | 140 | 0 | 120 | F | 0 | 480 |  |  |  | 29
2024-05-20 | r843 |  | 59490 | A | DONE | 2 | S | pt.neal | CDIS 6220028 | 1" s. accu | 2024-05-23 | Z | 2024-05-17 | 20 | 20 | 0 |  | 20 | 50 |  |  |  | 6
2024-05-20 | 2336 |  | 58804 | A | DONE | 2 | S |  | DEWITT 2240019 |  | 2024-05-28 | Z | 2024-05-20 | 20 | 0 | 0 |  | 0 | 20 |  | Reducer |  | 8
2024-05-20 | 1585 |  | 62385 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 |  | 2024-05-23 | Z | 2024-05-20 | 50 | 0 | 0 |  | 0 | 90 |  | Angle |  | 3
2024-05-20 | 4610 |  | hand drawn | A | DONE | 2 | S |  | HARMONICS 6240010 | VD | 2024-05-20 | Z | 2024-05-20 | 20 | 0 | 0 |  | 0 | 20 |  | Volume damper |  | 0
2024-05-22 | 2299 |  | 69333 - 69335 | A | DONE | 13 | S-M |  | HERITAGE 6220024 | paint | 2024-05-24 | Z | 2024-05-14 | 320 | 0 | 0 |  | 0 | 350 |  | HP-RA , D-Section |  | 10
2024-05-22 | 2950 |  | 69336 - 69337 | A | DONE | 2 | S-M |  | HERITAGE 6220024 |  | 2024-05-24 | Z | 2024-05-14 | 50 | 0 | 0 |  | 0 | 60 |  | HP-RA |  | 10
2024-05-22 | 2951 |  | 69338 - 69339 | A | DONE | 4 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-05-24 | Z | 2024-05-14 | 90 | 0 | 0 |  | 60 | 110 |  | HP-RA , D-Section TA |  | 10
2024-05-22 | 2954 |  | 69050 | A | DONE | 5 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-05-24 | Z | 2024-05-20 | 120 | 0 | 0 |  | 60 | 150 |  | 1st floor RA |  | 4
2024-05-22 | 2955 |  | 69259 | A | DONE | 2 | S-M |  | HERITAGE 6220024 | flex , bird s. | 2024-05-24 | Z | 2024-05-20 | 50 | 0 | 0 |  | 0 | 70 |  | EF-1 |  | 4
2024-05-21 | 2956 |  | 69261 | A | DONE | 2 | S |  | HERITAGE 6220024 | foam gasket | 2024-05-22 | Z | 2024-05-20 | 20 | 0 | 0 |  | 20 | 20 |  | EX fan |  | 2
2024-05-22 | 2957 |  | 69262 | A | DONE | 2 | S |  | HERITAGE 6220024 | paint | 2024-05-24 | Z | 2024-05-21 | 20 | 0 | 0 |  | 0 | 20 |  | Prep room |  | 3
2024-05-21 | 2827 | bth | 78576 - 78578 | A | DONE | 12 | S-M |  | JANESVILLE ESSR 6230011 | 2" liner | 2024-05-23 | Z | 2024-05-08 | 110 | 60 | 110 | F | 150 | 310 |  | VAV 59 |  | 15
2024-05-21 | 2828 | bth | 78580 , 78585 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-05-23 | Z | 2024-05-08 | 20 | 20 | 0 |  | 0 | 40 |  | VAV 61 |  | 15
2024-05-21 | 2829 | bth | 78581 , 78583 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-05-23 | Z | 2024-05-08 | 30 | 20 | 0 |  | 0 | 50 |  | VAV 62 |  | 15
2024-05-21 | 2830 |  | 78584 , 78592 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-05-23 | Z | 2024-05-08 | 30 | 0 | 0 |  | 0 | 40 |  | VAV 60 |  | 15
2024-05-21 | 2831 | bth | 78586 - 78587 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-05-23 | Z | 2024-05-08 | 20 | 20 | 0 |  | 0 | 20 |  | VAV 63 |  | 15
2024-05-21 | 2832 |  | 78589 - 78590 | A | DONE | 11 | S-M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-05-23 | Z | 2024-05-08 | 150 | 0 | 120 | F | 220 | 380 |  | Cafeteria / Corridor 300A |  | 15
2024-05-21 | 2833 | bth | 78594 - 78596 | A | DONE | 8 | S-M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-05-23 | Z | 2024-05-08 | 30 | 140 | 30 | F | 30 | 190 |  | Misc |  | 15
2024-05-21 | 2835 |  | 78614 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-05-23 | Z | 2024-05-14 | 40 | 0 | 0 |  | 0 | 30 |  | Pool RA |  | 9
2024-05-22 | 2836 |  | 78651 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-05-30 | Z | 2024-05-16 | 20 | 0 | 0 |  | 0 | 20 |  | Pool EA |  | 14
2024-05-20 | 2907 |  | 72927 | A | DONE | 4 | S-M |  | LABCORP 6240011 | 1" liner | 2024-05-21 | Z | 2024-05-13 | 100 | 0 | 0 |  | 80 | 100 |  | TA |  | 8
2024-05-20 | 2166 |  | 68602 - 68603 | A | DONE | 14 | S-M |  | MEMORIAL HS 6210024 |  | 2024-05-21 | Z | 2024-05-08 | 350 | 0 | 0 |  | 0 | 1050 |  | Pool Mech Rm. |  | 13
2024-05-23 | 2168 |  | 68586 | A | DONE | 5 | S-M |  | MEMORIAL HS 6210024 | 1" liner | 2024-05-28 | Z | 2024-05-13 | 120 | 0 | 0 |  | 100 | 330 |  | RTU-D2 SA |  | 15
2024-05-22 | 2169 |  | 68604 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-05-28 | Z | 2024-05-15 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 13
2024-05-22 | 1420 |  | 67545 - 67547 | A | DONE | 3 | S-M | alum | MENDOTA FOODS 6220027 | paint | 2024-05-23 | Z | 2024-05-20 | 70 | 0 | 0 |  | 0 | 100 |  | Basement finishes |  | 3
2024-05-22 | 1421 |  | 67535 , 57537 | A | DONE | 10 | S-M |  | MENDOTA FOODS 6220027 | 1" liner | 2024-05-23 | Z | 2024-05-20 | 190 | 0 | 40 | F | 40 | 300 |  | 1st floor RA / SA / TA |  | 3
2024-05-21 | 3847 |  | 67539 - 67540 | A | DONE | 22 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-05-23 | Z | 2024-05-17 | 120 | 0 | 430 | F | 0 | 720 |  | Chase RA/SA |  | 6
2024-05-22 | 3848 |  | 67542 | A | DONE | 5 | S | alum | MENDOTA FOODS 6220027 |  | 2024-05-23 | Z | 2024-05-17 | 60 | 0 | 50 | F | 0 | 80 |  | EA Chase |  | 6
2024-05-22 | 3849 |  | 67543 - 67544 | A | DONE | 5 | S-M |  | MENDOTA FOODS 6220027 | paint ,1" liner | 2024-05-23 | Z | 2024-05-20 | 110 | 0 | 0 |  | 50 | 160 |  | Basement finishes |  | 3
2024-05-21 | 3845 |  | 96900 - 96901 | A | DONE | 2 | S | ss | MENDOTA FOODS 8220036 |  | 2024-05-28 | Z | 2024-05-13 | 20 | 0 | 0 |  | 0 | 70 |  | Plates |  | 15
2024-05-21 | 181 | w | 78730 | A | DONE | 2 | S | ss | PERENNIAL YOGA 10055725 |  | 2024-05-22 | Z | 2024-05-20 | 20 | 0 | 0 |  | 0 | 20 |  | SS drain pan |  | 2
2024-05-20 | 1802 | sp | LO-EA-01 | A | DONE | 8 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 40 | 140 | 0 |  | 0 | 200 |  |  |  | 9
2024-05-20 | 1803 | sp | LO-EA-02 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 9
2024-05-20 | 1804 | sp | LO-EA-03 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 9
2024-05-20 | 1805 | sp | LO-EA-04 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 9
2024-05-21 | 1806 | sp | LO-EA-05 | A | DONE | 12 | S-M |  | PROMEGA BTC 6230022 | s.mates | 2024-05-22 | Z | 2024-05-13 | 70 | 210 | 0 |  | 0 | 350 |  |  |  | 9
2024-05-21 | 1807 | sp | LO-EAMP-01 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 30 | 20 | 0 |  | 0 | 60 |  |  |  | 9
2024-05-20 | 1808 | sp | LO-EAMP-02 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 9
2024-05-20 | 1809 | sp | LO-EAMP-03 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 9
2024-05-20 | 1810 | sp | LO-EAMP-04 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 9
2024-05-21 | 1811 |  | LO-EAMP-05 | A | DONE | 3 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 9
2024-05-23 | 1813 |  | LO-RA-01 | A | DONE | 52 | M-L |  | PROMEGA BTC 6230022 |  | 2024-05-29 | Z | 2024-05-13 | 250 | 0 | 1030 | F | 0 | 2090 |  |  |  | 16
2024-05-21 | 1814 | bth | LO-SALP-01 | A | DONE | 7 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 80 | 90 | 0 |  | 0 | 190 |  |  |  | 9
2024-05-21 | 1815 | bth | LO-SALP-02 | A | DONE | 3 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 40 | 30 | 0 |  | 0 | 80 |  |  |  | 9
2024-05-20 | 1816 | sp | LO-SALP-03 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 9
2024-05-20 | 1817 | sp | LO-SALP-04 | A | DONE | 9 | S-M |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 50 | 160 | 0 |  | 0 | 230 |  |  |  | 9
2024-05-21 | 1818 | bth | LO-SAMP-01 | A | DONE | 34 | M-L |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-13 | 340 | 50 | 440 | F | 0 | 1060 |  |  |  | 9
2024-05-21 | 1819 | bth | LO-SAMP-02 | A | DONE | 32 | M |  | PROMEGA BTC 6230022 | s.mates | 2024-05-22 | Z | 2024-05-16 | 280 | 240 | 270 | F | 0 | 1220 |  |  |  | 6
2024-05-21 | 1820 |  | 56281 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2024-05-22 | Z | 2024-05-17 | 80 | 0 | 0 |  | 0 | 100 |  | Misc |  | 5
2024-05-23 | 4546 | sp | 72384 | A | DONE | 8 | S-M |  | RAMC 6230009 | oval , accuflange | 2024-05-28 | Z | 2024-05-14 | 70 | 50 | 60 | F | 0 | 220 |  | LL/L1 outs |  | 14
2024-05-24 | 4547 |  | 72385 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-05-28 | Z | 2024-05-23 | 20 | 0 | 0 |  | 0 | 30 |  | Gnd floor SA |  | 5
2024-05-21 | 4754 | sp | 61198 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-05-23 | Z | 2024-05-15 | 40 | 0 | 0 |  | 0 | 40 |  | Max security |  | 8
2024-05-21 | 4755 |  | 78883 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 | paint | 2024-05-23 | Z | 2024-05-16 | 20 | 0 | 0 |  | 20 | 40 |  | Jail |  | 7
2024-05-21 | 4756 |  | 61160 - 61161 | A | DONE | 9 | S |  | ROCK CO. JAIL 6220018 | flex | 2024-05-23 | Z | 2024-05-17 | 210 | 0 | 0 |  | 0 | 320 |  | Misc |  | 6
2024-05-21 | 4757 |  | 78884 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 | bird screen | 2024-05-23 | Z | 2024-05-17 | 20 | 0 | 0 |  | 0 | 20 |  | Jail Admin |  | 6
2024-05-20 | 4752 |  | 33242 | A | DONE | 2 | S | d.plate | ROCK CO. JAIL 8220022 |  | 2024-05-22 | Z | 2024-05-08 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 14
2024-05-23 | 4687 |  | 70344 | A | DONE | 3 | S-M |  | ST.BERNARD 2230056 | 1" liner | 2024-05-28 | Z | 2024-05-15 | 70 | 0 | 0 |  | 70 | 80 |  | F-7 RA |  | 13
2024-05-23 | 4688 |  | 70346 - 70347 | A | DONE | 8 | S-M |  | ST.BERNARD 2230056 | 1" liner | 2024-05-28 | Z | 2024-05-15 | 180 | 0 | 0 |  | 170 | 260 |  | F-6 RA / SA |  | 13
2024-05-23 | 4686 |  | 70333 | A | DONE | 2 | S |  | ST.BERNARD 6230023 | flex | 2024-05-28 | Z | 2024-05-15 | 20 | 0 | 0 |  | 20 | 30 |  | RF-4 |  | 13
2024-05-23 | 4693 |  | 79902 | A | DONE | 8 | S |  | ST.BERNARD 6230023 | 1" liner | 2024-05-28 | Z | 2024-05-22 | 60 | 0 | 120 | F | 130 | 200 |  | Crawl space |  | 6
2024-05-22 | 273 | bth | 79614 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-05-28 | Z | 2024-03-20 | 30 | 20 | 0 |  | 0 | 50 |  | PACU 1321 RA |  | 69 |  | 2024-05-27 | 2024-04-22 | 2024-06-24
2024-05-21 | 4550 |  | 6424 | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2024-05-21 | Z | 2024-05-21 | 20 | 0 | 0 |  | 0 | 50 |  | Ring |  | 0
2024-05-20 | 3968 |  | L2Z1-RAMP-PLENUM | A | DONE | 20 | M |  | UWRF 6230010 | birdscreen , CD's | 2024-05-22 | Z | 2024-05-07 | 430 | 0 | 70 | F | 20 | 830 |  |  |  | 15
2024-05-20 | 3969 |  | SHAFT-194N-EAMP | A | DONE | 49 | L |  | UWRF 6230010 |  | 2024-05-22 | Z | 2024-05-07 | 660 | 0 | 560 | F | 0 | 2650 |  |  |  | 15
2024-05-21 | 3970 |  | SHAFT-194N-FAMP | A | DONE | 40 | L | pcd | UWRF 6230010 |  | 2024-05-22 | Z | 2024-05-07 | 620 | 0 | 360 | F | 0 | 2050 |  |  |  | 15
2024-05-21 | 3971 |  | SHAFT-194N-RAMP | A | DONE | 32 | M-L |  | UWRF 6230010 |  | 2024-05-22 | Z | 2024-05-07 | 500 | 0 | 290 | F | 0 | 1330 |  |  |  | 15
2024-05-23 | 3981 | bth | L3Z2-FEMP-13 | A | DONE | 12 | S-M | pcd | UWRF 6230010 |  | 2024-05-28 | Z | 2024-05-08 | 70 | 50 | 170 | F | 0 | 360 |  |  | L3 Zone 2 C | 20 |  | 2024-06-03
2024-05-20 | 4085 |  | 73400 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-05-22 | Z | 2024-05-16 | 20 | 0 | 0 |  | 0 | 20 |  | Duct testing |  | 6
2024-05-23 | 4086 |  | 73399 | A | DONE | 4 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-05-16 | 100 | 0 | 0 |  | 0 | 150 |  | Test caps |  | 13
2024-05-20 | 4861 | bth | L3Z1-FEMP-1 | A | DONE | 40 | M-L | pcd | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 620 | 30 | 330 | F | 0 | 1720 |  |  | L3 Zone 1 A/B | 55
2024-05-20 | 4864 | bth | L3Z1-FEMP-4 | A | DONE | 46 | L | pcd | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 400 | 30 | 720 | F | 0 | 1980 |  |  | L3 Zone 1 A/B | 55
2024-05-20 | 4866 | bth | L3Z1-FEMP-6 | A | DONE | 17 | M | pcd | UWRF 6230010 |  | 2024-05-20 | Z | 2024-03-26 | 110 | 30 | 280 | F | 0 | 660 |  |  | L3 Zone 1 A/B | 55
2024-05-23 | 4868 |  | L3Z2-FEMP-8 | A | DONE | 15 | S-M | pcd | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 120 | 0 | 250 | F | 0 | 530 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-23 | 4871 | bth | L3Z2-FEMP-11 | A | DONE | 13 | M | pcd | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 80 | 30 | 220 | F | 0 | 460 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-23 | 4872 | bth | L3Z2-FEMP-12 | A | DONE | 11 | S-M | pcd | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 150 | 30 | 90 | F | 0 | 370 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-23 | 4874 | bth | L3Z2-FEMP-14 | A | DONE | 8 | S | pcd | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 130 | 40 | 30 | F | 0 | 240 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-22 | 4895 | bth | L3Z2-EAMP-11 | A | DONE | 28 | M-L | pt.neal | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 190 | 20 | 480 | F | 0 | 1450 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-22 | 4896 | bth | L3Z2-EAMP-12 | A | DONE | 19 | M | pt.neal | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 300 | 80 | 80 | F | 0 | 770 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-22 | 4897 | bth | L3Z2-EAMP-13 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 160 | 30 | 110 | F | 0 | 400 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-24 | 4913 | bth | L3Z2-SAMP-12 | A | DONE | 19 | M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 180 | 70 | 220 | F | 0 | 900 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-24 | 4914 | bth | L3Z2-SAMP-13 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 80 | 50 | 170 | F | 0 | 570 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-24 | 4926 | bth | L3Z2-SAMP-25 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 60 | 40 | 20 | F | 0 | 140 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-23 | 4927 | bth | L3Z2-SAMP-26 | A | DONE | 30 | M-L |  | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 240 | 60 | 450 | F | 0 | 1540 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-23 | 4928 | bth | L3Z2-SAMP-27 | A | DONE | 35 | M-L |  | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 180 | 80 | 610 | F | 0 | 1430 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-23 | 4929 |  | L3Z2-SAMP-28 | A | DONE | 26 | M-L |  | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 310 | 0 | 330 | F | 0 | 1070 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-23 | 4930 | bth | L3Z2-SAMP-29 | A | DONE | 19 | M |  | UWRF 6230010 |  | 2024-05-28 | Z | 2024-03-26 | 210 | 60 | 200 | F | 0 | 730 |  |  | L3 Zone 2 C | 63 |  | 2024-06-03
2024-05-21 | 5003 |  | 96547 | A | DONE | 2 | S | BI | UWSP ALBERTSON 6230016 |  | 2024-05-21 | Z | 2024-05-21 | 20 | 0 | 0 |  | 0 | 30 |  | Cap |  | 0
2024-05-20 | 3223 |  | 72439 - 72440 | A | DONE | 6 | S-M |  | UW-VET MED 6210014 |  | 2024-05-22 | Z | 2024-05-20 | 130 | 0 | 0 |  | 0 | 210 |  | Flat stock |  | 2
[6 empty] | 1013 | [13 empty] | 38960 |  |  |  | 10410 | 26.72%
WEEK OF 5-27-2024
2024-05-30 | 2204 |  | 4TH FLOOR | A | DONE | 2 | S-M | BI | 121 E. WILSON 6230024 |  | 2024-06-07 | Z | 2024-05-24 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 14
2024-05-29 | 183 |  | 70606 | A | DONE | 2 | S |  | ACADIA 8230013 |  | 2024-05-31 | Z | 2024-05-24 | 20 | 0 | 0 |  | 0 | 20 |  | Plates |  | 7
2024-05-30 | 1752 |  | 68042 - 68043 | A | DONE | 17 | M | neal | BLACKHAWK BTC 6230025 | 1" liner , flex , bird s. | 2024-05-30 | Z | 2024-05-16 | 410 | 0 | 0 |  | 0 | 1170 |  | RTU-3 RA |  | 14
2024-05-29 | 1753 |  | 68044 - 68045 | A | DONE | 22 | M | neal | BLACKHAWK BTC 6230025 | 1" liner , flex , bird s. | 2024-05-30 | Z | 2024-05-16 | 530 | 0 | 0 |  | 500 | 1510 |  | RTU-2 RA |  | 14
2024-05-29 | 1754 |  | 68046 | A | DONE | 0 | S |  | BLACKHAWK BTC 6230025 |  | 2024-05-30 | Z | 2024-05-29 | 0 | 0 | 0 |  | 0 | 0 |  | DM frame |  | 1
2024-05-30 | 751 | bth | L4-A-EAMP-025 | A | DONE | 16 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 240 | 20 | 120 | F | 0 | 670 |  |  |  | 51 |  | 2024-06-21
2024-05-28 | 752 |  | L4-A-EAMP-026 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 80 | 0 | 160 | F | 0 | 340 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 753 | bth | L4-A-EAMP-027 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 30 | 150 | 30 | F | 0 | 240 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 754 | sp | L4-A-EAMP-028 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 20 | 130 | 0 |  | 0 | 180 |  |  |  | 51 |  | 2024-06-21
2024-05-28 | 755 | bth | L4-A-EAMP-029 | A | DONE | 12 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 70 | 20 | 210 | F | 0 | 350 |  |  |  | 51 |  | 2024-06-21
2024-05-28 | 756 | bth | L4-A-EAMP-030 | A | DONE | 11 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 40 | 20 | 210 | F | 0 | 300 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 757 | bth | L4-A-EAMP-031 | A | DONE | 16 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 170 | 40 | 180 | F | 0 | 350 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 758 | bth | L4-A-EAMP-032 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 190 | 20 | 0 |  | 0 | 280 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 759 | bth | L4-A-EAMP-033 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 100 | 70 | 40 | F | 0 | 260 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 760 | bth | L4-A-EAMP-035 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 90 | 20 | 80 | F | 0 | 210 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 761 | bth | L4-A-EAMP-036 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 60 | 20 | 100 | F | 0 | 210 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 762 | bth | L4-A-EAMP-037 | A | DONE | 7 | S-M | pt.neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 120 | 20 | 20 | F | 0 | 180 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 763 |  | L4-A-TAD-001 | A | DONE | 2 | S-M | neal | CDIS 6220028 | 1" liner | 2024-05-30 | Z | 2024-04-09 | 40 | 0 | 0 |  | 30 | 70 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 764 |  | L4-A-SAMP-031 | A | DONE | 20 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 240 | 0 | 240 | F | 0 | 880 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 765 |  | L4-A-SAMP-032 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 80 | 0 | 210 | F | 0 | 350 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 766 | bth | L4-A-SAMP-033 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 20 | 30 | 210 | F | 0 | 300 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 767 | bth | L4-A-SAMP-034 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 120 | 40 | 0 |  | 0 | 170 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 768 | bth | L4-A-SAMP-035 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 100 | 30 | 150 | F | 0 | 340 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 769 | bth | L4-A-SAMP-036 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 70 | 20 | 60 | F | 0 | 180 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 770 | bth | L4-A-SAMP-037 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 30 | 20 | 210 | F | 0 | 300 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 771 | bth | L4-A-SAMP-038 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 60 | 40 | 70 | F | 0 | 190 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 772 | bth | L4-A-SAMP-039 | A | DONE | 17 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 50 | 30 | 340 | F | 0 | 580 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 773 | bth | L4-A-SAMP-040 | A | DONE | 22 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 330 | 20 | 190 | F | 0 | 740 |  |  |  | 51 |  | 2024-06-21
2024-05-29 | 774 | sp | L4-A-SAMP-044 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 775 |  | L4-A-SAMP-0104 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-04-09 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 51 |  | 2024-06-21
2024-05-30 | 844 |  | 61356 - 61357 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-05-15 | 100 | 0 | 170 | F | 0 | 360 |  | Brogden |  | 15
2024-05-31 | 846 | w | 69914 , 69917 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-06-04 | Z | 2024-05-16 | 170 | 0 | 0 |  | 0 | 380 |  | Drain pan |  | 19
2024-05-30 | 847 |  | 69918 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-06-04 | Z | 2024-05-16 | 20 | 0 | 0 |  | 0 | 20 |  | BSMT-EAD-018 |  | 19
2024-05-29 | 849 |  | 69869 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-30 | Z | 2024-05-16 | 20 | 0 | 0 |  | 0 | 30 |  | EAMP-01 tap 4th floor |  | 14
2024-05-28 | 850 |  | 69870 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-05-16 | 20 | 0 | 0 |  | 0 | 30 |  | Tear drop hangers |  | 14
2024-05-30 | 917 | sp | 69959 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-04 | Z | 2024-05-28 | 20 | 0 | 0 |  | 0 | 40 |  | 7th floor N. core sleeves |  | 7
2024-05-28 | 927 |  | 59493 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-05-29 | Z | 2024-05-28 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor |  | 1
2024-05-29 | 929 |  | 59494 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-05-30 | Z | 2024-05-28 | 20 | 0 | 0 |  | 0 | 30 |  | 3rd floor |  | 2
2024-05-31 | 947 |  | 69503 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-06-04 | Z | 2024-05-29 | 270 | 0 | 0 |  | 0 | 380 |  | Angles |  | 6
2024-05-31 | 949 | sp | 59495 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-06-04 | Z | 2024-05-30 | 40 | 40 | 0 |  | 0 | 110 |  | 3rd floor |  | 5
2024-05-31 | 952 |  | 69871 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-06-04 | Z | 2024-05-30 | 230 | 0 | 0 |  | 0 | 280 |  | EC / Flashing |  | 5
2024-05-28 | a2336 |  | 58804 | A | DONE | 2 | S |  | DEWITT 2240019 |  | 2024-05-28 | Z | 2024-05-28 | 20 | 0 | 0 |  | 0 | 20 |  | Added reducers * |  | 0
2024-05-29 | 1586 |  | 52824 | A | DONE | 3 | S |  | EMBASSY SUITES 6220012 | bird s. , 1" liner | 2024-05-30 | Z | 2024-05-28 | 70 | 0 | 0 |  | 20 | 150 |  | Misc |  | 2
2024-05-30 | 1587 |  | hand - drawn | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 | paint | 2024-06-03 | Z | 2024-05-30 | 20 | 0 | 0 |  | 20 | 20 |  | Grille box |  | 4
2024-05-30 | 1588 |  | hand - drawn | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 | paint white | 2024-06-03 | Z | 2024-05-30 | 20 | 0 | 0 |  | 20 | 50 |  | Flashing |  | 4
2024-05-28 | 4611 |  | 69420 | A | DONE | 3 | S |  | HARMONICS 6240010 |  | 2024-05-30 | Z | 2024-05-23 | 70 | 0 | 0 |  | 0 | 110 |  | Roxx 2 ERV 1A |  | 7
2024-05-30 | 4612 | w | 69421 | A | DONE | 2 | S | BI | HARMONICS 6240010 |  | 2024-06-06 | Z | 2024-05-28 | 20 | 0 | 0 |  | 0 | 30 |  | Condensates |  | 9
2024-05-29 | 4613 |  | 69422 | A | DONE | 2 | S |  | HARMONICS 6240010 |  | 2024-05-30 | Z | 2024-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | Service corridor |  | 1
2024-05-28 | 2958 |  | 69263 | A | DONE | 2 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-05-30 | Z | 2024-05-23 | 50 | 0 | 0 |  | 20 | 80 |  | RA tie ins |  | 7
2024-05-29 | 2959 |  | 69264 - 69265 | A | DONE | 6 | S-M |  | HERITAGE 6220024 | paint | 2024-05-30 | Z | 2024-05-23 | 150 | 0 | 0 |  | 0 | 180 |  | A-Section tie ins |  | 7
2024-05-30 | 2960 |  | 69266 | A | DONE | 2 | S | neal | HERITAGE 6220024 |  | 2024-05-31 | Z | 2024-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd A-Corr. |  | 2
2024-05-30 | 2961 |  | 69267 | A | DONE | 2 | S |  | HERITAGE 6220024 | paint | 2024-05-31 | Z | 2024-05-30 | 20 | 0 | 0 |  | 20 | 20 |  | 1st floor TA |  | 1
2024-05-31 | 3734 |  | 55192 | A | DONE | 10 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-03 | Z | 2024-05-29 | 240 | 0 | 0 |  | 0 | 280 |  | B-Section |  | 5
2024-05-28 | 2908 | sp | 80151 | A | DONE | 5 | S-M |  | LABCORP 6240011 |  | 2024-05-30 | Z | 2024-05-22 | 50 | 60 | 0 |  | 0 | 110 |  |  |  | 8
2024-05-30 | 182 |  | 62949 | A | DONE | 2 | S |  | LINDSEY M 1000373 |  | 2024-05-30 | Z | 2024-05-23 | 20 | 0 | 0 |  | 0 | 30 |  | SA |  | 7
2024-05-30 | 186 |  | 70583 | A | DONE | 2 | S |  | LODI 10054718 |  | 2024-05-31 | Z | 2024-05-29 | 20 | 0 | 0 |  | 0 | 50 |  | Angles |  | 2
2024-05-31 | 2171 | sp | 68607 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-06-04 | Z | 2024-05-21 | 20 | 20 | 0 |  | 0 | 40 |  | EA |  | 14
2024-05-28 | 1422 |  | 67548 - 67550 | A | DONE | 11 | S-M | alum | MENDOTA FOODS 6220027 | paint | 2024-05-30 | Z | 2024-05-21 | 260 | 0 | 0 |  | 0 | 340 |  | Misc Bsmt , 1st floor |  | 9
2024-05-28 | 1423 |  | 67479 | A | DONE | 3 | S |  | MENDOTA FOODS 6220027 |  | 2024-05-30 | Z | 2024-05-21 | 70 | 0 | 0 |  | 0 | 80 |  | 1st floor tie ins |  | 9
2024-05-29 | 1424 |  | 67480 - 67481 | A | DONE | 10 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-05-30 | Z | 2024-05-24 | 240 | 0 | 0 |  | 0 | 460 |  | NW Corner |  | 6
2024-05-29 | 1425 |  | 67482 | A | DONE | 3 | S-M |  | MENDOTA FOODS 6220027 | 2" DB | 2024-05-30 | Z | 2024-05-24 | 70 | 0 | 0 |  | 30 | 150 |  | Louver blank off |  | 6
2024-05-29 | 1426 |  | 67483 - 67484 | A | DONE | 10 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-05-30 | Z | 2024-05-24 | 250 | 0 | 0 |  | 0 | 760 |  | AHU-5 Louver / S. Middle |  | 6
2024-05-29 | 1427 |  | 67485 - 67486 | A | DONE | 10 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-05-30 | Z | 2024-05-24 | 230 | 0 | 0 |  | 0 | 360 |  | AHU-4 Louver / NE |  | 6
2024-05-29 | 1428 |  | 67487 | A | DONE | 8 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-05-30 | Z | 2024-05-28 | 200 | 0 | 0 |  | 0 | 430 |  | AHU-5 |  | 2
2024-05-31 | 1430 |  | 67490 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-05-31 | Z | 2024-05-29 | 30 | 0 | 0 |  | 0 | 90 |  | SAMP-1 #10 |  | 2
2024-05-31 | 1431 |  | 67491 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | 1" liner | 2024-05-31 | Z | 2024-05-29 | 30 | 0 | 0 |  | 30 | 50 |  | Basement |  | 2
2024-05-29 | 1432 |  | 70584 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-05-29 | Z | 2024-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | Couplings |  | 0
2024-05-30 | 1434 |  | 70586 | A | DONE | 2 | S-M |  | MENDOTA FOODS 6220027 | bird s. | 2024-05-30 | Z | 2024-05-30 | 20 | 0 | 0 |  | 0 | 20 |  | Louver |  | 0
2024-05-31 | 1822 | sp | 59802 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-06-05 | Z | 2024-05-28 | 20 | 30 | 0 |  | 0 | 50 |  | SA vav's |  | 8
2024-05-28 | 4758 |  | 61162 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 | flex | 2024-05-30 | Z | 2024-05-22 | 30 | 0 | 0 |  | 20 | 40 |  | EP-7 guard station |  | 8
2024-05-28 | 4759 | sp | 78885 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-05-30 | Z | 2024-05-22 | 20 | 20 | 0 |  | 0 | 30 |  | Kitchen |  | 8
2024-05-30 | 4760 | sp | 78886 | A | DONE | 3 | S-M | neal | ROCK CO. JAIL 6220018 |  | 2024-06-03 | Z | 2024-05-29 | 40 | 20 | 0 |  | 0 | 70 |  | Vehicle EA |  | 5
2024-05-28 | 184 |  | 79758 | A | DONE | 2 | S |  | SIERRA SPACE 10054773 | filter rack | 2024-05-28 | Z | 2024-05-28 | 20 | 0 | 0 |  | 0 | 20 |  | Furnace |  | 0
2024-05-31 | 4694 |  | 70345 | A | DONE | 2 | S |  | ST.BERNARD 2230056 | 1" liner | 2024-06-04 | Z | 2024-05-28 | 40 | 0 | 0 |  | 30 | 40 |  | F-7 SA |  | 7
2024-05-31 | 4689 |  | 70334 - 70335 | A | DONE | 13 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-06-03 | Z | 2024-05-15 | 250 | 0 | 70 | F | 220 | 300 |  | PRV-1 |  | 19
2024-05-31 | 4690 |  | 70337 | A | DONE | 2 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-06-03 | Z | 2024-05-15 | 40 | 0 | 0 |  | 40 | 70 |  | SA riser in church |  | 19
2024-05-31 | 4691 |  | 70339 - 70340 | A | DONE | 13 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-06-03 | Z | 2024-05-15 | 320 | 0 | 0 |  | 190 | 490 |  | Big RA East/West side |  | 19
2024-05-31 | 4692 |  | 70341 | A | DONE | 2 | S-M |  | ST.BERNARD 6230023 |  | 2024-06-03 | Z | 2024-05-15 | 50 | 0 | 0 |  | 0 | 90 |  | 1st floor goose neck |  | 19
2024-05-30 | 4695 |  | 70350 | A | DONE | 2 | S |  | ST.BERNARD 6230023 | 1" liner | 2024-06-04 | Z | 2024-05-28 | 50 | 0 | 0 |  | 40 | 100 |  | RA thru floor |  | 7
2024-05-31 | 232 |  | 70076 - 70077 | A | DONE | 25 | S-M |  | UPLAND HILLS 2240008 |  | 2024-06-03 | Z | 2024-03-12 | 510 | 0 | 110 | F | 0 | 580 |  | 1330 LPSA |  | 83 |  | 2024-04-22 | 2024-06-03
2024-05-31 | 243 | sp | 70093 - 70094 | A | DONE | 8 | S-M |  | UPLAND HILLS 2240008 |  | 2024-06-03 | Z | 2024-03-12 | 60 | 120 | 0 |  | 0 | 160 |  | 1305 LPSA |  | 83 |  | 2024-05-06 | 2024-06-13
2024-05-30 | 250 | sp | 79606 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-06-03 | Z | 2024-03-13 | 20 | 30 | 0 |  | 0 | 50 |  | AT 1313 MPSA |  | 82 |  | 2024-05-13 | 2024-05-21
2024-05-31 | 251 | bth | 79607 - 79608 | A | DONE | 4 | S-M |  | UPLAND HILLS 2240008 |  | 2024-06-03 | Z | 2024-03-13 | 40 | 40 | 0 |  | 0 | 80 |  | AT 1313 LPSA |  | 82 |  | 2024-05-13 | 2024-05-21
2024-05-31 | 253 | sp | 79610 - 79611 | A | DONE | 3 | S-M |  | UPLAND HILLS 2240008 |  | 2024-06-03 | Z | 2024-03-13 | 30 | 40 | 0 |  | 0 | 70 |  | RAT 1313 LPRA |  | 82 |  | 2024-05-13 | 2024-05-21
2024-05-31 | 271 |  | 79612 - 79613 | A | DONE | 16 | S-M |  | UPLAND HILLS 2240008 |  | 2024-06-03 | Z | 2024-03-19 | 90 | 310 | 0 | F | 0 | 380 |  | Podiatry RA |  | 76 |  | 2024-05-13 | 2024-05-21
2024-05-29 | 3979 |  | 70117 | A | DONE | 7 | S-M |  | UWRF 6230010 |  | 2024-06-10 | Z | 2024-05-07 | 170 | 0 | 0 |  | 0 | 470 |  | Shaft 194M |  | 34
2024-05-30 | 4087 |  | 66914 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-06-03 | Z | 2024-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor SAMP 3 |  | 5
2024-05-28 | 4869 | bth | L3Z2-FEMP-9 | A | DONE | 11 | S-M | pcd | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 120 | 120 | 30 | F | 0 | 320 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4870 | bth | L3Z2-FEMP-10 | A | DONE | 10 | S | pcd | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 30 | 40 | 160 | F | 0 | 290 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4898 | bth | L3Z2-EAMP-14 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 150 | 50 | 40 | F | 0 | 350 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4899 | bth | L3Z2-EAMP-15 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 100 | 80 | 40 | F | 0 | 320 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4900 | bth | L3Z2-EAMP-16 | A | DONE | 11 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 110 | 120 | 40 | F | 0 | 330 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4901 | bth | L3Z2-EAMP-17 | A | DONE | 7 | S |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 80 | 20 | 70 | F | 0 | 250 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4915 | bth | L3Z2-SAMP-14 | A | DONE | 22 | M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 260 | 60 | 220 | F | 0 | 810 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4916 | bth | L3Z2-SAMP-15 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 70 | 30 | 150 | F | 0 | 360 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4917 | bth | L3Z2-SAMP-16 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 90 | 40 | 110 | F | 0 | 330 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4918 | bth | L3Z2-SAMP-17 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 90 | 70 | 130 | F | 0 | 370 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4919 | bth | L3Z2-SAMP-18 | A | DONE | 28 | M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 530 | 50 | 110 | F | 0 | 1100 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4920 | bth | L3Z2-SAMP-19 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 160 | 80 | 40 | F | 0 | 410 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4921 | bth | L3Z2-SAMP-20 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 160 | 100 | 40 | F | 0 | 360 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4922 | bth | L3Z2-SAMP-21 | A | DONE | 16 | M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 80 | 40 | 270 | F | 0 | 620 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4923 | bth | L3Z2-SAMP-22 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 140 | 40 | 40 | F | 0 | 290 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4924 | bth | L3Z2-SAMP-23 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 80 | 30 | 110 | F | 0 | 350 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-28 | 4925 | bth | L3Z2-SAMP-24 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-05-29 | Z | 2024-03-26 | 90 | 50 | 70 | F | 0 | 260 |  |  | L3 Zone 2 A/B | 64 |  | 2024-05-27
2024-05-30 | 3227 | sp | 72449 | A | DONE | 9 | S-M |  | UW-VET MED 6210014 |  | 2024-06-04 | Z | 2024-05-21 | 20 | 190 | 0 |  | 0 | 180 |  | F4-SA |  | 14
2024-05-30 | 3230 | sp | 72956 | A | DONE | 5 | S-M |  | UW-VET MED 6210014 |  | 2024-06-04 | Z | 2024-05-21 | 0 | 120 | 0 |  | 0 | 110 |  | F1-SA |  | 14
2024-05-30 | 266 |  | 78719 | A | DONE | 12 | M |  | WHS 4230041 | flex | 2024-05-31 | Z | 2024-03-18 | 280 | 0 | 0 |  | 0 | 560 |  |  |  | 74
[6 empty] | 810 | [13 empty] | 27280 |  |  |  | 5180 | 18.99%
WEEK OF 6-3-2024
2024-06-06 | 2209 | w | 79599 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-06-07 | Z | 2024-06-06 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeve w/ cap |  | 1
2024-06-03 | 1755 |  | 68047 | A | DONE | 4 | S |  | BLACKHAWK BTC 6230025 | 1" liner | 2024-06-06 | Z | 2024-05-30 | 50 | 0 | 30 | F | 60 | 100 |  | Stairway |  | 7
2024-06-03 | 1756 |  | 67078 | A | DONE | 3 | S | pt.neal | BLACKHAWK BTC 6230025 |  | 2024-06-10 | Z | 2024-05-30 | 60 | 0 | 0 |  | 0 | 80 |  | Caps |  | 11
2024-06-07 | 1757 | sp | 68048 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 | spiral mate | 2024-06-13 | Z | 2024-06-03 | 40 | 0 | 0 |  | 0 | 60 |  | EF-1 |  | 10
2024-06-03 | 928 | bth | 61036 | A | DONE | 3 | S | neal | CDIS 6220028 |  | 2024-06-04 | Z | 2024-05-28 | 20 | 40 | 0 |  | 0 | 60 |  | 2nd floor B EA |  | 7
2024-06-07 | 948 |  | 69504 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-11 | Z | 2024-05-30 | 50 | 0 | 0 |  | 0 | 80 |  | 2nd floor |  | 12
2024-06-07 | 950 |  | 61039 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-11 | Z | 2024-05-30 | 30 | 0 | 0 |  | 0 | 30 |  | 2nd floor B tie ins |  | 12
2024-06-03 | 953 |  | 69919 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-05 | Z | 2024-06-03 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2024-06-07 | 954 |  | 69507 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-06-11 | Z | 2024-06-03 | 40 | 0 | 0 |  | 0 | 40 |  | 2nd floor B EA |  | 8
2024-06-07 | 955 |  | 61043 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-06-11 | Z | 2024-06-04 | 50 | 0 | 0 |  | 0 | 60 |  | 2nd floor B EA |  | 7
2024-06-07 | 957 |  | 59496 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-06-11 | Z | 2024-06-04 | 230 | 0 | 0 |  | 0 | 380 |  | Flashing |  | 7
2024-06-05 | 958 | sp | 59497 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-06 | Z | 2024-06-04 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd fl |  | 2
2024-06-07 | 992 |  | 59500 | A | DONE | 2 | S | pt.neal | CDIS 6220028 |  | 2024-06-11 | Z | 2024-06-06 | 30 | 0 | 0 |  | 0 | 60 |  | 3rd Floor |  | 5
2024-06-05 | 3660 | sp | L4-A-EALP-043 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 63 |  | 2024-06-23
2024-06-03 | 3661 | sp | L4-A-EALP-044 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 50 | 0 |  | 0 | 60 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3662 | sp | L4-A-EALP-045 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3663 | bth | L4-A-EALP-046 | A | DONE | 3 | S | neal | CDIS 6220028 | 1" liner , 1" s. accu | 2024-06-06 | Z | 2024-04-04 | 50 | 20 | 0 |  | 20 | 100 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3664 | sp | L4-A-EALP-047 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3665 | sp | L4-A-EALP-048 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 40 | 0 |  | 0 | 70 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3666 | sp | L4-A-EALP-049 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3667 | sp | L4-A-EALP-050 | A | DONE | 6 | S |  | CDIS 6220028 | 1" s. accu | 2024-06-06 | Z | 2024-04-04 | 50 | 90 | 0 |  | 120 | 180 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3668 | bth | L4-A-EALP-051 | A | DONE | 4 | S | neal | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 60 | 30 | 0 |  | 0 | 110 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3669 | sp | L4-A-EALP-052 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 60 | 0 |  | 0 | 70 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3670 | bth | L4-A-EALP-053 | A | DONE | 4 | S | neal | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 80 | 20 | 0 |  | 40 | 100 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3671 | sp | L4-A-EALP-054 | A | DONE | 2 | S | pt.neal | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3672 | bth | L4-A-EALP-055 | A | DONE | 6 | S | neal | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 130 | 20 | 0 |  | 0 | 170 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3673 | bth | L4-A-EALP-056 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 80 | 20 | 0 |  | 0 | 90 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3674 | sp | L4-A-EALP-057 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 30 | 130 | 0 |  | 0 | 150 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3675 | bth | L4-A-EALP-058 | A | DONE | 6 | S |  | CDIS 6220028 | paint | 2024-06-06 | Z | 2024-04-04 | 80 | 20 | 50 | F | 0 | 150 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3676 | bth | L4-A-EALP-059 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 70 | 40 | 0 |  | 0 | 130 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3677 |  | L4-A-RAD-002 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-06-06 | Z | 2024-04-04 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3678 | bth | L4-A-SALP-056 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 40 | 70 | 0 |  | 20 | 120 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3679 |  | L4-A-SALP-057 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 50 | 70 | 0 |  | 20 | 120 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3680 | bth | L4-A-SALP-058 | A | DONE | 8 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 110 | 80 | 0 |  | 30 | 200 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3681 | bth | L4-A-SALP-060 | A | DONE | 7 | S |  | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 150 | 20 | 0 |  | 90 | 200 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3682 | bth | L4-A-SALP-061 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 60 | 90 | 0 |  | 20 | 140 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3683 | bth | L4-A-SALP-063 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 40 | 80 | 0 |  | 20 | 120 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3684 | bth | L4-A-SALP-064 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 40 | 70 | 0 |  | 20 | 120 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3685 | bth | L4-A-SALP-065 | A | DONE | 9 | S | neal | CDIS 6220028 | 1" liner , paint | 2024-06-06 | Z | 2024-04-04 | 140 | 20 | 60 | F | 60 | 250 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3686 | bth | L4-A-SALP-066 | A | DONE | 5 | S | neal | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 90 | 30 | 0 |  | 30 | 140 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3687 | bth | L4-A-SALP-067 | A | DONE | 3 | S |  | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 40 | 30 | 0 |  | 20 | 80 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3688 | bth | L4-A-SALP-069 | A | DONE | 4 | S | neal | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 30 | 50 | 20 | F | 20 | 120 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3689 | bth | L4-A-SALP-070 | A | DONE | 4 | S | neal | CDIS 6220028 | 1" liner , 1" s. accu | 2024-06-06 | Z | 2024-04-04 | 40 | 50 | 0 |  | 40 | 110 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3690 | bth | L4-A-SALP-071 | A | DONE | 6 | S | neal | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 90 | 50 | 0 |  | 30 | 160 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3691 | bth | L4-A-SALP-073 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 60 | 50 | 0 |  | 30 | 120 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3692 | bth | L4-A-SALP-074 | A | DONE | 4 | S | neal | CDIS 6220028 | 1" liner | 2024-06-06 | Z | 2024-04-04 | 50 | 40 | 0 |  | 20 | 110 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 3693 |  | L4-A-SALP-075 | A | DONE | 9 | S | neal | CDIS 6220028 | 1" liner , paint | 2024-06-06 | Z | 2024-04-04 | 180 | 0 | 40 | F | 30 | 260 |  |  |  | 63 |  | 2024-06-23
2024-06-04 | 3694 |  | L4-A-SALP-076 | A | DONE | 4 | S-M | neal | CDIS 6220028 | 1" liner , paint | 2024-06-06 | Z | 2024-04-04 | 70 | 0 | 20 | F | 40 | 110 |  |  |  | 63 |  | 2024-06-23
2024-06-05 | 189 | bth | 79414 | A | DONE | 7 | S-M |  | COLUMBUS CHEM. 10055823 |  | 2024-06-10 | Z | 2024-06-04 | 100 | 70 | 0 |  | 0 | 190 |  | EA |  | 6
2024-06-03 | 185 |  | 79759 | A | DONE | 7 | S |  | COMPASS HP 4230088 | 1" liner | 2024-06-04 | Z | 2024-05-29 | 160 | 0 | 0 |  | 0 | 300 |  | RTU-2 Drops |  | 6
2024-06-03 | 188 |  | 79766 | A | DONE | 2 | S |  | COMPASS HP 4230088 |  | 2024-06-04 | Z | 2024-05-30 | 30 | 0 | 0 |  | 0 | 40 |  | RA |  | 5
2024-06-06 | 1131 |  | 59499 | A | DONE | 2 | S | ss | DANE CO. AIRPORT 6210011 |  | 2024-06-10 | Z | 2024-06-06 | 50 | 0 | 0 |  | 0 | 90 |  | AHU-13 Coil Replacement |  | 4
2024-06-03 | 1589 |  | hand - drawn | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 |  | 2024-06-04 | Z | 2024-06-03 | 20 | 0 | 0 |  | 0 | 50 |  | Grille box |  | 1
2024-06-05 | 651 |  | 79661 | A | DONE | 2 | S |  | GRAND AVE 6230012 | 1/2" liner | 2024-06-10 | Z | 2024-05-21 | 20 | 0 | 0 |  | 30 | 30 |  | Added TA |  | 20 |  | 2024-06-24
2024-06-04 | 4614 |  | 79455 - 79456 | A | DONE | 8 | S |  | HARMONICS 6240010 |  | 2024-06-05 | Z | 2024-06-04 | 200 | 0 | 0 |  | 0 | 230 |  | DTOA / Flashing |  | 1
2024-06-07 | 1702 |  | 80200 - 80201 | A | DONE | 9 | S-M |  | INVENRA 6230001 | 1" liner , perf | 2024-06-12 | Z | 2024-05-29 | 210 | 0 | 0 |  | 120 | 390 |  | Silencers |  | 14
2024-06-05 | 1705 |  | 80209 | A | DONE | 2 | S |  | INVENRA 6230001 |  | 2024-06-12 | Z | 2024-05-29 | 20 | 0 | 0 |  | 0 | 20 |  | Pre-fab hangers |  | 14
2024-06-04 | 2837 |  | 70822 | A | DONE | 4 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-06-06 | Z | 2024-05-21 | 30 | 60 | 0 |  | 0 | 40 |  | Pool SA |  | 16
2024-06-04 | 2838 |  | 78616 | A | DONE | 9 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-06-06 | Z | 2024-05-21 | 210 | 0 | 0 |  | 0 | 270 |  | RE-5,6 |  | 16
2024-06-03 | 2839 |  | 78618 | A | DONE | 16 | S-M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-06-06 | Z | 2024-05-21 | 380 | 0 | 0 |  | 350 | 660 |  | RE-5,6 |  | 16
2024-06-03 | 2840 |  | 70823 | A | DONE | 4 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-06-06 | Z | 2024-05-24 | 90 | 0 | 0 |  | 0 | 80 |  | Pool EA |  | 13
2024-06-07 | 2843 | sp | 70826 | A | DONE | 8 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-06-13 | Z | 2024-06-03 | 40 | 150 | 0 |  | 0 | 200 |  | BCU-2,3 SA |  | 10
2024-06-07 | 1116 | sp | 80152 - 80153 | A | DONE | 10 | S-M |  | LABCORP 2240024 |  | 2024-06-12 | Z | 2024-06-04 | 90 | 160 | 0 |  | 0 | 250 |  | SA |  | 8
2024-06-03 | 2170 |  | 68605 - 68606 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 | flex | 2024-06-04 | Z | 2024-05-17 | 70 | 0 | 0 |  | 0 | 150 |  | FC SA |  | 18
2024-06-07 | 2174 | sp | 68590 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-06-11 | Z | 2024-05-31 | 20 | 0 | 0 |  | 0 | 20 |  | LMC saddle taps |  | 11
2024-06-04 | 1433 |  | 53684 | A | DONE | 3 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-06-06 | Z | 2024-05-29 | 60 | 0 | 0 |  | 0 | 120 |  | AHU-3 tie in |  | 8
2024-06-04 | 1435 |  | 53685 | A | DONE | 4 | S |  | MENDOTA FOODS 6220027 |  | 2024-06-06 | Z | 2024-05-31 | 90 | 0 | 0 |  | 0 | 250 |  | Misc |  | 6
2024-06-04 | 1436 |  | 53686 | A | DONE | 9 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-06-06 | Z | 2024-06-03 | 210 | 0 | 0 |  | 0 | 410 |  | AHU-3 SA |  | 3
2024-06-04 | 1437 |  | 53687 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-06-06 | Z | 2024-06-03 | 20 | 0 | 0 |  | 0 | 40 |  | AHU-6 OA |  | 3
2024-06-04 | 1438 |  | 53688 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-06-06 | Z | 2024-06-04 | 20 | 0 | 0 |  | 0 | 20 |  | RF-6-1 |  | 2
2024-06-05 | 3101 | sp | 79654 - 79655 | A | DONE | 48 | M-L | neal | PECATONICA 6240005 |  | 2024-06-10 | Z | 2024-04-12 | 180 | 1010 | 0 |  | 0 | 1390 |  | Gym SA |  | 59
2024-06-04 | 3102 |  | Pre-fab hangers | A | DONE | 2 | S | neal | PECATONICA 6240005 |  | 2024-06-10 | Z | 2024-04-12 | 30 | 0 | 0 |  | 0 | 70 |  | Gym hangers |  | 59
2024-06-06 | 3103 | sp | 79656 | A | DONE | 10 | S-M | neal | PECATONICA 6240005 |  | 2024-06-10 | Z | 2024-04-12 | 120 | 130 | 0 |  | 0 | 290 |  | GYM-SA |  | 59
2024-06-03 | 1801 |  | 62947 | A | DONE | 30 | S-M |  | PROMEGA BTC 6230022 |  | 2024-06-05 | Z | 2024-05-09 | 180 | 0 | 550 | F | 0 | 1040 |  | SA Main |  | 27
2024-06-03 | 1823 |  | 59803 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-06-05 | Z | 2024-05-28 | 50 | 0 | 0 |  | 0 | 90 |  | SA main |  | 8
2024-06-05 | 1825 | sp | 59804 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-06-06 | Z | 2024-06-05 | 30 | 20 | 0 |  | 0 | 50 |  | SA Main |  | 1
2024-06-03 | 1821 |  | 59801 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 | paint | 2024-06-05 | Z | 2024-05-28 | 30 | 0 | 0 |  | 20 | 40 |  | Grilles |  | 8
2024-06-05 | 4548 |  | 72386 | A | DONE | 17 | S-M |  | RAMC 6230009 | oval | 2024-06-10 | Z | 2024-05-23 | 420 | 0 | 0 |  | 0 | 600 |  | LL-SAMP |  | 18
2024-06-05 | 4549 | sp | 72387 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-06-10 | Z | 2024-06-04 | 30 | 20 | 0 |  | 0 | 50 |  | LL Misc |  | 6
2024-06-03 | 3001 |  | 62528 - 62529 | A | DONE | 14 | S-M |  | RETRO CX 6240004 | VD | 2024-06-04 | Z | 2024-05-21 | 340 | 0 | 0 |  | 0 | 650 |  | AHU-9 |  | 14
2024-06-03 | 3002 |  | 62530 - 62531 | A | DONE | 13 | S-M |  | RETRO CX 6240004 | VD | 2024-06-04 | Z | 2024-05-21 | 320 | 0 | 0 |  | 0 | 440 |  | AHU-10 |  | 14
2024-06-06 | 4762 |  | 33243 | A | DONE | 2 | S | d.plate | ROCK CO. JAIL 8220022 |  | 2024-06-07 | Z | 2024-06-05 | 20 | 0 | 0 |  | 0 | 20 |  | Plate covers |  | 2
2024-06-04 | 4696 |  | 70348 - 70349 | A | DONE | 4 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-06-10 | Z | 2024-05-28 | 90 | 0 | 0 |  | 20 | 130 |  | AHU-1 , 2 |  | 13
2024-06-05 | 4697 |  | 79904 - 79905 | A | DONE | 8 | S-M |  | ST.BERNARD 6230023 |  | 2024-06-10 | Z | 2024-05-28 | 190 | 0 | 0 |  | 0 | 380 |  | AHU-1 , 2 SA |  | 13
2024-06-05 | 4698 |  | 79906 | A | DONE | 11 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-06-10 | Z | 2024-05-28 | 190 | 0 | 80 | F | 180 | 350 |  | AHU-1 |  | 13
2024-06-05 | 4699 |  | 79907 - 79908 | A | DONE | 14 | S-M |  | ST.BERNARD 6230023 |  | 2024-06-10 | Z | 2024-05-28 | 300 | 0 | 40 | F | 0 | 470 |  | AHU-1 RA |  | 13
2024-06-06 | 2017 | bth | 58925 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 40 | 30 | 70 | F | 0 | 140 |  | SAT-5-3-4 |  | 32 |  | 2024-06-17
2024-06-06 | 2018 | bth | 67963 - 67965 | A | DONE | 7 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-06-10 | Z | 2024-05-09 | 70 | 50 | 40 | F | 20 | 170 |  | SAT-5-3-5,6,7 |  | 32 |  | 2024-06-17
2024-06-06 | 2019 | bth | 67966 - 67967 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 30 | 90 | 0 |  | 0 | 110 |  | SAT-5-3-8,9 |  | 32 |  | 2024-06-17
2024-06-06 | 2020 | bth | 67968 - 67969 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 50 | 40 | 0 |  | 0 | 100 |  | SAT-5-3-10,11 |  | 32 |  | 2024-06-17
2024-06-06 | 2021 |  | 67282 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-06-10 | Z | 2024-05-09 | 70 | 0 | 0 |  | 50 | 80 |  | SAT-5-3-12 |  | 32 |  | 2024-06-17
2024-06-06 | 2022 |  | 67971 - 67973 | A | DONE | 17 | S-M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 190 | 0 | 220 | F | 0 | 490 |  | SAT-5-3-12 |  | 32 |  | 2024-06-17
2024-06-07 | 2023 | bth | 67974 - 67975 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 30 | 0 | 40 | F | 0 | 170 |  | SAT-5-3-13 |  | 32 |  | 2024-06-17
2024-06-06 | 2024 | sp | 67976 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 20 | 70 | 0 |  | 0 | 80 |  | AHU-5 SA |  | 32 |  | 2024-06-17
2024-06-06 | 2025 | bth | 67977 - 67978 | A | DONE | 9 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 50 | 20 | 140 | F | 0 | 230 |  | SAT-5-3-14 |  | 32 |  | 2024-06-17
2024-06-07 | 2026 | bth | 67979 - 67981 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 120 | 60 | 60 | F | 0 | 380 |  | SAT-5-3-15,16,17 |  | 32 |  | 2024-06-17
2024-06-06 | 2027 |  | 67982 - 67983 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-06-10 | Z | 2024-05-09 | 120 | 0 | 30 | F | 120 | 180 |  | 315B TA |  | 32 |  | 2024-06-17
2024-06-07 | 2028 |  | 67992 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | VD | 2024-06-10 | Z | 2024-05-09 | 50 | 0 | 0 |  | 0 | 60 |  | 311 Lounge |  | 32 |  | 2024-06-17
2024-06-07 | 2029 |  | 67991 , 67993 | A | DONE | 16 | S-M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 260 | 0 | 140 | F | 0 | 500 |  | AHU-5 RA |  | 32 |  | 2024-06-17
2024-06-07 | 2030 | bth | 67994 - 67995 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 | VD | 2024-06-10 | Z | 2024-05-09 | 70 | 30 | 0 |  | 0 | 110 |  | 315 RA |  | 32 |  | 2024-06-17
2024-06-06 | 2031 | sp | 67996 , 67998 | A | DONE | 7 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 20 | 140 | 0 |  | 0 | 140 |  | 31,312,314 RA |  | 32 |  | 2024-06-17
2024-06-05 | 2032 | sp | 67999 | A | DONE | 12 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 20 | 260 | 0 |  | 0 | 240 |  | SAT-4-3-2 |  | 32 |  | 2024-06-17
2024-06-07 | 2033 |  | 71080 - 71081 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 160 | 0 | 110 | F | 0 | 350 |  | AHU-4 SA |  | 32 |  | 2024-06-17
2024-06-07 | 2034 | bth | 71082 - 71084 | A | DONE | 32 | M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 120 | 80 | 580 | F | 0 | 920 |  | AHU-4 SA |  | 32 |  | 2024-06-17
2024-06-07 | 2035 | bth | 71085 - 71086 | A | DONE | 7 | S |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 60 | 70 | 40 | F | 0 | 170 |  | SAT-4-3-1,2 |  | 32 |  | 2024-06-17
2024-06-07 | 2036 |  | 71087 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-06-10 | Z | 2024-05-09 | 80 | 0 | 0 |  | 70 | 120 |  | SAT-4-3-3 |  | 32 |  | 2024-06-17
2024-06-07 | 2037 | bth | 71088 - 71089 | A | DONE | 14 | S-M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 120 | 60 | 160 | F | 0 | 380 |  | SAT-4-3-3 |  | 32 |  | 2024-06-17
2024-06-07 | 2038 | bth | 71090 - 71091 | A | DONE | 16 | S-M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 80 | 70 | 240 | F | 0 | 430 |  | SAT-4-3-4 |  | 32 |  | 2024-06-17
2024-06-07 | 2039 |  | 71092 - 71094 | A | DONE | 30 | M-L |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 330 | 0 | 420 | F | 0 | 1150 |  | AHU-5 SA |  | 32 |  | 2024-06-17
2024-06-07 | 2040 | sp | 71095 - 71097 | A | DONE | 21 | M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 90 | 420 | 0 |  | 0 | 500 |  | AHU-5 SA |  | 32 |  | 2024-06-17
2024-06-07 | 2041 | bth | 71098 - 71100 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-05-09 | 60 | 120 | 100 | F | 0 | 300 |  | SAT-5-3-1 |  | 32 |  | 2024-06-17
2024-06-04 | 3525 |  | 79325 | A | DONE | 14 | S-M |  | UWL-GRAFF 6230017 |  | 2024-06-10 | Z | 2024-06-04 | 330 | 0 | 0 |  | 0 | 390 |  | S/D |  | 6
2024-06-05 | 3972 |  | SHAFT-194M-FEMP | A | DONE | 33 | M-L | pcd | UWRF 6230010 |  | 2024-06-10 | Z | 2024-05-07 | 470 | 0 | 340 | F | 0 | 1610 |  |  |  | 34
2024-06-06 | 3973 |  | SHAFT-194M-SAMP | A | DONE | 96 | VL |  | UWRF 6230010 |  | 2024-06-10 | Z | 2024-05-07 | 2400 | 0 | 0 |  | 0 | 9000 |  |  |  | 34
2024-06-05 | 3980 |  | 70118 | A | DONE | 6 | S-M |  | UWRF 6230010 |  | 2024-06-17 | Z | 2024-05-07 | 150 | 0 | 0 |  | 0 | 300 |  | Shaft 194L |  | 41
2024-06-05 | 4148 |  | 66917 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-06-10 | Z | 2024-06-05 | 20 | 0 | 0 |  | 0 | 40 |  | Flat stock |  | 5
2024-06-03 | 3232 | sp | 72959 | A | DONE | 2 | S | ss | UW-VET MED 2230012 |  | 2024-06-04 | Z | 2024-05-28 | 20 | 0 | 0 |  | 0 | 20 |  | CB 1531 |  | 7
2024-06-06 | 3233 |  | 72960 | A | DONE | 2 | S | ss | UW-VET MED 2230020 |  | 2024-06-10 | Z | 2024-05-30 | 20 | 0 | 0 |  | 0 | 20 |  | Pipe cover |  | 11
2024-06-03 | 3224 | bth | 72441 - 72442 | A | DONE | 14 | S-M |  | UW-VET MED 6210014 |  | 2024-06-04 | Z | 2024-05-21 | 100 | 100 | 130 | F | 0 | 360 |  | F4-EA |  | 14
2024-06-03 | 3225 |  | 72443 - 72444 | A | DONE | 9 | S-M |  | UW-VET MED 6210014 | VD | 2024-06-04 | Z | 2024-05-21 | 120 | 0 | 100 | F | 0 | 260 |  | F4-SA |  | 14
2024-06-03 | 3226 |  | 72445 - 72448 | A | DONE | 4 | S |  | UW-VET MED 6210014 | reheat coil | 2024-06-04 | Z | 2024-05-21 | 90 | 0 | 0 |  | 0 | 130 |  | F4-SA |  | 14
2024-06-03 | 3228 | bth | 72951 - 72952 | A | DONE | 13 | S-M |  | UW-VET MED 6210014 | VD | 2024-06-04 | Z | 2024-05-21 | 80 | 220 | 20 | F | 0 | 320 |  | F1-EA |  | 14
2024-06-03 | 3229 |  | 72953 - 72955 | A | DONE | 6 | S-M |  | UW-VET MED 6210014 | VD , reheat coil | 2024-06-04 | Z | 2024-05-21 | 130 | 0 | 20 | F | 0 | 170 |  | F1-SA |  | 14
2024-06-03 | 3231 | bth | 72957 - 72958 | A | DONE | 4 | S-M |  | UW-VET MED 6210014 | reheat coil | 2024-06-04 | Z | 2024-05-21 | 30 | 50 | 0 |  | 0 | 70 |  | RM 1126 |  | 14
2024-06-06 | 3234 |  | 72961 | A | DONE | 3 | S |  | UW-VET MED 6210014 | flex | 2024-06-10 | Z | 2024-06-03 | 60 | 0 | 0 |  | 0 | 130 |  | FCU-23 |  | 7
2024-06-05 | 3235 | sp | 72962 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-06-10 | Z | 2024-06-04 | 20 | 0 | 0 |  | 0 | 20 |  | L1-E4 |  | 6
[6 empty] | 973 | [13 empty] | 35430 |  |  |  | 5500 | 15.52%
WEEK OF 6-10-2024
2024-06-13 | 2234 | w | 23908 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 |  | 2024-06-17 | Z | 2024-06-12 | 50 | 0 | 0 |  | 0 | 120 |  | Duct wall sleeves L2-L13 |  | 5
2024-06-10 | 1758 |  | 68049 | A | DONE | 4 | S-M |  | BLACKHAWK BTC 6230025 | flex , bird s. , 1" liner | 2024-06-13 | Z | 2024-06-03 | 90 | 0 | 0 |  | 50 | 160 |  | Clean Rm |  | 10
2024-06-11 | 851 | bth | L5-A-EAMP-009 | A | DONE | 6 | S | neal | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 50 | 20 | 80 | F | 0 | 180 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 852 | bth | L5-A-SAMP-001 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 60 | 90 | 0 |  | 0 | 160 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 853 | bth | L5-B-EAMP-001 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 50 | 20 | 120 | F | 0 | 230 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 854 | bth | L5-B-EAMP-002 | A | DONE | 14 | S-M | neal | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 250 | 20 | 60 | F | 0 | 400 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 855 | bth | L5-B-EAMP-003 | A | DONE | 22 | M | neal | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 350 | 20 | 160 | F | 0 | 790 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 856 | bth | L5-B-EAMP-004 | A | DONE | 20 | M | neal | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 320 | 50 | 120 | F | 0 | 780 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 857 | bth | L5-B-EAMP-005 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 60 | 50 | 120 | F | 0 | 280 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 858 | bth | L5-B-EAMP-006 | A | DONE | 13 | S-M | neal | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 150 | 20 | 140 | F | 0 | 360 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 859 | bth | L5-B-EAMP-007 | A | DONE | 12 | S | neal | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 150 | 20 | 120 | F | 0 | 340 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 860 | bth | L5-B-EAMP-008 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 200 | 20 | 30 | F | 0 | 280 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 861 | bth | L5-B-EAMP-009 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 30 | 70 | 150 | F | 0 | 280 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 862 | bth | L5-SAMP-001 | A | DONE | 19 | M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 80 | 30 | 350 | F | 0 | 670 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 863 | bth | L5-SAMP-002 | A | DONE | 25 | M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 310 | 30 | 270 | F | 0 | 940 |  |  |  | 27 |  | 2024-06-18
2024-06-12 | 864 | bth | L5-SAMP-003 | A | DONE | 21 | M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 440 | 20 | 60 | F | 0 | 870 |  |  |  | 27 |  | 2024-06-18
2024-06-12 | 865 | bth | L5-SAMP-004 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 120 | 50 | 90 | F | 0 | 290 |  |  |  | 27 |  | 2024-06-18
2024-06-11 | 866 | bth | L5-SAMP-005 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 20 | 60 | 90 | F | 0 | 180 |  |  |  | 27 |  | 2024-06-18
2024-06-12 | 867 | bth | L5-SAMP-006 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 120 | 30 | 210 | F | 0 | 440 |  |  |  | 27 |  | 2024-06-18
2024-06-12 | 868 | bth | L5-SAMP-007 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 150 | 20 | 150 | F | 0 | 390 |  |  |  | 27 |  | 2024-06-18
2024-06-12 | 869 | bth | L5-SAMP-008 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 190 | 50 | 100 | F | 0 | 420 |  |  |  | 27 |  | 2024-06-18
2024-06-12 | 870 | bth | L5-SAMP-009 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-05-17 | 120 | 20 | 90 | F | 0 | 280 |  |  |  | 27 |  | 2024-06-18
2024-06-14 | 871 | sp | L5-B-EALP-001 | A | DONE | 7 | S | pt.neal | CDIS 6220028 |  | 2024-06-18 | Z | 2024-05-21 | 50 | 120 | 0 |  | 0 | 170 |  |  |  | 28 |  | 2024-06-25
2024-06-14 | 872 | bth | L5-B-EALP-002 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 | paint | 2024-06-18 | Z | 2024-05-21 | 80 | 130 | 30 | F | 20 | 260 |  |  |  | 28 |  | 2024-06-25
2024-06-13 | 873 | bth | L5-B-EALP-003 | A | DONE | 7 | S | pt.neal | CDIS 6220028 |  | 2024-06-18 | Z | 2024-05-21 | 90 | 80 | 0 |  | 0 | 190 |  |  |  | 28 |  | 2024-06-25
2024-06-14 | 874 | sp | L5-B-EALP-004 | A | DONE | 6 | S | pt.neal | CDIS 6220028 | paint | 2024-06-18 | Z | 2024-05-21 | 40 | 100 | 0 |  | 20 | 150 |  |  |  | 28 |  | 2024-06-25
2024-06-14 | 875 | sp | L5-B-EALP-005 | A | DONE | 6 | S | pt.neal | CDIS 6220028 | paint | 2024-06-18 | Z | 2024-05-21 | 50 | 90 | 0 |  | 20 | 140 |  |  |  | 28 |  | 2024-06-25
2024-06-13 | 876 | sp | L5-B-EALP-006 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-06-18 | Z | 2024-05-21 | 40 | 120 | 0 |  | 0 | 150 |  |  |  | 28 |  | 2024-06-25
2024-06-14 | 877 | bth | L5-A-EALP-013 | A | DONE | 2 | S | neal | CDIS 6220028 | paint | 2024-06-18 | Z | 2024-05-21 | 30 | 20 | 0 |  | 20 | 50 |  |  |  | 28 |  | 2024-06-25
2024-06-14 | 878 | bth | L5-B-SALP-001 | A | DONE | 9 | S-M | pt.neal | CDIS 6220028 | paint | 2024-06-18 | Z | 2024-05-21 | 100 | 120 | 0 |  | 40 | 260 |  |  |  | 28 |  | 2024-06-25
2024-06-14 | 879 | bth | L5-B-SALP-002 | A | DONE | 15 | S-M |  | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 150 | 20 | 200 | F | 20 | 440 |  |  |  | 28 |  | 2024-06-25
2024-06-14 | 889 | bth | L5-B-SALP-012 | A | DONE | 7 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 50 | 120 | 0 |  | 20 | 180 |  |  |  | 28 |  | 2024-06-25
2024-06-10 | 951 |  | 57939 - 57940 | A | DONE | 50 | L |  | CDIS 6220028 |  | 2024-06-11 | Z | 2024-05-30 | 480 | 0 | 750 | F | 0 | 2560 |  | Shaft |  | 12
2024-06-11 | 956 |  | 57941 | A | DONE | 16 | M |  | CDIS 6220028 |  | 2024-06-13 | Z | 2024-06-04 | 260 | 0 | 120 | F | 0 | 820 |  | EA 7th |  | 9
2024-06-10 | 959 |  | 59498 | A | DONE | 4 | S-M |  | CDIS 6220028 | VD's | 2024-06-11 | Z | 2024-06-05 | 90 | 0 | 0 |  | 60 | 130 |  | 3rd Floor |  | 6
2024-06-12 | 960 |  | 69651 | A | DONE | 2 | S | neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-06-06 | 20 | 0 | 0 |  | 20 | 20 |  | Basement |  | 12
2024-06-12 | 993 |  | 69873 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-18 | Z | 2024-06-06 | 20 | 0 | 0 |  | 0 | 20 |  | SAMP-007 |  | 12
2024-06-12 | 994 |  | 69874 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-18 | Z | 2024-06-11 | 20 | 0 | 0 |  | 0 | 20 |  | RA Tap |  | 7
2024-06-12 | 995 | sp | 69875 | A | DONE | 4 | S-M | pt.neal | CDIS 6220028 |  | 2024-06-18 | Z | 2024-06-11 | 0 | 80 | 0 |  | 0 | 80 |  | Extra Spiral |  | 7
2024-06-14 | 996 |  | 69878 | A | DONE | 2 | S | neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-06-11 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 7
2024-06-14 | 1024 |  | 69879 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-06-18 | Z | 2024-06-12 | 20 | 0 | 0 |  | 0 | 40 |  | Tear Drop |  | 6
2024-06-13 | r3559 | bth | L4-B-EALP-18 | A | DONE | 4 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-06-11 | 60 | 20 | 0 |  | 0 | 90 |  |  |  | 7
2024-06-12 | 187 | sp | 79761 | A | DONE | 11 | S-M |  | COMPASS HP 4230088 | oval , accuflange | 2024-06-17 | Z | 2024-05-29 | 180 | 90 | 0 |  | 0 | 310 |  | High side |  | 19
2024-06-11 | 1590 |  | 62387 | A | DONE | 2 | S |  | EMBASSY SUITES 6220012 |  | 2024-06-13 | Z | 2024-06-07 | 20 | 0 | 0 |  | 0 | 20 |  | Elev. Mech |  | 6
2024-06-13 | 1591 |  | 62388 | A | DONE | 2 | S | pt.ss | EMBASSY SUITES 6220012 |  | 2024-06-14 | Z | 2024-06-13 | 30 | 0 | 0 |  | 0 | 30 |  | Shrouds |  | 1
2024-06-11 | 2561 |  | 41339 - 41340 | A | DONE | 6 | M |  | EXACT BIO 2240028 | VD | 2024-06-14 | Z | 2024-05-30 | 140 | 0 | 0 |  | 0 | 230 |  | CO2 EA |  | 15
2024-06-10 | 2962 | bth | 69268 - 69269 | A | DONE | 4 | S-M |  | HERITAGE 6220024 | bird s. | 2024-06-14 | Z | 2024-06-04 | 50 | 50 | 0 |  | 0 | 120 |  | PRV-3 , KILN |  | 10
2024-06-11 | 2963 | bth | 69270 - 69271 | A | DONE | 4 | S-M |  | HERITAGE 6220024 | paint | 2024-06-14 | Z | 2024-06-04 | 80 | 20 | 0 |  | 60 | 120 |  | Rm 2098 SA , 2nd fl tie in |  | 10
2024-06-10 | 2964 |  | 69273 - 69274 | A | DONE | 8 | S-M |  | HERITAGE 6220024 | paint | 2024-06-14 | Z | 2024-06-05 | 180 | 0 | 0 |  | 130 | 230 |  | 2nd Floor |  | 9
2024-06-12 | 2965 |  | 69275 - 69276 | A | DONE | 5 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-06-14 | Z | 2024-06-05 | 110 | 0 | 0 |  | 70 | 180 |  | Rm 2004 |  | 9
2024-06-11 | 2966 |  | 69277 | A | DONE | 2 | S-M |  | HERITAGE 6220024 |  | 2024-06-14 | Z | 2024-06-05 | 30 | 0 | 0 |  | 0 | 40 |  | Ceiling tie ins |  | 9
2024-06-12 | 2967 |  | 67553 - 67554 | A | DONE | 2 | S |  | HERITAGE 6220024 | 1" liner , paint | 2024-06-14 | Z | 2024-06-10 | 50 | 0 | 0 |  | 30 | 80 |  | 1st floor RA |  | 4
2024-06-11 | 2968 |  | 67555 | A | DONE | 2 | S | alum | HERITAGE 6220024 |  | 2024-06-14 | Z | 2024-06-10 | 20 | 0 | 0 |  | 0 | 20 |  | Dryer |  | 4
2024-06-12 | 2969 | bth | 67556 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-06-14 | Z | 2024-06-10 | 30 | 20 | 0 |  | 0 | 50 |  | Data Office |  | 4
2024-06-13 | 2970 |  | 69284 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-06-14 | Z | 2024-06-10 | 20 | 0 | 0 |  | 0 | 30 |  | 2nd A-Section |  | 4
2024-06-12 | 718 |  | 71533 | A | DONE | 2 | S-M |  | HILLDALE 6240003 |  | 2024-06-17 | Z | 2024-05-29 | 40 | 0 | 0 |  | 0 | 120 |  | RTU-6 |  | 19
2024-06-14 | 719 |  | 71536 | A | DONE | 4 | S-M |  | HILLDALE 6240003 | flex | 2024-06-19 | Z | 2024-06-04 | 80 | 0 | 0 |  | 0 | 120 |  | RTU-12 Drops |  | 15
2024-06-11 | 1700 |  | 200020 | A | DONE | 6 | S-M | pt.neal | INVENRA 6230001 | 1" liner | 2024-06-12 | Z | 2024-05-29 | 140 | 0 | 0 |  | 0 | 210 |  | FCU |  | 14
2024-06-11 | 1701 |  | 200021 | A | DONE | 2 | S-M | neal | INVENRA 6230001 |  | 2024-06-13 | Z | 2024-05-29 | 30 | 0 | 0 |  | 0 | 60 |  | EA |  | 15
2024-06-14 | 1704 |  | 80206 - 80208 | A | DONE | 12 | M | neal | INVENRA 6230001 | 1" liner , perf | 2024-06-18 | Z | 2024-05-29 | 300 | 0 | 0 |  | 200 | 460 |  | Silencers |  | 20
2024-06-10 | 2841 |  | 70824 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-06-13 | Z | 2024-05-30 | 30 | 0 | 0 |  | 0 | 30 |  | AHU-1 SA |  | 14
2024-06-10 | 2842 |  | 70825 | A | DONE | 9 | S-M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-06-13 | Z | 2024-06-03 | 40 | 180 | 0 |  | 190 | 260 |  | BCU-2 SA |  | 10
2024-06-10 | 2844 |  | 70827 | A | DONE | 10 | S-M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-06-13 | Z | 2024-06-03 | 30 | 0 | 210 | F | 210 | 350 |  | BCU-3 SA |  | 10
2024-06-10 | 2172 |  | 68608 - 68609 | A | DONE | 8 | S-M |  | MEMORIAL HS 6210024 |  | 2024-06-11 | Z | 2024-05-30 | 200 | 0 | 0 |  | 0 | 280 |  | HP Tie ins |  | 12
2024-06-10 | 2173 |  | 68610 - 68611 | A | DONE | 14 | M |  | MEMORIAL HS 6210024 |  | 2024-06-11 | Z | 2024-05-30 | 330 | 0 | 0 |  | 0 | 580 |  | HP Tie ins |  | 12
2024-06-13 | 2175 | bth | 68612 , 68614 | A | DONE | 2 | S-M |  | MEMORIAL HS 6210024 | flex | 2024-06-18 | Z | 2024-06-04 | 30 | 20 | 0 |  | 0 | 50 |  | Conn. Fan |  | 14
2024-06-11 | 2176 |  | 68591 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-06-18 | Z | 2024-06-05 | 20 | 0 | 0 |  | 0 | 30 |  | Unit angle |  | 13
2024-06-10 | 1429 | sp | 67489 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | spiral mate , flex | 2024-06-11 | Z | 2024-05-28 | 20 | 0 | 0 |  | 0 | 20 |  | RF-4,5,6 |  | 14
2024-06-10 | 1439 |  | 53689 | A | DONE | 7 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-06-11 | Z | 2024-06-04 | 160 | 0 | 0 |  | 0 | 280 |  | Misc |  | 7
2024-06-10 | 1440 |  | 53690 | A | DONE | 11 | M |  | MENDOTA FOODS 6220027 |  | 2024-06-13 | Z | 2024-06-06 | 270 | 0 | 0 |  | 0 | 720 |  | AHU-4 Louver |  | 7
2024-06-10 | 1441 |  | 67493 - 67495 | A | DONE | 17 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-06-13 | Z | 2024-06-06 | 420 | 0 | 0 |  | 0 | 580 |  | Outs |  | 7
2024-06-10 | 1442 |  | 53691 - 53692 | A | DONE | 3 | S |  | MENDOTA FOODS 6220027 |  | 2024-06-13 | Z | 2024-06-07 | 90 | 0 | 0 |  | 0 | 160 |  | AHU-4 , 5 |  | 6
2024-06-11 | 1443 |  | 67496 - 67498 | A | DONE | 18 | S-M | pt.alum | MENDOTA FOODS 6220027 |  | 2024-06-13 | Z | 2024-06-10 | 330 | 0 | 120 | F | 0 | 570 |  | Outs |  | 3
2024-06-10 | 3100 | sp | 79652 - 79653 | A | DONE | 4 | S-M |  | PECATONICA 6240005 |  | 2024-06-17 | Z | 2024-03-25 | 30 | 70 | 0 |  | 0 | 90 |  | Admin 203 LPSA |  | 84
2024-06-11 | 3110 |  | 79651 | A | DONE | 3 | S |  | PECATONICA 6240005 | 2" liner | 2024-06-17 | Z | 2024-03-25 | 30 | 0 | 30 | F | 40 | 70 |  | Admin 203 LPSA |  | 84
2024-06-12 | 1824 | sp | L0-SAMP-03 | A | DONE | 6 | S-M |  | PROMEGA BTC 6230022 |  | 2024-06-17 | Z | 2024-06-04 | 50 | 190 | 0 |  | 0 | 250 |  |  |  | 13
2024-06-10 | 1826 |  | 56282 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-06-11 | Z | 2024-06-10 | 50 | 0 | 0 |  | 0 | 60 |  | Excerscise Rm. |  | 1
2024-06-13 | 1827 | sp | 56284 | A | DONE | 4 | S | neal | PROMEGA BTC 6230022 |  | 2024-06-17 | Z | 2024-06-12 | 20 | 80 | 0 |  | 0 | 120 |  | Engineering |  | 5
2024-06-14 | 1828 |  | 59805 - 59806 | A | DONE | 8 | S-M |  | PROMEGA BTC 6230022 |  | 2024-06-19 | Z | 2024-06-13 | 170 | 0 | 30 | F | 0 | 260 |  | SA Main |  | 6
2024-06-11 | 1988 |  | 56283 | A | DONE | 2 | S |  | PROMEGA FEYNMANN 6220014 | bird s. | 2024-06-12 | Z | 2024-06-11 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2024-06-12 | 3050 | sp | 72388 | A | DONE | 2 | S |  | RAMC 6230009 | oval | 2024-06-17 | Z | 2024-06-04 | 40 | 0 | 0 |  | 0 | 50 |  | LL SA out |  | 13
2024-06-11 | 3051 | sp | 72389 | A | DONE | 4 | S |  | RAMC 6230009 |  | 2024-06-17 | Z | 2024-06-06 | 30 | 50 | 0 |  | 0 | 80 |  | LL-SAMP-9,10 |  | 11
2024-06-12 | 3003 |  | 62533 | A | DONE | 2 | S |  | RETRO CX 6240004 |  | 2024-06-17 | Z | 2024-06-06 | 50 | 0 | 0 |  | 0 | 90 |  | RF-5,7 |  | 11
2024-06-13 | 192 |  | 79769 | A | DONE | 2 | S |  | REYNOLDS 10055407 | filter rack | 2024-06-17 | Z | 2024-06-13 | 30 | 0 | 0 |  | 0 | 30 |  | Furnace |  | 4
2024-06-10 | 4761 |  | 78959 | A | DONE | 2 | S | neal | ROCK CO. JAIL 6220018 |  | 2024-06-13 | Z | 2024-05-30 | 40 | 0 | 0 |  | 0 | 210 |  | Pipe enclosure |  | 14
2024-06-11 | 4250 |  | 79952 | A | DONE | 2 | S | pt.neal | ST.BERNARD 6230023 |  | 2024-06-17 | Z | 2024-06-04 | 30 | 0 | 0 |  | 0 | 50 |  | Misc |  | 13
2024-06-11 | 4251 |  | 79954 | A | DONE | 2 | S |  | ST.BERNARD 6230023 | 1" liner | 2024-06-17 | Z | 2024-06-05 | 20 | 0 | 0 |  | 20 | 20 |  | RA |  | 12
2024-06-12 | 3974 |  | SHAFT-194L-EAMP | A | DONE | 40 | M-L |  | UWRF 6230010 |  | 2024-06-17 | Z | 2024-05-07 | 640 | 0 | 350 | F | 0 | 2100 |  |  |  | 41
2024-06-12 | 3975 |  | SHAFT-194L-FEMP | A | DONE | 29 | M-L | pcd | UWRF 6230010 |  | 2024-06-17 | Z | 2024-05-07 | 310 | 0 | 400 | F | 0 | 1200 |  |  |  | 41
2024-06-13 | 3976 |  | SHAFT-194L-SAMP | A | DONE | 55 | L |  | UWRF 6230010 |  | 2024-06-17 | Z | 2024-05-07 | 760 | 0 | 600 | F | 0 | 2880 |  |  |  | 41
2024-06-13 | 3977 |  | SHAFT-194M-EAMP | A | DONE | 32 | M-L |  | UWRF 6230010 |  | 2024-06-17 | Z | 2024-05-07 | 430 | 0 | 370 | F | 0 | 1610 |  |  |  | 41
2024-06-13 | 4129 |  | 66915 | A | DONE | 10 | S-M | neal | UWRF 6230010 |  | 2024-06-19 | Z | 2024-06-04 | 230 | 0 | 0 |  | 0 | 320 |  | L2 Misc |  | 15
2024-06-11 | 4149 |  | 70534 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-06-11 | Z | 2024-06-11 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-06-12 | 4150 |  | 70152 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-06-17 | Z | 2024-06-11 | 50 | 0 | 0 |  | 0 | 100 |  | Shaft 194N-RAMP |  | 6
2024-06-10 | 3236 |  | 72965 | A | DONE | 2 | S |  | UW-VET MED 6210014 | VD | 2024-06-11 | Z | 2024-06-04 | 30 | 0 | 0 |  | 0 | 30 |  | Arena |  | 7
2024-06-10 | 3237 |  | 72966 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-06-11 | Z | 2024-06-10 | 50 | 0 | 0 |  | 0 | 70 |  | South |  | 1
2024-06-12 | 3238 |  | 72967 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-06-17 | Z | 2024-06-11 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2024-06-13 | 3239 |  | 72968 | A | DONE | 6 | S-M |  | UW-VET MED 6210014 |  | 2024-06-18 | Z | 2024-06-12 | 50 | 0 | 90 | F | 0 | 160 |  | FCU-23 |  | 6
2024-06-13 | 3240 |  | 72969 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-06-18 | Z | 2024-06-12 | 20 | 0 | 0 |  | 0 | 40 |  | South F4 |  | 6
2024-06-12 | 193 |  | 78731 | A | DONE | 7 | S |  | WHS AHU5 4230041 | flex | 2024-06-13 | Z | 2024-06-12 | 170 | 0 | 0 |  | 0 | 490 |  | AHU 5 |  | 1
[6 empty] | 855 | [13 empty] | 31410 |  |  |  | 10770 | 34.29%
WEEK OF 6-17-2024
2024-06-20 | 2205 |  | Stairwell-B-EA-6 | A | DONE | 13 | S-M |  | 121 E. WILSON 6230024 |  | 2024-06-24 | Z | 2024-06-06 | 130 | 0 | 190 | F | 0 | 400 |  |  |  | 18
2024-06-20 | 2206 |  | Stairwell-B-EA-7 | A | DONE | 13 | S-M |  | 121 E. WILSON 6230024 |  | 2024-06-24 | Z | 2024-06-06 | 130 | 0 | 180 | F | 0 | 370 |  |  |  | 18
2024-06-20 | 2207 |  | Stairwell-A-EA-2 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 |  | 2024-06-24 | Z | 2024-06-06 | 230 | 0 | 140 | F | 0 | 430 |  |  |  | 18
2024-06-21 | 2208 |  | Stairwell-A-EA-1 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 |  | 2024-06-24 | Z | 2024-06-06 | 110 | 0 | 90 | F | 0 | 250 |  |  |  | 18
2024-06-19 | 2400 |  | 78888 | A | DONE | 2 | S-M |  | ABE LINCOLN 6230029 |  | 2024-06-21 | Z | 2024-06-19 | 40 | 0 | 0 |  | 0 | 50 |  | Damper cover |  | 2
2024-06-18 | 1759 |  | 68050 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 | 1" Liner | 2024-06-20 | Z | 2024-06-10 | 30 | 0 | 0 |  | 30 | 80 |  | Misc |  | 10
2024-06-17 | 195 |  | 78727 | A | DONE | 2 | S |  | BOB H. 10054816 |  | 2024-06-18 | Z | 2024-06-17 | 30 | 0 | 0 |  | 0 | 30 |  | Misc |  | 1
2024-06-19 | 197 |  | 78732 | A | DONE | 2 | S |  | BOB H. 10054816 |  | 2024-06-19 | Z | 2024-06-19 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-06-17 | 880 | bth | L5-B-SALP-003 | A | DONE | 9 | S-M | neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 150 | 50 | 20 | F | 40 | 270 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 881 | bth | L5-B-SALP-004 | A | DONE | 6 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 60 | 80 | 0 |  | 30 | 210 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 882 | bth | L5-B-SALP-005 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 60 | 60 | 0 |  | 30 | 130 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 883 | bth | L5-B-SALP-006 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 110 | 120 | 0 |  | 40 | 250 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 884 | bth | L5-B-SALP-007 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 50 | 70 | 0 |  | 20 | 130 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 885 | bth | L5-B-SALP-008 | A | DONE | 7 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 80 | 90 | 0 |  | 30 | 180 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 886 | bth | L5-B-SALP-009 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 100 | 100 | 40 | F | 30 | 280 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 887 |  | L5-B-SALP-010 | A | DONE | 4 | S |  | CDIS 6220028 | paint , 1" liner | 2024-06-18 | Z | 2024-05-21 | 40 | 0 | 40 | F | 40 | 90 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 888 | bth | L5-B-SALP-011 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 50 | 90 | 0 |  | 20 | 150 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 890 | bth | L5-B-SALP-013 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 40 | 60 | 0 |  | 20 | 100 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 891 | bth | L5-B-SALP-014 | A | DONE | 12 | S-M |  | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 190 | 110 | 0 |  | 90 | 330 |  |  |  | 28 |  | 2024-06-25
2024-06-17 | 892 | bth | L5-B-SALP-015 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-06-18 | Z | 2024-05-21 | 40 | 60 | 0 |  | 20 | 100 |  |  |  | 28 |  | 2024-06-25
2024-06-18 | 894 | bth | L5-A-EAMP-001 | A | DONE | 12 | S-M | pt.neal | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 170 | 60 | 70 | F | 0 | 370 |  |  |  | 30 |  | 2024-07-02
2024-06-18 | 895 | bth | L5-A-EAMP-002 | A | DONE | 14 | S-M | neal | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 90 | 50 | 210 | F | 0 | 420 |  |  |  | 30 |  | 2024-07-02
2024-06-18 | 896 | bth | L5-A-EAMP-003 | A | DONE | 19 | M | neal | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 100 | 60 | 310 | F | 0 | 580 |  |  |  | 30 |  | 2024-07-02
2024-06-18 | 897 | bth | L5-A-EAMP-006 | A | DONE | 26 | M | neal | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 430 | 50 | 170 | F | 0 | 890 |  |  |  | 30 |  | 2024-07-02
2024-06-18 | 898 | bth | L5-A-SAMP-002 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 40 | 120 | 40 | F | 0 | 200 |  |  |  | 30 |  | 2024-07-02
2024-06-19 | 899 | bth | L5-A-SAMP-003 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 190 | 30 | 150 | F | 0 | 440 |  |  |  | 30 |  | 2024-07-02
2024-06-19 | 900 | bth | L5-A-SAMP-004 | A | DONE | 20 | M |  | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 150 | 100 | 230 | F | 0 | 610 |  |  |  | 30 |  | 2024-07-02
2024-06-19 | 901 | bth | L5-A-SAMP-005 | A | DONE | 21 | M |  | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 270 | 70 | 170 | F | 0 | 650 |  |  |  | 30 |  | 2024-07-02
2024-06-19 | 902 | bth | L5-A-SAMP-006 | A | DONE | 27 | M |  | CDIS 6220028 |  | 2024-06-20 | Z | 2024-05-21 | 240 | 30 | 400 | F | 0 | 940 |  |  |  | 30 |  | 2024-07-02
2024-06-21 | 1025 | sp | 61044 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-06-25 | Z | 2024-06-12 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd Floor A EAD 59 |  | 13
2024-06-21 | 1026 |  | 69880 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-25 | Z | 2024-06-13 | 20 | 0 | 0 |  | 0 | 30 |  | SALP-027-B |  | 12
2024-06-17 | 1027 |  | 61358 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-06-20 | Z | 2024-06-17 | 100 | 0 | 0 |  | 0 | 130 |  | Misc |  | 3
2024-06-18 | 1028 |  | 94263 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-20 | Z | 2024-06-17 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 3
2024-06-21 | 1056 |  | 69508 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-06-24 | Z | 2024-06-20 | 250 | 0 | 0 |  | 0 | 480 |  | PH Sleeves |  | 4
2024-06-19 | r3855 | sp | BSMT-A-SAMP-068 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-06-20 | Z | 2024-06-18 | 0 | 110 | 0 |  | 0 | 160 |  |  |  | 2
2024-06-18 | r4048 | sp | L1-A-SAMP-046 | A | DONE | 5 | S | neal | CDIS 6220028 | s.mates | 2024-06-20 | Z | 2024-06-18 | 20 | 90 | 0 |  | 0 | 150 |  |  |  | 2
2024-06-20 | 190 | sp | 79763 - 79765 | A | DONE | 18 | M |  | COMPASS HP 4230088 | oval | 2024-06-24 | Z | 2024-06-06 | 140 | 300 | 0 |  | 0 | 460 |  | VAV 7-9 |  | 18
2024-06-20 | 191 | sp | 79767 - 79768 | A | DONE | 6 | S-M |  | COMPASS HP 4230088 | oval | 2024-06-24 | Z | 2024-06-06 | 70 | 80 | 0 |  | 0 | 160 |  | VAV 17 |  | 18
2024-06-21 | 1133 | w | 86025 | A | DONE | 2 | S | ss | DANE CO. AIRPORT 2240042 |  | 2024-06-21 | Z | 2024-06-21 | 20 | 0 | 0 |  | 0 | 80 |  | Pan |  | 0
2024-06-17 | 2564 |  | 41341 | A | DONE | 2 | S |  | EXACT BIO 2240028 |  | 2024-06-18 | Z | 2024-06-17 | 30 | 0 | 0 |  | 0 | 40 |  | EA |  | 1
2024-06-18 | 4615 |  | 79457 | A | DONE | 2 | S |  | HARMONICS 6240010 | flex, bird s. | 2024-06-19 | Z | 2024-06-17 | 50 | 0 | 0 |  | 0 | 70 |  | EF-1 |  | 2
2024-06-18 | 4616 |  | 79461 | A | DONE | 2 | S | neal | HARMONICS 6240010 |  | 2024-06-18 | Z | 2024-06-18 | 20 | 0 | 0 |  | 0 | 30 |  | Hangers |  | 0
2024-06-19 | 2971 |  | 69278 - 69279 | A | DONE | 3 | S-M |  | HERITAGE 6220024 | 1" liner | 2024-06-21 | Z | 2024-06-17 | 70 | 0 | 0 |  | 20 | 100 |  | 2nd A RA , A-Corr. RA |  | 4
2024-06-18 | 2972 |  | 69280 | A | DONE | 2 | S |  | HERITAGE 6220024 | paint | 2024-06-21 | Z | 2024-06-18 | 40 | 0 | 0 |  | 30 | 50 |  | LMTC-2001 |  | 3
2024-06-17 | 1703 |  | 80202 - 80205 | A | DONE | 12 | M | neal | INVENRA 6230001 | 1" liner , perf | 2024-06-18 | Z | 2024-05-29 | 300 | 0 | 0 |  | 210 | 650 |  | Silencers |  | 20
2024-06-18 | 1706 |  | 80209 | A | DONE | 2 | S |  | INVENRA 6230001 |  | 2024-06-19 | Z | 2024-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-410 |  | 2
2024-06-19 | 1707 |  | 80210 | A | DONE | 2 | S | neal | INVENRA 6230001 | 1" liner | 2024-06-19 | Z | 2024-06-19 | 30 | 0 | 0 |  | 20 | 40 |  | FCU-411 |  | 0
2024-06-18 | 2845 |  | 70831 - 70833 | A | DONE | 11 | S-M |  | JANESVILLE ESSR 6230011 | VD | 2024-06-20 | Z | 2024-06-04 | 200 | 0 | 60 | F | 180 | 300 |  | BCU-RA |  | 16
2024-06-17 | 2846 |  | 70834 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | paint | 2024-06-20 | Z | 2024-06-04 | 20 | 0 | 0 |  | 20 | 40 |  | Misc |  | 16
2024-06-17 | 2847 |  | 62428 | A | DONE | 3 | S |  | JANESVILLE ESSR 6230011 |  | 2024-06-20 | Z | 2024-06-17 | 60 | 0 | 0 |  | 0 | 60 |  | D-section |  | 3
2024-06-19 | 2321 | sp | 67711 | A | DONE | 3 | S |  | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-17 | 30 | 30 | 0 |  | 0 | 60 |  | EVAV |  | 4
2024-06-19 | 3735 | sp | 55193 | A | DONE | 11 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-06 | 100 | 160 | 0 |  | 0 | 310 |  | EA |  | 15
2024-06-19 | 3736 | sp | 55194 - 55196 | A | DONE | 21 | S-M | alum | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-06 | 160 | 350 | 0 |  | 0 | 260 |  | EVAV |  | 15
2024-06-19 | 3737 | sp | 55197 | A | DONE | 7 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-06 | 50 | 110 | 0 |  | 0 | 180 |  | SA |  | 15
2024-06-19 | 3738 |  | 55198 - 55199 | A | DONE | 8 | S | neal | KOHL CENTER 6210034 | 1/2" & 1" liner | 2024-06-21 | Z | 2024-06-06 | 130 | 0 | 50 | F | 30 | 200 |  | VAV-A16 |  | 15
2024-06-18 | 3739 |  | 55200 | A | DONE | 2 | S |  | KOHL CENTER 6210034 | 1/2" & 1" liner | 2024-06-21 | Z | 2024-06-06 | 20 | 0 | 30 | F | 30 | 60 |  | VAV |  | 15
2024-06-19 | 3740 | sp | 67666 | A | DONE | 6 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-06 | 30 | 110 | 0 |  | 0 | 130 |  | VAV |  | 15
2024-06-19 | 3741 |  | 67667 | A | DONE | 5 | S-M |  | KOHL CENTER 6210034 | 1/2" & 1" liner | 2024-06-21 | Z | 2024-06-06 | 80 | 0 | 30 | F | 80 | 120 |  | VAV |  | 15
2024-06-19 | 3742 | bth | 67668 - 67669 | A | DONE | 13 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-06 | 100 | 140 | 80 | F | 0 | 330 |  | VAV |  | 15
2024-06-19 | 3743 | sp | 67670 , 67672 | A | DONE | 12 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-06 | 110 | 180 | 0 |  | 0 | 290 |  | EA B-Section |  | 15
2024-06-19 | 3744 |  | 67671 | A | DONE | 4 | S-M | alum | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-06 | 40 | 60 | 0 |  | 0 | 70 |  | EA B-Section |  | 15
2024-06-19 | 3745 |  | 67673 - 67674 | A | DONE | 5 | S-M |  | KOHL CENTER 6210034 | 1/2" liner | 2024-06-21 | Z | 2024-06-06 | 60 | 100 | 60 | F | 60 | 350 |  | EA B-Section |  | 15
2024-06-19 | 3746 | sp | 67676 | A | DONE | 3 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-21 | Z | 2024-06-06 | 20 | 50 | 0 |  | 0 | 60 |  | LL B VAV |  | 15
2024-06-19 | 1117 |  | 80154 | A | DONE | 4 | S |  | LABCORP 2240024 | 1" Liner | 2024-06-24 | Z | 2024-06-13 | 90 | 0 | 0 |  | 30 | 90 |  | SA/TA |  | 11
2024-06-20 | 2177 |  | 68615 | A | DONE | 5 | S |  | MEMORIAL HS 6210024 |  | 2024-06-25 | Z | 2024-06-05 | 120 | 0 | 0 |  | 0 | 190 |  | Pool Mech Rm. |  | 20
2024-06-21 | 2178 |  | 68616 | A | DONE | 9 | S-M |  | MEMORIAL HS 6210024 | 1/2" liner | 2024-06-25 | Z | 2024-06-13 | 210 | 0 | 0 |  | 80 | 320 |  | SA Tie ins |  | 12
2024-06-19 | 2179 |  | 68592 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 |  | 2024-06-25 | Z | 2024-06-14 | 50 | 0 | 0 |  | 0 | 120 |  | EC |  | 11
2024-06-18 | 1444 |  | 53693 - 53695 | A | DONE | 18 | S-M |  | MENDOTA FOODS 6220027 | flex | 2024-06-20 | Z | 2024-06-11 | 370 | 0 | 60 | F | 0 | 530 |  | RF-6-1, AHU-4, RF-5-1 |  | 9
2024-06-18 | 1445 |  | 53697 | A | DONE | 12 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-06-20 | Z | 2024-06-14 | 280 | 0 | 0 |  | 0 | 400 |  | Finals |  | 6
2024-06-18 | 1446 | bth | 67499 - 67500 | A | DONE | 14 | S-M |  | MENDOTA FOODS 6220027 | VD's | 2024-06-20 | Z | 2024-06-14 | 190 | 20 | 140 | F | 0 | 410 |  | Dishwasher |  | 6
2024-06-19 | 1448 | w | 53700 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-06-21 | Z | 2024-06-19 | 20 | 0 | 0 |  | 0 | 20 |  | Floor flashing |  | 2
2024-06-17 | 2632 |  | 79459 | A | DONE | 2 | S |  | OLIV 6210030 |  | 2024-06-19 | Z | 2024-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | Grey metal sleeve cover |  | 2
2024-06-19 | 3111 |  | 79664 | A | DONE | 2 | S |  | PECATONICA 6240005 | 2" liner | 2024-06-24 | Z | 2024-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | Admin. 203 LPSA |  | 7
2024-06-20 | 3112 | w | 81051 | A | DONE | 2 | S-M |  | PECATONICA 6240005 |  | 2024-06-24 | Z | 2024-06-18 | 50 | 0 | 0 |  | 0 | 110 |  | CCU-6 rail |  | 6
2024-06-21 | 3113 |  | 70535 | A | DONE | 2 | S |  | PECATONICA 6240005 | 2" liner | 2024-06-24 | Z | 2024-06-20 | 20 | 0 | 0 |  | 20 | 20 |  | Misc |  | 4
2024-06-17 | 1829 |  | 62899 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-06-19 | Z | 2024-06-13 | 20 | 0 | 0 |  | 0 | 20 |  | EXH-3-36 |  | 6
2024-06-19 | 3052 | bth | 72390 | A | DONE | 4 | S |  | RAMC 6230009 | flex , bird s. | 2024-06-24 | Z | 2024-06-12 | 70 | 20 | 0 |  | 0 | 100 |  | Roof EA |  | 12
2024-06-19 | 3004 |  | 62534 | A | DONE | 2 | S |  | RETRO CX 6240004 |  | 2024-06-25 | Z | 2024-06-19 | 20 | 0 | 0 |  | 0 | 20 |  | L1 Channel |  | 6
2024-06-17 | 196 |  | 79771 | A | DONE | 2 | S | neal | REYNOLDS 10055407 |  | 2024-06-18 | Z | 2024-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | Patches |  | 1
2024-06-17 | 4763 |  | 78887 | A | DONE | 5 | S |  | ROCK CO. JAIL 6220018 | bird s. | 2024-06-20 | Z | 2024-06-11 | 110 | 0 | 0 |  | 0 | 150 |  | Switch Rm |  | 9
2024-06-18 | 4764 |  | 61163 | A | DONE | 2 | S | neal | ROCK CO. JAIL 6220018 |  | 2024-06-20 | Z | 2024-06-13 | 40 | 0 | 0 |  | 0 | 120 |  | Pipe Cover |  | 7
2024-06-18 | 194 |  | 79415 - 79416 | A | DONE | 10 | S-M |  | SONOCO 10055969 | VD's | 2024-06-19 | Z | 2024-06-13 | 140 | 0 | 90 | F | 0 | 220 |  | EA |  | 6
2024-06-19 | 4253 |  | 80001 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-06-24 | Z | 2024-06-13 | 20 | 0 | 0 |  | 0 | 20 |  | Square to round |  | 11
2024-06-18 | 4252 |  | 79909 | A | DONE | 6 | S |  | ST.BERNARD 6230023 | 1" liner | 2024-06-20 | Z | 2024-06-06 | 80 | 0 | 70 | F | 120 | 180 |  | E. TA |  | 14
2024-06-18 | 3526 |  | 79326 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-06-24 | Z | 2024-06-11 | 40 | 0 | 0 |  | 0 | 70 |  | End Caps |  | 13
2024-06-18 | 4088 | bth | L1Z1-RAMP-1 | A | DONE | 25 | M | pt.neal | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 300 | 80 | 230 | F | 0 | 950 |  |  |  | 19
2024-06-17 | 4089 | bth | L1Z1-SAMP-1 | A | DONE | 53 | L |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 560 | 70 | 690 | F | 0 | 2750 |  |  |  | 19
2024-06-18 | 4090 | bth | L1Z1-SAMP-2 | A | DONE | 16 | M |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 80 | 60 | 240 | F | 0 | 520 |  |  |  | 19
2024-06-18 | 4091 | bth | L1Z1-SAMP-3 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 30 | 90 | 90 | F | 0 | 260 |  |  |  | 19
2024-06-17 | 4092 | bth | L1Z1-SAMP-4 | A | DONE | 36 | M-L |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 500 | 50 | 330 | F | 0 | 1700 |  |  |  | 19
2024-06-18 | 4093 | bth | L1Z1-SAMP-5 | A | DONE | 16 | M |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 130 | 40 | 220 | F | 0 | 560 |  |  |  | 19
2024-06-18 | 4094 | bth | L1Z1-SAMP-6 | A | DONE | 8 | S-M |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 100 | 50 | 50 | F | 0 | 250 |  |  |  | 19
2024-06-18 | 4095 | bth | L1Z1-SAMP-7 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 70 | 90 | 50 | F | 0 | 220 |  |  |  | 19
2024-06-17 | 4096 | bth | L1Z1-SAMP-8 | A | DONE | 14 | M |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 160 | 20 | 170 | F | 0 | 480 |  |  |  | 19
2024-06-17 | 4097 | bth | L1Z1-SAMP-9 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 30 | 30 | 170 | F | 0 | 380 |  |  |  | 19
2024-06-18 | 4098 | bth | L1Z1-SAMP-10 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-05-31 | 60 | 60 | 90 | F | 0 | 260 |  |  |  | 19
2024-06-21 | 4099 | bth | L1Z1-FEMP-1 | A | DONE | 23 | S-M | pcd | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 360 | 110 | 100 | F | 0 | 770 |  |  |  | 20
2024-06-20 | 4100 | bth | L1Z1-FEMP-2 | A | DONE | 15 | M | pcd | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 110 | 80 | 180 | F | 0 | 460 |  |  |  | 20
2024-06-21 | 4101 | bth | L1Z1-FEMP-3 | A | DONE | 16 | S-M | pcd | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 170 | 100 | 130 | F | 0 | 510 |  |  |  | 20
2024-06-21 | 4102 | bth | L1Z1-FEMP-4 | A | DONE | 25 | M | pcd | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 220 | 200 | 140 | F | 0 | 800 |  |  |  | 20
2024-06-19 | 4103 |  | L1Z1-FEMP-5 | A | DONE | 14 | S-M | pcd | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 130 | 0 | 210 | F | 0 | 440 |  |  |  | 20
2024-06-21 | 4104 | bth | L1Z1-FEMP-6 | A | DONE | 8 | S-M | pcd | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 70 | 90 | 30 | F | 0 | 220 |  |  |  | 20
2024-06-21 | 4105 | sp | L1Z1-EAMP-1.1 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 20
2024-06-21 | 4106 | bth | L1Z1-EAMP-1 | A | DONE | 32 | M-L |  | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 370 | 70 | 360 | F | 0 | 1400 |  |  |  | 20
2024-06-21 | 4107 | bth | L1Z1-EAMP-2 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 180 | 30 | 70 | F | 0 | 370 |  |  |  | 20
2024-06-21 | 4108 | bth | L1Z1-EAMP-3 | A | DONE | 8 | S | pt.neal | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 90 | 20 | 70 | F | 0 | 210 |  |  |  | 20
2024-06-21 | 4109 | bth | L1Z1-EAMP-4 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 200 | 30 | 70 | F | 0 | 410 |  |  |  | 20
2024-06-20 | 4110 | bth | L1Z1-EAMP-5 | A | DONE | 30 | M-L | pt.neal | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 350 | 20 | 380 | F | 0 | 1350 |  |  |  | 20
2024-06-21 | 4111 | bth | L1Z1-EAMP-6 | A | DONE | 25 | M |  | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 270 | 70 | 270 | F | 0 | 870 |  |  |  | 20
2024-06-20 | 4112 | bth | L1Z1-EAMP-7 | A | DONE | 14 | S-M | pt.neal | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 210 | 30 | 110 | F | 0 | 450 |  |  |  | 20
2024-06-21 | 4113 | bth | L1Z1-EAMP-8 | A | DONE | 11 | S-M |  | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 80 | 50 | 140 | F | 0 | 290 |  |  |  | 20
2024-06-21 | 4114 | bth | L1Z1-EAMP-9 | A | DONE | 11 | S-M |  | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 90 | 110 | 60 | F | 0 | 280 |  |  |  | 20
2024-06-20 | 4115 | bth | L1Z1-EAMP-10 | A | DONE | 9 | S | pt.neal | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-04 | 120 | 20 | 80 | F | 0 | 250 |  |  |  | 20
2024-06-18 | 4130 |  | 66916 | A | DONE | 2 | S | pcd/neal | UWRF 6230010 |  | 2024-06-19 | Z | 2024-06-04 | 20 | 0 | 0 |  | 0 | 20 |  | L2 Misc |  | 15
2024-06-17 | 4151 | sp | 66918 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-06-19 | Z | 2024-06-12 | 40 | 0 | 0 |  | 0 | 50 |  | 3rd Floor |  | 7
2024-06-20 | 4239 |  | 66919 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-20 | 20 | 0 | 0 |  | 0 | 30 |  | L3 |  | 6
2024-06-21 | r4842 | bth | L2Z2-SAMP-16 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-06-24 | Z | 2024-06-20 | 120 | 0 | 0 |  | 0 | 160 |  |  |  | 4
2024-06-21 | 5017 |  | 58795 - 58796 | A | DONE | 8 | S-M |  | UWSP-ALBERTSON 6230016 |  | 2024-06-25 | Z | 2024-06-11 | 200 | 0 | 0 |  | 0 | 310 |  | D.M Frames / Caps |  | 14
2024-06-20 | 3241 |  | 72971 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-06-25 | Z | 2024-06-17 | 20 | 0 | 0 |  | 0 | 20 |  | F1-EA |  | 8
2024-06-20 | 3242 |  | 72972 | A | DONE | 3 | S |  | UW-VET MED 6210014 |  | 2024-06-25 | Z | 2024-06-18 | 60 | 0 | 0 |  | 0 | 80 |  | FCU-23 |  | 7
[6 empty] | 1105 | [13 empty] | 35750 |  |  |  | 4880 | 13.65%
WEEK OF 6-24-2024
2024-06-28 | 2210 |  | 200022 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 | bird s. | 2024-07-02 | Z | 2024-06-11 | 120 | 0 | 170 | F | 0 | 270 |  | Misc |  | 21
2024-06-28 | 2211 |  | 200023 | A | DONE | 36 | M |  | 121 E. WILSON 6230024 | bird s. | 2024-07-02 | Z | 2024-06-11 | 340 | 0 | 540 | F | 0 | 860 |  | P109-EA |  | 21
2024-06-28 | 2212 |  | 200024 | A | DONE | 18 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-02 | Z | 2024-06-11 | 180 | 0 | 260 | F | 0 | 450 |  | ERV-3 EA |  | 21
2024-06-28 | 2213 |  | 200025 | A | DONE | 17 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-02 | Z | 2024-06-11 | 200 | 0 | 220 | F | 0 | 430 |  | ERV-3 OA |  | 21
2024-06-25 | 2401 |  | 78889 | A | DONE | 2 | S |  | ABE LINCOLN 6230029 | VD's ,1" liner | 2024-06-28 | Z | 2024-06-19 | 40 | 0 | 0 |  | 0 | 40 |  | Girls Lockeroom |  | 9
2024-06-26 | 2402 | bth | 78890 - 78891 | A | DONE | 8 | S-M |  | ABE LINCOLN 6230029 |  | 2024-06-28 | Z | 2024-06-19 | 130 | 20 | 40 | F | 70 | 180 |  | FC-118 |  | 9
2024-06-26 | 2403 | bth | 78892 , 78894 | A | DONE | 7 | S-M |  | ABE LINCOLN 6230029 |  | 2024-06-28 | Z | 2024-06-19 | 100 | 60 | 0 |  | 0 | 150 |  | FC-115 , FC-119 |  | 9
2024-06-26 | 2404 |  | 78895 - 78897 | A | DONE | 9 | S-M |  | ABE LINCOLN 6230029 | 1" liner | 2024-06-28 | Z | 2024-06-19 | 200 | 0 | 20 | F | 140 | 260 |  | FC-119 , 120 , 122 |  | 9
2024-06-26 | 2405 | bth | 78898 - 78899 | A | DONE | 8 | S-M |  | ABE LINCOLN 6230029 |  | 2024-06-28 | Z | 2024-06-19 | 50 | 70 | 60 | F | 0 | 180 |  | FC-122 |  | 9
2024-06-26 | 2406 |  | 78900 | A | DONE | 6 | S-M |  | ABE LINCOLN 6230029 | 1" liner | 2024-06-28 | Z | 2024-06-19 | 90 | 0 | 60 | F | 120 | 180 |  | TA 1 |  | 9
2024-06-26 | 2407 |  | 78960 | A | DONE | 4 | S-M |  | ABE LINCOLN 6230029 | VD's | 2024-06-28 | Z | 2024-06-19 | 80 | 0 | 0 |  | 30 | 140 |  | 2nd floor |  | 9
2024-06-26 | 2408 |  | 78893 | A | DONE | 3 | S |  | ABE LINCOLN 6230029 | 1" liner | 2024-06-28 | Z | 2024-06-19 | 50 | 0 | 20 | F | 50 | 80 |  | FC-115 |  | 9
2024-06-28 | 2410 | bth | 78962 - 78963 | A | DONE | 7 | S-M |  | ABE LINCOLN 6230029 |  | 2024-07-03 | Z | 2024-06-24 | 80 | 80 | 0 |  | 0 | 160 |  | AHU-6 |  | 9
2024-06-28 | 2411 |  | 78964 | A | DONE | 4 | S |  | ABE LINCOLN 6230029 |  | 2024-07-03 | Z | 2024-06-24 | 90 | 0 | 0 |  | 0 | 130 |  | Misc |  | 9
2024-06-25 | 1760 |  | 31238 - 31240 | A | DONE | 15 | S-M | neal | BLACKHAWK BTC 6230025 | VD's, 1" liner, s.mate | 2024-06-27 | Z | 2024-06-14 | 330 | 0 | 30 | F | 50 | 530 |  | EF , Mezz |  | 13
2024-06-28 | 1762 |  | 31243 | A | DONE | 7 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-07-03 | Z | 2024-06-17 | 30 | 40 | 0 |  | 0 | 80 |  | Weld Rm. |  | 16
2024-06-28 | 1766 |  | 31247 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 | 1" liner | 2024-07-03 | Z | 2024-06-24 | 20 | 0 | 0 |  | 20 | 20 |  | Vestibule |  | 9
2024-06-25 | 904 | sp | L5-A-EALP-001 | A | DONE | 6 | S | pt.neal | CDIS 6220028 | paint | 2024-06-25 | Z | 2024-05-24 | 30 | 100 | 0 |  | 0 | 130 |  |  |  | 32 |  | 2024-07-09
2024-06-25 | 905 | sp | L5-A-EALP-002 | A | DONE | 9 | S |  | CDIS 6220028 |  | 2024-06-25 | Z | 2024-05-24 | 60 | 160 | 0 |  | 0 | 240 |  |  |  | 32 |  | 2024-07-09
2024-06-24 | 906 | bth | L5-A-EALP-003 | A | DONE | 5 | S | pt.neal | CDIS 6220028 | VD's , paint | 2024-06-25 | Z | 2024-05-24 | 50 | 60 | 0 |  | 0 | 110 |  |  |  | 32 |  | 2024-07-09
2024-06-24 | 907 | bth | L5-A-EALP-011 | A | DONE | 8 | S | neal | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 130 | 20 | 30 | F | 40 | 200 |  |  |  | 32 |  | 2024-07-09
2024-06-24 | 908 | bth | L5-A-SALP-001 | A | DONE | 10 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 120 | 70 | 50 | F | 20 | 270 |  |  |  | 32 |  | 2024-07-09
2024-06-25 | 909 | bth | L5-A-SALP-002 | A | DONE | 8 | S |  | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 90 | 90 | 0 |  | 30 | 190 |  |  |  | 32 |  | 2024-07-09
2024-06-24 | 910 | bth | L5-A-SALP-003 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 60 | 60 | 0 |  | 20 | 130 |  |  |  | 32 |  | 2024-07-09
2024-06-25 | 911 | bth | L5-A-SALP-004 | A | DONE | 9 | S |  | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 100 | 120 | 0 |  | 40 | 230 |  |  |  | 32 |  | 2024-07-09
2024-06-25 | 912 | bth | L5-A-SALP-005 | A | DONE | 7 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 100 | 60 | 0 |  | 40 | 180 |  |  |  | 32 |  | 2024-07-09
2024-06-24 | 913 |  | L5-A-SALP-006 | A | DONE | 4 | S | neal | CDIS 6220028 | VD , 1" liner | 2024-06-25 | Z | 2024-05-24 | 100 | 0 | 0 |  | 20 | 140 |  |  |  | 32 |  | 2024-07-09
2024-06-24 | 914 | bth | L5-A-SALP-007 | A | DONE | 14 | S-M | neal | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 270 | 20 | 60 | F | 30 | 420 |  |  |  | 32 |  | 2024-07-09
2024-06-25 | 915 | bth | L5-A-SALP-008 | A | DONE | 7 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 80 | 90 | 0 |  | 30 | 200 |  |  |  | 32 |  | 2024-07-09
2024-06-24 | 916 | bth | L5-A-SALP-009 | A | DONE | 12 | S-M | neal | CDIS 6220028 | 1" liner | 2024-06-25 | Z | 2024-05-24 | 190 | 70 | 20 | F | 40 | 330 |  |  |  | 32 |  | 2024-07-09
2024-06-28 | 997 |  | SC-SAMP-006 | A | DONE | 54 | L |  | CDIS 6220028 |  | 2024-07-02 | Z | 2024-06-11 | 720 | 0 | 610 | F | 0 | 2930 |  |  |  | 21
2024-06-28 | 998 |  | SC-SAMP-007 | A | DONE | 22 | M |  | CDIS 6220028 |  | 2024-07-02 | Z | 2024-06-11 | 300 | 0 | 230 | F | 0 | 1230 |  |  |  | 21
2024-06-26 | 1029 | w | 69960 | A | DONE | 2 | S |  | CDIS 6220028 | 2" DB | 2024-06-27 | Z | 2024-06-17 | 30 | 0 | 0 |  | 30 | 100 |  | North Core curb cap |  | 10
2024-06-24 | 1030 |  | 61045 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-06-25 | Z | 2024-06-17 | 20 | 20 | 0 |  | 0 | 30 |  | EAD 10 2nd Floor B |  | 8
2024-06-24 | 1031 | sp | 69551 - 69552 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-06-25 | Z | 2024-06-18 | 40 | 30 | 0 |  | 0 | 80 |  | 3rd floor |  | 7
2024-06-24 | 1032 | sp | 69553 - 69554 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-06-25 | Z | 2024-06-18 | 50 | 20 | 0 |  | 0 | 70 |  | 3th floor |  | 7
2024-06-26 | 1033 |  | 69921 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-07-02 | Z | 2024-06-19 | 30 | 0 | 0 |  | 0 | 50 |  | 5th & 6th Taps |  | 13
2024-06-26 | 1035 |  | Pre-Fab Hangers | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-27 | Z | 2024-06-19 | 20 | 0 | 0 |  | 0 | 60 |  | 5th Floor B Section |  | 8
2024-06-24 | 1037 |  | 69557 - 69558 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-06-25 | Z | 2024-06-19 | 30 | 0 | 0 |  | 0 | 40 |  | 3rd floor |  | 6
2024-06-27 | 1059 |  | 69883 | A | DONE | 2 | S | neal | CDIS 6220028 | paint | 2024-07-02 | Z | 2024-06-24 | 20 | 0 | 0 |  | 20 | 20 |  | SALP-77 4th floor |  | 8
2024-06-28 | 1060 |  | 69509 | C | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-02 | Z | 2024-06-24 | 20 | 0 | 0 |  | 0 | 40 |  | Hanger |  | 8
2024-06-27 | 1061 | bth | EMAIL | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-07-02 | Z | 2024-06-25 | 50 | 50 | 0 |  | 30 | 100 |  | Lost pieces |  | 7
2024-06-27 | 1085 |  | 69559 - 69562 | A | DONE | 3 | S-M | neal | CDIS 6220028 |  | 2024-07-01 | Z | 2024-06-25 | 40 | 20 | 0 |  | 0 | 70 |  | 3rd floor |  | 6
2024-06-26 | 1086 |  | 69881 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-01 | Z | 2024-06-25 | 30 | 0 | 0 |  | 0 | 70 |  | Tear drop hangers |  | 6
2024-06-27 | 1087 |  | 57942 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-07-02 | Z | 2024-06-25 | 70 | 0 | 0 |  | 0 | 130 |  | NC Shaft |  | 7
2024-06-28 | 1088 |  | 69510 | A | DONE | 2 | S |  | CDIS 6220028 | 1" liner | 2024-07-03 | Z | 2024-06-26 | 20 | 0 | 0 |  | 20 | 20 |  | SAT-1-2-58 |  | 7
2024-06-24 | 3232 |  | SC-SAMP-002 | A | DONE | 41 | M-L |  | CDIS 6220028 |  | 2024-06-25 | Z | 2024-05-01 | 260 | 0 | 760 | F | 0 | 2180 |  |  |  | 55
2024-06-24 | 3233 |  | SC-SAMP-003 | A | DONE | 21 | M |  | CDIS 6220028 |  | 2024-06-25 | Z | 2024-05-01 | 110 | 0 | 400 | F | 0 | 990 |  |  |  | 55
2024-06-24 | r3505 |  | 69556 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-06-25 | Z | 2024-06-18 | 30 | 0 | 0 |  | 20 | 40 |  | 3rd floor |  | 7
2024-06-26 | 1132 | w | 69961 | A | DONE | 2 | S |  | DANE CO. AIRPORT 6210011 | 2" FB | 2024-06-28 | Z | 2024-06-17 | 40 | 0 | 0 |  | 20 | 120 |  | AHU-13 |  | 11
2024-06-28 | 2562 | sp | 56686 - 56687 | A | DONE | 27 | M-L |  | EXACT BIO 6230004 | s. mates | 2024-07-01 | Z | 2024-06-03 | 160 | 500 | 0 |  | 0 | 820 |  | DOAS SA |  | 28
2024-06-26 | 2563 |  | 56688 | A | DONE | 4 | S |  | EXACT BIO 6230004 |  | 2024-07-01 | Z | 2024-06-03 | 100 | 0 | 0 |  | 0 | 150 |  | V Hangers |  | 28
2024-06-27 | 4617 |  | 79461.1 | A | DONE | 2 | S | neal | HARMONICS 6240010 |  | 2024-07-01 | Z | 2024-06-24 | 20 | 0 | 0 |  | 0 | 80 |  | Hangers |  | 7
2024-06-25 | 2973 |  | 69283 | A | DONE | 2 | S | neal | HERITAGE 6220024 | paint | 2024-06-28 | Z | 2024-06-19 | 40 | 0 | 0 |  | 40 | 60 |  | 1st floor plenum boxes |  | 9
2024-06-24 | 2974 |  | 69287 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-06-25 | Z | 2024-06-24 | 30 | 0 | 0 |  | 0 | 40 |  | 2nd SA |  | 1
2024-06-28 | 1708 |  | 80211 | A | DONE | 2 | S | neal | INVENRA 6230001 |  | 2024-06-28 | Z | 2024-06-28 | 20 | 0 | 0 |  | 0 | 30 |  | 4th floor EA |  | 0
2024-06-25 | 2849 |  | 78626 | A | DONE | 4 | S |  | JANESVILLE ESSR 6230011 |  | 2024-06-27 | Z | 2024-06-20 | 90 | 0 | 0 |  | 0 | 240 |  | AHU-1 OA |  | 7
2024-06-27 | 3150 |  | 78627 | A | DONE | 5 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-06-27 | Z | 2024-06-20 | 120 | 0 | 0 |  | 0 | 200 |  | AHU-1 OA |  | 7
2024-06-24 | 3151 |  | 78653 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-06-27 | Z | 2024-06-20 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 7
2024-06-26 | 3152 |  | 62429 | A | DONE | 3 | S |  | JANESVILLE ESSR 6230011 | 1" liner , 2" DB | 2024-06-27 | Z | 2024-06-20 | 70 | 0 | 0 |  | 30 | 170 |  | BCU-1 |  | 7
2024-06-26 | 3153 |  | 78654 - 78655 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-07-01 | Z | 2024-06-24 | 20 | 0 | 0 |  | 0 | 40 |  | VAV-60 |  | 7
2024-06-26 | 2300 | sp | 67680 | A | DONE | 4 | S | alum | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 40 | 60 | 0 |  | 0 | 60 |  | EVAV B3 |  | 16
2024-06-26 | 2301 | sp | 67681 - 67682 | A | DONE | 18 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 120 | 320 | 0 |  | 0 | 440 |  | EVAV B9 |  | 16
2024-06-26 | 2302 | sp | 67683 | A | DONE | 4 | S | neal | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 20 | 70 | 0 |  | 0 | 100 |  | VAV B11 |  | 16
2024-06-25 | 2303 | sp | 67684 | A | DONE | 3 | S |  | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 30 | 30 | 0 |  | 0 | 70 |  | VAV B9 , B10 , B11 |  | 16
2024-06-25 | 2304 |  | 67685 | A | DONE | 5 | S | neal | KOHL CENTER 6210034 | 1/2 " , 1" liner | 2024-06-28 | Z | 2024-06-12 | 30 | 0 | 80 | F | 90 | 120 |  | VAV B9 , B11 |  | 16
2024-06-26 | 2305 | bth | 67686 - 67687 | A | DONE | 25 | M | neal | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 240 | 340 | 30 | F | 0 | 700 |  | VAV B11 |  | 16
2024-06-25 | 2306 |  | 67688 | A | DONE | 10 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 120 | 0 | 130 | F | 0 | 290 |  | VAV B9 |  | 16
2024-06-26 | 2307 | bth | 67689 | A | DONE | 6 | S-M |  | KOHL CENTER 6210034 | paint , 1/2 " , 1" liner | 2024-06-28 | Z | 2024-06-12 | 50 | 60 | 30 | F | 50 | 150 |  | VAV B10 |  | 16
2024-06-26 | 2308 |  | 67691 | A | DONE | 6 | S-M | neal | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 80 | 20 | 40 | F | 0 | 140 |  | EVAV B10 |  | 16
2024-06-26 | 2309 | bth | 67692 - 67693 | A | DONE | 8 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 150 | 30 | 0 |  | 0 | 200 |  | VAV 8 |  | 16
2024-06-26 | 2310 |  | 67694 | A | DONE | 8 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 150 | 0 | 40 | F | 0 | 240 |  | EA Main South |  | 16
2024-06-26 | 2322 |  | 67710 | A | DONE | 5 | S-M |  | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-17 | 80 | 0 | 40 | F | 70 | 140 |  | VAV B8 |  | 11
2024-06-26 | 3747 | sp | 67677 | A | DONE | 6 | S |  | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 30 | 100 | 0 |  | 0 | 120 |  | VAV B |  | 16
2024-06-25 | 3748 |  | 67678 | A | DONE | 4 | S |  | KOHL CENTER 6210034 | 1/2 " , 1" liner | 2024-06-28 | Z | 2024-06-12 | 20 | 20 | 60 | F | 30 | 90 |  | VAV B |  | 16
2024-06-26 | 3749 | sp | 67679 | A | DONE | 7 | S |  | KOHL CENTER 6210034 |  | 2024-06-28 | Z | 2024-06-12 | 40 | 130 | 0 |  | 0 | 170 |  | EVAV B3 |  | 16
2024-06-24 | 1118 |  | 80155 | A | DONE | 2 | S |  | LABCORP 2240024 |  | 2024-06-25 | Z | 2024-06-24 | 20 | 0 | 0 |  | 0 | 20 |  | Reducers |  | 1
2024-06-26 | r1117 |  | 80154 | A | DONE | 3 | S |  | LABCORP 2240024 | 1" liner | 2024-07-02 | Z | 2024-06-26 | 60 | 0 | 0 |  | 40 | 60 |  | TA |  | 6
2024-06-27 | 2180 | bth | 68618 | A | DONE | 2 | S | pt.neal | MEMORIAL HS 6210024 | bird s. | 2024-07-02 | Z | 2024-06-19 | 30 | 20 | 0 |  | 0 | 50 |  | Storage Rm. |  | 13
2024-06-27 | 2181 |  | 68619 - 68620 | A | DONE | 6 | S-M |  | MEMORIAL HS 6210024 | flex | 2024-07-02 | Z | 2024-06-19 | 140 | 0 | 0 |  | 0 | 270 |  | FCU-1-32 |  | 13
2024-06-27 | 2182 |  | 68621 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | paint | 2024-07-02 | Z | 2024-06-20 | 20 | 0 | 0 |  | 20 | 30 |  | Grille boxes |  | 12
2024-06-24 | 1449 |  | 80251 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-06-25 | Z | 2024-06-24 | 50 | 0 | 0 |  | 0 | 100 |  | Dishwasher SA |  | 1
2024-06-28 | 1447 | w | 96916 | A | DONE | 2 | S | BI | MENDOTA FOODS 8220036 |  | 2024-07-01 | Z | 2024-06-17 | 20 | 0 | 0 |  | 0 | 30 |  | Vault door |  | 14
2024-06-27 | 2350 |  | 80252 | A | DONE | 2 | S |  | MENDOTA FOODS 8220036 |  | 2024-06-28 | Z | 2024-06-27 | 30 | 0 | 0 |  | 0 | 40 |  | Dishwasher-SA |  | 1
2024-06-28 | 3115 |  | 81052 | A | DONE | 2 | S |  | PECATONICA 6240005 | 1/2"liner | 2024-07-08 | Z | 2024-06-26 | 20 | 0 | 0 |  | 20 | 20 |  | Admin Transfer |  | 12
2024-06-28 | 1830 |  | 56286 | A | DONE | 2 | S | neal | PROMEGA BTC 6230022 |  | 2024-07-03 | Z | 2024-06-18 | 20 | 0 | 0 |  | 0 | 20 |  | Engineering |  | 15
2024-06-28 | 1831 |  | 56289 | A | DONE | 7 | S-M |  | PROMEGA BTC 6230022 |  | 2024-07-03 | Z | 2024-06-18 | 170 | 0 | 0 |  | 0 | 200 |  | 1st floor |  | 15
2024-06-27 | 1832 | sp | 62900 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2024-07-01 | Z | 2024-06-27 | 60 | 20 | 0 |  | 0 | 100 |  | REDUCERS |  | 4
2024-06-28 | 1833 |  | 56293 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-07-01 | Z | 2024-06-27 | 20 | 0 | 0 |  | 0 | 20 |  | VAV-3-2 |  | 4
2024-06-24 | 1989 |  | 56287 - 56288 | A | DONE | 8 | S-M |  | PROMEGA FEYNMAN 6220014 |  | 2024-06-26 | Z | 2024-06-13 | 180 | 0 | 0 |  | 0 | 380 |  | PH Louver |  | 13
2024-06-28 | 3054 | w | 70665 | A | DONE | 2 | S |  | RAMC 6230007 |  | 2024-07-03 | Z | 2024-06-26 | 20 | 0 | 0 |  | 0 | 20 |  | Curb cap |  | 7
2024-06-25 | 3053 |  | 72392 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-07-01 | Z | 2024-06-18 | 20 | 0 | 0 |  | 0 | 50 |  | Flashing |  | 13
2024-06-27 | 3005 |  | 62532 | A | DONE | 3 | S-M |  | RETRO CX 6240004 | VD's | 2024-07-02 | Z | 2024-06-19 | 60 | 0 | 0 |  | 0 | 90 |  | AHU-10 |  | 13
2024-06-24 | 3006 |  | 41342 | A | DONE | 2 | S |  | RETRO CX 6240004 |  | 2024-06-25 | Z | 2024-06-24 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2024-06-26 | 4765 | sp | 78965 | A | DONE | 7 | S |  | ROCK CO. JAIL 6220018 |  | 2024-06-27 | Z | 2024-06-25 | 20 | 50 | 0 |  | 0 | 60 |  | Kitchen CB 103 |  | 2
2024-06-28 | 4258 |  | 80011 | A | DONE | 2 | S |  | ST.BERNARD 2230056 | 2" liner | 2024-07-08 | Z | 2024-06-25 | 20 | 0 | 0 |  | 20 | 30 |  | Window panel |  | 13
2024-06-28 | 4255 |  | 80004 | A | DONE | 2 | S |  | ST.BERNARD 6230023 |  | 2024-07-08 | Z | 2024-06-20 | 30 | 0 | 0 |  | 0 | 40 |  | Twin FCU RA |  | 18
2024-06-28 | 4259 |  | 80012 | A | DONE | 2 | S | neal | ST.BERNARD 6230023 | 2" DB | 2024-07-08 | Z | 2024-06-25 | 20 | 0 | 0 |  | 20 | 20 |  | Blank off panel |  | 13
2024-06-26 | 200 | sp | 79668 | A | DONE | 6 | S |  | UPLAND HILLS 2240008 |  | 2024-06-28 | Z | 2024-06-25 | 20 | 130 | 0 |  | 0 | 140 |  | 1307 SA |  | 3
2024-06-26 | 201 |  | 79670 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-06-28 | Z | 2024-06-25 | 30 | 0 | 0 |  | 0 | 50 |  | 1308 SA |  | 3
2024-06-28 | 3559 |  | 79328-29 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-08 | Z | 2024-06-27 | 40 | 0 | 0 |  | 0 | 40 |  | 3RD-SA-4&5 EC |  | 11
2024-06-25 | 4116 | bth | L1Z2-SAMP-11 | A | DONE | 43 | M-L |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 750 | 120 | 190 | F | 0 | 1600 |  |  |  | 22
2024-06-25 | 4117 | bth | L1Z2-SAMP-12 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 140 | 60 | 150 | F | 0 | 500 |  |  |  | 22
2024-06-25 | 4118 | bth | L1Z2-SAMP-13 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 110 | 50 | 180 | F | 0 | 430 |  |  |  | 22
2024-06-25 | 4119 | bth | L1Z2-SAMP-14 | A | DONE | 6 | S-M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 40 | 20 | 70 | F | 0 | 150 |  |  |  | 22
2024-06-27 | 4120 | bth | L1Z2-SAMP-15 | A | DONE | 7 | S |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 70 | 30 | 60 | F | 0 | 180 |  |  |  | 22
2024-06-25 | 4121 | bth | L1Z2-SAMP-16 | A | DONE | 25 | M-L |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 330 | 90 | 190 | F | 0 | 1100 |  |  |  | 22
2024-06-25 | 4122 | bth | L1Z2-SAMP-17 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 190 | 20 | 30 | F | 0 | 300 |  |  |  | 22
2024-06-25 | 4123 | bth | L1Z2-SAMP-18 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 80 | 30 | 140 | F | 0 | 380 |  |  |  | 22
2024-06-25 | 4124 | bth | L1Z2-SAMP-19 | A | DONE | 11 | S-M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 100 | 130 | 30 | F | 0 | 320 |  |  |  | 22
2024-06-26 | 4125 | bth | L1Z2-SAMP-20 | A | DONE | 22 | M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 210 | 50 | 280 | F | 0 | 950 |  |  |  | 22
2024-06-26 | 4126 | bth | L1Z2-SAMP-21 | A | DONE | 24 | M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 290 | 80 | 210 | F | 0 | 820 |  |  |  | 22
2024-06-25 | 4127 | bth | L1Z2-SAMP-22 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 40 | 40 | 200 | F | 0 | 420 |  |  |  | 22
2024-06-25 | 4128 | bth | L1Z2-SAMP-23 | A | DONE | 20 | M |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-04 | 330 | 90 | 70 | F | 0 | 720 |  |  |  | 22
2024-06-27 | 4131 | bth | L1Z2-FEMP-7 | A | DONE | 21 | M | pcd | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 300 | 100 | 110 | F | 0 | 670 |  |  |  | 26
2024-06-27 | 4132 | bth | L1Z2-FEMP-8 | A | DONE | 15 | S-M | pcd | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 300 | 30 | 30 | F | 0 | 440 |  |  |  | 26
2024-06-27 | 4133 | bth | L1Z2-FEMP-9 | A | DONE | 22 | M | pcd | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 240 | 110 | 200 | F | 0 | 770 |  |  |  | 26
2024-06-27 | 4134 | bth | L1Z2-FEMP-10 | A | DONE | 10 | S | pcd | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 50 | 20 | 170 | F | 0 | 290 |  |  |  | 26
2024-06-27 | 4135 | bth | L1Z2-FEMP-11 | A | DONE | 12 | S-M | pcd | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 30 | 20 | 230 | F | 0 | 340 |  |  |  | 26
2024-06-27 | 4136 | bth | L1Z2-FEMP-12 | A | DONE | 9 | S-M | pcd | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 30 | 20 | 170 | F | 0 | 320 |  |  |  | 26
2024-06-27 | 4137 | bth | L1Z2-FEMP-13 | A | DONE | 7 | S | pcd | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 20 | 20 | 130 | F | 0 | 200 |  |  |  | 26
2024-06-27 | 4138 | bth | L1Z2-FEMP-14 | A | DONE | 9 | S | pcd | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 40 | 20 | 150 | F | 0 | 260 |  |  |  | 26
2024-06-27 | 4139 | bth | L1Z2-EAMP-11 | A | DONE | 30 | M-L | pt.neal | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 480 | 30 | 230 | F | 0 | 1240 |  |  |  | 26
2024-06-27 | 4140 | bth | L1Z2-EAMP-12 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 60 | 30 | 160 | F | 0 | 330 |  |  |  | 26
2024-06-27 | 4141 | bth | L1Z2-EAMP-13 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 180 | 20 | 80 | F | 0 | 310 |  |  |  | 26
2024-06-27 | 4142 | bth | L1Z2-EAMP-14 | A | DONE | 7 | S |  | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 70 | 20 | 80 | F | 0 | 190 |  |  |  | 26
2024-06-27 | 4143 | bth | L1Z2-EAMP-15 | A | DONE | 29 | M-L | pt.neal | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 440 | 80 | 200 | F | 0 | 1170 |  |  |  | 26
2024-06-27 | 4144 | bth | L1Z2-EAMP-16 | A | DONE | 8 | S | pt.neal | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 80 | 20 | 100 | F | 0 | 250 |  |  |  | 26
2024-06-27 | 4145 | bth | L1Z2-EAMP-17 | A | DONE | 26 | M | pt.neal | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 240 | 50 | 350 | F | 0 | 910 |  |  |  | 26
2024-06-27 | 4146 | bth | L1Z2-EAMP-18 | A | DONE | 14 | S-M | pt.neal | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 80 | 20 | 230 | F | 0 | 390 |  |  |  | 26
2024-06-27 | 4147 | bth | L1Z2-EAMP-19 | A | DONE | 7 | S | neal | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-05 | 40 | 30 | 100 | F | 0 | 190 |  |  |  | 26
2024-06-25 | 4240 | sp | 66920 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-24 | 0 | 20 | 0 |  | 0 | 20 |  | EAMP-2 |  | 2
2024-06-25 | 4241 |  | 66921 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-06-26 | Z | 2024-06-24 | 0 | 0 | 0 |  | 0 | 0 |  | DM Frame |  | 2
2024-06-26 | 4243 |  | 66923 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-01 | Z | 2024-06-25 | 20 | 0 | 0 |  | 0 | 20 |  | EAMP-10 |  | 6
2024-06-27 | 5004 |  | RA-02-01 | A | DONE | 11 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-07-02 | Z | 2024-05-22 | 130 | 0 | 130 | F | 0 | 470 |  |  |  | 41
2024-06-27 | 5005 |  | SA-02-01 | A | DONE | 9 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-07-02 | Z | 2024-05-22 | 100 | 0 | 120 | F | 0 | 360 |  |  |  | 41
2024-06-28 | 5006 |  | RA-02-05 | A | DONE | 18 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-02 | Z | 2024-05-22 | 150 | 0 | 290 | F | 0 | 900 |  |  |  | 41
2024-06-28 | 5007 |  | SA-02-05 | A | DONE | 19 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-02 | Z | 2024-05-22 | 290 | 0 | 180 | F | 0 | 950 |  |  |  | 41
2024-06-27 | 5008 |  | EA-02-02 | A | DONE | 5 | S |  | UWSP ALBERTSON 6230016 |  | 2024-07-02 | Z | 2024-06-03 | 50 | 0 | 60 | F | 0 | 130 |  |  |  | 29
2024-06-28 | 5021 |  | EA-02-01 | A | DONE | 18 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-02 | Z | 2024-06-17 | 340 | 0 | 100 | F | 0 | 540 |  |  |  | 15
2024-06-28 | 199 | w | 79910 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-07-02 | Z | 2024-06-20 | 40 | 0 | 0 |  | 0 | 60 |  | Roof cap |  | 12
2024-06-24 | 198 |  | 23909 | A | DONE | 2 | S | pcd | WICELL 2230040 |  | 2024-06-26 | Z | 2024-06-19 | 20 | 0 | 0 |  | 0 | 30 |  | EA Hood tie in |  | 7
[6 empty] | 1253 | [13 empty] | 41690 |  |  |  | 5860 | 14.06%
WEEK OF 7-1-2024
2024-07-01 | 2214 |  | 200026 | A | DONE | 6 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-02 | Z | 2024-06-11 | 40 | 0 | 110 | F | 0 | 140 |  | ERV-3 SA |  | 21
2024-07-01 | 2215 |  | 200027 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-02 | Z | 2024-06-11 | 40 | 0 | 140 | F | 0 | 160 |  | ERV-3 RA |  | 21
2024-07-02 | 2235 | w | 80067 | A | DONE | 5 | S |  | 121 E. WILSON 6230024 |  | 2024-07-08 | Z | 2024-06-26 | 110 | 0 | 0 |  | 0 | 190 |  | Test Caps |  | 12
2024-07-02 | 2409 |  | 78961 | A | DONE | 8 | S |  | ABE LINCOLN 6230029 | flex , 1" liner | 2024-07-03 | Z | 2024-06-24 | 90 | 0 | 90 | F | 180 | 370 |  | AHU-6 |  | 9
2024-07-02 | 2412 |  | 78966 - 78969 | A | DONE | 4 | S-M |  | ABE LINCOLN 6230029 | flex | 2024-07-10 | Z | 2024-06-28 | 90 | 0 | 0 |  | 0 | 90 |  | EF's |  | 12
2024-07-02 | 2415 |  | 61165 | A | DONE | 2 | S | neal | ABE LINCOLN 6230029 |  | 2024-07-10 | Z | 2024-07-02 | 20 | 0 | 0 |  | 0 | 20 |  | CAB 1-4 |  | 8
2024-07-01 | 1761 |  | 31242 | A | DONE | 3 | S-M |  | BLACKHAWK BTC 6230025 | 1" liner | 2024-07-03 | Z | 2024-06-17 | 60 | 0 | 0 |  | 50 | 90 |  | RTU-4 |  | 16
2024-07-01 | 1763 |  | 31244 | A | DONE | 5 | S | neal | BLACKHAWK BTC 6230025 | oval, accu flange | 2024-07-03 | Z | 2024-06-17 | 30 | 20 | 0 |  | 0 | 70 |  | Weld Rm. |  | 16
2024-07-02 | 1764 |  | 31245 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-07-03 | Z | 2024-06-18 | 20 | 0 | 0 |  | 0 | 40 |  | Weld Rm. |  | 15
2024-07-01 | 1765 | sp | 31246 | A | DONE | 5 | S-M | neal | BLACKHAWK BTC 6230025 |  | 2024-07-03 | Z | 2024-06-18 | 30 | 80 | 0 |  | 0 | 130 |  | Weld Rm. |  | 15
2024-07-05 | 918 | bth | L5-A-EAMP-004 | A | DONE | 18 | S-M | pt.neal | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 300 | 40 | 110 | F | 0 | 540 |  |  |  | 42 |  | 2024-07-16
2024-07-03 | 919 | bth | L5-A-EAMP-005 | A | DONE | 30 | M-L | neal | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 390 | 60 | 300 | F | 0 | 1150 |  |  |  | 42 |  | 2024-07-16
2024-07-03 | 920 | bth | L5-A-EAMP-007 | A | DONE | 21 | M | neal | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 210 | 30 | 280 | F | 0 | 640 |  |  |  | 42 |  | 2024-07-16
2024-07-05 | 921 | bth | L5-A-EAMP-008 | A | DONE | 25 | M | neal | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 120 | 140 | 350 | F | 0 | 730 |  |  |  | 42 |  | 2024-07-16
2024-07-05 | 922 | bth | L5-A-SAMP-007 | A | DONE | 27 | M |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 270 | 70 | 320 | F | 0 | 920 |  |  |  | 42 |  | 2024-07-16
2024-07-05 | 923 | bth | L5-A-SAMP-008 | A | DONE | 25 | M |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 180 | 30 | 410 | F | 0 | 910 |  |  |  | 42 |  | 2024-07-16
2024-07-05 | 924 | bth | L5-A-SAMP-009 | A | DONE | 16 | S-M |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 240 | 80 | 60 | F | 0 | 420 |  |  |  | 42 |  | 2024-07-16
2024-07-05 | 925 | bth | L5-A-SAMP-010 | A | DONE | 22 | M |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 270 | 20 | 240 | F | 0 | 790 |  |  |  | 42 |  | 2024-07-16
2024-07-05 | 926 | bth | L5-A-SAMP-011 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-05-28 | 90 | 20 | 200 | F | 0 | 360 |  |  |  | 42 |  | 2024-07-16
2024-07-02 | 1034 |  | 69506 | A | DONE | 41 | L |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-06-19 | 1020 | 0 | 0 |  | 0 | 2980 |  | Test Caps |  | 20
2024-07-03 | 1036 |  | Pre-Fab Hangers | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-06-19 | 40 | 0 | 0 |  | 0 | 110 |  | 6th Floor B Section |  | 20
2024-07-01 | 1057 |  | 61046 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-06-24 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor B restrooms EA |  | 15
2024-07-02 | 1058 |  | 61047 | A | DONE | 2 | S |  | CDIS 6220028 | 1" liner | 2024-07-09 | Z | 2024-06-24 | 20 | 0 | 0 |  | 20 | 50 |  | 3rd floor B restrooms TA |  | 15
2024-07-02 | 1089 |  | 69884 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-09 | Z | 2024-06-27 | 20 | 0 | 0 |  | 0 | 30 |  | L4-EAMP-32 |  | 12
2024-07-03 | 1090 |  | 57943 | A | DONE | 22 | S-M |  | CDIS 6220028 |  | 2024-07-09 | Z | 2024-06-28 | 420 | 0 | 110 | F | 0 | 1050 |  | AHU-9 |  | 11
2024-07-01 | 1091 |  | 69922 | A | DONE | 2 | S | pt.neal | CDIS 6220028 |  | 2024-07-02 | Z | 2024-07-01 | 20 | 0 | 0 |  | 0 | 60 |  | Test Caps |  | 1
2024-07-03 | 1099 |  | 69611 - 12 | A | DONE | 2 | S | ss | CDIS 6220028 |  | 2024-07-08 | Z | 2024-07-03 | 20 | 0 | 0 |  | 0 | 20 |  | Wall mounts |  | 5
2024-07-01 | 203 |  | 70228 | A | DONE | 4 | S |  | COMPASS 4230088 |  | 2024-07-08 | Z | 2024-06-27 | 40 | 20 | 30 | F | 0 | 70 |  | EXHAUST |  | 11
2024-07-01 | 204 |  | 79773 | A | DONE | 5 | S-M |  | COMPASS 4230088 | paint | 2024-07-08 | Z | 2024-06-27 | 110 | 0 | 0 |  | 110 | 120 |  | REG BOXES |  | 11
2024-07-02 | 207 |  | 69511 | A | DONE | 2 | S |  | DSM 2240046 |  | 2024-07-08 | Z | 2024-07-01 | 20 | 0 | 0 |  | 0 | 30 |  | DR-2 Cabinet 4.16 |  | 7
2024-07-02 | 208 |  | 79417 | A | DONE | 2 | S | neal | EDGERTON MS 4240020 |  | 2024-07-10 | Z | 2024-07-01 | 50 | 0 | 0 |  | 0 | 80 |  | Covers |  | 9
2024-07-01 | 4618 |  | 79462 | A | DONE | 2 | S |  | HARMONICS 6240010 | flex | 2024-07-02 | Z | 2024-07-01 | 20 | 0 | 0 |  | 0 | 40 |  | Roxxy 1 SALP |  | 1
2024-07-01 | 4619 |  | 79463 | A | DONE | 2 | S |  | HARMONICS 6240010 | paint | 2024-07-02 | Z | 2024-07-01 | 30 | 0 | 0 |  | 30 | 40 |  | Roxxy 1 EA |  | 1
2024-07-02 | 4620 |  | 79464 | A | DONE | 2 | S | neal | HARMONICS 6240010 |  | 2024-07-02 | Z | 2024-07-01 | 20 | 0 | 0 |  | 0 | 20 |  | Roxxy 2 hangers |  | 1
2024-07-03 | 4621 |  | 79465 | A | DONE | 2 | S |  | HARMONICS 6240010 |  | 2024-07-05 | Z | 2024-07-02 | 30 | 0 | 0 |  | 0 | 40 |  | Roxxy 2 SALP |  | 3
2024-07-01 | 2984 |  | 69235 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-07-02 | Z | 2024-07-01 | 20 | 0 | 0 |  | 20 | 20 |  | Data rm OA |  | 1
2024-07-01 | 2183 |  | 68593 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 |  | 2024-07-09 | Z | 2024-06-24 | 40 | 0 | 0 |  | 0 | 80 |  | Wall cover |  | 15
2024-07-03 | 2187 |  | 68599 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-07-09 | Z | 2024-07-01 | 20 | 0 | 0 |  | 20 | 80 |  | RTU Divider |  | 8
2024-07-05 | 210 |  | 70536 | A | DONE | 10 | M |  | PARTS TRAYS |  | 2024-07-10 | Z | 2024-07-02 | 240 | 0 | 0 |  | 0 | 500 |  | Tray / bins |  | 8
2024-07-02 | 3114 |  | 79663 | A | DONE | 2 | S |  | PECATONICA 6240005 | 2" liner | 2024-07-08 | Z | 2024-06-24 | 40 | 0 | 0 |  | 30 | 90 |  | AHU retro fit |  | 14
2024-07-03 | 211 | bth | 79418 - 79419 | A | DONE | 14 | S-M |  | SAUK TRAILS ES 4240024 | 1/2" liner , VD | 2024-07-08 | Z | 2024-07-02 | 150 | 80 | 100 | F | 160 | 380 |  | Misc |  | 6
2024-07-01 | 4254 |  | 80003 | A | DONE | 6 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-07-08 | Z | 2024-06-20 | 130 | 0 | 0 |  | 110 | 180 |  | Twin FCU SA |  | 18
2024-07-02 | 4256 | bth | 80007 | A | DONE | 9 | S-M |  | ST.BERNARD 6230023 |  | 2024-07-08 | Z | 2024-06-24 | 50 | 160 | 0 |  | 0 | 200 |  | Alter SA |  | 14
2024-07-01 | 4257 |  | 80009 | A | DONE | 2 | S |  | ST.BERNARD 6230023 |  | 2024-07-08 | Z | 2024-06-24 | 40 | 0 | 0 |  | 0 | 60 |  | VAV-6 |  | 14
2024-07-02 | 205 |  | 79634 | A | DONE | 4 | S |  | UPLAND HILLS 2240008 | VD | 2024-07-08 | Z | 2024-06-28 | 50 | 0 | 30 | F | 0 | 100 |  | OR 4 RA changes |  | 10
2024-07-02 | 240 | sp | 70088 | A | DONE | 2 | S-M |  | UPLAND HILLS 2240008 |  | 2024-07-08 | Z | 2024-03-12 | 20 | 30 | 0 |  | 0 | 40 |  | 1326B |  | 118 |  | 2024-04-29 | 2024-06-10 | 2024-06-24
2024-07-05 | 3558 | sp | 79327 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-07-08 | Z | 2024-06-26 | 20 | 0 | 0 |  | 0 | 20 |  | AHU-5 SA |  | 12
2024-07-05 | 4244 |  | 66924 | A | DONE | 8 | S-M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-06-27 | 180 | 0 | 0 |  | 0 | 390 |  | L1-TEST CAPS |  | 13
2024-07-02 | 4245 | sp | 66925 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-08 | Z | 2024-07-02 | 0 | 20 | 0 |  | 0 | 20 |  | Misc L3 |  | 6
2024-07-02 | 5018 | bth | SA-02-06 | A | DONE | 63 | L |  | UWSP ALBERTSON 6230016 |  | 2024-07-09 | Z | 2024-06-11 | 610 | 40 | 910 | F | 0 | 2600 |  |  |  | 28
2024-07-01 | 5019 | bth | SA-02-07 | A | DONE | 43 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-07-09 | Z | 2024-06-11 | 440 | 60 | 570 | F | 0 | 1500 |  |  |  | 28
2024-07-02 | 5020 | bth | SA-02-08 | A | DONE | 64 | L |  | UWSP ALBERTSON 6230016 |  | 2024-07-09 | Z | 2024-06-11 | 530 | 100 | 960 | F | 0 | 2540 |  |  |  | 28
2024-07-05 | 3243 |  | 72973 | A | DONE | 2 | S | ss | UW-VET MED 2230012 |  | 2024-07-08 | Z | 2024-06-25 | 20 | 0 | 0 |  | 0 | 30 |  | Pipe covers |  | 13
2024-07-01 | 3244 |  | 72974 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-07-08 | Z | 2024-06-28 | 40 | 0 | 0 |  | 0 | 50 |  | L1-E4 |  | 10
2024-07-01 | 202 | bth | 67565-66 | A | DONE | 18 | S-M |  | WAUNAKEE DISTRICT 2240035 |  | 2024-07-03 | Z | 2024-06-26 | 80 | 100 | 270 | F | 30 | 520 |  | SA/Trans/Return |  | 7
2024-07-05 | 2975 | sp | 67560 - 67563 | A | DONE | 39 | M | neal | WAUNAKEE HS 6240013 |  | 2024-07-08 | Z | 2024-06-25 | 230 | 740 | 0 |  | 0 | 1290 |  | MAU-1 SA |  | 13
2024-07-02 | 2976 |  | 67559 | A | DONE | 13 | S-M |  | WAUNAKEE HS 6240013 | bird.s , 1" liner | 2024-07-08 | Z | 2024-06-25 | 200 | 0 | 110 | F | 200 | 430 |  | MAU RA |  | 13
2024-07-02 | 2977 |  | 69217 | A | DONE | 3 | S | neal | WAUNAKEE HS 6240013 |  | 2024-07-08 | Z | 2024-06-25 | 70 | 0 | 0 |  | 0 | 100 |  | EF-1E |  | 13
2024-07-01 | 2978 | sp | 69218 - 69219 | A | DONE | 10 | S-M | neal | WAUNAKEE HS 6240013 |  | 2024-07-08 | Z | 2024-06-25 | 70 | 160 | 0 |  | 0 | 290 |  | EF-1E |  | 13
2024-07-01 | 2979 | sp | 69220 | A | DONE | 2 | S | neal | WAUNAKEE HS 6240013 |  | 2024-07-08 | Z | 2024-06-25 | 20 | 20 | 0 |  | 0 | 40 |  | EF-1E |  | 13
2024-07-05 | 2980 | bth | 69221 - 69222 | A | DONE | 7 | S-M | neal | WAUNAKEE HS 6240013 |  | 2024-07-08 | Z | 2024-06-25 | 80 | 80 | 0 |  | 0 | 200 |  | EF-2E |  | 13
2024-07-02 | 2981 | w | 67564 | A | DONE | 4 | S-M |  | WAUNAKEE HS 6240013 | 2" liner | 2024-07-08 | Z | 2024-06-25 | 80 | 0 | 0 |  | 50 | 110 |  | Curb caps |  | 13
2024-07-02 | 2982 |  | 69230 - 69232 | A | DONE | 14 | S-M |  | WAUNAKEE HS 6240013 |  | 2024-07-08 | Z | 2024-06-25 | 250 | 0 | 100 | F | 0 | 410 |  | SA/ EA |  | 13
2024-07-01 | 2983 |  | 69288 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 |  | 2024-07-08 | Z | 2024-06-26 | 20 | 0 | 0 |  | 0 | 40 |  | Curb cap RH-1 |  | 12
[6 empty] | 694 | [13 empty] | 24830 |  |  |  | 7290 | 29.36%
WEEK OF 7-8-2024
2024-07-09 | 2236 |  | 4THFL-3 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-07-10 | Z | 2024-07-08 | 20 | 0 | 0 |  | 0 | 40 |  | Weld caps |  | 2
2024-07-11 | 2237 |  | 5THFL-1 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-07-16 | Z | 2024-07-11 | 20 | 0 | 0 |  | 0 | 50 |  | Caps |  | 5
2024-07-09 | 2413 |  | 78970 - 78971 | A | DONE | 5 | S-M |  | ABE LINCOLN 6230029 | flex | 2024-07-10 | Z | 2024-06-28 | 110 | 0 | 0 |  | 0 | 120 |  | EF's |  | 12
2024-07-09 | 2414 |  | 78972 - 78975 | A | DONE | 6 | S-M |  | ABE LINCOLN 6230029 | flex | 2024-07-10 | Z | 2024-06-28 | 130 | 0 | 0 |  | 0 | 160 |  | EF's |  | 12
2024-07-09 | 2416 |  | 78976 | A | DONE | 2 | S |  | ABE LINCOLN 6230029 | flex | 2024-07-10 | Z | 2024-07-02 | 40 | 0 | 0 |  | 0 | 90 |  | AHU-4 |  | 8
2024-07-09 | 1768 |  | 81401 | A | DONE | 3 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-07-11 | Z | 2024-07-03 | 60 | 0 | 0 |  | 0 | 200 |  | EF-1 |  | 8
2024-07-10 | 1094 |  | 69885 | A | DONE | 2 | S |  | CDIS 6220028 | 1" liner | 2024-07-11 | Z | 2024-07-01 | 20 | 0 | 0 |  | 20 | 20 |  | L4-A-SALP-077 |  | 10
2024-07-08 | 1095 |  | 69882 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-11 | Z | 2024-07-02 | 30 | 0 | 0 |  | 0 | 30 |  | Flashing fire wall |  | 9
2024-07-09 | 1300 |  | 69886 - 69890 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-11 | Z | 2024-07-08 | 40 | 0 | 0 |  | 0 | 60 |  | CB tie ins |  | 3
2024-07-09 | 1327 |  | 69892 | A | DONE | 2 | S |  | CDIS 6220028 | 1" liner | 2024-07-11 | Z | 2024-07-08 | 30 | 0 | 0 |  | 30 | 50 |  | TAD 01 |  | 3
2024-07-11 | 1328 |  | 69563 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-15 | Z | 2024-07-09 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd Floor |  | 6
2024-07-10 | 1329 |  | 69893 | A | DONE | 2 | S | neal | CDIS 6220028 | 1" liner | 2024-07-15 | Z | 2024-07-09 | 20 | 0 | 0 |  | 20 | 30 |  | L4-A-SALP-058 |  | 6
2024-07-11 | 1330 |  | 69894 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-15 | Z | 2024-07-09 | 20 | 0 | 0 |  | 0 | 20 |  | L4-B-EAMP-024 |  | 6
2024-07-11 | 1351 |  | 61314 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-16 | Z | 2024-07-10 | 50 | 0 | 0 |  | 0 | 60 |  | 5th floor |  | 6
2024-07-09 | 212 | bth | 79774 | A | DONE | 2 | S |  | COMPASS HP 4230088 |  | 2024-07-10 | Z | 2024-07-08 | 40 | 0 | 30 | F | 0 | 70 |  | Changes |  | 2
2024-07-10 | 1274 |  | 70072 - 70073 | A | DONE | 6 | S-M |  | EGENESIS PH2 6230026 | paint | 2024-07-15 | Z | 2024-02-22 | 110 | 0 | 40 | F | 20 | 180 |  | CB-3 LPSA |  | 144 |  | 2024-05-13 | 2024-07-08
2024-07-09 | 4622 |  | 69423 | A | DONE | 2 | S |  | HARMONICS 6240010 | paint | 2024-07-11 | Z | 2024-07-08 | 30 | 0 | 0 |  | 20 | 40 |  | Roxxy 2 OA |  | 3
2024-07-09 | 4623 |  | 69424 | A | DONE | 2 | S |  | HARMONICS 6240010 |  | 2024-07-11 | Z | 2024-07-08 | 20 | 0 | 0 |  | 0 | 30 |  | Kitchen |  | 3
2024-07-10 | 2989 |  | 69241 | A | DONE | 2 | S | neal | HERITAGE 6220024 |  | 2024-07-12 | Z | 2024-07-08 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 4
2024-07-10 | 2990 |  | 69290 - 69291 | A | DONE | 19 | S |  | HERITAGE 6220024 |  | 2024-07-12 | Z | 2024-07-08 | 250 | 0 | 210 | F | 0 | 540 |  | MAU-1 |  | 4
2024-07-11 | 2993 |  | 67568 | A | DONE | 2 | S | pt.neal | HERITAGE 6220024 |  | 2024-07-12 | Z | 2024-07-10 | 50 | 0 | 0 |  | 0 | 60 |  | Flashing |  | 2
2024-07-10 | 705 |  | 71514 - 71516 | A | DONE | 21 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-04-08 | 170 | 0 | 350 | F | 0 | 480 |  | RTU-3 |  | 98 |  | 2024-06-03
2024-07-11 | 707 | bth | 71518 - 71519 | A | DONE | 6 | S-M |  | HILLDALE 6240003 | flex | 2024-07-15 | Z | 2024-04-08 | 70 | 70 | 0 |  | 0 | 130 |  | FCU-1 |  | 98 |  | 2024-06-03
2024-07-11 | 708 |  | 71520 - 71521 | A | DONE | 20 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-04-08 | 110 | 0 | 380 | F | 0 | 460 |  | RTU-7 |  | 98 |  | 2024-07-08
2024-07-11 | 709 |  | 71522 - 71523 | A | DONE | 25 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-04-08 | 110 | 0 | 500 | F | 0 | 580 |  | RTU-7 |  | 98 |  | 2024-07-08
2024-07-11 | 715 |  | 71524 - 71525 | A | DONE | 24 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-04-10 | 170 | 0 | 410 | F | 0 | 540 |  | RTU-7 |  | 96 |  | 2024-07-08
2024-07-11 | 716 |  | 71526 - 71527 | A | DONE | 25 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-04-10 | 300 | 0 | 320 | F | 0 | 800 |  | RTU-1 |  | 96 |  | 2024-07-08
2024-07-11 | 717 |  | 71528 - 71529 | A | DONE | 29 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-04-10 | 350 | 0 | 360 | F | 0 | 920 |  | RTU-2 |  | 96 |  | 2024-07-08
2024-07-11 | 720 | bth | 66083 - 66084 | A | DONE | 6 | S-M |  | HILLDALE 6240003 | bird s. | 2024-07-15 | Z | 2024-06-04 | 130 | 0 | 0 |  | 0 | 150 |  | RTU-3 |  | 41
2024-07-10 | 721 |  | 66085 - 66086 | A | DONE | 15 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-06-12 | 250 | 0 | 110 | F | 0 | 410 |  | RTU-12 |  | 33
2024-07-10 | 722 |  | 66087 - 66088 | A | DONE | 14 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-06-12 | 180 | 0 | 170 | F | 0 | 410 |  | RTU-12 |  | 33
2024-07-09 | 2848 |  | 94082 | A | DONE | 7 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-07-11 | Z | 2024-06-20 | 160 | 0 | 0 |  | 0 | 110 |  | Misc |  | 21
2024-07-09 | 3154 |  | 62430 | A | DONE | 3 | S |  | JANESVILLE ESSR 6230011 |  | 2024-07-11 | Z | 2024-07-01 | 60 | 0 | 0 |  | 0 | 110 |  | BCU-4 Drops |  | 10
2024-07-09 | 3155 |  | 62431 - 62432 | A | DONE | 12 | S-M |  | JANESVILLE ESSR 6230011 | flex , 1" liner | 2024-07-11 | Z | 2024-07-01 | 200 | 0 | 90 | F | 140 | 340 |  | BCU-4 RA |  | 10
2024-07-10 | 3156 | sp | 62433 | F | DONE | 8 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-11 | Z | 2024-07-01 | 30 | 150 | 0 |  | 0 | 170 |  | BCU-4 |  | 10
2024-07-10 | 3157 |  | 62434 - 62435 | A | DONE | 24 | S-M |  | JANESVILLE ESSR 6230011 | flex , 2" liner | 2024-07-11 | Z | 2024-07-01 | 280 | 0 | 320 | F | 470 | 700 |  | BCU-4 SA |  | 10
2024-07-09 | 3158 |  | 80254 | A | DONE | 8 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-11 | Z | 2024-07-01 | 120 | 0 | 60 | F | 0 | 300 |  | AHU-5 OA louver |  | 10
2024-07-10 | 3159 |  | 62436 - 62437 | A | DONE | 9 | S-M |  | JANESVILLE ESSR 6230011 | flex , 2" liner | 2024-07-11 | Z | 2024-07-01 | 130 | 0 | 90 | F | 90 | 270 |  | FC-2 SA |  | 10
2024-07-11 | 3160 | sp | 62438 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-07-11 | Z | 2024-07-01 | 20 | 30 | 0 |  | 0 | 50 |  | FC-2 SA |  | 10
2024-07-09 | 3161 |  | 62439 | A | DONE | 3 | S-M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-07-11 | Z | 2024-07-01 | 70 | 0 | 0 |  | 60 | 90 |  | Band Rm. |  | 10
2024-07-11 | 3162 | w | 62440 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | 2" DB | 2024-07-11 | Z | 2024-07-01 | 30 | 0 | 0 |  | 30 | 60 |  | Curb cap |  | 10
2024-07-09 | 3166 |  | 62441 | A | DONE | 8 | S |  | JANESVILLE ESSR 6230011 |  | 2024-07-11 | Z | 2024-07-03 | 200 | 0 | 0 |  | 0 | 230 |  | 1st |  | 8
2024-07-09 | 2311 |  | 67695 | A | DONE | 11 | M | pt.neal | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-06-17 | 130 | 0 | 140 | F | 0 | 660 |  | EA Main |  | 25
2024-07-11 | 2312 | sp | 67696 | A | DONE | 13 | S-M |  | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-06-17 | 60 | 260 | 0 |  | 0 | 310 |  | EVAV |  | 25
2024-07-11 | 2313 | sp | 67697 | A | DONE | 9 | S | alum | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-06-17 | 60 | 150 | 0 |  | 0 | 110 |  | EVAV |  | 25
2024-07-11 | 2314 | bth | 67698 | A | DONE | 3 | S |  | KOHL CENTER 6210034 | paint | 2024-07-12 | Z | 2024-06-17 | 40 | 30 | 0 |  | 20 | 80 |  | EVAV |  | 25
2024-07-09 | 2315 |  | 67699 | A | DONE | 10 | S-M | neal | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-06-17 | 120 | 0 | 110 | F | 0 | 280 |  | VAV |  | 25
2024-07-11 | 2317 | sp | 67702 | A | DONE | 5 | S-M | neal | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-06-17 | 40 | 70 | 0 |  | 0 | 120 |  | SA Main |  | 25
2024-07-11 | 2318 | sp | 67703 - 67705 | A | DONE | 16 | S-M |  | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-06-17 | 70 | 320 | 0 |  | 0 | 420 |  | SA Main |  | 25
2024-07-10 | 2319 |  | 67706 | A | DONE | 6 | S-M |  | KOHL CENTER 6210034 | 1/2" , 1" liner | 2024-07-12 | Z | 2024-06-17 | 50 | 0 | 100 | F | 120 | 180 |  | SA VAV |  | 25
2024-07-11 | 2320 | bth | 67707 - 67709 | A | DONE | 10 | S-M |  | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-06-17 | 60 | 130 | 50 | F | 0 | 240 |  | VAV |  | 25
2024-07-11 | 2325 | sp | 67717 | A | DONE | 3 | S | alum | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-06-26 | 30 | 40 | 0 |  | 0 | 50 |  | A-Section |  | 16
2024-07-11 | 2326 |  | 67718 | A | DONE | 2 | S |  | KOHL CENTER 6210034 | paint | 2024-07-12 | Z | 2024-06-26 | 30 | 0 | 0 |  | 0 | 30 |  | VAV |  | 16
2024-07-09 | 2327 |  | 67719 | A | DONE | 2 | S |  | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-07-03 | 20 | 0 | 0 |  | 0 | 20 |  | Fireplace |  | 9
2024-07-11 | 2328 | bth | 67675 | A | DONE | 6 | S-M |  | KOHL CENTER 6210034 |  | 2024-07-12 | Z | 2024-07-03 | 50 | 50 | 30 | F | 0 | 140 |  | LL B VAV |  | 9
2024-07-10 | 1120 | w | 80161 | A | DONE | 2 | S | ss | LABCORP 6240011 |  | 2024-07-10 | Z | 2024-07-03 | 40 | 0 | 0 |  | 0 | 70 |  | EA |  | 7
2024-07-10 | 1119 | w | 80157 - 80160 | A | DONE | 7 | M | ss | LABCORP BIO 6240011 |  | 2024-07-10 | Z | 2024-07-01 | 170 | 0 | 0 |  | 0 | 480 |  | EA - SS |  | 9
2024-07-09 | 209 |  | 59807 - 59809 | A | DONE | 15 | S-M |  | LINDSEY M. 1000373 |  | 2024-07-12 | Z | 2024-07-01 | 370 | 0 | 0 |  | 0 | 130 |  | Furnace |  | 11
2024-07-11 | 2352 |  | 80303 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 |  | 2024-07-12 | Z | 2024-07-11 | 30 | 0 | 0 |  | 30 | 50 |  | Misc |  | 1
2024-07-11 | 2353 |  | 80302 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 |  | 2024-07-11 | Z | 2024-07-11 | 20 | 0 | 0 |  | 0 | 20 |  | PH |  | 0
2024-07-09 | 3117 |  | 79637 | A | DONE | 6 | S |  | PECATONICA 6240005 |  | 2024-07-15 | Z | 2024-07-02 | 130 | 0 | 0 |  | 0 | 200 |  | AHU-2 |  | 13
2024-07-10 | 3118 |  | 79638 | A | DONE | 2 | S |  | PECATONICA 6240005 | 1" liner | 2024-07-15 | Z | 2024-07-02 | 0 | 0 | 0 |  | 50 | 0 |  | AHU-2 liner |  | 13
2024-07-10 | 1834 |  | 56295 | A | DONE | 3 | S-M |  | PROMEGA 1518 2240009 |  | 2024-07-15 | Z | 2024-07-01 | 70 | 0 | 0 |  | 0 | 80 |  | PH |  | 14
2024-07-11 | 1835 |  | 56294 | A | DONE | 9 | S |  | PROMEGA BTC 6230022 | bird.s | 2024-07-15 | Z | 2024-07-01 | 100 | 0 | 110 | F | 0 | 280 |  | RA |  | 14
2024-07-11 | 1836 |  | L0-RA-02 | A | DONE | 23 | M |  | PROMEGA BTC 6230022 | VD | 2024-07-15 | Z | 2024-07-02 | 300 | 0 | 260 | F | 0 | 870 |  |  |  | 13
2024-07-08 | 1838 |  | 59657 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-07-10 | Z | 2024-07-02 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 8
2024-07-08 | 1839 |  | 59658 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-07-10 | Z | 2024-07-03 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 7
2024-07-09 | 4766 | bth | 78977 | A | DONE | 3 | S |  | ROCK CO. JAIL 6220018 | flex | 2024-07-10 | Z | 2024-07-03 | 40 | 20 | 0 |  | 0 | 60 |  | Jail |  | 7
2024-07-10 | 4260 |  | 80016 , 80018 | A | DONE | 8 | S-M |  | ST.BERNARD 6230023 | bird s. ,1" liner | 2024-07-12 | Z | 2024-06-28 | 130 | 0 | 70 | F | 80 | 230 |  | Lobby TA , VAV 6 |  | 14
2024-07-11 | 4261 |  | 80019 | A | DONE | 2 | S | neal | ST.BERNARD 6230023 | 2" DB | 2024-07-12 | Z | 2024-06-28 | 20 | 0 | 0 |  | 20 | 20 |  | Louver cover |  | 14
2024-07-10 | 4262 |  | 80021 | A | DONE | 2 | S |  | ST.BERNARD 6230023 | 1" liner | 2024-07-15 | Z | 2024-06-28 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 17
2024-07-10 | 206 |  | 81753 | A | DONE | 5 | S-M |  | TRAINING 3240014 |  | 2024-07-15 | Z | 2024-06-28 | 120 | 0 | 0 |  | 0 | 130 |  |  |  | 17
2024-07-11 | 2044 | bth | 67289 - 67291 | A | DONE | 28 | M-L |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 350 | 20 | 330 | F | 0 | 1300 |  | AHU-4 SA |  | 62
2024-07-11 | 3929 | sp | L2Z1-FEV-3-2-1 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 0 | 20 | 0 |  | 0 | 20 |  |  | Trailer #1 | 78
2024-07-11 | 3930 | sp | L2Z1-FEV-3-2-2 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-11 | 3931 | sp | L2Z1-FEV-3-2-3 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-10 | 3932 | bth | L2Z1-FEV-3-2-4 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-11 | 3933 | sp | L2Z1-FEV-3-2-5 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-11 | 3934 | sp | L2Z1-FEV-3-2-6 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 30 | 50 | 0 |  | 0 | 100 |  |  | Trailer #1 | 78
2024-07-09 | 3935 | sp | L2Z1-FEV-3-2-7 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-11 | 3936 | sp | L2Z1-FEV-3-2-8 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 50 |  |  | Trailer #1 | 78
2024-07-11 | 3937 | sp | L2Z1-FEV-3-2-9 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 30 | 0 |  | 0 | 60 |  |  | Trailer #1 | 78
2024-07-11 | 3938 | sp | L2Z2-FEV-3-2-10 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 30 |  |  | Trailer #1 | 78
2024-07-11 | 3939 | sp | L2Z2-FEV-3-2-11 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-11 | 3940 | sp | L2Z2-FEV-3-2-12 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-11 | 3941 | sp | L2Z2-FEV-3-2-13 | A | DONE | 6 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 50 | 100 | 0 |  | 0 | 180 |  |  | Trailer #1 | 78
2024-07-11 | 3942 | sp | L2Z2-FEV-3-2-14.1 | A | DONE | 10 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 80 | 150 | 0 |  | 0 | 310 |  |  | Trailer #1 | 78
2024-07-11 | 3943 | sp | L2Z2-FEV-3-2-14.2 | A | DONE | 6 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 40 | 90 | 0 |  | 0 | 160 |  |  | Trailer #1 | 78
2024-07-11 | 3944 | sp | L2Z2-FEV-3-2-15 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-11 | 3945 | sp | L2Z2-FEV-3-2-16 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-11 | 3946 | sp | L2Z2-FEV-3-2-17 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-23 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #1 | 78
2024-07-08 | 3959 |  | L2Z2-TA-33 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-25 | 70 | 0 | 30 | F | 80 | 130 |  |  | Trailer #1 | 76
2024-07-08 | 3960 |  | L2Z2-TA-34 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-25 | 80 | 0 | 30 | F | 80 | 140 |  |  | Trailer #1 | 76
2024-07-09 | 3966 | bth | L2Z1-RAT-1-2-2 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-05-02 | 90 | 20 | 90 | F | 0 | 220 |  |  | Trailer #1 | 69
2024-07-08 | 3967 | bth | L2Z2-RAT-1-2-1 | A | DONE | 11 | S-M | neal | UWRF 6230010 |  | 2024-07-10 | Z | 2024-05-02 | 120 | 20 | 120 | F | 0 | 310 |  |  |  | 69
2024-07-08 | 4242 |  | 66922 | A | DONE | 6 | S-M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-06-25 | 150 | 0 | 0 |  | 0 | 320 |  | L1 round hangers |  | 15
2024-07-10 | 4934 | bth | L2Z1-GET-1-2-1 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 140 | 30 | 60 | F | 0 | 250 |  |  | Trailer #1 | 86
2024-07-11 | 4935 | sp | L2Z1-GET-1-2-2 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 20 | 20 | 0 |  | 0 | 60 |  |  | Trailer #1 | 86
2024-07-09 | 4936 | sp | L2Z1-GET-1-2-3 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 20 | 50 | 0 |  | 0 | 70 |  |  | Trailer #1 | 86
2024-07-08 | 4937 | sp | L2Z1-GET-1-2-4 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 20 | 70 | 0 |  | 0 | 90 |  |  | Trailer #1 | 86
2024-07-09 | 4938 | sp | L2Z1-GET-1-2-5 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 20 | 30 | 0 |  | 0 | 50 |  |  | Trailer #1 | 86
2024-07-10 | 4939 | bth | L2Z1-GET-1-2-6 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 50 | 20 | 30 | F | 0 | 110 |  |  | Trailer #1 | 86
2024-07-08 | 4940 | sp | L2Z1-GET-1-2-7 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 40 | 50 | 0 |  | 0 | 100 |  |  | Trailer #1 | 86
2024-07-09 | 4941 | bth | L2Z1-GET-1-2-8 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 70 | 20 | 0 |  | 0 | 100 |  |  | Trailer #1 | 86
2024-07-09 | 4942 | bth | L2Z1-GET-1-2-9 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 230 | 20 | 80 | F | 0 | 380 |  |  | Trailer #1 | 86
2024-07-10 | 4943 | sp | L2Z1-GET-1-2-10 | A | DONE | 3 | S | pt.neal | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 20 | 40 | 0 |  | 0 | 60 |  |  | Trailer #1 | 86
2024-07-08 | 4944 | sp | L2Z1-GET-1-2-23 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 20 | 20 | 0 |  | 0 | 50 |  |  | Trailer #1 | 86
2024-07-08 | 4945 | bth | L2Z2-GET-1-2-11 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 50 | 20 | 80 | F | 0 | 170 |  |  | Trailer #1 | 86
2024-07-09 | 4946 | bth | L2Z2-GET-1-2-12 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 50 | 20 | 50 | F | 0 | 130 |  |  | Trailer #1 | 86
2024-07-09 | 4947 | bth | L2Z2-GET-1-2-13 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 50 | 20 | 80 | F | 0 | 170 |  |  | Trailer #1 | 86
2024-07-09 | 4948 | bth | L2Z2-GET-1-2-14 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 100 | 20 | 70 | F | 0 | 210 |  |  | Trailer #1 | 86
2024-07-09 | 4949 | bth | L2Z2-GET-1-2-15 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 80 | 20 | 50 | F | 0 | 160 |  |  | Trailer #1 | 86
2024-07-10 | 4950 | sp | L2Z2-GET-1-2-16 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 50 | 30 | 0 |  | 0 | 100 |  |  | Trailer #1 | 86
2024-07-11 | 4951 | bth | L2Z2-GET-1-2-17 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 120 | 70 | 30 | F | 0 | 240 |  |  | Trailer #1 | 86
2024-07-10 | 4952 | bth | L2Z2-GET-1-2-18 | A | DONE | 16 | S-M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 170 | 190 | 30 | F | 0 | 450 |  |  | Trailer #1 | 86
2024-07-10 | 4953 | bth | L2Z2-GET-1-2-19 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 100 | 20 | 100 | F | 0 | 250 |  |  | Trailer #1 | 86
2024-07-08 | 4954 | sp | L2Z2-GET-1-2-20 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 20 | 20 | 0 |  | 0 | 30 |  |  | Trailer #1 | 86
2024-07-11 | 4955 | bth | L2Z2-GET-1-2-21 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 130 | 20 | 0 |  | 0 | 180 |  |  | Trailer #1 | 86
2024-07-09 | 4956 | sp | L2Z2-GET-1-2-22 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 20 | 80 | 0 |  | 0 | 100 |  |  | Trailer #1 | 86
2024-07-09 | 4957 | bth | L2Z2-GET-1-2-24 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 50 | 20 | 80 | F | 0 | 170 |  |  | Trailer #1 | 86
2024-07-09 | 4958 | bth | L2Z2-GET-1-2-25 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 50 | 20 | 80 | F | 0 | 170 |  |  | Trailer #1 | 86
2024-07-11 | 4959 | bth | L2Z2-GET-1-2-26 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 60 | 220 | 0 |  | 0 | 280 |  | Exposed | Trailer #1 | 86
2024-07-08 | 4960 | bth | L2Z2-GET-1-2-27 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-15 | 40 | 40 | 30 | F | 0 | 130 |  |  | Trailer #1 | 86
2024-07-09 | 4978 |  | L2Z2-SAT-1-2-30 | A | DONE | 8 | S |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-17 | 100 | 0 | 80 | F | 30 | 220 |  |  | Trailer #1 | 84
2024-07-10 | 4979 |  | L2Z2-SAT-1-2-31.1 | A | DONE | 15 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-17 | 230 | 90 | 50 | F | 50 | 440 |  |  | Trailer #1 | 84
2024-07-09 | 4980 | bth | L2Z2-SAT-1-2-31.2 | A | DONE | 16 | M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-17 | 160 | 150 | 80 | F | 0 | 470 |  |  | Trailer #1 | 84
2024-07-10 | 4981 | bth | L2Z2-SAT-1-2-32.1 | A | DONE | 6 | S |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-17 | 120 | 30 | 0 |  | 70 | 180 |  |  | Trailer #1 | 84
2024-07-10 | 4982 | sp | L2Z2-SAT-1-2-32.2 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-17 | 30 | 200 | 0 |  | 0 | 230 |  |  | Trailer #1 | 84
2024-07-10 | 4983 | bth | L2Z2-SAT-1-2-33 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-17 | 60 | 40 | 0 |  | 30 | 120 |  |  | Trailer #1 | 84
2024-07-10 | 4984 | bth | L2Z2-SAT-1-2-34.1 | A | DONE | 12 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-17 | 230 | 60 | 0 |  | 50 | 320 |  |  | Trailer #1 | 84
2024-07-09 | 4985 | bth | L2Z2-SAT-1-2-34.2 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-17 | 80 | 60 | 0 |  | 0 | 140 |  |  | Trailer #1 | 84
2024-07-10 | 4986 | bth | L2Z2-SAT-1-2-35 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-17 | 60 | 60 | 0 |  | 20 | 130 |  |  | Trailer #1 | 84
2024-07-09 | 4987 |  | L2Z2-SAT-1-2-36 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-17 | 100 | 0 | 0 |  | 70 | 130 |  |  | Trailer #1 | 84
2024-07-08 | 4995 |  | L2Z2-SAT-1-2-64.1 | A | DONE | 9 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-10 | Z | 2024-04-17 | 210 | 0 | 0 |  | 50 | 300 |  |  | Trailer #1 | 84
2024-07-09 | 4996 | bth | L2Z2-SAT-1-2-64.2 | A | DONE | 5 | S | pt.neal | UWRF 6230010 |  | 2024-07-10 | Z | 2024-04-17 | 60 | 60 | 0 |  | 0 | 140 |  |  | Trailer #1 | 84
2024-07-09 | 2450 | w | 58805 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | 1" FB | 2024-07-10 | Z | 2024-07-09 | 20 | 0 | 0 |  | 0 | 20 |  | Wall sleeve |  | 1
2024-07-10 | 2991 |  | 69242 | A | DONE | 2 | S |  | WAUNAKEE D.O. 2240035 |  | 2024-07-15 | Z | 2024-07-08 | 40 | 0 | 0 |  | 0 | 50 |  | SA |  | 7
2024-07-09 | 2985 | sp | 69223 - 69224 | A | DONE | 9 | S-M |  | WAUNAKEE HS 6240013 |  | 2024-07-10 | Z | 2024-07-01 | 50 | 160 | 0 |  | 0 | 370 |  | Wood working EA |  | 9
2024-07-10 | 2986 | sp | 69225 , 69227 | A | DONE | 2 | S-M |  | WAUNAKEE HS 6240013 |  | 2024-07-10 | Z | 2024-07-01 | 20 | 20 | 0 |  | 0 | 60 |  | Wood working EA |  | 9
2024-07-09 | 2987 | sp | 69228 | A | DONE | 6 | S-M | neal | WAUNAKEE HS 6240013 |  | 2024-07-10 | Z | 2024-07-01 | 60 | 80 | 0 |  | 0 | 200 |  | Wood working EA |  | 9
2024-07-11 | 2988 |  | 69240 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 |  | 2024-07-12 | Z | 2024-07-05 | 50 | 0 | 0 |  | 0 | 90 |  | Wood shop |  | 7
2024-07-11 | 1877 |  | 32497 | A | DONE | 6 | S-M |  | WSCC 8240004 |  | 2024-07-16 | Z | 2024-07-02 | 150 | 0 | 0 |  | 0 | 730 |  | Plates |  | 14
2024-07-12 | 1273 | sp | 70071 | A | DONE | 6 | S-M |  | EGENESIS PH2 6230026 |  | 2024-07-15 | Z | 2024-02-22 | 40 | 110 | 0 |  | 0 | 180 |  | CB-3 HPSA |  | 144 |  | 2024-05-13 | 2024-07-08
2024-07-12 | 1275 | sp | 70074 | A | DONE | 4 | S-M |  | EGENESIS PH2 6230026 |  | 2024-07-15 | Z | 2024-02-22 | 20 | 60 | 0 |  | 0 | 80 |  | SAT 001 LPSA |  | 144 |  | 2024-05-13 | 2024-07-08
2024-07-12 | 1282 | sp | 79621 | A | DONE | 3 | S |  | EGENESIS PH2 6230026 |  | 2024-07-15 | Z | 2024-02-22 | 0 | 60 | 0 |  | 0 | 60 |  | CB-3R |  | 144
2024-07-12 | 706 | sp | 71517 | A | DONE | 4 | S-M |  | HILLDALE 6240003 |  | 2024-07-15 | Z | 2024-04-08 | 20 | 70 | 0 |  | 0 | 100 |  | RTU-3 Spiral |  | 98 |  | 2024-06-03
2024-07-12 | 2316 | bth | 67700 - 67701 | A | DONE | 18 | S-M |  | KOHL CENTER 6210034 | paint | 2024-07-12 | Z | 2024-06-17 | 220 | 20 | 190 | F | 20 | 500 |  | VAV |  | 25
2024-07-13 | 2185 |  | 68597 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-07-16 | Z | 2024-07-01 | 20 | 0 | 0 |  | 0 | 50 |  | AHU-Q2 |  | 15
2024-07-13 | 2196 |  | 68103 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-07-16 | Z | 2024-07-08 | 30 | 0 | 0 |  | 0 | 50 |  | Pipe guard |  | 8
2024-07-13 | 2197 |  | 68104 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-07-16 | Z | 2024-07-08 | 50 | 0 | 0 |  | 0 | 100 |  | Louver AHU A5 |  | 8
2024-07-13 | 2351 | w | 80301 | A | DONE | 2 | S |  | MENDOTA FOOD 6220027 |  | 2024-07-18 | Z | 2024-07-08 | 20 | 0 | 0 |  | 0 | 20 |  | Floor pen. |  | 10
2024-07-12 | 3116 | w | 79635 - 79636 | A | DONE | 2 | S | ss | PECATONICA 6240005 |  | 2024-07-15 | Z | 2024-07-02 | 40 | 0 | 0 |  | 0 | 70 |  | CC 1 SS Drain pan |  | 13
2024-07-12 | 1837 | sp | L0-SAMP-08 | A | DONE | 10 | S-M |  | PROMEGA BTC 6230022 |  | 2024-07-15 | Z | 2024-07-02 | 50 | 200 | 0 |  | 0 | 280 |  |  |  | 13
2024-07-12 | 3055 |  | 91648 | A | DONE | 4 | M |  | RAMC 6230009 |  | 2024-07-15 | Z | 2024-06-27 | 100 | 0 | 0 |  | 0 | 140 |  | BIRD SCREEN |  | 18
2024-07-12 | 3056 | bth | 72393 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-07-15 | Z | 2024-07-03 | 20 | 30 | 0 |  | 0 | 50 |  | LL-Misc |  | 12
2024-07-12 | 2042 |  | 67283 - 67286 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 250 | 0 | 30 | F | 220 | 320 |  | 205 TA |  | 62
2024-07-12 | 2043 |  | 67287 - 67288 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 | VD's | 2024-07-15 | Z | 2024-05-14 | 70 | 0 | 60 | F | 0 | 150 |  | 206 BR EA |  | 62
2024-07-12 | 2045 | sp | 67292 - 67293 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 20 | 110 | 0 |  | 0 | 130 |  | AHU-4 SA |  | 62
2024-07-12 | 2046 |  | 67294 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 40 | 0 | 0 |  | 40 | 80 |  | SAT-4-2-1 |  | 62
2024-07-12 | 2047 |  | 67295 - 67296 | A | DONE | 15 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 150 | 0 | 220 | F | 0 | 430 |  | SAT-4-2-1 |  | 62
2024-07-12 | 2048 | bth | 67297 - 67298 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 110 | 50 | 120 | F | 0 | 320 |  | SAT-4-2-1 |  | 62
2024-07-12 | 2049 |  | 67299 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 50 | 0 | 20 | F | 30 | 80 |  | SAT-4-2-2 |  | 62
2024-07-12 | 3500 | sp | 67300 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 0 | 20 | 0 |  | 0 | 20 |  | SAT-4-2-2 |  | 62
2024-07-12 | 3503 |  | 79205 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 30 | 0 | 0 |  | 30 | 50 |  | SAT-4-2-5 |  | 62
2024-07-12 | 3504 | bth | 79206 - 79207 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 100 | 30 | 50 | F | 0 | 200 |  | SAT-4-2-5 |  | 62
2024-07-12 | 3505 | bth | 79208 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 20 | 20 | 0 |  | 0 | 20 |  | SAT-4-2-7 |  | 62
2024-07-12 | 3506 |  | 79209 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 60 | 0 | 0 |  | 50 | 80 |  | SAT-4-2-6 |  | 62
2024-07-13 | 3508 |  | 79212 - 79213 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 90 | 0 | 40 | F | 0 | 150 |  | SAT-4-2-6 |  | 62
2024-07-13 | 3509 |  | 79214 - 79215 | A | DONE | 22 | M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 230 | 0 | 300 | F | 0 | 720 |  | AHU-4 RA |  | 62
2024-07-13 | 3511 |  | 79218 - 79219 | A | DONE | 14 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 170 | 0 | 180 | F | 0 | 420 |  | AHU-4 RA |  | 62
2024-07-13 | 3513 |  | 79223 - 79224 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 90 | 0 | 20 | F | 0 | 350 |  | 215 E, 217 C TA |  | 62
2024-07-13 | 3514 |  | 79225 - 79226 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 90 | 0 | 20 | F | 80 | 120 |  | 217 A,B TA |  | 62
2024-07-13 | 3515 | bth | 79227 - 79229 | A | DONE | 21 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 330 | 100 | 80 | F | 0 | 670 |  | AHU-5 SA |  | 62
2024-07-13 | 3516 | sp | 79230 - 79232 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 20 | 100 | 0 |  | 0 | 120 |  | AHU-5 SA |  | 62
2024-07-13 | 3517 | bth | 79233 - 79234 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 150 | 40 | 40 | F | 30 | 240 |  | SAT-5-2-1 |  | 62
2024-07-13 | 3518 | bth | 79235 - 79236 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 40 | 20 | 40 | F | 0 | 90 |  | SAT-5-2-4 |  | 62
2024-07-13 | 3519 | bth | 79237 - 79238 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 60 | 50 | 30 | F | 0 | 140 |  | SAT-5-2-5 |  | 62
2024-07-13 | 3520 | bth | 79239 - 79240 | A | DONE | 14 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 110 | 150 | 90 | F | 0 | 370 |  | SAT-5-2-2 |  | 62
2024-07-13 | 3521 | bth | 79241 - 79243 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 110 | 40 | 50 | F | 0 | 220 |  | SAT-5-2-7 |  | 62
2024-07-13 | 3523 |  | 79247 - 79248 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 | VD's | 2024-07-15 | Z | 2024-05-14 | 190 | 0 | 90 | F | 0 | 420 |  | AHU-5 RA |  | 62
2024-07-13 | 3524 | bth | 79249 - 79250 | A | DONE | 15 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 100 | 60 | 200 | F | 0 | 430 |  | AHU-5 RA |  | 62
2024-07-12 | 3245 | sp | 72975 - 72977 | A | DONE | 11 | S-M |  | UW-VET MED 6210014 |  | 2024-07-15 | Z | 2024-07-01 | 50 | 220 | 0 |  | 0 | 280 |  | L1-8A EA |  | 14
2024-07-12 | 3246 | bth | 72978 - 72979 | A | DONE | 5 | S |  | UW-VET MED 6210014 |  | 2024-07-15 | Z | 2024-07-01 | 60 | 60 | 0 |  | 0 | 120 |  | L1-8A SA |  | 14
[6 empty] | 1237 | [13 empty] | 35270 |  |  |  | 7420 | 21.04%
WEEK OF 7-15-2024
2024-07-16 | 2417 | bth | 78978 - 78979 | A | DONE | 4 | S |  | ABE LINCOLN 6230029 | flex , 1" liner | 2024-07-18 | Z | 2024-07-10 | 70 | 20 | 0 |  | 30 | 90 |  | AHU 6 |  | 8
2024-07-16 | 2418 |  | 78980 - 78981 | A | DONE | 4 | S-M |  | ABE LINCOLN 6230029 | flex , 1" liner | 2024-07-18 | Z | 2024-07-10 | 100 | 0 | 0 |  | 30 | 130 |  | AHU 7 |  | 8
2024-07-16 | 2419 |  | 78982 - 78983 | A | DONE | 9 | S-M |  | ABE LINCOLN 6230029 | VD , flex , 1" liner | 2024-07-18 | Z | 2024-07-10 | 160 | 0 | 60 | F | 130 | 290 |  | AHU 8 |  | 8
2024-07-16 | 2420 |  | 78984 - 78986 | A | DONE | 8 | S-M |  | ABE LINCOLN 6230029 | flex , 1" liner | 2024-07-18 | Z | 2024-07-10 | 200 | 0 | 0 |  | 140 | 300 |  | AHU-2 SA |  | 8
2024-07-16 | 2421 |  | 78987 | A | DONE | 6 | S |  | ABE LINCOLN 6230029 | flex | 2024-07-18 | Z | 2024-07-10 | 140 | 0 | 0 |  | 0 | 140 |  | AHU-1 |  | 8
2024-07-16 | 2422 | bth | 78988 - 78989 | A | DONE | 9 | S-M |  | ABE LINCOLN 6230029 | flex , 1" liner | 2024-07-18 | Z | 2024-07-10 | 190 | 20 | 0 |  | 90 | 230 |  | UV-129 |  | 8
2024-07-16 | 2423 |  | 78990 - 78991 | A | DONE | 4 | S |  | ABE LINCOLN 6230029 | flex , 1" liner | 2024-07-18 | Z | 2024-07-10 | 80 | 0 | 0 |  | 50 | 90 |  | AHU-3 |  | 8
2024-07-17 | 1767 | sp | 31248 - 31249 | A | DONE | 35 | M | neal | BLACKHAWK BTC 6230025 | s.mates | 2024-07-18 | Z | 2024-06-24 | 460 | 400 | 0 |  | 0 | 1300 |  | Weld EA |  | 24
2024-07-17 | 1769 |  | 81404 | A | DONE | 4 | S-M |  | BLACKHAWK BTC 6230025 | 1" liner | 2024-07-18 | Z | 2024-07-11 | 80 | 0 | 0 |  | 40 | 80 |  | RTU-4 |  | 7
2024-07-20 | 930 | bth | L5-A-EALP-004 | A | DONE | 6 | S | neal | CDIS 6220028 | paint | 2024-07-23 | Z | 2024-05-29 | 120 | 20 | 0 |  | 20 | 180 |  |  |  | 55 |  | 2024-07-23
2024-07-20 | 937 | sp | L5-A-EALP-012 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-07-23 | Z | 2024-05-29 | 60 | 130 | 0 |  | 0 | 210 |  |  |  | 55 |  | 2024-07-23
2024-07-20 | 939 | bth | L5-A-SALP-011 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 50 | 80 | 0 |  | 20 | 130 |  |  |  | 55 |  | 2024-07-23
2024-07-17 | 1092 |  | Pre-Fab Hangers | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-18 | Z | 2024-07-01 | 20 | 0 | 0 |  | 0 | 60 |  | 6th foor area B |  | 17
2024-07-15 | 1096 |  | 61509 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-07-16 | Z | 2024-07-02 | 50 | 0 | 0 |  | 50 | 90 |  | Basement |  | 14
2024-07-15 | 1352 |  | 61359 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-18 | Z | 2024-07-11 | 30 | 0 | 0 |  | 0 | 120 |  | EC |  | 7
2024-07-15 | 1353 | w | 61360 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-07-18 | Z | 2024-07-12 | 40 | 0 | 0 |  | 30 | 80 |  | Curb Cap |  | 6
2024-07-19 | 1354 | sp | 69924 - 69925 | A | DONE | 2 | S-M | neal | CDIS 6220028 |  | 2024-07-18 | Z | 2024-07-12 | 20 | 20 | 0 |  | 0 | 50 |  | 5th Floor |  | 6
2024-07-19 | 1355 |  | 69564 - 69567 | A | DONE | 4 | S-M | neal | CDIS 6220028 | paint , 1" liner | 2024-07-18 | Z | 2024-07-12 | 80 | 0 | 0 |  | 20 | 120 |  | 3rd Floor Misc |  | 6
2024-07-16 | 1356 |  | 69568 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-18 | Z | 2024-07-12 | 30 | 0 | 0 |  | 0 | 60 |  | 3rd Floor Misc |  | 6
2024-07-16 | 1365 |  | 69516 | A | DONE | 3 | S |  | CDIS 6220028 | paint | 2024-07-17 | Z | 2024-07-15 | 60 | 0 | 0 |  | 60 | 110 |  | Louver blank off |  | 2
2024-07-20 | 1399 |  | 61361 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-07-18 | Z | 2024-07-18 | 80 | 0 | 0 |  | 0 | 140 |  | Angle |  | 0
2024-07-20 | r872 |  | L5-B-EALP-002 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-23 | Z | 2024-07-10 | 20 | 20 | 0 |  | 0 | 20 |  | remake to neal |  | 13
2024-07-17 | 222 |  | 79421 | A | DONE | 2 | S |  | EDGERTON MS 4240020 |  | 2024-07-23 | Z | 2024-07-17 | 20 | 30 | 0 |  | 0 | 50 |  | Wall covers |  | 6
2024-07-15 | 2565 |  | 41343 | A | DONE | 2 | S | ss | EXACT 2230044 |  | 2024-07-17 | Z | 2024-06-28 | 20 | 0 | 0 |  | 0 | 20 |  | H-1 |  | 19
2024-07-19 | 2566 |  | L2-SALP-Z1-0001 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-07-22 | Z | 2024-07-09 | 70 | 0 | 100 | F | 0 | 200 |  |  |  | 13
2024-07-19 | 2567 |  | L2-SALP-Z1-0002 | A | DONE | 11 | S-M |  | EXACT TL-5 6240014 |  | 2024-07-22 | Z | 2024-07-09 | 130 | 0 | 130 | F | 0 | 310 |  |  |  | 13
2024-07-19 | 2568 |  | L2-SALP-Z1-0003 | A | DONE | 22 | M |  | EXACT TL-5 6240014 |  | 2024-07-22 | Z | 2024-07-09 | 290 | 0 | 240 | F | 0 | 670 |  |  |  | 13
2024-07-19 | 2569 |  | L2-SAMP-Z1-0001 | A | DONE | 30 | M-L |  | EXACT TL-5 6240014 |  | 2024-07-22 | Z | 2024-07-09 | 520 | 0 | 220 | F | 0 | 1440 |  |  |  | 13
2024-07-19 | 2570 |  | L2-SAMP-Z1-0002 | A | DONE | 38 | M-L |  | EXACT TL-5 6240014 |  | 2024-07-22 | Z | 2024-07-09 | 670 | 0 | 270 | F | 0 | 1480 |  |  |  | 13
2024-07-20 | 2574 |  | 41344 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-07-24 | Z | 2024-07-11 | 30 | 0 | 0 |  | 0 | 40 |  | Caps |  | 13
2024-07-16 | 4624 |  | 79466 | A | DONE | 2 | S |  | HARMONICS 6240010 | paint | 2024-07-18 | Z | 2024-07-15 | 20 | 0 | 0 |  | 30 | 40 |  | EA Grilles |  | 3
2024-07-19 | 1056 |  | 69298 | A | DONE | 3 | S |  | HERITAGE 6220024 |  | 2024-07-19 | Z | 2024-07-17 | 60 | 0 | 0 |  | 0 | 90 |  | Louver |  | 2
2024-07-17 | 2995 |  | 67575 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-07-19 | Z | 2024-07-15 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd fl |  | 4
2024-07-16 | 3163 |  | 80255 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | flex | 2024-07-18 | Z | 2024-07-01 | 20 | 0 | 0 |  | 0 | 60 |  | IF-1 |  | 17
2024-07-17 | 3164 | bth | 80256 - 80257 | A | DONE | 23 | M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-07-18 | Z | 2024-07-03 | 250 | 270 | 40 | F | 20 | 630 |  | AHU-8 |  | 15
2024-07-16 | 3165 |  | 80258 - 80260 | A | DONE | 44 | M |  | JANESVILLE ESSR 6230011 |  | 2024-07-18 | Z | 2024-07-03 | 560 | 0 | 530 | F | 0 | 1390 |  | AHU-9 |  | 15
2024-07-16 | 3167 |  | 62442 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-07-18 | Z | 2024-07-08 | 20 | 0 | 0 |  | 20 | 30 |  | Mech. Rm |  | 10
2024-07-15 | 3171 | w | 78659 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-07-18 | Z | 2024-07-12 | 30 | 0 | 0 |  | 0 | 70 |  | RE-12 Curb Adapt. |  | 6
2024-07-16 | 3172 |  | 78656 , 78660 | A | DONE | 4 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-18 | Z | 2024-07-12 | 90 | 0 | 0 |  | 0 | 120 |  | RE-12 , 14 |  | 6
2024-07-20 | 3178 |  | 80265 | A | DONE | 9 | M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-07-22 | Z | 2024-07-17 | 220 | 0 | 0 |  | 200 | 660 |  | RAHU-1 RA |  | 5
2024-07-20 | 3179 |  | 80266 | A | DONE | 8 | S-M |  | JANESVILLE ESSR 6230011 | 2" liner | 2024-07-22 | Z | 2024-07-17 | 180 | 0 | 0 |  | 140 | 390 |  | RAHU-1 SA |  | 5
2024-07-20 | 3181 |  | 80203 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-07-22 | Z | 2024-07-19 | 20 | 0 | 0 |  | 0 | 30 |  | UV-122 OA |  | 3
2024-07-19 | 2323 | bth | 67714 - 67715 | A | DONE | 8 | S-M | neal | KOHL CENTER 6210034 | VD | 2024-07-19 | Z | 2024-06-18 | 70 | 50 | 80 | F | 0 | 230 |  | Zamboni |  | 31
2024-07-17 | 2324 | bth | 67716 | A | DONE | 4 | S-M |  | KOHL CENTER 6210034 |  | 2024-07-19 | Z | 2024-06-18 | 40 | 40 | 0 |  | 0 | 80 |  | Zamboni |  | 31
2024-07-19 | 2329 |  | 67720 | A | DONE | 2 | S |  | KOHL CENTER 6210034 | 1" liner | 2024-07-19 | Z | 2024-07-12 | 20 | 0 | 0 |  | 20 | 20 |  | VAV B9 |  | 7
2024-07-15 | 2330 |  | 67719.1 | A | DONE | 3 | S |  | KOHL CENTER 6210034 |  | 2024-07-16 | Z | 2024-07-15 | 60 | 0 | 0 |  | 0 | 80 |  | Hangers |  | 1
2024-07-17 | 214 |  | 37563 | A | DONE | 3 | S |  | LINDSEY M. 1000373 | 1" liner | 2024-07-19 | Z | 2024-07-15 | 70 | 0 | 0 |  | 0 | 80 |  | RA |  | 4
2024-07-15 | 2184 |  | 68594 - 68596 | A | DONE | 14 | M |  | MEMORIAL HS 6210024 | 1" liner | 2024-07-16 | Z | 2024-07-01 | 330 | 0 | 0 |  | 210 | 880 |  | AHU-Q2 |  | 15
2024-07-15 | 2186 |  | 68598 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-07-16 | Z | 2024-07-01 | 40 | 0 | 0 |  | 40 | 90 |  | AHU-Q1 |  | 15
2024-07-15 | 2188 | w | 68600 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" DB | 2024-07-16 | Z | 2024-07-01 | 50 | 0 | 0 |  | 50 | 160 |  | Curb Adapt. |  | 15
2024-07-15 | 2189 |  | 68622 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 | 1/2" liner | 2024-07-16 | Z | 2024-07-02 | 60 | 0 | 0 |  | 40 | 80 |  | SA / RA |  | 14
2024-07-15 | 2190 |  | 68623 - 68625 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 |  | 2024-07-16 | Z | 2024-07-02 | 60 | 0 | 0 |  | 0 | 100 |  | SA / RA |  | 14
2024-07-15 | 2191 |  | 68626 | A | DONE | 2 | S-M |  | MEMORIAL HS 6210024 | 1/2" liner | 2024-07-16 | Z | 2024-07-02 | 50 | 0 | 0 |  | 20 | 90 |  | SA / RA |  | 14
2024-07-15 | 2192 |  | 68627 | A | DONE | 2 | S-M |  | MEMORIAL HS 6210024 |  | 2024-07-16 | Z | 2024-07-02 | 30 | 0 | 0 |  | 0 | 50 |  | EA Tie ins |  | 14
2024-07-15 | 2193 |  | 68101 | A | DONE | 5 | S-M |  | MEMORIAL HS 6210024 | flex | 2024-07-16 | Z | 2024-07-02 | 110 | 0 | 0 |  | 0 | 250 |  | AHU-Q1 SA |  | 14
2024-07-15 | 2194 |  | 68102 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | flex , 1" liner | 2024-07-16 | Z | 2024-07-02 | 40 | 0 | 0 |  | 30 | 110 |  | AHU-Q1 OA |  | 14
2024-07-15 | 2195 |  | 68628 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-07-16 | Z | 2024-07-03 | 30 | 0 | 0 |  | 0 | 40 |  | RA |  | 13
2024-07-17 | 2198 |  | 68105 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 |  | 2024-07-23 | Z | 2024-07-10 | 20 | 0 | 0 |  | 0 | 20 |  | Pipe Guard |  | 13
2024-07-17 | 3450 |  | 68629 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 |  | 2024-07-23 | Z | 2024-07-15 | 50 | 0 | 0 |  | 0 | 80 |  | Rm 1552 Q-Section |  | 8
2024-07-20 | 3452 |  | 68108 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 |  | 2024-07-23 | Z | 2024-07-17 | 70 | 0 | 0 |  | 0 | 210 |  | OA AHU-5 |  | 6
2024-07-20 | 3453 |  | 68109 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | paint | 2024-07-23 | Z | 2024-07-17 | 20 | 0 | 0 |  | 20 | 20 |  | Box |  | 6
2024-07-16 | 2354 |  | 80261 | A | DONE | 2 | S-M |  | MENDOTA FOOD 6220027 | paint | 2024-07-18 | Z | 2024-07-12 | 40 | 0 | 0 |  | 30 | 50 |  | Finishes |  | 6
2024-07-16 | 2355 |  | 80262 | A | DONE | 2 | S-M | pt. alum | MENDOTA FOOD 6220027 | paint | 2024-07-18 | Z | 2024-07-12 | 30 | 0 | 0 |  | 20 | 40 |  | Finishes |  | 6
2024-07-16 | 2356 |  | 80263 | A | DONE | 2 | S | alum | MENDOTA FOOD 6220027 | paint | 2024-07-18 | Z | 2024-07-12 | 30 | 0 | 0 |  | 20 | 30 |  | Wash Rm #2 |  | 6
2024-07-16 | 2633 |  | 79467 | A | DONE | 2 | S |  | OLIV 6210030 |  | 2024-07-18 | Z | 2024-07-15 | 20 | 0 | 0 |  | 0 | 20 |  | Pool mech roof |  | 3
2024-07-20 | 2634 |  | 79468 | A | DONE | 2 | S |  | OLIV 6210030 | bird s. | 2024-07-22 | Z | 2024-07-17 | 20 | 0 | 0 |  | 0 | 20 |  | HP Test table |  | 5
2024-07-17 | 3119 |  | 79640 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2024-07-22 | Z | 2024-07-17 | 40 | 0 | 0 |  | 0 | 90 |  | AHU-2 CC |  | 5
2024-07-17 | 1843 |  | 59810 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-07-18 | Z | 2024-07-17 | 40 | 0 | 0 |  | 0 | 50 |  | SA |  | 1
2024-07-17 | 3057 |  | 91651 | A | DONE | 2 | S | neal | RAMC 6230009 |  | 2024-07-22 | Z | 2024-07-16 | 50 | 0 | 0 |  | 0 | 50 |  | Fin tube shroud |  | 6
2024-07-20 | 4263 |  | 62389 - 62390 | A | DONE | 13 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-07-22 | Z | 2024-07-03 | 310 | 0 | 0 |  | 270 | 660 |  | Relief duct A ,B |  | 19
2024-07-20 | 4264 |  | 80022 | A | DONE | 2 | S |  | ST.BERNARD 6230023 |  | 2024-07-22 | Z | 2024-07-10 | 20 | 0 | 0 |  | 0 | 20 |  | VAV 6 |  | 12
2024-07-15 | 3501 | bth | 79201 - 79202 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 40 | 20 | 40 | F | 0 | 110 |  | SAT-4-2-3 |  | 62
2024-07-15 | 3502 | bth | 79203 - 79204 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 80 | 20 | 100 | F | 0 | 230 |  | SAT-4-2-4 |  | 62
2024-07-15 | 3507 | bth | 79210 - 79211 | A | DONE | 9 | S-M |  | UWL-GRAFF 6230017 |  | 2024-07-15 | Z | 2024-05-14 | 70 | 50 | 90 | F | 0 | 220 |  | SAT-4-2-6 |  | 62
2024-07-15 | 3510 | bth | 79216 - 79217 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 | VD's | 2024-07-15 | Z | 2024-05-14 | 180 | 80 | 40 | F | 0 | 330 |  | AHU-4 RA |  | 62
2024-07-15 | 3512 |  | 79220 - 79222 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 160 | 0 | 110 | F | 220 | 330 |  | 215 B,C,D TA |  | 62
2024-07-15 | 3522 | bth | 79245 - 79246 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-07-15 | Z | 2024-05-14 | 90 | 50 | 20 | F | 30 | 180 |  | SAT-5-2-8 |  | 62
2024-07-17 | 940 |  | 70153 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-22 | Z | 2024-07-16 | 50 | 0 | 0 |  | 0 | 80 |  | Shaft 194L |  | 6
2024-07-19 | 4152 | bth | L3Z2-SAT-1-3-40 | A | DONE | 12 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-17 | Z | 2024-06-13 | 120 | 90 | 70 | F | 40 | 300 |  |  | Trailer #3 | 34
2024-07-19 | 4153 | bth | L3Z2-SAT-1-3-41 | A | DONE | 11 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-17 | Z | 2024-06-13 | 110 | 90 | 70 | F | 50 | 290 |  |  | Trailer #3 | 34
2024-07-19 | 4154 | bth | L3Z2-SAT-1-3-42 | A | DONE | 7 | S |  | UWRF 6230010 | 1" liner | 2024-07-17 | Z | 2024-06-13 | 110 | 60 | 0 |  | 40 | 180 |  |  | Trailer #3 | 34
2024-07-19 | 4155 | bth | L3Z2-SAT-1-3-44 | A | DONE | 9 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-17 | Z | 2024-06-13 | 160 | 0 | 50 | F | 30 | 240 |  |  | Trailer #3 | 34
2024-07-17 | 4156 | bth | L3Z2-SAT-1-3-45 | A | DONE | 6 | S |  | UWRF 6230010 | 1" liner | 2024-07-17 | Z | 2024-06-13 | 100 | 30 | 0 |  | 60 | 140 |  |  | Trailer #3 | 34
2024-07-17 | 4157 | bth | L3Z2-SAT-1-3-46 | A | DONE | 8 | S |  | UWRF 6230010 | 1" liner | 2024-07-17 | Z | 2024-06-13 | 130 | 50 | 0 |  | 50 | 190 |  |  | Trailer #3 | 34
2024-07-19 | 4158 |  | L3Z2-SAT-1-3-47 | A | DONE | 6 | S |  | UWRF 6230010 | 1" liner | 2024-07-17 | Z | 2024-06-13 | 150 | 0 | 0 |  | 40 | 180 |  |  | Trailer #3 | 34
2024-07-19 | 4159 | sp | L3Z1-GET-1-3-3 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 30 | 20 | 0 |  | 0 | 50 |  |  | Trailer #3 | 34
2024-07-17 | 4160 | bth | L3Z1-GET-1-3-4 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 70 | 20 | 50 | F | 0 | 170 |  |  | Trailer #3 | 34
2024-07-19 | 4161 | sp | L3Z1-GET-1-3-5 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 30 | 0 |  | 0 | 40 |  |  | Trailer #3 | 34
2024-07-19 | 4162 | sp | L3Z1-GET-1-3-6 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 34
2024-07-19 | 4163 | sp | L3Z1-GET-1-3-7 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 30 | 40 | 0 |  | 0 | 70 |  |  | Trailer #3 | 34
2024-07-17 | 4164 |  | L3Z1-GET-1-3-8 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 100 | 0 | 0 |  | 0 | 120 |  |  | Trailer #3 | 34
2024-07-19 | 4165 | sp | L3Z1-GET-1-3-9 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 20 | 20 | F | 0 | 20 |  |  | Trailer #3 | 34
2024-07-19 | 4166 | sp | L3Z1-GET-1-3-19 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 40 | 0 |  | 0 | 60 |  |  | Trailer #3 | 34
2024-07-19 | 4167 | sp | L3Z1-GET-1-3-20 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 20 | 0 |  | 0 | 30 |  |  | Trailer #3 | 34
2024-07-19 | 4168 | sp | L3Z1-GET-1-3-21 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 50 | 0 |  | 0 | 60 |  |  | Trailer #3 | 34
2024-07-19 | 4169 | bth | L3Z2-GET-1-3-10 | A | DONE | 9 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 70 | 20 | 130 | F | 0 | 250 |  |  | Trailer #3 | 34
2024-07-19 | 4170 | sp | L3Z2-GET-1-3-11 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 30 | 50 | 0 |  | 0 | 80 |  |  | Trailer #3 | 34
2024-07-19 | 4171 | bth | L3Z2-GET-1-3-12 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #3 | 34
2024-07-19 | 4172 | sp | L3Z2-GET-1-3-13 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 60 | 220 | 0 |  | 0 | 280 |  |  | Trailer #3 | 34
2024-07-19 | 4173 | bth | L3Z2-GET-1-3-14 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 180 | 20 | 130 | F | 0 | 390 |  |  | Trailer #3 | 34
2024-07-19 | 4174 | bth | L3Z2-GET-1-3-15 | A | DONE | 16 | S-M |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 230 | 20 | 150 | F | 0 | 470 |  |  | Trailer #3 | 34
2024-07-19 | 4175 | bth | L3Z2-GET-1-3-16 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 70 | 20 | 30 | F | 0 | 130 |  |  | Trailer #3 | 34
2024-07-19 | 4176 | sp | L3Z2-GET-1-3-17 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 30 | 20 | 0 |  | 0 | 40 |  |  | Trailer #3 | 34
2024-07-19 | 4177 | sp | L3Z2-GET-1-3-18 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #3 | 34
2024-07-19 | 4178 | bth | L3Z2-GET-2-3-1 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 90 | 20 | 0 |  | 0 | 130 |  |  | Trailer #3 | 34
2024-07-19 | 4179 | bth | L3Z2-GET-2-3-2 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 50 | 20 | 0 |  | 0 | 60 |  |  | Trailer #3 | 34
2024-07-19 | 4180 | bth | L3Z2-GET-2-3-3 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 50 | 20 | 0 |  | 0 | 60 |  |  | Trailer #3 | 34
2024-07-19 | 4181 | bth | L3Z2-GET-2-3-4 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 60 | 20 | 20 | F | 0 | 110 |  |  | Trailer #3 | 34
2024-07-19 | 4182 | sp | L3Z2-GET-2-3-5 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 20 | 0 |  | 0 | 30 |  |  | Trailer #3 | 34
2024-07-19 | 4183 | bth | L3Z2-GET-2-3-6 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 30 | 0 |  | 0 | 60 |  |  | Trailer #3 | 34
2024-07-19 | 4184 | bth | L3Z2-GET-2-3-7 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 50 | 20 | 0 |  | 0 | 70 |  |  | Trailer #3 | 34
2024-07-19 | 4185 | bth | L3Z2-GET-2-3-8 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 40 | 20 | 0 |  | 0 | 70 |  |  | Trailer #3 | 34
2024-07-19 | 4186 | bth | L3Z2-GET-2-3-9 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 70 | 20 | 0 |  | 0 | 110 |  |  | Trailer #3 | 34
2024-07-19 | 4187 | bth | L3Z2-GET-2-3-10 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 40 | 20 | 0 |  | 0 | 50 |  |  | Trailer #3 | 34
2024-07-19 | 4188 | bth | L3Z2-GET-2-3-11 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 20 | 30 | F | 0 | 70 |  |  | Trailer #3 | 34
2024-07-19 | 4189 | sp | L3Z2-GET-2-3-12 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 34
2024-07-19 | 4190 | bth | L3Z2-GET-2-3-13 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-13 | 50 | 20 | 0 |  | 0 | 60 |  |  | Trailer #3 | 34
2024-07-19 | 4191 | bth | L3Z1-RAT-1-3-3 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-17 | 180 | 20 | 100 | F | 0 | 340 |  |  | Trailer #3 | 30
2024-07-19 | 4192 | sp | L3Z2-RAT-1-3-1 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-17 | 20 | 80 | 0 |  | 0 | 100 |  |  | Trailer #3 | 30
2024-07-19 | 4193 | bth | L3Z2-RAT-1-3-2 | A | DONE | 12 | S-M | pt.neal | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-17 | 200 | 20 | 80 | F | 0 | 340 |  |  | Trailer #3 | 30
2024-07-19 | 4194 | sp | L3Z2-RAT-1-3-4.1 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-17 | 40 | 110 | 0 |  | 0 | 160 |  |  | Trailer #3 | 30
2024-07-17 | 4195 | bth | L3Z2-RAT-1-3-4.2 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-17 | 40 | 30 | 60 | F | 0 | 140 |  |  | Trailer #3 | 30
2024-07-17 | 4196 | sp | L3Z2-FEV-3-3-22 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 30 | 50 | 0 |  | 0 | 90 |  |  | Trailer #3 | 29
2024-07-16 | 4197 | sp | L3Z2-FEV-3-3-23 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 30 | 0 |  | 0 | 50 |  |  | Trailer #3 | 29
2024-07-17 | 4198 | sp | L3Z2-FEV-3-3-24 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 30 | 20 | 0 |  | 0 | 60 |  |  | Trailer #3 | 29
2024-07-16 | 4199 | sp | L3Z2-FEV-3-3-25 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-16 | 4200 | sp | L3Z2-FEV-3-3-26 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 40 | 0 |  | 0 | 60 |  |  | Trailer #3 | 29
2024-07-17 | 4201 | sp | L3Z2-FEV-3-3-27.1 | A | DONE | 6 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 70 | 60 | 0 |  | 0 | 150 |  |  | Trailer #3 | 29
2024-07-16 | 4202 | sp | L3Z2-FEV-3-3-27.2 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 50 | 0 |  | 0 | 90 |  |  | Trailer #3 | 29
2024-07-16 | 4203 | sp | L3Z2-FEV-3-3-28 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #3 | 29
2024-07-16 | 4204 | sp | L3Z2-FEV-3-3-29 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 50 |  |  | Trailer #3 | 29
2024-07-16 | 4205 | sp | L3Z2-FEV-3-3-30 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-16 | 4206 | sp | L3Z2-FEV-3-3-31 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 30 |  |  | Trailer #3 | 29
2024-07-15 | 4207 | sp | L3Z2-FEV-3-3-32 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4208 | sp | L3Z2-FEV-3-3-33 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-16 | 4209 | sp | L3Z2-FEV-3-3-34 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4210 | sp | L3Z2-FEV-3-3-35 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-19 | 4211 | sp | L3Z2-FEV-3-3-36 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #3 | 29
2024-07-15 | 4212 | sp | L3Z2-FEV-3-3-37 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4213 | sp | L3Z2-FEV-3-3-38 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-16 | 4214 | sp | L3Z2-FEV-3-3-41 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-17 | 4215 | sp | L3Z2-FEV-3-3-42 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 40 | 70 | 0 |  | 0 | 140 |  |  | Trailer #3 | 29
2024-07-15 | 4216 | sp | L3Z1-FEV-3-3-1 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 40 |  |  | Trailer #3 | 29
2024-07-17 | 4217 | sp | L3Z1-FEV-3-3-2 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 40 | 30 | 0 |  | 0 | 80 |  |  | Trailer #3 | 29
2024-07-17 | 4218 | sp | L3Z1-FEV-3-3-4 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 50 | 60 | 0 |  | 0 | 130 |  |  | Trailer #3 | 29
2024-07-17 | 4219 | sp | L3Z1-FEV-3-3-5 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 50 | 60 | 0 |  | 0 | 130 |  |  | Trailer #3 | 29
2024-07-16 | 4220 | sp | L3Z1-FEV-3-3-6 | A | DONE | 6 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 60 | 70 | 0 |  | 0 | 170 |  |  | Trailer #3 | 29
2024-07-17 | 4221 | sp | L3Z1-FEV-3-3-7 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 60 | 50 | 0 |  | 0 | 140 |  |  | Trailer #3 | 29
2024-07-17 | 4222 | sp | L3Z1-FEV-3-3-8 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 40 | 20 | 0 |  | 0 | 70 |  |  | Trailer #3 | 29
2024-07-17 | 4223 | sp | L3Z1-FEV-3-3-9 | A | DONE | 6 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 30 | 100 | 0 |  | 0 | 160 |  |  | Trailer #3 | 29
2024-07-17 | 4224 | sp | L3Z1-FEV-3-3-10 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 30 | 70 | 0 |  | 0 | 120 |  |  | Trailer #3 | 29
2024-07-16 | 4225 | sp | L3Z1-FEV-3-3-11 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 40 | 0 |  | 0 | 60 |  |  | Trailer #3 | 29
2024-07-15 | 4226 | sp | L3Z1-FEV-3-3-12 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4227 | sp | L3Z1-FEV-3-3-13 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4228 | sp | L3Z1-FEV-3-3-14 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4229 | sp | L3Z1-FEV-3-3-15 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4230 | sp | L3Z1-FEV-3-3-16 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4231 | sp | L3Z1-FEV-3-3-17 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-16 | 4232 | sp | L3Z1-FEV-3-3-18 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-15 | 4233 | sp | L3Z1-FEV-3-3-19 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-17 | 4234 | sp | L3Z1-FEV-3-3-20.1 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 30 | 60 | 0 |  | 0 | 120 |  |  | Trailer #3 | 29
2024-07-16 | 4235 | sp | L3Z1-FEV-3-3-20.2 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 30 | 0 |  | 0 | 50 |  |  | Trailer #3 | 29
2024-07-16 | 4236 | sp | L3Z1-FEV-3-3-21 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-16 | 4237 | sp | L3Z1-FEV-3-3-39 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 20 | 0 |  | 0 | 20 |  |  | Trailer #3 | 29
2024-07-16 | 4238 | sp | L3Z1-FEV-3-3-40 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-07-17 | Z | 2024-06-18 | 20 | 30 | 0 |  | 0 | 70 |  |  | Trailer #3 | 29
2024-07-15 | 5009 | bth | SA-02-02 | A | DONE | 35 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-07-16 | Z | 2024-06-05 | 370 | 40 | 450 | F | 0 | 1190 |  |  |  | 41
2024-07-15 | 5010 | bth | SA-02-03 | A | DONE | 29 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-07-16 | Z | 2024-06-05 | 250 | 50 | 420 | F | 0 | 1150 |  |  |  | 41
2024-07-15 | 5011 | bth | SA-02-04 | A | DONE | 44 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-07-16 | Z | 2024-06-05 | 290 | 60 | 750 | F | 0 | 1540 |  |  |  | 41
2024-07-20 | 1450 | sp | 72987 | A | DONE | 7 | S-M |  | UW-VET MED 6210014 |  | 2024-07-22 | Z | 2024-07-08 | 30 | 130 | 0 |  | 0 | 150 |  | Area 9-SA |  | 14
2024-07-20 | 1451 |  | 72988 - 72989 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 | RH Coils | 2024-07-22 | Z | 2024-07-08 | 40 | 0 | 0 |  | 0 | 50 |  | Area 9-SA |  | 14
2024-07-20 | 1452 | sp | 72990 | A | DONE | 4 | S-M |  | UW-VET MED 6210014 |  | 2024-07-22 | Z | 2024-07-08 | 20 | 70 | 0 |  | 0 | 80 |  | Area 9-SA |  | 14
2024-07-20 | 1453 |  | 72991 - 72992 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 | RH Coils | 2024-07-22 | Z | 2024-07-08 | 40 | 0 | 0 |  | 0 | 50 |  | Area 9-SA |  | 14
2024-07-20 | 1454 | sp | 72993 - 72994 | A | DONE | 4 | S-M |  | UW-VET MED 6210014 |  | 2024-07-22 | Z | 2024-07-08 | 0 | 90 | 0 |  | 0 | 80 |  | Area 9-SA |  | 14
2024-07-20 | 1455 |  | 72995 - 72996 | A | DONE | 9 | S-M |  | UW-VET MED 6210014 | VD , RH Coils | 2024-07-22 | Z | 2024-07-08 | 80 | 0 | 140 | F | 0 | 270 |  | Area 9-SA |  | 14
2024-07-20 | 1456 | sp | 72997 | A | DONE | 8 | S-M |  | UW-VET MED 6210014 |  | 2024-07-22 | Z | 2024-07-08 | 40 | 140 | 0 |  | 0 | 170 |  | Area 9-SA |  | 14
2024-07-20 | 1457 |  | 72998 - 72999 | A | DONE | 18 | S-M |  | UW-VET MED 6210014 | VD | 2024-07-22 | Z | 2024-07-08 | 80 | 0 | 350 | F | 0 | 530 |  | Area 9-EA |  | 14
2024-07-20 | 1458 | sp | 73000 - 73001 | A | DONE | 10 | S-M |  | UW-VET MED 6210014 |  | 2024-07-22 | Z | 2024-07-08 | 40 | 190 | 0 |  | 0 | 210 |  | Area 9-EA |  | 14
2024-07-15 | 3247 | bth | 72980 - 72982 | A | DONE | 4 | S |  | UW-VET MED 6210014 |  | 2024-07-15 | Z | 2024-07-01 | 60 | 20 | 0 |  | 0 | 80 |  | L1-8A SA |  | 14
2024-07-20 | 3248 |  | 72983 - 72985 | A | DONE | 21 | S-M |  | UW-VET MED 6210014 | VD | 2024-07-22 | Z | 2024-07-08 | 240 | 0 | 270 | F | 0 | 610 |  | Area 9-SA |  | 14
2024-07-20 | 3249 |  | 72986 | A | DONE | 11 | S-M |  | UW-VET MED 6210014 | VD , RH Coils | 2024-07-22 | Z | 2024-07-08 | 140 | 0 | 130 | F | 0 | 320 |  | Area 9-SA |  | 14
2024-07-19 | 1050 |  | 67574 | A | DONE | 8 | S |  | WAUNAKEE HS 6240013 | VD's | 2024-07-19 | Z | 2024-07-15 | 50 | 0 | 30 | F | 0 | 90 |  | SA Area E |  | 4
2024-07-19 | 1051 |  | 67578 | A | DONE | 3 | S-M |  | WAUNAKEE HS 6240013 |  | 2024-07-19 | Z | 2024-07-16 | 70 | 0 | 0 |  | 0 | 100 |  | Wood shop |  | 3
2024-07-19 | 1052 |  | 69295 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 | 1" liner | 2024-07-19 | Z | 2024-07-16 | 20 | 0 | 0 |  | 20 | 30 |  | RA |  | 3
2024-07-19 | 1053 | sp | 67577 | A | DONE | 4 | S-M | neal | WAUNAKEE HS 6240013 |  | 2024-07-19 | Z | 2024-07-16 | 20 | 70 | 0 |  | 0 | 100 |  | Wood shop |  | 3
2024-07-19 | 1054 | bth | 69296 | A | DONE | 2 | S-M |  | WAUNAKEE HS 6240013 |  | 2024-07-19 | Z | 2024-07-16 | 20 | 0 | 0 |  | 0 | 40 |  | SA/RA |  | 3
2024-07-19 | 1055 | bth | 69297 | A | DONE | 3 | S-M |  | WAUNAKEE HS 6240013 | 1" liner | 2024-07-19 | Z | 2024-07-16 | 40 | 30 | 0 |  | 20 | 70 |  | SA/RA |  | 3
2024-07-15 | 2992 |  | 67567 , 67569 | A | DONE | 7 | S-M |  | WAUNAKEE HS 6240013 | bird.s | 2024-07-17 | Z | 2024-07-09 | 170 | 0 | 0 |  | 0 | 310 |  | Roof drops |  | 8
2024-07-15 | 2994 | sp | 67570 | A | DONE | 2 | S | neal | WAUNAKEE HS 6240013 |  | 2024-07-16 | Z | 2024-07-15 | 0 | 50 | 0 |  | 0 | 70 |  | Dust collector |  | 1
2024-07-16 | 2996 |  | 67576 | A | DONE | 2 | S | neal | WAUNAKEE HS 6240013 |  | 2024-07-19 | Z | 2024-07-15 | 20 | 0 | 0 |  | 0 | 20 |  | E-Section |  | 4
2024-07-16 | 2997 | w | 67571 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 | 1" liner | 2024-07-19 | Z | 2024-07-15 | 30 | 0 | 0 |  | 30 | 50 |  | Curb Cap |  | 4
2024-07-17 | 2998 | sp | 67572 | A | DONE | 4 | S |  | WAUNAKEE HS 6240013 |  | 2024-07-19 | Z | 2024-07-15 | 20 | 60 | 0 |  | 0 | 80 |  | SA network |  | 4
2024-07-19 | 2999 |  | 67573 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 | 1" liner | 2024-07-19 | Z | 2024-07-15 | 50 | 0 | 0 |  | 20 | 80 |  | TA network |  | 4
2024-07-20 | 1850 |  | 66089 | A | DONE | 2 | S |  | WSCC 6240006 | 1" liner | 2024-07-22 | Z | 2024-06-11 | 20 | 0 | 0 |  | 20 | 20 |  | TA A-Section |  | 41
2024-07-20 | 1851 | w | 66090 | A | DONE | 7 | S-M |  | WSCC 6240006 |  | 2024-07-22 | Z | 2024-06-11 | 160 | 0 | 0 |  | 0 | 340 |  | Sleeves |  | 41
[6 empty] | 1108 | [13 empty] | 33200 |  |  |  | 9730 | 29.31%
WEEK OF 7-22-2024
2024-07-26 | 2238 |  | 1STFL-1 | A | DONE | 2 | S-M | neal | 121 E. WILSON 6230024 |  | 2024-07-29 | Z | 2024-07-22 | 40 | 0 | 0 |  | 0 | 110 |  | Tear drops |  | 7
2024-07-23 | 2424 |  | 78992 - 78993 | A | DONE | 15 | S-M |  | ABE LINCOLN 6230029 | VD , flex , 1" liner | 2024-07-24 | Z | 2024-07-11 | 360 | 0 | 0 |  | 240 | 470 |  | Misc |  | 13
2024-07-23 | 2425 | bth | 78994 | A | DONE | 8 | S-M |  | ABE LINCOLN 6230029 |  | 2024-07-24 | Z | 2024-07-11 | 150 | 40 | 0 |  | 0 | 170 |  | Misc |  | 13
2024-07-23 | 2426 |  | 78995 - 78996 | A | DONE | 12 | S-M |  | ABE LINCOLN 6230029 | flex , 1" liner | 2024-07-24 | Z | 2024-07-11 | 200 | 0 | 80 | F | 200 | 490 |  | Misc |  | 13
2024-07-23 | 2427 |  | 78997 | A | DONE | 8 | S-M |  | ABE LINCOLN 6230029 |  | 2024-07-24 | Z | 2024-07-18 | 180 | 0 | 0 |  | 0 | 180 |  | Ceiling tie ins |  | 6
2024-07-23 | 2428 |  | 78998 | A | DONE | 2 | S |  | ABE LINCOLN 6230029 | flex | 2024-07-24 | Z | 2024-07-18 | 20 | 20 | 0 |  | 0 | 30 |  | 1st bathroom |  | 6
2024-07-23 | 2429 |  | 79000 | A | DONE | 2 | S |  | ABE LINCOLN 6230029 |  | 2024-07-24 | Z | 2024-07-23 | 20 | 0 | 0 |  | 0 | 30 |  | 2nd floor |  | 1
2024-07-22 | 1770 | sp | 81405 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-07-25 | Z | 2024-07-22 | 20 | 0 | 0 |  | 0 | 20 |  | Welding |  | 3
2024-07-22 | 931 | bth | L5-A-EALP-005 | A | DONE | 6 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 90 | 60 | 0 |  | 40 | 170 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 932 | bth | L5-A-EALP-006 | A | DONE | 4 | S | pt.neal | CDIS 6220028 |  | 2024-07-23 | Z | 2024-05-29 | 40 | 50 | 0 |  | 0 | 100 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 933 | bth | L5-A-EALP-007 | A | DONE | 5 | S | pt.neal | CDIS 6220028 | 1" sp.accu ,1" liner | 2024-07-23 | Z | 2024-05-29 | 40 | 80 | 0 |  | 20 | 120 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 934 | bth | L5-A-EALP-008 | A | DONE | 4 | S | neal | CDIS 6220028 | paint | 2024-07-23 | Z | 2024-05-29 | 60 | 40 | 0 |  | 20 | 110 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 935 | sp | L5-A-EALP-009 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-07-23 | Z | 2024-05-29 | 40 | 90 | 0 |  | 0 | 130 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 936 | bth | L5-A-EALP-010 | A | DONE | 9 | S | pt.neal | CDIS 6220028 |  | 2024-07-23 | Z | 2024-05-29 | 110 | 60 | 40 | F | 0 | 240 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 938 |  | L5-A-SALP-010 | A | DONE | 14 | S-M | neal | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 330 | 0 | 20 | F | 70 | 420 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 940 | bth | L5-A-SALP-012 | A | DONE | 8 | S | neal | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 140 | 30 | 20 | F | 50 | 220 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 941 | bth | L5-A-SALP-013 | A | DONE | 8 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 140 | 20 | 20 | F | 60 | 190 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 942 | bth | L5-A-SALP-014 | A | DONE | 8 | S |  | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 70 | 90 | 20 | F | 40 | 190 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 943 | bth | L5-A-SALP-015 | A | DONE | 8 | S | pt.neal | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 100 | 80 | 0 |  | 40 | 210 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 944 | bth | L5-A-SALP-016 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 40 | 60 | 0 |  | 20 | 100 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 945 | bth | L5-A-SALP-017 | A | DONE | 8 | S |  | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 70 | 120 | 0 |  | 30 | 200 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 946 | bth | L5-A-SALP-018 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-07-23 | Z | 2024-05-29 | 70 | 20 | 0 |  | 20 | 100 |  |  |  | 55 |  | 2024-07-23
2024-07-22 | 1301 |  | 61048 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-23 | Z | 2024-07-08 | 30 | 0 | 0 |  | 0 | 30 |  | 2nd Floor 2556 tie in |  | 15
2024-07-22 | 1302 |  | 61049 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-07-23 | Z | 2024-07-08 | 20 | 0 | 0 |  | 20 | 20 |  | 2nd Floor SA chase |  | 15
2024-07-25 | 1357 |  | SA(10wg)PH-01 | A | DONE | 116 | VL |  | CDIS 6220028 | partial , 1" DW | 2024-07-25 | Z | 2024-07-12 | 1260 | 0 | 1630 | F | 1740 | 5210 |  |  |  | 13
2024-07-25 | 1358 |  | EA-(-10wg)-PH-02 | A | DONE | 83 | L |  | CDIS 6220028 | partial , 1" DW | 2024-07-25 | Z | 2024-07-12 | 2070 | 0 | 0 |  | 810 | 3860 |  |  |  | 13
2024-07-25 | 1363 |  | 69898 - 69899 | A | DONE | 4 | S-M | pt.neal | CDIS 6220028 |  | 2024-07-25 | Z | 2024-07-15 | 80 | 0 | 0 |  | 0 | 150 |  | FD Tie in / Fin wall |  | 10
2024-07-25 | 1364 |  | 69897 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-07-25 | Z | 2024-07-15 | 120 | 0 | 0 |  | 0 | 140 |  | Flashing |  | 10
2024-07-26 | 1367 |  | 69900 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-25 | Z | 2024-07-17 | 20 | 0 | 0 |  | 0 | 20 |  | CB Rm 4695 |  | 8
2024-07-25 | 1368 |  | 69652 | A | DONE | 2 | S |  | CDIS 6220028 | 1" liner | 2024-07-25 | Z | 2024-07-17 | 30 | 0 | 0 |  | 20 | 30 |  | TA 4th floor |  | 8
2024-07-26 | 1400 |  | 69569 - 69573 | A | DONE | 6 | S-M |  | CDIS 6220028 | paint , bird s. , VD's | 2024-07-25 | Z | 2024-07-22 | 140 | 0 | 0 |  | 30 | 240 |  | 3rd flor shaft tie in |  | 3
2024-07-25 | 1403 |  | 69653 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-29 | Z | 2024-07-24 | 50 | 0 | 0 |  | 0 | 110 |  | Misc |  | 5
2024-07-25 | 1449 |  | 69654 | A | DONE | 3 | S | neal | CDIS 6220028 |  | 2024-07-25 | Z | 2024-07-23 | 60 | 0 | 0 |  | 0 | 80 |  | S/D |  | 2
2024-07-26 | 3402 |  | 69575 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-29 | Z | 2024-07-24 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor |  | 5
2024-07-22 | r3982 |  | L1-A-EAD-027 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-07-23 | Z | 2024-07-08 | 100 | 0 | 0 |  | 0 | 140 |  | Fluorecent labels | Keep separate | 15
2024-07-22 | r4035 | bth | L1-A-EAD-028 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-07-23 | Z | 2024-07-08 | 100 | 30 | 60 | F | 0 | 210 |  | Fluorecent labels | Keep separate | 15
2024-07-22 | r4036 |  | L1-A-EAD-029 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-07-23 | Z | 2024-07-08 | 190 | 0 | 60 | F | 0 | 290 |  | Fluorecent labels | Keep separate | 15
2024-07-22 | r861 | bth | L5-B-EAMP-009 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-07-23 | Z | 2024-07-10 | 30 | 70 | 150 | F | 0 | 290 |  | remake to neal |  | 13
2024-07-23 | 2571 |  | L2-EAD-Z1-0001 | A | DONE | 83 | L |  | EXACT TL-5 6240014 |  | 2024-07-24 | Z | 2024-07-09 | 1290 | 0 | 770 | F | 0 | 3840 |  |  |  | 15
2024-07-24 | 2572 |  | L2-EAD-Z1-0002 | A | DONE | 26 | M |  | EXACT TL-5 6240014 |  | 2024-07-24 | Z | 2024-07-09 | 450 | 0 | 190 | F | 0 | 940 |  |  |  | 15
2024-07-23 | 2573 |  | L2-RAD-Z1-0001 | A | DONE | 8 | S |  | EXACT TL-5 6240014 |  | 2024-07-24 | Z | 2024-07-09 | 120 | 0 | 80 | F | 0 | 230 |  |  |  | 15
2024-07-25 | 1058 |  | 69300 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-07-26 | Z | 2024-07-23 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd RA |  | 3
2024-07-24 | 1059 | sp | 79801 | A | DONE | 2 | S |  | HERITAGE 6220024 |  | 2024-07-26 | Z | 2024-07-23 | 20 | 20 | 0 |  | 0 | 30 |  | Kiln |  | 3
2024-07-26 | 725 |  | 80836 | A | DONE | 3 | S |  | HILLDALE 6240003 |  | 2024-07-29 | Z | 2024-07-18 | 70 | 0 | 0 |  | 0 | 60 |  | RTU-3 |  | 11
2024-07-25 | 726 |  | 80837 | A | DONE | 2 | S-M |  | HILLDALE 6240003 |  | 2024-07-29 | Z | 2024-07-19 | 20 | 0 | 0 |  | 0 | 20 |  | FCU-1 |  | 10
2024-07-24 | 3168 |  | 62443 - 62444 | A | DONE | 29 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-25 | Z | 2024-07-11 | 560 | 0 | 150 | F | 0 | 830 |  | AHU-2 OA |  | 14
2024-07-24 | 3169 |  | 62445 - 62447 | A | DONE | 29 | M |  | JANESVILLE ESSR 6230011 | 1" , 2" liner | 2024-07-25 | Z | 2024-07-11 | 570 | 0 | 150 | F | 510 | 1020 |  | AHU SA |  | 14
2024-07-24 | 3170 |  | 62448 - 62450 | A | DONE | 17 | M |  | JANESVILLE ESSR 6230011 | VD , 2" liner | 2024-07-25 | Z | 2024-07-11 | 410 | 0 | 0 |  | 280 | 820 |  | AHU SA |  | 14
2024-07-24 | 3173 |  | 70852 - 70854 | A | DONE | 10 | S-M |  | JANESVILLE ESSR 6230011 | 1" liner | 2024-07-25 | Z | 2024-07-15 | 240 | 0 | 0 |  | 120 | 380 |  | AHU-7 |  | 10
2024-07-24 | 3174 |  | 70855 - 70856 | A | DONE | 7 | S-M |  | JANESVILLE ESSR 6230011 | 2" liner | 2024-07-25 | Z | 2024-07-15 | 170 | 0 | 0 |  | 40 | 320 |  | AHU-6 |  | 10
2024-07-24 | 3175 | sp | 78597 | A | DONE | 4 | S |  | JANESVILLE ESSR 6230011 | bird s. | 2024-07-25 | Z | 2024-07-15 | 20 | 50 | 0 |  | 0 | 60 |  | Pool Boiler |  | 10
2024-07-24 | 3180 |  | 80264 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-07-25 | Z | 2024-07-17 | 20 | 0 | 0 |  | 0 | 20 |  | Front Entry grilles |  | 8
2024-07-24 | 3182 |  | 78661 - 78662 | A | DONE | 3 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-25 | Z | 2024-07-19 | 70 | 0 | 0 |  | 0 | 100 |  | BCU-4 / FC-2 |  | 6
2024-07-24 | 3184 |  | 78664 - 78667 | A | DONE | 7 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-25 | Z | 2024-07-22 | 160 | 0 | 0 |  | 0 | 270 |  | L1,L2, UV"s |  | 3
2024-07-24 | 3185 |  | 78668 - 78670 | A | DONE | 8 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-25 | Z | 2024-07-22 | 200 | 0 | 0 |  | 0 | 340 |  | UV's , RE-24 |  | 3
2024-07-24 | 3186 |  | 78671 - 78672 | A | DONE | 5 | S-M | alum | JANESVILLE ESSR 6230011 | flex , bird s. | 2024-07-25 | Z | 2024-07-22 | 70 | 0 | 40 | F | 0 | 70 |  | MISC |  | 3
2024-07-24 | 3188 |  | 70860 | A | DONE | 14 | S |  | JANESVILLE ESSR 6230011 | bird s. | 2024-07-25 | Z | 2024-07-23 | 330 | 0 | 0 |  | 0 | 450 |  | Misc |  | 2
2024-07-26 | 3189 |  | 70861 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-07-26 | Z | 2024-07-26 | 20 | 0 | 0 |  | 0 | 20 |  | Louver L-1 |  | 0
2024-07-25 | 1401 |  | 69574 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2024-07-29 | Z | 2024-07-22 | 20 | 0 | 0 |  | 0 | 20 |  | 1st floor |  | 7
2024-07-22 | 2199 | w | 68106 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" DB | 2024-07-23 | Z | 2024-07-12 | 50 | 0 | 0 |  | 20 | 150 |  | Cap , Adapt. |  | 11
2024-07-24 | 2357 |  | 80267 | A | DONE | 3 | S |  | MENDOTA FOODS 6220027 |  | 2024-07-25 | Z | 2024-07-19 | 70 | 0 | 0 |  | 0 | 80 |  | Louvers |  | 6
2024-07-24 | 2358 | bth | 80269 - 80271 | A | DONE | 5 | S-M |  | MENDOTA FOODS 6220027 | flex , paint | 2024-07-25 | Z | 2024-07-19 | 90 | 20 | 0 |  | 20 | 120 |  | Misc |  | 6
2024-07-22 | 313 |  | 70537 | A | DONE | 16 | S |  | PP 10056811 |  | 2024-07-22 | Z | 2024-07-22 | 400 | 0 | 0 |  | 0 | 870 |  | Flat stock |  | 0
2024-07-22 | 1844 |  | 56296 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-07-23 | Z | 2024-07-22 | 40 | 0 | 0 |  | 0 | 60 |  | Misc |  | 1
2024-07-23 | 1848 |  | 56297 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-07-23 | Z | 2024-07-23 | 30 | 0 | 0 |  | 0 | 40 |  | Misc |  | 0
2024-07-26 | 3060 | bth | 70676 | A | DONE | 2 | S |  | RAMC PT/OT 2240017 |  | 2024-07-29 | Z | 2024-07-22 | 20 | 30 | 0 |  | 0 | 50 |  | RH-G118 |  | 7
2024-07-23 | 4767 |  | 78999 | A | DONE | 2 | S | alum | ROCK CO. JAIL 6220018 |  | 2024-07-24 | Z | 2024-07-23 | 20 | 20 | 0 |  | 0 | 30 |  | Min Security |  | 1
2024-07-25 | 230 |  | 80759 | A | DONE | 2 | S |  | SSM OKEEFE 8240002 |  | 2024-07-25 | Z | 2024-07-25 | 20 | 0 | 0 |  | 0 | 60 |  | Drain plates |  | 0
2024-07-24 | 226 |  | 72424 | A | DONE | 2 | S | BI | SSM O'KEEFE 8240002 |  | 2024-07-24 | Z | 2024-07-24 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 0
2024-07-26 | 4265 |  | 80023 - 80024 | A | DONE | 3 | S-M |  | ST.BERNARD 6230023 | 1" liner | 2024-07-29 | Z | 2024-07-15 | 60 | 0 | 0 |  | 40 | 80 |  | Misc |  | 14
2024-07-25 | 225 | w | 79642 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-07-25 | Z | 2024-07-24 | 20 | 0 | 0 |  | 0 | 70 |  | Drip pan |  | 1
2024-07-22 | 941 |  | 66926 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-07-24 | Z | 2024-07-16 | 20 | 0 | 0 |  | 0 | 30 |  | L1Z1-A-SA Main |  | 8
2024-07-23 | 958 |  | 66927 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-07-24 | Z | 2024-07-23 | 130 | 0 | 0 |  | 0 | 180 |  | EA valve couplings |  | 1
2024-07-26 | 3907 | bth | L2Z1-SAT-1-2-11 | A | DONE | 2 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 20 | 20 | 0 |  | 20 | 40 |  |  | Trailer #2 | 96
2024-07-26 | 3910 | bth | L2Z1-SAT-1-2-39 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 50 | 70 | 0 |  | 30 | 110 |  |  | Trailer #2 | 96
2024-07-26 | 3911 | bth | L2Z1-SAT-1-2-40 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 50 | 40 | 0 |  | 30 | 100 |  |  | Trailer #2 | 96
2024-07-26 | 3915 |  | L2Z1-SAT-1-2-44 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 20 | 0 | 0 |  | 20 | 40 |  |  | Trailer #2 | 96
2024-07-26 | 3919 |  | L2Z1-SAT-1-2-51 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 20 | 0 | 0 |  | 20 | 30 |  |  | Trailer #2 | 96
2024-07-26 | 3925 |  | L2Z1-SAT-1-2-57 | A | DONE | 13 | S-M | pt.neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 200 | 0 | 110 | F | 90 | 390 |  |  | Trailer #2 | 96
2024-07-26 | 3928 |  | L2Z1-SAT-1-2-66 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 20 | 0 | 0 |  | 20 | 20 |  |  | Trailer #2 | 96
2024-07-26 | 4965 | bth | L2Z2-SAT-1-2-16 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 40 | 30 | 0 |  | 20 | 70 |  |  | Trailer #2 | 98
2024-07-25 | 4966 | bth | L2Z2-SAT-1-2-17 | A | DONE | 6 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 80 | 30 | 40 | F | 50 | 170 |  |  | Trailer #2 | 98
2024-07-26 | 4967 | bth | L2Z2-SAT-1-2-18 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 20 | 20 | 30 | F | 30 | 60 |  |  | Trailer #2 | 98
2024-07-26 | 4968 |  | L2Z2-SAT-1-2-19 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 20 | 0 | 0 |  | 20 | 20 |  |  | Trailer #2 | 98
2024-07-26 | 4969 |  | L2Z2-SAT-1-2-20 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 20 | 0 | 0 |  | 20 | 20 |  |  | Trailer #2 | 98
2024-07-26 | 4970 | bth | L2Z2-SAT-1-2-21 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 50 | 30 | 0 |  | 20 | 120 |  |  | Trailer #2 | 98
2024-07-26 | 4971 | bth | L2Z2-SAT-1-2-22 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 40 | 20 | 0 |  | 20 | 60 |  |  | Trailer #2 | 98
2024-07-26 | 4972 |  | L2Z2-SAT-1-2-23 | A | DONE | 5 | S | neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 70 | 0 | 50 | F | 40 | 150 |  | Exposed | Trailer #2 | 98
2024-07-26 | 4973 | bth | L2Z2-SAT-1-2-24 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 50 | 70 | 0 |  | 30 | 110 |  |  | Trailer #2 | 98
2024-07-26 | 4974 |  | L2Z2-SAT-1-2-25 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 40 | 20 | 0 |  | 20 | 50 |  |  | Trailer #2 | 98
2024-07-26 | 4975 | bth | L2Z2-SAT-1-2-26 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 50 | 30 | 0 |  | 30 | 90 |  |  | Trailer #2 | 98
2024-07-26 | 4976 |  | L2Z2-SAT-1-2-27 | A | DONE | 8 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 120 | 0 | 60 | F | 40 | 220 |  |  | Trailer #2 | 98
2024-07-26 | 4990 | bth | L2Z2-SAT-1-2-50 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 40 | 20 | 0 |  | 30 | 60 |  |  | Trailer #2 | 98
2024-07-26 | 4992 |  | L2Z2-SAT-1-2-60 | A | DONE | 4 | S | neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 100 | 0 | 0 |  | 30 | 120 |  | Exposed | Trailer #2 | 98
2024-07-26 | 4993 |  | L2Z2-SAT-1-2-62 | A | DONE | 2 | S | neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 20 | 0 | 0 |  | 20 | 40 |  | Exposed | Trailer #2 | 98
2024-07-26 | 4994 |  | L2Z2-SAT-1-2-63 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 20 | 0 | 0 |  | 20 | 30 |  |  | Trailer #2 | 98
2024-07-26 | 4997 |  | L2Z1-SAT-1-2-1 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 20 | 0 | 0 |  | 20 | 30 |  |  | Trailer #2 | 96
2024-07-23 | 5012 | bth | RA-02-02 | A | DONE | 28 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-06-05 | 390 | 20 | 270 | F | 0 | 780 |  |  |  | 48
2024-07-23 | 5013 | bth | RA-02-03 | A | DONE | 45 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-06-05 | 640 | 20 | 450 | F | 0 | 1820 |  |  |  | 48
2024-07-23 | 5014 | bth | RA-02-04 | A | DONE | 23 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-06-05 | 260 | 40 | 270 | F | 0 | 690 |  |  |  | 48
2024-07-23 | 5015 | bth | RA-02-07 | A | DONE | 14 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-06-05 | 120 | 20 | 190 | F | 0 | 390 |  |  |  | 48
2024-07-23 | 5016 |  | RA-02-08 | A | DONE | 17 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-06-05 | 200 | 0 | 210 | F | 0 | 490 |  |  |  | 48
2024-07-23 | 5022 |  | EA-03-01 | A | DONE | 5 | S |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-07-02 | 30 | 0 | 80 | F | 0 | 130 |  |  |  | 21
2024-07-23 | 5023 |  | EA-03-02 | A | DONE | 4 | S |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-07-02 | 30 | 0 | 60 | F | 0 | 110 |  |  |  | 21
2024-07-23 | 5024 |  | EA-03-03 | A | DONE | 6 | S |  | UWSP ALBERTSON 6230016 | VD's | 2024-07-23 | Z | 2024-07-02 | 130 | 0 | 20 | F | 0 | 170 |  |  |  | 21
2024-07-23 | 5025 |  | EA-03-04 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | VD's | 2024-07-23 | Z | 2024-07-02 | 250 | 0 | 40 | F | 0 | 350 |  |  |  | 21
2024-07-23 | 5026 |  | RA-03-01 | A | DONE | 15 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-07-02 | 110 | 0 | 250 | F | 0 | 730 |  |  |  | 21
2024-07-23 | 5027 |  | RA-03-02 | A | DONE | 15 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-07-02 | 50 | 0 | 320 | F | 0 | 810 |  |  |  | 21
2024-07-23 | 5028 |  | SA-03-01 | A | DONE | 13 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-07-02 | 150 | 0 | 160 | F | 0 | 560 |  |  |  | 21
2024-07-23 | 5029 |  | SA-03-08 | A | DONE | 18 | M |  | UWSP ALBERTSON 6230016 |  | 2024-07-23 | Z | 2024-07-02 | 90 | 0 | 340 | F | 0 | 940 |  |  |  | 21
2024-07-26 | 2452 |  | 72624 | A | DONE | 2 | S | BI | UWSP CHAMPIONS 6240008 |  | 2024-07-30 | Z | 2024-07-26 | 20 | 0 | 0 |  | 0 | 30 |  | Caps |  | 4
2024-07-25 | 1459 |  | 73002 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-07-29 | Z | 2024-07-15 | 20 | 0 | 0 |  | 0 | 20 |  | Arena |  | 14
2024-07-25 | 1460 | w | 73006 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-07-29 | Z | 2024-07-17 | 20 | 0 | 0 |  | 0 | 40 |  | CB-154 |  | 12
2024-07-24 | 1461 |  | 73003 | deleted |  |  | S-M |  | UW-VET MED 6210014 |  | 2024-07-31 | Z | 2024-07-17 | [7 empty] | E1-EA |  | 14
2024-07-26 | 1464 | sp | 73009 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-07-29 | Z | 2024-07-23 | 20 | 20 | 0 |  | 0 | 30 |  | 1st floor |  | 6
2024-07-25 | 1057 |  | 69299 | A | DONE | 2 | S-M |  | WAUNAKEE HS 6240013 | 1" liner | 2024-07-26 | Z | 2024-07-22 | 50 | 0 | 0 |  | 40 | 90 |  | MAU SA/RA |  | 4
2024-07-25 | 1060 |  | 79851 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 |  | 2024-07-26 | Z | 2024-07-24 | 40 | 0 | 0 |  | 0 | 40 |  | SA |  | 2
2024-07-25 | 1061 | bth | 79852 | A | DONE | 6 | S | neal | WAUNAKEE HS 6240013 |  | 2024-07-26 | Z | 2024-07-24 | 50 | 100 | 0 |  | 0 | 180 |  | Plasma Cutter |  | 2
2024-07-26 | 1062 |  | 79853 | A | DONE | 3 | S |  | WAUNAKEE HS 6240013 | VD , bird s. | 2024-07-29 | Z | 2024-07-25 | 40 | 0 | 30 | F | 0 | 80 |  | PRV-2 |  | 4
[6 empty] | 1051 | [13 empty] | 37170 |  |  |  | 16080 | 43.26%
WEEK OF 7-29-2024
2024-07-30 | 2216 |  | 200028 | A | DONE | 27 | M |  | 121 E. WILSON 6230024 | flex | 2024-07-29 | Z | 2024-06-11 | 190 | 0 | 470 | F | 0 | 650 |  | ERV-1 EA |  | 48
2024-07-30 | 2217 |  | 200029 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-29 | Z | 2024-06-11 | 50 | 0 | 0 |  | 0 | 60 |  | ERV-1 SA |  | 48
2024-07-30 | 2218 |  | 200029.1 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 |  | 2024-07-29 | Z | 2024-06-11 | 0 | 0 | 190 | F | 0 | 190 |  | ERV-1 SA |  | 48
2024-07-30 | 2219 |  | 200029.2 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 | bird s. | 2024-07-29 | Z | 2024-06-11 | 80 | 0 | 0 |  | 0 | 100 |  | ERV-1 SA |  | 48
2024-07-30 | 2220 |  | 200029.3 | A | DONE | 24 | S-M |  | 121 E. WILSON 6230024 |  | 2024-07-29 | Z | 2024-06-11 | 160 | 0 | 440 | F | 0 | 630 |  | ERV-1 SA |  | 48
2024-07-30 | 2221 |  | 200030 | A | DONE | 6 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-29 | Z | 2024-06-11 | 90 | 0 | 40 | F | 0 | 130 |  | ERV-1 RA |  | 48
2024-07-30 | 2222 |  | 200031 | A | DONE | 28 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-29 | Z | 2024-06-11 | 220 | 0 | 470 | F | 0 | 680 |  | ERV-1 OA |  | 48
2024-07-30 | 2223 |  | 200032 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-07-29 | Z | 2024-06-11 | 30 | 0 | 70 | F | 20 | 90 |  | HP-113 SA |  | 48
2024-07-30 | 2224 |  | 200033 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-29 | Z | 2024-06-11 | 20 | 0 | 40 | F | 0 | 60 |  | HP-113 RA |  | 48
2024-07-30 | 2225 |  | 200034 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 | flex | 2024-07-29 | Z | 2024-06-11 | 80 | 0 | 290 | F | 0 | 400 |  | HP-102 SA |  | 48
2024-07-29 | 2226 | bth | 200035 | A | DONE | 8 | S-M | neal | 121 E. WILSON 6230024 | flex , 1" liner | 2024-07-29 | Z | 2024-06-11 | 30 | 170 | 0 |  | 40 | 230 |  | HP-120/130 |  | 48
2024-07-30 | 2227 | bth | 200036 | A | DONE | 43 | M | neal | 121 E. WILSON 6230024 | flex , 1" liner | 2024-07-29 | Z | 2024-06-11 | 90 | 970 | 0 |  | 110 | 1220 |  | HP-140 A,B HP150 A,B,C |  | 48
2024-07-30 | 2228 | bth | 200037 | A | DONE | 10 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-07-29 | Z | 2024-06-11 | 60 | 80 | 90 | F | 20 | 200 |  | HP-107 SA |  | 48
2024-07-30 | 2229 | bth | 200038 | A | DONE | 2 | S-M | neal | 121 E. WILSON 6230024 | flex | 2024-07-29 | Z | 2024-06-11 | 20 | 20 | 0 |  | 0 | 20 |  | HP-111 SA |  | 48
2024-07-30 | 2230 |  | 200039 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 | flex , paint | 2024-07-29 | Z | 2024-06-11 | 60 | 0 | 130 | F | 20 | 180 |  | HP-105-1 RA |  | 48
2024-07-30 | 2231 | bth | 200040 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-07-29 | Z | 2024-06-11 | 40 | 30 | 130 | F | 30 | 190 |  | HP-105-1 SA |  | 48
2024-07-30 | 2232 |  | 200041 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 | flex , paint | 2024-07-29 | Z | 2024-06-11 | 30 | 0 | 90 | F | 20 | 120 |  | HP-105-2 RA |  | 48
2024-07-30 | 2233 | bth | 200042 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-07-29 | Z | 2024-06-11 | 50 | 50 | 80 | F | 20 | 180 |  | HP-105-2 SA |  | 48
2024-07-30 | 2430 | bth | 78765 - 78767 | A | DONE | 6 | S |  | ABE LINCOLN 6230029 |  | 2024-07-30 | Z | 2024-07-24 | 120 | 20 | 0 |  | 0 | 140 |  | 2nd floor |  | 6
2024-07-30 | 2431 |  | 78768 | A | DONE | 8 | S-M |  | ABE LINCOLN 6230029 | 1" liner | 2024-07-30 | Z | 2024-07-25 | 200 | 0 | 0 |  | 70 | 170 |  | 2nd floor |  | 5
2024-08-02 | 2434 |  | 78771 | A | DONE | 2 | S |  | ABE LINCOLN 6230029 | flex , paint | 2024-08-01 | Z | 2024-08-01 | 50 | 0 | 0 |  | 20 | 80 |  | EF-2 |  | 0
2024-07-29 | 1771 |  | 81407 | A | DONE | 2 | S-M | neal | BLACKHAWK BTC 6230025 |  | 2024-07-30 | Z | 2024-07-22 | 40 | 0 | 0 |  | 0 | 80 |  | Mezz flashing |  | 8
2024-07-31 | 961 |  | L6-B-EAMP-001 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 200 | 0 | 0 |  | 0 | 320 |  |  |  | 54
2024-07-31 | 962 |  | L6-B-EAMP-002 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 180 | 0 | 0 |  | 0 | 220 |  |  |  | 54
2024-07-31 | 963 |  | L6-B-EAMP-003 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 130 | 0 | 0 |  | 0 | 170 |  |  |  | 54
2024-07-31 | 964 | bth | L6-B-EAMP-004 | A | DONE | 12 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 210 | 20 | 50 | F | 0 | 360 |  |  |  | 54
2024-07-31 | 965 |  | L6-B-EAMP-005 | A | DONE | 16 | S-M | pt.neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 330 | 0 | 50 | F | 0 | 590 |  |  |  | 54
2024-07-31 | 966 | bth | L6-B-EAMP-006 | A | DONE | 9 | S-M | pt.neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 160 | 60 | 0 |  | 0 | 160 |  |  |  | 54
2024-07-31 | 967 |  | L6-B-EAMP-007 | A | DONE | 12 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 200 | 0 | 90 | F | 0 | 410 |  |  |  | 54
2024-07-31 | 968 | bth | L6-B-EAMP-008 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 50 | 20 | 130 | F | 0 | 240 |  |  |  | 54
2024-07-31 | 969 |  | L6-B-EAMP-009 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 100 | 20 | 110 | F | 0 | 260 |  |  |  | 54
2024-07-31 | 970 | bth | L6-B-EAMP-010 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 100 | 30 | 80 | F | 0 | 250 |  |  |  | 54
2024-07-31 | 971 |  | L6-B-EAMP-011 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 40 | 0 | 170 | F | 0 | 250 |  |  |  | 54
2024-07-31 | 972 | bth | L6-B-EAMP-012 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 80 | 20 | 30 | F | 0 | 140 |  |  |  | 54
2024-07-31 | 973 |  | L6-A-EAMP-030 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 100 | 20 | 60 | F | 0 | 200 |  |  |  | 54
2024-07-31 | 974 | bth | L6-A-EAMP-031 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 90 | 30 | 0 |  | 0 | 130 |  |  |  | 54
2024-07-31 | 975 | bth | L6-A-SAMP-052 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 70 | 20 | 20 | F | 0 | 120 |  |  |  | 54
2024-07-31 | 976 | bth | L6-A-SAMP-053 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 50 | 20 | 40 | F | 0 | 120 |  |  |  | 54
2024-07-31 | 977 | bth | L6-A-SAMP-054 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 54
2024-07-31 | 978 | bth | L6-B-SAMP-001 | A | DONE | 21 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 360 | 20 | 130 | F | 0 | 800 |  |  |  | 54
2024-07-31 | 979 | bth | L6-B-SAMP-002 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 70 | 20 | 110 | F | 0 | 250 |  |  |  | 54
2024-07-31 | 980 | bth | L6-B-SAMP-003 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 160 | 20 | 0 |  | 0 | 250 |  |  |  | 54
2024-07-31 | 981 | bth | L6-B-SAMP-004 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 160 | 20 | 0 |  | 0 | 240 |  |  |  | 54
2024-07-31 | 982 |  | L6-B-SAMP-005 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 60 | 0 | 60 | F | 0 | 160 |  |  |  | 54
2024-07-31 | 983 | bth | L6-B-SAMP-006 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 240 | 20 | 30 | F | 0 | 330 |  |  |  | 54
2024-08-01 | 984 | bth | L6-B-SAMP-007 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 30 | 20 | 120 | F | 0 | 190 |  |  |  | 54
2024-08-01 | 985 | bth | L6-B-SAMP-008 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 100 | 30 | 0 |  | 0 | 160 |  |  |  | 54
2024-07-31 | 986 |  | L6-B-SAMP-009 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 160 | 0 | 30 | F | 0 | 250 |  |  |  | 54
2024-07-31 | 987 | bth | L6-B-SAMP-010 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 110 | 30 | 150 | F | 0 | 340 |  |  |  | 54
2024-08-01 | 988 | bth | L6-B-SAMP-011 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 150 | 20 | 0 |  | 0 | 210 |  |  |  | 54
2024-08-01 | 989 | bth | L6-B-SAMP-012 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 170 | 20 | 60 | F | 0 | 310 |  |  |  | 54
2024-07-31 | 990 | bth | L6-B-SAMP-013 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-06-06 | 50 | 30 | 60 | F | 0 | 150 |  |  |  | 54
2024-08-01 | 991 |  | L6-B-SAMP-014 | A | DONE | 2 | S |  | CDIS 6220028 | VD | 2024-07-30 | Z | 2024-06-06 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 54
2024-08-02 | 1093 |  | Pre-Fab Hangers | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-01 | Z | 2024-07-01 | 40 | 0 | 0 |  | 0 | 60 |  | 6th foor area A |  | 31
2024-07-30 | 1359 |  | EA(-6wg)PH-01 | A | DONE | 21 | M-L |  | CDIS 6220028 | partial | 2024-07-30 | Z | 2024-07-12 | 360 | 0 | 150 | F | 0 | 1140 |  |  |  | 18
2024-07-30 | 1360 |  | SA(2wg)PH-FCU-1 | A | DONE | 23 | M |  | CDIS 6220028 | flex , VD | 2024-07-30 | Z | 2024-07-12 | 480 | 0 | 90 | F | 0 | 860 |  |  |  | 18
2024-07-30 | 1361 |  | RA(-2wg)PH-FCU-1 | A | DONE | 17 | M |  | CDIS 6220028 | flex , VD | 2024-07-30 | Z | 2024-07-12 | 370 | 0 | 50 | F | 0 | 630 |  |  |  | 18
2024-07-30 | 1362 |  | OA(4wg)PH-10 | A | DONE | 26 | M-L |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-07-12 | 130 | 0 | 520 | F | 0 | 1100 |  |  |  | 18
2024-07-29 | 1366 |  | 69926 | A | DONE | 2 | S | neal | CDIS 6220028 | paint | 2024-07-30 | Z | 2024-07-15 | 20 | 0 | 0 |  | 20 | 20 |  | 5th floor |  | 15
2024-07-29 | 1402 |  | 61514 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-07-30 | Z | 2024-07-23 | 20 | 0 | 0 |  | 0 | 20 |  | Basement |  | 7
2024-07-29 | 3403 |  | 69930 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-07-24 | 30 | 0 | 0 |  | 0 | 50 |  | 5th floor |  | 6
2024-08-01 | 3404 |  | 69655 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-08-01 | Z | 2024-07-24 | 20 | 0 | 0 |  | 0 | 20 |  | FSD out 6th floor |  | 8
2024-07-30 | 3405 |  | 69656 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-01 | Z | 2024-07-24 | 20 | 0 | 0 |  | 0 | 20 |  | L5-EALP-003 |  | 8
2024-08-01 | 3407 |  | 69929 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-06 | Z | 2024-07-24 | 20 | 0 | 0 |  | 0 | 30 |  | 5th floor |  | 13
2024-07-29 | 3408 |  | 69657 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-07-30 | Z | 2024-07-29 | 30 | 0 | 0 |  | 0 | 50 |  | Sleeve |  | 1
2024-07-31 | 3412 | w | 69620 | A | DONE | 2 | S | BI,alum | CDIS 6220028 |  | 2024-08-07 | Z | 2024-07-29 | 20 | 0 | 0 |  | 0 | 60 |  | Storm collar |  | 9
2024-08-01 | 3413 |  | 64707 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-08-01 | Z | 2024-07-30 | 20 | 0 | 0 |  | 0 | 40 |  | 6th floor sleeve ext. |  | 2
2024-08-03 | 3434 |  | 69659 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-08-06 | Z | 2024-08-02 | 50 | 0 | 0 |  | 0 | 140 |  | EC |  | 4
2024-08-02 | 215 |  | 79778 | A | DONE | 6 | S-M |  | COMPASS HP 4230088 | 1" liner | 2024-08-05 | Z | 2024-07-15 | 140 | 0 | 0 |  | 130 | 280 |  | High side |  | 21
2024-08-02 | 216 |  | 79779 - 79781 | A | DONE | 29 | M |  | COMPASS HP 4230088 | oval , accuflange | 2024-08-05 | Z | 2024-07-15 | 110 | 610 | 0 |  | 0 | 790 |  | High side |  | 21
2024-08-02 | 217 |  | 79782 | A | DONE | 11 | S-M |  | COMPASS HP 4230088 | 1" liner | 2024-08-05 | Z | 2024-07-16 | 260 | 0 | 0 |  | 240 | 470 |  | RA |  | 20
2024-07-29 | 224 |  | 79793 | A | DONE | 2 | S |  | COMPASS HP 4230088 |  | 2024-07-31 | Z | 2024-07-24 | 30 | 0 | 0 |  | 0 | 50 |  | C-Channel |  | 7
2024-07-31 | 229 | sp | 62395 | A | DONE | 5 | S |  | DEFOREST HS |  | 2024-07-30 | Z | 2024-07-25 | 20 | 90 | 0 |  | 0 | 100 |  | VAV connection |  | 5
2024-08-01 | 2575 |  | L2-EAD-Z2-0012 | A | DONE | 46 | M-L |  | EXACT TL-5 6240014 |  | 2024-07-31 | Z | 2024-07-25 | 370 | 0 | 770 | F | 0 | 1950 |  |  |  | 6
2024-08-01 | 2576 |  | L2-EAD-Z2-0013 | A | DONE | 36 | M-L |  | EXACT TL-5 6240014 |  | 2024-07-31 | Z | 2024-07-25 | 270 | 0 | 630 | F | 0 | 1500 |  |  |  | 6
2024-08-01 | 2580 |  | L2-EAD-Z2-0018 | A | DONE | 21 | M |  | EXACT TL-5 6240014 |  | 2024-07-31 | Z | 2024-07-25 | 250 | 0 | 270 | F | 0 | 820 |  |  |  | 6
2024-07-31 | 2581 | sp | L2-SAMP-Z2-0009 | A | DONE | 8 | S |  | EXACT TL-5 6240014 |  | 2024-07-31 | Z | 2024-07-25 | 20 | 160 | 0 |  | 0 | 160 |  |  |  | 6
2024-08-01 | 2582 |  | L2-SAMP-Z2-0010 | A | DONE | 42 | M-L |  | EXACT TL-5 6240014 |  | 2024-07-31 | Z | 2024-07-25 | 520 | 0 | 520 | F | 0 | 2010 |  |  |  | 6
2024-08-01 | 2583 | bth | L2-SAMP-Z2-0011 | A | DONE | 33 | M-L |  | EXACT TL-5 6240014 |  | 2024-07-31 | Z | 2024-07-25 | 350 | 30 | 430 | F | 0 | 1310 |  |  |  | 6
2024-08-01 | 2584 | bth | L2-SAMP-Z2-0012 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2024-07-31 | Z | 2024-07-25 | 40 | 20 | 0 |  | 0 | 50 |  |  |  | 6
2024-08-01 | 2585 |  | L2-EAD-Z2-0019 | A | DONE | 20 | M |  | EXACT TL-5 6240014 |  | 2024-07-31 | Z | 2024-07-26 | 200 | 0 | 300 | F | 0 | 880 |  |  |  | 5
2024-07-31 | 1064 |  | 79855 | A | DONE | 3 | S |  | HERITAGE 2240047 |  | 2024-08-02 | Z | 2024-07-31 | 70 | 0 | 0 |  | 0 | 80 |  | Condensate bracket |  | 2
2024-07-29 | 723 | bth | 80823 - 80824 | A | DONE | 10 | S-M |  | HILLDALE 6240003 |  | 2024-07-29 | Z | 2024-07-11 | 100 | 40 | 110 | F | 0 | 230 |  | EF |  | 18
2024-07-29 | 724 |  | 80825 - 80826 | A | DONE | 13 | S-M |  | HILLDALE 6240003 | bird.s | 2024-07-29 | Z | 2024-07-11 | 140 | 0 | 170 | F | 0 | 300 |  | IH-1 |  | 18
2024-07-29 | 3176 |  | 70857 | A | DONE | 10 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-30 | Z | 2024-07-16 | 250 | 0 | 0 |  | 0 | 600 |  | AHU-4 OA |  | 14
2024-07-29 | 3177 |  | 70858 - 70859 | A | DONE | 25 | M |  | JANESVILLE ESSR 6230011 | VD , 1" liner | 2024-07-30 | Z | 2024-07-16 | 480 | 0 | 130 | F | 370 | 920 |  | AHU-4 RA , RE-9 |  | 14
2024-07-29 | 3183 |  | 78663 | A | DONE | 6 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-07-30 | Z | 2024-07-19 | 130 | 0 | 0 |  | 0 | 300 |  | AHU-6,7 |  | 11
2024-07-29 | 3187 |  | 73051 - 73053 | A | DONE | 4 | S-M |  | JANESVILLE ESSR 6230011 | bird s. | 2024-07-30 | Z | 2024-07-22 | 100 | 0 | 0 |  | 0 | 150 |  | RE 5,6,18,21,23 |  | 8
2024-07-30 | 3190 |  | 78675 - 78676 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | paint , 1" liner | 2024-07-30 | Z | 2024-07-29 | 30 | 0 | 0 |  | 30 | 50 |  | RA Grilles |  | 1
2024-08-03 | 3196 |  | 78683 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-06 | Z | 2024-08-02 | 20 | 0 | 0 |  | 0 | 20 |  | Kitchen |  | 4
2024-08-02 | 1900 |  | 62392 | A | DONE | 5 | S-M |  | JPC OFFICE 6240002 | 1" liner | 2024-08-05 | Z | 2024-07-24 | 120 | 0 | 0 |  | 100 | 330 |  | Curb cap |  | 12
2024-08-02 | 2331 | bth | 67721 | A | DONE | 4 | S-M |  | KOHL CENTER 6210034 |  | 2024-08-02 | Z | 2024-07-25 | 60 | 40 | 0 |  | 0 | 110 |  | Misc |  | 8
2024-08-02 | 2332 |  | 67722 | A | DONE | 2 | S |  | KOHL CENTER 6210034 |  | 2024-08-02 | Z | 2024-07-29 | 30 | 0 | 0 |  | 0 | 60 |  | EA |  | 4
2024-07-31 | 2333 |  | 67723 | A | DONE | 2 | S |  | KOHL CENTER 6210034 |  | 2024-08-02 | Z | 2024-07-29 | 20 | 0 | 0 |  | 0 | 20 |  | Mezz |  | 4
2024-07-29 | 3451 |  | 68107 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-07-30 | Z | 2024-07-15 | 30 | 0 | 0 |  | 20 | 80 |  | EC , Angles |  | 15
2024-07-30 | 3454 |  | 68110 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 | 1" liner | 2024-07-30 | Z | 2024-07-17 | 40 | 0 | 0 |  | 30 | 100 |  | Q1 SA |  | 13
2024-07-29 | 3455 |  | 68111 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-07-30 | Z | 2024-07-18 | 20 | 0 | 0 |  | 0 | 40 |  | AHU-Q2 |  | 12
2024-07-29 | 3456 |  | 68112 | A | DONE | 2 | S-M |  | MEMORIAL HS 6210024 |  | 2024-07-30 | Z | 2024-07-24 | 40 | 0 | 0 |  | 0 | 110 |  | A5-OA |  | 6
2024-08-02 | 3457 |  | 68631 | A | DONE | 2 | S-M |  | MEMORIAL HS 6210024 |  | 2024-08-05 | Z | 2024-07-30 | 50 | 0 | 0 |  | 0 | 110 |  | EC's |  | 6
2024-07-30 | 2359 |  | 80272 - 80274 | A | DONE | 5 | S-M | pt.alum | MENDOTA FOODS 6220027 | paint , 1" liner | 2024-07-30 | Z | 2024-07-24 | 120 | 0 | 0 |  | 80 | 180 |  | Finishes |  | 6
2024-07-30 | 2360 |  | 80275 - 80276 | A | DONE | 4 | S-M | pt.alum | MENDOTA FOODS 6220027 | paint , 1" liner | 2024-07-30 | Z | 2024-07-24 | 80 | 0 | 0 |  | 70 | 90 |  | Finishes |  | 6
2024-07-31 | 2635 |  | 79469 | A | DONE | 2 | S |  | OLIV 6210030 | bird s. | 2024-07-31 | Z | 2024-07-29 | 20 | 0 | 0 |  | 0 | 30 |  | PH / HP-9 |  | 2
2024-08-01 | 1840 | w | 56290 - 56292 | A | DONE | 4 | M |  | PROMEGA CMC 2240038 | 1" wrap , spiralmate | 2024-08-05 | Z | 2024-07-11 | 80 | 0 | 0 |  | 0 | 280 |  | Roof |  | 25
2024-08-03 | 1841 | sp | 62704 , 62706 - 62707 | A | DONE | 14 | M |  | PROMEGA CMC 2240038 | spiralmate | 2024-08-05 | Z | 2024-07-11 | 110 | 230 | 0 |  | 0 | 390 |  | Roof |  | 25
2024-08-01 | 1842 | sp | 62705 | A | DONE | 3 | S-M | ss | PROMEGA CMC 2240038 | spiralmate | 2024-08-05 | Z | 2024-07-11 | 30 | 30 | 0 |  | 0 | 60 |  | Rm 1344 |  | 25
2024-07-29 | 3058 | bth | 70668 , 70670 | A | DONE | 11 | S-M |  | RAMC PT/OT 2240017 | VD | 2024-07-29 | Z | 2024-07-22 | 120 | 140 | 0 |  | 0 | 300 |  | RH-G112 SA |  | 7
2024-07-29 | 3059 |  | 70671 - 70673 | A | DONE | 7 | S-M |  | RAMC PT/OT 2240017 | VD's | 2024-07-29 | Z | 2024-07-22 | 110 | 0 | 50 | F | 0 | 190 |  | G112,115,120 |  | 7
2024-07-31 | 232 |  | 73124 | A | DONE | 2 | S | BI | SSM O'KEEFE 8240002 |  | 2024-07-31 | Z | 2024-07-31 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 0
2024-08-01 | 233 |  | 80760 | A | DONE | 2 | S |  | SSM O'KEEFE 8240002 |  | 2024-08-01 | Z | 2024-07-31 | 20 | 0 | 0 |  | 0 | 20 |  | L-Channel |  | 1
2024-07-29 | 3600 | w | 67713 | A | DONE | 3 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-08-16 | Z | 2024-06-18 | 60 | 0 | 0 |  | 0 | 140 |  | Curb caps |  | 59
2024-07-31 | 3601 |  | 86784 | A | DONE | 2 | S | BI | STOUGHTON TRAILERS 6240015 |  | 2024-07-31 | Z | 2024-07-31 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 0
2024-07-31 | 231 |  | 78735 | A | DONE | 2 | S | ss | THERMO FISHER 10056762 |  | 2024-07-31 | Z | 2024-07-29 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 2
2024-08-01 | 223 |  | 79641 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-08-05 | Z | 2024-07-23 | 50 | 0 | 0 |  | 0 | 80 |  | OR 4 RA tap |  | 13
2024-07-31 | 233 |  | 70078 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-08-05 | Z | 2024-03-12 | 50 | 0 | 0 |  | 0 | 60 |  | 1330 LPSA |  | 146 |  | 2024-04-22 | 2024-06-03 | 2024-06-17
2024-08-02 | 234 | sp | 70079 | A | DONE | 13 | S |  | UPLAND HILLS 2240008 |  | 2024-08-05 | Z | 2024-03-12 | 140 | 170 | 0 |  | 0 | 280 |  | 1330 LPSA |  | 146 |  | 2024-04-22 | 2024-06-03 | 2024-06-17
2024-08-02 | 235 | bth | 70080 - 70081 | A | DONE | 8 | S-M |  | UPLAND HILLS 2240008 |  | 2024-08-05 | Z | 2024-03-12 | 110 | 40 | 50 | F | 0 | 380 |  | 1330 LPRA |  | 146 |  | 2024-04-22 | 2024-06-03 | 2024-06-17
2024-08-02 | 236 |  | 70083 | A | DONE | 12 | S-M |  | UPLAND HILLS 2240008 |  | 2024-08-05 | Z | 2024-03-12 | 210 | 0 | 90 | F | 0 | 290 |  | 1330 LPRA |  | 146 |  | 2024-04-22 | 2024-06-03 | 2024-06-17
2024-08-02 | 237 |  | 70084 | A | DONE | 9 | S-M |  | UPLAND HILLS 2240008 | paint | 2024-08-05 | Z | 2024-03-12 | 70 | 0 | 140 | F | 0 | 200 |  | 1330 LPRA |  | 146 |  | 2024-04-29 | 2024-06-10 | 2024-06-24
2024-08-02 | 238 |  | 70085 - 70086 | A | DONE | 6 | S-M |  | UPLAND HILLS 2240008 | paint | 2024-08-05 | Z | 2024-03-12 | 120 | 0 | 30 | F | 0 | 140 |  | 1330 LPRA SW |  | 146 |  | 2024-04-29 | 2024-06-10 | 2024-06-24
2024-08-02 | 239 |  | 70087 | A | DONE | 6 | S-M |  | UPLAND HILLS 2240008 |  | 2024-08-05 | Z | 2024-03-12 | 80 | 0 | 70 | F | 0 | 140 |  | 1330 EA |  | 146 |  | 2024-04-29 | 2024-06-10 | 2024-06-24
2024-08-01 | 2453 |  | 96552 | A | DONE | 2 | S | BI | UW-CHAMPIONS HALL 6240008 |  | 2024-08-01 | Z | 2024-07-31 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 1
2024-07-29 | 3560 |  | 58945 - 58946 | A | DONE | 14 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-05 | Z | 2024-07-10 | 130 | 0 | 200 | F | 0 | 460 |  | AHU-4 RA |  | 26
2024-08-03 | 3561 |  | 58947 - 58948 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-05 | Z | 2024-07-10 | 130 | 0 | 120 | F | 0 | 430 |  | AHU-4 SA |  | 26
2024-08-03 | 3562 |  | 58949 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-05 | Z | 2024-07-10 | 30 | 0 | 250 | F | 0 | 440 |  | AHU-4 RA |  | 26
2024-07-29 | 3563 |  | 58950 , 79351 | A | DONE | 18 | M |  | UWL-GRAFF 6230017 |  | 2024-08-05 | Z | 2024-07-10 | 150 | 0 | 300 | F | 0 | 890 |  | AHU-5 RA |  | 26
2024-08-03 | 3564 |  | 79352 - 79353 | A | DONE | 16 | M |  | UWL-GRAFF 6230017 |  | 2024-08-05 | Z | 2024-07-10 | 80 | 0 | 310 | F | 0 | 610 |  | AHU-5 SA |  | 26
2024-08-03 | 3572 | sp | 79335 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-08-12 | Z | 2024-07-25 | 20 | 0 | 0 |  | 0 | 20 |  | AHU-4 SA |  | 18
2024-08-03 | 3573 |  | 79336 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-08-12 | Z | 2024-07-25 | 30 | 0 | 20 | F | 0 | 60 |  | SAT-5-3-2 |  | 18
2024-08-03 | 3575 |  | 79338 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-08-05 | Z | 2024-07-29 | 20 | 0 | 0 |  | 0 | 20 |  | AHU-RA-2nd |  | 7
2024-08-03 | 1000 | bth | 66928 | A | DONE | 56 | S-M |  | UWRF 6230010 |  | 2024-08-07 | Z | 2024-07-25 | 1300 | 80 | 0 |  | 0 | 1900 |  | Misc flashing |  | 13
2024-07-29 | 3900 |  | L2Z1-SAT-1-2-4 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 40 | 0 | 0 |  | 20 | 50 |  |  | Trailer #2 | 96
2024-07-29 | 3901 | bth | L2Z1-SAT-1-2-5 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 40 | 20 | 0 |  | 20 | 50 |  |  | Trailer #2 | 96
2024-07-29 | 3902 | bth | L2Z1-SAT-1-2-6 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 30 | 40 | 30 | F | 30 | 90 |  |  | Trailer #2 | 96
2024-07-29 | 3903 | bth | L2Z1-SAT-1-2-7 | A | DONE | 7 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 90 | 70 | 0 |  | 30 | 170 |  |  | Trailer #2 | 96
2024-07-29 | 3904 | bth | L2Z1-SAT-1-2-8 | A | DONE | 14 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 190 | 140 | 0 |  | 110 | 360 |  |  | Trailer #2 | 96
2024-07-29 | 3905 | bth | L2Z1-SAT-1-2-9 | A | DONE | 8 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 80 | 110 | 0 |  | 30 | 210 |  |  | Trailer #2 | 96
2024-07-29 | 3906 | bth | L2Z1-SAT-1-2-10 | A | DONE | 14 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 170 | 70 | 110 | F | 50 | 380 |  |  | Trailer #2 | 96
2024-07-29 | 3908 |  | L2Z1-SAT-1-2-37 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 40 | 0 | 0 |  | 20 | 50 |  |  | Trailer #2 | 96
2024-07-29 | 3909 | bth | L2Z1-SAT-1-2-38 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 50 | 50 | 0 |  | 30 | 100 |  |  | Trailer #2 | 96
2024-07-29 | 3912 |  | L2Z1-SAT-1-2-41 | A | DONE | 6 | S | neal | UWRF 6230010 | VD's ,1" liner | 2024-07-24 | Z | 2024-04-19 | 100 | 0 | 50 | F | 30 | 180 |  | Exposed | Trailer #2 | 96
2024-07-29 | 3913 | bth | L2Z1-SAT-1-2-42 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 30 | 20 | 0 |  | 20 | 40 |  |  | Trailer #2 | 96
2024-07-29 | 3914 | bth | L2Z1-SAT-1-2-43 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 50 | 30 | 0 |  | 20 | 80 |  |  | Trailer #2 | 96
2024-07-29 | 3916 | bth | L2Z1-SAT-1-2-45 | A | DONE | 4 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 60 | 20 | 0 |  | 30 | 80 |  |  | Trailer #2 | 96
2024-07-29 | 3917 | bth | L2Z1-SAT-1-2-46 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 20 | 20 | 30 | F | 30 | 70 |  |  | Trailer #2 | 96
2024-07-29 | 3918 | bth | L2Z1-SAT-1-2-47 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 70 | 40 | 0 |  | 30 | 110 |  |  | Trailer #2 | 96
2024-07-29 | 3920 |  | L2Z1-SAT-1-2-52 | A | DONE | 2 | S | neal | UWRF 6230010 | VD's ,1" liner | 2024-07-24 | Z | 2024-04-19 | 40 | 0 | 0 |  | 20 | 60 |  | Exposed | Trailer #2 | 96
2024-07-29 | 3921 |  | L2Z1-SAT-1-2-53 | A | DONE | 2 | S | neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 50 | 0 | 0 |  | 20 | 60 |  | Exposed | Trailer #2 | 96
2024-07-29 | 3922 | bth | L2Z1-SAT-1-2-54 | A | DONE | 4 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 40 | 20 | 30 | F | 30 | 80 |  |  | Trailer #2 | 96
2024-07-29 | 3923 | bth | L2Z1-SAT-1-2-55 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 40 | 20 | 0 |  | 20 | 60 |  |  | Trailer #2 | 96
2024-07-29 | 3924 | bth | L2Z1-SAT-1-2-56 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 60 | 20 | 0 |  | 30 | 90 |  |  | Trailer #2 | 96
2024-07-29 | 3926 |  | L2Z1-SAT-1-2-58 | A | DONE | 5 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 70 | 0 | 40 | F | 40 | 130 |  | Exposed | Trailer #2 | 96
2024-07-29 | 3927 |  | L2Z1-SAT-1-2-65 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 30 | 0 | 0 |  | 20 | 40 |  |  | Trailer #2 | 96
2024-08-03 | 4058 |  | L3Z2-SAT-1-3-37 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 70 | 0 | 0 |  | 20 | 110 |  |  | Trailer #4 | 88
2024-08-03 | 4072 |  | L3Z2-SAT-1-3-69 | A | DONE | 2 | S | neal | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 0 | 0 |  | 20 | 50 |  |  | Trailer #4 | 88
2024-08-03 | 4075 |  | L3Z2-SAT-1-3-72 | A | DONE | 2 | S | neal | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 0 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-03 | 4079 |  | L3Z2-SAT-1-3-77 | A | DONE | 10 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 140 | 0 | 90 | F | 20 | 260 |  |  | Trailer #4 | 88
2024-07-29 | 4961 | bth | L2Z2-SAT-1-2-12 | A | DONE | 19 | M |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 130 | 200 | 140 | F | 60 | 500 |  |  | Trailer #2 | 98
2024-07-29 | 4962 | bth | L2Z2-SAT-1-2-13 | A | DONE | 6 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 50 | 60 | 30 | F | 40 | 160 |  |  | Trailer #2 | 98
2024-07-29 | 4963 | bth | L2Z2-SAT-1-2-14 | A | DONE | 18 | M |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 180 | 190 | 70 | F | 60 | 470 |  |  | Trailer #2 | 98
2024-07-29 | 4964 | bth | L2Z2-SAT-1-2-15 | A | DONE | 11 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 180 | 90 | 0 |  | 60 | 290 |  |  | Trailer #2 | 98
2024-07-29 | 4977 | bth | L2Z2-SAT-1-2-28 | A | DONE | 2 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 30 | 20 | 0 |  | 20 | 40 |  |  | Trailer #2 | 98
2024-07-29 | 4988 |  | L2Z2-SAT-1-2-48 | A | DONE | 5 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 50 | 30 | 30 | F | 40 | 120 |  |  | Trailer #2 | 98
2024-07-29 | 4989 | bth | L2Z2-SAT-1-2-49 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 40 | 20 | 0 |  | 30 | 60 |  |  | Trailer #2 | 98
2024-07-29 | 4991 | bth | L2Z2-SAT-1-2-59 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-17 | 30 | 20 | 30 | F | 30 | 60 |  |  | Trailer #2 | 98
2024-07-29 | 4998 | bth | L2Z1-SAT-1-2-2 | A | DONE | 10 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 140 | 70 | 30 | F | 50 | 260 |  |  | Trailer #2 | 96
2024-07-29 | 4999 | bth | L2Z1-SAT-1-2-3 | A | DONE | 10 | S-M |  | UWRF 6230010 | 1" liner | 2024-07-24 | Z | 2024-04-19 | 80 | 90 | 60 | F | 40 | 250 |  |  | Trailer #2 | 96
2024-07-31 | 5030 | bth | SA-03-02 | A | DONE | 43 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-07-30 | Z | 2024-07-02 | 350 | 70 | 640 | F | 0 | 1920 |  |  |  | 28
2024-07-31 | 5031 | bth | SA-03-03 | A | DONE | 47 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-07-30 | Z | 2024-07-02 | 710 | 50 | 400 | F | 0 | 1510 |  |  |  | 28
2024-08-01 | 5032 | bth | SA-03-04 | A | DONE | 33 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-07-30 | Z | 2024-07-02 | 570 | 20 | 230 | F | 0 | 1540 |  |  |  | 28
2024-08-01 | 5033 | bth | SA-03-05 | A | DONE | 11 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-07-30 | Z | 2024-07-02 | 140 | 50 | 70 | F | 0 | 310 |  |  |  | 28
2024-08-01 | 5034 | bth | SA-03-06 | A | DONE | 11 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-07-30 | Z | 2024-07-02 | 130 | 20 | 120 | F | 0 | 320 |  |  |  | 28
2024-08-01 | 5035 | bth | SA-03-07 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-07-30 | Z | 2024-07-02 | 100 | 50 | 150 | F | 0 | 340 |  |  |  | 28
2024-07-31 | 1462 |  | 73004 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-07-31 | Z | 2024-07-17 | 20 | 0 | 0 |  | 0 | 20 |  | CB-155 |  | 14
2024-07-31 | 1463 |  | 73005 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-07-31 | Z | 2024-07-17 | 20 | 0 | 0 |  | 0 | 20 |  | RH-4-1-13 |  | 14
2024-08-01 | 1466 | sp | 73056 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-08-05 | Z | 2024-07-30 | 20 | 20 | 0 |  | 0 | 20 |  | 1st EA |  | 6
2024-08-03 | 1065 | bth | 67581 , 67583 | A | DONE | 14 | S-M |  | WAUNAKEE HS 6220013 | MOD | 2024-08-05 | Z | 2024-08-01 | 280 | 0 | 60 | F | 0 | 620 |  | EF-1 , EF-2 |  | 4
2024-08-02 | 1063 |  | 79854 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 | 3/4" nipple , bird s. | 2024-08-02 | Z | 2024-07-29 | 40 | 0 | 0 |  | 0 | 90 |  | Relief hood |  | 4
[6 empty] | 1603 | [13 empty] | 51840 |  |  |  | 14850 | 28.65%
WEEK OF 8-5-2024
2024-08-08 | 3651 |  | 80082 , 80089 | A | DONE | 14 | S-M |  | 121 E. WILSON 6230024 |  | 2024-08-09 | Z | 2024-07-30 | 130 | 0 | 210 | F | 0 | 340 |  | EF-1,2 , EA-1 |  | 10
2024-08-09 | 3696 |  | 80138 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-08-09 | Z | 2024-08-09 | 20 | 0 | 0 |  | 0 | 20 |  | Stairwell A-EA-2 |  | 0
2024-08-05 | 2432 |  | 78769 | A | DONE | 4 | S |  | ABE LINCOLN 6230029 |  | 2024-08-05 | Z | 2024-07-30 | 90 | 0 | 0 |  | 0 | 150 |  | 1st floor |  | 6
2024-08-05 | 2433 |  | 78770 | A | DONE | 2 | S |  | ABE LINCOLN 6230029 |  | 2024-08-05 | Z | 2024-07-31 | 40 | 0 | 0 |  | 0 | 40 |  | 1st floor |  | 5
2024-08-07 | 1772 |  | 81409 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-08-09 | Z | 2024-07-29 | 50 | 0 | 0 |  | 0 | 70 |  | Flashing |  | 11
2024-08-08 | 1773 |  | 81408 | A | DONE | 6 | S |  | BLACKHAWK BTC 6230025 | paint , 1" liner | 2024-08-09 | Z | 2024-07-29 | 140 | 0 | 0 |  | 120 | 150 |  | RA Plenum |  | 11
2024-08-09 | 999 | bth | L6-B-EALP-013 | A | DONE | 7 | S | neal | CDIS 6220028 | paint | 2024-08-12 | Z | 2024-06-12 | 70 | 20 | 70 | F | 30 | 190 |  |  |  | 61
2024-08-09 | 1000 | bth | L6-B-EALP-014 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-08-12 | Z | 2024-06-12 | 40 | 20 | 0 |  | 0 | 50 |  |  |  | 61
2024-08-09 | 1002 | bth | L6-B-EALP-016 | A | DONE | 4 | S | pt.neal | CDIS 6220028 | paint | 2024-08-12 | Z | 2024-06-12 | 50 | 20 | 30 | F | 20 | 120 |  |  |  | 61
2024-08-08 | 1005 | bth | L6-B-EALP-019 | A | DONE | 7 | S | neal | CDIS 6220028 | paint | 2024-08-12 | Z | 2024-06-12 | 50 | 80 | 30 | F | 20 | 180 |  |  |  | 61
2024-08-09 | 1006 |  | L6-B-RAD-001 | A | DONE | 2 | S | neal | CDIS 6220028 | VD | 2024-08-12 | Z | 2024-06-12 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 61
2024-08-09 | 1007 | bth | L6-B-SALP-015 | A | DONE | 4 | S | pt.neal | CDIS 6220028 |  | 2024-08-12 | Z | 2024-06-12 | 80 | 20 | 0 |  | 30 | 100 |  |  |  | 61
2024-08-09 | 1008 | bth | L6-B-SALP-016 | A | DONE | 5 | S |  | CDIS 6220028 | paint , VD , 1" liner | 2024-08-12 | Z | 2024-06-12 | 70 | 20 | 30 | F | 20 | 130 |  |  |  | 61
2024-08-09 | 1012 | bth | L6-B-SALP-020 | A | DONE | 7 | S | neal | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 70 | 60 | 30 | F | 20 | 180 |  |  |  | 61
2024-08-09 | 1014 | bth | L6-B-SALP-022 | A | DONE | 7 | S |  | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 80 | 20 | 60 | F | 20 | 180 |  |  |  | 61
2024-08-09 | 1015 |  | L6-B-SALP-023 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 100 | 0 | 20 | F | 40 | 140 |  |  |  | 61
2024-08-09 | 1017 | bth | L6-B-SALP-025 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 70 | 20 | 20 | F | 20 | 120 |  |  |  | 61
2024-08-09 | 1019 |  | L6-B-SALP-027 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 60 | 90 | 0 |  | 20 | 150 |  |  |  | 61
2024-08-08 | 3400 |  | EA(-10wg)PH-08 | A | DONE | 69 | VL |  | CDIS 6220028 |  | 2024-08-09 | Z | 2024-07-23 | 1720 | 0 | 0 |  | 0 | 8320 |  |  |  | 17
2024-08-08 | 3401 |  | L2-A-RAD-002 | A | DONE | 2 | S | neal | CDIS 6220028 | VD | 2024-08-12 | Z | 2024-07-23 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 20
2024-08-05 | 3406 |  | 69927 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-08-06 | Z | 2024-07-24 | 20 | 20 | 0 |  | 0 | 40 |  | L5-SAMP-004 |  | 13
2024-08-05 | 3435 |  | 69660 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-08-06 | Z | 2024-08-02 | 40 | 0 | 0 |  | 0 | 90 |  | EC |  | 4
2024-08-09 | 3437 |  | 69813 | A | DONE | 16 | S |  | CDIS 6220028 |  | 2024-08-13 | Z | 2024-08-06 | 380 | 0 | 0 |  | 0 | 550 |  | Temp EC |  | 7
2024-08-08 | 3439 |  | 69661 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-08-09 | Z | 2024-08-07 | 30 | 0 | 0 |  | 0 | 40 |  | 6th floor taps |  | 2
2024-08-07 | 3440 |  | 70539 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-08-07 | Z | 2024-08-07 | 30 | 0 | 0 |  | 0 | 50 |  | SC-SAMP-003 |  | 0
2024-08-08 | 218 |  | 79783 - 79784 | A | DONE | 10 | S-M |  | COMPASS HP 4230088 | oval | 2024-08-09 | Z | 2024-07-16 | 90 | 150 | 0 |  | 0 | 230 |  | VAV's |  | 24
2024-08-08 | 219 | sp | 79785 - 79786 | A | DONE | 6 | S-M |  | COMPASS HP 4230088 |  | 2024-08-09 | Z | 2024-07-16 | 40 | 110 | 0 |  | 0 | 160 |  | VAV-16 |  | 24
2024-08-08 | 220 | bth | 79787 - 79789 | A | DONE | 18 | M |  | COMPASS HP 4230088 | oval | 2024-08-09 | Z | 2024-07-16 | 140 | 310 | 0 |  | 0 | 470 |  | VAV's |  | 24
2024-08-08 | 221 | bth | 79790 - 79792 | A | DONE | 18 | M |  | COMPASS HP 4230088 | oval | 2024-08-09 | Z | 2024-07-16 | 180 | 210 | 50 | F | 0 | 430 |  | VAV's |  | 24
2024-08-06 | 800 | w | 70538 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2024-08-07 | Z | 2024-08-05 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeves |  | 2
2024-08-05 | 236 |  | 79422 | A | DONE | 4 | S |  | EDGERTON HS 4240020 |  | 2024-08-05 | Z | 2024-07-31 | 80 | 0 | 0 |  | 0 | 240 |  | Curb cap |  | 5
2024-08-07 | 1283 | sp | 79649 | A | DONE | 3 | S |  | EGENESIS 6230026 |  | 2024-08-09 | Z | 2024-08-05 | 20 | 40 | 0 |  | 0 | 60 |  | DOAS-1 SA |  | 4
2024-08-08 | 241 |  | 70540 | A | DONE | 2 | S |  | HERITAGE 4240041 |  | 2024-08-08 | Z | 2024-08-08 | 30 | 0 | 0 |  | 0 | 30 |  | Angle |  | 0
2024-08-05 | 3191 |  | 78677 | A | DONE | 9 | S-M | alum | JANESVILLE ESSR 6230011 |  | 2024-08-05 | Z | 2024-08-01 | 210 | 0 | 0 |  | 0 | 130 |  | Pool |  | 4
2024-08-05 | 3192 | sp | 78679 | A | DONE | 8 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-08-05 | Z | 2024-08-01 | 40 | 150 | 0 |  | 0 | 170 |  | V-64 |  | 4
2024-08-05 | 3193 |  | 80278 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-05 | Z | 2024-08-02 | 30 | 0 | 0 |  | 0 | 50 |  | Misc |  | 3
2024-08-05 | 3194 |  | 78681 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-05 | Z | 2024-08-02 | 40 | 0 | 0 |  | 0 | 70 |  | Wood shop |  | 3
2024-08-05 | 3195 | sp | 78682 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-05 | Z | 2024-08-02 | 20 | 20 | 0 |  | 0 | 40 |  | Wood shop |  | 3
2024-08-06 | 3197 |  | 70862 | A | DONE | 4 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-06 | Z | 2024-08-05 | 40 | 0 | 60 | F | 20 | 110 |  | AHU-4 OA |  | 1
2024-08-05 | 3198 |  | 78685 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-06 | Z | 2024-08-05 | 20 | 0 | 0 |  | 0 | 20 |  | Choir office |  | 1
2024-08-06 | 3199 | w | 78686 - 78687 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | 2" DB | 2024-08-06 | Z | 2024-08-05 | 50 | 0 | 0 |  | 20 | 110 |  | Caps |  | 1
2024-08-06 | 3350 |  | 78688 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-06 | Z | 2024-08-05 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd EA |  | 1
2024-08-05 | 3351 |  | 78684 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | bird s. | 2024-08-06 | Z | 2024-08-05 | 20 | 0 | 0 |  | 0 | 20 |  | LMC |  | 1
2024-08-06 | 3352 |  | 80279 | A | DONE | 3 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-06 | Z | 2024-08-05 | 60 | 0 | 0 |  | 0 | 60 |  | AHU-8 RA |  | 1
2024-08-06 | 3353 |  | 78689 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | paint | 2024-08-06 | Z | 2024-08-05 | 30 | 0 | 0 |  | 0 | 80 |  | Kitchen RA grilles |  | 1
2024-08-06 | 3354 |  | 70863 | A | DONE | 5 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-06 | Z | 2024-08-05 | 110 | 0 | 0 |  | 0 | 340 |  | OA #4 |  | 1
2024-08-07 | 3355 |  | 70864 - 70865 | A | DONE | 13 | S-M | neal | JANESVILLE ESSR 6230011 |  | 2024-08-08 | Z | 2024-08-06 | 310 | 0 | 0 |  | 0 | 520 |  | Pipe Covers / bathroom |  | 2
2024-08-07 | 3356 |  | 70867 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-08 | Z | 2024-08-06 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 2
2024-08-07 | 3357 | bth | 78690 - 78691 | A | DONE | 3 | S-M |  | JANESVILLE ESSR 6230011 |  | 2024-08-08 | Z | 2024-08-06 | 30 | 20 | 0 |  | 0 | 60 |  | Pool FCU |  | 2
2024-08-08 | 3358 |  | 54523 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-08 | Z | 2024-08-08 | 30 | 0 | 0 |  | 0 | 30 |  | AHU-6,7 |  | 0
2024-08-08 | 3359 |  | 54524 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-08 | Z | 2024-08-08 | 30 | 0 | 0 |  | 0 | 70 |  | RAHU-1 |  | 0
2024-08-08 | 3360 |  | 78692 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-08 | Z | 2024-08-08 | 40 | 0 | 0 |  | 0 | 50 |  | UV-38 OA |  | 0
2024-08-06 | 1901 |  | 62393 - 62394 | A | DONE | 38 | S-M |  | JPC OFFICE 6240002 |  | 2024-08-08 | Z | 2024-07-25 | 80 | 0 | 850 | F | 0 | 870 |  | VAV mains |  | 14
2024-08-09 | 1903 |  | 70541 | A | DONE | 2 | S |  | JPC OFFICE 6240002 | 1" DB | 2024-08-12 | Z | 2024-08-08 | 40 | 0 | 0 |  | 30 | 80 |  | Curb cap |  | 4
2024-08-06 | 2334 |  | 67725 | A | DONE | 2 | S | alum | KOHL CENTER 6210034 |  | 2024-08-08 | Z | 2024-07-30 | 40 | 0 | 0 |  | 0 | 30 |  | Shower finishes |  | 9
2024-08-06 | 2335 |  | 67726 | A | DONE | 2 | S |  | KOHL CENTER 6210034 | paint | 2024-08-08 | Z | 2024-07-30 | 30 | 0 | 0 |  | 0 | 40 |  | B-Ceiling |  | 9
2024-08-07 | 2336 |  | 67727 | A | DONE | 3 | S |  | KOHL CENTER 6210034 | paint | 2024-08-09 | Z | 2024-07-31 | 70 | 0 | 0 |  | 0 | 100 |  | A-Finishes |  | 9
2024-08-09 | 1122 | sp | 55329 - 55330 | A | DONE | 7 | S-M |  | LABCORP BIO 6240011 |  | 2024-08-12 | Z | 2024-07-30 | 20 | 150 | 0 |  | 0 | 200 |  | 1st floor Bio A |  | 13
2024-08-08 | 4551 |  | 64248 | A | DONE | 2 | S | BI | LEVY HALL 6230028 |  | 2024-08-09 | Z | 2024-08-06 | 20 | 0 | 0 |  | 0 | 70 |  | Caps |  | 3
2024-08-09 | 3458 |  | 68632 | A | DONE | 4 | S |  | MEMORIAL HS 6210024 |  | 2024-08-13 | Z | 2024-08-01 | 80 | 0 | 0 |  | 0 | 110 |  | EA |  | 12
2024-08-09 | 3459 | w | 68113 | A | DONE | 3 | S-M |  | MEMORIAL HS 6210024 | 1" DB | 2024-08-13 | Z | 2024-08-01 | 70 | 0 | 0 |  | 40 | 160 |  | Caps |  | 12
2024-08-09 | 2361 |  | 80305 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | 1" liner | 2024-08-12 | Z | 2024-08-08 | 20 | 0 | 0 |  | 20 | 20 |  | TA |  | 4
2024-08-07 | 1845 | sp | L0-SALP-05 | A | DONE | 9 | S |  | PROMEGA BTC 6230022 |  | 2024-08-08 | Z | 2024-07-22 | 70 | 150 | 0 |  | 0 | 260 |  |  |  | 17
2024-08-07 | 1846 | sp | L0-SALP-06 | A | DONE | 11 | S-M |  | PROMEGA BTC 6230022 |  | 2024-08-08 | Z | 2024-07-22 | 80 | 180 | 0 |  | 0 | 300 |  |  |  | 17
2024-08-08 | 1847 | sp | L0-SAMP-09 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-08-08 | Z | 2024-07-22 | 30 | 10 | 0 |  | 0 | 40 |  |  |  | 17
2024-08-07 | 1849 | w | 56300 | A | DONE | 2 | S | ss | PROMEGA BTC 6230022 |  | 2024-08-14 | Z | 2024-08-01 | 70 | 0 | 0 |  | 0 | 160 |  | Plenum box |  | 13
2024-08-07 | 1990 |  | L2-EA(-4wg)-08 | A | DONE | 28 | S-M |  | PROMEGA MCBR 2240039 |  | 2024-08-08 | Z | 2024-07-25 | 350 | 0 | 350 | F | 0 | 1140 |  |  |  | 14
2024-08-07 | 1991 |  | L2-EA(-4wg)-07 | A | DONE | 26 | S-M |  | PROMEGA MCBR 2240039 |  | 2024-08-08 | Z | 2024-07-25 | 340 | 0 | 310 | F | 0 | 1040 |  |  |  | 14
2024-08-07 | 1992 |  | L2-EA(-4wg)-06 | A | DONE | 10 | S-M |  | PROMEGA MCBR 2240039 |  | 2024-08-08 | Z | 2024-07-25 | 230 | 0 | 0 |  | 0 | 500 |  |  |  | 14
2024-08-05 | 3007 |  | 41345 | A | DONE | 2 | S |  | RETRO CX 6240004 |  | 2024-08-07 | Z | 2024-07-25 | 20 | 0 | 0 |  | 0 | 20 |  | AFMS patches |  | 13
2024-08-06 | 238 |  | 79794 | A | DONE | 2 | S |  | SIERRA SPACE 10057185 | bird s. | 2024-08-06 | Z | 2024-08-05 | 30 | 0 | 0 |  | 0 | 40 |  | Furnace |  | 1
2024-08-06 | 4266 | bth | 79915 | A | DONE | 4 | S |  | ST.BERNARD 6230023 | 1" liner | 2024-08-08 | Z | 2024-07-29 | 40 | 50 | 0 |  | 20 | 80 |  | Misc |  | 10
2024-08-07 | 4267 |  | 79916 | A | DONE | 2 | S |  | ST.BERNARD 6230023 |  | 2024-08-09 | Z | 2024-08-01 | 20 | 0 | 0 |  | 0 | 30 |  | SA |  | 8
2024-08-08 | 213 |  | 78733 | A | DONE | 13 | M |  | SUNSET RIDGE 4240013 |  | 2024-08-09 | Z | 2024-07-15 | 310 | 0 | 0 |  | 0 | 840 |  | Cooling tower |  | 25
2024-08-08 | 240 |  | 78738 | A | DONE | 4 | S |  | SUNSET RIDGE 4240013 | flex | 2024-08-09 | Z | 2024-08-07 | 100 | 0 | 0 |  | 0 | 210 |  | Cooling tower |  | 2
2024-08-09 | 227 |  | 79643 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 | paint | 2024-08-12 | Z | 2024-07-24 | 20 | 0 | 0 |  | 20 | 30 |  | Storage 1336 reg. boxes |  | 19
2024-08-09 | 228 | w | 79644 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 | 2" DB | 2024-08-12 | Z | 2024-07-24 | 30 | 0 | 0 |  | 20 | 70 |  | OR AHU curb adapt. |  | 19
2024-08-06 | 234 | sp | 79647 | A | DONE | 14 | S-M |  | UPLAND HILLS 2240008 |  | 2024-08-12 | Z | 2024-08-01 | 160 | 180 | 0 |  | 0 | 380 |  | PR 4 |  | 11
2024-08-05 | 2451 | w | 58807 | A | DONE | 4 | S-M |  | UW-CHAMPIONS HALL 6240008 | paint | 2024-08-05 | Z | 2024-07-23 | 100 | 0 | 0 |  | 50 | 300 |  | Floor sleeves |  | 13
2024-08-07 | 525 |  | 66929 | A | DONE | 6 | S | pt.pcd | UWRF 6230010 |  | 2024-08-08 | Z | 2024-07-30 | 60 | 70 | 0 |  | 0 | 150 |  | Misc |  | 9
2024-08-06 | 526 |  | 66930 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-07 | Z | 2024-08-01 | 20 | 0 | 0 |  | 20 | 30 |  | L2-SAT-1-2-36 |  | 6
2024-08-09 | 527 |  | 70154 | A | DONE | 3 | S-M | pt.pcd | UWRF 6230010 | 1" liner | 2024-08-12 | Z | 2024-08-01 | 90 | 0 | 0 |  | 20 | 170 |  | SAT-1-3-47 |  | 11
2024-08-06 | 4003 | bth | L3Z1-SAT-1-3-1 | A | DONE | 14 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 160 | 70 | 100 | F | 30 | 370 |  |  | Trailer #4 | 90
2024-08-06 | 4004 | bth | L3Z1-SAT-1-3-2 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 30 | 20 | 30 | F | 30 | 80 |  |  | Trailer #4 | 90
2024-08-06 | 4005 | bth | L3Z1-SAT-1-3-5 | A | DONE | 13 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 130 | 60 | 130 | F | 70 | 350 |  |  | Trailer #4 | 90
2024-08-06 | 4006 |  | L3Z1-SAT-1-3-6 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 50 | 0 | 0 |  | 20 | 70 |  |  | Trailer #4 | 90
2024-08-06 | 4007 | bth | L3Z1-SAT-1-3-9 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 40 | 20 | 0 |  | 20 | 70 |  |  | Trailer #4 | 90
2024-08-06 | 4008 |  | L3Z1-SAT-1-3-48 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 30 | 0 | 0 |  | 20 | 40 |  |  | Trailer #4 | 90
2024-08-06 | 4009 | bth | L3Z1-SAT-1-3-49 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 40 | 30 | 0 |  | 20 | 70 |  |  | Trailer #4 | 90
2024-08-06 | 4010 | bth | L3Z1-SAT-1-3-50 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 40 | 40 | 0 |  | 20 | 80 |  |  | Trailer #4 | 90
2024-08-06 | 4011 | bth | L3Z1-SAT-1-3-51 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 40 | 20 | 0 |  | 30 | 70 |  |  | Trailer #4 | 90
2024-08-06 | 4012 |  | L3Z1-SAT-1-3-52 | A | DONE | 6 | S | neal | UWRF 6230010 | VD,s , 1" liner | 2024-08-05 | Z | 2024-05-07 | 70 | 0 | 80 | F | 40 | 180 |  |  | Trailer #4 | 90
2024-08-06 | 4013 | bth | L3Z1-SAT-1-3-53 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 40 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 90
2024-08-06 | 4014 | bth | L3Z1-SAT-1-3-54 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 40 | 40 | 0 |  | 20 | 80 |  |  | Trailer #4 | 90
2024-08-06 | 4015 |  | L3Z1-SAT-1-3-55 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 20 | 0 | 0 |  | 20 | 20 |  |  | Trailer #4 | 90
2024-08-06 | 4016 | bth | L3Z1-SAT-1-3-56 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 30 | 20 | 0 |  | 0 | 40 |  |  | Trailer #4 | 90
2024-08-06 | 4017 |  | L3Z1-SAT-1-3-57 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 20 | 0 | 0 |  | 20 | 20 |  |  | Trailer #4 | 90
2024-08-06 | 4018 | bth | L3Z1-SAT-1-3-58 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 30 | 20 | 30 | F | 30 | 80 |  |  | Trailer #4 | 90
2024-08-06 | 4019 | bth | L3Z1-SAT-1-3-59 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 50 | 20 | 0 |  | 30 | 70 |  |  | Trailer #4 | 90
2024-08-06 | 4020 |  | L3Z1-SAT-1-3-63 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 30 | 0 | 0 |  | 20 | 40 |  |  | Trailer #4 | 90
2024-08-06 | 4021 |  | L3Z1-SAT-1-3-64 | A | DONE | 2 | S | neal | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 40 | 0 | 0 |  | 20 | 60 |  |  | Trailer #4 | 90
2024-08-06 | 4022 | bth | L3Z1-SAT-1-3-65 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 30 | 20 | 30 | F | 40 | 80 |  |  | Trailer #4 | 90
2024-08-06 | 4023 | bth | L3Z1-SAT-1-3-66 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 50 | 20 | 0 |  | 20 | 70 |  |  | Trailer #4 | 90
2024-08-06 | 4024 | bth | L3Z1-SAT-1-3-67 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 40 | 20 | 0 |  | 20 | 70 |  |  | Trailer #4 | 90
2024-08-06 | 4025 |  | L3Z1-SAT-1-3-76 | A | DONE | 3 | S | neal | UWRF 6230010 | VD,s , 1" liner | 2024-08-05 | Z | 2024-05-07 | 60 | 0 | 0 |  | 20 | 90 |  |  | Trailer #4 | 90
2024-08-06 | 4026 | bth | L3Z1-SAT-1-3-79 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 30 | 20 | 0 |  | 20 | 60 |  |  | Trailer #4 | 90
2024-08-06 | 4027 | bth | L3Z1-SAT-1-3-3 | A | DONE | 10 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 160 | 70 | 0 |  | 80 | 300 |  |  | Trailer #4 | 90
2024-08-06 | 4028 | bth | L3Z1-SAT-1-3-4 | A | DONE | 13 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-07 | 170 | 40 | 110 | F | 80 | 400 |  |  | Trailer #4 | 90
2024-08-06 | 4029 |  | L3Z1-SAT-1-3-7 | A | DONE | 8 | S | neal | UWRF 6230010 | perf , 1" liner | 2024-08-05 | Z | 2024-05-07 | 200 | 0 | 0 |  | 40 | 290 |  |  | Trailer #4 | 90
2024-08-06 | 4030 |  | L3Z1-SAT-1-3-8 | A | DONE | 8 | S | neal | UWRF 6230010 | perf , 1" liner | 2024-08-05 | Z | 2024-05-07 | 190 | 0 | 0 |  | 40 | 270 |  |  | Trailer #4 | 90
2024-08-06 | 4031 | bth | L3Z2-SAT-1-3-10 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 20 | 0 |  | 20 | 60 |  |  | Trailer #4 | 88
2024-08-06 | 4032 | bth | L3Z2-SAT-1-3-11 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 20 | 0 |  | 30 | 70 |  |  | Trailer #4 | 88
2024-08-06 | 4033 | bth | L3Z2-SAT-1-3-12 | A | DONE | 15 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 160 | 40 | 170 | F | 50 | 430 |  |  | Trailer #4 | 88
2024-08-06 | 4034 | bth | L3Z2-SAT-1-3-13 | A | DONE | 10 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 140 | 100 | 0 |  | 40 | 260 |  |  | Trailer #4 | 88
2024-08-06 | 4035 | bth | L3Z2-SAT-1-3-14 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4036 | bth | L3Z2-SAT-1-3-15 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 20 | 0 |  | 20 | 50 |  |  | Trailer #4 | 88
2024-08-06 | 4037 | bth | L3Z2-SAT-1-3-16 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 20 | 0 |  | 20 | 60 |  |  | Trailer #4 | 88
2024-08-06 | 4038 | bth | L3Z2-SAT-1-3-17 | A | DONE | 7 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 140 | 30 | 0 |  | 30 | 200 |  |  | Trailer #4 | 88
2024-08-06 | 4039 | bth | L3Z2-SAT-1-3-18 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 20 | 0 |  | 20 | 50 |  |  | Trailer #4 | 88
2024-08-06 | 4040 | bth | L3Z2-SAT-1-3-19 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4041 | bth | L3Z2-SAT-1-3-20 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 60 | 20 | 0 |  | 30 | 80 |  |  | Trailer #4 | 88
2024-08-06 | 4042 | bth | L3Z2-SAT-1-3-21 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 20 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4043 | bth | L3Z2-SAT-1-3-22 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 20 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4044 | bth | L3Z2-SAT-1-3-23 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 20 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4045 | bth | L3Z2-SAT-1-3-24 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 20 | 0 |  | 20 | 60 |  |  | Trailer #4 | 88
2024-08-06 | 4046 |  | L3Z2-SAT-1-3-25 | A | DONE | 10 | S-M |  | UWRF 6230010 | VD's ,1" liner | 2024-08-05 | Z | 2024-05-09 | 230 | 0 | 0 |  | 40 | 310 |  |  | Trailer #4 | 88
2024-08-06 | 4047 | bth | L3Z2-SAT-1-3-26 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 20 | 30 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4048 | bth | L3Z2-SAT-1-3-27 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 40 | 0 |  | 20 | 80 |  |  | Trailer #4 | 88
2024-08-06 | 4049 |  | L3Z2-SAT-1-3-28 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 0 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4050 | bth | L3Z2-SAT-1-3-29 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 30 | 0 |  | 20 | 60 |  |  | Trailer #4 | 88
2024-08-06 | 4051 |  | L3Z2-SAT-1-3-30 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 0 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4052 | bth | L3Z2-SAT-1-3-31 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 20 | 0 |  | 20 | 50 |  |  | Trailer #4 | 88
2024-08-06 | 4053 | bth | L3Z2-SAT-1-3-32 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 20 | 0 |  | 20 | 50 |  |  | Trailer #4 | 88
2024-08-05 | 4054 |  | L3Z2-SAT-1-3-33 | A | DONE | 6 | S | neal | UWRF 6230010 | VD's ,1" liner | 2024-08-05 | Z | 2024-05-09 | 110 | 0 | 20 | F | 30 | 150 |  |  | Trailer #4 | 88
2024-08-06 | 4055 | bth | L3Z2-SAT-1-3-34 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 30 | 0 |  | 20 | 70 |  |  | Trailer #4 | 88
2024-08-06 | 4056 | bth | L3Z2-SAT-1-3-35 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-06 | 4057 | bth | L3Z2-SAT-1-3-36 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 50 | 30 | 0 |  | 20 | 80 |  |  | Trailer #4 | 88
2024-08-05 | 4059 |  | L3Z2-SAT-1-3-39 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 50 | 0 | 0 |  | 20 | 70 |  |  | Trailer #4 | 88
2024-08-06 | 4060 | bth | L3Z2-SAT-1-3-40 | A | DONE | 12 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 150 | 90 | 40 | F | 40 | 300 |  |  |  | 88
2024-08-06 | 4063 | bth | L3Z2-SAT-1-3-43 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 50 | 20 | 30 | F | 50 | 140 |  |  |  | 88
2024-08-06 | 4068 | bth | L3Z2-SAT-1-3-60 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 20 | 20 | 0 |  | 20 | 50 |  |  | Trailer #4 | 88
2024-08-06 | 4069 | bth | L3Z2-SAT-1-3-61 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 20 | 0 |  | 20 | 60 |  |  | Trailer #4 | 88
2024-08-06 | 4070 | bth | L3Z2-SAT-1-3-62 | A | DONE | 7 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 50 | 60 | 60 | F | 30 | 180 |  |  | Trailer #4 | 88
2024-08-05 | 4071 |  | L3Z2-SAT-1-3-68 | A | DONE | 5 | S | neal | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 50 | 0 | 60 | F | 40 | 130 |  |  | Trailer #4 | 88
2024-08-06 | 4073 | bth | L3Z2-SAT-1-3-70 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 20 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-05 | 4074 |  | L3Z2-SAT-1-3-71 | A | DONE | 2 | S | neal | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 0 | 0 |  | 20 | 60 |  |  | Trailer #4 | 88
2024-08-05 | 4076 |  | L3Z2-SAT-1-3-73 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 0 | 0 |  | 30 | 50 |  |  | Trailer #4 | 88
2024-08-06 | 4077 | bth | L3Z2-SAT-1-3-74 | A | DONE | 13 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 210 | 40 | 70 | F | 40 | 390 |  |  | Trailer #4 | 88
2024-08-05 | 4078 | bth | L3Z2-SAT-1-3-75 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 0 | 0 |  | 30 | 50 |  |  | Trailer #4 | 88
2024-08-06 | 4080 | bth | L3Z2-SAT-1-3-78 | A | DONE | 3 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 20 | 0 |  | 20 | 70 |  |  | Trailer #4 | 88
2024-08-05 | 4081 | bth | L3Z2-SAT-1-3-80 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 30 | 0 |  | 30 | 80 |  |  | Trailer #4 | 88
2024-08-05 | 4082 | bth | L3Z2-SAT-1-3-81 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 30 | 0 |  | 20 | 50 |  |  | Trailer #4 | 88
2024-08-05 | 4083 | bth | L3Z2-SAT-1-3-82 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 30 | 20 | 0 |  | 20 | 60 |  |  | Trailer #4 | 88
2024-08-06 | 4084 | bth | L3Z2-SAT-1-3-83 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-05 | Z | 2024-05-09 | 40 | 20 | 0 |  | 20 | 40 |  |  | Trailer #4 | 88
2024-08-05 | r3932 | bth | L2Z1-FEV-3-2-4 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-05 | Z | 2024-07-30 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 6
2024-08-07 | 5036 | bth | RA-03-04 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 170 | 40 | 90 | F | 0 | 340 |  |  |  | 37
2024-08-07 | 5037 | bth | RA-03-05 | A | DONE | 11 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 140 | 20 | 100 | F | 0 | 310 |  |  |  | 37
2024-08-07 | 5038 | bth | RA-03-06 | A | DONE | 22 | M |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 430 | 20 | 100 | F | 0 | 880 |  |  |  | 37
2024-08-07 | 5039 |  | RA-03-07 | A | DONE | 30 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 210 | 0 | 530 | F | 0 | 1180 |  |  |  | 37
2024-08-07 | 5040 |  | RA-03-08 | A | DONE | 24 | M |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 270 | 0 | 330 | F | 0 | 730 |  |  |  | 37
2024-08-07 | 5041 | bth | RA-03-10 | A | DONE | 15 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 170 | 20 | 180 | F | 0 | 440 |  |  |  | 37
2024-08-07 | 5042 |  | RA-03-11 | A | DONE | 13 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 130 | 0 | 180 | F | 0 | 380 |  |  |  | 37
2024-08-07 | 5043 |  | RA-03-12 | A | DONE | 6 | S |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 150 | 0 | 0 |  | 0 | 230 |  |  |  | 37
2024-08-07 | 5044 | bth | RA-03-13 | A | DONE | 7 | S |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 90 | 20 | 50 | F | 0 | 180 |  |  |  | 37
2024-08-07 | 5045 |  | RA-03-03 | A | DONE | 44 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-08-08 | Z | 2024-07-02 | 820 | 0 | 270 | F | 0 | 2150 |  |  |  | 37
2024-08-09 | 1465 |  | 73054 - 73055 | A | DONE | 14 | S-M |  | UW-VET MED 6210014 |  | 2024-08-12 | Z | 2024-07-30 | 170 | 0 | 170 | L | 0 | 490 |  | EA-Area 9 |  | 13
2024-08-05 | 1066 | b/w | 67579 - 67580 | A | DONE | 8 | S-M |  | WAUNAKEE HS 6220013 | flex | 2024-08-05 | Z | 2024-08-01 | 200 | 0 | 0 |  | 20 | 570 |  | EF-1 , EF-2 |  | 4
2024-08-07 | 1067 |  | 67585 - 67586 | A | DONE | 2 | S-M | neal | WAUNAKEE HS 6240013 |  | 2024-08-08 | Z | 2024-08-06 | 30 | 0 | 0 |  | 0 | 50 |  | Welding EA |  | 2
2024-08-07 | 1068 |  | 67587 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 |  | 2024-08-08 | Z | 2024-08-06 | 30 | 0 | 0 |  | 0 | 40 |  | Tech ED |  | 2
2024-08-07 | 1069 |  | 79856 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 |  | 2024-08-09 | Z | 2024-08-07 | 40 | 0 | 0 |  | 0 | 50 |  | Flashing |  | 2
[6 empty] | 1056 | [13 empty] | 38410 |  |  |  | 7470 | 19.45%
WEEK OF 8-12-2024
2024-08-14 | 3670 |  | 80113 - 80114 | A | DONE | 33 | M |  | 121 E. WILSON 6230024 |  | 2024-08-13 | Z | 2024-07-31 | 110 | 0 | 710 | F | 0 | 980 |  | 2nd floor west EA |  | 13
2024-08-15 | 3675 |  | 80119 - 80120 | A | DONE | 27 | S-M |  | 121 E. WILSON 6230024 |  | 2024-08-15 | Z | 2024-07-31 | 90 | 0 | 570 | F | 0 | 790 |  | 2nd floor east EA |  | 15
2024-08-12 | 3676 |  | 80121 | A | DONE | 21 | S-M |  | 121 E. WILSON 6230024 |  | 2024-08-13 | Z | 2024-08-02 | 0 | 0 | 520 | F | 0 | 630 |  | ERV-1 |  | 11
2024-08-12 | 1001 | bth | L6-B-EALP-015 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 40 | 30 | 50 | F | 20 | 160 |  |  |  | 61
2024-08-12 | 1003 | sp | L6-B-EALP-017 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-08-12 | Z | 2024-06-12 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 61
2024-08-12 | 1004 | sp | L6-B-EALP-018 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-08-12 | Z | 2024-06-12 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 61
2024-08-12 | 1009 | bth | L6-B-SALP-017 | A | DONE | 6 | S | neal | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 130 | 20 | 0 |  | 30 | 210 |  |  |  | 61
2024-08-12 | 1010 | bth | L6-B-SALP-018 | A | DONE | 4 | S | neal | CDIS 6220028 |  | 2024-08-12 | Z | 2024-06-12 | 70 | 30 | 0 |  | 0 | 90 |  |  |  | 61
2024-08-12 | 1011 | bth | L6-B-SALP-019 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-08-12 | Z | 2024-06-12 | 60 | 30 | 30 | F | 0 | 120 |  |  |  | 61
2024-08-12 | 1013 | bth | L6-B-SALP-021 | A | DONE | 5 | S | neal | CDIS 6220028 |  | 2024-08-12 | Z | 2024-06-12 | 50 | 60 | 0 |  | 0 | 60 |  |  |  | 61
2024-08-12 | 1016 | bth | L6-B-SALP-024 | A | DONE | 7 | S-M | neal | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 120 | 40 | 0 |  | 30 | 200 |  |  |  | 61
2024-08-12 | 1018 | bth | L6-B-SALP-026 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 40 | 60 | 0 |  | 20 | 120 |  |  |  | 61
2024-08-12 | 1020 |  | L6-B-SALP-028 | A | DONE | 5 | S-M | neal | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 90 | 0 | 20 | F | 40 | 130 |  |  |  | 61
2024-08-12 | 1021 | bth | L6-B-SALP-029 | A | DONE | 10 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 130 | 20 | 100 | F | 30 | 280 |  |  |  | 61
2024-08-12 | 1022 | bth | L6-B-SALP-030 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 70 | 130 | 0 |  | 20 | 200 |  |  |  | 61
2024-08-12 | 1023 | bth | L6-B-SALP-031 | A | DONE | 10 | S-M | neal | CDIS 6220028 | 1" liner | 2024-08-12 | Z | 2024-06-12 | 90 | 100 | 40 | F | 20 | 270 |  |  |  | 61
2024-08-17 | 1046 |  | L6-A-EAMP-028 | A | DONE | 9 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 130 | 0 | 80 | F | 0 | 250 |  |  |  | 56
2024-08-17 | 1047 | bth | L6-A-EAMP-029 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 70 | 40 | 90 | F | 0 | 250 |  |  |  | 56
2024-08-14 | 1098 |  | Pre-Fab Hangers | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-07-02 | 20 | 0 | 0 |  | 0 | 30 |  | 7th B-Section |  | 44
2024-08-12 | 3409 |  | 69931 - 69932 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-13 | Z | 2024-07-29 | 30 | 0 | 0 |  | 0 | 30 |  | A-SALP-005 |  | 15
2024-08-13 | 3410 |  | 69933 | A | DONE | 2 | S | neal | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-07-29 | 50 | 0 | 0 |  | 20 | 50 |  | L5-A-SALP-002 |  | 17
2024-08-12 | 3411 |  | 69934 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-07-29 | 80 | 0 | 0 |  | 0 | 90 |  | Flashing |  | 17
2024-08-13 | 3414 |  | 69935 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-07-30 | 370 | 0 | 0 |  | 0 | 690 |  | 5th floor |  | 16
2024-08-17 | 3415 |  | 69658 | A | DONE | 26 | M | pt.neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-30 | 650 | 0 | 0 |  | 0 | 1060 |  | Flashing 6th floor |  | 21
2024-08-14 | 3428 |  | EA-(-10wg)-PH-05 | A | DONE | 26 | L |  | CDIS 6220028 | partial | 2024-08-15 | Z | 2024-08-01 | 630 | 0 | 0 |  | 0 | 2500 |  |  |  | 14
2024-08-14 | 3429 |  | EA-(-10wg)-PH-06 | A | DONE | 45 | L |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-08-01 | 1120 | 0 | 0 |  | 0 | 3040 |  |  |  | 14
2024-08-12 | 3438 |  | 69814 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-08-06 | 20 | 0 | 0 |  | 0 | 20 |  | PH FCU-1 |  | 9
2024-08-12 | 3441 |  | 61364 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-13 | Z | 2024-08-07 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor GEH-2-24 |  | 6
2024-08-15 | 4310 |  | 57946 - 57947 | A | DONE | 26 | M-L |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-08-12 | 510 | 0 | 120 | F | 0 | 1350 |  | SC Chase |  | 3
2024-08-15 | 4314 |  | 57949 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 7th floor shaft |  | 3
2024-08-13 | 231 | bth | 78734 | A | DONE | 4 | S |  | CESA 5 4240015 |  | 2024-08-14 | Z | 2024-07-26 | 80 | 0 | 0 |  | 0 | 100 |  | Misc |  | 19
2024-08-15 | r800 | w | 70538 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2024-08-15 | Z | 2024-08-15 | 40 | 0 | 0 |  | 0 | 80 |  | Sleeves |  | 0
2024-08-13 | 246 |  | 32499 | A | DONE | 2 | S |  | EXACT TL-5 8240012 |  | 2024-08-16 | Z | 2024-08-12 | 30 | 0 | 0 |  | 0 | 30 |  | Plate |  | 4
2024-08-13 | 244 |  | 55120 | A | DONE | 2 | S | ss | GTCH 8220002 |  | 2024-08-15 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 3
2024-08-13 | 239 | bth | 64972 - 64974 | A | DONE | 4 | S-M |  | HOLY WISDOM 6220019 | paint | 2024-08-14 | Z | 2024-08-05 | 140 | 50 | 0 |  | 20 | 210 |  | Misc |  | 9
2024-08-12 | 3361 |  | 78694 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | paint | 2024-08-14 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | Lvl 2 Storage Rm |  | 2
2024-08-14 | 3362 |  | 70868 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-08-15 | Z | 2024-08-14 | 20 | 0 | 0 |  | 0 | 20 |  | AHU-3 |  | 1
2024-08-14 | 1125 |  | 69576 | A | DONE | 2 | S |  | LABCORP 6240011 |  | 2024-08-16 | Z | 2024-08-13 | 20 | 0 | 0 |  | 0 | 30 |  | HP Tie-in |  | 3
2024-08-12 | 1121 |  | 55328 | A | DONE | 8 | S |  | LABCORP BIO 6240011 | flex | 2024-08-12 | Z | 2024-07-30 | 140 | 0 | 40 | F | 0 | 200 |  | 1st floor Bio A |  | 13
2024-08-12 | 1123 |  | 55331 | A | DONE | 10 | S |  | LABCORP BIO 6240011 | 1" liner | 2024-08-12 | Z | 2024-07-30 | 210 | 0 | 30 | F | 140 | 330 |  | 1st floor Bio A |  | 13
2024-08-15 | 1124 | sp | 55332 | A | DONE | 5 | S |  | LABCORP BIO 6240011 | paint | 2024-08-16 | Z | 2024-08-12 | 40 | 80 | 0 |  | 20 | 130 |  | Lab S121 |  | 4
2024-08-12 | 3460 |  | 68114 - 68116 | A | DONE | 5 | S-M | neal | MEMORIAL HS 6210024 |  | 2024-08-13 | Z | 2024-08-07 | 120 | 0 | 0 |  | 0 | 190 |  | Pipe shroud |  | 6
2024-08-12 | 3461 |  | 68117 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-08-13 | Z | 2024-08-09 | 40 | 0 | 0 |  | 0 | 50 |  | Caps |  | 4
2024-08-14 | 2362 |  | 80306 - 80308 | A | DONE | 5 | S-M |  | MENDOTA FOODS 6220027 | flex , VD's | 2024-08-15 | Z | 2024-08-09 | 110 | 0 | 0 |  | 0 | 130 |  | EF |  | 6
2024-08-15 | 237 |  | 69811 | A | DONE | 21 | S-M |  | MSN 2240054 | flex | 2024-08-16 | Z | 2024-08-05 | 240 | 0 | 280 | F | 0 | 640 |  | DR-3 Row 2,3 |  | 11
2024-08-14 | 242 | sp/w | 56336 | A | DONE | 2 | S | pt.ss | PROMEGA 1518 |  | 2024-08-14 | Z | 2024-08-09 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 5
2024-08-12 | 1993 | bth | L2-SAMP-01 | A | DONE | 66 | M |  | PROMEGA MCBR 2240039 |  | 2024-08-13 | Z | 2024-07-25 | 1140 | 140 | 350 | F | 0 | 2590 |  |  |  | 19
2024-08-12 | 3061 | bth | 70678 | A | DONE | 3 | S-M |  | RAMC PT/OT 2240017 |  | 2024-08-12 | Z | 2024-08-01 | 30 | 30 | 0 |  | 0 | 60 |  | Misc outs |  | 11
2024-08-12 | 243 |  | 78740 | A | DONE | 4 | S |  | SUNSET RIDGE 4240013 |  | 2024-08-13 | Z | 2024-08-09 | 100 | 0 | 0 |  | 0 | 220 |  | Cooling Tower |  | 4
2024-08-12 | 235 |  | 79646 | A | DONE | 4 | S-M |  | UPLAND HILLS 2240008 | paint | 2024-08-12 | Z | 2024-08-01 | 60 | 0 | 40 | F | 20 | 130 |  | PR 4 |  | 11
2024-08-12 | 274 | sp | 79615 - 79616 | A | DONE | 4 | S-M |  | UPLAND HILLS 2240008 |  | 2024-08-12 | Z | 2024-03-20 | 50 | 50 | 0 |  | 0 | 120 |  | RAT 1336 |  | 145 |  | 2024-05-27 | 2024-06-17 | 2024-06-24
2024-08-12 | 275 | sp | 79617 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-08-12 | Z | 2024-03-20 | 20 | 30 | 0 |  | 0 | 40 |  | 1336 EA |  | 145 |  | 2024-05-27 | 2024-06-17 | 2024-06-24
2024-08-16 | 3527 |  | 79289 - 79290 | A | DONE | 18 | S-M |  | UWL-GRAFF 6230017 | VD's | 2024-08-16 | Z | 2024-06-24 | 290 | 0 | 160 | F | 0 | 710 |  | AHU-5 RA |  | 53
2024-08-16 | 3528 |  | 79292 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 80 | 0 | 50 | F | 0 | 170 |  | AHU-5 RA |  | 53
2024-08-16 | 3529 | bth | 79294 - 79296 | A | DONE | 17 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 190 | 70 | 150 | F | 0 | 480 |  | AHU-5 RA/SA |  | 53
2024-08-16 | 3530 |  | 79297 - 79300 | A | DONE | 24 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 560 | 0 | 30 | F | 0 | 940 |  | AHU-5 SA |  | 53
2024-08-16 | 3531 | bth | 79302 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 50 | 20 | 30 | F | 0 | 120 |  | AHU-5 SA |  | 53
2024-08-16 | 3532 | sp | 79303 - 79304 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 50 | 90 | 0 |  | 0 | 140 |  | AHU-5 SA |  | 53
2024-08-15 | 3533 | bth | 79305 - 79306 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 50 | 20 | 30 | F | 0 | 100 |  | SAT-5-1-14 |  | 53
2024-08-16 | 3534 | bth | 79307 - 79308 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 100 | 50 | 20 | F | 0 | 170 |  | SAT-5-1-12 / 13 |  | 53
2024-08-16 | 3535 | bth | 79309 - 793010 | A | DONE | 9 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 60 | 70 | 80 | F | 0 | 210 |  | SAT-5-1-11 / 10 |  | 53
2024-08-16 | 3536 | bth | 79311 - 79313 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 60 | 50 | 20 | F | 0 | 130 |  | SAT-5-1-8 / 7 / 6 |  | 53
2024-08-15 | 3537 | bth | 79314 - 79315 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 70 | 20 | 40 | F | 0 | 140 |  | SAT-5-1-5 |  | 53
2024-08-16 | 3538 | bth | 79316 - 79318 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 80 | 30 | 60 | F | 0 | 190 |  | SAT-5-1-4 / 9 |  | 53
2024-08-16 | 3539 | bth | 79319 - 79320 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 60 | 90 | 0 |  | 0 | 150 |  | SAT-5-1-2 |  | 53
2024-08-16 | 3540 |  | 79323 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-16 | Z | 2024-06-24 | 50 | 0 | 20 | F | 30 | 80 |  | SAT-5-1-1 |  | 53
2024-08-17 | 3541 | bth | 79324 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-06-24 | 30 | 20 | 20 | F | 0 | 60 |  | SAT-5-1-1 |  | 53
2024-08-17 | 3565 |  | 79332 - 79333 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-16 | Z | 2024-07-19 | 40 | 0 | 0 |  | 20 | 60 |  | SAT-5-3-12 |  | 28
2024-08-15 | 3566 | sp | 79354 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-07-19 | 30 | 30 | 0 |  | 0 | 60 |  | RM 315 SA |  | 28
2024-08-17 | 3567 |  | 79355 - 79356 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-07-19 | 80 | 0 | 80 | F | 0 | 250 |  | AHU-5 RA |  | 28
2024-08-17 | 3568 |  | 79357 - 79359 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-07-19 | 160 | 0 | 0 |  | 0 | 350 |  | EF-3 |  | 28
2024-08-17 | 3569 |  | 38266 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-07-19 | 50 | 0 | 0 |  | 0 | 60 |  | EF-1 - 3rd floor |  | 28
2024-08-15 | 3570 | w | 38268 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-07-19 | 30 | 0 | 0 |  | 30 | 80 |  | Curb Cap |  | 28
2024-08-17 | 3571 |  | 38269 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-07-19 | 20 | 0 | 0 |  | 0 | 30 |  | EF-1 1st floor |  | 28
2024-08-16 | 3574 |  | 79337 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-07-29 | 40 | 0 | 30 | F | 0 | 70 |  | SAT-5-3-4 |  | 18
2024-08-16 | 3576 |  | 79339 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-07-29 | 110 | 0 | 0 |  | 0 | 130 |  | SAT-5-3-4 |  | 18
2024-08-16 | 3577 |  | 79340 , 79342-43 | F | DONE | 8 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-08-01 | 140 | 0 | 60 |  | 0 | 290 |  | Misc |  | 15
2024-08-14 | 3579 |  | 79346 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-08-05 | 30 | 0 | 0 |  | 0 | 60 |  | AHU-5 SA - 3rd |  | 11
2024-08-17 | 3583 |  | 79365 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-08-08 | 100 | 0 | 0 |  | 0 | 120 |  | AHU-4 RA |  | 8
2024-08-17 | 3584 |  | 79366 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-08-08 | 70 | 0 | 0 |  | 0 | 200 |  | AHU-4 SA |  | 8
2024-08-17 | 3585 |  | 79367 - 79368 | A | DONE | 9 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-08-08 | 170 | 0 | 40 | F | 0 | 240 |  | AHU-4 RA |  | 8
2024-08-17 | 3588 |  | 79373 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-08-09 | 30 | 0 | 0 |  | 0 | 50 |  | AHU-4 SA C386 |  | 7
2024-08-15 | 3589 |  | 67906 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2024-08-16 | Z | 2024-08-14 | 60 | 0 | 0 |  | 0 | 140 |  | AHU test EC |  | 2
2024-08-16 | 3512r |  | 79220 - 79222 | A | DONE | 14 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-16 | Z | 2024-07-29 | 200 | 0 | 130 | F | 270 | 380 |  | 215 B,C,D TA |  | 18
2024-08-16 | 3513r |  | 79223 - 79224 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-16 | Z | 2024-07-29 | 100 | 0 | 30 | F | 100 | 160 |  | 215 E, 217 C TA |  | 18
2024-08-16 | 3514r |  | 79225 - 79226 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-16 | Z | 2024-07-29 | 120 | 0 | 30 | F | 100 | 160 |  | 217 A,B TA |  | 18
2024-08-13 | 543 | sp | 66931 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-14 | Z | 2024-08-05 | 20 | 20 | 0 |  | 0 | 40 |  | L2-SAT-1-2-2 |  | 9
2024-08-13 | 959 |  | L3Z1-TA-1 | A | DONE | 9 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 70 | 0 | 150 | F | 180 | 300 |  |  |  | 21
2024-08-14 | 960 |  | L3Z1-TA-2 | A | DONE | 6 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 80 | 0 | 70 | F | 100 | 190 |  |  |  | 21
2024-08-14 | 961 |  | L3Z1-TA-3 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 50 | F | 70 | 140 |  |  |  | 21
2024-08-13 | 962 |  | L3Z1-TA-4 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 21
2024-08-13 | 963 |  | L3Z1-TA-5 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 21
2024-08-13 | 964 |  | L3Z1-TA-6 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 21
2024-08-13 | 965 |  | L3Z1-TA-7 | A | DONE | 11 | S | neal | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 260 | 0 | 0 |  | 20 | 340 |  |  |  | 21
2024-08-14 | 966 |  | L3Z1-TA-8 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 80 | 0 | 0 |  | 20 | 100 |  |  |  | 21
2024-08-14 | 967 |  | L3Z1-TA-9 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-13 | 968 |  | L3Z1-TA-10 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-14 | 969 |  | L3Z1-TA-11 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-14 | 970 |  | L3Z1-TA-12 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 90 | 0 | 0 |  | 50 | 110 |  |  |  | 21
2024-08-13 | 971 |  | L3Z1-TA-13 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-14 | 972 |  | L3Z1-TA-14 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 21
2024-08-13 | 973 |  | L3Z1-TA-15 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 21
2024-08-13 | 974 |  | L3Z1-TA-16 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 21
2024-08-13 | 975 |  | L3Z1-TA-17 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 21
2024-08-13 | 976 |  | L3Z1-TA-18 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-13 | 977 |  | L3Z1-TA-19 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 0 |  | 20 | 70 |  |  |  | 21
2024-08-13 | 978 |  | L3Z1-TA-20 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 110 | 0 | 0 |  | 40 | 130 |  |  |  | 21
2024-08-13 | 979 |  | L3Z2-TA-21 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 21
2024-08-13 | 980 |  | L3Z2-TA-22 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 21
2024-08-13 | 981 |  | L3Z2-TA-23 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 21
2024-08-14 | 982 |  | L3Z2-TA-24 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 90 | 0 | 0 |  | 40 | 120 |  |  |  | 21
2024-08-14 | 983 |  | L3Z2-TA-25 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 60 | 0 | 0 |  | 30 | 70 |  |  |  | 21
2024-08-13 | 984 |  | L3Z2-TA-26 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 21
2024-08-13 | 985 |  | L3Z2-TA-27 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 110 | 0 | 0 |  | 50 | 130 |  |  |  | 21
2024-08-13 | 986 |  | L3Z2-TA-28 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 21
2024-08-14 | 987 |  | L3Z2-TA-29 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-13 | 988 |  | L3Z2-TA-30 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-13 | 989 |  | L3Z2-TA-31 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-13 | 990 |  | L3Z2-TA-32 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 21
2024-08-14 | 991 |  | L3Z2-TA-33 | A | DONE | 6 | S | neal | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 80 | 0 | 50 | F | 50 | 160 |  |  |  | 21
2024-08-14 | 992 |  | L3Z2-TA-34 | A | DONE | 7 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 130 | 0 | 30 | F | 100 | 190 |  |  |  | 21
2024-08-14 | 993 |  | L3Z2-TA-35 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 30 | F | 30 | 80 |  |  |  | 21
2024-08-13 | 994 |  | L3Z2-TA-36 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 21
2024-08-14 | 995 |  | L3Z2-TA-37 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 21
2024-08-14 | 996 |  | L3Z2-TA-38 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 50 | 0 | 50 | F | 70 | 140 |  |  |  | 21
2024-08-14 | 997 |  | L3Z2-TA-39 | A | DONE | 10 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 100 | 0 | 130 | F | 180 | 300 |  |  |  | 21
2024-08-13 | 998 |  | L3Z2-TA-40 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-07-24 | 80 | 0 | 30 | F | 60 | 130 |  |  |  | 21
2024-08-14 | 999 |  | L3Z2-TA-41 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-08-14 | Z | 2024-07-24 | 100 | 0 | 0 |  | 40 | 120 |  |  |  | 21
2024-08-12 | 3947 |  | L2Z2-TA-21 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 111
2024-08-12 | 3948 |  | L2Z2-TA-22 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 111
2024-08-12 | 3949 |  | L2Z2-TA-23 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 111
2024-08-13 | 3950 |  | L2Z2-TA-24 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 111
2024-08-13 | 3951 |  | L2Z2-TA-25 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 30 | 0 | 50 | F | 50 | 100 |  |  |  | 111
2024-08-14 | 3952 |  | L2Z2-TA-26 | A | DONE | 14 | S-M | neal | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 280 | 0 | 50 | F | 190 | 430 |  |  |  | 111
2024-08-13 | 3953 |  | L2Z2-TA-27 | A | DONE | 12 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 110 | 0 | 180 | F | 210 | 380 |  |  |  | 111
2024-08-13 | 3954 |  | L2Z2-TA-28 | A | DONE | 6 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 60 | 0 | 70 | F | 90 | 160 |  |  |  | 111
2024-08-13 | 3955 |  | L2Z2-TA-29 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 40 | 0 | 50 | F | 60 | 110 |  |  |  | 111
2024-08-13 | 3956 |  | L2Z2-TA-30 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 111
2024-08-13 | 3957 |  | L2Z2-TA-31 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 111
2024-08-13 | 3958 |  | L2Z2-TA-32 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 111
2024-08-13 | 3961 |  | L2Z2-TA-35 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 111
2024-08-13 | 3962 |  | L2Z2-TA-36 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 80 | 0 | 0 |  | 40 | 90 |  |  |  | 111
2024-08-13 | 3963 |  | L2Z2-TA-37 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 111
2024-08-13 | 3964 |  | L2Z2-TA-38 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 111
2024-08-12 | 3965 |  | L2Z2-TA-39 | A | DONE | 7 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-04-25 | 100 | 0 | 70 | F | 70 | 140 |  |  |  | 111
2024-08-14 | 3983 |  | L2Z1-TA-1 | A | DONE | 10 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 80 | 0 | 150 | F | 180 | 310 |  |  |  | 104
2024-08-14 | 3984 |  | L2Z1-TA-2 | A | DONE | 6 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 70 | 0 | 80 | F | 110 | 180 |  |  |  | 104
2024-08-13 | 3985 |  | L2Z1-TA-3 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 70 | 0 | 30 | F | 60 | 130 |  |  |  | 104
2024-08-13 | 3986 |  | L2Z1-TA-4 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 104
2024-08-13 | 3987 |  | L2Z1-TA-5 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 104
2024-08-14 | 3988 |  | L2Z1-TA-6 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 104
2024-08-14 | 3989 |  | L2Z1-TA-7 | A | DONE | 8 | S-M | neal | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 200 | 0 | 0 |  | 100 | 230 |  |  |  | 104
2024-08-13 | 3990 |  | L2Z1-TA-8 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 104
2024-08-13 | 3991 |  | L2Z1-TA-9 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 104
2024-08-13 | 3992 |  | L2Z1-TA-10 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 20 | 60 |  |  |  | 104
2024-08-13 | 3993 |  | L2Z1-TA-11 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 104
2024-08-13 | 3994 |  | L2Z1-TA-12 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 104
2024-08-13 | 3995 |  | L2Z1-TA-13 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 104
2024-08-14 | 3996 |  | L2Z1-TA-14 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 30 | 60 |  |  |  | 104
2024-08-13 | 3997 |  | L2Z1-TA-15 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 104
2024-08-13 | 3998 |  | L2Z1-TA-16 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 104
2024-08-13 | 3999 |  | L2Z1-TA-17 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 104
2024-08-13 | 4000 |  | L2Z1-TA-18 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 60 | 0 | 30 | F | 60 | 120 |  |  |  | 104
2024-08-13 | 4001 |  | L2Z1-TA-19 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 60 | 0 | 0 |  | 30 | 70 |  |  |  | 104
2024-08-13 | 4002 |  | L2Z1-TA-20 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-14 | Z | 2024-05-02 | 90 | 0 | 0 |  | 50 | 110 |  |  |  | 104
2024-08-15 | 5046 | bth | SA-03-09 | A | DONE | 52 | L |  | UWSP ALBERTSON 6230016 |  | 2024-08-15 | Z | 2024-07-05 | 430 | 40 | 820 | F | 0 | 2170 |  |  |  | 41
2024-08-15 | 5047 | bth | SA-03-10 | A | DONE | 37 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-08-15 | Z | 2024-07-05 | 620 | 20 | 280 | F | 0 | 1480 |  |  |  | 41
2024-08-15 | 5048 |  | SA-03-11 | A | DONE | 31 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-08-15 | Z | 2024-07-05 | 120 | 0 | 640 | F | 0 | 1310 |  |  |  | 41
2024-08-15 | 5049 | bth | SA-03-12 | A | DONE | 18 | M |  | UWSP ALBERTSON 6230016 |  | 2024-08-15 | Z | 2024-07-05 | 150 | 40 | 240 | F | 0 | 680 |  |  |  | 41
2024-08-15 | 5050 | bth | SA-03-13 | A | DONE | 10 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-08-15 | Z | 2024-07-05 | 70 | 80 | 90 | F | 0 | 260 |  |  |  | 41
2024-08-15 | 5051 | bth | SA-03-14 | A | DONE | 20 | M |  | UWSP ALBERTSON 6230016 |  | 2024-08-15 | Z | 2024-07-05 | 270 | 30 | 180 | F | 0 | 660 |  |  |  | 41
2024-08-15 | 5052 | bth | SA-03-15 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-08-15 | Z | 2024-07-05 | 100 | 30 | 150 | F | 0 | 350 |  |  |  | 41
2024-08-13 | 5075 |  | 81101 | delete |  |  | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-08-20 | Z | 2024-08-06 | [5 empty] | 0 |  | 3rd floor EC |  | 14
2024-08-13 | 1467 |  | 73057 - 73059 | A | DONE | 34 | M-L |  | UW-VET MED 6210014 | flex , CD | 2024-08-14 | Z | 2024-07-31 | 510 | 0 | 330 | F | 0 | 1370 |  | CB 1547 |  | 14
2024-08-12 | 1468 |  | 73007 - 73008 | A | DONE | 32 | M-L |  | UW-VET MED 6210014 |  | 2024-08-14 | Z | 2024-07-31 | 230 | 0 | 550 | F | 0 | 1560 |  | CB 1547 |  | 14
2024-08-13 | 1476 |  | 73010 - 73012 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 |  | 2024-08-14 | Z | 2024-08-07 | 30 | 0 | 0 |  | 0 | 30 |  | Drip pans |  | 7
2024-08-13 | 1479 |  | 73015 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-08-14 | Z | 2024-08-13 | 20 | 0 | 0 |  | 0 | 20 |  | L1-EA |  | 1
[6 empty] | 1233 | [13 empty] | 43710 |  |  |  | 6450 | 14.76%
WEEK OF 8-19-2024
2024-08-19 | 3652 |  | 80096 , 80102 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 |  | 2024-08-15 | Z | 2024-07-30 | 110 | 0 | 180 | F | 0 | 310 |  | EF-3,4 , EA-1 |  | 16
2024-08-20 | 2435 |  | 61166 | A | DONE | 2 | S | neal | ABE LINCOLN 6230029 |  | 2024-08-22 | Z | 2024-08-19 | 20 | 0 | 0 |  | 0 | 20 |  | Existing wall fin cover |  | 3
2024-08-22 | 2436 | sp | 61167 | A | DONE | 2 | S |  | ABE LINCOLN 6230029 |  | 2024-08-26 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 30 |  | Grille hetos |  | 4
2024-08-19 | 1774 |  | 81410 | A | DONE | 2 | S-M | neal | BLACKHAWK BTC 6230025 |  | 2024-08-19 | Z | 2024-08-14 | 30 | 0 | 0 |  | 0 | 80 |  | Flashing |  | 5
2024-08-19 | 1038 | bth | L6-A-EAMP-020 | A | DONE | 19 | M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 230 | 20 | 210 | F | 0 | 760 |  |  |  | 56
2024-08-19 | 1039 | bth | L6-A-EAMP-021 | A | DONE | 22 | M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 260 | 20 | 250 | F | 0 | 830 |  |  |  | 56
2024-08-19 | 1040 | bth | L6-A-EAMP-022 | A | DONE | 15 | M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 70 | 50 | 250 | F | 0 | 560 |  |  |  | 56
2024-08-19 | 1041 | bth | L6-A-EAMP-023 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 60 | 20 | 50 | F | 0 | 160 |  |  |  | 56
2024-08-19 | 1042 | bth | L6-A-EAMP-024 | A | DONE | 14 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 150 | 20 | 170 | F | 0 | 530 |  |  |  | 56
2024-08-19 | 1043 |  | L6-A-EAMP-025 | A | DONE | 7 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 60 | 0 | 110 | F | 0 | 210 |  |  |  | 56
2024-08-19 | 1044 | bth | L6-A-EAMP-026 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 60 | 20 | 40 | F | 0 | 130 |  |  |  | 56
2024-08-19 | 1045 | bth | L6-A-EAMP-027 | A | DONE | 14 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 90 | 20 | 230 | F | 0 | 510 |  |  |  | 56
2024-08-19 | 1048 | bth | L6-A-SAMP-034 | A | DONE | 29 | M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 380 | 40 | 290 | F | 0 | 1200 |  |  |  | 56
2024-08-20 | 1049 | bth | L6-A-SAMP-035 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 150 | 20 | 180 | F | 0 | 520 |  |  |  | 56
2024-08-20 | 1050 | bth | L6-A-SAMP-036 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 230 | 20 | 40 | F | 0 | 370 |  |  |  | 56
2024-08-19 | 1051 |  | L6-A-SAMP-037 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 240 | 0 | 100 | F | 0 | 470 |  |  |  | 56
2024-08-20 | 1052 | Bth | L6-A-SAMP-038 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 150 | 40 | 90 | F | 0 | 370 |  |  |  | 56
2024-08-19 | 1053 | Bth | L6-A-SAMP-039 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 120 | 20 | 60 | F | 0 | 240 |  |  |  | 56
2024-08-20 | 1054 | Bth | L6-A-SAMP-040 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 170 | 30 | 50 | F | 0 | 300 |  |  |  | 56
2024-08-19 | 1055 | Bth | L6-A-SAMP-041 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-20 | 50 | 40 | 30 | F | 0 | 130 |  |  |  | 56
2024-08-20 | 1062 | bth | L6-A-EALP-040 | A | DONE | 5 | S-M | neal | CDIS 6220028 | paint | 2024-08-15 | Z | 2024-06-25 | 60 | 30 | 30 | F | 20 | 130 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1063 | bth | L6-A-EALP-041 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-25 | 140 | 40 | 20 | F | 0 | 240 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1064 | bth | L6-A-EALP-042 | A | DONE | 4 | S-M | pt.neal | CDIS 6220028 | paint | 2024-08-15 | Z | 2024-06-25 | 60 | 30 | 0 |  | 20 | 100 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1065 | bth | L6-A-EALP-043 | A | DONE | 7 | S-M | neal | CDIS 6220028 | paint | 2024-08-15 | Z | 2024-06-25 | 120 | 20 | 20 | F | 20 | 180 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1066 | bth | L6-A-EALP-044 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-25 | 50 | 50 | 0 |  | 0 | 110 |  |  |  | 51 |  | 2024-08-02
2024-08-21 | 1067 | bth | L6-A-EALP-045 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-25 | 60 | 50 | 0 |  | 0 | 120 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1068 | bth | L6-A-EALP-046 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 | paint , 1" spiral accu | 2024-08-15 | Z | 2024-06-25 | 50 | 60 | 0 |  | 30 | 140 |  |  |  | 51 |  | 2024-08-02
2024-08-22 | 1069 | bth | L6-A-EALP-055 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 | paint , 1" spiral accu | 2024-08-15 | Z | 2024-06-25 | 80 | 30 | 20 | F | 30 | 140 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1070 | bth | L6-A-EALP-056 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-25 | 20 | 30 | 20 | F | 0 | 90 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1071 | bth | L6-A-SALP-056 | A | DONE | 6 | S-M | neal | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 90 | 20 | 30 | F | 20 | 170 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1072 | bth | L6-A-SALP-057 | A | DONE | 7 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-25 | 100 | 30 | 40 | F | 0 | 190 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1073 | bth | L6-A-SALP-058 | A | DONE | 6 | S-M | neal | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 90 | 20 | 30 | F | 20 | 180 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1074 | bth | L6-A-SALP-059 | A | DONE | 7 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-25 | 120 | 30 | 20 | F | 0 | 190 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1075 | bth | L6-A-SALP-060 | A | DONE | 7 | S-M | neal | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 120 | 20 | 20 | F | 20 | 170 |  |  |  | 51 |  | 2024-08-02
2024-08-21 | 1076 | bth | L6-A-SALP-061 | A | DONE | 7 | S-M | neal | CDIS 6220028 |  | 2024-08-15 | Z | 2024-06-25 | 110 | 30 | 20 | F | 0 | 180 |  |  |  | 51 |  | 2024-08-02
2024-08-21 | 1077 | bth | L6-A-SALP-062 | A | DONE | 7 | S-M |  | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 90 | 20 | 60 | F | 20 | 200 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1078 | bth | L6-A-SALP-063 | A | DONE | 3 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1079 | bth | L6-A-SALP-064 | A | DONE | 7 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 90 | 20 | 60 | F | 20 | 200 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1080 |  | L6-A-SALP-065 | A | DONE | 3 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 50 | 20 | 0 |  | 20 | 60 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1081 | bth | L6-A-SALP-066 | A | DONE | 8 | S-M | neal | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 50 | 110 | 30 | F | 30 | 210 |  |  |  | 51 |  | 2024-08-02
2024-08-21 | 1082 | bth | L6-A-SALP-067 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 | 1" spiral accu,1" liner | 2024-08-15 | Z | 2024-06-25 | 100 | 40 | 0 |  | 60 | 140 |  |  |  | 51 |  | 2024-08-02
2024-08-21 | 1083 | bth | L6-A-SALP-068 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 70 | 20 | 50 | F | 20 | 150 |  |  |  | 51 |  | 2024-08-02
2024-08-20 | 1084 | bth | L6-A-SALP-088 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-08-15 | Z | 2024-06-25 | 50 | 60 | 0 |  | 20 | 100 |  |  |  | 51 |  | 2024-08-02
2024-08-22 | 1097 |  | Pre-Fab Hangers | A | DONE | 3 | S | neal | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-02 | 70 | 0 | 0 |  | 0 | 150 |  | 7th A-Section |  | 51
2024-08-21 | 1331 |  | L6-A-EAMP-032 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 170 | 0 | 30 | F | 0 | 290 |  |  |  | 42 |  | 2024-08-09
2024-08-21 | 1332 | bth | L6-A-EAMP-033 | A | DONE | 12 | S-M | neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 30 | 30 | 240 | F | 0 | 350 |  |  |  | 42 |  | 2024-08-09
2024-08-21 | 1333 | bth | L6-A-EAMP-034 | A | DONE | 11 | S-M | neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 60 | 50 | 150 | F | 0 | 310 |  |  |  | 42 |  | 2024-08-09
2024-08-21 | 1334 | bth | L6-A-EAMP-035 | A | DONE | 10 | S-M | neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 140 | 20 | 80 | F | 0 | 270 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1335 | bth | L6-A-EAMP-036 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 20 | 30 | 80 | F | 0 | 150 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1336 | bth | L6-A-EAMP-037 | A | DONE | 13 | S-M | neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 30 | 20 | 270 | F | 0 | 380 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1337 | bth | L6-A-EAMP-038 | A | DONE | 12 | S-M | neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 20 | 70 | 210 | F | 0 | 350 |  |  |  | 42 |  | 2024-08-09
2024-08-21 | 1338 |  | L6-A-RAD-002 | A | DONE | 2 | S | neal | CDIS 6220028 | VD | 2024-08-20 | Z | 2024-07-09 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1339 | bth | L6-A-SAMP-032 | A | DONE | 18 | M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 360 | 20 | 60 | F | 0 | 740 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1340 | bth | L6-A-SAMP-033 | A | DONE | 24 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 240 | 60 | 300 | F | 0 | 930 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1341 | bth | L6-A-SAMP-042 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 80 | 20 | 270 | F | 0 | 430 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1342 | bth | L6-A-SAMP-043 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 70 | 70 | 150 | F | 0 | 330 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1343 | bth | L6-A-SAMP-044 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 110 | 20 | 210 | F | 0 | 390 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1344 | bth | L6-A-SAMP-045 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 100 | 20 | 150 | F | 0 | 320 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1345 | bth | L6-A-SAMP-046 | A | DONE | 7 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 80 | 40 | 40 | F | 0 | 190 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1346 | bth | L6-A-SAMP-047 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 180 | 20 | 90 | F | 0 | 370 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1347 | bth | L6-A-SAMP-048 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 90 | 20 | 250 | F | 0 | 510 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1348 | bth | L6-A-SAMP-049 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 100 | 20 | 60 | F | 0 | 200 |  |  |  | 42 |  | 2024-08-09
2024-08-22 | 1349 | bth | L6-A-SAMP-050 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-07-09 | 80 | 20 | 120 | F | 0 | 250 |  |  |  | 42 |  | 2024-08-09
2024-08-21 | 1350 |  | L6-A-SAMP-051 | A | DONE | 2 | S |  | CDIS 6220028 | VD | 2024-08-20 | Z | 2024-07-09 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 42
2024-08-21 | 3426 |  | SA-(10wg)-PH-05 | A | DONE | 63 | M-L |  | CDIS 6220028 | partial , 1" DW | 2024-08-20 | Z | 2024-08-01 | 1570 | 0 | 0 |  | 330 | 2200 |  |  |  | 19
2024-08-21 | 3430 |  | SA-(10wg)-PH-03 | A | DONE | 53 | L |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-08-01 | 1310 | 0 | 0 |  | 0 | 3540 |  |  |  | 19
2024-08-21 | 3431 |  | SA-(10wg)-PH-04 | A | DONE | 48 | L |  | CDIS 6220028 | 1" DW | 2024-08-20 | Z | 2024-08-01 | 1190 | 0 | 0 |  | 160 | 3010 |  |  |  | 19
2024-08-20 | 3432 |  | 69810 | A | DONE | 33 | M-L |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-08-01 | 810 | 0 | 0 |  | 0 | 1790 |  | End caps |  | 19
2024-08-20 | 3433 |  | 69936 - 69937 | F | DONE | 2 | S-M | pt.neal | CDIS 6220028 |  | 2024-08-20 | Z | 2024-08-02 | 30 | 0 | 0 |  | 0 | 70 |  | 5th floor |  | 18
2024-08-20 | 3436 |  | 61518 | A | DONE | 3 | S-M | pt.alum | CDIS 6220028 |  | 2024-08-20 | Z | 2024-08-05 | 40 | 20 | 0 |  | 0 | 80 |  | Basement |  | 15
2024-08-20 | 3443 |  | 69815 | A | DONE | 2 | S |  | CDIS 6220028 | flex | 2024-08-20 | Z | 2024-08-08 | 20 | 0 | 0 |  | 0 | 20 |  | AHU-1A EA |  | 12
2024-08-20 | 3444 |  | 69816 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-08-20 | Z | 2024-08-08 | 40 | 0 | 0 |  | 0 | 60 |  | 2nd flashing |  | 12
2024-08-21 | 3445 |  | 69940 | A | DONE | 2 | S |  | CDIS 6220028 | VD | 2024-08-22 | Z | 2024-08-09 | 20 | 0 | 0 |  | 0 | 30 |  | 5th floor N. core EAMP |  | 13
2024-08-21 | 4311 |  | 69967 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-08-12 | 60 | 0 | 0 |  | 0 | 100 |  | 8th floor sleeves |  | 10
2024-08-24 | 4315 |  | 69662 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-08-13 | 90 | 0 | 0 |  | 0 | 150 |  | EC North core |  | 9
2024-08-24 | 4344 |  | 69943 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-26 | Z | 2024-08-21 | 20 | 0 | 0 |  | 0 | 20 |  | 5TH FLOOR |  | 5
2024-08-22 | 4353 |  | 61365 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-22 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 50 |  | Misc |  | 0
2024-08-24 | 4354 |  | 69817 | A | DONE | 2 | S-M |  | CDIS 6220028 | flex | 2024-08-22 | Z | 2024-08-09 | 0 | 0 | 0 |  | 0 | 0 |  | AHU-1A |  | 13
2024-08-20 | 3428a |  | EA-(-10wg)-PH-05 | A | DONE | 24 | M-L |  | CDIS 6220028 | partial | 2024-08-27 | Z | 2024-08-01 | 600 | 0 | 0 |  | 0 | 900 |  |  |  | 26
2024-08-20 | 248 |  | 78741 | A | DONE | 2 | S |  | COTTAGE GROVE ES 4240033 |  | 2024-08-21 | Z | 2024-08-19 | 20 | 0 | 0 |  | 0 | 30 |  | Misc |  | 2
2024-08-21 | 250 |  | 92358 | A | DONE | 2 | S | BI | COTTAGE GROVE ES 4240033 |  | 2024-08-22 | Z | 2024-08-21 | 20 | 0 | 0 |  | 0 | 50 |  | Flat Plate |  | 1
2024-08-21 | 251 |  | hand drawn | A | DONE | 2 | S |  | COTTAGE GROVE ES 4240033 |  | 2024-08-21 | Z | 2024-08-21 | 20 | 0 | 0 |  | 0 | 20 |  | Flange gaskets |  | 0
2024-08-22 | 2586 | bth | L2-EAD-Z3-0024 | A | DONE | 23 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 220 | 60 | 280 | F | 0 | 800 |  |  |  | 21
2024-08-22 | 2587 |  | L2-EAD-Z3-0025 | A | DONE | 23 | M |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 330 | 0 | 240 | F | 0 | 850 |  |  |  | 21
2024-08-22 | 2588 |  | L2-EAD-Z3-0027 | A | DONE | 23 | M |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 140 | 0 | 420 | F | 0 | 930 |  |  |  | 21
2024-08-22 | 2589 |  | L2-EAD-Z3-0028 | A | DONE | 19 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 240 | 0 | 220 | F | 0 | 710 |  |  |  | 21
2024-08-22 | 2590 |  | L2-EAD-Z3-0031 | A | DONE | 14 | M |  | EXACT TL-5 6240014 | VD | 2024-08-23 | Z | 2024-08-02 | 140 | 0 | 190 | F | 0 | 670 |  |  |  | 21
2024-08-22 | 2591 |  | L2-EAD-Z3-0032 | A | DONE | 21 | M |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 440 | 0 | 70 | F | 0 | 860 |  |  |  | 21
2024-08-22 | 2592 |  | L2-SAMP-Z3-0013 | A | DONE | 22 | M |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 150 | 0 | 400 | F | 0 | 860 |  |  |  | 21
2024-08-22 | 2593 | bth | L2-SAMP-Z3-0014 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 30 | 20 | 110 | F | 0 | 240 |  |  |  | 21
2024-08-22 | 2594 | bth | L2-SAMP-Z3-0015 | A | DONE | 8 | S |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 80 | 20 | 90 | F | 0 | 200 |  |  |  | 21
2024-08-22 | 2595 | sp | L2-SAMP-Z3-0016 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 20 | 50 | 0 | F | 0 | 60 |  |  |  | 21
2024-08-22 | 2596 |  | L2-SAMP-Z3-0017 | A | DONE | 24 | M-L |  | EXACT TL-5 6240014 |  | 2024-08-23 | Z | 2024-08-02 | 230 | 0 | 360 | F | 0 | 1020 |  |  |  | 21
2024-08-19 | 245 |  | 61292 | A | DONE | 2 | S |  | HOLY WISDOM 6220019 |  | 2024-08-19 | Z | 2024-08-12 | 30 | 0 | 0 |  | 0 | 50 |  | Sq/rnd , angle |  | 7
2024-08-19 | 3363 |  | 78696 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-08-20 | Z | 2024-08-19 | 20 | 0 | 0 |  | 0 | 20 |  | Pool |  | 1
2024-08-23 | 3364 |  | 78697 | A | DONE | 2 | S | neal | JANESVILLE ESSR 6230011 |  | 2024-08-26 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 50 |  | Flashing |  | 4
2024-08-20 | 1902 | sp | 62396 | A | DONE | 17 | S-M |  | JPC OFFICE 6240002 |  | 2024-08-20 | Z | 2024-08-06 | 40 | 370 | 0 |  | 0 | 480 |  | Roof spiral |  | 14
2024-08-22 | 1904 | sp | 62188 | A | DONE | 7 | S |  | JPC OFFICE 6240002 |  | 2024-08-26 | Z | 2024-08-19 | 20 | 150 | 0 |  | 0 | 160 |  | Spiral |  | 7
2024-08-23 | 1905 |  | 62189 - 62190 | A | DONE | 10 | S-M |  | JPC OFFICE 6240002 | 1" liner | 2024-08-26 | Z | 2024-08-19 | 250 | 0 | 0 |  | 150 | 310 |  | Drops |  | 7
2024-08-23 | 1906 |  | 62397 - 62399 | A | DONE | 11 | S-M |  | JPC OFFICE 6240002 |  | 2024-08-26 | Z | 2024-08-19 | 220 | 0 | 50 | F | 0 | 250 |  | VAV Connections |  | 7
2024-08-23 | 1909 |  | 82401 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-08-26 | Z | 2024-08-21 | 20 | 0 | 0 |  | 0 | 20 |  | VAV-6 Revision |  | 5
2024-08-23 | 1910 |  | 82402 | A | DONE | 7 | S-M |  | JPC OFFICE 6240002 |  | 2024-08-26 | Z | 2024-08-22 | 160 | 0 | 0 |  | 0 | 160 |  | VAV-5 |  | 4
2024-08-19 | 2337 |  | 67728 | A | DONE | 4 | S-M |  | KOHL CENTER 6210034 | paint | 2024-08-20 | Z | 2024-08-15 | 120 | 0 | 0 |  | 30 | 160 |  | Ceiling Tie-in |  | 5
2024-08-22 | 3462 |  | 68118 | A | DONE | 4 | S | neal | MEMORIAL HS 6210024 |  | 2024-08-27 | Z | 2024-08-19 | 80 | 0 | 0 |  | 0 | 160 |  | Pipe cover |  | 8
2024-08-22 | 3463 |  | 68119 - 68120 | A | DONE | 5 | S-M |  | MEMORIAL HS 6210024 |  | 2024-08-27 | Z | 2024-08-19 | 110 | 0 | 0 |  | 0 | 180 |  | Pipe cover |  | 8
2024-08-24 | 3464 |  | 70548 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 |  | 2024-08-26 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 100 |  | Pipe cover |  | 4
2024-08-24 | 3465 |  | 70549 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-08-23 | Z | 2024-08-23 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-08-21 | 2363 |  | 80311 | A | DONE | 2 | S | pt.alum | MENDOTA FOODS 6220027 |  | 2024-08-22 | Z | 2024-08-15 | 30 | 0 | 0 |  | 0 | 40 |  | Misc |  | 7
2024-08-21 | 2364 |  | 80312 | A | DONE | 4 | S-M | ss | MENDOTA FOODS 6220027 |  | 2024-08-22 | Z | 2024-08-15 | 50 | 30 | 0 |  | 0 | 70 |  | Dishwasher |  | 7
2024-08-21 | 249 |  | 69819 | A | DONE | 16 | S-M |  | MSN 2240054 |  | 2024-08-22 | Z | 2024-08-19 | 150 | 0 | 240 | F | 0 | 500 |  | DR-3 Row 2,3 |  | 3
2024-08-24 | 3109 |  | DH0001 - DH0002 | A | DONE | 2 | S | neal | PECATONICA 6240005 |  | 2024-08-26 | Z | 2024-05-24 | 30 | 0 | 0 |  | 0 | 80 |  | Pre-fab hangers |  | 94 |  | 2024-10-07
2024-08-22 | 314 | w | 70545 | A | DONE | 2 | S | BI | PP 10057320 |  | 2024-08-23 | Z | 2024-08-14 | 20 | 0 | 0 |  | 0 | 40 |  | Box |  | 9
2024-08-21 | 315 |  | 70544 | A | DONE | 16 | S |  | PP 10057320 |  | 2024-08-23 | Z | 2024-08-14 | 400 | 0 | 0 |  | 0 | 870 |  | Flat stock |  | 9
2024-08-20 | 2377 | sp | 56338 | A | DONE | 2 | S |  | PROMEGA CMC 2240038 |  | 2024-08-21 | Z | 2024-08-20 | 20 | 20 | 0 |  | 0 | 40 |  | Misc |  | 1
2024-08-22 | 2378 |  | 70547 | A | DONE | 2 | S |  | PROMEGA CMC 2240038 |  | 2024-08-21 | Z | 2024-08-20 | 20 | 0 | 0 |  | 0 | 20 |  | EC |  | 1
2024-08-22 | 1994 | sp | L2-EA (-10wg)-01 | A | DONE | 9 | S |  | PROMEGA MCBR 2240039 |  | 2024-08-21 | Z | 2024-08-08 | 60 | 150 | 0 |  | 0 | 260 |  |  |  | 13
2024-08-22 | 1995 | sp | L2-EA (-10wg)-02 | A | DONE | 11 | S |  | PROMEGA MCBR 2240039 |  | 2024-08-21 | Z | 2024-08-08 | 50 | 220 | 0 |  | 0 | 330 |  |  |  | 13
2024-08-23 | 1996 | bth | L2-SALP-01 | A | DONE | 18 | S-M |  | PROMEGA MCBR 2240039 |  | 2024-08-21 | Z | 2024-08-08 | 260 | 60 | 110 | F | 0 | 490 |  |  |  | 13
2024-08-23 | 1997 | bth | L2-SALP-03 | A | DONE | 9 | S |  | PROMEGA MCBR 2240039 |  | 2024-08-21 | Z | 2024-08-08 | 80 | 130 | 0 |  | 0 | 230 |  |  |  | 13
2024-08-23 | 1998 | bth | L2-SALP-04 | A | DONE | 16 | S-M |  | PROMEGA MCBR 2240039 |  | 2024-08-21 | Z | 2024-08-08 | 220 | 120 | 40 | F | 0 | 430 |  |  |  | 13
2024-08-22 | 2376 |  | 56337 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-08-21 | Z | 2024-08-15 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 6
2024-08-24 | 3062 |  | 70682 | A | DONE | 2 | S |  | RAMC PT/OT 2240017 |  | 2024-08-26 | Z | 2024-08-21 | 40 | 0 | 0 |  | 0 | 50 |  | GRILLE OUTS |  | 5
2024-08-24 | 4768 |  | 78774 | A | DONE | 2 | S | neal | ROCK CO. JAIL 6220018 |  | 2024-08-26 | Z | 2024-08-14 | 20 | 0 | 0 |  | 0 | 40 |  | Max pipe cover |  | 12
2024-08-24 | 4553 |  | 96558 | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2024-08-26 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 60 |  | Caps |  | 4
2024-08-19 | 4552 |  | 96557 | A | DONE | 2 | S | BI | UW-LEVY HALL 8230028 |  | 2024-08-20 | Z | 2024-08-19 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 1
2024-08-23 | 3542 |  | 79253 - 79254 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 | VD's | 2024-08-23 | Z | 2024-06-24 | 180 | 0 | 80 | F | 0 | 350 |  | AHU-4 RA |  | 60
2024-08-23 | 3543 |  | 79255 - 79256 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 | VD's | 2024-08-23 | Z | 2024-06-24 | 80 | 0 | 60 | F | 0 | 170 |  | AHU-4 RA |  | 60
2024-08-23 | 3544 | bth | 79257 - 79258 | A | DONE | 16 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-06-24 | 250 | 20 | 120 | F | 0 | 530 |  | AHU-4 SA |  | 60
2024-08-22 | 3545 | sp | 79259 - 79260 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-06-24 | 40 | 190 | 0 |  | 0 | 230 |  | AHU-4 SA |  | 60
2024-08-23 | 3546 |  | 79261 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-23 | Z | 2024-06-24 | 60 | 0 | 60 | F | 90 | 150 |  | SAT-4-1-1 |  | 60
2024-08-23 | 3547 |  | 79262 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-06-24 | 60 | 0 | 0 |  | 0 | 90 |  | EA/RA PH2 1st |  | 60
2024-08-23 | 3548 | bth | 79263 - 79265 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-06-24 | 90 | 90 | 120 | F | 0 | 320 |  | SAT-4-1-6 / 3 |  | 60
2024-08-23 | 3549 | bth | 79266 - 79268 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-06-24 | 90 | 50 | 20 | F | 0 | 180 |  | SAT-4-1-2 / 7 |  | 60
2024-08-23 | 3550 | bth | 79269 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-06-24 | 40 | 20 | 0 |  | 0 | 60 |  | SAT-4-1-5 |  | 60
2024-08-23 | 3551 |  | 79270 - 79271 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-23 | Z | 2024-06-24 | 120 | 0 | 60 | F | 150 | 210 |  | 105C/D TA |  | 60
2024-08-23 | 3552 |  | 79272 - 79273 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-06-24 | 60 | 0 | 100 | F | 0 | 190 |  | SAT-4-1-4 |  | 60
2024-08-23 | 3553 |  | 79275 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-06-24 | 70 | 0 | 30 | F | 0 | 100 |  | 114 EA |  | 60
2024-08-23 | 3554 |  | 79277 - 79279 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-23 | Z | 2024-06-24 | 150 | 0 | 0 |  | 130 | 230 |  | TA |  | 60
2024-08-23 | 3555 |  | 79280 - 79282 | A | DONE | 12 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-23 | Z | 2024-06-24 | 220 | 0 | 60 | F | 220 | 340 |  | TA |  | 60
2024-08-23 | 3556 |  | 79283 - 79285 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-23 | Z | 2024-06-24 | 150 | 0 | 50 | F | 160 | 250 |  | TA |  | 60
2024-08-23 | 3557 |  | 79286 - 79288 | A | DONE | 7 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-23 | Z | 2024-06-24 | 160 | 0 | 0 |  | 140 | 210 |  | TA |  | 60
2024-08-23 | 3578 |  | 79344 - 79345 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-08-02 | 60 | 0 | 0 |  | 0 | 120 |  | AHU-4 RA / EC |  | 21
2024-08-22 | 3580 |  | 79347 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-08-08 | 20 | 0 | 90 | F | 0 | 150 |  | 2nd floor |  | 15
2024-08-23 | 3581 |  | 79348 - 79350 | A | DONE | 14 | M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-23 | Z | 2024-08-08 | 220 | 0 | 130 | F | 280 | 420 |  | 2nd TA |  | 15
2024-08-23 | 3582 |  | 67901 - 67904 | A | DONE | 11 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-08-23 | Z | 2024-08-08 | 220 | 0 | 50 | F | 200 | 330 |  | 2nd TA |  | 15
2024-08-22 | 3586 |  | 67905 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-08-08 | 50 | 0 | 0 |  | 0 | 110 |  | 2nd RA main |  | 15
2024-08-23 | 3587 |  | 79369 - 79372 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-08-08 | 170 | 0 | 60 | F | 0 | 290 |  | AHU-4 RA |  | 15
2024-08-23 | 3590 |  | 67907 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-08-14 | 50 | 0 | 0 |  | 0 | 80 |  | SAT-4-2-1 |  | 9
2024-08-21 | 3594 |  | 70587 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-08-23 | Z | 2024-08-19 | 20 | 0 | 0 |  | 0 | 20 |  | EC's |  | 4
2024-08-24 | 553 |  | 66932 - 66934 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 90 | 0 | 0 |  | 0 | 240 |  | Flat flashing |  | 15
2024-08-24 | 557 |  | 66938 | A | DONE | 2 | S |  | UWRF 6230010 | paint | 2024-08-26 | Z | 2024-08-14 | 20 | 0 | 0 |  | 20 | 30 |  | L3-GET-Drops |  | 12
2024-08-23 | 5053 |  | EA-01-SF-1 | A | DONE | 22 | M |  | UWSP ALBERTSON 6230016 | CD , flex | 2024-08-20 | Z | 2024-07-30 | 330 | 0 | 220 | F | 0 | 750 |  |  |  | 21
2024-08-23 | 5059 |  | SA-01-VRF-1-1-1 | A | DONE | 5 | S |  | UWSP ALBERTSON 6230016 |  | 2024-08-20 | Z | 2024-07-30 | 90 | 0 | 30 | F | 0 | 140 |  |  |  | 21
2024-08-20 | 1469 |  | 73060 - 73062 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 | reheat coils , VD | 2024-08-26 | Z | 2024-07-31 | 50 | 0 | 0 |  | 0 | 90 |  | Pec / Ct SA |  | 26
2024-08-20 | 1470 | sp | 73063 , 73066 | A | DONE | 13 | S-M |  | UW-VET MED 6210014 |  | 2024-08-26 | Z | 2024-07-31 | 40 | 280 | 0 |  | 0 | 290 |  | Pec / Ct SA - EA |  | 26
2024-08-20 | 1471 | bth | 73064 - 65 , 73067 | A | DONE | 13 | S-M | alum | UW-VET MED 6210014 |  | 2024-08-26 | Z | 2024-07-31 | 70 | 20 | 220 | F | 0 | 180 |  | Pec / Ct SA - EA |  | 26
2024-08-20 | 1472 |  | 73068 | A | DONE | 8 | S-M |  | UW-VET MED 6210014 |  | 2024-08-19 | Z | 2024-08-05 | 60 | 0 | 140 | F | 0 | 240 |  | 2nd floor SA |  | 14
2024-08-19 | 1473 | sp | 73070 - 73071 | A | DONE | 8 | S-M |  | UW-VET MED 6210014 |  | 2024-08-19 | Z | 2024-08-05 | 50 | 140 | 0 |  | 0 | 200 |  | 2nd floor EA / SA |  | 14
2024-08-19 | 1474 | sp | 73072- 73073 | A | DONE | 7 | S-M |  | UW-VET MED 6210014 |  | 2024-08-19 | Z | 2024-08-05 | 40 | 130 | 0 |  | 0 | 180 |  | 2nd floor SA |  | 14
2024-08-19 | 1475 |  | 73074 | A | DONE | 6 | S-M |  | UW-VET MED 6210014 |  | 2024-08-19 | Z | 2024-08-05 | 110 | 0 | 40 | F | 0 | 170 |  | 2nd floor EA |  | 14
2024-08-24 | 1478 |  | 73014 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-08-26 | Z | 2024-08-12 | 30 | 0 | 0 |  | 0 | 40 |  | L1-E2 |  | 14
2024-08-24 | 1480 |  | 73016 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-08-26 | Z | 2024-08-15 | 50 | 0 | 0 |  | 0 | 90 |  | CB-1547 |  | 11
2024-08-24 | 1488 |  | 73029 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-08-26 | Z | 2024-08-15 | 30 | 0 | 0 |  | 0 | 70 |  | CB-1547 |  | 11
2024-08-21 | 1489 |  | 73075 | A | DONE | 2 | S-M |  | UW-VET MED 6210014 |  | 2024-08-26 | Z | 2024-08-20 | 50 | 0 | 0 |  | 0 | 60 |  | Flatstock |  | 6
2024-08-22 | 1070 |  | 79857 | A | DONE | 2 | S | alum | WAUNAKEE HS 6240013 |  | 2024-08-23 | Z | 2024-08-15 | 20 | 0 | 0 |  | 0 | 20 |  | Drain pan |  | 8
[6 empty] | 1488 | [13 empty] | 51120 |  |  |  | 6220 | 12.17%
WEEK OF 8-26-2024
2024-08-30 | 2239 |  | 80070 | A | DONE | 11 | S-M |  | 121 E. WILSON 6230024 | paint | 2024-08-26 | Z | 2024-07-25 | 140 | 0 | 120 | F | 20 | 260 |  | DOAS-1 / OA-1 |  | 32
2024-08-30 | 3665 |  | 80109 | A | DONE | 3 | S |  | 121 E. WILSON 6230024 |  | 2024-08-26 | Z | 2024-07-31 | 60 | 0 | 0 |  | 0 | 60 |  | 2nd floor west unit taps |  | 26
2024-08-30 | 3666 |  | 80110 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 |  | 2024-08-26 | Z | 2024-07-31 | 90 | 0 | 0 |  | 0 | 100 |  | 2nd floor west unit sliders |  | 26
2024-08-30 | 3667 |  | 80111 | A | DONE | 13 | S-M |  | 121 E. WILSON 6230024 |  | 2024-08-26 | Z | 2024-07-31 | 40 | 0 | 270 | F | 0 | 290 |  | 2nd floor west SA duct |  | 26
2024-08-30 | 3668 |  | 80112 | A | DONE | 6 | S |  | 121 E. WILSON 6230024 | 1" liner | 2024-08-26 | Z | 2024-07-31 | 30 | 0 | 120 | F | 130 | 160 |  | 2nd floor west TA |  | 26
2024-08-30 | 3678 |  | 80128 | A | DONE | 32 | S-M |  | 121 E. WILSON 6230024 |  | 2024-08-26 | Z | 2024-08-07 | 20 | 0 | 770 | F | 0 | 730 |  | 3rd floor West EA |  | 19
2024-08-30 | 3690 |  | Stairwell A-EA 3 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 |  | 2024-08-26 | Z | 2024-08-07 | 90 | 0 | 280 | F | 0 | 420 |  |  |  | 19
2024-08-30 | 3697 |  | 96554 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-08-26 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 50 |  | Caps |  | 14
2024-08-27 | 256 |  | 82224 | A | DONE | 2 | S |  | AYERS SPACE 20008947 | 1" liner | 2024-08-26 | Z | 2024-08-22 | 20 | 0 | 0 |  | 20 | 20 |  | Filter boxes |  | 4
2024-08-30 | 1303 | bth | L7-B-EALP-004 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-08-22 | Z | 2024-07-08 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 45 |  | 2024-08-09
2024-08-29 | 1304 | sp | L7-B-EALP-005 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1305 | sp | L7-B-EALP-006 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 45 |  | 2024-08-09
2024-08-28 | 1306 | sp | L7-B-EALP-007 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 50 | 50 | 20 | F | 20 | 140 |  |  |  | 45 |  | 2024-08-09
2024-08-27 | 1307 | bth | L7-B-EAMP-001 | A | DONE | 7 | S | pt.neal | CDIS 6220028 | paint | 2024-08-22 | Z | 2024-07-08 | 140 | 30 | 0 |  | 20 | 190 |  |  |  | 45 |  | 2024-09-28
2024-08-27 | 1308 | bth | L7-B-EAMP-002 | A | DONE | 10 | S | pt.neal | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 30 | 40 | 160 | F | 0 | 270 |  |  |  | 45 |  | 2024-09-28
2024-08-27 | 1309 | bth | L7-B-EAMP-003 | A | DONE | 9 | S | pt.neal | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 60 | 30 | 130 | F | 0 | 280 |  |  |  | 45 |  | 2024-09-28
2024-08-30 | 1310 |  | L7-B-RAD-001 | A | DONE | 2 | S | neal | CDIS 6220028 | VD | 2024-08-22 | Z | 2024-07-08 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1311 | bth | L7-B-SALP-008 | A | DONE | 6 | S | pt.neal | CDIS 6220028 | paint , 1" liner | 2024-08-22 | Z | 2024-07-08 | 90 | 20 | 20 | F | 50 | 130 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1312 | bth | L7-B-SALP-009 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-08-22 | Z | 2024-07-08 | 50 | 60 | 0 |  | 20 | 120 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1313 | bth | L7-B-SALP-010 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-08-22 | Z | 2024-07-08 | 60 | 60 | 0 |  | 20 | 120 |  |  |  | 45 |  | 2024-08-09
2024-08-29 | 1314 | bth | L7-B-SALP-011 | A | DONE | 6 | S | neal | CDIS 6220028 | 1" liner | 2024-08-22 | Z | 2024-07-08 | 60 | 30 | 40 | F | 20 | 160 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1315 | bth | L7-B-SALP-012 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-08-22 | Z | 2024-07-08 | 60 | 20 | 0 |  | 30 | 80 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1316 |  | L7-B-SALP-013 | A | DONE | 8 | S | neal | CDIS 6220028 | paint , 1" liner | 2024-08-22 | Z | 2024-07-08 | 130 | 0 | 60 | F | 30 | 240 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1317 | bth | L7-B-SALP-014 | A | DONE | 4 | S | pt.neal | CDIS 6220028 | paint , 1" liner | 2024-08-22 | Z | 2024-07-08 | 40 | 50 | 0 |  | 20 | 90 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1318 | bth | L7-B-SALP-015 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-08-22 | Z | 2024-07-08 | 70 | 20 | 50 | F | 30 | 170 |  |  |  | 45 |  | 2024-08-09
2024-08-30 | 1319 | bth | L7-B-SALP-016 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-08-22 | Z | 2024-07-08 | 90 | 20 | 30 | F | 30 | 160 |  |  |  | 45 |  | 2024-08-09
2024-08-27 | 1320 | bth | L7-B-SAMP-001 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 170 | 20 | 160 | F | 0 | 470 |  |  |  | 45 |  | 2024-09-28
2024-08-27 | 1321 | bth | L7-B-SAMP-002 | A | DONE | 11 | S-M |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 30 | 40 | 190 | F | 0 | 350 |  |  |  | 45 |  | 2024-09-28
2024-08-27 | 1322 | bth | L7-B-SAMP-003 | A | DONE | 8 | S |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 90 | 30 | 70 | F | 0 | 250 |  |  |  | 45 |  | 2024-09-28
2024-08-27 | 1323 | bth | L7-B-SAMP-004 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 50 | 70 | 30 | F | 0 | 160 |  |  |  | 45 |  | 2024-09-28
2024-08-27 | 1324 |  | L7-B-SAMP-005 | A | DONE | 7 | S |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 110 | 0 | 50 | F | 0 | 200 |  |  |  | 45 |  | 2024-09-28
2024-08-27 | 1325 | bth | L7-B-SAMP-006 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-08-22 | Z | 2024-07-08 | 70 | 50 | 30 | F | 0 | 150 |  |  |  | 45 |  | 2024-09-28
2024-08-27 | 1326 |  | L7-B-SAMP-007 | A | DONE | 2 | S |  | CDIS 6220028 | VD | 2024-08-22 | Z | 2024-07-08 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 45 |  | 2024-09-28
2024-08-29 | 1372 | bth | L6-A-EALP-049 | A | DONE | 3 | S-M | neal | CDIS 6220028 | paint , 1" liner | 2024-09-09 | Z | 2024-07-17 | 40 | 20 | 0 |  | 20 | 70 |  |  |  | 54 |  | 2024-08-27
2024-08-30 | 1441 | sp | L7-A-SAMP-027 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 37 |  | 2024-09-04
2024-08-26 | 3427 |  | EA-(-10wg)-PH-04 | A | DONE | 27 | L |  | CDIS 6220028 |  | 2024-08-27 | Z | 2024-08-01 | 670 | 0 | 0 |  | 0 | 3170 |  |  |  | 26
2024-08-27 | 3442 |  | 69938 - 69939 | A | DONE | 4 | S-M | neal | CDIS 6220028 |  | 2024-08-22 | Z | 2024-08-08 | 100 | 0 | 0 |  | 50 | 120 |  | 5th floor |  | 14 |  | 2024-09-27
2024-08-27 | 4312 |  | 69941 | A | DONE | 4 | S | pt.neal | CDIS 6220028 | VD , 1" liner | 2024-08-22 | Z | 2024-08-12 | 100 | 0 | 0 |  | 90 | 140 |  | L5-A-SALP-013 |  | 10 |  | 2024-09-27
2024-08-27 | 4316 |  | 61521 | A | DONE | 2 | S-M |  | CDIS 6220028 | bird s | 2024-08-27 | Z | 2024-08-13 | 40 | 0 | 0 |  | 0 | 110 |  | Basement |  | 14 |  | 2024-09-28
2024-08-27 | 4318 |  | 69818 | A | DONE | 10 | S-M |  | CDIS 6220028 | paint | 2024-08-27 | Z | 2024-08-14 | 250 | 0 | 0 |  | 160 | 530 |  | EA plenum PH |  | 13 |  | 2024-09-28
2024-08-30 | 4321 |  | 69665 | L | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-03 | Z | 2024-08-19 | 20 | 0 | 0 |  | 0 | 20 |  | EALP 15 outs |  | 15 |  | 2024-09-05
2024-08-30 | 4327 | bth | L7-A-EALP-036 | A | DONE | 7 | S-M | pt.neal | CDIS 6220028 | paint | 2024-09-04 | Z | 2024-08-20 | 70 | 50 | 50 |  | 0 | 200 |  |  |  | 15
2024-08-30 | 4342 |  | L7-A-TAD-001 | A | DONE | 2 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-04 | Z | 2024-08-20 | 30 | 0 | 0 |  | 0 | 30 |  |  |  | 15
2024-08-26 | 4343 |  | 69928 | A | DONE | 2 | S | neal | CDIS 6220028 | paint | 2024-08-26 | Z | 2024-08-21 | 20 | 0 | 0 |  | 20 | 40 |  | 5TH FLOOR |  | 5
2024-08-30 | 4345 |  | 69944 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-09-03 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 20 |  | 5th floor |  | 12 |  | 2024-09-05
2024-08-30 | 255 |  | 79796 , 79798 | A | DONE | 3 | S-M |  | COMPASS HP 4230088 | oval accuflange | 2024-09-03 | Z | 2024-08-22 | 70 | 0 | 0 |  | 0 | 80 |  | VAV-5 / EA |  | 12
2024-08-26 | 257 |  | 78742 | A | DONE | 2 | S |  | COTTAGE GROVE ES 4240033 |  | 2024-08-27 | Z | 2024-08-26 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2024-08-29 | 2577 | sp | L2-EAD-Z2-0014 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-26 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 2
2024-08-29 | 2578 |  | L2-EAD-Z2-0015 | A | DONE | 16 | M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-26 | 130 | 0 | 250 |  | 0 | 580 |  |  |  | 2
2024-08-29 | 2597 | sp | L2-SAMP-Z1-0003 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 20 | 80 | 0 |  | 0 | 90 |  |  |  | 14
2024-08-29 | 2598 | bth | L2-SAMP-Z1-0004 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 50 | 30 | 20 | F | 0 | 90 |  |  |  | 14
2024-08-29 | 2599 | bth | L2-SAMP-Z1-0005 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 90 | 20 | 60 | F | 0 | 210 |  |  |  | 14
2024-08-29 | 4000 | bth | L2-SAMP-Z1-0006 | A | DONE | 6 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 70 | 20 | 60 | F | 0 | 180 |  |  |  | 14
2024-08-29 | 4001 |  | L2-SAMP-Z1-0007 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 60 | 0 | 100 | F | 0 | 210 |  |  |  | 14
2024-08-28 | 4002 |  | L2-SAMP-Z1-0008 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 80 | 0 | 40 | F | 0 | 150 |  |  |  | 14
2024-08-29 | 4003 | bth | L2-RAD-Z1-0002 | A | DONE | 9 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 20 | 200 | 0 |  | 0 | 250 |  |  |  | 14
2024-08-29 | 4004 |  | L2-TAD-Z1-0001 | A | DONE | 4 | S |  | EXACT TL-5 6240014 | 1" liner | 2024-08-28 | Z | 2024-08-14 | 90 | 0 | 0 |  | 60 | 110 |  |  |  | 14
2024-08-29 | 4005 |  | L2-SALP-Z1-0003 | A | DONE | 22 | M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 290 | 0 | 240 | F | 0 | 690 |  |  |  | 14
2024-08-29 | 4006 | bth | L2-SALP-Z1-0004 | A | DONE | 8 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 90 | 20 | 70 | F | 0 | 190 |  |  |  | 14
2024-08-29 | 4007 |  | L2-SALP-Z1-0005 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 | flex | 2024-08-28 | Z | 2024-08-14 | 220 | 0 | 70 | F | 0 | 340 |  |  |  | 14
2024-08-29 | 4008 | bth | L2-SALP-Z1-0006 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 50 | 140 | 110 | F | 0 | 360 |  |  |  | 14
2024-08-29 | 4009 |  | L2-SALP-Z1-0007 | A | DONE | 16 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 290 | 0 | 110 | F | 0 | 480 |  |  |  | 14
2024-08-29 | 4010 | bth | L2-SALP-Z1-0008 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 110 | 120 | 60 | F | 0 | 340 |  |  |  | 14
2024-08-28 | 4011 |  | L2-SALP-Z1-0009 | A | DONE | 16 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 220 | 0 | 170 | F | 0 | 550 |  |  |  | 14
2024-08-29 | 4012 | bth | L2-SALP-Z1-0010 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 14
2024-08-29 | 4013 | sp | L2-EAD-Z1-0003 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 14
2024-08-29 | 4014 | bth | L2-EAD-Z1-0004 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 30 | 140 | 0 |  | 0 | 200 |  |  |  | 14
2024-08-29 | 4015 | bth | L2-EAD-Z1-0005 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 14
2024-08-29 | 4016 | bth | L2-EAD-Z1-0006 | A | DONE | 10 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 80 | 20 | 140 | F | 0 | 290 |  |  |  | 14
2024-08-29 | 4017 | bth | L2-EAD-Z1-0007 | A | DONE | 14 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 290 | 50 | 0 |  | 0 | 400 |  |  |  | 14
2024-08-29 | 4018 | sp | L2-EAD-Z1-0008 | A | DONE | 6 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 40 | 110 | 0 |  | 0 | 170 |  |  |  | 14
2024-08-29 | 4019 |  | L2-EAD-Z1-0009 | A | DONE | 14 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 250 | 0 | 80 | F | 0 | 470 |  |  |  | 14
2024-08-29 | 4020 | bth | L2-EAD-Z1-0010 | A | DONE | 11 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 220 | 20 | 20 | F | 0 | 280 |  |  |  | 14
2024-08-29 | 4021 | sp | L2-EAD-Z1-0011 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-14 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 14
2024-08-28 | 4023 |  | 79006 | A | DONE | 4 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-22 | 90 | 0 | 0 |  | 0 | 180 |  | EA |  | 6
2024-08-28 | 4024 |  | 79051 | A | DONE | 6 | S-M |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-22 | 130 | 0 | 0 |  | 0 | 230 |  | Zone 1 outs |  | 6
2024-08-28 | 4025 |  | 79052 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 20 |  | L2-L1 SALP outs |  | 6
2024-08-30 | 4022 |  | 79007 | A | DONE | 2 | S |  | EXACT-BIOSAFE 6230005 |  | 2024-08-26 | Z | 2024-08-21 | 20 | 0 | 0 |  | 0 | 20 |  | TAP |  | 5
2024-08-27 | 727 |  | 80901 - 80902 | A | DONE | 10 | S-M |  | HILLDALE 6240003 | flex | 2024-08-26 | Z | 2024-08-08 | 160 | 0 | 90 | F | 0 | 290 |  | EF-2 inline |  | 18
2024-08-28 | 729 |  | 80318 | A | DONE | 5 | S |  | HILLDALE 6240003 |  | 2024-08-29 | Z | 2024-08-27 | 20 | 0 | 90 | F | 0 | 150 |  | RTU-1 RA |  | 2
2024-08-30 | 731 |  | 80850 | A | DONE | 2 | S |  | HILLDALE 6240003 |  | 2024-09-04 | Z | 2024-08-29 | 20 | 0 | 0 |  | 0 | 20 |  | EF-2 IN LINE |  | 6
2024-08-28 | 730 |  | 80319 | A | DONE | 6 | S |  | HILLLDALE 6240003 |  | 2024-08-29 | Z | 2024-08-28 | 50 | 0 | 90 |  | 0 | 190 |  | RTU-1 outs |  | 1
2024-08-27 | 252 |  | 66704 - 66705 | A | DONE | 7 | S-M |  | HOLY WISDOM 6220019 |  | 2024-08-28 | Z | 2024-08-22 | 170 | 0 | 0 |  | 0 | 180 |  | BCU-3 |  | 6
2024-08-27 | 253 |  | 66708 - 66709 | A | DONE | 5 | S-M |  | HOLY WISDOM 6220019 |  | 2024-08-28 | Z | 2024-08-22 | 110 | 0 | 0 |  | 0 | 140 |  | BCU-6 |  | 6
2024-08-27 | 254 |  | 66710 | A | DONE | 2 | S |  | HOLY WISDOM 6220019 |  | 2024-08-28 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 20 |  | Condensat pump |  | 6
2024-08-29 | 260 |  | 66707 | A | DONE | 3 | S-M |  | HOLY WISDOM 6220019 |  | 2024-08-28 | Z | 2024-08-28 | 70 | 0 | 0 |  | 0 | 70 |  | BCU-5 |  | 0
2024-08-29 | 1907 |  | 62191 | A | DONE | 2 | S-M |  | JPC OFFICE 6240002 | 1" DB | 2024-09-03 | Z | 2024-08-20 | 50 | 0 | 0 |  | 20 | 100 |  | Curb adapt. |  | 14
2024-08-28 | 1908 |  | 62192 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-09-03 | Z | 2024-08-20 | 40 | 0 | 0 |  | 0 | 50 |  | Roof flashing |  | 14
2024-08-30 | 1911 |  | 62193 | A | DONE | 14 | S-M |  | JPC OFFICE 6240002 | flex , 1" liner | 2024-09-03 | Z | 2024-08-22 | 290 | 0 | 50 | F | 250 | 440 |  | RTU RA |  | 12
2024-08-30 | 1912 | bth | 62194 , 62196 - 97 | A | DONE | 20 | M |  | JPC OFFICE 6240002 | flex , 1" liner | 2024-09-03 | Z | 2024-08-22 | 250 | 230 | 0 |  | 30 | 550 |  | RTU-2 SA |  | 12
2024-08-30 | 1913 |  | 62400 | A | DONE | 7 | S-M |  | JPC OFFICE 6240002 | 1" liner | 2024-09-03 | Z | 2024-08-22 | 170 | 0 | 0 |  | 90 | 320 |  | Misc |  | 12
2024-08-30 | 1914 |  | 82404 | A | DONE | 5 | S |  | JPC OFFICE 6240002 | 1"liner | 2024-09-04 | Z | 2024-08-29 | 100 | 0 | 0 |  | 20 | 100 |  | vav outs |  | 6
2024-08-30 | 1915 |  | 82405 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-09-03 | Z | 2024-08-29 | 50 | 0 | 0 |  | 0 | 50 |  | EF-1 |  | 5
2024-08-28 | 3466 |  | 70588 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 |  | 2024-08-28 | Z | 2024-08-28 | 30 | 0 | 0 |  | 0 | 60 |  | Angle |  | 0
2024-08-30 | 2365 |  | 80314 | A | DONE | 3 | S |  | MENDOTA FOODS 6220027 | 1" liner | 2024-09-03 | Z | 2024-08-22 | 60 | 0 | 0 |  | 40 | 80 |  | Basement hard ties |  | 12
2024-08-30 | 2366 |  | 80315 - 80316 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | bird s. | 2024-09-03 | Z | 2024-08-22 | 50 | 0 | 0 |  | 0 | 60 |  | EF-2 / SF-2 |  | 12
2024-08-26 | 3107 |  | 79629 - 79631 | A | DONE | 26 | S-M |  | PECATONICA 6240005 | 1" liner | 2024-08-26 | Z | 2024-05-24 | 340 | 0 | 310 | F | 480 | 940 |  | Gym RA |  | 94
2024-08-26 | 3108 |  | 79632 | A | DONE | 4 | S |  | PECATONICA 6240005 | 2" liner | 2024-08-26 | Z | 2024-05-24 | 40 | 0 | 60 | F | 80 | 120 |  | Gym office SA |  | 94
2024-08-27 | 1623 |  | 62711 | A | DONE | 2 | S |  | PROMEGA CMC 2240038 | flex | 2024-08-28 | Z | 2024-08-27 | 30 | 0 | 0 |  | 0 | 50 |  | Roof tie ins |  | 1
2024-08-29 | 1624 |  | 62713 | A | DONE | 3 | S | pt.ss | PROMEGA CMC 2240038 |  | 2024-09-03 | Z | 2024-08-28 | 20 | 20 | 0 |  | 0 | 40 |  | Misc |  | 6
2024-08-26 | 2382 |  | 62710 | A | DONE | 2 | S | ss | PROMEGA CMC 2240038 |  | 2024-08-27 | Z | 2024-08-26 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2024-08-28 | 2380 |  | 56339 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-08-26 | Z | 2024-08-22 | 30 | 0 | 0 |  | 0 | 70 |  | Misc |  | 4
2024-08-30 | 2381 | w | 62708 | F | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-11 | Z | 2024-08-26 | 20 | 0 | 0 |  | 0 | 30 |  | Floor Sleeve |  | 16
2024-08-27 | 4768 |  | 78774 | A | DONE | 2 | S | neal | ROCK CO. JAIL 6220018 |  | 2024-08-28 | Z | 2024-08-14 | 20 | 0 | 0 |  | 0 | 40 |  | Max pipe cover |  | 14
2024-08-27 | 4769 |  | 61168 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-08-28 | Z | 2024-08-23 | 20 | 0 | 0 |  | 0 | 20 |  | Jail |  | 5
2024-08-27 | 4770 |  | 33243 | A | DONE | 2 | S |  | ROCK CO. JAIL 8220022 | d.plate | 2024-08-27 | Z | 2024-08-27 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-08-26 | 4268 | sp | 79918 | A | DONE | 4 | S-M |  | ST.BERNARD 2230056 | bird s | 2024-08-27 | Z | 2024-08-13 | 20 | 20 | 0 |  | 0 | 50 |  | Goosenecks |  | 14
2024-08-27 | 4270 |  | 80026 - 80027 | A | DONE | 5 | S-M |  | ST.BERNARD 2230056 |  | 2024-08-29 | Z | 2024-08-15 | 120 | 0 | 0 |  | 0 | 120 |  | F-6 RA |  | 14
2024-08-27 | 4271 | bth | 80031 | A | DONE | 12 | S-M |  | ST.BERNARD 2230056 |  | 2024-08-29 | Z | 2024-08-15 | 40 | 240 | 0 |  | 0 | 260 |  | Basement |  | 14
2024-08-30 | 4272 | bth | 80033 - 80034 | A | DONE | 7 | S-M |  | ST.BERNARD 2230056 |  | 2024-09-03 | Z | 2024-08-16 | 140 | 0 | 30 | F | 0 | 150 |  | Basement RA |  | 18
2024-08-30 | 4273 |  | 80035 - 80036 | A | DONE | 3 | S-M |  | ST.BERNARD 2230056 |  | 2024-09-03 | Z | 2024-08-16 | 60 | 0 | 0 |  | 0 | 70 |  | Basement RA |  | 18
2024-08-26 | 4269 |  | 79919 | A | DONE | 2 | S |  | ST.BERNARD 6230023 |  | 2024-08-27 | Z | 2024-08-13 | 20 | 0 | 0 |  | 20 | 50 |  | Offset |  | 14
2024-08-27 | 247 |  | 79650 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-08-26 | Z | 2024-08-14 | 40 | 0 | 0 |  | 0 | 40 |  | RAT 1330 |  | 12
2024-08-28 | 258 |  | 79680 | A | DONE | 3 | S |  | UPLAND HILLS 2240008 |  | 2024-09-03 | Z | 2024-08-26 | 40 | 0 | 30 | F | 0 | 80 |  | RAT 1330 LPSA |  | 8
2024-08-27 | 4554 | w | 72554 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2024-08-27 | Z | 2024-08-23 | 30 | 0 | 0 |  | 0 | 70 |  | Sleeves |  | 4
2024-08-27 | 4555 |  | 2906 | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2024-08-28 | Z | 2024-08-26 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 2
2024-08-28 | 553 |  | 66932 - 66934 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 90 | 0 | 0 |  | 0 | 240 |  | Flat flashing |  | 15
2024-08-27 | 554 |  | 66935 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 30 | 20 | 0 |  | 0 | 50 |  | L2Z1-A-FEV-3-2-4 |  | 15
2024-08-28 | 554 |  | 66935 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 30 | 20 | 0 |  | 0 | 50 |  | L2Z1-A-FEV-3-2-4 |  | 15
2024-08-26 | 555 |  | 66936 | A | DONE | 2 | S | alum | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 20 | 30 | 0 |  | 0 | 30 |  | L1Z1-A dryer vent |  | 15
2024-08-28 | 555 |  | 66936 | A | DONE | 2 | S | alum | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 20 | 30 | 0 |  | 0 | 30 |  | L1Z1-A dryer vent |  | 15
2024-08-26 | 556 |  | 66937 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 40 | 0 | 0 |  | 30 | 60 |  | Misc |  | 15
2024-08-28 | 556 |  | 66937 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 40 | 0 | 0 |  | 30 | 60 |  | Misc |  | 15
2024-08-26 | 558 |  | 66939 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-15 | 20 | 0 | 0 |  | 0 | 20 |  | FEV-3-3-25 |  | 13
2024-08-28 | 558 |  | 66939 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-15 | 20 | 0 | 0 |  | 0 | 20 |  | FEV-3-3-25 |  | 13
2024-08-27 | 900 |  | L1Z1-SAT-1-1-5 | A | DONE | 2 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 49
2024-08-27 | 901 |  | L1Z1-SAT-1-1-6 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 49
2024-08-28 | 902 | bth | L1Z1-SAT-1-1-7 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 60 | 0 | 0 |  | 20 | 70 |  |  |  | 49
2024-08-28 | 903 | bth | L1Z1-SAT-1-1-8 | A | DONE | 20 | M |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 190 | 50 | 250 | F | 40 | 580 |  |  |  | 49
2024-08-28 | 904 | bth | L1Z1-SAT-1-1-9 | A | DONE | 11 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 130 | 90 | 40 | F | 40 | 260 |  |  |  | 49
2024-08-28 | 905 | bth | L1Z1-SAT-1-1-10 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 50 | 40 | 0 |  | 30 | 90 |  |  |  | 49
2024-08-28 | 906 | bth | L1Z1-SAT-1-1-11 | A | DONE | 10 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 90 | 80 | 70 | F | 50 | 270 |  |  |  | 49
2024-08-28 | 907 | bth | L1Z1-SAT-1-1-46 | A | DONE | 9 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 130 | 20 | 60 | F | 50 | 250 |  |  |  | 49
2024-08-28 | 908 | bth | L1Z1-SAT-1-1-47 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 50 | 20 | 0 |  | 30 | 80 |  |  |  | 49
2024-08-28 | 909 | bth | L1Z1-SAT-1-1-48 | A | DONE | 9 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 130 | 20 | 60 | F | 80 | 260 |  |  |  | 49
2024-08-28 | 910 | bth | L1Z1-SAT-1-1-49 | A | DONE | 11 | S-M |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 150 | 80 | 30 | F | 40 | 280 |  |  |  | 49
2024-08-28 | 911 | bth | L1Z1-SAT-1-1-50 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 80 | 30 | 0 |  | 20 | 110 |  |  |  | 49
2024-08-28 | 912 | bth | L1Z1-SAT-1-1-51 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 60 | 20 | 0 |  | 40 | 80 |  |  |  | 49
2024-08-28 | 913 | bth | L1Z1-SAT-1-1-52 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 30 | 20 | 0 |  | 20 | 50 |  |  |  | 49
2024-08-28 | 914 | bth | L1Z1-SAT-1-1-53 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 49
2024-08-28 | 915 |  | L1Z1-SAT-1-1-54 | A | DONE | 3 | S | neal | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 49
2024-08-28 | 916 |  | L1Z1-SAT-1-1-55 | A | DONE | 3 | S | neal | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 49
2024-08-28 | 917 | bth | L1Z1-SAT-1-1-56 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 30 | 20 | 0 |  | 20 | 60 |  |  |  | 49
2024-08-28 | 918 |  | L1Z1-SAT-1-1-61 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 70 | 0 | 0 |  | 20 | 80 |  |  |  | 49
2024-08-28 | 919 | bth | L1Z1-GET-1-1-1 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 44
2024-08-28 | 920 | bth | L1Z1-GET-1-1-2 | A | DONE | 4 | S | neal | UWRF 6230010 | VD's | 2024-08-28 | Z | 2024-07-15 | 50 | 30 | 0 |  | 0 | 90 |  |  |  | 44
2024-08-27 | 921 | sp | L1Z1-GET-1-1-3 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 44
2024-08-27 | 922 | sp | L1Z1-GET-1-1-4 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 44
2024-08-27 | 923 | sp | L1Z1-GET-1-1-5 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 44
2024-08-27 | 924 | sp | L1Z1-GET-1-1-6 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 44
2024-08-27 | 925 | sp | L1Z1-GET-1-1-7 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 44
2024-08-28 | 926 | bth | L1Z1-GET-1-1-8 | A | DONE | 10 | S-M |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 170 | 50 | 30 | F | 0 | 310 |  |  |  | 44
2024-08-28 | 927 | bth | L1Z1-GET-1-1-9 | A | DONE | 7 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 110 | 50 | 0 |  | 0 | 270 |  |  |  | 44
2024-08-27 | 928 | sp | L1Z1-GET-1-1-10 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 40 | 50 | 0 |  | 0 | 90 |  |  |  | 44
2024-08-28 | 929 | bth | L1Z1-GET-1-1-11 | A | DONE | 10 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 120 | 60 | 70 | F | 0 | 280 |  |  |  | 44
2024-08-28 | 930 | bth | L1Z1-GET-1-1-36 | A | DONE | 6 | S |  | UWRF 6230010 | VD's | 2024-08-28 | Z | 2024-07-15 | 120 | 20 | 0 |  | 0 | 160 |  |  |  | 44
2024-08-27 | 931 | sp | L1Z1-GET-1-1-37 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 44
2024-08-28 | 932 | bth | L1Z1-GET-1-1-38 | A | DONE | 8 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 180 | 20 | 0 |  | 0 | 230 |  |  |  | 44
2024-08-28 | 933 | sp | L1Z1-GET-1-1-39 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 44
2024-08-28 | 934 | sp | L1Z1-GET-1-1-40 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 44
2024-08-27 | 935 | sp | L1Z1-GET-1-1-41 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 44
2024-08-28 | 936 | sp | L1Z1-GET-1-1-42 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 44
2024-08-27 | 937 | sp | L1Z1-GET-1-1-43 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 44
2024-08-28 | 938 | bth | L1Z1-GET-1-1-44 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 50 | 20 | 0 |  | 0 | 70 |  |  |  | 44
2024-08-28 | 939 | bth | L1Z1-GET-1-1-45 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-15 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 44
2024-08-26 | 942 | sp | L1Z1-FEV-3-1-1 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 42
2024-08-26 | 943 | sp | L1Z1-FEV-3-1-2 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 0 | 30 | 0 |  | 0 | 40 |  |  |  | 42
2024-08-27 | 944 | bth | L1Z1-FEV-3-1-3 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 42
2024-08-26 | 945 | sp | L1Z1-FEV-3-1-4 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 42
2024-08-26 | 946 | sp | L1Z1-FEV-3-1-15 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 42
2024-08-26 | 947 | sp | L1Z1-FEV-3-1-16 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 42
2024-08-26 | 948 | sp | L1Z1-FEV-3-1-17 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 42
2024-08-26 | 949 | sp | L1Z1-FEV-3-1-18 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 42
2024-08-26 | 950 | sp | L1Z1-FEV-3-1-19 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 42
2024-08-27 | 951 | bth | L1Z1-FEV-3-1-20 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 30 | 20 | 0 |  | 0 | 60 |  |  |  | 42
2024-08-26 | 952 | sp | L1Z1-FEV-3-1-21 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 42
2024-08-26 | 953 | sp | L1Z1-FEV-3-1-22 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 42
2024-08-27 | 954 | sp | L1Z1-FEV-3-1-23 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 60 | 0 |  | 0 | 100 |  |  |  | 42
2024-08-26 | 955 | sp | L1Z1-FEV-3-1-24 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 42
2024-08-27 | 956 | sp | L1Z1-FEV-3-1-25 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 42
2024-08-27 | 957 | sp | L1Z1-FEV-3-1-26 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-08-28 | Z | 2024-07-17 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 42
2024-08-29 | 4246 |  | L1Z1-SAT-1-1-1 | A | DONE | 3 | S | neal | UWRF 6230010 | VD , 1" liner | 2024-08-28 | Z | 2024-07-10 | 60 | 0 | 0 |  | 30 | 80 |  |  |  | 49
2024-08-27 | 4247 |  | L1Z1-SAT-1-1-2 | A | DONE | 2 | S | neal | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 49
2024-08-27 | 4248 |  | L1Z1-SAT-1-1-3 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 20 | 0 | 0 |  | 20 | 40 |  |  |  | 49
2024-08-27 | 4249 |  | L1Z1-SAT-1-1-4 | A | DONE | 2 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-08-28 | Z | 2024-07-10 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 49
2024-08-27 | r4006 |  | L3Z1-SAT-1-3-6 | A | DONE | 2 | S | alum | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 30 | 0 | 0 |  | 0 | 30 |  | remake to alum |  | 15
2024-08-26 | r4163 |  | L3Z1-GET-1-3-7 | A | DONE | 3 | S | alum | UWRF 6230010 |  | 2024-08-28 | Z | 2024-08-13 | 30 | 40 | 0 |  | 0 | 30 |  | remake to alum |  | 15
2024-08-26 | 5054 |  | EA-01-SF-2 | A | DONE | 8 | S-M |  | UWSP ALBERTSON 6230016 | CD , flex | 2024-08-20 | Z | 2024-07-30 | 190 | 0 | 0 |  | 0 | 380 |  |  |  | 21
2024-08-26 | 5055 |  | EA-01-SF-3 | A | DONE | 19 | M |  | UWSP ALBERTSON 6230016 | VD | 2024-08-20 | Z | 2024-07-30 | 400 | 0 | 70 | F | 0 | 560 |  |  |  | 21
2024-08-26 | 5056 |  | OA-01-SF-1 | A | DONE | 8 | S |  | UWSP ALBERTSON 6230016 | CD , flex | 2024-08-20 | Z | 2024-07-30 | 150 | 0 | 40 | F | 0 | 230 |  |  |  | 21
2024-08-26 | 5057 |  | OA-01-SF-2 | A | DONE | 22 | M |  | UWSP ALBERTSON 6230016 | CD , VD , flex | 2024-08-20 | Z | 2024-07-30 | 430 | 0 | 100 | F | 0 | 680 |  |  |  | 21
2024-08-26 | 5058 |  | RA-01-VRF-1-1-1 | A | DONE | 3 | S |  | UWSP ALBERTSON 6230016 | flex | 2024-08-20 | Z | 2024-07-30 | 60 | 0 | 0 |  | 0 | 80 |  |  |  | 21
2024-08-29 | 1487 |  | 73028 | A | DONE | 5 | S-M | ss | UW-VET MED 6210014 |  | 2024-09-03 | Z | 2024-08-15 | 30 | 80 | 0 |  | 0 | 100 |  | 10-C |  | 19
2024-08-26 | 1490 |  | 73030 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-08-26 | Z | 2024-08-20 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor |  | 6
2024-08-30 | 261 |  | 78744 | A | DONE | 2 | S |  | WAUNAKEE ADMIN 10057356 |  | 2024-09-03 | Z | 2024-08-29 | 20 | 0 | 0 |  | 0 | 30 |  | F-4 |  | 5
2024-08-30 | 1073 |  | 68121 | A | DONE | 2 | S | neal | WAUNAKEE HS 6240013 |  | 2024-09-03 | Z | 2024-08-30 | 20 | 0 | 0 |  | 0 | 20 |  | HANGER |  | 4
2024-08-27 | 1071 |  | 79802 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 |  | 2024-08-29 | Z | 2024-08-26 | 20 | 0 | 0 |  | 0 | 20 |  | PRV-2 |  | 3
2024-08-28 | 1072 |  | 70550 | A | DONE | 2 | S |  | WAUNAKEE HS 6240013 |  | 2024-08-28 | Z | 2024-08-28 | 20 | 0 | 0 |  | 0 | 20 |  | End cap |  | 0
[6 empty] | 1074 | [13 empty] | 31710 |  |  |  | 4960 | 15.64%
WEEK OF 9-3-2024
2024-09-05 | 2240 |  | 80076 | A | DONE | 11 | S-M |  | 121 E. WILSON 6230024 | paint | 2024-09-03 | Z | 2024-07-25 | 140 | 0 | 120 | F | 20 | 250 |  | DOAS-2 / OA-1 |  | 40
2024-09-06 | 3653 |  | 80083 , 80090 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-09 | Z | 2024-07-30 | 50 | 0 | 340 | F | 0 | 400 |  | EF-1,2 , EA-2 |  | 41
2024-09-03 | 3664 |  | 80108 | A | DONE | 10 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-08-26 | Z | 2024-07-31 | 240 | 0 | 0 |  | 190 | 230 |  | 2nd floor west SA plenums |  | 26
2024-09-03 | 3669 |  | 79572 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-08-26 | Z | 2024-07-31 | 40 | 0 | 0 |  | 20 | 40 |  | HP-200C |  | 26
2024-09-05 | 3671 |  | 80115 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-09-05 | Z | 2024-07-31 | 190 | 0 | 0 |  | 170 | 220 |  | 2nd floor east SA plenums |  | 36
2024-09-05 | 3672 |  | 80116 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-09-05 | Z | 2024-07-31 | 50 | 0 | 0 |  | 0 | 70 |  | 2nd floor east unit taps |  | 36
2024-09-05 | 3673 |  | 80117 | A | DONE | 3 | S |  | 121 E. WILSON 6230024 |  | 2024-09-05 | Z | 2024-07-31 | 70 | 0 | 0 |  | 0 | 70 |  | 2nd floor east unit sliders |  | 36
2024-09-05 | 3674 |  | 80118 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-05 | Z | 2024-07-31 | 40 | 0 | 160 | F | 0 | 190 |  | 2nd floor east SA duct |  | 36
2024-09-03 | 3677 |  | 80126 - 80127 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2024-08-26 | Z | 2024-08-07 | 100 | 0 | 0 |  | 0 | 120 |  | 3rd floor West EA |  | 19
2024-09-05 | 3679 |  | 80136 - 80137 | A | DONE | 35 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-03 | Z | 2024-08-07 | 120 | 0 | 740 | F | 0 | 790 |  | 3rd floor East EA |  | 27
2024-09-04 | 3698 |  | 96554.1 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-09-03 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 50 |  | Caps |  | 22
2024-09-04 | 3918 |  | 81906 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-08-30 | Z | 2024-08-16 | 20 | 0 | 20 | F | 0 | 30 |  | 2nd floor West EA |  | 14
2024-09-05 | 3919 |  | 81907 - 81908 | A | DONE | 4 | S |  | 121 E. WILSON 6230024 |  | 2024-09-05 | Z | 2024-08-23 | 30 | 0 | 50 | F | 0 | 80 |  | 2E-EA South / North |  | 13
2024-09-05 | 3920 |  | 81909 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 | 1" liner | 2024-09-05 | Z | 2024-08-26 | 110 | 0 | 170 | F | 230 | 270 |  | Vestibule 100 TA |  | 10
2024-09-06 | 750 |  | 80206 - 80208 | A | DONE | 31 | M |  | BMH AHU-9 6240001 |  | 2024-09-09 | Z | 2024-08-26 | 330 | 0 | 460 | F | 0 | 1130 |  | Loading dock SA HP |  | 14 |  |  |  |  | 2024-09-09
2024-09-06 | 751 | sp | 80209 | A | DONE | 5 | S-M |  | BMH AHU-9 6240001 |  | 2024-09-09 | Z | 2024-08-26 | 20 | 120 | 0 |  | 0 | 60 |  | Loading dock SA HP |  | 14 |  |  |  |  | 2024-09-09
2024-09-06 | 1369 | bth | L6-A-EALP-039 | A | DONE | 4 | S-M | pt.neal | CDIS 6220028 |  | 2024-09-09 | Z | 2024-07-17 | 70 | 30 | 0 |  | 0 | 120 |  |  |  | 54 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-06 | 1370 | sp | L6-A-EALP-047 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-09-09 | Z | 2024-07-17 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 54 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-06 | 1371 |  | L6-A-EALP-048 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-09-09 | Z | 2024-07-17 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 54 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-06 | 1373 | bth | L6-A-EALP-050 | A | DONE | 5 | S-M | neal | CDIS 6220028 | paint , 1" liner | 2024-09-09 | Z | 2024-07-17 | 90 | 20 | 0 |  | 50 | 110 |  |  |  | 54 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-06 | 1374 | sp | L6-A-EALP-051 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-09-09 | Z | 2024-07-17 | 30 | 60 | 0 |  | 0 | 90 |  |  |  | 54 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-06 | 1375 | sp | L6-A-EALP-052 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-09-09 | Z | 2024-07-17 | 20 | 70 | 0 |  | 0 | 80 |  |  |  | 54 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-05 | 1376 | sp | L6-A-EALP-053 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-09-06 | Z | 2024-07-17 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 51 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-03 | 1404 | bth | L7-A-EAMP-014 | A | DONE | 18 | S-M | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 130 | 70 | 240 | F | 0 | 690 |  |  |  | 37 |  | 2024-09-04
2024-09-03 | 1405 | bth | L7-A-EAMP-015 | A | DONE | 22 | M | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 140 | 60 | 330 | F | 0 | 870 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1406 |  | L7-A-EAMP-016 | A | DONE | 16 | S-M | pt.neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 170 | 0 | 220 | F | 0 | 550 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1407 | bth | L7-A-EAMP-017 | A | DONE | 15 | S-M | pt.neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 200 | 50 | 120 | F | 0 | 510 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1408 | bth | L7-A-EAMP-018 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 40 | 90 | 0 |  | 0 | 150 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1409 | bth | L7-A-EAMP-019 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 80 | 20 | 80 | F | 0 | 200 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1410 | bth | L7-A-EAMP-020 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 50 | 100 | 50 | F | 0 | 200 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1411 | bth | L7-A-EAMP-021 | A | DONE | 27 | M | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 320 | 20 | 330 | F | 0 | 1100 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1412 | bth | L7-A-EAMP-022 | A | DONE | 17 | S-M | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 400 | 20 | 0 |  | 0 | 620 |  |  |  | 37 |  | 2024-09-04
2024-09-03 | 1413 | sp | L7-A-EAMP-023 | A | DONE | 5 | S-M | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 20 | 100 | 0 |  | 0 | 130 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1414 | bth | L7-A-EAMP-024 | A | DONE | 12 | S-M | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 70 | 160 | 70 | F | 0 | 370 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1415 | bth | L7-A-EAMP-025 | A | DONE | 33 | M | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 130 | 40 | 650 | F | 0 | 1790 |  |  |  | 37 |  | 2024-09-04
2024-09-05 | 1416 | bth | L7-A-RAD-002 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 37 | 2024-09-04
2024-09-04 | 1438 | bth | L7-A-SAMP-024 | A | DONE | 31 | M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 240 | 20 | 500 | F | 0 | 1310 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1439 | bth | L7-A-SAMP-025 | A | DONE | 25 | S-M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 40 | 140 | 430 | F | 0 | 910 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1440 | bth | L7-A-SAMP-026 | A | DONE | 32 | S-M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 430 | 50 | 310 | F | 0 | 1270 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1442 | bth | L7-A-SAMP-028 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 150 | 40 | 90 | F | 0 | 310 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1443 |  | L7-A-SAMP-029 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 80 | 0 | 220 | F | 0 | 490 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1444 | bth | L7-A-SAMP-030 | A | DONE | 18 | S-M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 60 | 90 | 280 | F | 0 | 560 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1445 | bth | L7-A-SAMP-031 | A | DONE | 30 | M-L |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 150 | 30 | 560 | F | 0 | 1630 |  |  |  | 37 |  | 2024-09-04
2024-09-05 | 1446 |  | L7-A-SAMP-032 | A | DONE | 21 | M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 210 | 0 | 310 | F | 0 | 730 |  |  |  | 37 | 2024-09-04
2024-09-04 | 1447 | bth | L7-A-SAMP-033 | A | DONE | 8 | S-M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 120 | 20 | 40 | F | 0 | 220 |  |  |  | 37 |  | 2024-09-04
2024-09-04 | 1448 | bth | L7-A-SAMP-034 | A | DONE | 15 | S-M |  | CDIS 6220028 |  | 2024-08-29 | Z | 2024-07-23 | 100 | 30 | 240 | F | 0 | 450 |  |  |  | 37 |  | 2024-09-04
2024-09-05 | 4313 |  | SA-(10wg)-PH-02 | A | DONE | 39 | L |  | CDIS 6220028 |  | 2024-09-03 | Z | 2024-08-15 | 970 | 0 | 0 |  | 0 | 2970 |  |  |  | 19 | 2024-09-05
2024-09-03 | 4317 |  | 69942 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-09-03 | Z | 2024-08-14 | 20 | 0 | 0 |  | 0 | 20 |  | 5th floor |  | 20 |  | 2024-09-05
2024-09-05 | 4319 |  | 69820 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-09-03 | Z | 2024-08-19 | 140 | 0 | 0 |  | 0 | 330 |  | PH Flashing |  | 15 | 2024-09-05
2024-09-03 | 4320 |  | 69663 - 64 , 69666 | A | DONE | 4 | S-M | neal | CDIS 6220028 |  | 2024-09-03 | Z | 2024-08-19 | 90 | 0 | 0 |  | 0 | 130 |  | Rm 6544 CB |  | 15 |  | 2024-09-05
2024-09-04 | 4355 |  | 61317 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-03 | Z | 2024-08-23 | 20 | 0 | 0 |  | 0 | 30 |  | 3rd floor bathrooms |  | 11 |  | 2024-09-06
2024-09-04 | 4356 | w | 95240 - 95244 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-09-03 | Z | 2024-08-26 | 130 | 0 | 0 |  | 0 | 280 |  | Drain pans |  | 8 |  | 2024-09-06
2024-09-06 | 4357 |  | 69823 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-13 | Z | 2024-08-26 | 20 | 0 | 0 |  | 0 | 20 |  | FCU-6 |  | 18 | 2024-09-13
2024-09-05 | 4360 |  | 69945 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-09-06 | Z | 2024-08-28 | 10 | 0 | 0 |  | 0 | 10 |  | L5-A-EALP-3 |  | 9 |  |  |  |  | 2024-09-09
2024-09-05 | 4361 |  | 69667 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-06 | Z | 2024-08-28 | 20 | 0 | 0 |  | 0 | 20 |  | Reducers |  | 9 |  |  |  |  | 2024-09-09
2024-09-03 | 4362 | w | 95245 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-05 | Z | 2024-08-28 | 30 | 0 | 0 |  | 0 | 80 |  | Drain pans |  | 8
2024-09-06 | 4365 |  | 69946 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-09-09 | Z | 2024-09-03 | 60 | 0 | 0 |  | 0 | 160 |  | Test caps |  | 6 |  |  |  |  | 2024-09-09
2024-09-06 | 4371 |  | 69672 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-09 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 30 |  | FSD-4th floor |  | 3
2024-09-04 | 259 | w | 79799 | A | DONE | 2 | S-M |  | COMPASS HP 4230088 | 1" liner | 2024-09-05 | Z | 2024-08-28 | 50 | 0 | 0 |  | 30 | 160 |  | RTU Cap |  | 8
2024-09-06 | 264 |  | 70229 | A | DONE | 3 | S |  | COMPASS HP 4230088 |  | 2024-09-09 | Z | 2024-09-04 | 50 | 20 | 0 |  | 0 | 70 |  | VAV-15 |  | 5
2024-09-03 | 2579 | bth | L2-EAD-Z2-0016 | A | DONE | 9 | S | alum | EXACT TL-5 6240014 |  | 2024-08-28 | Z | 2024-08-26 | 90 | 30 | 100 | F | 0 | 110 |  |  |  | 2
2024-09-06 | 4026 |  | 79053 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 20 |  | SA |  | 18 |  |  |  |  | 2024-09-09
2024-09-06 | 4027 |  | L2-SALP-Z2-0011 | A | DONE | 13 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 280 | 0 | 40 | F | 0 | 390 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4028 |  | L2-SALP-Z2-0012 | A | DONE | 24 | M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 290 | 0 | 310 | F | 0 | 720 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4029 |  | L2-SALP-Z2-0013 | A | DONE | 24 | M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 210 | 0 | 380 | F | 0 | 710 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4030 |  | L2-SALP-Z2-0014 | A | DONE | 20 | M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 370 | 0 | 110 | F | 0 | 570 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4031 |  | L2-SALP-Z2-0015 | A | DONE | 16 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 280 | 0 | 110 | F | 0 | 510 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4032 |  | L2-SALP-Z2-0016 | A | DONE | 14 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 190 | 0 | 150 | F | 0 | 400 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4033 | bth | L2-EAD-Z2-0016 | A | DONE | 11 | S | alum | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 240 | 30 | 0 |  | 0 | 110 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4034 | bth | L2-EAD-Z2-0017 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 220 | 30 | 50 | F | 0 | 390 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4035 |  | L2-EAD-Z2-0018 | A | DONE | 21 | M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 240 | 0 | 270 | F | 0 | 890 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4036 |  | L2-EAD-Z2-0019 | A | DONE | 20 | M |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 140 | 0 | 340 | F | 0 | 810 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4037 | bth | L2-EAD-Z2-0020 | A | DONE | 8 | S |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 90 | 20 | 70 | F | 0 | 200 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-06 | 4038 | bth | L2-EAD-Z2-0021 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-09-09 | Z | 2024-08-23 | 100 | 20 | 40 | F | 0 | 170 |  |  |  | 17 |  |  |  |  | 2024-09-09
2024-09-03 | 4039 |  | 41346 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2024-09-04 | Z | 2024-08-26 | 60 | 0 | 0 |  | 0 | 130 |  | Spool change |  | 9
2024-09-03 | 732 |  | 80320 | A | DONE | 2 | S |  | HILLDALE 6230003 |  | 2024-09-04 | Z | 2024-09-03 | 20 | 0 | 0 |  | 0 | 20 |  | RTU-12 |  | 1
2024-09-03 | 728 | sp | 80903 | A | DONE | 4 | S-M |  | HILLDALE 6240003 |  | 2024-09-04 | Z | 2024-08-26 | 20 | 70 | 0 |  | 0 | 80 |  | FCU-1 OA |  | 9
2024-09-06 | 733 |  | 80321 | A | DONE | 2 | S |  | HILLDALE 6240003 |  | 2024-09-09 | Z | 2024-09-06 | 30 | 0 | 0 |  | 0 | 30 |  | Intake hood |  | 3
2024-09-03 | 262 |  | 66712 | A | DONE | 2 | S |  | HOLY WISDOM 6220019 |  | 2024-09-04 | Z | 2024-09-03 | 50 | 0 | 0 |  | 0 | 80 |  | BCUS |  | 1
2024-09-03 | 1709 |  | 80204 | A | DONE | 2 | S |  | INVENRA 6230001 |  | 2024-09-05 | Z | 2024-08-22 | 0 | 0 | 0 |  | 0 | 0 |  | DM Frames |  | 14
2024-09-05 | 3365 |  | 78699 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-09-06 | Z | 2024-09-05 | 20 | 0 | 0 |  | 0 | 30 |  | Grilles |  | 1
2024-09-05 | 3366 |  | 78700 | A | DONE | 2 | S | neal | JANESVILLE ESSR 6230011 |  | 2024-09-06 | Z | 2024-09-05 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2024-09-06 | 3367 |  | 78628 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-09-09 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 20 |  | Boiler venting |  | 3
2024-09-04 | 1916 |  | 82406 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-09-04 | Z | 2024-09-04 | 20 | 0 | 0 |  | 0 | 20 |  | Bath EA |  | 0
2024-09-05 | 1917 |  | 62198 | A | DONE | 2 | S | pt.neal | JPC OFFICE 6240002 |  | 2024-09-06 | Z | 2024-09-05 | 50 | 0 | 0 |  | 0 | 50 |  | Soffit duct |  | 1
2024-09-06 | 2338 |  | 67729 - 67730 | A | DONE | 9 | S-M |  | KOHL CENTER 6210034 | bird s. | 2024-09-09 | Z | 2024-08-26 | 180 | 0 | 40 | F | 0 | 250 |  | Misc |  | 14 |  |  |  |  | 2024-09-09
2024-09-05 | 2339 | sp | 67731 | A | DONE | 5 | S-M |  | KOHL CENTER 6210034 |  | 2024-09-06 | Z | 2024-08-26 | 80 | 40 | 0 |  | 0 | 130 |  | Courtside club |  | 11 |  |  |  |  | 2024-09-09
2024-09-04 | 2340 |  | 67732 | A | DONE | 2 | S | alum | KOHL CENTER 6210034 |  | 2024-09-09 | Z | 2024-08-27 | 20 | 0 | 0 |  | 0 | 20 |  | MISC |  | 13
2024-09-04 | 2341 |  | 67733 | A | DONE | 2 | S | neal | KOHL CENTER 6210034 |  | 2024-09-09 | Z | 2024-08-27 | 20 | 0 | 0 |  | 0 | 20 |  | Courtside club |  | 13
2024-09-06 | 2342 |  | 67734 | A | DONE | 2 | S |  | KOHL CENTER 8210034 |  | 2024-09-09 | Z | 2024-08-28 | 40 | 0 | 0 |  | 0 | 60 |  | ANGLE |  | 12 |  |  |  |  | 2024-09-09
2024-09-05 | 3467 |  | 68122 | A | DONE | 2 | S | neal | MEMORIAL HS 6210024 |  | 2024-09-06 | Z | 2024-09-03 | 20 | 0 | 0 |  | 0 | 20 |  | Pipe cover |  | 3 |  |  |  |  | 2024-09-09
2024-09-05 | 3468 |  | 68123 | A | DONE | 2 | S | alum | MEMORIAL HS 6210024 |  | 2024-09-06 | Z | 2024-09-04 | 20 | 0 | 0 |  | 0 | 20 |  | Pipe cover |  | 2 |  |  |  |  | 2024-09-09
2024-09-06 | 2367 |  | 80317 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-09-09 | Z | 2024-08-27 | 30 | 0 | 0 |  | 20 | 40 |  | Basement outs |  | 13
2024-09-06 | 2369 |  | 80351 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-09-09 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 20 |  | Damper |  | 3
2024-09-04 | 3802 |  | 62715 | A | DONE | 2 | S | ss | PROMEGA 1518 2240009 |  | 2024-09-04 | Z | 2024-09-04 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-09-04 | 1625 |  | 62717 | A | DONE | 2 | S |  | PROMEGA CMC 2240038 |  | 2024-09-05 | Z | 2024-09-04 | 50 | 0 | 0 |  | 0 | 50 |  | Misc |  | 1
2024-09-06 | 1626 |  | 90624 | A | DONE | 2 | S | ss | PROMEGA CMC 2240038 |  | 2024-09-09 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 3
2024-09-04 | 1999 | sp | L2-EA (-4wg)-01 | A | DONE | 4 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-11 | Z | 2024-08-08 | 20 | 60 | 0 |  | 0 | 100 |  |  |  | 34 |  | 2024-08-28
2024-09-04 | 2370 | sp | L2-EA (-4wg)-02 | A | DONE | 3 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-11 | Z | 2024-08-08 | 30 | 30 | 0 |  | 0 | 60 |  |  |  | 34 |  | 2024-08-28
2024-09-04 | 2372 | sp | L2-EA (-4wg)-04 | A | DONE | 6 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-11 | Z | 2024-08-08 | 50 | 90 | 0 |  | 0 | 150 |  |  |  | 34 |  | 2024-08-28
2024-09-04 | 2375 | bth | L2-SALP-05 | A | DONE | 9 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-04 | Z | 2024-08-08 | 100 | 120 | 0 |  | 0 | 230 |  |  |  | 27 |  | 2024-08-28
2024-09-03 | 2379 |  | 56339 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-04 | Z | 2024-08-20 | 30 | 0 | 0 |  | 0 | 70 |  | Misc |  | 15 |  | 2024-08-28
2024-09-03 | 3800 |  | 62709 | A | DONE | 2 | S |  | PROMEGA RPP 6240019 | paint | 2024-09-04 | Z | 2024-08-28 | 40 | 0 | 0 |  | 20 | 60 |  | Misc |  | 7
2024-09-04 | 3801 | sp | 62716 | A | DONE | 8 | S |  | PROMEGA RPP 6240019 |  | 2024-09-04 | Z | 2024-09-04 | 40 | 150 | 0 |  | 0 | 180 |  | Misc |  | 0
2024-09-06 | 268 |  | 78747 | A | DONE | 2 | S |  | RICK P. 10056835 |  | 2024-09-06 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-09-04 | 4771 |  | 61183 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-09-06 | Z | 2024-08-30 | 20 | 0 | 0 |  | 0 | 20 |  | Max Security BS |  | 7
2024-09-05 | 4274 |  | 79955 | A | DONE | 5 | S-M |  | ST.BERNARD 2230056 |  | 2024-09-05 | Z | 2024-08-22 | 50 | 0 | 60 | F | 0 | 90 |  | 2nd floor SA |  | 14
2024-09-05 | 4275 |  | 79956 - 79957 | A | DONE | 18 | S-M |  | ST.BERNARD 2230056 |  | 2024-09-05 | Z | 2024-08-22 | 90 | 0 | 350 | F | 280 | 420 |  | Shaft SA |  | 14
2024-09-05 | 1499 |  | 73040 | A | DONE | 2 | S |  | UW VET MED 6210014 | paint | 2024-09-11 | Z | 2024-08-29 | 20 | 0 | 0 |  | 10 | 20 |  | L1-F1 |  | 11 |  |  |  |  | 2024-09-09
2024-09-05 | 3591 |  | 67909 | A | DONE | 8 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-09-03 | Z | 2024-08-19 | 160 | 0 | 30 | F | 140 | 230 |  | Attic Auditorium |  | 15
2024-09-05 | 3592 |  | 67910 - 67911 | A | DONE | 20 | S-M |  | UWL-GRAFF 6230017 | VD | 2024-09-03 | Z | 2024-08-19 | 480 | 0 | 0 |  | 0 | 780 |  | AHU-4 RA Attic |  | 15
2024-09-04 | 3593 |  | 67913 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-03 | Z | 2024-08-19 | 30 | 0 | 0 |  | 0 | 50 |  | Misc |  | 15
2024-09-05 | 3595 |  | 79382 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-09-03 | Z | 2024-08-22 | 110 | 0 | 30 | F | 0 | 240 |  | AHU-4 SA 2nd floor |  | 12
2024-09-04 | 3596 |  | 67914 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-03 | Z | 2024-08-22 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-5-2-4 |  | 12
2024-09-05 | 559 |  | 66940 | A | DONE | 4 | S-M | pcd/nl | UWRF 6230010 |  | 2024-09-04 | Z | 2024-08-19 | 60 | 20 | 0 |  | 0 | 80 |  | Misc |  | 16
2024-09-05 | 560 | bth | 66941 | A | DONE | 2 | S | pt.pcd | UWRF 6230010 | 1" liner | 2024-09-04 | Z | 2024-08-20 | 30 | 20 | 0 |  | 20 | 50 |  | L2Z2-C |  | 15
2024-09-05 | 561 | bth | 66942 | A | DONE | 3 | S | pt. pcd | UWRF 6230010 |  | 2024-09-04 | Z | 2024-08-22 | 50 | 20 | 0 |  | 20 | 70 |  | Misc |  | 13
2024-09-03 | 5076 |  | 81104 - 81105 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-08-27 | Z | 2024-08-12 | 300 | 0 | 0 |  | 0 | 460 |  | 2nd floor EC / Flashing |  | 15
2024-09-03 | 5082 |  | RA-01-10 | A | DONE | 24 | M |  | UWSP ALBERTSON 6230016 | VD's | 2024-08-27 | Z | 2024-08-12 | 290 | 0 | 310 | F | 0 | 720 |  |  |  | 15
2024-09-03 | 5083 |  | RA-01-11 | A | DONE | 23 | M |  | UWSP ALBERTSON 6230016 | VD's | 2024-08-27 | Z | 2024-08-12 | 320 | 0 | 250 | F | 0 | 710 |  |  |  | 15
2024-09-03 | 5084 |  | RA-01-12 | A | DONE | 22 | M |  | UWSP ALBERTSON 6230016 | VD's | 2024-08-27 | Z | 2024-08-12 | 180 | 0 | 350 | F | 0 | 640 |  |  |  | 15
2024-09-03 | 5085 |  | RA-01-13 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | VD's | 2024-08-27 | Z | 2024-08-12 | 190 | 0 | 90 | F | 0 | 330 |  |  |  | 15
2024-09-03 | 5086 |  | RA-01-14 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | VD's | 2024-08-27 | Z | 2024-08-12 | 160 | 0 | 120 | F | 0 | 340 |  |  |  | 15
2024-09-03 | 5087 |  | RA-01-15 | A | DONE | 6 | S |  | UWSP ALBERTSON 6230016 | VD's | 2024-08-27 | Z | 2024-08-12 | 70 | 0 | 60 | F | 0 | 160 |  |  |  | 15
2024-09-03 | 5088 |  | RA-01-16 | A | DONE | 19 | M |  | UWSP ALBERTSON 6230016 | VD's | 2024-08-27 | Z | 2024-08-12 | 210 | 0 | 260 | F | 0 | 570 |  |  |  | 15
2024-09-05 | 1481 |  | 73017 - 73018 | A | DONE | 54 | M |  | UW-VET MED 6210014 |  | 2024-09-03 | Z | 2024-08-15 | 280 | 0 | 1070 | F | 0 | 1860 |  | 10-C SA/EA |  | 19
2024-09-04 | 1482 | sp | 73019 | A | DONE | 5 | S-M |  | UW-VET MED 6210014 |  | 2024-09-03 | Z | 2024-08-15 | 30 | 90 | 0 |  | 0 | 130 |  | 10-C EA |  | 19
2024-09-05 | 1483 |  | 73020 - 73021 | A | DONE | 5 | S-M |  | UW-VET MED 6210014 |  | 2024-09-03 | Z | 2024-08-15 | 100 | 0 | 20 | F | 0 | 150 |  | 10-C SA |  | 19
2024-09-05 | 1486 | sp | 73026 - 73027 | A | DONE | 6 | S-M |  | UW-VET MED 6210014 |  | 2024-09-11 | Z | 2024-08-15 | 10 | 140 | 0 |  | 0 | 130 |  | 10-C |  | 27 |  |  |  |  | 2024-09-09
2024-09-05 | 1491 |  | 73031 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-09-11 | Z | 2024-08-22 | 10 | 0 | 0 |  | 0 | 20 |  | 10-C |  | 20 |  |  |  |  | 2024-09-09
2024-09-04 | 1497 |  | 73038 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-09-06 | Z | 2024-08-27 | 30 | 0 | 0 |  | 0 | 80 |  | Misc |  | 10
2024-09-06 | 1530 |  | 73042 | A | DONE | 2 | S | alum | UW-VET MED 6210014 |  | 2024-09-09 | Z | 2024-09-03 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2024-09-06 | 1531 |  | 73043 | A | DONE | 2 | S | alum | UW-VET MED 6210014 |  | 2024-09-09 | Z | 2024-09-04 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 5
2024-09-04 | 265 |  | 78746 | A | DONE | 2 | S |  | WAUNAKEE ADMIN 10057356 |  | 2024-09-04 | Z | 2024-09-04 | 20 | 0 | 0 |  | 0 | 20 |  | F-4 |  | 0
[6 empty] | 1232 | [13 empty] | 40490 |  |  |  | 2970 | 7.335%
WEEK OF 9-9-2024
2024-09-13 | 3680 |  | 80122 | A | DONE | 10 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-09-16 | Z | 2024-08-07 | 250 | 0 | 0 |  | 230 | 290 |  | 3rd floor West unit plenum |  | 40
2024-09-13 | 3681 |  | 80123 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-16 | Z | 2024-08-07 | 100 | 0 | 0 |  | 0 | 100 |  | 3rd floor West unit taps |  | 40
2024-09-13 | 3682 |  | 80124 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-16 | Z | 2024-08-07 | 70 | 0 | 0 |  | 0 | 80 |  | 3rd floor West unit sliders |  | 40
2024-09-13 | 3683 |  | 80125 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-09-16 | Z | 2024-08-07 | 20 | 0 | 0 |  | 20 | 20 |  | HP-300C |  | 40
2024-09-13 | 3907 |  | 80143 - 80144 | A | DONE | 35 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-16 | Z | 2024-08-12 | 100 | 0 | 770 | F | 0 | 810 |  | 4th Fl. West EA |  | 35
2024-09-11 | 3921 |  | 81911 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-09-12 | Z | 2024-08-28 | 30 | 0 | 0 |  | 0 | 40 |  | Unit 204 , Stairwell |  | 15
2024-09-10 | 3922 |  | 81912 | A | DONE | 6 | S |  | 121 E. WILSON 6230024 |  | 2024-09-11 | Z | 2024-09-09 | 20 | 0 | 110 |  | 0 | 120 |  | 3rd West EA |  | 2
2024-09-09 | 1775 |  | 38617 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-09-09 | Z | 2024-09-09 | 20 | 0 | 0 |  | 0 | 60 |  | Weld EA cap |  | 0
2024-09-12 | 755 |  | 80215 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-09-13 | Z | 2024-09-12 | 30 | 0 | 0 |  | 0 | 50 |  | Loading Dock SAMP |  | 1
2024-09-11 | 825 |  | NC-SAMP-005 | A | DONE | 58 | L |  | CDIS 6220028 | partial , 1" DW | 2024-09-12 | Z | 2024-08-15 | 1430 | 0 | 0 |  | 530 | 2070 |  |  |  | 28 | 2024-09-06
2024-09-11 | 827 |  | NC-EAD-002 | A | DONE | 56 | L |  | CDIS 6220028 | partial , 1" DW | 2024-09-12 | Z | 2024-08-15 | 1380 | 0 | 0 |  | 490 | 2070 |  |  |  | 28 | 2024-09-06
2024-09-09 | 1372 | bth | L6-A-EALP-049 | A | DONE | 3 | S-M | neal | CDIS 6220028 | paint , 1" liner | 2024-09-09 | Z | 2024-07-17 | 40 | 20 | 0 |  | 20 | 70 |  |  |  | 54 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1377 | sp | L6-A-EALP-054 | A | DONE | 7 | S-M |  | CDIS 6220028 | 1" spiral accu | 2024-09-10 | Z | 2024-07-17 | 80 | 90 | 0 |  | 110 | 210 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1378 | bth | L6-A-SALP-055 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 | paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 100 | 40 | 0 |  | 50 | 140 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1379 | bth | L6-A-SALP-069 | A | DONE | 8 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 170 | 30 | 0 |  | 90 | 250 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1380 | bth | L6-A-SALP-070 | A | DONE | 6 | S-M | neal | CDIS 6220028 | paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 120 | 20 | 0 |  | 40 | 150 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1381 |  | L6-A-SALP-071 | A | DONE | 4 | S-M | neal | CDIS 6220028 | paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 40 | 0 | 40 | F | 30 | 90 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1382 |  | L6-A-SALP-072 | A | DONE | 6 | S-M | neal | CDIS 6220028 | VD , paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 100 | 0 | 50 | F | 20 | 180 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1383 |  | L6-A-SALP-073 | A | DONE | 7 | S-M | neal | CDIS 6220028 | VD , paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 100 | 0 | 70 | F | 30 | 200 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1384 | bth | L6-A-SALP-074 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 80 | 40 | 0 |  | 30 | 140 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1385 | bth | L6-A-SALP-075 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 50 | 80 | 0 |  | 20 | 130 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1386 | bth | L6-A-SALP-076 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 40 | 70 | 0 |  | 20 | 110 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1387 | bth | L6-A-SALP-077 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 50 | 40 | 0 |  | 20 | 80 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1388 | bth | L6-A-SALP-078 | A | DONE | 3 | S-M | neal | CDIS 6220028 | paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1389 | bth | L6-A-SALP-079 | A | DONE | 4 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 50 | 50 | 0 |  | 60 | 120 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1390 | bth | L6-A-SALP-080 | A | DONE | 4 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 50 | 40 | 0 |  | 20 | 100 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1391 | bth | L6-A-SALP-081 | A | DONE | 4 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 60 | 40 | 0 |  | 30 | 180 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1392 | bth | L6-A-SALP-082 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 40 | 70 | 0 |  | 20 | 120 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1393 | bth | L6-A-SALP-083 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 40 | 70 | 0 |  | 20 | 110 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1394 | bth | L6-A-SALP-084 | A | DONE | 6 | S-M |  | CDIS 6220028 | paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 80 | 70 | 0 |  | 60 | 160 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1395 | bth | L6-A-SALP-085 | A | DONE | 11 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 150 | 110 | 0 |  | 30 | 270 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1396 |  | L6-A-SALP-086 | A | DONE | 6 | S-M | neal | CDIS 6220028 | VD , paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 90 | 0 | 40 | F | 30 | 180 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1397 | bth | L6-A-SALP-087 | A | DONE | 7 | S-M | neal | CDIS 6220028 | VD , paint , 1" liner | 2024-09-10 | Z | 2024-07-17 | 130 | 30 | 0 |  | 50 | 180 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-09 | 1398 |  | L6-A-TAD-001 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-10 | Z | 2024-07-17 | 90 | 0 | 0 |  | 70 | 120 |  |  |  | 55 | 2024-08-27 |  |  |  | 2024-09-09
2024-09-12 | 1417 | bth | L7-A-SALP-046 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 50 | 50 | 0 |  | 20 | 110 |  |  |  | 52 | 2024-09-16
2024-09-12 | 1418 | bth | L7-A-SALP-047 | A | DONE | 5 | S |  | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 50 | 70 | 0 |  | 20 | 120 |  |  |  | 52 | 2024-09-16
2024-09-12 | 1419 | bth | L7-A-SALP-048 | A | DONE | 5 | S | neal | CDIS 6220028 | paint , 1" liner | 2024-09-13 | Z | 2024-07-23 | 80 | 40 | 0 |  | 40 | 130 |  |  |  | 52 | 2024-09-16
2024-09-12 | 1420 | bth | L7-A-SALP-049 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 50 | 80 | 0 |  | 20 | 130 |  |  |  | 52 | 2024-09-16
2024-09-12 | 1421 | bth | L7-A-SALP-050 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 50 | 90 | 0 |  | 20 | 130 |  |  |  | 52 | 2024-09-16
2024-09-13 | 1422 | bth | L7-A-SALP-051 | A | DONE | 8 | S | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-23 | 60 | 140 | 0 |  | 20 | 240 |  |  |  | 55 | 2024-09-16
2024-09-12 | 1423 | bth | L7-A-SALP-052 | A | DONE | 6 | S |  | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 60 | 80 | 0 |  | 20 | 150 |  |  |  | 52 | 2024-09-16
2024-09-13 | 1424 | bth | L7-A-SALP-053 | A | DONE | 6 | S | neal | CDIS 6220028 | VD's , paint , 1" liner | 2024-09-16 | Z | 2024-07-23 | 70 | 70 | 0 |  | 30 | 160 |  |  |  | 55 | 2024-09-16
2024-09-13 | 1425 | bth | L7-A-SALP-054 | A | DONE | 6 | S | pt.neal | CDIS 6220028 | paint , 1" liner | 2024-09-16 | Z | 2024-07-23 | 90 | 40 | 0 |  | 40 | 150 |  |  |  | 55 | 2024-09-16
2024-09-12 | 1426 | bth | L7-A-SALP-055 | A | DONE | 13 | S |  | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 150 | 40 | 120 | F | 40 | 350 |  |  |  | 52 | 2024-09-16
2024-09-12 | 1427 | bth | L7-A-SALP-056 | A | DONE | 10 | S | neal | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 120 | 20 | 100 | F | 50 | 280 |  |  |  | 52 | 2024-09-16
2024-09-13 | 1428 | bth | L7-A-SALP-057 | A | DONE | 7 | S | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-23 | 100 | 20 | 40 | F | 50 | 180 |  |  |  | 55 | 2024-09-16
2024-09-13 | 1429 | bth | L7-A-SALP-058 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-09-16 | Z | 2024-07-23 | 70 | 0 | 70 | F | 0 | 200 |  |  |  | 55 | 2024-09-16
2024-09-13 | 1430 | bth | L7-A-SALP-059 | A | DONE | 8 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-23 | 100 | 20 | 70 | F | 30 | 200 |  |  |  | 55 | 2024-09-16
2024-09-13 | 1431 | bth | L7-A-SALP-060 | A | DONE | 6 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-23 | 90 | 20 | 30 | F | 20 | 180 |  |  |  | 55 | 2024-09-16
2024-09-13 | 1432 | bth | L7-A-SALP-061 | A | DONE | 7 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-23 | 80 | 40 | 40 | F | 60 | 180 |  |  |  | 55 | 2024-09-16
2024-09-13 | 1433 | bth | L7-A-SALP-062 | A | DONE | 9 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-23 | 60 | 50 | 110 | F | 20 | 260 |  |  |  | 55 | 2024-09-16
2024-09-12 | 1434 | bth | L7-A-SALP-063 | A | DONE | 8 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 140 | 60 | 0 |  | 60 | 240 |  |  |  | 52 | 2024-09-16
2024-09-12 | 1435 | bth | L7-A-SALP-064 | A | DONE | 8 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 80 | 20 | 90 | F | 20 | 210 |  |  |  | 52 | 2024-09-16
2024-09-12 | 1436 | bth | L7-A-SALP-065 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-07-23 | 100 | 20 | 0 |  | 30 | 150 |  |  |  | 52 | 2024-09-16
2024-09-13 | 1437 | bth | L7-A-SALP-066 | A | DONE | 8 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-23 | 130 | 20 | 40 | F | 30 | 230 |  |  |  | 55 | 2024-09-16
2024-09-13 | 3416 | bth | L7-A-EALP-031 | A | DONE | 5 | S | pt.neal | CDIS 6220028 | paint , 1" liner | 2024-09-16 | Z | 2024-07-30 | 80 | 30 | 0 |  | 40 | 120 |  |  |  | 48 | 2024-09-16
2024-09-12 | 3417 | sp | L7-A-EALP-032 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-09-13 | Z | 2024-07-30 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 45 | 2024-09-16
2024-09-13 | 3418 | bth | L7-A-EALP-033 | A | DONE | 7 | S | neal | CDIS 6220028 |  | 2024-09-16 | Z | 2024-07-30 | 80 | 80 | 0 |  | 0 | 190 |  |  |  | 48 | 2024-09-16
2024-09-13 | 3419 |  | L7-A-EALP-034 | A | DONE | 5 | S |  | CDIS 6220028 |  | 2024-09-16 | Z | 2024-07-30 | 40 | 70 | 0 |  | 0 | 160 |  |  |  | 48 | 2024-09-16
2024-09-13 | 3420 | bth | L7-A-EALP-035 | A | DONE | 5 | S | pt.neal | CDIS 6220028 | paint , VD | 2024-09-16 | Z | 2024-07-30 | 50 | 70 | 0 |  | 20 | 120 |  |  |  | 48 | 2024-09-16
2024-09-13 | 3421 | bth | L7-A-EALP-040 | A | DONE | 3 | S |  | CDIS 6220028 | paint | 2024-09-16 | Z | 2024-07-30 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 48 | 2024-09-16
2024-09-13 | 3422 | bth | L7-A-EALP-041 | A | DONE | 10 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-30 | 150 | 30 | 60 | F | 50 | 280 |  |  |  | 48 | 2024-09-16
2024-09-13 | 3423 | bth | L7-A-EALP-042 | A | DONE | 12 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-30 | 190 | 40 | 60 | F | 40 | 340 |  |  |  | 48 | 2024-09-16
2024-09-13 | 3424 | bth | L7-A-EALP-043 | A | DONE | 13 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-30 | 160 | 40 | 120 | F | 50 | 370 |  |  |  | 48 | 2024-09-16
2024-09-13 | 3425 | bth | L7-A-EALP-044 | A | DONE | 12 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-16 | Z | 2024-07-30 | 180 | 30 | 90 | F | 50 | 350 |  |  |  | 48 | 2024-09-16
2024-09-12 | 4346 |  | SA-(10wg)-PH-01 | A | DONE | 42 | M-L |  | CDIS 6220028 | partial | 2024-09-13 | Z | 2024-08-22 | 920 | 0 | 120 | F | 0 | 2270 |  |  |  | 22 | 2024-09-13
2024-09-11 | 4347 |  | EA-(6wg)-PH-01 | A | DONE | 10 | M |  | CDIS 6220028 | partial | 2024-09-13 | Z | 2024-08-22 | 160 | 0 | 80 | F | 0 | 410 |  |  |  | 22 | 2024-09-16
2024-09-12 | 4348 |  | EA-(10wg)-PH-02 | A | DONE | 30 | L |  | CDIS 6220028 | partial | 2024-09-13 | Z | 2024-08-22 | 740 | 0 | 0 |  | 0 | 2060 |  |  |  | 22 | 2024-09-16
2024-09-11 | 4349 |  | EA-(10wg)-PH-03 | A | DONE | 16 | M-L |  | CDIS 6220028 | partial | 2024-09-12 | Z | 2024-08-22 | 400 | 0 | 0 |  | 0 | 500 |  |  |  | 21 | 2024-09-13
2024-09-11 | 4350 |  | EA-(10wg)-PH-09 | A | DONE | 78 | L |  | CDIS 6220028 |  | 2024-09-12 | Z | 2024-08-22 | 1940 | 0 | 0 |  | 0 | 5780 |  |  |  | 21 | 2024-09-13
2024-09-11 | 4363 |  | 69825 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1-1/2" wrap | 2024-09-12 | Z | 2024-08-28 | 140 | 0 | 0 |  | 0 | 230 |  | AHU-7,8 OA |  | 15
2024-09-11 | 4364 |  | 69824 | A | DONE | 2 | S |  | CDIS 6220028 | angle frames , flex | 2024-09-12 | Z | 2024-08-28 | 0 | 0 | 0 |  | 0 | 0 |  | AHU-1B,C EA |  | 15
2024-09-12 | 4366 |  | 69668 - 69669 | A | DONE | 2 | S-M | neal | CDIS 6220028 |  | 2024-09-13 | Z | 2024-09-03 | 40 | 0 | 0 |  | 0 | 50 |  | CB tie ins |  | 10
2024-09-14 | 4367 |  | 57950 | A | DONE | 5 | S-M |  | CDIS 6220028 |  | 2024-09-19 | Z | 2024-09-04 | 110 | 0 | 0 |  | 0 | 360 |  | PH-SA-05 |  | 15 |  |  |  |  | 2024-09-17
2024-09-14 | 4368 |  | 69826 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-19 | Z | 2024-09-04 | 20 | 0 | 0 |  | 0 | 60 |  | Saddle hangers |  | 15 |  |  |  |  | 2024-09-17
2024-09-10 | 4369 |  | 69670 - 69671 | A | DONE | 2 | S-M | pt.neal | CDIS 6220028 | paint , 1" liner | 2024-09-13 | Z | 2024-09-05 | 50 | 0 | 0 |  | 30 | 50 |  | 6th floor outs |  | 8
2024-09-12 | 4370 |  | 69947 | A | DONE | 4 | S |  | CDIS 6220028 | 1" liner | 2024-09-13 | Z | 2024-09-05 | 90 | 0 | 0 |  | 70 | 110 |  | 7th floor TA |  | 8
2024-09-10 | 4372 |  | 69674 | A | DONE | 2 | S |  | CDIS 6220028 | 1" liner | 2024-09-12 | Z | 2024-09-06 | 20 | 0 | 0 |  | 20 | 20 |  | SALP-62 |  | 6
2024-09-09 | 4375 |  | 69970 | A | DONE | 2 | S | BI/alum | CDIS 6220028 |  | 2024-09-13 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2024-09-09 | 4376 |  | 70589 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-09 | Z | 2024-09-09 | 20 | 0 | 0 |  | 0 | 60 |  | Collar |  | 0
2024-09-12 | 4377 |  | hand drawn | A | DONE | 25 | M-L |  | CDIS 6220028 |  | 2024-09-13 | Z | 2024-09-10 | 620 | 0 | 0 |  | 0 | 1750 |  | EC's |  | 3
2024-09-11 | 266 |  | 31601 | A | DONE | 4 | S |  | COMPASS HP 4230088 | oval | 2024-09-12 | Z | 2024-09-05 | 30 | 70 | 0 |  | 0 | 100 |  | EA |  | 7
2024-09-12 | 271 |  | 31602 | A | DONE | 2 | S |  | COMPASS HP 4230088 |  | 2024-09-16 | Z | 2024-09-10 | 30 | 0 | 0 |  | 0 | 40 |  | Offset |  | 6
2024-09-11 | 267 | bth | 79423 - 79424 | A | DONE | 10 | S-M |  | EGENESIS 10057199 | bird.s | 2024-09-12 | Z | 2024-09-06 | 120 | 120 | 0 |  | 0 | 290 |  | Misc |  | 6
2024-09-11 | 4040 |  | 79055 | A | DONE | 3 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-12 | Z | 2024-08-28 | 60 | 0 | 0 |  | 0 | 140 |  | EAD |  | 15
2024-09-11 | 4041 |  | 79056-57 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2024-09-12 | Z | 2024-08-29 | 60 | 0 | 0 |  | 0 | 90 |  | L2EAD23-0032/L2SAMP22 |  | 13
2024-09-11 | 4042 | sp | 62535 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-12 | Z | 2024-08-29 | 20 | 80 | 0 |  | 0 | 120 |  | North Corr Outs |  | 13
2024-09-10 | 4047 |  | L2-EAD-Z3-0031 | delete |  |  | S |  | EXACT TL-5 6240014 | VD | 2024-09-26 | Z | 2024-09-04 | [9 empty] | 22 |  |  |  |  | 2024-09-18
2024-09-10 | 4048 |  | L2-EAD-Z3-0032 | delete |  |  | M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | [9 empty] | 22 |  |  |  |  | 2024-09-18
2024-09-09 | 4072 | sp | L2-SALP-Z2-0027 | delete |  |  | S |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | [9 empty] | 10
2024-09-09 | 4086 | sp | L2-EAD-Z2-0023 | delete |  |  | S |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | [9 empty] | 10
2024-09-14 | 4088 |  | 79008 | A | DONE | n/a | S |  | EXACT TL-5 6240014 |  | 2024-09-18 | Z | 2024-09-10 | 0 | 0 | 0 |  | 0 | 0 |  | DM Frames |  | 8
2024-09-11 | 4043 | sp | 62536 | A | DONE | 2 | S |  | EXACT-SPL-3 2230023 |  | 2024-09-12 | Z | 2024-08-29 | 20 | 0 | 0 |  | 0 | 20 |  | machine reducer |  | 13
2024-09-12 | 263 |  | 66944 | A | DONE | 2 | S |  | GTCH 6220003 | paint | 2024-09-13 | Z | 2024-09-03 | 20 | 0 | 0 |  | 20 | 20 |  | Reg. box |  | 10
2024-09-09 | 734 |  | 80322 | A | DONE | 2 | S |  | HILLDALE 6240003 |  | 2024-09-11 | Z | 2024-09-09 | 20 | 0 | 0 |  | 0 | 30 |  | IH-1 |  | 2
2024-09-11 | 3368 |  | 78629 | A | DONE | 2 | S | neal | JANESVILLE ESSR 6230011 |  | 2024-09-12 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 1
2024-09-12 | 3370 |  | 78634 - 78635 | A | DONE | 2 | S | neal | JANESVILLE ESSR 6230011 |  | 2024-09-12 | Z | 2024-09-12 | 20 | 0 | 0 |  | 0 | 20 |  | UV-EC |  | 0
2024-09-10 | 1918 |  | 62199 | A | DONE | 3 | S |  | JPC OFFICE 6240002 |  | 2024-09-11 | Z | 2024-09-06 | 60 | 0 | 0 |  | 0 | 80 |  | Misc |  | 5
2024-09-13 | 1919 |  | 62200 | A | DONE | 3 | S |  | JPC OFFICE 6240002 | bird s. | 2024-09-16 | Z | 2024-09-12 | 60 | 0 | 0 |  | 20 | 80 |  | Roof tie-ins |  | 4
2024-09-12 | 2343 |  | 67751 | A | DONE | 2 | S |  | KOHL CENTER 6210034 |  | 2024-09-12 | Z | 2024-09-12 | 20 | 0 | 0 |  | 0 | 40 |  | E,K |  | 0
2024-09-09 | 269 |  | 80352 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-09-09 | Z | 2024-09-09 | 20 | 0 | 0 |  | 0 | 20 |  | Louver tie-in |  | 0
2024-09-11 | 275 |  | 80356 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-09-11 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 40 |  | AHU-2 |  | 0
2024-09-13 | 3105 | sp | 79625 - 79626 | A | DONE | 38 | M | neal | PECATONICA 6240005 | accuflange | 2024-09-16 | Z | 2024-05-24 | 120 | 810 | 0 |  | 0 | 1090 |  | Gym SA |  | 115 | 2024-10-07
2024-09-13 | 3106 | sp | 79627 - 79628 | A | DONE | 14 | M | neal | PECATONICA 6240005 |  | 2024-09-16 | Z | 2024-05-24 | 60 | 290 | 0 |  | 0 | 410 |  | Gym SA |  | 115 | 2024-10-07
2024-09-13 | 3120 |  | 79645 | A | DONE | 6 | S-M |  | PECATONICA 6240005 |  | 2024-09-16 | Z | 2024-07-29 | 150 | 0 | 0 |  | 0 | 220 |  | OA Louver |  | 49
2024-09-13 | 3124 |  | 79648 | A | DONE | 9 | S-M |  | PECATONICA 6240005 | 1" liner | 2024-09-16 | Z | 2024-08-01 | 140 | 0 | 0 |  | 80 | 150 |  | A-Section EA drops |  | 46
2024-09-12 | 3139 | w | 80135 | A | DONE | 2 | S-M |  | PECATONICA 6240005 |  | 2024-09-16 | Z | 2024-08-22 | 30 | 0 | 0 |  | 0 | 120 |  | Boiler venting curb cap |  | 25
2024-09-12 | 3140 |  | DH0003 - DH0004 | A | DONE | 2 | S | neal | PECATONICA 6240005 |  | 2024-09-16 | Z | 2024-08-28 | 20 | 0 | 0 |  | 0 | 60 |  | pre-fab hangers |  | 19
2024-09-09 | 1627 |  | 62718 | A | DONE | 2 | S | ss | PROMEGA CMC 2240038 |  | 2024-09-09 | Z | 2024-09-09 | 20 | 30 | 0 |  | 0 | 50 |  | Misc |  | 0
2024-09-10 | 2371 | bth | L2-EA (-4wg)-03 | A | DONE | 8 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-12 | Z | 2024-08-08 | 120 | 80 | 0 |  | 0 | 230 |  |  |  | 35 | 2024-08-28
2024-09-10 | 2373 | bth | L2-EA (-4wg)-05 | A | DONE | 8 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-12 | Z | 2024-08-08 | 100 | 60 | 40 | F | 0 | 230 |  |  |  | 35 | 2024-08-28
2024-09-10 | 2374 | bth | L2-SALP-02 | A | DONE | 4 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-12 | Z | 2024-08-08 | 70 | 20 | 0 |  | 0 | 80 |  |  |  | 35 | 2024-08-28
2024-09-10 | 3803 | bth | 56342 , 56344 | A | DONE | 4 | S |  | PROMEGA RPP 6240019 |  | 2024-09-11 | Z | 2024-09-09 | 60 | 20 | 0 |  | 0 | 80 |  | FCU-2,4 |  | 2
2024-09-10 | 3804 |  | 56343 | A | DONE | 2 | S |  | PROMEGA RPP 6240019 |  | 2024-09-11 | Z | 2024-09-10 | 20 | 0 | 0 |  | 0 | 20 |  | FCU-3 |  | 1
2024-09-14 | 3805 | bth | 56345 | A | DONE | 5 | S-M |  | PROMEGA RPP 6240019 |  | 2024-09-16 | Z | 2024-09-13 | 40 | 70 | 0 |  | 0 | 120 |  | Dampers |  | 3
2024-09-14 | 4276 |  | 79920 - 79921 | A | DONE | 2 | S-M | neal | ST.BERNARD 6230023 |  | 2024-09-19 | Z | 2024-09-05 | 30 | 0 | 0 |  | 0 | 40 |  | Storm collars / cover |  | 14
2024-09-09 | 3597 |  | 67915 , 67917 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-09-12 | Z | 2024-08-28 | 30 | 0 | 0 |  | 0 | 40 |  | 2nd EA , 3rd RA 307 |  | 15 |  |  |  |  | 2024-09-09
2024-09-09 | 3598 |  | 79392 | A | DONE | 4 | S-M |  | UWL-GRAFF 6230017 |  | 2024-09-12 | Z | 2024-08-28 | 90 | 0 | 0 |  | 0 | 110 |  | AHU-4 RA 2nd floor |  | 15 |  |  |  |  | 2024-09-09
2024-09-10 | 500 |  | L1Z2-SAT-1-1-25 | A | DONE | 4 | S | neal | UWRF 6230010 | VD , 1" liner | 2024-09-11 | Z | 2024-07-26 | 80 | 0 | 0 |  | 30 | 100 |  |  |  | 47
2024-09-10 | 501 | bth | L1Z2-SAT-1-1-26 | A | DONE | 10 | S-M |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 120 | 20 | 110 | F | 40 | 290 |  |  |  | 47
2024-09-10 | 502 | bth | L1Z2-SAT-1-1-27 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 20 | 30 | 30 | F | 30 | 90 |  |  |  | 47
2024-09-10 | 503 |  | L1Z2-SAT-1-1-28 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 47
2024-09-10 | 504 | bth | L1Z2-SAT-1-1-29 | A | DONE | 8 | S | neal | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 130 | 40 | 20 | F | 30 | 220 |  |  |  | 47
2024-09-10 | 505 |  | L1Z2-SAT-1-1-30 | A | DONE | 2 | S | neal | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 50 | 0 | 0 |  | 30 | 60 |  |  |  | 47
2024-09-10 | 506 |  | L1Z2-SAT-1-1-31 | A | DONE | 2 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 47
2024-09-14 | 531 |  | L1Z2-TA 1 | A | DONE | 7 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-08-02 | 130 | 0 | 30 | F | 110 | 200 |  |  |  | 46
2024-09-14 | 532 |  | L1Z2-TA 2 | A | DONE | 8 | S |  | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-08-02 | 130 | 0 | 50 | F | 110 | 210 |  |  |  | 46
2024-09-14 | 533 |  | L1Z2-TA 3 | A | DONE | 5 | S |  | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-08-02 | 60 | 0 | 50 | F | 70 | 130 |  |  |  | 46
2024-09-14 | 534 |  | L1Z2-TA 4 | A | DONE | 8 | S |  | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-08-02 | 130 | 0 | 50 | F | 120 | 220 |  |  |  | 46
2024-09-09 | 562 |  | L3Z1-FEV-3-3-3 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-08-23 | 30 | 30 | 0 |  | 0 | 60 |  |  |  | 18
2024-09-10 | 595 |  | 70155 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-12 | Z | 2024-08-27 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-1-3-37 |  | 16
2024-09-10 | 596 |  | 66943 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-09-12 | Z | 2024-08-28 | 50 | 0 | 0 |  | 30 | 50 |  | L2 TA |  | 15
2024-09-09 | 1001 | sp | L1Z2-FEV-3-1-5 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 47
2024-09-09 | 1002 | sp | L1Z2-FEV-3-1-6 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 47
2024-09-09 | 1003 | bth | L1Z2-FEV-3-1-7 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 40 | 70 | 0 |  | 0 | 140 |  |  |  | 47
2024-09-09 | 1004 | sp | L1Z2-FEV-3-1-8 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 30 | 20 | 0 |  | 0 | 60 |  |  |  | 47
2024-09-09 | 1005 | bth | L1Z2-FEV-3-1-9.1 | A | DONE | 9 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 100 | 110 | 0 |  | 0 | 260 |  |  |  | 47
2024-09-09 | 1006 | sp | L1Z2-FEV-3-1-9.2 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 60 | 60 | 0 |  | 0 | 170 |  |  |  | 47
2024-09-09 | 1007 | bth | L1Z2-FEV-3-1-10 | A | DONE | 5 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 50 | 60 | 0 |  | 0 | 130 |  |  |  | 47
2024-09-09 | 1008 | sp | L1Z2-FEV-3-1-11 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 47
2024-09-09 | 1009 | sp | L1Z2-FEV-3-1-12 | A | DONE | 4 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 40 | 60 | 0 |  | 0 | 120 |  |  |  | 47
2024-09-09 | 1010 | sp | L1Z2-FEV-3-1-13 | A | DONE | 2 | 2 | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 0 | 0 |  | 0 | 30 |  |  |  | 47
2024-09-09 | 1011 | sp | L1Z2-FEV-3-1-14 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 20 | 0 |  | 0 | 50 |  |  |  | 47
2024-09-09 | 1012 | sp | L1Z2-FEV-3-1-27 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 30 | 50 | 0 |  | 0 | 90 |  |  |  | 47
2024-09-10 | 1013 | sp | L1Z2-GET-1-1-12 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 47
2024-09-09 | 1014 | sp | L1Z2-GET-1-1-13 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 47
2024-09-10 | 1015 | sp | L1Z2-GET-1-1-14 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 10 | 10 | 0 |  | 0 | 20 |  |  |  | 47
2024-09-10 | 1016 | sp | L1Z2-GET-1-1-15 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 10 | 10 | 0 |  | 0 | 30 |  |  |  | 47
2024-09-10 | 1017 | sp | L1Z2-GET-1-1-16 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 10 | 10 | 0 |  | 0 | 20 |  |  |  | 47
2024-09-10 | 1018 | sp | L1Z2-GET-1-1-17 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 47
2024-09-10 | 1019 | sp | L1Z2-GET-1-1-18 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 47
2024-09-10 | 1020 | sp | L1Z2-GET-1-1-19 | A | DONE | 4 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 40 | 50 | 0 |  | 0 | 100 |  |  |  | 47
2024-09-10 | 1021 | sp | L1Z2-GET-1-1-20 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-09-10 | Z | 2024-07-25 | 40 | 30 | 0 |  | 0 | 70 |  |  |  | 47
2024-09-10 | 1022 | bth | L1Z2-GET-1-1-21 | A | DONE | 5 | S |  | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 60 | 20 | 30 | F | 0 | 120 |  |  |  | 48
2024-09-10 | 1023 | bth | L1Z2-GET-1-1-22 | A | DONE | 6 | S |  | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 130 | 20 | 0 |  | 0 | 170 |  |  |  | 48
2024-09-10 | 1024 | bth | L1Z2-GET-1-1-23 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 20 | 10 | 0 |  | 0 | 30 |  |  |  | 48
2024-09-10 | 1025 | bth | L1Z2-GET-1-1-24 | A | DONE | 7 | S |  | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 90 | 20 | 70 | F | 0 | 200 |  |  |  | 48
2024-09-10 | 1026 | sp | L1Z2-GET-1-1-25 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 48
2024-09-10 | 1027 | sp | L1Z2-GET-1-1-26 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 48
2024-09-10 | 1028 | sp | L1Z2-GET-1-1-27 | A | DONE | 3 | S | neal | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 48
2024-09-10 | 1029 | bth | L1Z2-GET-1-1-28 | A | DONE | 11 | S | pt.neal | UWRF 6230010 | VD | 2024-09-11 | Z | 2024-07-25 | 100 | 170 | 0 |  | 0 | 280 |  |  |  | 48
2024-09-10 | 1030 | bth | L1Z2-GET-1-1-29 | A | DONE | 4 | S | pt.neal | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 80 | 20 | 0 |  | 0 | 100 |  |  |  | 48
2024-09-10 | 1031 | bth | L1Z2-GET-1-1-30 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 48
2024-09-10 | 1032 | bth | L1Z2-GET-1-1-31 | A | DONE | 3 | S | neal | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 30 | 30 | 0 |  | 0 | 60 |  |  |  | 48
2024-09-10 | 1033 | bth | L1Z2-GET-1-1-32 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 30 | 30 | 0 |  | 0 | 70 |  |  |  | 48
2024-09-10 | 1034 | sp | L1Z2-GET-1-1-33 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 48
2024-09-10 | 1035 | bth | L1Z2-GET-1-1-34 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 30 | 20 | 0 |  | 0 | 60 |  |  |  | 48
2024-09-10 | 1036 | sp | L1Z2-GET-1-1-35 | A | DONE | 4 | S | pt.neal | UWRF 6230010 |  | 2024-09-11 | Z | 2024-07-25 | 40 | 60 | 0 |  | 0 | 100 |  |  |  | 48
2024-09-10 | 1037 | bth | L1Z2-SAT-1-1-12 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 30 | 30 | 30 | F | 40 | 100 |  |  |  | 47
2024-09-10 | 1038 | bth | L1Z2-SAT-1-1-13 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 30 | 0 | 0 |  | 20 | 30 |  |  |  | 47
2024-09-10 | 1039 |  | L1Z2-SAT-1-1-14 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 47
2024-09-09 | 1040 |  | L1Z2-SAT-1-1-15 | A | DONE | 6 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 80 | 0 | 60 | F | 30 | 160 |  |  |  | 47
2024-09-10 | 1041 | bth | L1Z2-SAT-1-1-16 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 40 | 20 | 0 |  | 20 | 50 |  |  |  | 47
2024-09-10 | 1042 | bth | L1Z2-SAT-1-1-17 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 30 | 20 | 0 |  | 20 | 40 |  |  |  | 47
2024-09-10 | 1043 | bth | L1Z2-SAT-1-1-18 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 60 | 20 | 0 |  | 40 | 90 |  |  |  | 47
2024-09-10 | 1044 | bth | L1Z2-SAT-1-1-19 | A | DONE | 4 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 50 | 40 | 0 |  | 30 | 90 |  |  |  | 47
2024-09-10 | 1045 | bth | L1Z2-SAT-1-1-20 | A | DONE | 7 | S |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 80 | 80 | 0 |  | 40 | 160 |  |  |  | 47
2024-09-10 | 1046 | bth | L1Z2-SAT-1-1-21 | A | DONE | 12 | S-M |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 120 | 50 | 120 | F | 60 | 330 |  |  |  | 47
2024-09-10 | 1047 | bth | L1Z2-SAT-1-1-22 | A | DONE | 13 | S-M |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 180 | 70 | 60 | F | 40 | 340 |  |  |  | 47
2024-09-10 | 1048 | bth | L1Z2-SAT-1-1-23 | A | DONE | 14 | S-M |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 120 | 60 | 160 | F | 60 | 380 |  |  |  | 47
2024-09-10 | 1049 | bth | L1Z2-SAT-1-1-24 | A | DONE | 11 | S-M |  | UWRF 6230010 | 1" liner | 2024-09-11 | Z | 2024-07-26 | 130 | 90 | 40 | F | 70 | 280 |  |  |  | 47
2024-09-11 | 1484 |  | 73022 - 73024 | A | DONE | 5 | S-M |  | UW-VET MED 6210014 | reheat coils , VD | 2024-09-12 | Z | 2024-08-15 | 120 | 10 | 0 |  | 0 | 140 |  | 10-C |  | 28 |  |  |  |  | 2024-09-09
2024-09-10 | 1485 |  | 73025 | A | DONE | 3 | S |  | UW-VET MED 6210014 |  | 2024-09-12 | Z | 2024-08-15 | 40 | 0 | 20 | F | 0 | 70 |  | 10-C |  | 28 |  |  |  |  | 2024-09-09
2024-09-13 | 1074 | sp | 82901 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2024-09-16 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 30 |  | KH-1,2 |  | 5
2024-09-10 | 850 |  | 67874 - 67875 | A | DONE | 25 | M |  | WINDSOR 6240012 |  | 2024-09-12 | Z | 2024-08-22 | 220 | 0 | 400 | F | 0 | 600 |  | DOAS 1 1st floor |  | 21 |  |  |  |  | 2024-09-09
2024-09-11 | 851 | sp | 67876 - 67877 | A | DONE | 15 | S-M |  | WINDSOR 6240012 |  | 2024-09-12 | Z | 2024-08-22 | 60 | 310 | 0 |  | 0 | 330 |  | DOAS 1 1st floor |  | 21 |  |  |  |  | 2024-09-09
2024-09-09 | 852 |  | 67878 - 67880 | A | DONE | 29 | M |  | WINDSOR 6240012 |  | 2024-09-12 | Z | 2024-08-22 | 500 | 0 | 210 | F | 0 | 650 |  | DOAS 2 1st floor |  | 21 |  |  |  |  | 2024-09-09
2024-09-11 | 853 | sp | 67881 | A | DONE | 5 | S |  | WINDSOR 6240012 |  | 2024-09-12 | Z | 2024-08-22 | 20 | 100 | 0 |  | 0 | 110 |  | DOAS 2 1st floor |  | 21 |  |  |  |  | 2024-09-09
2024-09-13 | 854 |  | 67882 | A | DONE | 14 | S-M |  | WINDSOR 6240012 |  | 2024-09-16 | Z | 2024-08-23 | 150 | 0 | 190 | F | 0 | 310 |  | 1st fl. EA West |  | 24
2024-09-13 | 855 | sp | 67883 | A | DONE | 13 | S-M |  | WINDSOR 6240012 |  | 2024-09-16 | Z | 2024-08-23 | 30 | 290 | 0 |  | 0 | 290 |  | 1st fl. EA West |  | 24
2024-09-13 | 856 | sp | 67884 - 67885 | A | DONE | 6 | S-M |  | WINDSOR 6240012 |  | 2024-09-16 | Z | 2024-08-23 | 30 | 100 | 0 |  | 0 | 120 |  | 1st fl. EA East |  | 24
2024-09-14 | 857 |  | 67886 | A | DONE | 6 | S-M |  | WINDSOR 6240012 |  | 2024-09-16 | Z | 2024-08-23 | 70 | 0 | 80 | F | 0 | 140 |  | 2nd fl. EA East |  | 24
2024-09-14 | 858 |  | 67887 , 67889 | A | DONE | 28 | S-M |  | WINDSOR 6240012 |  | 2024-09-16 | Z | 2024-08-23 | 310 | 0 | 380 | F | 0 | 680 |  | FCU-120 A/B |  | 24
2024-09-14 | 859 | sp | 67888 , 67890 | A | DONE | 11 | S-M |  | WINDSOR 6240012 |  | 2024-09-16 | Z | 2024-08-23 | 50 | 220 | 0 |  | 0 | 250 |  | FCU-120 A/B |  | 24
2024-09-13 | 1852 |  | 66091 - 66092 | A | DONE | 32 | M |  | WSCC 6240006 | flex , 1" liner | 2024-09-16 | Z | 2024-06-11 | 780 | 0 | 0 |  | 540 | 1250 |  | RTU-Drops |  | 97 | 2024-08-12 | 2024-08-24
2024-09-13 | 1853 |  | 66093 - 66094 | A | DONE | 11 | M |  | WSCC 6240006 | flex , 1" liner | 2024-09-16 | Z | 2024-06-11 | 260 | 0 | 0 |  | 220 | 380 |  | RTU-Drops |  | 97 | 2024-08-12 | 2024-08-24
[6 empty] | 1399 | [13 empty] | 45170 |  |  |  | 3600 | 7.97%
WEEK OF 9-16-2024
2024-09-18 | 3654 |  | 80097 , 80103 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-19 | Z | 2024-07-30 | 50 | 0 | 320 | F | 0 | 380 |  | EF-3,4 , EA-2 |  | 51 |  |  |  |  | 2024-09-16
2024-09-20 | 3684 |  | 80129 | A | DONE | 10 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-09-23 | Z | 2024-08-07 | 250 | 0 | 0 |  | 230 | 290 |  | 3rd floor East unit plenum |  | 47 |  |  |  |  | 2024-09-20
2024-09-20 | 3685 |  | 80130 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-23 | Z | 2024-08-07 | 100 | 0 | 0 |  | 0 | 100 |  | 3rd floor East unit taps |  | 47 |  |  |  |  | 2024-09-20
2024-09-20 | 3687 |  | 80132 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-23 | Z | 2024-08-07 | 20 | 0 | 30 | F | 0 | 50 |  | 3rd floor East unit duct |  | 47 |  |  |  |  | 2024-09-20
2024-09-20 | 3688 |  | 80133 - 80134 | A | DONE | 3 | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-09-23 | Z | 2024-08-07 | 30 | 0 | 30 | F | 40 | 60 |  | HP-300D / 3rd floor TA |  | 47 |  |  |  |  | 2024-09-20
2024-09-19 | 3689 | sp | 80135 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-23 | Z | 2024-08-07 | 20 | 90 | 0 |  | 0 | 100 |  | 3rd floor OA |  | 47 |  |  |  |  | 2024-09-20
2024-09-18 | 3693 |  | Stairwell B-EA 8 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-19 | Z | 2024-08-07 | 80 | 0 | 290 | F | 0 | 450 |  |  |  | 43 |  |  |  |  | 2024-09-16
2024-09-16 | 3699 |  | 96554.2 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-09-19 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 38 |  |  |  |  | 2024-09-16
2024-09-20 | 3914 |  | 81901 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2024-09-25 | Z | 2024-08-12 | 0 | 0 | 30 | F | 30 | 50 |  | 5th Fl. IDF TA | Design Air | 44 |  |  |  |  | 2024-09-26
2024-09-20 | 3915 | sp | 81902 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-23 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 4th Fl. OA | Design Air | 42 |  |  |  |  | 2024-09-20
2024-09-20 | 3916 |  | 81903 - 81904 | A | DONE | 33 | M |  | 121 E. WILSON 6230024 |  | 2024-09-23 | Z | 2024-08-12 | 0 | 0 | 730 | F | 0 | 770 |  | 4th Fl. East EA | Design Air | 42 |  |  |  |  | 2024-09-20
2024-09-16 | 3923 |  | 96554.3 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-09-17 | Z | 2024-09-13 | 50 | 0 | 0 |  | 0 | 170 |  | Caps |  | 4
2024-09-20 | 3907a |  | 80143 - 80144 | A | DONE | 35 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-23 | Z | 2024-08-12 | 0 | 0 | 770 | F | 0 | 810 |  | 5th Fl. West EA | Design Air | 42 |  |  |  |  | 2024-09-20
2024-09-20 | 3915a | sp | 81902 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-25 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 5th Fl. OA | Design Air | 44 |  |  |  |  | 2024-09-26
2024-09-17 | 752 |  | 80212 | A | DONE | 33 | M |  | BMH AHU-9 6240001 | VD | 2024-09-19 | Z | 2024-09-05 | 180 | 0 | 630 | F | 0 | 1170 |  | Temp AHU |  | 14
2024-09-17 | 753 | sp | 80213 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-09-19 | Z | 2024-09-05 | 0 | 40 | 0 |  | 0 | 40 |  | Temp AHU |  | 14
2024-09-16 | 754 |  | 80214 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-09-19 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 20 |  | Curb flashing |  | 13
2024-09-17 | 756 |  | 80216 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-09-18 | Z | 2024-09-17 | 40 | 0 | 0 |  | 0 | 140 |  | Rail caps |  | 1
2024-09-17 | 757 |  | 67217 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-09-18 | Z | 2024-09-17 | 20 | 0 | 0 |  | 0 | 30 |  | Loading Docks |  | 1
2024-09-19 | 3446 | bth | L7-A-EAMP-008 | A | DONE | 30 | M | neal | CDIS 6220028 | 1" DW | 2024-09-20 | Z | 2024-08-19 | 710 | 30 | 0 |  | 110 | 1220 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 3447 | bth | L7-A-EAMP-009 | A | DONE | 16 | S-M | neal | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 130 | 30 | 220 | F | 0 | 450 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 3448 | bth | L7-A-EAMP-010 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 40 | 40 | 110 | F | 0 | 220 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 3449 | bth | L7-A-EAMP-011 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 80 | 60 | 0 |  | 0 | 160 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4300 | bth | L7-A-EAMP-012 | A | DONE | 8 | S-M | neal | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 90 | 20 | 90 | F | 0 | 250 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4301 | bth | L7-A-EAMP-013 | A | DONE | 6 | S-M | neal | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 50 | 30 | 70 | F | 0 | 180 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4302 | bth | L7-A-SAMP-017 | A | DONE | 25 | M |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 140 | 60 | 420 | F | 0 | 1010 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4303 | bth | L7-A-SAMP-018 | A | DONE | 18 | S-M |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 240 | 20 | 170 | F | 0 | 550 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4304 | bth | L7-A-SAMP-019 | A | DONE | 14 | S-M |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 30 | 40 | 260 | F | 0 | 440 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4305 | bth | L7-A-SAMP-020 | A | DONE | 9 | S-M |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 60 | 30 | 120 | F | 0 | 250 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4306 | bth | L7-A-SAMP-021 | A | DONE | 12 | S-M |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 20 | 20 | 240 | F | 0 | 330 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4307 | bth | L7-A-SAMP-022 | A | DONE | 10 | S-M |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 90 | 120 | 30 | F | 0 | 250 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4308 | bth | L7-A-SAMP-023 | A | DONE | 29 | S-M |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-19 | 410 | 60 | 250 | F | 0 | 1150 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-19 | 4309 |  | L7-A-SAMP-067 | A | DONE | 2 | S |  | CDIS 6220028 | VD | 2024-09-20 | Z | 2024-08-19 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 32 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-18 | 4351 |  | EA-(10wg)-PH-10 | A | DONE | 45 | L |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-08-22 | 1120 | 0 | 0 |  | 0 | 3500 |  |  |  | 29
2024-09-16 | 4374 |  | 61367 | A | DONE | 2 | S |  | CDIS 6220028 | 1" liner | 2024-09-19 | Z | 2024-09-06 | 20 | 0 | 0 |  | 20 | 20 |  | 3rd floor |  | 13
2024-09-17 | 4378 | w | 69948 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-09-11 | 40 | 0 | 0 |  | 0 | 120 |  | 7th Floor telecom |  | 9
2024-09-19 | 4379 | w | 95582 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-20 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 9
2024-09-19 | 4388 |  | 69949 | A | DONE | 15 | S-M | neal | CDIS 6220028 |  | 2024-09-20 | Z | 2024-09-11 | 360 | 0 | 0 |  | 0 | 410 |  | 7th floor |  | 9
2024-09-16 | 4389 |  | 61368 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-16 | Z | 2024-09-12 | 20 | 0 | 0 |  | 0 | 50 |  | C-Channel |  | 4
2024-09-16 | 4390 |  | 61369 | A | DONE | n/a | S |  | CDIS 6220028 |  | 2024-09-17 | Z | 2024-09-13 | 0 | 0 | 0 |  | 0 | 0 |  | DM Frames |  | 4
2024-09-19 | 4391 |  | 61370 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-09-20 | Z | 2024-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | 4th floor CB |  | 4
2024-09-18 | 4349a | sp | EA-(10wg)-PH-03 | A | DONE | 22 | M-L |  | CDIS 6220028 | spiralmates , partial | 2024-09-20 | Z | 2024-08-26 | 310 | 220 | 0 |  | 0 | 1000 |  |  |  | 25 | 2024-09-20 |  |  |  | 2024-09-19
2024-09-18 | 825a |  | NC-SAMP-005 | A | DONE | 20 | M-L |  | CDIS 6220028 | partial | 2024-09-19 | Z | 2024-08-27 | 480 | 0 | 0 |  | 0 | 1700 |  |  |  | 23 |  |  |  |  | 2024-09-17
2024-09-18 | 827a |  | NC-EAD-002 | A | DONE | 20 | M-L |  | CDIS 6220028 | partial | 2024-09-19 | Z | 2024-08-27 | 480 | 0 | 0 |  | 0 | 1720 |  |  |  | 23 |  |  |  |  | 2024-09-17
2024-09-18 | 276 |  | 31603 | A | DONE | 5 | S-M |  | COMPASS HP 4230088 | paint | 2024-09-19 | Z | 2024-09-12 | 120 | 0 | 0 |  | 130 | 140 |  | TA |  | 7
2024-09-19 | 278 |  | 70230 | A | DONE | 5 | S-M |  | EAGER LIBRARY 10057782 |  | 2024-09-23 | Z | 2024-09-16 | 60 | 0 | 60 | F | 0 | 120 |  | SA |  | 7
2024-09-20 | 4054 | sp | L2-EAD-Z3-0038 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 20 | 70 | 0 |  | 0 | 100 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-17 | 4062 |  | L2-SALP-Z2-0017 | A | DONE | 12 | S |  | EXACT TL-5 6240014 |  | 2024-09-18 | Z | 2024-09-09 | 240 | 0 | 50 | F | 0 | 370 |  |  |  | 9
2024-09-18 | 4063 | bth | L2-SALP-Z2-0018 | A | DONE | 21 | M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 180 | 50 | 290 | F | 0 | 690 |  |  |  | 10
2024-09-17 | 4064 | bth | L2-SALP-Z2-0019 | A | DONE | 17 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-18 | Z | 2024-09-09 | 100 | 100 | 210 | F | 0 | 490 |  |  |  | 9
2024-09-18 | 4065 | bth | L2-SALP-Z2-0020 | A | DONE | 25 | M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 400 | 170 | 50 | F | 0 | 840 |  |  |  | 10
2024-09-18 | 4066 | bth | L2-SALP-Z2-0021 | A | DONE | 18 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 180 | 100 | 150 | F | 0 | 590 |  |  |  | 10
2024-09-18 | 4067 | bth | L2-SALP-Z2-0022 | A | DONE | 20 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 280 | 80 | 130 | F | 0 | 640 |  |  |  | 10
2024-09-17 | 4068 | bth | L2-SALP-Z2-0023 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-18 | Z | 2024-09-09 | 170 | 70 | 50 | F | 0 | 350 |  |  |  | 9
2024-09-17 | 4069 | bth | L2-SALP-Z2-0024 | A | DONE | 16 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 100 | 190 | 90 | F | 0 | 450 |  |  |  | 10
2024-09-18 | 4070 | bth | L2-SALP-Z2-0025 | A | DONE | 15 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 40 | 290 | 30 | F | 0 | 410 |  |  |  | 10
2024-09-17 | 4071 | bth | L2-SALP-Z2-0026 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 30 | 20 | 110 | F | 0 | 170 |  |  |  | 10
2024-09-17 | 4073 |  | L2-SALP-Z2-0028 | A | DONE | 14 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 250 | 0 | 90 | F | 0 | 410 |  |  |  | 10
2024-09-18 | 4074 |  | L2-SALP-Z2-0029 | A | DONE | 13 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 160 | 0 | 150 | F | 0 | 400 |  |  |  | 10
2024-09-17 | 4075 |  | L2-SALP-Z2-0030 | A | DONE | 20 | M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 70 | 0 | 410 | F | 0 | 690 |  |  |  | 10
2024-09-17 | 4076 |  | L2-SALP-Z2-0031 | A | DONE | 13 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 100 | 0 | 210 | F | 0 | 370 |  |  |  | 10
2024-09-17 | 4077 |  | L2-SALP-Z2-0032 | A | DONE | 4 | S |  | EXACT TL-5 6240014 | CD | 2024-09-19 | Z | 2024-09-09 | 100 | 0 | 0 |  | 0 | 120 |  |  |  | 10
2024-09-17 | 4078 |  | L2-SALP-Z2-0033 | A | DONE | 11 | S-M |  | EXACT TL-5 6240014 | CD | 2024-09-19 | Z | 2024-09-09 | 270 | 0 | 0 |  | 0 | 340 |  |  |  | 10
2024-09-17 | 4079 |  | L2-SALP-Z2-0034 | A | DONE | 11 | S-M |  | EXACT TL-5 6240014 | CD | 2024-09-19 | Z | 2024-09-09 | 260 | 0 | 0 |  | 0 | 290 |  |  |  | 10
2024-09-17 | 4080 |  | L2-SALP-Z2-0035 | A | DONE | 10 | S-M |  | EXACT TL-5 6240014 | CD | 2024-09-19 | Z | 2024-09-09 | 250 | 0 | 0 |  | 0 | 290 |  |  |  | 10
2024-09-17 | 4081 |  | L2-RAD-Z2-0003 | A | DONE | 20 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 340 | 0 | 160 | F | 0 | 600 |  |  |  | 10
2024-09-17 | 4082 |  | L2-RAD-Z2-0004 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 100 | 0 | 70 | F | 0 | 200 |  |  |  | 10
2024-09-17 | 4083 |  | L2-RAD-Z2-0005 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 190 | 0 | 110 | F | 0 | 350 |  |  |  | 10
2024-09-17 | 4084 |  | L2-RAD-Z2-0006 | A | DONE | 6 | S |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 100 | 0 | 40 | F | 0 | 160 |  |  |  | 10
2024-09-17 | 4085 | sp | L2-EAD-Z2-0022 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-09-19 | Z | 2024-09-09 | 40 | 70 | 0 |  | 0 | 120 |  |  |  | 10
2024-09-18 | 4087 |  | 79059 - 79060 | A | DONE | 8 | S-M |  | EXACT TL-5 6240014 | flex | 2024-09-19 | Z | 2024-09-10 | 180 | 0 | 0 |  | 0 | 290 |  | BCU SALP |  | 9
2024-09-17 | 4089 |  | 62537 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-09-18 | Z | 2024-09-10 | 20 | 0 | 0 |  | 0 | 20 |  | Hetos |  | 8
2024-09-17 | 4090 | bth | 79061 - 79063 | A | DONE | 4 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-18 | Z | 2024-09-10 | 60 | 20 | 0 |  | 0 | 110 |  | Misc |  | 8
2024-09-17 | 4407 |  | 79064 - 79065 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-09-18 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 20 |  | EAD |  | 7
2024-09-19 | 279 | sp | 64976 | A | DONE | 2 | S |  | HOLY WISDOM 6220019 |  | 2024-09-23 | Z | 2024-09-18 | 20 | 0 | 0 |  | 0 | 20 |  | BCU-5 OA |  | 5
2024-09-18 | 3369 |  | 78632 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 | bird s. | 2024-09-19 | Z | 2024-09-11 | 50 | 0 | 0 |  | 0 | 150 |  | Louver damper |  | 8
2024-09-16 | 3371 |  | 78637 | A | DONE | 2 | S | alum/nl | JANESVILLE ESSR 6230011 |  | 2024-09-17 | Z | 2024-09-16 | 30 | 0 | 0 |  | 0 | 50 |  | PM pick up |  | 1
2024-09-20 | 277 |  | 82903 | A | DONE | 5 | S-M | neal | JASON S. 1000378 | liner | 2024-09-23 | Z | 2024-09-12 | 180 | 0 | 0 |  | 0 | 400 |  | Cap |  | 11
2024-09-17 | 1920 |  | 82407 | A | DONE | 2 | S |  | JPC OFFICE 6240002 | 1" liner | 2024-09-18 | Z | 2024-09-13 | 30 | 0 | 0 |  | 30 | 40 |  | VAV 1-2 Drops |  | 5
2024-09-17 | 1921 |  | 82408 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-09-18 | Z | 2024-09-13 | 40 | 0 | 0 |  | 0 | 50 |  | VAV 1 |  | 5
2024-09-18 | 1922 |  | 82409 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-09-19 | Z | 2024-09-18 | 20 | 0 | 0 |  | 0 | 30 |  | VAV-1 offset |  | 1
2024-09-20 | 2344 |  | 64708 | A | DONE | 2 | S |  | KOHL CENTER 8210034 |  | 2024-09-27 | Z | 2024-09-13 | 30 | 0 | 0 |  | 0 | 60 |  | Water stop |  | 14
2024-09-19 | 1147 |  | 56599 - 56600 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2024-09-20 | Z | 2024-09-17 | 20 | 0 | 0 |  | 0 | 50 |  | 3rd floor / spec 121 |  | 3
2024-09-16 | 3104 |  | 79623 - 79624 | A | DONE | 10 | S-M | neal | PECATONICA 6240005 | VD , 2" liner | 2024-09-16 | Z | 2024-05-24 | 250 | 0 | 0 |  | 50 | 310 |  | Gym SA |  | 115 | 2024-10-07
2024-09-20 | 3121 |  | 81001 | A | DONE | 8 | S-M |  | PECATONICA 6240005 | 2" liner | 2024-09-23 | Z | 2024-08-01 | 190 | 0 | 0 |  | 160 | 480 |  | AHU-2 SA |  | 53
2024-09-16 | 3122 | sp | 81002 - 81004 | A | DONE | 21 | M |  | PECATONICA 6240005 | oval , accuflange | 2024-09-16 | Z | 2024-08-01 | 120 | 390 | 0 |  | 0 | 710 |  | AHU-2 SA |  | 46
2024-09-20 | 3123 |  | DH0003 - DH0004 | A | DONE | 2 | S-M |  | PECATONICA 6240005 |  | 2024-09-23 | Z | 2024-08-01 | 30 | 0 | 0 |  | 0 | 70 |  | pre-fab hangers |  | 53
2024-09-20 | 3126 |  | 81006 - 81007 | A | DONE | 11 | S-M |  | PECATONICA 6240005 |  | 2024-09-23 | Z | 2024-08-05 | 270 | 0 | 0 |  | 0 | 360 |  | AHU-2 |  | 49
2024-09-20 | 3127 |  | 81008 - 81009 | A | DONE | 6 | S-M |  | PECATONICA 6240005 | 1" liner | 2024-09-23 | Z | 2024-08-05 | 90 | 0 | 50 | F | 100 | 150 |  | AHU-2 |  | 49
2024-09-20 | 3128 |  | 81013 - 81014 | A | DONE | 38 | M |  | PECATONICA 6240005 | 2" liner | 2024-09-23 | Z | 2024-08-14 | 510 | 0 | 420 | F | 710 | 1320 |  | AHU-1 |  | 40
2024-09-20 | 3129 |  | 81015 - 81017 | A | DONE | 15 | S-M |  | PECATONICA 6240005 | VD , 1" liner | 2024-09-23 | Z | 2024-08-14 | 240 | 0 | 120 | F | 280 | 470 |  |  |  | 40
2024-09-20 | 3141 |  | 81010 - 81012 | A | DONE | 31 | M |  | PECATONICA 6240005 | 1" liner | 2024-09-23 | Z | 2024-08-08 | 210 | 0 | 560 | F | 660 | 780 |  | AHU-2 RA |  | 46
2024-09-20 | 3142 |  | 80137 - 81038 | A | DONE | 2 | S |  | PECATONICA 6240005 | 2" liner | 2024-09-23 | Z | 2024-09-13 | 20 | 0 | 0 |  | 20 | 30 |  | Gym office RA / SA |  | 10
2024-09-16 | 1628 | sp | 56341 | A | DONE | 2 | S |  | PROMEGA CMC 2240060 |  | 2024-09-17 | Z | 2024-09-13 | 20 | 20 | 0 |  | 0 | 20 |  | Misc |  | 4
2024-09-19 | 1629 |  | 62712 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-23 | Z | 2024-09-16 | 30 | 0 | 0 |  | 0 | 40 |  | VAV tie ins |  | 7
2024-09-16 | 3806 |  | 56346 | A | DONE | 2 | S |  | PROMEGA RPP 6240019 |  | 2024-09-17 | Z | 2024-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | Bathrooms |  | 1
2024-09-18 | 4772 | bth | 61169-71 | A | DONE | 34 | S-M |  | ROCK CO. JAIL 6220018 |  | 2024-09-19 | Z | 2024-08-30 | 140 | 420 | 280 | F | 0 | 890 |  | MISC |  | 20 |  |  |  |  | 2024-09-19
2024-09-18 | 4773 | bth | 61172-76 | A | DONE | 39 | M-L |  | ROCK CO. JAIL 6220018 |  | 2024-09-19 | Z | 2024-08-30 | 140 | 130 | 690 | F | 0 | 1110 |  | MISC |  | 20 |  |  |  |  | 2024-09-19
2024-09-18 | 4774 | bth | 61177-81 | A | DONE | 31 | S-M |  | ROCK CO. JAIL 6220018 | 1"liner | 2024-09-19 | Z | 2024-08-30 | 240 | 100 | 420 | F | 20 | 900 |  | MISC |  | 20 |  |  |  |  | 2024-09-19
2024-09-18 | 4775 |  | 61182 | A | DONE | 3 | S |  | ROCK CO. JAIL 6220018 | paint | 2024-09-19 | Z | 2024-08-30 | 60 | 0 | 0 |  | 70 | 100 |  | Remodel Grilles |  | 20 |  |  |  |  | 2024-09-19
2024-09-20 | 274 |  | 80761 | A | DONE | 2 | S |  | SSM O'KEEFE 8240002 |  | 2024-09-27 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 20 |  | L-channel |  | 16
2024-09-18 | 4277 |  | 79924 | A | DONE | 3 | S |  | ST.BERNARD 2230056 |  | 2024-09-19 | Z | 2024-09-12 | 60 | 0 | 0 |  | 0 | 70 |  | 2nd floor fire damper tie in |  | 7
2024-09-20 | 4278 |  | 79926 | A | DONE | 2 | S |  | ST.BERNARD 2230056 | 1" liner | 2024-09-24 | Z | 2024-09-16 | 50 | 0 | 0 |  | 50 | 70 |  | Fire damper |  | 8
2024-09-19 | 4279 |  | 79927 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-09-24 | Z | 2024-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor |  | 8
2024-09-20 | 4283 | bth | 80039 - 80040 | delete |  | 0 | S-M |  | ST.BERNARD 2230056 |  | 2024-10-02 | Z | 2024-09-18 | 0 | 0 | 0 |  | 0 | 0 |  | 1st floor SA / East |  | 14
2024-09-17 | 3602 |  | 1001 - 1002 | A | DONE | 23 | M |  | STOUGHTON TRAILER 6240015 |  | 2024-09-19 | Z | 2024-09-06 | 560 | 0 | 0 |  | 0 | 900 |  | Roof caps |  | 13
2024-09-17 | 270 |  | 78748 | A | DONE | 6 | S |  | TST COATING 4240025 |  | 2024-09-18 | Z | 2024-09-10 | 150 | 0 | 0 |  | 0 | 250 |  | RTU-2 |  | 8
2024-09-16 | 4556 |  | 96559 | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2024-09-24 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 50 |  | Caps |  | 13
2024-09-19 | 4557 |  | 96561 | A | DONE | 2 | S | BI | UW-LEVY HALL 8230028 |  | 2024-09-24 | Z | 2024-09-18 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 6
2024-09-19 | 4558 |  | 2909 | A | DONE | 2 | S | BI | UW-LEVY HALL 8230028 |  | 2024-09-24 | Z | 2024-09-18 | 20 | 0 | 0 |  | 0 | 50 |  | Caps |  | 6
2024-09-17 | 3599 |  | 79383 | A | DONE | 8 | S |  | UWL-GRAFF 6230017 |  | 2024-09-18 | Z | 2024-08-28 | 230 | 0 | 0 |  | 0 | 380 |  | Relief air RH-1 |  | 21 |  |  |  |  | 2024-09-16
2024-09-16 | 3850 |  | 79384 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2024-09-18 | Z | 2024-08-28 | 60 | 0 | 0 |  | 0 | 120 |  | AHU-5 SA |  | 21 |  |  |  |  | 2024-09-16
2024-09-16 | 3851 |  | 79385 - 79387 | A | DONE | 36 | M |  | UWL-GRAFF 6230017 |  | 2024-09-18 | Z | 2024-08-28 | 880 | 0 | 0 |  | 0 | 1890 |  | AHU-5 OA , Relief air |  | 21 |  |  |  |  | 2024-09-16
2024-09-16 | 3852 |  | 79388 - 79389 | A | DONE | 30 | M |  | UWL-GRAFF 6230017 |  | 2024-09-18 | Z | 2024-08-28 | 750 | 0 | 0 |  | 0 | 1340 |  | AHU-5 RA |  | 21 |  |  |  |  | 2024-09-16
2024-09-17 | 3853 |  | 79390 - 79391 | A | DONE | 33 | M |  | UWL-GRAFF 6230017 |  | 2024-09-18 | Z | 2024-08-28 | 820 | 0 | 0 |  | 0 | 1330 |  | AHU-4 Relief air |  | 21 |  |  |  |  | 2024-09-16
2024-09-16 | 3854 |  | 67918,79393 | A | DONE | 5 | S |  | UWL-GRAFF 6230017 |  | 2024-09-18 | Z | 2024-08-29 | 110 | 0 | 0 |  | 0 | 180 |  | AHU-4-SA/SAT-4-2-1 |  | 18 |  |  |  |  | 2024-09-16
2024-09-19 | 3855 |  | 67921 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-23 | Z | 2024-09-05 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-5-2-4/5 |  | 18
2024-09-19 | 3856 |  | 79394 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-23 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 20 |  | Conv. Back box |  | 17
2024-09-20 | 3857 | w | 79395 | A | DONE | 2 | S | ss | UWL-GRAFF 6230017 |  | 2024-09-23 | Z | 2024-09-06 | 20 | 0 | 0 |  | 0 | 20 |  | FCU-1,2,3 drain pans |  | 17
2024-09-19 | 3858 |  | 67922 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-23 | Z | 2024-09-09 | 20 | 0 | 0 |  | 0 | 20 |  | Misc 5.2.1 |  | 14
2024-09-19 | 3859 |  | 67923 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-23 | Z | 2024-09-10 | 20 | 0 | 0 |  | 20 | 20 |  | Attic Aud SA |  | 13
2024-09-19 | 3860 |  | 67924 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-23 | Z | 2024-09-10 | 20 | 0 | 0 |  | 0 | 30 |  | SAT-5-2-2/7 |  | 13
2024-09-16 | 507 | bth | L1Z2-SAT-1-1-32 | A | DONE | 5 | S | neal | UWRF 6230010 | VD , 1" liner | 2024-09-17 | Z | 2024-07-26 | 50 | 60 | 0 |  | 20 | 130 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 508 | bth | L1Z2-SAT-1-1-33 | A | DONE | 26 | M |  | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-07-26 | 220 | 310 | 120 | F | 40 | 680 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 509 |  | L1Z2-SAT-1-1-34 | A | DONE | 2 | S | neal | UWRF 6230010 | VD , 1" liner | 2024-09-17 | Z | 2024-07-26 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 510 |  | L1Z2-SAT-1-1-35 | A | DONE | 3 | S | neal | UWRF 6230010 | VD , 1" liner | 2024-09-17 | Z | 2024-07-26 | 70 | 0 | 0 |  | 30 | 80 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 511 | bth | L1Z2-SAT-1-1-36 | A | DONE | 3 | S | neal | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-07-26 | 40 | 20 | 0 |  | 20 | 70 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 512 | bth | L1Z2-SAT-1-1-37 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-07-26 | 50 | 20 | 0 |  | 20 | 60 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 513 |  | L1Z2-SAT-1-1-38 | A | DONE | 3 | S | neal | UWRF 6230010 | VD , 1" liner | 2024-09-17 | Z | 2024-07-26 | 60 | 0 | 0 |  | 20 | 70 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 514 | bth | L1Z2-SAT-1-1-39 | A | DONE | 3 | S | pt.neal | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-07-26 | 40 | 30 | 0 |  | 20 | 80 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 515 | bth | L1Z2-SAT-1-1-40 | A | DONE | 3 | S | neal | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-07-26 | 40 | 30 | 0 |  | 20 | 70 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 516 |  | L1Z2-SAT-1-1-41 | A | DONE | 3 | S | neal | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-07-26 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 517 |  | L1Z2-SAT-1-1-42 | A | DONE | 3 | S | neal | UWRF 6230010 | VD , 1" liner | 2024-09-17 | Z | 2024-07-26 | 110 | 0 | 60 | F | 40 | 190 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 518 | bth | L1Z2-SAT-1-1-43 | A | DONE | 6 | S | pt.neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-07-26 | 50 | 60 | 30 | F | 40 | 150 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 519 | bth | L1Z2-SAT-1-1-44 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-17 | Z | 2024-07-26 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 520 |  | L1Z2-SAT-1-1-45 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-17 | Z | 2024-07-26 | 40 | 0 | 0 |  | 20 | 50 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 521 |  | L1Z2-SAT-1-1-57 | A | DONE | 2 | S | neal | UWRF 6230010 | VD , 1" liner | 2024-09-17 | Z | 2024-07-26 | 50 | 0 | 0 |  | 20 | 60 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 522 |  | L1Z2-SAT-1-1-58 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-07-26 | 30 | 0 | 0 |  | 20 | 40 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 523 | bth | L1Z2-SAT-1-1-59 | A | DONE | 18 | M | pt.neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-07-26 | 130 | 250 | 60 | F | 40 | 470 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 524 |  | L1Z2-SAT-1-1-60 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-07-26 | 50 | 0 | 0 |  | 40 | 60 |  |  |  | 53 |  |  |  |  | 2024-09-16
2024-09-16 | 535 |  | L1Z2-TA 5 | A | DONE | 8 | S |  | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-08-02 | 180 | 0 | 0 |  | 140 | 240 |  |  |  | 46
2024-09-16 | 536 |  | L1Z2-TA 6 | A | DONE | 19 | S-M |  | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-08-02 | 460 | 0 | 0 |  | 250 | 540 |  |  |  | 46
2024-09-16 | 537 |  | L1Z2-TA 7 | A | DONE | 4 | S | neal | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-08-02 | 100 | 0 | 0 |  | 80 | 170 |  |  |  | 46
2024-09-16 | 538 | bth | L1Z2-RAT 1-1-1 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-08-02 | 30 | 20 | 0 |  | 0 | 50 |  |  |  | 46
2024-09-16 | 539 | sp | L1Z2-RAT 1-1-2.1 | A | DONE | 4 | S | neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-08-02 | 20 | 70 | 0 |  | 0 | 110 |  |  |  | 46 |  |  |  |  | 2024-09-16
2024-09-16 | 540 | sp | L1Z2-RAT 1-1-2.2 | A | DONE | 8 | S | pt.neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-08-02 | 90 | 90 | 0 |  | 0 | 120 |  |  |  | 46 |  |  |  |  | 2024-09-16
2024-09-16 | 541 |  | L1Z2-RAT 1-1-3 | A | DONE | 9 | S | neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-08-02 | 170 | 20 | 30 | F | 0 | 240 |  |  |  | 46 |  |  |  |  | 2024-09-16
2024-09-16 | 542 |  | L1Z2-RAT 1-1-4 | A | DONE | 23 | M | pt.neal | UWRF 6230010 |  | 2024-09-17 | Z | 2024-08-02 | 570 | 0 | 0 |  | 0 | 680 |  |  |  | 46 |  |  |  |  | 2024-09-16
2024-09-16 | 598 | bth | 66945 - 66946 | A | DONE | 4 | S-M |  | UWRF 6230010 | 1" liner | 2024-09-17 | Z | 2024-09-04 | 60 | 30 | 0 |  | 30 | 100 |  | Misc |  | 13 |  |  |  |  | 2024-09-18
2024-09-16 | 599 |  | 66947 | A | DONE | 5 | S-M | pcd | UWRF 6230010 |  | 2024-09-17 | Z | 2024-09-05 | 100 | 20 | 0 |  | 0 | 130 |  | FEV-3-1-9,20 |  | 12
2024-09-20 | 650 |  | 66948 | A | DONE | 2 | S-M |  | UWRF 6230010 | VD's | 2024-09-24 | Z | 2024-09-05 | 20 | 20 | 0 |  | 0 | 30 |  | Misc |  | 19
2024-09-16 | 653 |  | 93206 | A | DONE | 2 | S | BI | UWRF 6230010 |  | 2024-09-17 | Z | 2024-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | Plate |  | 1
2024-09-21 | 528a |  | L4-SAMP-1 | A | DONE | 88 | L |  | UWRF 6230010 |  | 2024-09-24 | Z | 2024-08-02 | 2190 | 0 | 0 |  | 0 | 4800 |  |  |  | 53 |  |  |  |  | 2024-09-24
2024-09-21 | 528b |  | L4-SAMP-1 | A | DONE | 88 | L |  | UWRF 6230010 |  | 2024-09-24 | Z | 2024-08-02 | 2190 | 0 | 0 |  | 0 | 4800 |  |  |  | 53 | 2024-09-09 |  |  |  | 2024-09-24
2024-09-18 | 5067 |  | RA-01-08 | A | DONE | n/a | L |  | UWSP ALBERTSON 6230016 |  | 2024-09-19 | Z | 2024-07-31 | 0 | 0 | 0 |  | 0 | 0 | 2070 |  | Greater Wisco | 50 | 2024-09-03 | 2024-09-10 |  |  | 2024-09-17
2024-09-18 | 5068 |  | RA-01-09 | A | DONE | n/a | L |  | UWSP ALBERTSON 6230016 | VD | 2024-09-19 | Z | 2024-07-31 | 0 | 0 | 0 |  | 0 | 0 | 2250 |  | Greater Wisco | 50 | 2024-09-03 | 2024-09-10 |  |  | 2024-09-17
2024-09-18 | 5077 | bth | SA-01-07 | A | DONE | n/a | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-09-19 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 1360 |  | Greater Wisco | 38 |  | 2024-09-10 |  |  | 2024-09-17
2024-09-18 | 5078 | bth | SA-01-08 | A | DONE | n/a | M |  | UWSP ALBERTSON 6230016 |  | 2024-09-19 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 690 |  | Greater Wisco | 38 |  | 2024-09-10 |  |  | 2024-09-17
2024-09-18 | 5079 | bth | SA-01-09 | A | DONE | n/a | M |  | UWSP ALBERTSON 6230016 |  | 2024-09-19 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 830 |  | Greater Wisco | 38 |  | 2024-09-10 |  |  | 2024-09-17
2024-09-18 | 5080 | bth | SA-01-10 | A | DONE | n/a | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-09-19 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 1500 |  | Greater Wisco | 38 |  | 2024-09-10 |  |  | 2024-09-17
2024-09-18 | 5081 | bth | SA-01-11 | A | DONE | n/a | M |  | UWSP ALBERTSON 6230016 |  | 2024-09-19 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 780 |  | Greater Wisco | 38 |  | 2024-09-10 |  |  | 2024-09-17
2024-09-20 | 5093 |  | 58797 | A | DONE | 3 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-09-25 | Z | 2024-09-09 | 60 | 0 | 0 |  | 0 | 80 |  | 1st floor EC |  | 16
2024-09-18 | 5094 |  | 58798 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-09-25 | Z | 2024-09-10 | 20 | 0 | 0 |  | 0 | 20 |  | Shims |  | 15
2024-09-16 | 2455 |  | 82701 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-09-17 | Z | 2024-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | End cap |  | 1
2024-09-16 | 1492 |  | 73032 | A | DONE | 15 | S-M |  | UW-VET MED 6210014 |  | 2024-09-17 | Z | 2024-08-22 | 110 | 0 | 250 | F | 0 | 510 |  | 10-C North |  | 26 |  |  |  |  | 2024-09-16
2024-09-17 | 1493 | sp | 73033 | A | DONE | 11 | S-M |  | UW-VET MED 6210014 |  | 2024-09-17 | Z | 2024-08-22 | 40 | 220 | 0 |  | 0 | 240 |  | 10-C North EA |  | 26 |  |  |  |  | 2024-09-16
2024-09-16 | 1494 | sp | 73034 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-09-17 | Z | 2024-08-22 | 20 | 20 | 0 |  | 0 | 40 |  | 10-C North EA |  | 26 |  |  |  |  | 2024-09-16
2024-09-17 | 1495 | sp | 73035 | A | DONE | 10 | S-M |  | UW-VET MED 6210014 |  | 2024-09-17 | Z | 2024-08-22 | 30 | 220 | 0 |  | 0 | 260 |  | 10-C North SA |  | 26 |  |  |  |  | 2024-09-16
2024-09-17 | 1496 |  | 73037 | A | DONE | 2 | S |  | UW-VET MED 6210014 | reheat coils | 2024-09-17 | Z | 2024-08-22 | 50 | 0 | 0 |  | 0 | 100 |  | 10-C North |  | 26 |  |  |  |  | 2024-09-16
2024-09-19 | 1532 |  | 73044 | A | DONE | 2 | S | pt.alum | UW-VET MED 6210014 |  | 2024-09-23 | Z | 2024-09-10 | 50 | 0 | 0 |  | 0 | 50 |  | RH-8-1-49 |  | 13
2024-09-19 | 1533 |  | 73045 | A | DONE | 2 | S | neal | UW-VET MED 6210014 |  | 2024-09-23 | Z | 2024-09-10 | 20 | 0 | 0 |  | 0 | 30 |  | L1-Area 9 |  | 13
2024-09-19 | 1534 |  | 73046 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-09-23 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 20 |  | 10C SA |  | 12
2024-09-18 | 1535 |  | 73048 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-09-19 | Z | 2024-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | Decon Rm |  | 3
2024-09-19 | 1536 |  | 73047 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-09-23 | Z | 2024-09-16 | 40 | 0 | 0 |  | 0 | 50 |  | 10C EA |  | 7
[6 empty] | 1700 | [13 empty] | 61680 |  |  |  | 13880 | 22.5%
WEEK OF 9-23-2024
2024-09-27 | 2241 |  | 80071 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 | paint | 2024-10-01 | Z | 2024-07-25 | 40 | 0 | 150 | F | 20 | 180 |  | DOAS-1 / OA-2 |  | 68
2024-09-27 | 3655 |  | 80084 , 80091 | A | DONE | 16 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-01 | Z | 2024-07-30 | 50 | 0 | 340 | F | 0 | 400 |  | EF-1,2 , EA-3 |  | 63
2024-09-23 | 3686 |  | 80131 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-23 | Z | 2024-08-07 | 100 | 0 | 0 |  | 0 | 90 |  | 3rd floor East unit sliders |  | 47 |  |  |  |  | 2024-09-20
2024-09-26 | 3900 |  | 96554.3 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-10-01 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 50
2024-09-23 | 3903 |  | 80139 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-09-25 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 300 | 4th Fl. West unit plenums | Design Air | 44 |  |  |  |  | 2024-09-26
2024-09-23 | 3904 |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-25 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 90 | 4th Fl. West unit Taps | Design Air | 44 |  |  |  |  | 2024-09-26
2024-09-23 | 3905 |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-09-25 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 250 | 4th Fl. West unit sliders | Design Air | 44 |  |  |  |  | 2024-09-26
2024-09-23 | 3906 |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-09-25 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 160 | 4th Fl. West Corr. HP's | Design Air | 44 |  |  |  |  | 2024-09-26
2024-09-26 | 3909 |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-01 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 4th Fl. East unit plenums | Design Air | 50
2024-09-26 | 3910 |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-01 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 4th Fl. East Taps | Design Air | 50
2024-09-26 | 3911 |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-01 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 4th Fl. East sliders | Design Air | 50
2024-09-25 | 3912 |  | 80149 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-10-01 | Z | 2024-08-12 | 0 | 0 | 30 | F | 0 | 30 |  | 4th Fl. East unit SA | Design Air | 50
2024-09-26 | 3913 |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-01 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 4th Fl. East Corr. HP's | Design Air | 50
2024-09-25 | 3907b |  | 80143 - 80144 | A | DONE | 31 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-01 | Z | 2024-08-12 | 0 | 0 | 770 | F | 0 | 720 |  | 6th Fl. West EA | Design Air | 50
2024-09-23 | 3916a |  | 81903 - 81904 | A | DONE | 34 | M |  | 121 E. WILSON 6230024 |  | 2024-09-25 | Z | 2024-08-12 | 0 | 0 | 730 | F | 0 | 770 |  | 5th Fl. East EA | Design Air | 44 |  |  |  |  | 2024-09-26
2024-09-23 | 280 |  | 192024 | A | DONE | 2 | S | ss | 320 HOLTZMAN 6230005 |  | 2024-09-25 | Z | 2024-09-19 | 20 | 0 | 0 |  | 0 | 20 |  | Channel |  | 6
2024-09-25 | 758 |  | 80217 | A | DONE | 12 | S-M |  | BMH AHU-9 6240001 |  | 2024-09-26 | Z | 2024-09-19 | 280 | 0 | 0 |  | 0 | 350 |  | Loading docks |  | 7
2024-09-25 | 759 | sp | 80218 | A | DONE | 3 | S |  | BMH AHU-9 6240001 |  | 2024-09-26 | Z | 2024-09-19 | 0 | 70 | 0 |  | 0 | 80 |  | Temp AHU |  | 7
2024-09-25 | 760 |  | 67720 - 67721 | A | DONE | 5 | S |  | BMH AHU-9 6240001 |  | 2024-09-26 | Z | 2024-09-19 | 70 | 0 | 50 | F | 0 | 140 |  | VAV's |  | 7
2024-09-25 | 826 |  | NC-EAD-001 | A | DONE | 3 | S |  | CDIS 6220028 | partial | 2024-09-27 | Z | 2024-08-15 | 70 | 0 | 0 |  | 0 | 280 |  |  |  | 43
2024-09-26 | 1450 |  | 69680 | A | DONE | 2 | S-M | neal | CDIS 6220028 |  | 2024-10-01 | Z | 2024-09-19 | 30 | 0 | 0 |  | 0 | 40 |  | 6th floor EA |  | 12
2024-09-26 | 1451 |  | 69681 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-01 | Z | 2024-09-19 | 20 | 0 | 0 |  | 0 | 30 |  | SA N Core |  | 12
2024-09-23 | 1452 | sp | 69682 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-01 | Z | 2024-09-19 | 20 | 0 | 0 |  | 0 | 20 |  | CB Rm 6558 |  | 12
2024-09-25 | 1453 |  | 69683 - 69684 | A | DONE | 2 | S-M | neal | CDIS 6220028 |  | 2024-10-01 | Z | 2024-09-20 | 40 | 0 | 0 |  | 0 | 40 |  | Rm 6570 CB |  | 11
2024-09-26 | 1454 |  | 69685 | A | DONE | 2 | S | neal | CDIS 6220028 | 1" liner | 2024-10-01 | Z | 2024-09-20 | 20 | 0 | 0 |  | 20 | 20 |  | SALP 64 |  | 11
2024-09-25 | 1455 | w | 95584 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-01 | Z | 2024-09-23 | 20 | 0 | 0 |  | 0 | 20 |  | Plate |  | 8
2024-09-23 | 1456 |  | 61371 | A | DONE | 2 | S |  | CDIS 6220028 | DM Frames | 2024-09-27 | Z | 2024-09-23 | 0 | 0 | 0 |  | 0 | 0 |  | DM Frames |  | 4
2024-09-25 | 4322 | bth | L7-A-EALP-026 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 | paint | 2024-09-27 | Z | 2024-08-20 | 60 | 50 | 0 |  | 0 | 140 |  |  |  | 38
2024-09-24 | 4323 | sp | L7-A-EALP-027 | A | DONE | 4 | S-M |  | CDIS 6220028 |  | 2024-09-27 | Z | 2024-08-20 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 38
2024-09-25 | 4324 | bth | L7-A-EALP-028 | A | DONE | 2 | S-M |  | CDIS 6220028 | 1" spiral acoustic. | 2024-09-27 | Z | 2024-08-20 | 20 | 30 | 0 |  | 20 | 50 |  |  |  | 38
2024-09-25 | 4325 | bth | L7-A-EALP-029 | A | DONE | 4 | S-M | neal | CDIS 6220028 | paint | 2024-09-27 | Z | 2024-08-20 | 60 | 40 | 0 |  | 0 | 120 |  |  |  | 38
2024-09-25 | 4326 | bth | L7-A-EALP-030 | A | DONE | 6 | S-M | pt.neal | CDIS 6220028 | paint | 2024-09-27 | Z | 2024-08-20 | 60 | 20 | 50 | F | 20 | 150 |  |  |  | 38
2024-09-24 | 4328 | sp | L7-A-EALP-037 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-09-27 | Z | 2024-08-20 | 20 | 50 | 0 |  | 0 | 50 |  |  |  | 38
2024-09-25 | 4329 | sp | L7-A-EALP-038 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-09-27 | Z | 2024-08-20 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 38
2024-09-25 | 4330 | bth | L7-A-EALP-039 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 | paint , VD | 2024-09-27 | Z | 2024-08-20 | 50 | 70 | 0 |  | 0 | 140 |  |  |  | 38
2024-09-25 | 4331 | bth | L7-A-SALP-035 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 60 | 40 | 0 |  | 30 | 130 |  |  |  | 38
2024-09-25 | 4332 | bth | L7-A-SALP-036 | A | DONE | 6 | S-M | neal | CDIS 6220028 | paint , VD , 1" liner | 2024-09-27 | Z | 2024-08-20 | 90 | 60 | 0 |  | 30 | 170 |  |  |  | 38
2024-09-25 | 4333 | bth | L7-A-SALP-037 | A | DONE | 5 | S-M | pt.neal | CDIS 6220028 | paint , 1" liner | 2024-09-27 | Z | 2024-08-20 | 90 | 30 | 0 |  | 40 | 140 |  |  |  | 38
2024-09-25 | 4334 | bth | L7-A-SALP-038 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 40 | 70 | 0 |  | 20 | 120 |  |  |  | 38
2024-09-25 | 4335 | bth | L7-A-SALP-039 | A | DONE | 6 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 50 | 80 | 0 |  | 20 | 120 |  |  |  | 38
2024-09-25 | 4336 | bth | L7-A-SALP-040 | A | DONE | 8 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 100 | 80 | 0 |  | 30 | 190 |  |  |  | 38
2024-09-25 | 4337 | bth | L7-A-SALP-041 | A | DONE | 5 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 50 | 70 | 0 |  | 20 | 120 |  |  |  | 38
2024-09-25 | 4338 | bth | L7-A-SALP-042 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 40 | 60 | 0 |  | 20 | 100 |  |  |  | 38
2024-09-25 | 4339 | bth | L7-A-SALP-043 | A | DONE | 4 | S-M |  | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 40 | 40 | 0 |  | 20 | 80 |  |  |  | 38
2024-09-25 | 4340 | bth | L7-A-SALP-044 | A | DONE | 5 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 90 | 30 | 0 |  | 50 | 170 |  |  |  | 38
2024-09-25 | 4341 | bth | L7-A-SALP-045 | A | DONE | 8 | S-M | neal | CDIS 6220028 | 1" liner | 2024-09-27 | Z | 2024-08-20 | 90 | 90 | 0 |  | 60 | 210 |  |  |  | 38
2024-09-25 | 4352 |  | EA-(10wg)-PH-11 | A | DONE | 21 | M-L |  | CDIS 6220028 |  | 2024-09-26 | Z | 2024-08-22 | 520 | 0 | 0 |  | 0 | 1620 |  |  |  | 35 |  |  |  |  | 2024-09-30
2024-09-27 | 4358 |  | OA-(4wg)-PH-11 | A | DONE | 50 | M-L |  | CDIS 6220028 |  | 2024-10-01 | Z | 2024-08-27 | 800 | 0 | 440 | F | 0 | 2190 |  |  |  | 35
2024-09-27 | 4359 |  | EA-(-6wg)-PH-02 | A | DONE | 28 | M |  | CDIS 6220028 |  | 2024-10-01 | Z | 2024-08-27 | 550 | 0 | 150 | F | 0 | 1310 |  |  |  | 35
2024-09-26 | 4373 |  | 69827 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-10-01 | Z | 2024-09-06 | 40 | 0 | 0 |  | 20 | 60 |  | SA-PH-07 |  | 25
2024-09-27 | 4381 |  | OA (4wg )-PH-010 | A | DONE | 39 | M-L |  | CDIS 6220028 | partial | 2024-10-03 | Z | 2024-09-11 | 800 | 0 | 160 | F | 0 | 1710 |  |  |  | 22
2024-09-27 | 4382 |  | SA (4wg )-PH-07 | A | DONE | 12 | M |  | CDIS 6220028 |  | 2024-10-03 | Z | 2024-09-11 | 200 | 0 | 100 | F | 0 | 490 |  |  |  | 22
2024-09-27 | 4392 |  | EA(-10wg )-PH-01 | A | DONE | 98 | L |  | CDIS 6220028 | 1" DW | 2024-10-01 | Z | 2024-09-17 | 2280 | 150 | 0 |  | 540 | 4650 |  |  |  | 14
2024-09-23 | 4393 |  | 69950 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-24 | Z | 2024-09-18 | 30 | 0 | 0 |  | 0 | 70 |  | 7th floor |  | 6
2024-09-24 | 4394 |  | 61318 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-01 | Z | 2024-09-18 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor NC |  | 13
2024-09-25 | 4396 |  | 69830 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-03 | Z | 2024-09-18 | 20 | 0 | 0 |  | 0 | 50 |  | PH hangers |  | 15
2024-09-26 | 4397 |  | 69675 - 69678 | A | DONE | 2 | S-M | pt.neal | CDIS 6220028 |  | 2024-10-01 | Z | 2024-09-18 | 50 | 0 | 0 |  | 20 | 80 |  | Misc |  | 13
2024-09-23 | 4398 |  | 69679 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-24 | Z | 2024-09-18 | 20 | 0 | 0 |  | 0 | 30 |  | 7th floor |  | 6
2024-09-23 | 4399 | sp | 61319 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-09-27 | Z | 2024-09-19 | 0 | 20 | 0 |  | 0 | 20 |  | 3rd floor EA Rm. 3544 |  | 8
2024-09-25 | 4346a |  | SA-(10wg)-PH-01 | A | DONE | 196 | L |  | CDIS 6220028 | partial , 1" DW | 2024-09-26 | Z | 2024-08-26 | 3050 | 0 | 1850 | F | 3100 | 9220 |  | 2nd half of spool |  | 31 |  |  |  |  | 2024-09-30
2024-09-25 | 4347a |  | EA-(6wg)-PH-01 | A | DONE | 62 | M-L |  | CDIS 6220028 | partial | 2024-09-26 | Z | 2024-08-26 | 1330 | 0 | 220 | F | 0 | 3060 |  | 2nd half of spool |  | 31 |  |  |  |  | 2024-09-30
2024-09-23 | 4348a |  | EA(-10wg )-PH-02 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-09-25 | Z | 2024-08-26 | 40 | 0 | 0 |  | 0 | 80 |  |  |  | 30
2024-09-23 | 825b |  | NC-SAMP-005 | A | DONE | 19 | M-L |  | CDIS 6220028 | partial | 2024-09-25 | Z | 2024-08-27 | 460 | 0 | 0 |  | 0 | 1590 |  |  |  | 29 |  |  |  |  | 2024-09-24
2024-09-25 | 825c |  | NC-SAMP-005 | A | DONE | 17 | M-L |  | CDIS 6220028 | partial | 2024-09-30 | Z | 2024-08-27 | 420 | 0 | 0 |  | 0 | 1470 |  |  |  | 34
2024-09-23 | 827b |  | NC-EAD-002 | A | DONE | 19 | M-L |  | CDIS 6220028 | partial | 2024-09-25 | Z | 2024-08-27 | 460 | 0 | 0 |  | 0 | 1590 |  |  |  | 29 |  |  |  |  | 2024-09-24
2024-09-25 | 827c |  | NC-EAD-002 | A | DONE | 15 | M-L |  | CDIS 6220028 | partial | 2024-09-30 | Z | 2024-08-27 | 360 | 0 | 0 |  | 0 | 1050 |  |  |  | 34
2024-09-24 | 283 |  | 83155 | A | DONE | 2 | S |  | CESA 5 4240015 | bird s. | 2024-09-24 | Z | 2024-09-24 | 30 | 0 | 0 |  | 0 | 40 |  | Misc |  | 0
2024-09-27 | 801 | w | 1128 | A | DONE | 4 | S-M |  | DELLSHIRE 6240017 |  | 2024-10-08 | Z | 2024-09-24 | 80 | 0 | 0 |  | 0 | 180 |  | Sleeves |  | 14
2024-09-23 | 281 |  | 83152 | A | DONE | 2 | S |  | ENCAPSYS 10057814 |  | 2024-09-25 | Z | 2024-09-20 | 20 | 0 | 0 |  | 0 | 20 |  | HP Bern. 2 |  | 5
2024-09-24 | 4416 |  | 79072 | A | DONE | 3 | S-M |  | EXACT SP L-3 2230023 |  | 2024-09-25 | Z | 2024-09-18 | 40 | 30 | 0 |  | 0 | 80 |  | EA |  | 7
2024-09-23 | 4044 |  | L2-EAD-Z3-0026 | A | DONE | 14 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 230 | 0 | 110 | F | 0 | 410 |  |  |  | 22 | 2024-09-18 |  |  |  | 2024-09-18
2024-09-23 | 4045 |  | L2-EAD-Z3-0029 | A | DONE | 7 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 80 | 0 | 90 | F | 0 | 200 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4046 | bth | L2-EAD-Z3-0030 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 70 | 30 | 0 |  | 0 | 110 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4049 |  | L2-EAD-Z3-0033 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 40 | 50 | 0 |  | 0 | 110 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4050 |  | L2-EAD-Z3-0034 | A | DONE | 10 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 130 | 20 | 90 | F | 0 | 300 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4051 | sp | L2-EAD-Z3-0035 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 40 | 120 | 0 |  | 0 | 180 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4052 | bth | L2-EAD-Z3-0036 | A | DONE | 2 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4053 |  | L2-EAD-Z3-0037 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 50 | 20 | 20 | F | 0 | 80 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4055 |  | L2-RAD-Z3-0007 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 130 | 0 | 40 | F | 0 | 200 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4056 |  | L2-RAD-Z3-0008 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 170 | 0 | 0 |  | 0 | 200 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4057 |  | L2-RAD-Z3-0009 | A | DONE | 10 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 130 | 0 | 100 | F | 0 | 280 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4058 | bth | L2-SAMP-Z3-0018 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 70 | 20 | 0 |  | 0 | 100 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-24 | 4059 | bth | L2-SAMP-Z3-0019 | A | DONE | 9 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 120 | 20 | 80 | F | 0 | 250 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-24 | 4060 | bth | L2-SAMP-Z3-0020 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-04 | 60 | 20 | 0 |  | 0 | 80 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-23 | 4061 |  | L2-TAD-Z3-0002 | A | DONE | 2 | S |  | EXACT TL-5 6240014 | 1" liner | 2024-09-26 | Z | 2024-09-04 | 50 | 0 | 0 |  | 30 | 70 |  |  |  | 22 |  |  |  |  | 2024-09-18
2024-09-24 | 4091 |  | L2-RAD-Z3-0010 | A | DONE | 6 | S |  | EXACT TL-5 6240014 | VD | 2024-09-26 | Z | 2024-09-10 | 100 | 0 | 40 | F | 0 | 160 |  |  |  | 16
2024-09-24 | 4092 |  | L2-SAMP-Z3-0021 | A | DONE | 23 | M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 270 | 0 | 300 | F | 0 | 940 |  |  |  | 16
2024-09-24 | 4093 | bth | L2-SALP-Z3-0028 | A | DONE | 25 | M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 260 | 70 | 290 | F | 0 | 810 |  |  |  | 16
2024-09-24 | 4094 | bth | L2-SALP-Z3-0029 | A | DONE | 16 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 160 | 110 | 130 | F | 0 | 490 |  |  |  | 16
2024-09-24 | 4095 | bth | L2-SALP-Z3-0030 | A | DONE | 15 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 50 | 110 | 210 | F | 0 | 480 |  |  |  | 16
2024-09-24 | 4096 | bth | L2-SALP-Z3-0031 | A | DONE | 10 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 120 | 20 | 100 | F | 0 | 260 |  |  |  | 16
2024-09-24 | 4097 | bth | L2-SALP-Z3-0032 | A | DONE | 11 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 90 | 70 | 100 | F | 0 | 300 |  |  |  | 16
2024-09-24 | 4098 |  | L2-SALP-Z3-0033 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 110 | 0 | 0 |  | 0 | 160 |  |  |  | 16
2024-09-24 | 4099 | bth | L2-SALP-Z3-0034 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 16
2024-09-24 | 4400 | bth | L2-SALP-Z3-0035 | A | DONE | 9 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 100 | 30 | 80 | F | 0 | 170 |  |  |  | 16
2024-09-24 | 4401 | bth | L2-SALP-Z3-0036 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 30 | 80 | 0 |  | 0 | 120 |  |  |  | 16
2024-09-24 | 4402 | bth | L2-SALP-Z3-0037 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 50 | 150 | 100 | F | 0 | 360 |  |  |  | 16
2024-09-24 | 4403 |  | L2-SALP-Z3-0038 | A | DONE | 12 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 240 | 0 | 50 | F | 0 | 420 |  |  |  | 16
2024-09-24 | 4404 |  | L2-SALP-Z3-0039 | A | DONE | 14 | S-M |  | EXACT TL-5 6240014 | CD | 2024-09-26 | Z | 2024-09-10 | 300 | 0 | 40 | F | 0 | 410 |  |  |  | 16
2024-09-24 | 4405 |  | L2-SALP-Z3-0040 | A | DONE | 13 | S-M |  | EXACT TL-5 6240014 | CD | 2024-09-26 | Z | 2024-09-10 | 270 | 0 | 50 | F | 0 | 430 |  |  |  | 16
2024-09-24 | 4406 |  | L2-SALP-Z3-0041 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-10 | 80 | 0 | 0 |  | 0 | 100 |  |  |  | 16
2024-09-23 | 4408 | bth | 79068 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2024-09-26 | Z | 2024-09-12 | 20 | 40 | 0 |  | 0 | 80 |  | EA outs Z1 |  | 14
2024-09-25 | 4409 |  | email | A | DONE | 4 | S |  | EXACT TL-5 6240014 | VD's | 2024-09-30 | Z | 2024-09-12 | 80 | 0 | 0 |  | 0 | 140 |  | Damper / EC |  | 18
2024-09-23 | 4410 |  | 79067 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-09-25 | Z | 2024-09-13 | 20 | 0 | 0 |  | 0 | 20 |  | SAMP |  | 12
2024-09-23 | 4411 |  | 79069 | A | DONE | 2 | S | alum | EXACT TL-5 6240014 |  | 2024-09-25 | Z | 2024-09-13 | 30 | 0 | 0 |  | 0 | 30 |  | EAD |  | 12
2024-09-23 | 4412 |  | 79070 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-09-25 | Z | 2024-09-13 | 40 | 0 | 0 |  | 0 | 80 |  | SAMP |  | 12
2024-09-23 | 4413 |  | L2-SALP-Z2-0023 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-25 | Z | 2024-09-18 | 20 | 60 | 0 |  | 0 | 80 |  |  |  | 7
2024-09-23 | 4414 |  | L2-EAD-Z2-0027 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-09-25 | Z | 2024-09-18 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 7
2024-09-24 | 4415 |  | 79071 | A | DONE | 5 | S-M |  | EXACT TL-5 6240014 |  | 2024-09-25 | Z | 2024-09-18 | 110 | 0 | 0 |  | 0 | 160 |  | SALP |  | 7
2024-09-27 | 4417 | sp | 79074 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-10-02 | Z | 2024-09-25 | 20 | 100 | 0 |  | 0 | 140 |  | HP SA |  | 7
2024-09-25 | 3372 |  | 78638 | A | DONE | 2 | S |  | JANESVILLE ESSR 6230011 |  | 2024-09-27 | Z | 2024-09-25 | 20 | 0 | 0 |  | 0 | 20 |  | Grille box |  | 2
2024-09-25 | 3373 |  | 78639 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-09-27 | Z | 2024-09-25 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 2
2024-09-26 | 3374 |  | 70839 | A | DONE | 2 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-09-27 | Z | 2024-09-26 | 20 | 0 | 0 |  | 0 | 20 |  | Plate |  | 1
2024-09-24 | 282 | sp | 83154 | A | DONE | 2 | S |  | JHT HR 10057934 |  | 2024-09-27 | Z | 2024-09-23 | 20 | 20 | 0 |  | 0 | 40 |  | Misc |  | 4
2024-09-27 | 1129 | bth | 55339 - 55341 | A | DONE | 88 | L | ss | LABCORP 6240016 |  | 2024-09-27 | Z | 2024-09-09 | 850 | 540 | 800 | F | 0 | 2250 |  | 3rd floor EA LP |  | 18 | 2024-10-07
2024-09-23 | 273 | sp | 80353 - 80354 | A | DONE | 4 | S-M |  | MENDOTA FOODS 6220027 |  | 2024-09-27 | Z | 2024-09-11 | 60 | 40 | 0 |  | 0 | 100 |  | EA Dishwasher |  | 16
2024-09-27 | 2650 |  | 5678 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2024-10-08 | Z | 2024-09-26 | 20 | 0 | 0 |  | 0 | 50 |  | Sleeves |  | 12
2024-09-27 | 286 |  | 31605 | A | DONE | 3 | S-M |  | MPI 10057152 | filter rack | 2024-10-02 | Z | 2024-09-25 | 70 | 0 | 0 |  | 0 | 80 |  | Furnace |  | 7
2024-09-27 | 3130 |  | 81018 - 81019 | A | DONE | 17 | S-M |  | PECATONICA 6240005 |  | 2024-10-02 | Z | 2024-08-15 | 330 | 0 | 80 | F | 0 | 720 |  | AHU-1 OA |  | 48
2024-09-27 | 3131 |  | 81020 | A | DONE | 9 | S-M |  | PECATONICA 6240005 | 1" liner | 2024-10-02 | Z | 2024-08-15 | 220 | 0 | 0 |  | 150 | 260 |  | AHU-1 RA |  | 48
2024-09-27 | 3132 |  | 81021 | A | DONE | 4 | S |  | PECATONICA 6240005 |  | 2024-10-02 | Z | 2024-08-15 | 60 | 0 | 40 | F | 0 | 120 |  | AHU-2 OA |  | 48
2024-09-26 | 3143 |  | 81053 | A | DONE | 2 | S |  | PECATONICA 6240005 | 1" liner | 2024-09-30 | Z | 2024-09-20 | 50 | 0 | 0 |  | 30 | 40 |  | Mezz tie ins |  | 10
2024-09-25 | 2500 |  | 81804 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2024-09-30 | Z | 2024-09-23 | 80 | 0 | 0 |  | 0 | 100 |  | BCU-C |  | 7
2024-09-25 | 2383 |  | 81851 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-26 | Z | 2024-09-24 | 50 | 0 | 0 |  | 0 | 60 |  | Misc |  | 2
2024-09-25 | 2384 |  | 81805 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-09-26 | Z | 2024-09-24 | 30 | 0 | 0 |  | 0 | 40 |  | Misc |  | 2
2024-09-27 | 3807 |  | 81803 | A | DONE | 4 | S-M |  | PROMEGA RDC 6210033 |  | 2024-10-02 | Z | 2024-09-19 | 90 | 0 | 0 |  | 0 | 120 |  | EA |  | 13
2024-09-27 | 3809 |  | 81802 | A | DONE | 6 | S-M |  | PROMEGA RDC 6210033 | bird s. | 2024-10-02 | Z | 2024-09-19 | 110 | 0 | 30 | F | 0 | 160 |  | SA |  | 13
2024-09-26 | 285 | sp | 83201 | A | DONE | 4 | S-M |  | RING & DIN 2240061 |  | 2024-10-02 | Z | 2024-09-25 | 20 | 70 | 0 |  | 0 | 80 |  | 6" Spiral |  | 7
2024-09-25 | 4280 |  | 79928 - 79931 | A | DONE | 8 | S |  | ST.BERNARD 2230056 |  | 2024-09-30 | Z | 2024-09-16 | 190 | 0 | 0 |  | 0 | 180 |  | Misc |  | 14
2024-09-26 | 4281 |  | 79932 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-10-02 | Z | 2024-09-18 | 30 | 0 | 0 |  | 0 | 30 |  | Kitchen RA |  | 14
2024-09-27 | 4282 |  | 80037 - 80038 | A | DONE | 14 | S-M |  | ST.BERNARD 2230056 |  | 2024-10-02 | Z | 2024-09-18 | 120 | 0 | 230 | F | 0 | 370 |  | 1st floor RA / Kitchen |  | 14
2024-09-23 | 4284 |  | 79933 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-09-25 | Z | 2024-09-19 | 20 | 0 | 0 |  | 0 | 20 |  | Outs |  | 6
2024-09-25 | 4285 |  | 79934 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-10-02 | Z | 2024-09-24 | 30 | 0 | 0 |  | 0 | 60 |  | FCU backing |  | 8
2024-09-27 | 3642 |  | 83001 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-03 | Z | 2024-09-24 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeves |  | 9
2024-09-26 | 284 | w | 81054 | A | DONE | 2 | S |  | UPLAND HILLS 2240008 |  | 2024-10-03 | Z | 2024-09-24 | 20 | 0 | 0 |  | 0 | 20 |  | Welded drain pan |  | 9
2024-09-25 | 4559 | w | 70591 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2024-09-26 | Z | 2024-09-25 | 20 | 0 | 0 |  | 0 | 40 |  | Sleeves |  | 1
2024-09-26 | 3861 |  | 67927 - 67929 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-09-30 | Z | 2024-09-16 | 60 | 0 | 0 |  | 0 | 100 |  | AHU4 SA / 5 RA |  | 14
2024-09-26 | 3862 |  | 67930 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-30 | Z | 2024-09-16 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-4-2-4 |  | 14
2024-09-26 | 3863 |  | 67931 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-09-30 | Z | 2024-09-16 | 40 | 0 | 0 |  | 30 | 40 |  | SAT-4-2-6 |  | 14
2024-09-26 | 3864 |  | 67932 - 67933 | A | DONE | 6 | S-M |  | UWL-GRAFF 6230017 |  | 2024-09-30 | Z | 2024-09-16 | 60 | 0 | 70 | F | 0 | 150 |  | 1st AHU4 SA / 5 RA |  | 14
2024-09-26 | 3865 |  | 67934 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-09-30 | Z | 2024-09-17 | 20 | 0 | 0 |  | 0 | 30 |  | AHU-5 RA 1st |  | 13
2024-09-26 | 3866 |  | 67935 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | 1" liner | 2024-09-30 | Z | 2024-09-17 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-4-2-5 |  | 13
2024-09-23 | 597 | sp | L1Z2-DC-1 | A | DONE | 7 | S-M | BI/neal | UWRF 6230010 | angle rings | 2024-09-17 | Z | 2024-08-28 | 170 | 0 | 0 |  | 0 | 410 |  |  |  | 20
2024-09-23 | 651 |  | 66883 | A | DONE | 3 | S-M |  | UWRF 6230010 |  | 2024-09-24 | Z | 2024-09-10 | 60 | 0 | 0 |  | 0 | 170 |  | Mech room |  | 14
2024-09-23 | 652 |  | 66949 | A | DONE | 2 | S | neal | UWRF 6230010 |  | 2024-09-24 | Z | 2024-09-11 | 20 | 0 | 0 |  | 0 | 20 |  | L1Z1 SAT1-1-2 |  | 13
2024-09-23 | 654 |  | 66950 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-09-30 | Z | 2024-09-17 | 20 | 0 | 0 |  | 0 | 20 |  | L1Z1-A-SAT-1-1-1 |  | 13
2024-09-27 | 655 |  | 70451 | A | DONE | 3 | S | pcd | UWRF 6230010 |  | 2024-10-01 | Z | 2024-09-19 | 30 | 0 | 60 | F | 0 | 110 |  | L1Z2-FEV-3-1-7 |  | 12
2024-09-26 | 656 |  | 70401 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-10-01 | Z | 2024-09-19 | 40 | 0 | 0 |  | 0 | 40 |  | 1st floor |  | 12
2024-09-26 | 528c |  | L4-SAMP-1 | A | DONE | 88 | L |  | UWRF 6230010 |  | 2024-10-01 | Z | 2024-08-02 | 2190 | 0 | 0 |  | 0 | 4800 |  |  |  | 60 | 2024-09-11 |  |  |  | 2024-10-01
2024-09-26 | 528d |  | L4-SAMP-1 | A | DONE | 88 | L |  | UWRF 6230010 |  | 2024-10-01 | Z | 2024-08-02 | 2190 | 0 | 0 |  | 0 | 4800 |  |  |  | 60 | 2024-09-16 |  |  |  | 2024-10-01
2024-09-25 | r3930 | sp | L2Z1-FEV-3-2-2 | A | DONE | 2 | S | ss | UWRF 6230010 |  | 2024-09-30 | Z | 2024-09-16 | 20 | 20 | 0 |  | 0 | 40 |  | remake in SS |  | 14
2024-09-25 | r4817 | bth | L2Z1-FEMP-6 | A | DONE | 2 | S | ss | UWRF 6230010 |  | 2024-09-30 | Z | 2024-09-16 | 20 | 20 | 0 |  | 0 | 40 |  | remake in SS |  | 14
2024-09-26 | 5060 |  | RA-01-01 | A | DONE | 39 | M-L |  | UWSP ALBERTSON 6230016 | VD | 2024-09-30 | Z | 2024-07-31 | 430 | 0 | 530 | F | 0 | 1170 |  |  |  | 61 | 2024-09-24
2024-09-26 | 5061 | bth | RA-01-02 | A | DONE | 10 | S |  | UWSP ALBERTSON 6230016 |  | 2024-09-30 | Z | 2024-07-31 | 110 | 40 | 80 | F | 0 | 270 |  |  |  | 61 | 2024-09-24
2024-09-26 | 5062 |  | RA-01-03 | A | DONE | 13 | S-M |  | UWSP ALBERTSON 6230016 | VD | 2024-09-30 | Z | 2024-07-31 | 150 | 0 | 170 | F | 0 | 400 |  |  |  | 61 | 2024-09-24
2024-09-26 | 5063 |  | RA-01-04 | A | DONE | 14 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-09-30 | Z | 2024-07-31 | 180 | 0 | 160 | F | 0 | 380 |  |  |  | 61 | 2024-09-24
2024-09-26 | 5064 | bth | RA-01-05 | A | DONE | 14 | S-M |  | UWSP ALBERTSON 6230016 | VD | 2024-09-30 | Z | 2024-07-31 | 170 | 20 | 160 | F | 0 | 390 |  |  |  | 61 | 2024-09-24
2024-09-26 | 5065 |  | RA-01-06 | A | DONE | 16 | S-M |  | UWSP ALBERTSON 6230016 | VD | 2024-09-30 | Z | 2024-07-31 | 340 | 0 | 50 | F | 0 | 470 |  |  |  | 61 | 2024-09-24
2024-09-26 | 5066 | bth | RA-01-07 | A | DONE | 13 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-09-30 | Z | 2024-07-31 | 180 | 30 | 100 | F | 0 | 370 |  |  |  | 61 | 2024-09-24
2024-09-23 | 5073 | bth | SA-01-05 | A | DONE | 50 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-09-25 | Z | 2024-07-31 | 820 | 60 | 360 | F | 0 | 1850 |  |  |  | 56 | 2024-09-17 |  |  |  | 2024-09-24
2024-09-23 | 5074 | bth | SA-01-06 | A | DONE | 54 | L |  | UWSP ALBERTSON 6230016 |  | 2024-09-25 | Z | 2024-07-31 | 620 | 50 | 680 | F | 0 | 2280 |  |  |  | 56 | 2024-09-17 |  |  |  | 2024-09-24
2024-09-25 | 2454 |  | 58808 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-10-01 | Z | 2024-09-12 | 50 | 0 | 0 |  | 0 | 70 |  | Straps |  | 19
2024-09-24 | 1537 |  | 10001 | A | DONE | 2 | S | BI | UW-VET MED 6210014 |  | 2024-09-26 | Z | 2024-09-19 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 7
2024-09-26 | 860 |  | 67891 - 67892 | A | DONE | 11 | S-M |  | WINDSOR 6240012 |  | 2024-09-30 | Z | 2024-09-06 | 100 | 0 | 160 | F | 0 | 240 |  | FCU's |  | 24 | 2024-09-24
2024-09-26 | 861 | sp | 67893 - 67895 | A | DONE | 27 | M |  | WINDSOR 6240012 |  | 2024-09-30 | Z | 2024-09-06 | 90 | 580 | 0 |  | 0 | 610 |  | FCU's |  | 24 | 2024-09-24
2024-09-26 | 862 | sp | 67896 - 67897 | A | DONE | 11 | S-M |  | WINDSOR 6240012 |  | 2024-09-30 | Z | 2024-09-06 | 50 | 210 | 0 |  | 0 | 240 |  | FCU's |  | 24 | 2024-09-24
2024-09-23 | 863 |  | 67899 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2024-09-24 | Z | 2024-09-19 | 50 | 0 | 0 |  | 0 | 50 |  | DOAS 2 outs |  | 5
2024-09-26 | 1895 | w | 80869 | A | DONE | 2 | S |  | WSCC 6240006 | 2" FB | 2024-10-07 | Z | 2024-09-25 | 30 | 0 | 0 |  | 0 | 70 |  | Sleeves |  | 12
[6 empty] | 1829 | [13 empty] | 70110 |  |  |  | 3110 | 4.436%
WEEK OF 9/30/2024
2024-10-01 | 2242 |  | 80077 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 | paint | 2024-10-07 | Z | 2024-07-25 | 50 | 0 | 150 | F | 20 | 180 |  | DOAS-2 / OA-2 |  | 74 |  |  |  |  | 2024-10-09
2024-10-01 | 3656 |  | 80098 , 80104 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-07 | Z | 2024-07-30 | 50 | 0 | 320 | F | 0 | 380 |  | EF-3,4 , EA-3 |  | 69 |  |  |  |  | 2024-10-09
2024-10-03 | 3691 |  | Stairwell A-EA 4 | A | DONE | 19 | M |  | 121 E. WILSON 6230024 |  | 2024-10-11 | Z | 2024-08-07 | 60 | 0 | 410 | F | 0 | 660 |  |  |  | 65 |  |  |  |  | 2024-10-15
2024-10-01 | 3901 |  | 96554.4 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-10-07 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 56 |  |  |  |  | 2024-10-09
2024-10-02 | 3908 |  | 80145 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. West EA | Design Air | 60 |  |  |  |  | 2024-10-15
2024-10-01 | 3903a |  | 80139 | A | DONE | n/a | M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-07 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 300 | 5th Fl. West unit plenums | Design Air | 56 |  |  |  |  | 2024-10-09
2024-10-01 | 3904a |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-07 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 90 | 5th Fl. West unit Taps | Design Air | 56 |  |  |  |  | 2024-10-09
2024-10-01 | 3905a |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-07 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 250 | 5th Fl. West unit sliders | Design Air | 56 |  |  |  |  | 2024-10-09
2024-10-01 | 3906a |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-07 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 | 160 | 5th Fl. West Corr. HP's | Design Air | 56 |  |  |  |  | 2024-10-09
2024-10-02 | 3909a |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 5th Fl. East unit plenums | Design Air | 60 |  |  |  |  | 2024-10-15
2024-10-02 | 3910a |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 5th Fl. East Taps | Design Air | 60 |  |  |  |  | 2024-10-15
2024-10-02 | 3911a |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 5th Fl. East sliders | Design Air | 60 |  |  |  |  | 2024-10-15
2024-10-01 | 3915b | sp | 81902 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-07 | Z | 2024-08-12 | 20 | 90 | 0 |  | 0 | 20 |  | 6th Fl. OA | Design Air | 56 |  |  |  |  | 2024-10-09
2024-10-01 | 3916b |  | 81903 - 81904 | A | DONE | 30 | M |  | 121 E. WILSON 6230024 |  | 2024-10-07 | Z | 2024-08-12 | 0 | 0 | 730 | F | 0 | 770 |  | 6th Fl. East EA | Design Air | 56 |  |  |  |  | 2024-10-09
2024-10-01 | 761 | bth | 67226 | A | DONE | 6 | S-M |  | BMH AHU-9 6240001 |  | 2024-10-10 | Z | 2024-09-27 | 40 | 40 | 70 | F | 0 | 160 |  | Misc |  | 13
2024-10-02 | 762 |  | 67227 - 67229 | A | DONE | 12 | S-M |  | BMH AHU-9 6240001 |  | 2024-10-10 | Z | 2024-09-27 | 160 | 0 | 120 | F | 0 | 320 |  | Misc |  | 13
2024-10-03 | 764 |  | 80221 | A | DONE | 3 | S-M |  | BMH AHU-9 6240001 |  | 2024-10-10 | Z | 2024-09-27 | 30 | 0 | 30 | F | 0 | 60 |  | Storage space |  | 13
2024-10-03 | 1457 |  | 61372 | A | DONE | 13 | S-M |  | CDIS 6220028 |  | 2024-10-11 | Z | 2024-09-23 | 60 | 0 | 250 | F | 0 | 570 |  | NC Riser |  | 18
2024-09-30 | 1460 |  | 69686 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-01 | Z | 2024-09-27 | 20 | 0 | 0 |  | 0 | 20 |  | 6th Floor stairs |  | 4
2024-10-01 | 1462 |  | 61320 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-03 | Z | 2024-09-30 | 20 | 0 | 0 |  | 0 | 20 |  | 2nd floor Rm. 2570D , 2582 |  | 3
2024-10-01 | 1463 |  | 69688 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-02 | Z | 2024-10-01 | 20 | 0 | 0 |  | 0 | 30 |  | 7th floor spool |  | 1
2024-10-01 | 1464 |  | 61373 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-04 | Z | 2024-10-01 | 20 | 0 | 0 |  | 0 | 20 |  | Chase |  | 3
2024-10-04 | 1467 |  | 69831 | A | DONE | 7 | M | ss | CDIS 6220028 |  | 2024-10-10 | Z | 2024-10-02 | 180 | 0 | 0 |  | 0 | 450 |  | STACK FLASHING |  | 8
2024-10-01 | 4380 | bth | EA (-6wg )-PH-03 | A | DONE | 18 | M |  | CDIS 6220028 | s.mates , VD , flex | 2024-10-03 | Z | 2024-09-11 | 140 | 40 | 250 | F | 0 | 740 |  |  |  | 22
2024-09-30 | 4395 |  | 69829 | A | DONE | 3 | S-M |  | CDIS 6220028 | flex | 2024-10-03 | Z | 2024-09-18 | 70 | 0 | 0 |  | 0 | 170 |  | PH-FCU-6 |  | 15
2024-09-30 | 825d |  | NC-SAMP-005 | A | DONE | 17 | M-L |  | CDIS 6220028 | partial | 2024-10-03 | Z | 2024-08-27 | 410 | 0 | 0 |  | 0 | 1640 |  |  |  | 37 |  |  |  |  | 2024-10-08
2024-10-04 | 825e |  | NC-SAMP-005 | A | DONE | 22 | M-L |  | CDIS 6220028 | partial | 2024-10-11 | Z | 2024-08-27 | 550 | 0 | 0 |  | 0 | 1920 |  |  |  | 45 |  |  |  |  | 2024-10-15
2024-09-30 | 826a |  | NC-EAD-001 | A | DONE | 16 | M-L |  | CDIS 6220028 | partial | 2024-10-03 | Z | 2024-08-27 | 400 | 0 | 0 |  | 0 | 1380 |  |  |  | 37 |  |  |  |  | 2024-10-08
2024-10-04 | 826b |  | NC-EAD-001 | A | DONE | 22 | M-L |  | CDIS 6220028 | partial | 2024-10-11 | Z | 2024-08-27 | 550 | 0 | 0 |  | 0 | 1930 |  |  |  | 45 |  |  |  |  | 2024-10-15
2024-10-04 | 826c |  | NC-EAD-001 | A | DONE | 12 | M |  | CDIS 6220028 | partial | 2024-10-22 | Z | 2024-08-27 | 290 | 0 | 0 |  | 0 | 940 |  |  |  | 56
2024-10-01 | r3449 |  | L7-A-EAMP-011 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-03 | Z | 2024-09-30 | 20 | 0 | 0 |  | 0 | 20 |  | Offset heto |  | 3
2024-10-02 | 4431 |  | 69105 | A | DONE | 2 | S | neal | EXACT SCIENCES 2240052 |  | 2024-10-03 | Z | 2024-10-02 | 20 | 0 | 0 |  | 0 | 20 |  | Tray |  | 1
2024-09-30 | 4418 |  | 79075 - 79076 | A | DONE | 5 | S-M |  | EXACT TL-5 6240014 |  | 2024-10-02 | Z | 2024-09-27 | 100 | 20 | 0 |  | 0 | 140 |  | EAT 2901 |  | 5
2024-10-01 | 4419 | bth | 79078 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-10-02 | Z | 2024-09-30 | 20 | 20 | 0 |  | 0 | 50 |  | 2801 EAT |  | 2
2024-10-01 | 4420 |  | 79077 | A | DONE | 3 | S-M |  | EXACT TL-5 6240014 |  | 2024-10-02 | Z | 2024-09-30 | 50 | 20 | 0 |  | 0 | 70 |  | SA |  | 2
2024-10-03 | 4421 | bth | L2-SAMP-Z6-01 | A | DONE | 8 | S |  | EXACT TL-5 6240014 |  | 2024-10-09 | Z | 2024-10-01 | 130 | 60 | 0 |  | 0 | 230 |  |  |  | 8
2024-10-03 | 4422 | bth | L2_EAMP_Z6_01 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-10-09 | Z | 2024-10-01 | 150 | 20 | 0 |  | 0 | 220 |  |  |  | 8
2024-10-02 | 4423 | sp | L2_Z6_EAT-2701.1 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-01 | 20 | 100 | 0 |  | 0 | 130 |  |  |  | 15
2024-09-30 | 1923 |  | 82410 | A | DONE | 2 | S |  | JPC OFFICE 6240002 | paint | 2024-10-07 | Z | 2024-09-19 | 40 | 0 | 0 |  | 40 | 60 |  | TA boxes |  | 18
2024-10-01 | 1126 |  | 55333 | A | DONE | 74 | M-L |  | LABCORP 6240016 |  | 2024-10-07 | Z | 2024-09-09 | 340 | 0 | 1490 | F | 0 | 2810 |  | 3rd floor E. EA main |  | 28
2024-09-30 | 1127 | bth | 55334 - 55336 | A | DONE | 20 | S-M |  | LABCORP 6240016 |  | 2024-10-07 | Z | 2024-09-09 | 160 | 330 | 0 |  | 0 | 570 |  | 3rd floor E. EA main / LP |  | 28
2024-10-01 | 1128 | sp | 55337 - 55338 | A | DONE | 14 | S-M |  | LABCORP 6240016 |  | 2024-10-07 | Z | 2024-09-09 | 40 | 300 | 0 |  | 0 | 390 |  | 3rd floor EA LP |  | 28
2024-09-30 | 1130 | sp | 55342 - 55344 | A | DONE | 29 | S-M | ss | LABCORP 6240016 |  | 2024-10-07 | Z | 2024-09-09 | 120 | 590 | 0 |  | 0 | 730 |  | 3rd floor EA LP |  | 28
2024-09-30 | 1131 | sp | 55345 - 55347 | A | DONE | 24 | S-M | ss | LABCORP 6240016 |  | 2024-10-07 | Z | 2024-09-09 | 120 | 460 | 0 |  | 0 | 590 |  | 3rd floor EA LP |  | 28
2024-10-03 | 1132 | sp | 55348 - 55349 | L | DONE | 17 | S-M | ss | LABCORP 6240016 |  | 2024-10-14 | Z | 2024-09-09 | 90 | 330 | 0 |  | 0 | 420 |  | 3rd floor EA LP |  | 35
2024-10-03 | 1134 | bth | 59542 - 59544 | F | DONE | 41 | S-M |  | LABCORP 6240016 |  | 2024-10-14 | Z | 2024-09-09 | 530 | 60 | 430 | F | 0 | 1530 |  | 3rd floor SA main |  | 35
2024-10-03 | 1135 | bth | 59559 | A | DONE | 10 | S-M |  | LABCORP 6240016 |  | 2024-10-14 | Z | 2024-09-09 | 120 | 40 | 70 | F | 0 | 250 |  | 3rd floor EA A |  | 35
2024-10-04 | 2651 |  | 5678a | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2024-10-08 | Z | 2024-10-03 | 30 | 0 | 0 |  | 0 | 50 |  | Added Sleeves |  | 5
2024-10-02 | 3133 | sp | 81022 - 81023 | A | DONE | 20 | M |  | PECATONICA 6240005 | oval , accuflange | 2024-10-08 | Z | 2024-08-16 | 120 | 360 | 0 |  | 0 | 570 |  | AHU-2 SA classrooms |  | 53
2024-10-02 | 3134 | sp | 81024 - 81025 | A | DONE | 10 | S-M |  | PECATONICA 6240005 | accuflange | 2024-10-08 | Z | 2024-08-16 | 50 | 200 | 0 |  | 0 | 270 |  | AHU-2 SA classrooms |  | 53
2024-10-01 | 3144 | sp | 81039 | A | DONE | 2 | S |  | PECATONICA 6240005 | oval , accuflange | 2024-10-07 | Z | 2024-09-30 | 0 | 20 | 0 |  | 0 | 20 |  | AHU-2 SA |  | 7
2024-10-02 | 3145 |  | 81040 | A | DONE | 2 | S |  | PECATONICA 6240005 | paint , 1" liner | 2024-10-07 | Z | 2024-09-30 | 20 | 0 | 0 |  | 20 | 20 |  | RE-1 LPEA |  | 7
2024-10-01 | 3146 | sp | 81041 | A | DONE | 6 | S |  | PECATONICA 6240005 |  | 2024-10-07 | Z | 2024-09-30 | 20 | 120 | 0 |  | 0 | 120 |  | RE-1 LPEA |  | 7
2024-10-02 | 2501 |  | L0-SAMP-04 | A | DONE | 44 | L |  | PROMEGA BTC 6230022 |  | 2024-10-09 | Z | 2024-09-23 | 290 | 0 | 800 | F | 0 | 2370 |  |  |  | 16
2024-10-02 | 2502 | bth | L0-SAMP-06 | A | DONE | 18 | M |  | PROMEGA BTC 6230022 |  | 2024-10-09 | Z | 2024-09-23 | 270 | 80 | 80 | F | 0 | 580 |  |  |  | 16
2024-10-02 | 2503 | bth | L0-SAMP-10 | A | DONE | 14 | S-M |  | PROMEGA BTC 6230022 |  | 2024-10-09 | Z | 2024-09-23 | 190 | 40 | 100 | F | 0 | 370 |  |  |  | 16
2024-10-02 | 2504 |  | L0-SAMP-11 | A | DONE | 10 | S-M |  | PROMEGA BTC 6230022 |  | 2024-10-09 | Z | 2024-09-23 | 170 | 0 | 80 | F | 0 | 400 |  |  |  | 16
2024-09-30 | 3808 | bth | 81801 | A | DONE | 16 | S-M |  | PROMEGA RDC 6210033 |  | 2024-10-02 | Z | 2024-09-19 | 140 | 260 | 0 |  | 0 | 400 |  | CB 50 |  | 13
2024-10-02 | 290 |  | 83202 | A | DONE | 2 | S |  | RING & DIN 2240061 |  | 2024-10-07 | Z | 2024-10-01 | 20 | 0 | 0 |  | 0 | 20 |  | Tap |  | 6
2024-10-01 | 4286 |  | 64048 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-10-07 | Z | 2024-10-01 | 20 | 0 | 0 |  | 0 | 20 |  | F-2 |  | 6
2024-10-01 | 3603 | sp | 82951 | A | DONE | 5 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 20 | 100 | 0 |  | 0 | 100 |  | Extra |  | 16
2024-10-03 | 3604 | bth | L01-B-EAD-001 | A | DONE | 11 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 100 | 120 | 50 | F | 0 | 250 |  |  |  | 16
2024-10-01 | 3605 | sp | L01-B-EAD-002 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 40 | 50 | 0 |  | 0 | 80 |  |  |  | 16
2024-10-03 | 3606 | bth | L01-B-EAD-003 | A | DONE | 7 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 70 | 40 | 50 | F | 0 | 150 |  |  |  | 16
2024-10-01 | 3608 | bth | L01-B-EAD-005 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 16
2024-10-03 | 3630 | bth | L01-B-SAMP-001 | A | DONE | 10 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 110 | 40 | 80 | F | 0 | 310 |  |  |  | 16
2024-10-03 | 3631 | bth | L01-B-SAMP-002 | A | DONE | 8 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 80 | 30 | 80 | F | 0 | 220 |  |  |  | 16
2024-10-03 | 3632 | bth | L01-B-SAMP-003 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 60 | 40 | 0 |  | 0 | 90 |  |  |  | 16
2024-10-03 | 3633 | bth | L01-B-SAMP-004 | A | DONE | 10 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 170 | 50 | 30 | F | 0 | 280 |  |  |  | 16
2024-10-03 | 3634 | bth | L01-B-SAMP-005 | A | DONE | 13 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 110 | 50 | 150 | F | 0 | 390 |  |  |  | 16
2024-10-03 | 3635 | sp | L01-B-SAMP-006 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 16
2024-10-03 | 3636 | bth | L01-B-SAMP-007 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 50 | 40 | 30 | F | 0 | 130 |  |  |  | 16
2024-10-03 | 3637 | sp | L01-B-SAMP-008 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 50 | 0 | 0 |  | 0 | 50 |  |  |  | 16
2024-10-03 | 291 |  | 83159 | A | DONE | 2 | S | pcd | THERMO FISHER 4240042 |  | 2024-10-04 | Z | 2024-10-02 | 20 | 0 | 0 |  | 0 | 20 |  | ST COLLAR |  | 2
2024-10-01 | 287 | bth | 83156 - 83157 | A | DONE | 12 | S-M | pcd | THERMO FISHER 4240042 |  | 2024-10-04 | Z | 2024-09-26 | 100 | 190 | 0 |  | 0 | 340 |  | LAB 4102 |  | 8
2024-10-01 | 288 |  | 83158 | A | DONE | 2 | S | pcd | THERMO FISHER 4240042 |  | 2024-10-04 | Z | 2024-09-30 | 20 | 0 | 0 |  | 0 | 30 |  | Lab 4102 |  | 4
2024-10-03 | 292 |  | 83160 | A | DONE | 8 | S-M | pt ss | TST COATING 4240025 |  | 2024-10-11 | Z | 2024-10-02 | 190 | 0 | 0 |  | 0 | 180 |  | RTU-1-SA |  | 9
2024-10-04 | 293 |  | 83161 | A | DONE | 4 | S-M |  | TST COATING 4240025 |  | 2024-10-11 | Z | 2024-10-02 | 100 | 0 | 0 |  | 0 | 120 |  | RTU-1-RA |  | 9
2024-09-30 | 4560 | w | 72556 | A | DONE | 4 | S |  | UW-LEVY HALL 6230028 |  | 2024-10-09 | Z | 2024-09-26 | 90 | 0 | 0 |  | 0 | 190 |  | Sleeves |  | 13
2024-09-30 | 3867 |  | 67937 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-07 | Z | 2024-09-19 | 20 | 0 | 0 |  | 0 | 20 |  | SA-AHU-4 2nd |  | 18
2024-10-01 | 3868 |  | 67926 | A | DONE | 4 | S |  | UWL-GRAFF 6230017 |  | 2024-10-07 | Z | 2024-09-23 | 100 | 0 | 0 |  | 0 | 170 |  | 1st AHU4 RA |  | 14
2024-10-01 | 3869 |  | 67938 - 67941 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2024-10-07 | Z | 2024-09-23 | 220 | 0 | 30 | F | 0 | 290 |  | Misc |  | 14
2024-10-03 | 3870 |  | 67942 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 |  | 2024-10-07 | Z | 2024-09-23 | 20 | 0 | 50 | F | 0 | 80 |  | 2nd RA |  | 14
2024-10-01 | 3871 |  | 67943 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-14 | Z | 2024-09-25 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-4-2-3 |  | 19
2024-10-01 | 563 |  | L4 MER - EAMP-5 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 230 | 0 | 100 | F | 0 | 450 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 564 |  | L4 MER - EAMP-6 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 130 | 0 | 210 | F | 0 | 510 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 565 |  | L4 MER - EAMP-7 | A | DONE | 12 | S-M |  | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 120 | 0 | 170 | F | 0 | 410 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 566 |  | L4 MER - EAMP-8 | A | DONE | 22 | M |  | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 160 | 0 | 370 | F | 0 | 780 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 567 |  | L4 MER - EAMP-9 | A | DONE | 14 | S-M |  | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 200 | 0 | 130 | F | 0 | 460 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 568 |  | L4 MER - FEMP-7 | A | DONE | 13 | S-M | pcd | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 170 | 0 | 140 | F | 0 | 520 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 569 |  | L4 MER - FEMP-6 | A | DONE | 17 | M | pcd | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 240 | 0 | 180 | F | 0 | 690 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 570 |  | L4 MER - FEMP-5 | A | DONE | 25 | M-L | pcd | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 210 | 0 | 400 | F | 0 | 1070 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 571 |  | L4 MER - FEMP-4 | A | DONE | 20 | M | pcd | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 450 | 0 | 50 | F | 0 | 860 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 572 |  | L4 MER - FEMP-2 | A | DONE | 22 | M-L | pcd | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 340 | 0 | 200 | F | 0 | 1180 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-01 | 573 |  | L4 MER - FEMP-1 | A | DONE | 22 | M | pcd | UWRF 6230010 |  | 2024-10-08 | Z | 2024-08-23 | 240 | 0 | 310 | F | 0 | 840 |  |  |  | 46 |  |  |  |  | 2024-09-23
2024-10-02 | 574 |  | L4 MER - EAMP-2 | A | DONE | 40 | M-L |  | UWRF 6230010 |  | 2024-10-10 | Z | 2024-08-23 | 780 | 0 | 220 | F | 0 | 2180 |  |  |  | 48 |  |  |  |  | 2024-09-25
2024-10-03 | 575 |  | L4 MER - EAMP-1 | A | DONE | 64 | L |  | UWRF 6230010 | CD's | 2024-10-10 | Z | 2024-08-23 | 710 | 0 | 880 | F | 0 | 3440 |  |  |  | 48 |  |  |  |  | 2024-09-25
2024-10-02 | 576 |  | L4 MER - EAMP-4 | A | DONE | 61 | L |  | UWRF 6230010 |  | 2024-10-10 | Z | 2024-08-23 | 1130 | 0 | 380 | F | 0 | 3310 |  |  |  | 48 |  |  |  |  | 2024-09-25
2024-10-02 | 577 |  | L4 MER - EAMP-3 | A | DONE | 54 | L |  | UWRF 6230010 |  | 2024-10-10 | Z | 2024-08-23 | 930 | 0 | 400 | F | 0 | 2920 |  |  |  | 48 |  |  |  |  | 2024-09-25
2024-10-01 | 657 |  | 70452 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-10-08 | Z | 2024-09-24 | 20 | 0 | 0 |  | 0 | 40 |  | L3-SAT-1-3-3 |  | 14
2024-10-01 | 658 |  | 70453 | A | DONE | 2 | S | alum/nl | UWRF 6230010 | VD | 2024-10-08 | Z | 2024-09-26 | 20 | 20 | 0 |  | 0 | 40 |  | L3Z1-B-SAT-1-3-6 |  | 12
2024-10-01 | 659 | bth | 70454 - 70455 | A | DONE | 3 | S-M |  | UWRF 6230010 | 1" liner | 2024-10-08 | Z | 2024-09-26 | 70 | 0 | 0 |  | 50 | 100 |  | Misc |  | 12
2024-10-01 | 660 |  | 70456 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-10-08 | Z | 2024-09-26 | 30 | 0 | 0 |  | 20 | 30 |  | L1Z1-A-SAT-1-1-61 |  | 12
2024-10-02 | 661 |  | 70458 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-10-08 | Z | 2024-10-01 | 20 | 0 | 0 |  | 0 | 20 |  | L1-FEV wall drop |  | 7
2024-10-03 | 662 |  | 70457 | A | DONE | 3 | S |  | UWRF 6230010 | 1" liner | 2024-10-08 | Z | 2024-10-01 | 70 | 0 | 0 |  | 40 | 80 |  | Misc |  | 7
2024-10-03 | 665 |  | 70461 | F | DONE | 2 | S |  | UWRF 6230010 |  | 2024-10-15 | Z | 2024-10-02 | 20 | 0 | 0 |  | 0 | 20 |  | 12" RD VDS |  | 13
2024-09-30 | 1314 |  | 81112 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-10-08 | Z | 2024-09-24 | 20 | 0 | 0 |  | 0 | 20 |  | 1st fl EC |  | 14
2024-09-30 | 1315 | sp | 81113 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-10-08 | Z | 2024-09-24 | 0 | 20 | 0 |  | 0 | 20 |  | SAT-1-1-41 |  | 14
2024-10-01 | 1316 | sp | 81114 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-10-08 | Z | 2024-09-26 | 20 | 20 | 0 |  | 0 | 20 |  | SAT-1-1-47 |  | 12
2024-09-30 | 5069 | bth | SA-01-01 | A | DONE | 39 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-10-04 | Z | 2024-07-31 | 250 | 50 | 660 | F | 0 | 1380 |  |  |  | 65 | 2024-10-01 |  |  |  | 2024-10-08
2024-09-30 | 5070 | bth | SA-01-02 | A | DONE | 24 | M |  | UWSP ALBERTSON 6230016 |  | 2024-10-04 | Z | 2024-07-31 | 330 | 70 | 200 | F | 0 | 780 |  |  |  | 65 | 2024-10-01 |  |  |  | 2024-10-08
2024-09-30 | 5071 | bth | SA-01-03 | A | DONE | 27 | M |  | UWSP ALBERTSON 6230016 |  | 2024-10-04 | Z | 2024-07-31 | 110 | 60 | 500 | F | 0 | 940 |  |  |  | 65 | 2024-10-01 |  |  |  | 2024-10-08
2024-09-30 | 5072 | bth | SA-01-04 | A | DONE | 17 | M |  | UWSP ALBERTSON 6230016 |  | 2024-10-04 | Z | 2024-07-31 | 210 | 30 | 170 | F | 0 | 550 |  |  |  | 65 | 2024-10-01 |  |  |  | 2024-10-08
2024-09-30 | 5089 |  | RA-04-01 | A | DONE | 10 | M |  | UWSP ALBERTSON 6230016 |  | 2024-10-04 | Z | 2024-09-05 | 140 | 0 | 90 | F | 0 | 540 |  |  |  | 29 |  |  |  |  | 2024-10-08
2024-09-30 | 5090 |  | RA-04-05 | A | DONE | 16 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-10-04 | Z | 2024-09-05 | 390 | 0 | 0 |  | 0 | 860 |  |  |  | 29 |  |  |  |  | 2024-10-08
2024-09-30 | 5091 |  | SA-04-01 | A | DONE | 12 | M |  | UWSP ALBERTSON 6230016 |  | 2024-10-04 | Z | 2024-09-05 | 210 | 0 | 90 | F | 0 | 500 |  |  |  | 29 |  |  |  |  | 2024-10-08
2024-09-30 | 5092 |  | SA-04-05 | A | DONE | 14 | M |  | UWSP ALBERTSON 6230016 |  | 2024-10-04 | Z | 2024-09-05 | 210 | 0 | 120 | F | 0 | 750 |  |  |  | 29 |  |  |  |  | 2024-10-08
2024-10-03 | 1539 | sp | 73050 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-10-14 | Z | 2024-09-30 | 40 | 0 | 0 |  | 0 | 40 |  | 10-C |  | 14
2024-10-02 | 1541 |  | 73077 | A | DONE | 3 | S-M |  | UW-VET MED 6210014 | flex | 2024-10-14 | Z | 2024-09-30 | 70 | 0 | 0 |  | 0 | 90 |  | BCU-1 |  | 14
2024-10-02 | 1542 |  | 73078 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-10-14 | Z | 2024-09-30 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 14
2024-10-04 | 289a |  | email | A | DONE | 9 | M |  | WESTPHAL 2420007 |  | 2024-10-11 | Z | 2024-09-30 | 220 | 0 | 0 |  | 0 | 780 |  | Boxes |  | 11
2024-10-02 | 289 |  | email | A | DONE | 9 | M |  | WESTPHAL 2440013 |  | 2024-10-04 | Z | 2024-09-30 | 220 | 0 | 0 |  | 0 | 880 |  | Boxes |  | 4
2024-09-30 | 864 | sp | 67900 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2024-10-07 | Z | 2024-09-24 | 20 | 40 | 0 |  | 0 | 50 |  | FCU-120 A/B |  | 13
2024-09-30 | 865 |  | 82501 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2024-10-07 | Z | 2024-09-26 | 20 | 0 | 0 |  | 0 | 20 |  | FCU-120 DA |  | 11
2024-10-04 | 1854 |  | 80807 | A | DONE | 2 | S-M | neal | WSCC 6240006 | 1" liner | 2024-10-14 | Z | 2024-06-25 | 70 | 0 | 0 |  | 50 | 80 |  | RTU-12 |  | 111 | 2024-10-02
2024-10-02 | 1857 |  | 80812 | A | DONE | 2 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 20 | 0 | 0 |  | 0 | 20 |  | RTU-12 |  | 111 | 2024-10-02
2024-10-04 | 1860 |  | 71537 | A | DONE | 4 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 100 | 0 | 0 |  | 80 | 140 |  | Fan - 09 |  | 111 | 2024-10-02
2024-10-04 | 1863 |  | 80801 | A | DONE | 3 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 30 | 0 | 40 | F | 0 | 80 |  | RTU A Section |  | 111 | 2024-10-02
2024-10-04 | 1865 | sp | 71539 | A | DONE | 10 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 50 | 190 | 0 |  | 0 | 280 |  | RTU - 08 |  | 111 | 2024-10-02
2024-10-04 | 1866 |  | 71540 | A | DONE | 3 | S-M | neal | WSCC 6240006 | 1" liner | 2024-10-14 | Z | 2024-06-25 | 60 | 0 | 0 |  | 30 | 80 |  | RTU - 10 |  | 111 | 2024-10-02
2024-10-04 | 1867 | sp | 71541 | A | DONE | 2 | S-M | neal | WSCC 6240006 | 1" spiral accu | 2024-10-14 | Z | 2024-06-25 | 20 | 30 | 0 |  | 30 | 50 |  | RTU - 10 |  | 111 | 2024-10-02
2024-10-04 | 1868 | sp | 71542 | A | DONE | 8 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 20 | 160 | 0 |  | 0 | 210 |  | RTU - 10 |  | 111 | 2024-10-02
2024-10-04 | 1869 |  | 71543 | A | DONE | 3 | S-M | neal | WSCC 6240006 | 1" liner | 2024-10-14 | Z | 2024-06-25 | 70 | 0 | 0 |  | 70 | 110 |  | RTU - 11 |  | 111 | 2024-10-02
2024-10-04 | 1870 | sp | 71544 | A | DONE | 3 | S-M | neal | WSCC 6240006 | 1" spiral accu | 2024-10-14 | Z | 2024-06-25 | 10 | 50 | 0 |  | 50 | 70 |  | RTU - 11 |  | 111 | 2024-10-02
2024-10-04 | 1872 |  | 71548 | A | DONE | 2 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 20 | 0 | 30 | F | 0 | 50 |  | RTU - 11 |  | 111 | 2024-10-02
2024-10-04 | 1873 |  | 71549 | A | DONE | 3 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 60 | 0 | 0 |  | 0 | 70 |  | Fan - 04 |  | 111 | 2024-10-02
2024-10-04 | 1874 | sp | 71550 , 80802 | A | DONE | 12 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 30 | 260 | 0 |  | 0 | 330 |  | Fan - 04 |  | 111 | 2024-10-02
2024-10-04 | 1897 |  | 80951 | A | DONE | 9 | S-M |  | WSCC 6240006 | flex , 1" liner | 2024-10-14 | Z | 2024-09-25 | 220 | 0 | 0 |  | 200 | 310 |  | RTU-Drops A-Sec |  | 19
[6 empty] | 1478 | [13 empty] | 59520 |  |  |  | 5380 | 9.039%
WEEK OF 10/7/2024
2024-10-08 | 3925 |  | 81913 | A | DONE | 8 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-14 | Z | 2024-10-07 | 190 | 0 | 0 |  | 0 | 220 |  | ANGLES |  | 7
2024-10-11 | 3926 | w | 81914 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-10-14 | Z | 2024-10-10 | 30 | 0 | 0 |  | 0 | 50 |  | Wall sleeves |  | 4
2024-10-10 | 3927 |  | 81915 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-10-23 | Z | 2024-10-10 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 13
2024-10-07 | 3907c |  | 80143 - 80144 | A | DONE | 31 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-11 | Z | 2024-08-12 | 0 | 0 | 770 | F | 0 | 720 |  | 7th Fl. West EA | Design Air | 60 |  |  |  |  | 2024-10-15
2024-10-07 | 3912a |  | 80149 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-10-11 | Z | 2024-08-12 | 0 | 0 | 30 | F | 0 | 30 |  | 5th Fl. East unit SA | Design Air | 60 |  |  |  |  | 2024-10-15
2024-10-07 | 3913a |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 5th Fl. East Corr. HP's | Design Air | 60 |  |  |  |  | 2024-10-15
2024-10-09 | r3685 |  | 80130 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-10-10 | Z | 2024-10-09 | 40 | 0 | 0 |  | 0 | 40 |  | 3rd Fl East Taps |  | 1
2024-10-09 | 763 | sp | 80220 | A | DONE | 8 | S-M |  | BMH AHU-9 6240001 |  | 2024-10-10 | Z | 2024-09-27 | 20 | 170 | 0 |  | 0 | 210 |  | Storage space |  | 13
2024-10-07 | 765 |  | 80226 | A | DONE | 3 | S |  | BMH AHU-9 6240001 |  | 2024-10-10 | Z | 2024-10-03 | 60 | 0 | 0 |  | 0 | 90 |  | VAV-9.9S |  | 7
2024-10-11 | 766 | bth | 80222-25 | A | DONE | 23 | M |  | BMH AHU-9 6240001 |  | 2024-10-17 | Z | 2024-10-03 | 480 | 80 | 0 |  | 0 | 730 |  | Misc |  | 14
2024-10-10 | 767 |  | 80227 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-10-17 | Z | 2024-10-09 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 8
2024-10-08 | 1465 |  | 69692 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-15 | Z | 2024-10-02 | 30 | 0 | 0 |  | 0 | 40 |  | L7-A-RAD-002 |  | 13
2024-10-08 | 1466 |  | 69689-90 | A | DONE | 8 | S-M | neal | CDIS 6220028 | paint | 2024-10-15 | Z | 2024-10-02 | 70 | 0 | 130 | F | 20 | 230 |  | 7TH FL MISC TIE INS |  | 13
2024-10-08 | 1468 |  | 69687,93-95 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-15 | Z | 2024-10-03 | 50 | 0 | 0 |  | 0 | 100 |  | MISC |  | 12
2024-10-11 | 1470 |  | 81601 | A | DONE | 3 | S | neal | CDIS 6220028 |  | 2024-10-22 | Z | 2024-10-04 | 0 | 0 | 70 |  | 0 | 140 |  | 7th Floor |  | 18
2024-10-08 | 1471 |  | 61374 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-15 | Z | 2024-10-04 | 40 | 0 | 0 |  | 0 | 80 |  |  |  | 9
2024-10-10 | 1471 |  | 61374 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-15 | Z | 2024-10-04 | 30 | 0 | 0 |  | 0 | 80 |  | 1st Fl Angles |  | 11
2024-10-09 | 1476 |  | 61375 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-09 | Z | 2024-10-09 | 20 | 0 | 0 |  | 0 | 30 |  | Tap |  | 0
2024-10-09 | 4383 |  | RA (-4wg)-PH-AHU-5 | A | DONE | 49 | M-L |  | CDIS 6220028 | flex | 2024-10-15 | Z | 2024-09-11 | 1040 | 0 | 170 | F | 0 | 2580 |  |  |  | 34
2024-10-09 | 4384 | bth | RA (-4wg)-PH-AHU-6 | A | DONE | 34 | M-L |  | CDIS 6220028 | s.mates , flex | 2024-10-15 | Z | 2024-09-11 | 700 | 140 | 0 |  | 0 | 1900 |  |  |  | 34
2024-10-08 | 4385 |  | SA (4wg)-PH-06 | A | DONE | 5 | S |  | CDIS 6220028 | flex | 2024-10-15 | Z | 2024-09-11 | 120 | 0 | 0 |  | 0 | 250 |  |  |  | 34
2024-10-08 | 4386 |  | SA (4wg)-PH-08 | A | DONE | 36 | M-L |  | CDIS 6220028 | flex | 2024-10-15 | Z | 2024-09-11 | 610 | 0 | 290 | F | 0 | 1840 |  |  |  | 34
2024-10-07 | 4387 |  | SA (4wg)-PH-09 | A | DONE | 11 | M |  | CDIS 6220028 |  | 2024-10-15 | Z | 2024-09-11 | 70 | 0 | 190 | F | 0 | 440 |  |  |  | 34
2024-10-11 | 297 | sp | 79425-27 | A | DONE | 24 | S-M |  | DMB 4240050 |  | 2024-10-15 | Z | 2024-10-08 | 200 | 400 | 0 |  | 0 | 540 |  | VAV'S |  | 7
2024-10-10 | 1284 |  | 70232 | A | DONE | 2 | S |  | EGENESIS 10058316 |  | 2024-10-14 | Z | 2024-10-09 | 20 | 0 | 0 |  | 0 | 50 |  | Covers |  | 5
2024-10-10 | 4434 | bth | 69106-09 | A | DONE | 16 | M |  | EXACT SCIENCES 2240052 |  | 2024-10-14 | Z | 2024-10-04 | 160 | 240 | 0 |  | 0 | 460 |  | MISC-FC |  | 10
2024-10-10 | 4437 |  | 69111 | A | DONE | 2 | S | pt.neal | EXACT SCIENCES 2240052 |  | 2024-10-14 | Z | 2024-10-10 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor |  | 4
2024-10-11 | 4424 | sp | L2_Z6_EAT-2701 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-01 | 20 | 90 | 0 |  | 0 | 140 |  |  |  | 15
2024-10-08 | 4425 | bth | L2_Z6_EAT-2710 | A | DONE | 7 | S |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-01 | 140 | 20 | 0 |  | 0 | 180 |  |  |  | 15
2024-10-08 | 4426 | bth | L2_Z6_SAT-2700D | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-01 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 15
2024-10-08 | 4428 | bth | L2_Z6_SAT-2701 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-01 | 20 | 100 | 0 |  | 0 | 140 |  |  |  | 15
2024-10-08 | 4429 | bth | L2_Z6_SAT-2705 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-01 | 20 | 100 | 0 |  | 0 | 130 |  |  |  | 15
2024-10-07 | 4432 | sp | 79079 | A | DONE | 3 | S |  | EXACT TL-5 6240014 |  | 2024-10-08 | Z | 2024-10-03 | 30 | 40 | 0 |  | 0 | 70 |  | EAT-2810 |  | 5
2024-10-07 | 4433 |  | 79080 | A | DONE | 4 | S |  | EXACT TL-5 6240014 |  | 2024-10-08 | Z | 2024-10-04 | 90 | 0 | 0 |  | 0 | 110 |  | EAT 2810 |  | 4
2024-10-09 | 4435 | sp | 79014 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-10-15 | Z | 2024-10-07 | 20 | 10 | 0 |  | 0 | 30 |  | Outs |  | 8
2024-10-09 | 4436 | sp | 79015 | A | DONE | 6 | S |  | EXACT TL-5 6240014 |  | 2024-10-15 | Z | 2024-10-09 | 20 | 70 | 40 | F | 0 | 130 |  | EAD-2-3-0039 missing |  | 6
2024-10-08 | R4074 |  | L2-SALP-Z2-0029 | A | DONE | 7 | S-M |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-07 | 170 | 0 | 0 |  | 0 | 210 |  | REVISED |  | 9
2024-10-10 | R4075 |  | L2-SALP-Z2-0030 | A | DONE | 19 | S-M |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-07 | 490 | 0 | 0 |  | 0 | 580 |  | REVISED |  | 9
2024-10-11 | R4427 | sp | L2_Z6_SAT-2701.1 | A | DONE | 5 | S |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-01 | 20 | 80 | 0 |  | 0 | 120 |  | REVISED |  | 15
2024-10-11 | R4430 | bth | L2_Z6_SAT-2710 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-01 | 70 | 230 | 0 |  | 0 | 340 |  | REVISED |  | 15
2024-10-09 | 1133 | sp | 59541 , 55350 | A | DONE | 28 | S-M | ss | LABCORP 6240016 |  | 2024-10-14 | Z | 2024-09-09 | 110 | 580 | 0 |  | 0 | 700 |  | 3rd floor EA LP |  | 35
2024-10-09 | 298 |  | 79428 | A | DONE | 2 | S |  | MPI 10058326 |  | 2024-10-10 | Z | 2024-10-08 | 20 | 0 | 0 |  | 0 | 30 |  | Tool Rm Furnace |  | 2
2024-10-07 | 296 |  | 83153 | F | DONE | 2 | S |  | OAKWOOD 10058177 |  | 2024-10-09 | Z | 2024-10-03 | 20 | 0 | 0 |  | 0 | 20 |  | APT-415 |  | 6
2024-10-07 | 3811 |  | 81806 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-10-09 | Z | 2024-10-04 | 20 | 0 | 0 |  | 0 | 20 |  | 6.25"RD |  | 5
2024-10-08 | 2385 |  | 81811 | A | DONE | 2 | S |  | PROMEGA RDC 6210033 |  | 2024-10-08 | Z | 2024-10-08 | 20 | 0 | 0 |  | 0 | 20 |  | MISC |  | 0.5
2024-10-08 | 2386 |  | 81812 | A | DONE | 2 | S |  | PROMEGA RDC 6210033 |  | 2024-10-08 | Z | 2024-10-08 | 30 | 0 | 0 |  | 0 | 40 |  | MISC |  | 0.5
2024-10-08 | 3810 | sp | 81807-09 | A | DONE | 11 | S-M |  | PROMEGA RPP 6240019 |  | 2024-10-08 | Z | 2024-10-04 | 170 | 100 | 0 |  | 0 | 310 |  | MISC |  | 4
2024-10-09 | 3812 | sp | 81814 | A | DONE | 2 | S |  | PROMEGA RPP 6240019 |  | 2024-10-10 | Z | 2024-10-09 | 20 | 30 | 0 |  | 0 | 50 |  | Misc |  | 1
2024-10-10 | 3813 | sp | 81815 | A | DONE | 2 | S |  | PROMEGA RPP 6240019 |  | 2024-10-11 | Z | 2024-10-10 | 20 | 30 | 0 |  | 0 | 40 |  | Misc |  | 1
2024-10-09 | 3607 | sp | L01-B-EAD-004 | A | DONE | 3 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-10-10 | Z | 2024-09-24 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 16
2024-10-09 | 3643 |  | 82952 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-10-02 | 120 | 0 | 0 |  | 0 | 120 |  | S & D |  | 15
2024-10-08 | 294 | sp | 83162-63 | A | DONE | 25 | S-M |  | TST COATING 4240025 |  | 2024-10-11 | Z | 2024-10-02 | 150 | 490 | 0 |  | 0 | 640 |  | RTU-1-SA/RA |  | 9
2024-10-07 | 295 | bth | 83164-65 | A | DONE | 11 | S-M |  | TST COATING 4240025 |  | 2024-10-11 | Z | 2024-10-02 | 80 | 200 | 0 |  | 0 | 330 |  | RTU-2 |  | 9
2024-10-08 | 3872 |  | 67944 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-21 | Z | 2024-10-02 | 40 | 0 | 0 |  | 0 | 70 |  | SAT-4-2-1 |  | 19
2024-10-08 | 3873 |  | 67945 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-21 | Z | 2024-10-02 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-5-1-10 |  | 19
2024-10-09 | 3876 |  | 67948 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-21 | Z | 2024-10-08 | 20 | 0 | 0 |  | 0 | 30 |  | RA 207 |  | 13
2024-10-10 | 547 | bth | L4 MER - RAMP 1 | A | DONE | 60 | L |  | UWRF 6230010 | spiral mate , CD | 2024-10-17 | Z | 2024-08-07 | 1160 | 0 | 320 | F | 0 | 2750 |  |  |  | 71 |  |  |  |  | 2024-10-17
2024-10-09 | 578 |  | L4 MER - EAMP-16 | A | DONE | 56 | L |  | UWRF 6230010 |  | 2024-10-15 | Z | 2024-08-23 | 1400 | 0 | 0 |  | 0 | 3540 |  |  |  | 53 |  |  |  |  | 2024-09-30
2024-10-09 | 579 |  | L4 MER - EAMP-17 | A | DONE | 53 | L |  | UWRF 6230010 |  | 2024-10-15 | Z | 2024-08-23 | 1310 | 0 | 0 |  | 0 | 3790 |  |  |  | 53 |  |  |  |  | 2024-09-30
2024-10-09 | 580 |  | L4 MER - EAMP-18 | A | DONE | 52 | L |  | UWRF 6230010 |  | 2024-10-15 | Z | 2024-08-23 | 1290 | 0 | 0 |  | 0 | 3620 |  |  |  | 53 |  |  |  |  | 2024-09-30
2024-10-08 | 581 |  | L4 MER - EAMP-10 | A | DONE | 22 | M |  | UWRF 6230010 | CD | 2024-10-17 | Z | 2024-08-23 | 350 | 0 | 180 | F | 0 | 870 |  |  |  | 55 |  |  |  |  | 2024-10-17
2024-10-07 | 582 |  | L4 MER - EAMP-11 | A | DONE | 22 | M |  | UWRF 6230010 | CD | 2024-10-17 | Z | 2024-08-23 | 420 | 0 | 130 | F | 0 | 790 |  |  |  | 55 |  |  |  |  | 2024-10-17
2024-10-08 | 583 |  | L4 MER - EAMP-12 | A | DONE | 7 | S-M |  | UWRF 6230010 | CD | 2024-10-17 | Z | 2024-08-23 | 90 | 0 | 70 | F | 0 | 340 |  |  |  | 55 |  |  |  |  | 2024-10-17
2024-10-08 | 584 |  | L4 MER - EAMP-13 | A | DONE | 7 | S-M |  | UWRF 6230010 |  | 2024-10-17 | Z | 2024-08-23 | 160 | 0 | 0 |  | 0 | 430 |  |  |  | 55 |  |  |  |  | 2024-10-17
2024-10-11 | 585 |  | L4 MER - FEMP-3 | A | DONE | 30 | M-L | pcd | UWRF 6230010 |  | 2024-10-17 | Z | 2024-08-23 | 470 | 0 | 260 | F | 0 | 1640 |  |  |  | 55 |  |  |  |  | 2024-10-17
2024-10-11 | 586 |  | L4 MER - FEMP-11 | A | DONE | 27 | M-L | pcd | UWRF 6230010 |  | 2024-10-17 | Z | 2024-08-23 | 250 | 0 | 420 | F | 0 | 1460 |  |  |  | 55 |  |  |  |  | 2024-10-17
2024-10-07 | 663 |  | 70459 | A | DONE | 2 | S |  | UWRF 6230010 | paint , 1" liner | 2024-10-15 | Z | 2024-10-01 | 30 | 0 | 0 |  | 20 | 40 |  | L1Z1-B Rm 111 TA |  | 14
2024-10-09 | 664 |  | 70460 | A | DONE | 2 | S |  | UWRF 6230010 | 1" liner | 2024-10-15 | Z | 2024-10-02 | 20 | 0 | 0 |  | 20 | 20 |  | SAT-1-1-32 |  | 13
2024-10-10 | 5096 |  | RA-04-02 | A | DONE | 68 | L |  | UWSP ALBERTSON 6230016 | VD's | 2024-10-15 | Z | 2024-09-10 | 1390 | 0 | 310 | F | 0 | 2950 |  |  |  | 35
2024-10-10 | 5097 |  | RA-04-03 | A | DONE | 54 | L |  | UWSP ALBERTSON 6230016 |  | 2024-10-15 | Z | 2024-09-10 | 980 | 0 | 360 | F | 0 | 2670 |  |  |  | 35
2024-10-10 | 5098 |  | RA-04-04 | A | DONE | 61 | L |  | UWSP ALBERTSON 6230016 | VD's | 2024-10-15 | Z | 2024-09-10 | 880 | 0 | 640 | F | 0 | 2900 |  |  |  | 35
2024-10-08 | 1538 | sp | 73049 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-10-14 | Z | 2024-09-30 | 20 | 0 | 0 |  | 0 | 20 |  | 10-C |  | 14
2024-10-08 | 1540 |  | 73076 | L | DONE | 10 | S-M |  | UW-VET MED 6210014 |  | 2024-10-14 | Z | 2024-09-30 | 250 | 0 | 0 |  | 0 | 510 |  | CB-1547 |  | 14
2024-10-08 | 1075 | w | 82905 | A | DONE | 3 | S |  | WAUNAKEE MS 6230013 |  | 2024-10-08 | Z | 2024-10-07 | 60 | 0 | 0 |  | 0 | 120 |  | SLEEVES |  | 1
2024-10-11 | 870 | sp | 82451-54 | A | DONE | 12 | S-M |  | WINDSOR 6240012 |  | 2024-10-15 | Z | 2024-10-07 | 70 | 220 | 0 |  | 0 | 260 |  | Misc-FCU |  | 8
2024-10-09 | 871 |  | 82511 | A | DONE | 4 | S |  | WINDSOR 6240012 | 1"liner | 2024-10-23 | Z | 2024-10-07 | 60 | 0 | 0 |  | 40 | 60 |  | Grand Stair Trans |  | 16
2024-10-11 | 1855 | sp | 80808 | A | DONE | 4 | S-M | neal | WSCC 6240006 | 1" spiral accu | 2024-10-14 | Z | 2024-06-25 | 50 | 30 | 0 |  | 30 | 70 |  | RTU-12 |  | 111 | 2024-10-02
2024-10-08 | 1856 | sp | 80809 - 80811 | A | DONE | 16 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 40 | 360 | 0 |  | 0 | 470 |  | RTU-12 |  | 111 | 2024-10-02
2024-10-07 | 1858 |  | 80813 | A | DONE | 4 | S-M | neal | WSCC 6240006 | flex , MOD | 2024-10-14 | Z | 2024-06-25 | 40 | 0 | 60 | F | 0 | 120 |  | Fan - 05 |  | 111 | 2024-10-02
2024-10-09 | 1859 |  | 80814 - 80815 | A | DONE | 16 | S-M | neal | WSCC 6240006 | flex | 2024-10-14 | Z | 2024-06-25 | 210 | 0 | 170 | F | 0 | 540 |  | Fan - 06 |  | 111 | 2024-10-02
2024-10-10 | 1861 | sp | 71538 | A | DONE | 4 | S-M | neal | WSCC 6240006 | 1" spiral accu | 2024-10-14 | Z | 2024-06-25 | 30 | 60 | 0 |  | 60 | 90 |  | Fan - 09 |  | 111 | 2024-10-02
2024-10-09 | 1862 |  | 66095 - 66098 | A | DONE | 22 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 50 | 490 | 0 |  | 0 | 620 |  | Fan - 09 |  | 111 | 2024-10-02
2024-10-11 | 1864 | sp | 66099 - 66100 | A | DONE | 4 | S-M | neal | WSCC 6240006 | 1" sp. accu , 1" liner | 2024-10-14 | Z | 2024-06-25 | 60 | 20 | 0 |  | 60 | 120 |  | RTU - 08 |  | 111 | 2024-10-02
2024-10-09 | 1871 | sp | 71545 - 71547 | A | DONE | 20 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 50 | 450 | 0 |  | 0 | 580 |  | RTU - 11 |  | 111 | 2024-10-02
2024-10-08 | 1875 | sp | 80803 - 80804 | A | DONE | 13 | S-M | neal | WSCC 6240006 |  | 2024-10-14 | Z | 2024-06-25 | 40 | 270 | 0 |  | 0 | 350 |  | RTU- 02 |  | 111 | 2024-10-02
2024-10-09 | 1876 |  | 80805 - 80806 | A | DONE | 8 | S-M | neal | WSCC 6240006 | 1" liner | 2024-10-14 | Z | 2024-06-25 | 70 | 20 | 90 | F | 0 | 200 |  | RTU - 02 , Rm 173 |  | 111 | 2024-10-02
2024-10-09 | 1896 |  | 92424 | A | DONE | 3 | S-M |  | WSCC 6240006 |  | 2024-10-14 | Z | 2024-09-24 | 60 | 0 | 0 |  | 0 | 120 |  | Tear drop hangers |  | 20
[6 empty] | 1136 | [13 empty] | 47700 |  |  |  | 5330 | 11.17%
WEEK OF 10/14/2024
2024-10-15 | 3917 |  | 81905 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-23 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. East EA | Design Air | 72
2024-10-15 | 3903b |  | 80139 | A | DONE | n/a | M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-23 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 6th Fl. West unit plenums | Design Air | 72
2024-10-15 | 3904b |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-23 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 6th Fl. West unit Taps | Design Air | 72
2024-10-15 | 3905b |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-23 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 6th Fl. West unit sliders | Design Air | 72
2024-10-15 | 3906b |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-23 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 6th Fl. West Corr. HP's | Design Air | 72
2024-10-15 | 3914a |  | 81901 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2024-10-23 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 7th Fl. IDF TA |  | 72
2024-10-15 | 3916c |  | 81903 - 81904 | A | DONE | 35 | M |  | 121 E. WILSON 6230024 |  | 2024-10-23 | Z | 2024-08-12 | 860 | 0 | 0 |  | 0 | 810 |  | 7th Fl. East EA |  | 72
2024-10-15 | 1458 |  | EA(-10wg)-PH-07 | A | DONE | 150 | L |  | CDIS 6220028 | 1" DW | 2024-10-17 | Z | 2024-09-23 | 3760 | 0 | 0 |  | 800 | 4040 |  |  |  | 24
2024-10-15 | 1459 |  | SA(10wg)-PH-05 | A | DONE | 159 | L |  | CDIS 6220028 | 1" DW | 2024-10-17 | Z | 2024-09-23 | 3970 | 0 | 0 |  | 870 | 4550 |  |  |  | 24
2024-10-15 | 1469 |  | 69832 | A | DONE | 10 | L |  | CDIS 6220028 |  | 2024-10-17 | Z | 2024-10-03 | 250 | 0 | 0 |  | 0 | 660 |  | EA-PH Tie In |  | 14
2024-10-14 | 1472 |  | 81602 | A | DONE | 3 | S | neal | CDIS 6220028 |  | 2024-10-22 | Z | 2024-10-07 | 80 | 0 | 0 |  | 0 | 130 |  | 7th Floor |  | 15
2024-10-16 | 1478 | w | 95660 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-18 | Z | 2024-10-10 | 20 | 0 | 0 |  | 0 | 60 |  | Pan |  | 8
2024-10-15 | 1479 |  | 61376 | A | DONE | 2 | S | neal | CDIS 6220028 | paint | 2024-10-17 | Z | 2024-10-11 | 20 | 0 | 0 |  | 20 | 20 |  | 4th floor B EA |  | 6
2024-10-15 | 1480 |  | 69691 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-15 | Z | 2024-10-11 | 20 | 0 | 0 |  | 0 | 20 |  | 7th floor RM 7581 |  | 4
2024-10-18 | 1481 |  | 61377 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-29 | Z | 2024-10-11 | 20 | 0 | 0 |  | 0 | 30 |  | Patches |  | 18
2024-10-17 | 1483 |  | 69696 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-21 | Z | 2024-10-16 | 20 | 0 | 0 |  | 20 | 70 |  | F Wall flashing |  | 5
2024-10-17 | 1486 |  | 69697 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-22 | Z | 2024-10-16 | 20 | 0 | 0 |  | 20 | 20 |  | SALP-15 |  | 6
2024-10-18 | 1489 |  | 61382 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-22 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 50 |  | Shaft tap |  | 4
2024-10-16 | 825f |  | NC-SAMP-005 | A | DONE | 9 | M |  | CDIS 6220028 | partial | 2024-10-22 | Z | 2024-08-27 | 220 | 0 | 0 |  | 0 | 750 |  |  |  | 56
2024-10-16 | 802 | w | 70684 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2024-10-21 | Z | 2024-10-03 | 20 | 0 | 0 |  | 0 | 40 |  | Vent Collar |  | 18
2024-10-15 | 4438 |  | 79016 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-11 | 50 | 0 | 0 |  | 0 | 80 |  | Corr. 2800 SA |  | 5
2024-10-18 | 4442 |  | 79017 | A | DONE | n/a | S |  | EXACT TL-5 6240014 |  | 2024-10-23 | Z | 2024-10-18 | 0 | 0 | 0 |  | 0 | 0 |  | Area 6 , Dampers |  | 5
2024-10-14 | R4076 |  | L2-SALP-Z2-0031 | A | DONE | 12 | S-M |  | EXACT TL-5 6240014 |  | 2024-10-16 | Z | 2024-10-07 | 300 | 0 | 0 |  | 0 | 350 |  | REVISED |  | 9
2024-10-15 | 3375 |  | 78640 | A | DONE | 2 | S | neal | JANESVILLE ESSR 6230011 |  | 2024-10-21 | Z | 2024-10-15 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2024-10-17 | 1080 |  | 82411 | A | DONE | 2 | S |  | JPC OFFICE 624002 | paint , 1" liner | 2024-10-21 | Z | 2024-10-16 | 20 | 0 | 0 |  | 20 | 40 |  | RA con. |  | 5
2024-10-15 | 2345 |  | 55121 | A | DONE | 2 | S | neal | KOHL CENTER 6210034 |  | 2024-10-17 | Z | 2024-10-11 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 6
2024-10-17 | 1136 | bth | 59545 - 59547 | A | DONE | 19 | S-M |  | LABCORP 6240016 | bird s. | 2024-10-21 | Z | 2024-09-09 | 140 | 320 | 0 |  | 0 | 410 |  | 3rd floor SA LP |  | 42
2024-10-18 | 1137 | bth | 59548 | A | DONE | 4 | S-M |  | LABCORP 6240016 | coils | 2024-10-21 | Z | 2024-09-09 | 40 | 30 | 30 | F | 0 | 120 |  | 3rd floor SA LP |  | 42
2024-10-18 | 1138 | bth | 59549 - 59550 | A | DONE | 14 | S-M | ss | LABCORP 6240016 | coils | 2024-10-21 | Z | 2024-09-09 | 120 | 230 | 0 |  | 0 | 350 |  | 3rd floor SA LP |  | 42
2024-10-16 | 1139 | bth | 56552 | A | DONE | 3 | S-M |  | LABCORP 6240016 |  | 2024-10-21 | Z | 2024-09-09 | 20 | 50 | 0 |  | 0 | 80 |  | 3rd floor SA LP |  | 42
2024-10-18 | 1140 | bth | 56553 - 56555 | A | DONE | 24 | S-M | ss | LABCORP 6240016 | coils | 2024-10-21 | Z | 2024-09-09 | 230 | 310 | 60 | F | 0 | 610 |  | 3rd floor SA LP |  | 42
2024-10-18 | 1142 | sp | 56560 | A | DONE | 4 | S |  | LABCORP 6240016 |  | 2024-10-28 | Z | 2024-09-11 | 70 | 20 | 0 |  | 0 | 100 |  | 3rd floor SAMP |  | 47
2024-10-18 | 1145 | sp | 56565 | A | DONE | 5 | S |  | LABCORP 6240016 |  | 2024-10-28 | Z | 2024-09-11 | 90 | 20 | 0 |  | 0 | 100 |  | 3rd floor EAMP |  | 47
2024-10-17 | 100 |  | 78749 | A | DONE | 2 | S |  | M.S.D SUNSET RIDGE 4240045 |  | 2024-10-23 | Z | 2024-10-16 | 20 | 0 | 0 |  | 0 | 60 |  |  |  | 7
2024-10-16 | 3135 |  | 81026 - 81030 | A | DONE | 50 | M |  | PECATONICA 6240005 | 2" liner | 2024-10-21 | Z | 2024-08-20 | 360 | 0 | 890 | F | 980 | 1170 |  | V2-7 SA |  | 62 |  |  |  |  | 2024-10-21
2024-10-17 | 3136 | sp | 81031 - 81032 | A | DONE | 10 | S-M |  | PECATONICA 6240005 |  | 2024-10-21 | Z | 2024-08-20 | 40 | 200 | 0 |  | 0 | 210 |  | VAV LPS |  | 62 |  |  |  |  | 2024-10-21
2024-10-15 | 3147 |  | 81055 | A | DONE | 7 | S |  | PECATONICA 6240005 | 1"liner | 2024-10-28 | Z | 2024-10-08 | 170 | 0 | 0 |  | 0 | 200 |  | 110-WEST TRANSFER |  | 20
2024-10-15 | 3148 |  | 81056 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2024-10-21 | Z | 2024-10-11 | 30 | 0 | 0 |  | 0 | 40 |  | AFMS |  | 10
2024-10-15 | 2505 |  | 81852 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-10-16 | Z | 2024-10-11 | 20 | 0 | 0 |  | 0 | 40 |  | BCU Tie-ins |  | 5
2024-10-15 | 2506 | sp | 59812 | A | DONE | 11 | S-M |  | PROMEGA BTC 6230022 |  | 2024-10-16 | Z | 2024-10-11 | 100 | 170 | 0 |  | 0 | 310 |  | VAV change |  | 5
2024-10-15 | 2507 |  | 81854 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-10-16 | Z | 2024-10-12 | 20 | 0 | 0 |  | 0 | 20 |  | Filter section |  | 4
2024-10-15 | 2509 |  | 59815 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-10-16 | Z | 2024-10-14 | 40 | 0 | 0 |  | 0 | 70 |  | Testing |  | 2
2024-10-15 | 2388 | sp | 59813 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 |  | 2024-10-16 | Z | 2024-10-14 | 20 | 20 | 0 |  | 0 | 40 |  | EA |  | 2
2024-10-15 | 2389 | sp | 59814 | A | DONE | 4 | S | pcd | PROMEGA FEYNMAN 6220014 |  | 2024-10-16 | Z | 2024-10-14 | 30 | 70 | 0 |  | 0 | 100 |  | EA |  | 2
2024-10-15 | 2387 | bth | 59811 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-10-16 | Z | 2024-10-12 | 30 | 20 | 0 |  | 0 | 40 |  | Outs |  | 4
2024-10-15 | 4287 |  | 80044 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-10-18 | Z | 2024-10-07 | 40 | 0 | 0 |  | 0 | 40 |  | DINING 105 |  | 11
2024-10-14 | 3614 | bth | L01-B-SALP-001 | A | DONE | 6 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 30 | 120 | 0 |  | 0 | 150 |  |  |  | 23
2024-10-14 | 3615 | sp | L01-B-SALP-002 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 20 | 40 | 0 |  | 0 | 50 |  |  |  | 23
2024-10-14 | 3616 | sp | L01-B-SALP-003 | A | DONE | 12 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 50 | 240 | 0 |  | 0 | 320 |  |  |  | 23
2024-10-14 | 3617 | sp | L01-B-SALP-004 | A | DONE | 7 | S-M | neal | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 40 | 120 | 0 |  | 0 | 190 |  |  |  | 23
2024-10-16 | 3618 | bth | L01-B-SALP-005 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 50 | 40 | 0 |  | 0 | 80 |  |  |  | 23
2024-10-15 | 3619 | sp | L01-B-SALP-006 | A | DONE | 9 | S-M | neal | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 50 | 170 | 0 |  | 0 | 260 |  |  |  | 23
2024-10-15 | 3620 | sp | L01-B-SALP-007 | A | DONE | 15 | S-M | pt.neal | STOUGHTON TRAILER 6240015 | VD | 2024-10-17 | Z | 2024-09-24 | 80 | 290 | 0 |  | 0 | 420 |  |  |  | 23
2024-10-14 | 3621 | sp | L01-B-SALP-008 | A | DONE | 9 | S-M | neal | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 50 | 160 | 0 |  | 0 | 230 |  |  |  | 23
2024-10-15 | 3622 | bth | L01-B-SALP-009 | A | DONE | 12 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 280 | 20 | 0 |  | 0 | 270 |  |  |  | 23
2024-10-16 | 3623 | bth | L01-B-SALP-010 | A | DONE | 10 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 190 | 40 | 0 |  | 0 | 220 |  |  |  | 23
2024-10-16 | 3624 | sp | L01-B-SALP-011 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 30 | 60 | 0 |  | 0 | 80 |  |  |  | 23
2024-10-16 | 3625 | bth | L01-B-SALP-012 | A | DONE | 7 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 70 | 100 | 0 |  | 0 | 150 |  |  |  | 23
2024-10-16 | 3626 | bth | L01-B-SALP-013 | A | DONE | 8 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 80 | 120 | 0 |  | 0 | 220 |  |  |  | 23
2024-10-16 | 3627 | sp | L01-B-SALP-014 | A | DONE | 7 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 30 | 130 | 0 |  | 0 | 180 |  |  |  | 23
2024-10-16 | 3628 | bth | L01-B-SALP-015 | A | DONE | 7 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 100 | 70 | 0 |  | 0 | 170 |  |  |  | 23
2024-10-14 | 3629 | sp | L01-B-SALP-016 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-09-24 | 20 | 50 | 0 |  | 0 | 50 |  |  |  | 23
2024-10-15 | 3644 |  | 83002-04,06 | A | DONE | 25 | M |  | STOUGHTON TRAILER 6240015 | 1"liner | 2024-10-17 | Z | 2024-10-04 | 510 | 0 | 0 |  | 130 | 710 |  | RTU |  | 13
2024-10-15 | 3645 |  | 55122 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-10-17 | Z | 2024-10-14 | 30 | 0 | 0 |  | 0 | 50 |  | Flat stock |  | 3
2024-10-16 | 101 |  | 78750 | A | DONE | 2 | S |  | TST COATINGS 4240025 |  | 2024-10-16 | Z | 2024-10-16 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 0
2024-10-16 | 4561 |  | 2913 | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2024-10-18 | Z | 2024-10-11 | 20 | 0 | 0 |  | 0 | 30 |  | Caps |  | 7
2024-10-18 | 4563 |  | email | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2024-10-18 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 30 |  | Caps |  | 0
2024-10-15 | 3874 |  | 82102-04 | A | DONE | 12 | M |  | UWL-GRAFF 6230017 |  | 2024-10-21 | Z | 2024-10-02 | 300 | 0 | 0 |  | 0 | 350 |  | AHU-4-MISC |  | 19
2024-10-15 | 3875 | bth | 67946-47 | A | DONE | 6 | S |  | UWL-GRAFF 6230017 | 1"liner | 2024-10-21 | Z | 2024-10-04 | 60 | 30 | 0 |  | 50 | 110 |  | Vault TA / AHU-4-SA |  | 17
2024-10-16 | 3877 |  | 67949 - 67950 | A | DONE | 14 | M |  | UWL-GRAFF 6230017 |  | 2024-10-21 | Z | 2024-10-10 | 330 | 0 | 0 |  | 0 | 770 |  | AHU-4 RA |  | 11
2024-10-16 | 3878 |  | 82105 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2024-10-21 | Z | 2024-10-10 | 250 | 0 | 0 |  | 0 | 520 |  | Attic EA |  | 11
2024-10-18 | 3880 |  | 82108 - 82110 | A | DONE | 19 | M |  | UWL-GRAFF 6230017 |  | 2024-10-21 | Z | 2024-10-11 | 480 | 0 | 0 |  | 0 | 1100 |  | Attic duct |  | 10
2024-10-16 | 3881 |  | 82111 | A | DONE | 5 | S-M |  | UWL-GRAFF 6230017 |  | 2024-10-21 | Z | 2024-10-11 | 120 | 0 | 0 |  | 0 | 200 |  | AHU-4 SA |  | 10
2024-10-17 | 529 |  | L4 MER-SAMP 2 | A | DONE | 41 | M-L |  | UWRF 6230010 |  | 2024-10-22 | Z | 2024-08-02 | 780 | 0 | 230 | F | 0 | 2190 |  |  |  | 81 |  |  |  |  | 2024-10-07
2024-10-17 | 530 |  | L4 MER-SAMP 3 | A | DONE | 19 | M-L |  | UWRF 6230010 |  | 2024-10-22 | Z | 2024-08-02 | 220 | 0 | 250 | F | 0 | 1020 |  |  |  | 81 |  |  |  |  | 2024-10-07
2024-10-17 | 549 |  | L4 MER - OAMP 1 | A | DONE | 27 | M-L |  | UWRF 6230010 | CD | 2024-10-22 | Z | 2024-08-07 | 540 | 0 | 130 | F | 0 | 1080 |  |  |  | 76 |  |  |  |  | 2024-10-07
2024-10-17 | 550 |  | L4 MER - OAMP 2 | A | DONE | 16 | M |  | UWRF 6230010 |  | 2024-10-22 | Z | 2024-08-07 | 400 | 0 | 0 |  | 0 | 680 |  |  |  | 76 |  |  |  |  | 2024-10-07
2024-10-18 | 551 |  | L4 MER - OAMP 3 | A | DONE | 26 | M-L |  | UWRF 6230010 |  | 2024-10-22 | Z | 2024-08-07 | 630 | 0 | 0 |  | 0 | 1030 |  |  |  | 76 |  |  |  |  | 2024-10-07
2024-10-17 | 587 |  | L4 MER - FEMP-9 | A | DONE | 24 | M-L | pcd | UWRF 6230010 | CD | 2024-10-22 | Z | 2024-08-23 | 580 | 0 | 0 |  | 0 | 1950 |  |  |  | 60 |  |  |  |  | 2024-10-07
2024-10-17 | r5096 |  | RA-04-02 | A | DONE | 8 | M |  | UWSP ALBERTSON 6230016 |  | 2024-10-18 | Z | 2024-10-15 | 180 | 0 | 0 |  | 0 | 600 |  | Pants |  | 3
2024-10-17 | 1498 | sp | 73039 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-11-04 | Z | 2024-08-28 | 20 | 30 | 0 |  | 0 | 40 |  | CB 1547 |  | 68 | 2024-09-30 | 2024-10-14
2024-10-17 | 1546 | sp | 73086 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-10-24 | Z | 2024-10-16 | 20 | 20 | 0 |  | 0 | 20 |  | 10-C Hood |  | 8
2024-10-18 | 1547 |  | 73087 | A | DONE | 2 | S | neal | UW-VET MED 6210014 |  | 2024-10-21 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 110 |  | Large Animal |  | 3
2024-10-14 | 299 | w | 101124 | A | DONE | 2 | S | ss | WESTFIELD HS 8240022 |  | 2024-10-15 | Z | 2024-10-11 | 20 | 0 | 0 |  | 0 | 20 |  | Floor drain |  | 4
2024-10-15 | 289b |  | email | A | DONE | 9 | M |  | WESTPHAL 2240062 |  | 2024-10-16 | Z | 2024-10-14 | 290 | 0 | 0 |  | 0 | 1060 |  |  |  | 2
2024-10-15 | 289c |  | email | A | DONE | 9 | M |  | WESTPHAL 2240063 |  | 2024-10-16 | Z | 2024-10-14 | 290 | 0 | 0 |  | 0 | 1060 |  |  |  | 2
2024-10-18 | 873 | sp | 82458 | A | DONE | 3 | S |  | WINDSOR 6240012 |  | 2024-10-28 | Z | 2024-10-14 | 0 | 70 | 0 |  | 0 | 60 |  | FCU's |  | 14
2024-10-16 | 1898 |  | 12345 | A | DONE | 6 | S-M | neal | WSCC 6240006 |  | 2024-10-24 | Z | 2024-10-11 | 130 | 0 | 0 |  | 0 | 380 |  | Saddle hangers |  | 13
2024-10-15 | 1900 |  | 71451 | A | DONE | 3 | S | neal | WSCC 6240006 |  | 2024-10-17 | Z | 2024-10-11 | 60 | 0 | 0 |  | 50 | 90 |  | RTU-8 , 9 |  | 6
[6 empty] | 996 | [13 empty] | 34210 |  |  |  | 8280 | 24.2%
WEEK OF 10/21/2024
2024-10-21 | 3902 |  | 96554.5 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-10-23 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 72
2024-10-22 | 3928 |  | 81916 | A | DONE | 12 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-23 | Z | 2024-10-11 | 290 | 0 | 0 |  | 0 | 330 |  | EF-3,4,5,6 |  | 12
2024-10-24 | 3929 |  | 81917 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-28 | Z | 2024-10-14 | 80 | 0 | 0 |  | 0 | 90 |  | EF-2 |  | 14
2024-10-25 | 3907d |  | 80143 - 80144 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. West EA | Design Air | 78 | 2024-11-11
2024-10-25 | 3909b |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 6th Fl. East unit plenums | Design Air | 78
2024-10-25 | 3910b |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 6th Fl. East Taps | Design Air | 78
2024-10-25 | 3911b |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 6th Fl. East sliders | Design Air | 78
2024-10-22 | 3912b |  | 80149 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-10-29 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 6th Fl. East unit SA | Design Air | 78
2024-10-25 | 3913b |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-10-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 6th Fl. East Corr. HP's | Design Air | 78
2024-10-21 | 3915c | sp | 81902 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-23 | Z | 2024-08-12 | 20 | 90 | 0 |  | 0 | 90 |  | 7th Fl. OA |  | 72
2024-10-21 | 768 |  | 80229 | A | DONE | 3 | S |  | BMH AHU-9 6240001 |  | 2024-10-24 | Z | 2024-10-18 | 60 | 0 | 0 |  | 0 | 110 |  | Misc |  | 6
2024-10-24 | 823 |  | NC-SAMP-003 | A | DONE | 29 | L |  | CDIS 6220028 |  | 2024-10-29 | Z | 2024-05-01 | 710 | 0 | 0 |  | 0 | 1140 |  |  |  | 181
2024-10-24 | 824 |  | NC-SAMP-004 | A | DONE | 23 | L |  | CDIS 6220028 |  | 2024-10-29 | Z | 2024-05-01 | 570 | 0 | 0 |  | 0 | 1000 |  |  |  | 181
2024-10-21 | 1461 | w | EA-(-10wg)-PH-SED | A | DONE | 25 | M-L | ss | CDIS 6220028 | flex , s.mates | 2024-10-22 | Z | 2024-09-27 | 620 | 0 | 0 |  | 0 | 2140 |  |  |  | 25
2024-10-22 | 1473 |  | OA(4wg)PH-AHU-7 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-10-24 | Z | 2024-10-09 | 60 | 0 | 0 |  | 0 | 120 |  |  |  | 15
2024-10-22 | 1474 |  | OA(4wg)PH-AHU-8 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-10-24 | Z | 2024-10-09 | 50 | 0 | 0 |  | 0 | 100 |  |  |  | 15
2024-10-24 | 1475 |  | EA(-10wg)PH-08 | A | DONE | 5 | M |  | CDIS 6220028 |  | 2024-10-24 | z | 2024-10-09 | 120 | 0 | 0 |  | 0 | 470 |  | pc's 21 & 22 only |  | 15
2024-10-24 | 1477 |  | 69517 | A | DONE | 14 | L |  | CDIS 6220028 |  | 2024-10-24 | z | 2024-10-09 | 340 | 0 | 0 |  | 0 | 980 |  | EA-TIE INS |  | 15
2024-10-21 | 1482 |  | 61378 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-10-22 | Z | 2024-10-11 | 170 | 0 | 0 |  | 0 | 370 |  | NC |  | 11
2024-10-22 | 1484 | bth | 61321 | A | DONE | 2 | S | pt.neal | CDIS 6220028 |  | 2024-10-29 | Z | 2024-10-16 | 20 | 0 | 0 |  | 0 | 20 |  | 4th Floor |  | 13
2024-10-21 | 1485 |  | 61322 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-29 | Z | 2024-10-16 | 20 | 0 | 0 |  | 0 | 20 |  | 4th Floor B rm4527 |  | 13
2024-10-25 | 1487 |  | 69518 | A | DONE | 2 | S-M |  | CDIS 6220028 | flex | 2024-10-29 | Z | 2024-10-17 | 50 | 0 | 0 |  | 0 | 130 |  | PH-AHU-8 |  | 12
2024-10-21 | 1488 |  | 61323 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-10-29 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor A-Corridor |  | 11
2024-10-21 | 1490 |  | 61383 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-22 | Z | 2024-10-21 | 20 | 0 | 0 |  | 0 | 50 |  | NC tap |  | 1
2024-10-22 | 1493 | sp | 61324 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-10-29 | Z | 2024-10-22 | 0 | 20 | 0 |  | 0 | 20 |  | 4th floor |  | 7
2024-10-22 | 1461a | w | EA-(-10wg)-PH-SED | A | DONE | n/a | M-L | ss | CDIS 6220028 | flex , s.mates | 2024-10-24 | Z | 2024-09-27 | 0 | 0 | 0 |  | 0 | 0 |  |  | Badger | 27
2024-10-24 | 1461b | w | EA-(-10wg)-PH-SED | A | DONE | n/a | M-L | ss | CDIS 6220028 | flex , s.mates | 2024-10-29 | Z | 2024-09-27 | 0 | 0 | 0 |  | 0 | 0 |  |  | Badger | 32
2024-10-21 | 4439 |  | 79105 | A | DONE | 2 | S-M |  | EXACT TL-5 6240014 | flex | 2024-10-23 | Z | 2024-10-18 | 50 | 0 | 0 |  | 0 | 100 |  | BCU-2906 |  | 5
2024-10-22 | 4440 |  | 79106 , 79108 | A | DONE | 5 | S-M |  | EXACT TL-5 6240014 | flex | 2024-10-28 | Z | 2024-10-18 | 120 | 0 | 0 |  | 0 | 180 |  | BCU-2906 SA |  | 10
2024-10-22 | 4441 | bth | 79109 - 79110 | A | DONE | 6 | S-M |  | EXACT TL-5 6240014 |  | 2024-10-28 | Z | 2024-10-18 | 120 | 20 | 0 |  | 0 | 160 |  | FCU SA |  | 10
2024-10-22 | 4443 |  | 79112 | A | DONE | 5 | S-M |  | EXACT TL-5 6240014 |  | 2024-10-23 | Z | 2024-10-21 | 120 | 0 | 0 |  | 0 | 170 |  | SALP |  | 2
2024-10-21 | 735 | bth | 81918 | A | DONE | 2 | S |  | HILLDALE | bird s. , 1" DB | 2024-10-23 | Z | 2024-10-18 | 20 | 0 | 0 |  | 20 | 40 |  | Unit 150 |  | 5
2024-10-24 | 3376 |  | 78641 | A | DONE | 6 | S | alum | JANESVILLE ESSR 6230011 |  | 2024-10-24 | Z | 2024-10-23 | 130 | 0 | 0 |  | 0 | 100 |  | Pool duct |  | 1
2024-10-21 | 1081 |  | 82412 | A | DONE | 2 | S | neal | JPC OFFICE 6240002 |  | 2024-10-22 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 20 |  | Blank off |  | 4
2024-10-21 | 1082 |  | 82413 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-10-22 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 30 |  | Rm 172 |  | 4
2024-10-24 | 1083 |  | 82414 | A | DONE | 2 | S |  | JPC OFFICE 6240002 | paint | 2024-10-25 | Z | 2024-10-22 | 20 | 0 | 0 |  | 20 | 20 |  | TA boxes |  | 3
2024-10-25 | 1084 |  | 82415 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-10-28 | Z | 2024-10-28 | 20 | 0 | 0 |  | 0 | 20 |  | TA |  | 0
2024-10-21 | 1141 | bth | 56556 - 56558 | A | DONE | 33 | S-M | ss | LABCORP 6240016 | coils | 2024-10-21 | Z | 2024-09-09 | 230 | 580 | 0 |  | 0 | 810 |  | 3rd floor SA LP |  | 42
2024-10-22 | 1143 | bth | 56561 | A | DONE | 3 | S |  | LABCORP 6240016 |  | 2024-10-28 | Z | 2024-09-11 | 20 | 40 | 0 |  | 0 | 60 |  | 3rd floor SALP |  | 47
2024-10-24 | 1144 | bth | 56562 - 56563 | A | DONE | 59 | S-M | ss | LABCORP 6240016 | coils | 2024-10-28 | Z | 2024-09-11 | 320 | 1140 | 0 |  | 0 | 1470 |  | 3rd floor SALP |  | 47
2024-10-22 | 1146 | sp | 56566 - 56567 | A | DONE | 10 | S-M |  | LABCORP 6240016 |  | 2024-10-28 | Z | 2024-09-11 | 30 | 220 | 0 |  | 0 | 230 |  | 3rd floor EALP |  | 47
2024-10-24 | 1148 | sp | 56568 - 56569 | A | DONE | 102 | M | ss | LABCORP 6240016 |  | 2024-11-04 | Z | 2024-10-01 | 490 | 2040 | 0 |  | 0 | 2560 |  |  |  | 34
2024-10-24 | 2909 |  | 82552 | A | DONE | 2 | S | ss | LABCORP 6240016 |  | 2024-10-28 | Z | 2024-10-21 | 30 | 20 | 0 |  | 0 | 40 |  | EV-3E24 |  | 7
2024-10-24 | 2910 | w | 81257 - 81258 | A | DONE | 2 | S | BI | LABCORP 6240016 |  | 2024-10-28 | Z | 2024-10-22 | 20 | 0 | 0 |  | 0 | 20 |  | Storm collars |  | 6
2024-10-24 | 2911 |  | 56571 | A | DONE | 4 | S | ss | LABCORP 6240016 |  | 2024-10-28 | Z | 2024-10-23 | 90 | 0 | 0 |  | 0 | 220 |  | 3rd Floor misc |  | 5
2024-10-21 | 2652 |  | 78775 | A | DONE | 2 | S |  | MONROE HS 6240018 |  | 2024-10-24 | Z | 2024-10-18 | 30 | 0 | 0 |  | 0 | 40 |  | Wall sleeves |  | 6
2024-10-22 | 3137 |  | 81033 | A | DONE | 4 | S-M |  | PECATONICA 6240005 | 1" liner | 2024-10-24 | Z | 2024-08-20 | 100 | 0 | 0 |  | 90 | 130 |  | Classroom TA |  | 65
2024-10-22 | 3138 |  | 81034 | A | DONE | 3 | S-M |  | PECATONICA 6240005 |  | 2024-10-24 | Z | 2024-08-20 | 70 | 0 | 0 |  | 0 | 100 |  | Angles |  | 65
2024-10-21 | 3149 | sp | 81057 | A | DONE | 3 | S |  | PECATONICA 6240005 |  | 2024-10-28 | Z | 2024-10-16 | 20 | 50 | 0 |  | 0 | 50 |  | V-7 LPSA |  | 12
2024-10-24 | 3951 |  | 81059 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2024-11-04 | z | 2024-10-22 | 20 | 0 | 0 |  | 0 | 30 |  | AHU-2 SA |  | 13
2024-10-24 | 3952 | sp | 81060 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2024-10-28 | Z | 2024-10-22 | 20 | 20 | 0 |  | 0 | 20 |  | VAV 3 Inlet EA |  | 6
2024-10-25 | 2510 | sp | 59816 | A | DONE | 10 | S-M |  | PROMEGA BTC 6230022 |  | 2024-10-30 | Z | 2024-10-16 | 50 | 200 | 0 |  | 0 | 280 |  | VAV 6-1 |  | 14
2024-10-24 | 2511 | bth | 59817 | A | DONE | 4 | S-M |  | PROMEGA BTC 6230022 |  | 2024-10-30 | z | 2024-10-16 | 40 | 60 | 0 |  | 0 | 120 |  | VAV 6-1 |  | 14
2024-10-24 | 2512 | bth | 59818 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-10-30 | z | 2024-10-22 | 20 | 30 | 0 |  | 0 | 50 |  | VAV 20-OF |  | 8
2024-10-24 | 2390 |  | 56349 | A | DONE | 2 | S |  | PROMEGA FEYNMAN 6220014 | bird s. | 2024-10-30 | z | 2024-10-22 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 8
2024-10-21 | 3814 | bth | 56347 | A | DONE | 7 | S-M |  | PROMEGA RPP 6240019 | bird s. | 2024-10-23 | Z | 2024-10-17 | 70 | 100 | 0 |  | 0 | 200 |  | FCU-3 |  | 6
2024-10-22 | 1400 | bth | 68127 - 68128 | A | DONE | 15 | S-M |  | SPH BIRTH CTR. 6240022 |  | 2024-10-28 | Z | 2024-09-10 | 340 | 30 | 0 |  | 0 | 420 |  | SA mains |  | 48 | 2024-11-11
2024-10-22 | 1401 | sp | 68129 - 68130 | A | DONE | 5 | S-M |  | SPH BIRTH CTR. 6240022 |  | 2024-10-28 | Z | 2024-09-10 | 40 | 70 | 0 |  | 0 | 110 |  | VAV-21 D |  | 48 | 2024-11-11
2024-10-22 | 1402 | sp | 68131 - 68132 | A | DONE | 7 | S-M |  | SPH BIRTH CTR. 6240022 |  | 2024-10-28 | Z | 2024-09-10 | 40 | 120 | 0 |  | 0 | 180 |  | VAV-19 D / 7-201 |  | 48 | 2024-11-11
2024-10-22 | 1403 | sp | 68133 - 68134 | A | DONE | 5 | S-M |  | SPH BIRTH CTR. 6240022 |  | 2024-10-28 | Z | 2024-09-10 | 30 | 90 | 0 |  | 0 | 110 |  | RA VAV 20 D |  | 48 | 2024-11-11
2024-10-22 | 1404 |  | 68135 | A | DONE | 2 | S |  | SPH BIRTH CTR. 6240022 | 1" liner | 2024-10-28 | Z | 2024-09-10 | 40 | 0 | 0 |  | 30 | 50 |  | Existing EF |  | 48 | 2024-11-11
2024-10-22 | 272 | bth | 68124 - 68126 | A | DONE | 9 | S-M |  | SPH ERP 2240001 |  | 2024-10-28 | Z | 2024-09-10 | 100 | 110 | 0 |  | 0 | 210 |  | RA / SA |  | 48 | 2024-11-11
2024-10-24 | 104 | sp | 83169 | A | DONE | 14 | S-M |  | THERMO FISHER 4240032 |  | 2024-11-01 | z | 2024-10-17 | 110 | 220 | 0 |  | 0 | 300 |  | SA-PCC-1 |  | 15
2024-10-21 | 107 |  | 83173 | A | DONE | 2 | S |  | TST COATING 4240053 |  | 2024-10-21 | Z | 2024-10-21 | 20 | 0 | 0 |  | 0 | 30 |  | Condensate pump |  | 0
2024-10-21 | 4562 | w | 72557 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2024-10-28 | Z | 2024-10-15 | 30 | 0 | 0 |  | 0 | 80 |  | Sleeves |  | 13
2024-10-22 | 4564 |  | 102124 | A | DONE | 2 | S | BI | UW-LEVY HALL 6230028 |  | 2024-10-23 | Z | 2024-10-21 | 40 | 0 | 0 |  | 0 | 90 |  | Caps |  | 2
2024-10-24 | 3879 |  | 82106 - 82107 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-28 | Z | 2024-10-11 | 50 | 0 | 0 |  | 0 | 80 |  | SAT-5-1-2 / AHU RA |  | 17
2024-10-24 | 3882 |  | 82112 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 | 1" liner | 2024-10-28 | Z | 2024-10-15 | 60 | 0 | 0 |  | 20 | 80 |  | 1st RA / TA |  | 13
2024-10-22 | 3883 | w | 82152 | A | DONE | 16 | S-M | ss | UWL-GRAFF 6230017 |  | 2024-10-28 | Z | 2024-10-16 | 380 | 0 | 0 |  | 0 | 780 |  | AHU-O.A |  | 12
2024-10-24 | 3884 |  | 82153 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-28 | Z | 2024-10-16 | 50 | 0 | 0 |  | 0 | 120 |  | AHU-4 O.A |  | 12
2024-10-24 | 3885 |  | 82114 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-28 | Z | 2024-10-17 | 20 | 0 | 0 |  | 0 | 20 |  | SAT-4-1/2-5 |  | 11
2024-10-24 | 3886 |  | 82115 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-28 | Z | 2024-10-18 | 30 | 0 | 0 |  | 0 | 40 |  | SAT 4-1-4/2 |  | 10
2024-10-25 | 3888 |  | 82117 - 82119 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-10-28 | Z | 2024-10-23 | 20 | 0 | 0 |  | 0 | 40 |  | 1st , 2nd floor SA |  | 5
2024-10-21 | 552 |  | L4 MER - OAMP 4 | A | DONE | 5 | S-M |  | UWRF 6230010 |  | 2024-10-22 | Z | 2024-08-07 | 120 | 0 | 0 |  | 0 | 340 |  |  |  | 76 |  |  |  |  | 2024-10-07
2024-10-22 | 590 | w | L4 MER - FEMP-12 | deleted |  |  | M-L | ss | UWRF 6230010 | angle rings , CD | 2024-11-12 | Z | 2024-08-23 | [5 empty] | 0 |  |  |  | 81
2024-10-22 | 591 | w | L4 MER - FEMP-13 | deleted |  |  | M-L | ss | UWRF 6230010 | angle rings , CD | 2024-11-12 | Z | 2024-08-23 | [5 empty] | 0 |  |  |  | 81
2024-10-22 | 592 | w | L4 MER - FEMP-14 | deleted |  |  | M-L | ss | UWRF 6230010 | angle rings , CD | 2024-11-12 | Z | 2024-08-23 | [5 empty] | 0 |  |  |  | 81
2024-10-22 | 593 | w | L4 MER - EAMP-14 | deleted |  |  | M | pt. ss | UWRF 6230010 | angle rings , CD | 2024-11-12 | Z | 2024-08-23 | [5 empty] | 0 |  |  |  | 81
2024-10-22 | 594 |  | L4 MER - EAMP-15 | deleted |  |  | M |  | UWRF 6230010 |  | 2024-11-12 | Z | 2024-08-23 | [5 empty] | 0 |  |  |  | 81
2024-10-22 | 667 | sp | 70463 | A | DONE | 3 | S |  | UWRF 6230010 |  | 2024-10-30 | Z | 2024-10-17 | 60 | 0 | 0 |  | 0 | 60 |  | Misc |  | 13
2024-10-21 | 1300 |  | RA-04-07 | A | DONE | 9 | S-M |  | UWSP ALBERTSON 6230016 | VD's - NO TAPS | 2024-10-23 | Z | 2024-09-10 | 220 | 0 | 0 |  | 0 | 310 |  |  |  | 43
2024-10-21 | 1301 | bth | LPSA-01-06 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | 1"liner | 2024-10-23 | Z | 2024-09-10 | 250 | 50 | 0 |  | 70 | 350 |  |  |  | 43
2024-10-24 | 1302 | bth | LPSA-01-08 | A | DONE | 21 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | z | 2024-09-10 | 460 | 50 | 0 |  | 60 | 590 |  |  |  | 49
2024-10-24 | 1303 | bth | LPSA-01-11 | A | DONE | 11 | S |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | z | 2024-09-10 | 160 | 60 | 0 |  | 40 | 260 |  |  |  | 49
2024-10-24 | 1304 | bth | LPSA-01-12 | A | DONE | 10 | S |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | z | 2024-09-10 | 100 | 50 | 80 | F | 20 | 260 |  |  |  | 49
2024-10-24 | 1305 | bth | LPSA-01-13 | A | DONE | 24 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | z | 2024-09-10 | 350 | 120 | 0 |  | 140 | 520 |  |  |  | 49
2024-10-24 | 1306 | bth | LPSA-01-14 | A | DONE | 21 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | z | 2024-09-10 | 420 | 50 | 40 | F | 30 | 600 |  |  |  | 49
2024-10-25 | 1307 | bth | LPSA-01-15 | A | DONE | 14 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | Z | 2024-09-10 | 280 | 30 | 30 | F | 40 | 390 |  |  |  | 49
2024-10-24 | 1308 | bth | LPSA-01-16 | A | DONE | 8 | S |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | z | 2024-09-10 | 150 | 50 | 0 |  | 80 | 220 |  |  |  | 49
2024-10-25 | 1309 | bth | LPSA-01-17 | A | DONE | 10 | S |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | Z | 2024-09-10 | 170 | 40 | 20 | F | 60 | 260 |  |  |  | 49
2024-10-25 | 1310 |  | LPSA-01-20 | A | DONE | 20 | M |  | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2024-10-29 | Z | 2024-09-10 | 260 | 0 | 230 | F | 30 | 580 |  |  |  | 49
2024-10-25 | 1311 | bth | LPSA-01-21 | A | DONE | 23 | M |  | UWSP ALBERTSON 6230016 | VD's , 1" liner | 2024-10-29 | Z | 2024-09-10 | 550 | 20 | 0 |  | 30 | 660 |  |  |  | 49
2024-10-21 | 5099 |  | RA-04-06 | A | DONE | 54 | L |  | UWSP ALBERTSON 6230016 | VD's - NO TAPS | 2024-10-23 | Z | 2024-09-10 | 1340 | 0 | 0 |  | 0 | 4430 |  |  |  | 43
2024-10-24 | 1548 |  | 73088 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-10-31 | z | 2024-10-21 | 20 | 0 | 0 |  | 0 | 30 |  | BSL-3 |  | 10
2024-10-25 | 2000 |  | 73090 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-10-31 | Z | 2024-10-23 | 20 | 0 | 0 |  | 0 | 20 |  | BSL |  | 8
2024-10-22 | 866 |  | 82502-03 | A | DONE | 63 | M |  | WINDSOR 6240012 | 1"liner | 2024-10-23 | Z | 2024-10-04 | 930 | 0 | 0 |  | 650 | 1290 |  | 1ST-FCU-RA |  | 19
2024-10-22 | 867 |  | 82504-06 | A | DONE | 27 | M |  | WINDSOR 6240012 | 1"liner | 2024-10-23 | Z | 2024-10-04 | 400 | 0 | 0 |  | 290 | 540 |  | 1ST-FCU-RA |  | 19
2024-10-22 | 868 |  | 82507-08 | A | DONE | 3 | S |  | WINDSOR 6240012 |  | 2024-10-23 | Z | 2024-10-04 | 70 | 0 | 0 |  | 0 | 70 |  | 1ST-FCU |  | 19
2024-10-22 | 869 |  | 82509-10 | A | DONE | 17 | S-M |  | WINDSOR 6240012 | 1"liner | 2024-10-23 | Z | 2024-10-04 | 260 | 0 | 0 |  | 170 | 250 |  | 1ST FL-TRANS |  | 19
2024-10-24 | 872 |  | 82455 - 82457 | A | DONE | 2 | S-M |  | WINDSOR 6240012 | flex | 2024-10-28 | Z | 2024-10-14 | 50 | 0 | 0 |  | 0 | 50 |  | FCU Dishcharge 1st |  | 14
2024-10-24 | 1899 |  | 13579 | A | DONE | 4 | S-M | neal | WSCC 6240006 |  | 2024-10-31 | z | 2024-10-11 | 80 | 0 | 0 |  | 0 | 210 |  | Saddle hangers |  | 20
2024-10-22 | 1920 |  | 71455 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2024-10-23 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 20 |  | Fan 4 |  | 5
2024-10-24 | 1921 | sp | 71456 | A | DONE | 3 | S |  | WSCC 6240006 |  | 2024-10-25 | Z | 2024-10-22 | 40 | 20 | 0 |  | 0 | 40 |  | RTU-2 |  | 3
[6 empty] | 899 | [13 empty] | 29640 |  |  |  | 4050 | 13.66%
WEEK OF 10/28/2024
2024-10-28 | 2243 |  | 80072 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 | paint | 2024-10-29 | Z | 2024-07-25 | 90 | 0 | 120 | F | 20 | 200 |  | DOAS-1 / OA-3 |  | 96
2024-11-01 | 2244 |  | 80078 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 | paint | 2024-11-04 | Z | 2024-07-25 | 90 | 0 | 120 | F | 20 | 190 |  | DOAS-2 / OA-3 |  | 102
2024-11-01 | 3657 |  | 80085 , 80092 | A | DONE | 16 | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-04 | Z | 2024-07-30 | 40 | 0 | 340 | F | 0 | 400 |  | EF-1,2 , EA-4 |  | 97
2024-11-01 | 3694 |  | Stairwell B-EA 9 | A | DONE | 16 | M |  | 121 E. WILSON 6230024 |  | 2024-11-04 | Z | 2024-08-07 | 400 | 0 | 0 |  | 0 | 640 |  |  |  | 89
2024-10-28 | 3930 |  | 81919 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2024-10-29 | Z | 2024-10-18 | 50 | 0 | 0 |  | 0 | 60 |  | Trash room EA |  | 11
2024-11-01 | 3931 |  | 81920 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-04 | Z | 2024-10-24 | 0 | 220 | 0 |  | 0 | 210 |  | EF-4-Exhaust |  | 11
2024-10-30 | 3903c |  | 80139 | A | DONE | n/a | M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-04 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. West unit plenums | Design Air | 84
2024-10-30 | 3904c |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-04 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. West unit Taps | Design Air | 84
2024-10-30 | 3905c |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-04 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. West unit sliders | Design Air | 84
2024-10-30 | 3906c |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-04 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. West Corr. HP's | Design Air | 84
2024-10-30 | 3914b |  | 81901 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2024-11-04 | Z | 2024-08-12 | 30 | 0 | 0 |  | 20 | 30 |  | 8th Fl. IDF TA |  | 84
2024-10-29 | 3915d | sp | 81902 | A | DONE | 4 | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-04 | Z | 2024-08-12 | 0 | 90 | 0 |  | 0 | 100 |  | 8th Fl. OA | Design Air | 84
2024-11-01 | 3916d |  | 81903 - 81904 | A | DONE | 34 | M |  | 121 E. WILSON 6230024 |  | 2024-11-04 | Z | 2024-08-12 | 20 | 0 | 820 | F | 0 | 820 |  | 8th Fl. East EA | Design Air | 84
2024-11-01 | 115 |  | email | A | DONE | 2 | S | ss | 320 HOLTZMAN 6230005 |  | 2024-11-01 | Z | 2024-11-01 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-10-28 | 769 |  | 80230 | A | DONE | 2 | S |  | BMH AHU-9 6240001 | VD | 2024-10-29 | Z | 2024-10-28 | 20 | 0 | 0 |  | 0 | 20 |  | Temp Relief |  | 1
2024-10-28 | 1494 |  | 81552 | A | DONE | 6 | S-M |  | CDIS 6220028 |  | 2024-10-29 | Z | 2024-10-24 | 150 | 0 | 0 |  | 0 | 480 |  | North Core |  | 5
2024-11-01 | 1497 | bth | 69710 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-11-04 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 30 |  | 1st floor outs |  | 4
2024-10-28 | 108 |  | 83204 | A | DONE | 2 | S |  | DEWITT 2240064 |  | 2024-10-29 | Z | 2024-10-24 | 20 | 0 | 0 |  | 0 | 20 |  | Oval 90* |  | 5
2024-10-31 | 1100 |  | 69114 , 69118 | A | DONE | 19 | M-L |  | EXACT SCIENCES 6240009 | VD , bird s. | 2024-11-04 | Z | 2024-10-28 | 470 | 0 | 0 |  | 0 | 1540 |  | EF 1,2,3 |  | 7
2024-10-30 | 1101 |  | 69117 , 69120 | A | DONE | 3 | S-M |  | EXACT SCIENCES 6240009 |  | 2024-11-04 | Z | 2024-10-28 | 50 | 20 | 0 |  | 0 | 90 |  | VAV 117 , 1st and 2nd Fl. |  | 7
2024-10-30 | 1102 | w | 69123 | A | DONE | 2 | S |  | EXACT SCIENCES 6240009 | 1" DB , flex | 2024-11-04 | Z | 2024-10-28 | 50 | 0 | 0 |  | 20 | 130 |  | EF 1,2,3 |  | 7
2024-10-30 | 4448 | sp | 69115 - 69116 | A | DONE | 3 | S-M |  | EXACT SCIENCES 6240009 |  | 2024-11-01 | Z | 2024-10-28 | 20 | 50 | 0 |  | 0 | 100 |  | 123 A,B |  | 4
2024-10-30 | 4449 |  | 69119 , 69121 | A | DONE | 11 | S-M |  | EXACT SCIENCES 6240009 |  | 2024-11-01 | Z | 2024-10-28 | 60 | 200 | 0 |  | 0 | 320 |  | EAT |  | 4
2024-10-31 | 1103 |  | 79089 - 79092 | A | DONE | 7 | S-M |  | EXACT TL-5 6240014 | flex | 2024-11-01 | Z | 2024-10-28 | 160 | 0 | 0 |  | 0 | 270 |  | BCU's |  | 4
2024-10-29 | 4444 |  | 79083 - 79086 | A | DONE | 8 | S-M |  | EXACT TL-5 6240014 | flex | 2024-10-30 | Z | 2024-10-23 | 180 | 0 | 0 |  | 0 | 280 |  | BCU's |  | 7
2024-10-29 | 4445 |  | 79081 | A | DONE | 2 | S |  | EXACT TL-5 6240014 | flex | 2024-10-30 | Z | 2024-10-23 | 30 | 0 | 0 |  | 0 | 40 |  | BCU's |  | 7
2024-10-31 | 4446 |  | 79087 - 79088 | A | DONE | 4 | S-M |  | EXACT TL-5 6240014 | flex | 2024-11-01 | Z | 2024-10-25 | 100 | 0 | 0 |  | 0 | 240 |  | BCU-2830 |  | 7
2024-10-31 | 4447 |  | 79113 | A | DONE | 2 | S |  | EXACT TL-5 6240014 | flex | 2024-11-01 | Z | 2024-10-25 | 20 | 0 | 0 |  | 0 | 40 |  | SA/RA |  | 7
2024-10-30 | 2915 | sp | 56577 | A | DONE | 6 | S | ss | LABCORP 6240016 |  | 2024-11-04 | Z | 2024-10-30 | 20 | 130 | 0 |  | 0 | 140 |  | 3rd floor |  | 5
2024-10-31 | 111 |  | 83174 | A | DONE | 2 | S |  | LARK 4240052 |  | 2024-11-05 | Z | 2024-10-29 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2024-11-01 | 112 |  | 83175 | A | DONE | 2 | S |  | MPI 10057152 |  | 2024-11-06 | Z | 2024-10-30 | 20 | 0 | 0 |  | 0 | 20 |  | F6 |  | 7
2024-10-31 | 3950 | bth | 81058 | A | DONE | 2 | S |  | PECATONICA 6240005 | oval accu flange | 2024-11-04 | Z | 2024-10-21 | 20 | 20 | 0 |  | 0 | 40 |  | Mezz / Misc |  | 14
2024-10-31 | 3953 |  | 81061 | A | DONE | 4 | S-M |  | PECATONICA 6240005 | 1" liner | 2024-11-04 | Z | 2024-10-25 | 100 | 0 | 0 |  | 90 | 200 |  | TA |  | 10
2024-10-29 | 2508 |  | 81856 | A | DONE | 3 | S |  | PROMEGA BTC 6230022 |  | 2024-10-30 | Z | 2024-10-12 | 60 | 0 | 0 |  | 0 | 80 |  | Warehouse RA out |  | 18
2024-10-28 | 109 |  | 80762 | A | DONE | 2 | S |  | SSM O'KEEFE 6240002 |  | 2024-10-29 | Z | 2024-10-28 | 20 | 0 | 0 |  | 0 | 30 |  | Reducers |  | 1
2024-10-28 | 4288 |  | 64049 | A | DONE | 5 | S |  | ST BERNARDS 6230023 |  | 2024-10-30 | Z | 2024-10-16 | 110 | 0 | 0 |  | 0 | 150 |  | Flashing |  | 14
2024-10-29 | 4289 | sp | 79961 | A | DONE | 2 | S |  | ST.BERNARD 2230056 |  | 2024-10-30 | Z | 2024-10-24 | 0 | 10 | 0 |  | 0 | 20 |  | VH VENT |  | 6
2024-10-30 | 113 |  | 79429 | A | DONE | 2 | S |  | ST.OLAF CHURCH 4240039 | flex | 2024-10-31 | Z | 2024-10-30 | 20 | 0 | 0 |  | 0 | 20 |  | AHU |  | 1
2024-10-29 | 413 |  | 82953 , 82955 | A | DONE | 5 | S-M |  | STOUGHTON TRAILER 6240015 | flex , 1" liner | 2024-10-31 | Z | 2024-10-24 | 120 | 0 | 0 |  | 90 | 340 |  | RTU-2 RA |  | 7
2024-10-29 | 414 |  | 82954 , 82956 | A | DONE | 6 | S-M |  | STOUGHTON TRAILER 6240015 | flex | 2024-10-31 | Z | 2024-10-24 | 150 | 0 | 0 |  | 0 | 290 |  | RTU-2 SA |  | 7
2024-10-29 | 415 |  | 83007 | A | DONE | 2 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-10-24 | 40 | 0 | 0 |  | 30 | 50 |  | Roof |  | 7
2024-10-29 | 416 |  | 83008 | A | DONE | 2 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-10-31 | Z | 2024-10-24 | 20 | 0 | 0 |  | 0 | 40 |  | Roof |  | 7
2024-10-29 | 3609 |  | L01_B_RAD_001 | A | DONE | 12 | M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 290 | 0 | 0 |  | 250 | 510 |  |  |  | 37 | 2024-10-24
2024-10-29 | 3610 |  | L01_B_RAD_002 | A | DONE | 18 | M | pt.neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 440 | 0 | 0 |  | 310 | 620 |  |  |  | 37 | 2024-10-24
2024-10-29 | 3611 |  | L01_B_RAD_003 | A | DONE | 13 | S-M | neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 320 | 0 | 0 |  | 270 | 450 |  |  |  | 37 | 2024-10-24
2024-10-29 | 3612 |  | L01_B_RAD_004 | A | DONE | 7 | S | pt.neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 160 | 0 | 0 |  | 100 | 210 |  |  |  | 37 | 2024-10-24
2024-10-29 | 3613 |  | L01_B_RAD_005 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 50 | 0 | 0 |  | 50 | 80 |  |  |  | 37 | 2024-10-24
2024-10-29 | 3638 |  | L01_B_TAD_001 | A | DONE | 7 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 160 | 0 | 0 |  | 100 | 190 |  |  |  | 37 | 2024-10-24
2024-10-29 | 3639 |  | L01_B_TAD_002 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 80 | 0 | 0 |  | 60 | 100 |  |  |  | 37 | 2024-10-24
2024-10-29 | 3640 |  | L01_B_TAD_003 | A | DONE | 3 | S | pt.neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 60 | 0 | 0 |  | 50 | 100 |  |  |  | 37 | 2024-10-24
2024-10-29 | 3641 |  | L01_B_TAD_004 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-10-31 | Z | 2024-09-24 | 20 | 0 | 0 |  | 20 | 20 |  |  |  | 37 | 2024-10-24
2024-10-30 | 102 |  | 83167 | A | DONE | 2 | S |  | THERMO FISHER 4240032 |  | 2024-11-01 | Z | 2024-10-17 | 50 | 0 | 0 |  | 0 | 80 |  | LAB 4103 |  | 15
2024-10-30 | 103 |  | 83168 | A | DONE | 4 | S-M | ss | THERMO FISHER 4240032 | nipple | 2024-11-01 | Z | 2024-10-17 | 40 | 0 | 50 | F | 0 | 110 |  | EA |  | 15
2024-10-30 | 105 |  | 83170 - 83171 | A | DONE | 18 | S-M |  | THERMO FISHER 4240032 |  | 2024-11-01 | Z | 2024-10-17 | 280 | 0 | 150 | F | 0 | 440 |  | SA-PCC-1 |  | 15
2024-10-31 | 106 | w | 83172 | A | DONE | 2 | S |  | THERMO FISHER 4240032 | 1" DB | 2024-11-01 | Z | 2024-10-17 | 20 | 0 | 0 |  | 20 | 80 |  | Curb |  | 15
2024-10-31 | 4565 |  | 2914 | A | DONE | 2 | S |  | UW-LEVY HALL 6230028 |  | 2024-11-05 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 5
2024-10-31 | 3887 |  | 82116 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | flex | 2024-11-04 | Z | 2024-10-21 | 20 | 0 | 0 |  | 0 | 20 |  | RA flex connection |  | 14
2024-11-01 | 544 |  | L4 MER - FCU 3 SA | A | DONE | 7 | S | neal | UWRF 6230010 | 1" liner | 2024-11-04 | Z | 2024-08-07 | 160 | 0 | 0 |  | 40 | 230 |  |  |  | 89
2024-10-31 | 545 |  | L4 MER - AHU 4 SA | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-11-04 | Z | 2024-08-07 | 50 | 0 | 0 |  | 0 | 150 |  |  |  | 89
2024-10-31 | 546 |  | L4 MER - AHU 3 SA | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-11-04 | Z | 2024-08-07 | 40 | 0 | 0 |  | 0 | 130 |  |  |  | 89
2024-10-31 | 588 |  | L4 MER - FEMP-8 | A | DONE | 8 | M | pcd | UWRF 6230010 | CD | 2024-11-04 | Z | 2024-08-23 | 180 | 0 | 0 |  | 0 | 580 |  |  |  | 73
2024-10-31 | 589 |  | L4 MER - FEMP-10 | A | DONE | 8 | M | pcd | UWRF 6230010 | CD | 2024-11-04 | Z | 2024-08-23 | 180 | 0 | 0 |  | 0 | 540 |  |  |  | 73
2024-10-28 | 666 |  | 70462 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-10-30 | Z | 2024-10-16 | 30 | 0 | 0 |  | 0 | 40 |  | FEV-3-1-9 |  | 14
2024-10-30 | 668 | sp | 70464 | A | DONE | 2 | S | ss | UWRF 6230010 |  | 2024-11-05 | Z | 2024-10-23 | 20 | 20 | 0 |  | 0 | 40 |  | L2Z1 Tie ins |  | 13
2024-11-01 | 669 |  | 70465 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-11-05 | Z | 2024-10-23 | 40 | 0 | 0 |  | 0 | 50 |  | PEV 3-2-3 Wall drop |  | 13
2024-10-31 | 670 | sp | 70466 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-11-05 | Z | 2024-10-23 | 0 | 20 | 0 |  | 0 | 20 |  | SAT-1-3-17 L3Z2-B |  | 13
2024-11-01 | 672 |  | 83501 | A | DONE | 5 | S-M |  | UWRF 6230010 |  | 2024-11-04 | Z | 2024-10-31 | 120 | 0 | 0 |  | 0 | 330 |  | PH Tie ins |  | 4
2024-10-31 | 673 |  | 83502 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-11-04 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 30 |  | PH outs |  | 4
2024-10-31 | 675 |  | 70470 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-11-04 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 20 |  | L2-Soffit Extension |  | 4
2024-10-28 | 1312 | bth | LPSA-01-22 | A | DONE | 59 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | Z | 2024-09-10 | 1410 | 60 | 0 |  | 40 | 1740 |  |  |  | 49
2024-10-28 | 1313 | bth | LPSA-01-23 | A | DONE | 18 | M-L |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-10-29 | Z | 2024-09-10 | 420 | 20 | 0 |  | 30 | 500 |  |  |  | 49
2024-10-29 | 1319 |  | SA-01-VRF-1-1-1 | deleted |  |  | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-05 | Z | 2024-10-09 | [5 empty] | 0 |  |  |  | 27
2024-10-29 | 1320 |  | RA-01-VRF-1-1-1 | deleted |  |  | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-05 | Z | 2024-10-09 | [5 empty] | 0 |  |  |  | 27
2024-11-01 | 2456 | bth | L2_SAMP 1 | A | DONE | 17 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-05 | Z | 2024-10-21 | 170 | 70 | 180 | F | 0 | 490 |  |  |  | 15
2024-10-30 | 2461 | bth | L2_SAMP 6 | A | DONE | 38 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-10-31 | Z | 2024-10-21 | 470 | 20 | 450 | F | 0 | 1790 |  |  |  | 10
2024-10-30 | 2462 |  | L2_SAMP 7 | A | DONE | 47 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-10-31 | Z | 2024-10-21 | 640 | 0 | 440 | F | 0 | 2250 |  |  |  | 10
2024-10-30 | 2463 | bth | L2_SAMP 8 | A | DONE | 31 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-10-31 | Z | 2024-10-21 | 530 | 110 | 120 | F | 0 | 1270 |  |  |  | 10
2024-10-30 | 2464 | bth | L2_SAMP 9 | A | DONE | 17 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-10-31 | Z | 2024-10-21 | 370 | 40 | 0 |  | 0 | 640 |  |  |  | 10
2024-10-30 | 2465 |  | L2_SAMP 10 | A | DONE | 8 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-10-31 | Z | 2024-10-21 | 80 | 0 | 120 | F | 0 | 370 |  |  |  | 10
2024-10-29 | 2468 |  | 70120 | A | DONE | n/a | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-10-31 | Z | 2024-10-23 | 0 | 0 | 0 |  | 0 | 0 |  | Duct Mate frames |  | 8
2024-10-31 | 2469 |  | 70122 - 70123 | A | DONE | 18 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-04 | Z | 2024-10-24 | 440 | 0 | 0 |  | 410 | 670 |  | 2nd floor TA |  | 11
2024-10-31 | 1545 |  | 73085 | A | DONE | 14 | S-M |  | UW-VET MED 6210014 |  | 2024-11-04 | Z | 2024-08-07 | 350 | 0 | 0 |  | 0 | 590 |  | CB 1547 North Hall |  | 89 | 2024-09-30 | 2024-10-14
2024-10-29 | 1549 |  | 73089 | A | DONE | 2 | S |  | UW-VET MED 6210014 | paint | 2024-10-31 | Z | 2024-10-23 | 20 | 0 | 0 |  | 0 | 30 |  | BCU-1 |  | 8
2024-10-31 | 2001 |  | 83901 | A | DONE | 2 | S |  | UW-VET MED 6210014 | 1" liner | 2024-11-04 | Z | 2024-10-30 | 40 | 0 | 0 |  | 40 | 70 |  | Flashing |  | 5
2024-10-31 | 1076 |  | 3000 | A | DONE | 2 | S | BI | WAUNAKEE MS 6230013 |  | 2024-11-05 | Z | 2024-10-30 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 6
2024-10-31 | 1077 |  | 103124 | A | DONE | 2 | S | BI | WAUNAKEE MS 6230013 |  | 2024-10-31 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 0
2024-10-31 | 874 |  | 82512 - 82513 | A | DONE | 9 | S-M |  | WINDSOR 6240012 |  | 2024-11-04 | Z | 2024-10-16 | 130 | 0 | 90 | F | 0 | 220 |  | FCU-223A |  | 19
2024-10-31 | 875 | sp | 82514 | A | DONE | 12 | S-M |  | WINDSOR 6240012 |  | 2024-11-04 | Z | 2024-10-16 | 20 | 270 | 0 |  | 0 | 280 |  | FCU-223A |  | 19
2024-10-31 | 876 |  | 82515 -82517 | A | DONE | 9 | S-M |  | WINDSOR 6240012 |  | 2024-11-04 | Z | 2024-10-16 | 220 | 0 | 0 |  | 0 | 260 |  | FCU-223A |  | 19
2024-10-31 | 877 | sp | 82518 - 82519 | A | DONE | 12 | S-M |  | WINDSOR 6240012 |  | 2024-11-04 | Z | 2024-10-16 | 40 | 240 | 0 |  | 0 | 260 |  | FCU-223B |  | 19
2024-11-01 | 878 |  | 82459 | A | DONE | 9 | S-M |  | WINDSOR 6240012 | VD | 2024-11-04 | Z | 2024-10-21 | 210 | 0 | 0 |  | 0 | 230 |  | DOAS 1 2nd Floor |  | 14
2024-10-30 | 879 | sp | 82460 | A | DONE | 12 | S-M |  | WINDSOR 6240012 |  | 2024-11-04 | Z | 2024-10-21 | 30 | 260 | 0 |  | 0 | 270 |  | DOAS 1 2nd Floor |  | 14
2024-10-31 | 880 |  | 82461 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2024-11-04 | Z | 2024-10-21 | 20 | 0 | 0 |  | 0 | 20 |  | DOAS 1 2nd Floor |  | 14
2024-10-31 | 881 |  | 82462 - 82463 | A | DONE | 19 | M |  | WINDSOR 6240012 |  | 2024-11-04 | Z | 2024-10-21 | 200 | 0 | 270 | F | 0 | 440 |  | FCU-211 A |  | 14
2024-11-01 | 882 |  | 82464 - 82465 | A | DONE | 6 | S-M |  | WINDSOR 6240012 | VD's | 2024-11-04 | Z | 2024-10-21 | 130 | 0 | 0 |  | 0 | 150 |  | FCU-211 AB |  | 14
2024-10-31 | 883 | sp | 82466 - 82467 | A | DONE | 20 | M |  | WINDSOR 6240012 |  | 2024-11-04 | Z | 2024-10-21 | 110 | 380 | 0 |  | 0 | 450 |  | FCU-211 AB |  | 14
2024-11-01 | 889 |  | 72394 - 72395 | A | DONE | 4 | S-M |  | WINDSOR 6240012 | flex , 1" liner | 2024-11-04 | Z | 2024-10-24 | 80 | 0 | 0 |  | 20 | 100 |  | FCU-SA |  | 11
2024-10-31 | 890 | sp | 72396 | A | DONE | 2 | S |  | WINDSOR 6240012 | VD | 2024-11-04 | Z | 2024-10-24 | 20 | 30 | 0 |  | 0 | 50 |  | FCU-SA |  | 11
2024-10-30 | 1878 | sp | 80816 - 80818 | A | DONE | 28 | M | neal | WSCC 6240006 |  | 2024-10-31 | Z | 2024-07-03 | 30 | 660 | 0 |  | 0 | 800 |  | RTU-2 |  | 120 |  |  |  | 2024-10-14 | 2024-11-04
2024-10-29 | 1879 | sp | 80819 - 80821 | A | DONE | 13 | M | neal | WSCC 6240006 |  | 2024-10-31 | Z | 2024-07-03 | 30 | 300 | 0 |  | 0 | 370 |  | RTU-2 |  | 120 |  |  |  | 2024-10-14 | 2024-11-04
2024-10-30 | 1880 |  | 80822 | A | DONE | 4 | S | neal | WSCC 6240006 | 1" liner | 2024-10-31 | Z | 2024-07-03 | 100 | 0 | 0 |  | 90 | 190 |  | TA lobby / link155 |  | 120 |  |  |  | 2024-10-14 | 2024-11-04
2024-10-29 | 1881 | sp | 80827 - 80830 | A | DONE | 89 | L | neal | WSCC 6240006 | spiral mate | 2024-10-31 | Z | 2024-07-22 | 300 | 1920 | 0 |  | 0 | 2610 |  | DHU-02 |  | 101 |  |  |  | 2024-10-14 | 2024-11-04
2024-10-30 | 1882 |  | 80831 | A | DONE | 22 | M | neal | WSCC 6240006 | 1" liner | 2024-10-31 | Z | 2024-07-22 | 540 | 0 | 0 |  | 490 | 1160 |  | RTU-4,6 |  | 101 |  |  |  | 2024-10-14 | 2024-11-04
2024-10-29 | 1883 | sp | 80832 - 80835 , 80839 | A | DONE | 83 | M-L | neal | WSCC 6240006 | spiral mate | 2024-10-31 | Z | 2024-07-22 | 340 | 1730 | 0 |  | 0 | 2910 |  | RTU-4,6 |  | 101 |  |  |  | 2024-10-14 | 2024-11-04
2024-10-30 | 1884 |  | 80838 | A | DONE | 18 | S-M | neal | WSCC 6240006 | 1" liner | 2024-10-31 | Z | 2024-07-22 | 440 | 0 | 0 |  | 390 | 1090 |  | RTU-4,7 |  | 101 |  |  |  | 2024-10-14 | 2024-11-04
2024-10-29 | 1922 |  | 80982 | A | DONE | 2 | S |  | WSCC 6240006 | 1" liner | 2024-10-31 | Z | 2024-10-25 | 30 | 0 | 0 |  | 20 | 40 |  | TA |  | 6
2024-10-29 | 1923 |  | 71457 | A | DONE | 4 | S-M |  | WSCC 6240006 | flex , 1" liner | 2024-10-30 | Z | 2024-10-28 | 80 | 0 | 0 |  | 60 | 170 |  |  |  | 2
[6 empty] | 1017 | [13 empty] | 35440 |  |  |  | 13080 | 36.91%
WEEK OF 11/4/2024
2024-11-07 | 3658 |  | 80099 , 80105 | A | DONE | 15 | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-11 | Z | 2024-07-30 | 40 | 0 | 320 | F | 0 | 380 |  | EF-3,4 , EA-4 |  | 104
2024-11-04 | 3932 | w | 23911 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-11-06 | Z | 2024-11-04 | 20 | 0 | 0 |  | 0 | 40 |  | Wall sleeves |  | 2
2024-11-07 | 3933 |  | 23912 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2024-11-08 | Z | 2024-11-07 | 30 | 0 | 0 |  | 20 | 30 |  | TA |  | 1
2024-11-06 | 3907e |  | 80143 - 80144 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. West EA | Design Air | 91
2024-11-06 | 3909c |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. East unit plenums | Design Air | 91
2024-11-06 | 3910c |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. East Taps | Design Air | 91
2024-11-06 | 3911c |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. East sliders | Design Air | 91
2024-11-06 | 3912c |  | 80149 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-11-11 | Z | 2024-08-12 | 30 | 0 | 0 |  | 0 | 40 |  | 7th Fl. East unit SA | Design Air | 91
2024-11-06 | 3913c |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-11 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 7th Fl. East Corr. HP's | Design Air | 91
2024-11-06 | 770 |  | 80232 - 80233 | A | DONE | 7 | S-M |  | BMH AHU-9 6240001 |  | 2024-11-14 | Z | 2024-10-31 | 90 | 0 | 70 | F | 0 | 180 |  | Haz mat SALP |  | 14
2024-11-06 | 771 | bth | 80234 - 80235 | A | DONE | 12 | S-M |  | BMH AHU-9 6240001 |  | 2024-11-14 | Z | 2024-10-31 | 90 | 170 | 40 | F | 0 | 340 |  | Sterile SALP |  | 14
2024-11-06 | 772 |  | 80236 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-11-14 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 20 |  | 9.4 E |  | 14
2024-11-05 | 773 |  | 80237 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-11-07 | Z | 2024-11-04 | 20 | 0 | 0 |  | 0 | 30 |  | Misc SALP |  | 3
2024-11-09 | 774 |  | 80238 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-11-09 | Z | 2024-11-09 | 20 | 0 | 0 |  | 0 | 20 |  | Soiled SPD SALP |  | 0
2024-11-06 | 1491 |  | 69701 - 69704 | A | DONE | 4 | S-M |  | CDIS 6220028 | paint | 2024-11-11 | Z | 2024-10-22 | 90 | 0 | 0 |  | 80 | 120 |  | Linear grill box |  | 20
2024-11-06 | 1492 |  | 69707 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-11-11 | Z | 2024-10-22 | 70 | 0 | 0 |  | 0 | 220 |  | OA louver EA Rm |  | 20
2024-11-08 | 1495 | sp | 69833 | A | DONE | 2 | S |  | CDIS 6220028 | flex | 2024-11-13 | Z | 2024-10-24 | 20 | 30 | 0 |  | 0 | 40 |  | PH-GET-1-8-2 |  | 20
2024-11-06 | 1496 |  | 69520 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-11-11 | Z | 2024-10-28 | 80 | 0 | 0 |  | 0 | 220 |  | EA(-10wg)PH-07 tie in |  | 14
2024-11-06 | 1498 |  | 69698 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-11-11 | Z | 2024-11-01 | 20 | 0 | 0 |  | 0 | 60 |  | 1st floor core SA |  | 10
2024-11-04 | 1499 |  | 81553 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-11-05 | Z | 2024-11-01 | 50 | 0 | 0 |  | 40 | 60 |  | Riser taps |  | 4
2024-11-06 | 2050 |  | 69711 | A | DONE | 6 | S |  | CDIS 6220028 |  | 2024-11-11 | Z | 2024-11-01 | 150 | 0 | 0 |  | 0 | 320 |  | Loading dock louver |  | 10
2024-11-06 | 2051 |  | 69712 | A | DONE | 2 | S |  | CDIS 6220028 | 1" liner | 2024-11-11 | Z | 2024-11-01 | 20 | 0 | 0 |  | 20 | 40 |  | Loading dock TA |  | 10
2024-11-06 | 2053 |  | 69713 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-11-11 | Z | 2024-11-05 | 20 | 0 | 0 |  | 0 | 40 |  | 1A-SAMP-35 |  | 6
2024-11-07 | 2054 |  | 69522 | A | DONE | 4 | S |  | CDIS 6220028 |  | 2024-11-15 | Z | 2024-11-06 | 100 | 0 | 0 |  | 0 | 220 |  | Flashing |  | 9
2024-11-07 | 2055 |  | 61461 , 85994 | A | DONE | 2 | S | alum | CDIS 6220028 |  | 2024-11-07 | Z | 2024-11-07 | 20 | 0 | 0 |  | 0 | 20 |  | Pit 164-10 |  | 0
2024-11-04 | 1108 |  | 79118 | A | DONE | 2 | S | wt.alum | EXACT 2230044 |  | 2024-11-06 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 20 |  | Humidifier |  | 6
2024-11-06 | 1107 | bth | 69124 | A | DONE | 4 | S-M |  | EXACT SCIENCES 2240066 | 1" liner | 2024-11-12 | Z | 2024-10-31 | 40 | 20 | 30 | F | 50 | 90 |  | VAV-103 |  | 12
2024-11-06 | 1100r |  | 69118 | A | DONE | 4 | S |  | EXACT SCIENCES 2240066 |  | 2024-11-06 | Z | 2024-11-06 | 100 | 0 | 0 |  | 0 | 240 |  | Change in size |  | 0
2024-11-04 | 1110 |  | 70592 | A | DONE | 2 | S |  | EXACT SCIENCES 6240009 |  | 2024-11-04 | Z | 2024-11-04 | 20 | 0 | 0 |  | 0 | 20 |  | Reducers |  | 0
2024-11-07 | 1113 |  | 72399 | A | DONE | 2 | S-M |  | EXACT SCIENCES 6240009 |  | 2024-11-08 | Z | 2024-11-07 | 50 | 0 | 0 |  | 0 | 90 |  | Roof fan tie ins |  | 1
2024-11-07 | 1114 | sp | 69125 | A | DONE | 2 | S |  | EXACT SCIENCES 6240009 |  | 2024-11-12 | Z | 2024-11-07 | 20 | 30 | 0 |  | 0 | 40 |  | VAV-103 |  | 5
2024-11-05 | 1104 |  | 79093 - 79094 | A | DONE | 3 | S-M |  | EXACT TL-5 6240014 | paint | 2024-11-06 | Z | 2024-10-30 | 70 | 0 | 0 |  | 50 | 100 |  | Misc |  | 7
2024-11-05 | 1105 |  | 79095 - 79096 | A | DONE | 2 | S-M |  | EXACT TL-5 6240014 | paint | 2024-11-06 | Z | 2024-10-30 | 60 | 0 | 0 |  | 20 | 100 |  | Misc |  | 7
2024-11-05 | 1106 |  | 79097 - 79099 | A | DONE | 4 | S-M |  | EXACT TL-5 6240014 | paint | 2024-11-06 | Z | 2024-10-30 | 80 | 0 | 0 |  | 20 | 110 |  | Misc |  | 7
2024-11-05 | 1109 |  | 79100 | A | DONE | 2 | S-M |  | EXACT TL-5 6240014 |  | 2024-11-06 | Z | 2024-11-01 | 40 | 0 | 0 |  | 0 | 60 |  | Ceiling tie in RA |  | 5
2024-11-08 | 1111 |  | 79119 | A | DONE | 2 | S |  | EXACT TL-5 6240014 | paint | 2024-11-13 | Z | 2024-11-06 | 20 | 0 | 0 |  | 20 | 20 |  | GRD finish |  | 7
2024-11-05 | 1149 |  | 56570 | A | DONE | 65 | M | ss | LABCORP 6240016 |  | 2024-11-06 | Z | 2024-10-01 | 690 | 0 | 930 | F | 0 | 1680 |  | Misc |  | 36
2024-11-06 | 2912 | bth | 56572 - 56574 | A | DONE | 14 | S-M |  | LABCORP 6240016 | VD , paint | 2024-11-11 | Z | 2024-10-28 | 180 | 160 | 0 |  | 20 | 350 |  | Misc |  | 14
2024-11-06 | 2913 | w | 56575 | A | DONE | 2 | S | ss | LABCORP 6240016 | coil | 2024-11-11 | Z | 2024-10-28 | 20 | 0 | 0 |  | 0 | 70 |  | 3rd floor misc |  | 14
2024-11-05 | 2914 |  | 56576 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2024-11-11 | Z | 2024-10-28 | 30 | 0 | 0 |  | 0 | 60 |  | 3rd floor misc |  | 14
2024-11-06 | 2916 | sp | 56578 | A | DONE | 3 | S | pt.ss | LABCORP 6240016 |  | 2024-11-11 | Z | 2024-11-04 | 20 | 50 | 0 |  | 0 | 70 |  | 3rd floor misc |  | 7
2024-11-05 | 117 |  | 70594 | A | DONE | 2 | S |  | MEMORIAL HS 6210024 |  | 2024-11-05 | Z | 2024-11-05 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-11-05 | 116 |  | 70593 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | paint | 2024-11-05 | Z | 2024-11-05 | 20 | 0 | 0 |  | 20 | 30 |  | Grille tie ins |  | 0
2024-11-05 | 118 | bth | 70595 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | paint | 2024-11-05 | Z | 2024-11-05 | 20 | 20 | 0 |  | 20 | 60 |  | Misc |  | 0
2024-11-05 | 120 |  | 70596 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 |  | 2024-11-05 | Z | 2024-11-05 | 30 | 0 | 0 |  | 20 | 50 |  | Misc |  | 0
2024-11-05 | 3954 |  | 81066 | A | DONE | 2 | S |  | PECATONICA 6240005 | paint , 1" liner | 2024-11-11 | Z | 2024-10-30 | 30 | 0 | 0 |  | 30 | 40 |  | 107 / 108 tie ins |  | 12
2024-11-05 | 3955 | sp | 81067 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2024-11-11 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 30 |  | Boiler storm collar |  | 11
2024-11-06 | 3956 |  | 81068 | A | DONE | 3 | S-M |  | PECATONICA 6240005 | 1" liner | 2024-11-11 | Z | 2024-11-04 | 70 | 0 | 0 |  | 60 | 110 |  | AHU-1 RA |  | 7
2024-11-06 | 3957 | sp | 81069 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2024-11-11 | Z | 2024-11-04 | 20 | 30 | 0 |  | 0 | 40 |  | VAV 1 inlet |  | 7
2024-11-08 | 2516 |  | 62721 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-11-11 | Z | 2024-11-07 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 4
2024-11-08 | 2517 |  | 81858 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-11-11 | Z | 2024-11-07 | 30 | 0 | 0 |  | 0 | 50 |  | SA outs |  | 4
2024-11-05 | 114 |  | 70688 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-11-11 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 40 |  | Misc outs |  | 11
2024-11-06 | 4290 |  | 79962 | A | DONE | 2 | S |  | ST.BERNARD 6230023 |  | 2024-11-11 | Z | 2024-11-01 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 10
2024-11-06 | 4291 |  | 79965 | A | DONE | 2 | S |  | ST.BERNARD 6230023 |  | 2024-11-12 | Z | 2024-11-05 | 20 | 0 | 0 |  | 0 | 20 |  | Angle flashing |  | 7
2024-11-07 | 354 | bth | L02_B_SAMP_001 | A | DONE | 10 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 230 | 20 | 0 |  | 0 | 350 |  |  |  | 27
2024-11-07 | 355 |  | L02_B_SAMP_002 | A | DONE | 12 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 190 | 0 | 90 | F | 0 | 370 |  |  |  | 27
2024-11-07 | 356 | bth | L02_B_SAMP_003 | A | DONE | 11 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 100 | 80 | 90 | F | 0 | 330 |  |  |  | 27
2024-11-07 | 357 | bth | L02_B_SAMP_004 | A | DONE | 11 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 80 | 20 | 170 | F | 0 | 340 |  |  |  | 27
2024-11-07 | 358 | bth | L02_B_SAMP_005 | A | DONE | 10 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 100 | 30 | 110 | F | 0 | 290 |  |  |  | 27
2024-11-07 | 359 | bth | L02_B_SAMP_006 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 70 | 40 | 30 | F | 0 | 160 |  |  |  | 27
2024-11-07 | 360 | bth | L02_B_SAMP_007 | A | DONE | 10 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 60 | 70 | 100 | F | 0 | 270 |  |  |  | 27
2024-11-06 | 361 | bth | L02_B_SAMP_008 | A | DONE | 15 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-11-07 | Z | 2024-10-18 | 260 | 20 | 90 | F | 0 | 590 |  |  |  | 20
2024-11-06 | 362 | bth | L02_B_SAMP_009 | A | DONE | 11 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-11-07 | Z | 2024-10-18 | 160 | 60 | 50 | F | 0 | 380 |  |  |  | 20
2024-11-06 | 363 | bth | L02_B_SAMP_010 | A | DONE | 16 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-11-07 | Z | 2024-10-18 | 30 | 30 | 340 | F | 0 | 670 |  |  |  | 20
2024-11-06 | 364 | bth | L02_B_SAMP_011 | A | DONE | 8 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-07 | Z | 2024-10-18 | 100 | 20 | 60 | F | 0 | 200 |  |  |  | 20
2024-11-06 | 365 | bth | L02_B_SAMP_012 | A | DONE | 7 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-07 | Z | 2024-10-18 | 70 | 20 | 80 | F | 0 | 180 |  |  |  | 20
2024-11-06 | 366 | bth | L02_B_SAMP_013 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-07 | Z | 2024-10-18 | 70 | 30 | 30 | F | 0 | 150 |  |  |  | 20
2024-11-07 | 367 |  | L02_B_SAMP_014 | A | DONE | 8 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 150 | 0 | 40 | F | 0 | 370 |  |  |  | 27
2024-11-07 | 368 |  | L02_B_SAMP_015 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-14 | Z | 2024-10-18 | 0 | 0 | 80 | F | 0 | 120 |  |  |  | 27
2024-11-06 | 119 | bth | 83176 - 83178 | A | DONE | 10 | S-M |  | THERMO FISHER 4240032 | flex | 2024-11-12 | Z | 2024-11-05 | 70 | 50 | 120 | F | 0 | 230 |  | Misc |  | 7
2024-11-08 | 121 | bth | 83179 - 83180 | A | DONE | 7 | S-M |  | THERMO FISHER 4240032 |  | 2024-11-12 | Z | 2024-11-06 | 130 | 30 | 0 |  | 0 | 170 |  | EF-4103 |  | 6
2024-11-08 | 122 |  | 83181 - 83182 | A | DONE | 10 | S-M |  | THERMO FISHER 4240032 |  | 2024-11-12 | Z | 2024-11-06 | 100 | 0 | 140 | F | 0 | 230 |  | PC1 SA / RA |  | 6
2024-11-08 | 123 | sp | 83183 | A | DONE | 3 | S |  | THERMO FISHER 4240032 |  | 2024-11-12 | Z | 2024-11-06 | 20 | 40 | 0 |  | 0 | 60 |  | EA DH |  | 6
2024-11-06 | 671 |  | 70468 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-11-12 | Z | 2024-10-30 | 50 | 0 | 0 |  | 0 | 70 |  | L1Z1-A-FEMP-Change |  | 13
2024-11-07 | 674 |  | 70469 | A | DONE | 2 | S | BI | UWRF 6230010 |  | 2024-11-12 | Z | 2024-10-31 | 20 | 0 | 0 |  | 0 | 20 |  | DC-1 L1Z2-C |  | 12
2024-11-06 | 676 |  | 70471 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-11-12 | Z | 2024-10-31 | 50 | 0 | 0 |  | 0 | 150 |  | L1Z1-A-CUH-9 |  | 12
2024-11-05 | 677 | w | Email | A | DONE | 2 | S | BI | UWRF 6230010 |  | 2024-11-11 | Z | 2024-11-04 | 20 | 0 | 0 |  | 0 | 70 |  | Storm collars |  | 7
2024-11-06 | 1317 |  | EA-04-01 | A | DONE | 7 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-12 | Z | 2024-10-09 | 80 | 0 | 80 | F | 0 | 190 |  |  |  | 34
2024-11-07 | 1318 |  | RA-02-06 | A | DONE | 18 | S-M |  | UWSP ALBERTSON 6230016 | 2" liner | 2024-11-12 | Z | 2024-10-09 | 440 | 0 | 0 |  | 320 | 870 |  |  |  | 34
2024-11-04 | 1321 | bth | LPSA-01-19 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 230 | 50 | 0 |  | 60 | 410 |  |  |  | 27
2024-11-04 | 1322 | bth | LPSA-01-01 | A | DONE | 16 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 370 | 30 | 0 |  | 90 | 490 |  |  |  | 27
2024-11-04 | 1323 | bth | LPSA-01-02 | A | DONE | 10 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 200 | 50 | 0 |  | 100 | 330 |  |  |  | 27
2024-11-04 | 1324 | bth | LPSA-01-03 | A | DONE | 15 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 240 | 80 | 40 | F | 60 | 490 |  |  |  | 27
2024-11-04 | 1325 | bth | LPSA-01-04 | A | DONE | 14 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 220 | 110 | 0 |  | 60 | 360 |  |  |  | 27
2024-11-04 | 1326 | bth | LPSA-01-05 | A | DONE | 13 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 210 | 50 | 60 | F | 50 | 420 |  |  |  | 27
2024-11-04 | 1327 | bth | LPSA-01-07 | A | DONE | 7 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 70 | 40 | 50 | F | 30 | 180 |  |  |  | 27
2024-11-04 | 1328 | bth | LPSA-01-09 | A | DONE | 21 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 470 | 20 | 20 | F | 40 | 590 |  |  |  | 27
2024-11-05 | 1329 | bth | LPSA-01-10 | A | DONE | 16 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 200 | 20 | 160 | F | 40 | 500 |  |  |  | 27
2024-11-05 | 1330 | bth | LPSA-01-18 | A | DONE | 6 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-05 | Z | 2024-10-09 | 80 | 70 | 0 |  | 40 | 170 |  |  |  | 27
2024-11-06 | 1348 |  | EA-04-02 | A | DONE | 16 | M |  | UWSP ALBERTSON 6230016 |  | 2024-11-12 | Z | 2024-10-16 | 300 | 0 | 100 | F | 0 | 510 |  |  |  | 27
2024-11-07 | 1349 |  | EA-04-03 | A | DONE | 6 | S |  | UWSP ALBERTSON 6230016 |  | 2024-11-12 | Z | 2024-10-16 | 100 | 0 | 30 | F | 0 | 150 |  |  |  | 27
2024-11-07 | 1350 |  | EA-04-04 | A | DONE | 20 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-11-12 | Z | 2024-10-16 | 500 | 0 | 0 |  | 0 | 1270 |  |  |  | 27
2024-11-07 | 1351 |  | EA-04-05 | A | DONE | 21 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-11-12 | Z | 2024-10-16 | 510 | 0 | 0 |  | 0 | 1460 |  |  |  | 27
2024-11-07 | 1352 |  | EA-04-06 | A | DONE | 4 | S |  | UWSP ALBERTSON 6230016 |  | 2024-11-12 | Z | 2024-10-16 | 80 | 0 | 20 | F | 0 | 140 |  |  |  | 27
2024-11-07 | 1368 |  | 81126 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-11-12 | Z | 2024-11-06 | 50 | 0 | 0 |  | 0 | 60 |  | Strap |  | 6
2024-11-04 | 2457 | bth | L2_SAMP 2 | A | DONE | 24 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-05 | Z | 2024-10-21 | 400 | 60 | 120 | F | 0 | 1180 |  |  |  | 15
2024-11-04 | 2458 | bth | L2_SAMP 3 | A | DONE | 26 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-05 | Z | 2024-10-21 | 520 | 60 | 70 | F | 0 | 1140 |  |  |  | 15
2024-11-04 | 2459 | bth | L2_SAMP 4 | A | DONE | 14 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-05 | Z | 2024-10-21 | 180 | 60 | 90 | F | 0 | 680 |  |  |  | 15
2024-11-04 | 2460 | bth | L2_SAMP 5 | A | DONE | 31 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-05 | Z | 2024-10-21 | 290 | 40 | 440 | F | 0 | 1270 |  |  |  | 15
2024-11-04 | 2466 |  | L2_SAMP 11 | A | DONE | 9 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-05 | Z | 2024-10-21 | 220 | 0 | 0 |  | 0 | 590 |  |  |  | 15
2024-11-04 | 2467 |  | 58808 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-07 | Z | 2024-10-23 | 50 | 0 | 0 |  | 0 | 80 |  | Straps |  | 15
2024-11-04 | 2470 | sp | L2_EA 1 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-07 | Z | 2024-10-29 | 30 | 120 | 0 |  | 0 | 160 |  |  |  | 9
2024-11-04 | 2471 | sp | L2_EA 2 | A | DONE | 7 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-07 | Z | 2024-10-29 | 60 | 110 | 0 |  | 0 | 170 |  |  |  | 9
2024-11-05 | 2472 |  | L2_EA 3 | A | DONE | 8 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-07 | Z | 2024-10-29 | 60 | 0 | 130 | F | 0 | 240 |  |  |  | 9
2024-11-05 | 2473 |  | L2_RA 1 | A | DONE | 30 | M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-07 | Z | 2024-10-29 | 620 | 0 | 110 | F | 0 | 970 |  |  |  | 9
2024-11-05 | 2474 |  | L2_RA 2 | A | DONE | 54 | L |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-07 | Z | 2024-10-29 | 1170 | 0 | 170 | F | 0 | 2260 |  |  |  | 9
2024-11-05 | 2475 |  | L2_RA 3 | A | DONE | 22 | M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-07 | Z | 2024-10-29 | 260 | 0 | 290 | F | 0 | 910 |  |  |  | 9
2024-11-07 | 2002 |  | 73091 | A | DONE | 2 | S | neal | UW-VET MED 6210014 |  | 2024-11-11 | Z | 2024-11-07 | 40 | 0 | 0 |  | 0 | 80 |  | Arena |  | 4
2024-11-06 | 894 |  | 72397 - 72398 | A | DONE | 5 | S-M |  | WINDSOR 6240012 | bird.s , flex | 2024-11-11 | Z | 2024-10-31 | 110 | 0 | 0 |  | 0 | 160 |  | FCU SA |  | 11
2024-11-06 | 1949 | sp | 71459 | A | DONE | 10 | S-M | neal | WSCC 6240006 |  | 2024-11-11 | Z | 2024-11-05 | 20 | 230 | 0 |  | 0 | 280 |  | RTU-02 |  | 6
2024-11-07 | 1950 |  | 71460 | A | DONE | 4 | S | neal | WSCC 6240006 |  | 2024-11-11 | Z | 2024-11-05 | 0 | 90 | 0 |  | 0 | 100 |  | RTU-2 |  | 6
2024-11-08 | 1951 |  | 71461 | A | DONE | 4 | S-M | neal | WSCC 6240006 | 1" liner | 2024-11-11 | Z | 2024-11-07 | 90 | 0 | 0 |  | 80 | 180 |  | RTU-6 SA |  | 4
2024-11-07 | 1953 |  | Pre-Fab Hangers | A | DONE | 2 | S | neal | WSCC 6240006 |  | 2024-11-11 | Z | 2024-11-07 | 20 | 0 | 0 |  | 0 | 40 |  | Hangers |  | 4
[6 empty] | 888 | [13 empty] | 30960 |  |  |  | 9000 | 29.07%
WEEK OF 11/11/2024
2024-11-12 | 3924 |  | 96564 | A | DONE | 2 | S-M | BI | 121 E. WILSON 6230024 |  | 2024-11-15 | Z | 2024-09-26 | 40 | 0 | 0 |  | 0 | 90 |  | Caps |  | 50
2024-11-12 | 3903d |  | 80139 | A | DONE | n/a | M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-15 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. West unit plenums | Design Air | 95
2024-11-12 | 3904d |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-15 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. West unit Taps | Design Air | 95
2024-11-12 | 3905d |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-15 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. West unit sliders | Design Air | 95
2024-11-12 | 3906d |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-15 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. West Corr. HP's | Design Air | 95
2024-11-18 | 3909d |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-22 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. East unit plenums | Design Air | 102
2024-11-18 | 3910d |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-22 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. East Taps | Design Air | 102
2024-11-18 | 3911d |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-22 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. East sliders | Design Air | 102
2024-11-18 | 3913d |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-22 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 8th Fl. East Corr. HP's | Design Air | 102
2024-11-13 | 3914c |  | 81901 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2024-11-18 | Z | 2024-08-12 | 30 | 0 | 0 |  | 20 | 30 |  | 9th Fl. IDF TA |  | 98
2024-11-13 | 3915e | sp | 81902 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-18 | Z | 2024-08-12 | 20 | 90 | 0 |  | 0 | 90 |  | 9th Fl. OA |  | 98
2024-11-14 | 3916e |  | 81903 - 81904 | A | DONE | 34 | M |  | 121 E. WILSON 6230024 |  | 2024-11-18 | Z | 2024-08-12 | 830 | 0 | 0 |  | 0 | 890 |  | 9th Fl. East EA |  | 98
2024-11-12 | 775 | sp | 80239 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-11-14 | Z | 2024-11-11 | 20 | 30 | 0 |  | 0 | 50 |  | Sterile SPD RA |  | 3
2024-11-13 | 2052 |  | 69834 | A | DONE | 2 | S-M | ss | CDIS 6220028 | flex , angle frames | 2024-11-15 | Z | 2024-11-01 | 30 | 0 | 0 |  | 0 | 90 |  | PH 1A,1N VIV |  | 14
2024-11-14 | 2056 | sp | 61325 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-11-19 | Z | 2024-11-07 | 20 | 0 | 0 |  | 0 | 30 |  | 5th floor misc |  | 12
2024-11-12 | 2057 |  | 61327 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-11-19 | Z | 2024-11-08 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor Rm. 3611 |  | 11
2024-11-14 | 2058 |  | 61384 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-11-19 | Z | 2024-11-08 | 40 | 0 | 0 |  | 0 | 60 |  | AHU-7 |  | 11
2024-11-14 | 2059 | sp | 61329 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-11-19 | Z | 2024-11-13 | 20 | 0 | 0 |  | 0 | 20 |  | 4th / 5th misc |  | 6
2024-11-14 | 803 |  | 70689 | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2024-11-15 | Z | 2024-11-13 | 20 | 20 | 0 |  | 0 | 40 |  | Heater outs |  | 2
2024-11-11 | 1112 |  | 79019 | A | DONE | 8 | S-M |  | EXACT SNOW HOOD 2240029 |  | 2024-11-13 | Z | 2024-11-06 | 190 | 0 | 0 |  | 0 | 580 |  | Snow Hood |  | 7
2024-11-13 | 1115 |  | 79120 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-11-14 | Z | 2024-11-13 | 20 | 0 | 0 |  | 0 | 40 |  | RA tie ins |  | 1
2024-11-14 | 2917 | sp | 56579 - 56581 | A | DONE | 14 | M |  | LABCORP 6240016 | flex , spiral mates | 2024-11-19 | Z | 2024-11-05 | 150 | 180 | 0 |  | 0 | 400 |  | 1st floor area B |  | 14
2024-11-14 | 2653 |  | 13579 | A | DONE | 3 | S |  | MONROE HS 6240018 | 2" FB | 2024-11-18 | Z | 2024-11-13 | 70 | 0 | 0 |  | 0 | 120 |  | Sleeves |  | 5
2024-11-14 | 110 | bth | 84749 | A | DONE | 12 | S-M |  | OEM 4249999 | flex | 2024-11-19 | Z | 2024-10-28 | 120 | 170 | 0 |  | 0 | 270 |  | Misc |  | 22
2024-11-13 | 3958 |  | 81043 | A | DONE | 2 | S |  | PECATONICA 6240005 | 1" liner | 2024-11-18 | Z | 2024-11-11 | 40 | 0 | 0 |  | 40 | 70 |  | Misc |  | 7
2024-11-18 | 3960 |  | 81045 | A | DONE | 2 | S |  | PECATONICA 6240005 |  | 2024-11-25 | Z | 2024-11-13 | 20 | 0 | 0 |  | 0 | 60 |  | Louver blank off |  | 12
2024-11-13 | 2513 | w | 56350 | A | DONE | 3 | S-M |  | PROMEGA BTC 6230022 | 1-1/2" DB | 2024-11-18 | Z | 2024-10-31 | 60 | 0 | 0 |  | 50 | 180 |  | Curb |  | 18
2024-11-13 | 2514 | sp | 62720 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 | bird.s | 2024-11-18 | Z | 2024-10-31 | 40 | 60 | 0 |  | 0 | 120 |  | Boiler intake |  | 18
2024-11-18 | 2515 | sp | 59819 | A | DONE | 10 | S-M |  | PROMEGA BTC 6230022 | spiral mate | 2024-11-20 | Z | 2024-11-06 | 150 | 90 | 0 |  | 0 | 320 |  | EA |  | 14
2024-11-14 | 2518 | sp | 81859 | A | DONE | 2 | S | ss | PROMEGA MCBR 2240039 |  | 2024-11-20 | Z | 2024-11-14 | 20 | 0 | 0 |  | 0 | 20 |  | EA hood |  | 6
2024-11-18 | 4776 |  | 61184 - 61185 | A | DONE | 7 | S-M |  | ROCK CO. JAIL 6220018 |  | 2024-11-20 | Z | 2024-11-13 | 170 | 0 | 0 |  | 0 | 200 |  | Remodel |  | 7
2024-11-18 | 4777 |  | 61186 | A | DONE | 4 | S |  | ROCK CO. JAIL 6220018 |  | 2024-11-20 | Z | 2024-11-13 | 80 | 0 | 0 |  | 0 | 110 |  | Remodel |  | 7
2024-11-13 | 4292 |  | 79966 | A | DONE | 2 | S | neal | ST.BERNARD 2230056 |  | 2024-11-18 | Z | 2024-11-13 | 20 | 0 | 0 |  | 0 | 20 |  | UH Vent flashing |  | 5
2024-11-13 | 478 |  | 83011 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-11-13 | 20 | 0 | 0 |  | 0 | 30 |  | Flat stock |  | 8
2024-11-11 | 125 |  | 83184 | A | DONE | 2 | S |  | THERMO FISHER 4240032 |  | 2024-11-11 | Z | 2024-11-11 | 20 | 0 | 0 |  | 0 | 30 |  | DH-OA |  | 0
2024-11-12 | 126 |  | 83185 | A | DONE | 2 | S |  | THERMO FISHER 4240032 |  | 2024-11-12 | Z | 2024-11-12 | 20 | 0 | 0 |  | 0 | 30 |  | PC-OC |  | 0
2024-11-18 | 127 | sp | 83186 | A | DONE | 2 | S |  | THERMO FISHER 4240032 |  | 2024-11-15 | Z | 2024-11-15 | 20 | 20 | 0 |  | 0 | 40 |  | Misc |  | 0
2024-11-12 | 4567 |  | 001112 | A | DONE | 2 | S | BI | UW LEVY HALL 8230028 |  | 2024-11-15 | Z | 2024-11-12 | 40 | 0 | 0 |  | 0 | 160 |  | BI CAPS |  | 3
2024-11-11 | 4566 |  | 111124 | A | DONE | 2 | S | BI | UW-LEVY HALL 8230028 |  | 2024-11-11 | Z | 2024-11-11 | 20 | 0 | 0 |  | 0 | 40 |  | Caps |  | 0
2024-11-13 | 3889 |  | 82122 - 82123 | A | DONE | 2 | S-M |  | UWL-GRAFF 6230017 |  | 2024-11-18 | Z | 2024-11-05 | 40 | 0 | 0 |  | 0 | 80 |  | 2nd RA / SA |  | 13
2024-11-13 | 3890 |  | 82124 | A | DONE | 3 | S |  | UWL-GRAFF 6230017 | flex | 2024-11-18 | Z | 2024-11-06 | 60 | 0 | 0 |  | 0 | 80 |  | 2ND RA |  | 12
2024-11-14 | 3891 |  | 82125 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 |  | 2024-11-18 | Z | 2024-11-11 | 30 | 0 | 0 |  | 0 | 90 |  | AHU-4 OA |  | 7
2024-11-14 | 548 |  | L4 MER - RAMP 2 | A | DONE | 66 | L |  | UWRF 6230010 | perf | 2024-11-19 | Z | 2024-08-07 | 1640 | 0 | 0 |  | 0 | 4530 |  |  |  | 104
2024-11-14 | 678 |  | 70472 | A | DONE | 2 | S-M | neal | UWRF 6230010 | bird s. | 2024-11-19 | Z | 2024-11-06 | 20 | 0 | 0 |  | 0 | 30 |  | CUH-16-L1Z2-16 |  | 13
2024-11-12 | 679 |  | 70473 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-11-19 | Z | 2024-11-07 | 50 | 0 | 0 |  | 0 | 120 |  | Flashing |  | 12
2024-11-13 | 680 | sp | 70474 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-11-19 | Z | 2024-11-13 | 20 | 0 | 0 |  | 0 | 50 |  | Temp heat |  | 6
2024-11-14 | 1331 |  | RA-04-17 | A | DONE | 15 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-19 | Z | 2024-10-09 | 80 | 0 | 290 | F | 0 | 480 |  |  |  | 41
2024-11-14 | 1332 |  | RA-04-11 | A | DONE | 31 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-11-19 | Z | 2024-10-09 | 570 | 0 | 190 | F | 0 | 1490 |  |  |  | 41
2024-11-14 | 1333 |  | RA-04-12 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-19 | Z | 2024-10-09 | 180 | 0 | 110 | F | 0 | 400 |  |  |  | 41
2024-11-14 | 1334 |  | RA-04-13 | A | DONE | 23 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-19 | Z | 2024-10-09 | 180 | 0 | 380 | F | 0 | 1140 |  |  |  | 41
2024-11-14 | 1335 |  | RA-04-14 | A | DONE | 22 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-19 | Z | 2024-10-09 | 290 | 0 | 240 | F | 0 | 640 |  |  |  | 41
2024-11-14 | 1336 |  | RA-04-15 | A | DONE | 20 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-19 | Z | 2024-10-09 | 190 | 0 | 290 | F | 0 | 640 |  |  |  | 41
2024-11-18 | 1337 |  | RA-04-16 | A | DONE | 6 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-11-19 | Z | 2024-10-09 | 60 | 0 | 90 | F | 0 | 180 |  |  |  | 41
2024-11-18 | 1361 |  | RA-01-CAB-1 | A | DONE | 4 | S |  | UWSP ALBERTSON 6230016 | flex | 2024-11-19 | Z | 2024-11-04 | 80 | 0 | 0 |  | 0 | 110 |  |  |  | 15
2024-11-18 | 1362 |  | SA-01-CAB-2 | A | DONE | 13 | M |  | UWSP ALBERTSON 6230016 | VD , flex | 2024-11-19 | Z | 2024-11-04 | 160 | 0 | 160 | F | 0 | 410 |  |  |  | 15
2024-11-11 | 2476 | bth | L2_SALP 1 | A | DONE | 7 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 90 | 70 | 0 |  | 30 | 180 |  |  |  | 9
2024-11-11 | 2477 | bth | L2_SALP 2 | A | DONE | 8 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 150 | 0 | 30 | F | 40 | 240 |  |  |  | 9
2024-11-11 | 2478 | bth | L2_SALP 3 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 50 | 50 | 0 |  | 0 | 100 |  |  |  | 9
2024-11-11 | 2479 | bth | L2_SALP 4 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 80 | 40 | 20 | F | 30 | 160 |  |  |  | 9
2024-11-11 | 2480 | bth | L2_SALP 5 | A | DONE | 5 | S | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 40 | 70 | 0 |  | 30 | 130 |  |  |  | 9
2024-11-11 | 2481 | bth | L2_SALP 6 | A | DONE | 20 | M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 250 | 120 | 130 | F | 60 | 560 |  |  |  | 9
2024-11-11 | 2482 | bth | L2_SALP 7 | A | DONE | 3 | S | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 40 | 30 | 0 |  | 30 | 80 |  |  |  | 9
2024-11-11 | 2483 | bth | L2_SALP 8 | A | DONE | 15 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 200 | 50 | 110 | F | 40 | 460 |  |  |  | 9
2024-11-11 | 2484 | bth | L2_SALP 9 | A | DONE | 12 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-14 | Z | 2024-11-05 | 180 | 40 | 80 | F | 0 | 400 |  |  |  | 9
2024-11-11 | 2485 | bth | L2_SALP 10 | A | DONE | 10 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 70 | 30 | 140 | F | 40 | 300 |  |  |  | 9
2024-11-12 | 2486 |  | L2_SALP 11 | A | DONE | 16 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 320 | 0 | 60 | F | 80 | 510 |  |  |  | 9
2024-11-12 | 2487 | bth | L2_SALP 12 | A | DONE | 8 | S | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 150 | 20 | 20 | F | 40 | 230 |  |  |  | 9
2024-11-12 | 2488 | bth | L2_SALP 13 | A | DONE | 11 | S-M | neal | UWSP CHAMPION HALL 6240008 |  | 2024-11-14 | Z | 2024-11-05 | 70 | 20 | 180 | F | 0 | 340 |  |  |  | 9
2024-11-12 | 2489 |  | L2_SALP 14 | A | DONE | 7 | S | neal | UWSP CHAMPION HALL 6240008 |  | 2024-11-14 | Z | 2024-11-05 | 40 | 0 | 120 | F | 0 | 210 |  |  |  | 9
2024-11-12 | 2490 |  | L2_SALP 15 | A | DONE | 9 | S-M | neal | UWSP CHAMPION HALL 6240008 |  | 2024-11-14 | Z | 2024-11-05 | 90 | 0 | 130 | F | 0 | 290 |  |  |  | 9
2024-11-12 | 2491 |  | L2_SALP 16 | A | DONE | 11 | S-M | neal | UWSP CHAMPION HALL 6240008 |  | 2024-11-14 | Z | 2024-11-05 | 70 | 0 | 190 | F | 0 | 340 |  |  |  | 9
2024-11-12 | 2492 | bth | L2_SALP 17 | A | DONE | 7 | S | neal | UWSP CHAMPION HALL 6240008 |  | 2024-11-14 | Z | 2024-11-05 | 110 | 30 | 30 | F | 0 | 220 |  |  |  | 9
2024-11-12 | 2493 |  | L2_SALP 18 | A | DONE | 14 | S-M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 150 | 0 | 180 | F | 30 | 410 |  |  |  | 9
2024-11-12 | 2494 |  | L2_SALP 19 | A | DONE | 16 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 160 | 0 | 220 | F | 30 | 460 |  |  |  | 9
2024-11-12 | 2495 |  | L2_SALP 20 | A | DONE | 12 | S-M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 160 | 0 | 140 | F | 40 | 390 |  |  |  | 9
2024-11-12 | 2496 |  | L2_SALP 21 | A | DONE | 16 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 140 | 0 | 250 | F | 40 | 470 |  |  |  | 9
2024-11-12 | 2497 |  | L2_SALP 22 | A | DONE | 13 | S-M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 190 | 0 | 130 | F | 40 | 420 |  |  |  | 9
2024-11-12 | 2498 |  | L2_SALP 23 | A | DONE | 15 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 120 | 0 | 250 | F | 40 | 480 |  |  |  | 9
2024-11-13 | 2499 |  | L2_SALP 24 | A | DONE | 15 | S-M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 220 | 0 | 140 | F | 40 | 430 |  |  |  | 9
2024-11-13 | 2600 |  | L2_SALP 25 | A | DONE | 16 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 150 | 20 | 220 | F | 40 | 490 |  |  |  | 9
2024-11-13 | 2601 |  | L2_SALP 26 | A | DONE | 15 | S-M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 280 | 0 | 80 | F | 40 | 440 |  |  |  | 9
2024-11-13 | 2602 | bth | L2_SALP 27 | A | DONE | 16 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 140 | 20 | 240 | F | 40 | 530 |  |  |  | 9
2024-11-13 | 2603 | bth | L2_SALP 28 | A | DONE | 15 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 140 | 20 | 210 | F | 30 | 480 |  |  |  | 9
2024-11-13 | 2604 | bth | L2_SALP 29 | A | DONE | 20 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 270 | 20 | 190 | F | 40 | 570 |  |  |  | 9
2024-11-13 | 2605 | bth | L2_SALP 30 | A | DONE | 19 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 300 | 20 | 140 | F | 50 | 590 |  |  |  | 9
2024-11-13 | 2606 | bth | L2_SALP 31 | A | DONE | 18 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 110 | 20 | 320 | F | 40 | 570 |  |  |  | 9
2024-11-13 | 2607 | bth | L2_SALP 32 | A | DONE | 13 | S-M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 150 | 20 | 140 | F | 50 | 400 |  |  |  | 9
2024-11-13 | 2608 |  | L2_SALP 33 | A | DONE | 20 | M | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 150 | 0 | 330 | F | 40 | 600 |  |  |  | 9
2024-11-13 | 2609 |  | L2_SALP 34 | A | DONE | 22 | M-L | neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-14 | Z | 2024-11-05 | 380 | 0 | 160 | F | 60 | 820 |  |  |  | 9
2024-11-13 | 2610 |  | L2_SALP 35 | A | DONE | 20 | M | neal | UWSP CHAMPION HALL 6240008 |  | 2024-11-14 | Z | 2024-11-05 | 330 | 0 | 160 | F | 0 | 580 |  |  |  | 9
2024-11-14 | 2611 |  | 58809 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-21 | Z | 2024-11-11 | 140 | 0 | 0 |  | 0 | 190 |  | Angle |  | 10
2024-11-12 | 2613 |  | 70124 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-14 | Z | 2024-11-11 | 60 | 0 | 0 |  | 0 | 200 |  | L2-SAMP-6 |  | 3
2024-11-18 | 2631 |  | 58812 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 20 | 0 | 0 |  | 0 | 40 |  | DSS Dog house |  | 15
2024-11-11 | 2003 |  | 73092 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-11-12 | Z | 2024-11-11 | 20 | 0 | 0 |  | 0 | 20 |  | Arena |  | 1
2024-11-11 | 124 | w | 11824 | A | DONE | 2 | S |  | WISCO. LIFT TRUCK 20009100 |  | 2024-11-13 | Z | 2024-11-08 | 30 | 0 | 0 |  | 0 | 100 |  | Curb caps |  | 5
2024-11-14 | 1888 |  | 80851 | A | DONE | 4 | S | neal | WSCC 6240006 | s.mates | 2024-11-18 | Z | 2024-08-13 | 80 | 0 | 0 |  | 0 | 180 |  | DHU-1 |  | 97 |  |  |  |  | 2024-12-09
2024-11-13 | 1889 | sp | 80852 - 80853 | A | DONE | 104 | L | neal | WSCC 6240006 | s.mates | 2024-11-18 | Z | 2024-08-13 | 210 | 2370 | 0 |  | 0 | 3620 |  | DHU-1 |  | 97 |  |  |  |  | 2024-12-09
2024-11-11 | 1948 |  | Pre-Fab Hangers | A | DONE | 2 | S | neal | WSCC 6240006 |  | 2024-11-14 | Z | 2024-11-05 | 20 | 0 | 0 |  | 0 | 60 |  | Hangers |  | 9
2024-11-12 | 1955 |  | 71464 | A | DONE | 4 | S |  | WSCC 6240006 |  | 2024-11-12 | Z | 2024-11-12 | 80 | 0 | 0 |  | 0 | 180 |  | Flat Stock |  | 0
2024-11-13 | 1956 |  | 71464 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2024-11-14 | Z | 2024-11-13 | 20 | 0 | 0 |  | 0 | 20 |  | B-Roof |  | 1
[6 empty] | 955 | [13 empty] | 33210 |  |  |  | 16870 | 50.8%
WEEK OF 11/18/2024
2024-11-19 | 2245 |  | 80073 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 | paint | 2024-11-25 | Z | 2024-07-25 | 50 | 0 | 170 | F | 20 | 200 |  | DOAS-1 / OA-4 |  | 123
2024-11-19 | 3659 |  | 80086 , 80093 | A | DONE | 18 | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-25 | Z | 2024-07-30 | 90 | 0 | 340 | F | 0 | 460 |  | EF-1,2 , EA-5 |  | 118
2024-11-21 | 3903e |  | 80139 | A | DONE | n/a | M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. West unit plenums | Design Air | 109
2024-11-21 | 3904e |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. West unit Taps | Design Air | 109
2024-11-21 | 3905e |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. West unit sliders | Design Air | 109
2024-11-21 | 3906e |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-11-29 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. West Corr. HP's | Design Air | 109
2024-11-18 | 3907f |  | 80143 - 80144 | A | DONE | 31 | S-M |  | 121 E. WILSON 6230024 |  | 2024-11-25 | Z | 2024-08-12 | 770 | 0 | 0 |  | 0 | 840 |  | 10th Fl. West EA |  | 105
2024-11-18 | 3912d |  | 80149 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-11-22 | Z | 2024-08-12 | 30 | 0 | 0 |  | 0 | 40 |  | 8th Fl. East unit SA | Design Air | 102
2024-11-19 | 2060 |  | 61333 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-11-22 | Z | 2024-11-13 | 20 | 0 | 0 |  | 20 | 20 |  | 5th floor TA |  | 9
2024-11-19 | 2062 |  | 69714 | A | DONE | 3 | S |  | CDIS 6220028 |  | 2024-11-22 | Z | 2024-11-18 | 60 | 0 | 0 |  | 0 | 160 |  | Flashing |  | 4
2024-11-21 | 2063 |  | 61334 | A | DONE | 2 | S | neal | CDIS 6220028 | paint | 2024-11-26 | Z | 2024-11-18 | 20 | 0 | 0 |  | 20 | 30 |  | 4th floor 4625 |  | 8
2024-11-21 | 2065 |  | 81603 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-11-26 | Z | 2024-11-20 | 30 | 0 | 0 |  | 20 | 50 |  | 2ND Floor TA |  | 6
2024-11-21 | 2067 |  | 61385 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-11-22 | Z | 2024-11-21 | 30 | 0 | 0 |  | 0 | 30 |  | Temp Heat |  | 1
2024-11-20 | 128 | sp | 80904 | A | DONE | 12 | S-M |  | DEWITT 2240064 |  | 2024-11-25 | Z | 2024-11-15 | 80 | 210 | 0 |  | 0 | 270 |  | Conf. 805 |  | 10
2024-11-19 | 1108r |  | 79118 | A | DONE | 2 | S | ss | EXACT 2230049 |  | 2024-11-20 | Z | 2024-11-13 | 20 | 0 | 0 |  | 0 | 20 |  | Humidifier |  | 7
2024-11-20 | 1118 |  | 69126 | A | DONE | 2 | S |  | EXACT SCIENCE 6240009 |  | 2024-11-22 | Z | 2024-11-20 | 40 | 0 | 0 |  | 0 | 60 |  | C-Channel |  | 2
2024-11-20 | 132 |  | 84251 | A | DONE | 2 | S |  | HEARTLAND |  | 2024-11-21 | Z | 2024-11-20 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 1
2024-11-19 | 131 |  | email | A | DONE | 2 | S |  | HEATLAND 4240049 |  | 2024-11-19 | Z | 2024-11-19 | 20 | 0 | 0 |  | 0 | 20 |  | EC |  | 0
2024-11-22 | 3377 |  | 92788 | A | DONE | 2 | S | BI | JANESVILLE ESSR 6230011 |  | 2024-11-26 | Z | 2024-11-20 | 20 | 0 | 0 |  | 0 | 20 |  | Steel plate |  | 6
2024-11-20 | 3378 |  | 71467 | A | DONE | 4 | S | neal | JANESVILLE ESSR 6230011 |  | 2024-11-26 | Z | 2024-11-20 | 100 | 0 | 0 |  | 0 | 210 |  | Flashing |  | 6
2024-11-20 | 129 |  | 93187 | A | DONE | 2 | S | ss | JHT 4240048 |  | 2024-11-25 | Z | 2024-11-18 | 30 | 0 | 0 |  | 0 | 50 |  | Misc |  | 7
2024-11-19 | 2917r | sp | 56579 - 56581 | A | DONE | 14 | M |  | LABCORP 6240016 | flex , spiral mates | 2024-11-19 | Z | 2024-11-19 | 80 | 180 | 0 |  | 0 | 300 |  |  |  | 0
2024-11-21 | 133 |  | 80250 | A | DONE | 4 | S | pt.neal | OCTOPI 2240071 |  | 2024-11-22 | Z | 2024-11-21 | 60 | 20 | 0 |  | 20 | 80 |  | Conf. Rm |  | 1
2024-11-19 | 3959 |  | 81044 | A | DONE | 3 | S-M |  | PECATONICA 6240005 | 2" liner | 2024-11-25 | Z | 2024-11-13 | 70 | 0 | 0 |  | 50 | 100 |  | AHU-1 SA |  | 12
2024-11-18 | 350 | bth | L02_B_EAD_005 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 0 | 20 | 0 |  | 0 | 20 |  |  |  | 34
2024-11-18 | 351 |  | L02_B_RAD_001 | A | DONE | 37 | M-L | pt.neal | STOUGHTON TRAILER 6240015 | VD , 1" liner | 2024-11-21 | Z | 2024-10-18 | 520 | 0 | 400 | F | 310 | 1530 |  |  |  | 34
2024-11-18 | 352 |  | L02_B_RAD_002 | A | DONE | 12 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-11-21 | Z | 2024-10-18 | 250 | 0 | 50 | F | 220 | 380 |  |  |  | 34
2024-11-18 | 353 |  | L02_B_RAD_003 | A | DONE | 10 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 180 | 0 | 60 | F | 180 | 340 |  |  |  | 34
2024-11-18 | 369 |  | L02_B_SALP_015 | A | DONE | 5 | S | pt.neal | STOUGHTON TRAILER 6240015 | VD | 2024-11-21 | Z | 2024-10-18 | 120 | 0 | 0 |  | 0 | 180 |  |  |  | 34
2024-11-18 | 370 | bth | L02_B_SALP_016 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 20 | 70 | 60 | F | 0 | 140 |  |  |  | 34
2024-11-18 | 371 | bth | L02_B_SALP_018 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 34
2024-11-18 | 372 | bth | L02_B_SALP_019 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 40 | 30 | 0 |  | 0 | 60 |  |  |  | 34
2024-11-18 | 373 | bth | L02_B_SALP_020 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 34
2024-11-18 | 374 | bth | L02_B_SALP_021 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 80 | 20 | 40 | F | 0 | 130 |  |  |  | 34
2024-11-18 | 375 | bth | L02_B_SALP_022 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 34
2024-11-18 | 376 | bth | L02_B_SALP_023 | A | DONE | 15 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 90 | 280 | 0 |  | 0 | 370 |  |  |  | 34
2024-11-18 | 377 | sp | L02_B_SALP_024 | A | DONE | 9 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 40 | 170 | 0 |  | 0 | 230 |  |  |  | 34
2024-11-18 | 378 | sp | L02_B_SALP_025 | A | DONE | 8 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 30 | 150 | 0 |  | 0 | 180 |  |  |  | 34
2024-11-18 | 379 | bth | L02_B_SALP_026 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 34
2024-11-18 | 380 | bth | L02_B_SALP_027 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 34
2024-11-18 | 381 | bth | L02_B_SALP_028 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 20 | 80 | 0 |  | 0 | 100 |  |  |  | 34
2024-11-18 | 382 | bth | L02_B_SALP_029 | A | DONE | 8 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 130 | 50 | 0 |  | 0 | 160 |  |  |  | 34
2024-11-18 | 383 | bth | L02_B_SALP_030 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 70 | 20 | 0 |  | 0 | 90 |  |  |  | 34
2024-11-18 | 479 |  | 83012 | A | DONE | 2 | S-M | pt.neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-11-21 | Z | 2024-11-14 | 50 | 0 | 0 |  | 40 | 80 |  | 1st fl B |  | 7
2024-11-18 | 3646 | bth | L02_B_EAD_001 | A | DONE | 10 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 70 | 100 | 70 | F | 0 | 240 |  |  |  | 34
2024-11-18 | 3647 | bth | L02_B_EAD_002 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 | VD | 2024-11-21 | Z | 2024-10-18 | 50 | 40 | 40 | F | 0 | 120 |  |  |  | 34
2024-11-18 | 3648 |  | L02_B_EAD_003 | A | DONE | 9 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 150 | 0 | 60 | F | 0 | 250 |  |  |  | 34
2024-11-18 | 3649 | bth | L02_B_EAD_004 | A | DONE | 3 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-11-21 | Z | 2024-10-18 | 40 | 20 | 0 |  | 0 | 70 |  |  |  | 34
2024-11-20 | 3612r |  | L01_B_RAD_004 | A | DONE | 4 | S | pt.neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-11-21 | Z | 2024-11-18 | 90 | 0 | 0 |  | 70 | 140 |  | Missing pc's |  | 3
2024-11-21 | 3892 |  | 82126 - 82128 | A | DONE | 3 | S-M |  | UWL-GRAFF 6230017 |  | 2024-11-25 | Z | 2024-11-20 | 60 | 0 | 0 |  | 0 | 90 |  | Misc |  | 5
2024-11-19 | 681 |  | 83508 | A | DONE | 6 | S-M | pcd | UWRF 6230010 |  | 2024-11-25 | Z | 2024-11-13 | 130 | 0 | 0 |  | 0 | 320 |  | PH outs |  | 12
2024-11-19 | 682 |  | 83503 - 83504 | A | DONE | 9 | S-M |  | UWRF 6230010 |  | 2024-11-25 | Z | 2024-11-13 | 220 | 0 | 0 |  | 0 | 720 |  | PH outs |  | 12
2024-11-19 | 683 |  | 83506 - 83507 | A | DONE | 16 | S-M |  | UWRF 6230010 |  | 2024-11-25 | Z | 2024-11-13 | 390 | 0 | 0 |  | 0 | 1010 |  | PH outs |  | 12
2024-11-19 | 684 |  | 83509 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2024-11-25 | Z | 2024-11-14 | 50 | 0 | 0 |  | 0 | 180 |  | PH FEMP 3 |  | 11
2024-11-19 | 685 |  | 83510 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-11-25 | Z | 2024-11-14 | 20 | 0 | 0 |  | 0 | 70 |  | PH EAMP 2 |  | 11
2024-11-20 | 1338 | bth | LPSA-02-01 | A | DONE | 14 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-26 | Z | 2024-10-16 | 180 | 70 | 80 | F | 30 | 400 |  |  |  | 41
2024-11-20 | 1339 |  | VRF-1-2-1 | A | DONE | 6 | S |  | UWSP ALBERTSON 6230016 |  | 2024-11-26 | Z | 2024-10-16 | 130 | 0 | 0 |  | 0 | 220 |  |  |  | 41
2024-11-20 | 1340 | bth | LPSA-02-02 | A | DONE | 5 | S |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-26 | Z | 2024-10-16 | 50 | 30 | 30 | F | 50 | 130 |  |  |  | 41
2024-11-20 | 1341 | bth | LPSA-02-03 | A | DONE | 13 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-26 | Z | 2024-10-16 | 160 | 30 | 120 | F | 50 | 400 |  |  |  | 41
2024-11-20 | 1342 | bth | LPSA-02-04 | A | DONE | 23 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-26 | Z | 2024-10-16 | 280 | 20 | 270 | F | 60 | 730 |  |  |  | 41
2024-11-21 | 1343 | bth | LPSA-02-05 | A | DONE | 13 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-26 | Z | 2024-10-16 | 210 | 20 | 80 | F | 60 | 410 |  |  |  | 41
2024-11-21 | 1344 | bth | LPSA-02-06 | A | DONE | 15 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-26 | Z | 2024-10-16 | 250 | 20 | 100 | F | 50 | 500 |  |  |  | 41
2024-11-21 | 1345 | bth | LPSA-02-07 | A | DONE | 11 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-11-26 | Z | 2024-10-16 | 120 | 60 | 90 | F | 40 | 310 |  |  |  | 41
2024-11-21 | 1346 | bth | LPSA-02-08 | A | DONE | 17 | M |  | UWSP ALBERTSON 6230016 |  | 2024-11-26 | Z | 2024-10-16 | 150 | 80 | 180 | F | 40 | 500 |  |  |  | 41
2024-11-21 | 1347 | bth | LPSA-02-09 | A | DONE | 12 | M |  | UWSP ALBERTSON 6230016 |  | 2024-11-26 | Z | 2024-10-16 | 200 | 30 | 70 | F | 40 | 380 |  |  |  | 41
2024-11-20 | 1369 |  | RA-04-09 | A | DONE | 23 | M-L |  | UWSP ALBERTSON 6230016 | CD | 2024-11-26 | Z | 2024-11-11 | 570 | 0 | 0 |  | 0 | 1590 |  |  |  | 15
2024-11-20 | 1370 |  | RA-04-10 | A | DONE | 23 | M-L |  | UWSP ALBERTSON 6230016 | CD | 2024-11-26 | Z | 2024-11-11 | 560 | 0 | 0 |  | 0 | 1730 |  |  |  | 15
2024-11-20 | 1352r |  | EA-04-06 | A | DONE | 4 | S | alum | UWSP ALBERTSON 6230016 |  | 2024-11-26 | Z | 2024-11-13 | 80 | 0 | 20 | F | 0 | 80 |  |  |  | 13
2024-11-21 | 2612 | w | 58811 | A | DONE | 2 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-26 | Z | 2024-11-11 | 40 | 0 | 0 |  | 40 | 120 |  | DSS curb cap |  | 15
2024-11-22 | 2632 |  | 70125 - 70126 | A | DONE | 31 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-11-26 | Z | 2024-11-13 | 760 | 0 | 0 |  | 750 | 1150 |  | L1W-TA |  | 13
2024-11-20 | 1078 |  | 79858 - 79859 | A | DONE | 4 | S |  | WAUNAKEE MS 6230013 |  | 2024-11-26 | Z | 2024-11-15 | 90 | 0 | 0 |  | 0 | 160 |  | Grille sleeves |  | 11
2024-11-20 | 1079 | sp | 79860 | A | DONE | 8 | S |  | WAUNAKEE MS 6230013 |  | 2024-11-26 | Z | 2024-11-19 | 190 | 0 | 0 |  | 0 | 220 |  | Temp heat |  | 7
2024-11-19 | 891 |  | 82520 | A | DONE | 4 | S-M |  | WINDSOR 6240012 |  | 2024-11-25 | Z | 2024-10-30 | 70 | 0 | 30 | F | 0 | 110 |  | Rm. 129 |  | 26
2024-11-19 | 892 |  | 82521 | A | DONE | 2 | S |  | WINDSOR 6240012 | flex | 2024-11-25 | Z | 2024-10-30 | 20 | 0 | 30 | F | 0 | 50 |  | Rm. 106 |  | 26
2024-11-19 | 893 | sp | 82522 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2024-11-25 | Z | 2024-10-30 | 20 | 0 | 0 |  | 0 | 20 |  | Rm. 106 |  | 26
2024-11-21 | 1252 | sp | 82534 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2024-12-16 | Z | 2024-10-31 | 0 | 40 | 0 |  | 0 | 50 |  | FCU-202 SA |  | 46 | 2024-12-09
2024-11-21 | 1886 | sp | 80843 - 80846 | A | DONE | 93 | L | neal | WSCC 6240006 |  | 2024-12-02 | Z | 2024-07-29 | 0 | 2310 | 0 |  | 0 | 2670 |  | RTU-3,5,7,13 |  | 126 |  |  |  |  | 2024-10-28
2024-11-20 | 1957 |  | 80991 | A | DONE | 6 | S |  | WSCC 6240006 | spiral mate | 2024-11-26 | Z | 2024-11-13 | 90 | 40 | 0 |  | 20 | 180 |  | DHU-2 |  | 13
[6 empty] | 664 | [13 empty] | 22440 |  |  |  | 5840 | 26.02%
WEEK OF 11/25/2024
2024-11-27 | 1204 |  | 81934 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-12-02 | Z | 2024-11-26 | 0 | 0 | 50 | F | 0 | 50 |  | Stairwell B |  | 6
2024-11-27 | 3915f | sp | 81902 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-03 | Z | 2024-08-12 | 20 | 90 | 0 |  | 0 | 90 |  | 10th Fl. OA |  | 113
2024-11-26 | 776 |  | 80240 | A | DONE | 2 | S |  | BMH AHU-9 6240001 | VD | 2024-11-27 | Z | 2024-11-18 | 20 | 0 | 20 | F | 0 | 30 |  | Tunnel SA |  | 9
2024-11-27 | 777 | w | 80241 | A | DONE | 2 | S |  | BMH AHU-9 6240001 |  | 2024-12-12 | Z | 2024-11-20 | 20 | 0 | 0 |  | 0 | 30 |  | Curb Cap |  | 22 | 2024-12-05
2024-11-27 | 2066 |  | 69528 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-12-04 | Z | 2024-11-20 | 50 | 0 | 0 |  | 0 | 110 |  | PH Flashing |  | 14
2024-11-26 | 2068 | w | 61389 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-02 | Z | 2024-11-21 | 20 | 0 | 0 |  | 0 | 20 |  | Floor sleeve |  | 11
2024-11-26 | 2069 |  | 69529 | A | DONE | 11 | S |  | CDIS 6220028 |  | 2024-12-02 | Z | 2024-11-21 | 260 | 0 | 0 |  | 0 | 440 |  | PH Flashing |  | 11
2024-11-26 | 2070 |  | 61335 | A | DONE | 2 | S | neal | CDIS 6220028 | paint | 2024-12-02 | Z | 2024-11-25 | 20 | 0 | 0 |  | 20 | 20 |  | 4th floor 4600P |  | 7
2024-11-27 | 2071 |  | 69530 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-04 | Z | 2024-11-27 | 50 | 0 | 0 |  | 0 | 100 |  | PH |  | 7
2024-11-26 | 1116 |  | 79122 | A | DONE | 7 | S-M |  | EXACT BIOSAFE 6230005 |  | 2024-12-02 | Z | 2024-11-18 | 170 | 0 | 0 |  | 0 | 430 |  | DOAS |  | 14
2024-11-26 | 1117 |  | 79123 | A | DONE | 2 | S |  | EXACT BIOSAFE 6230005 |  | 2024-12-02 | Z | 2024-11-19 | 20 | 0 | 0 |  | 0 | 30 |  | DOAS |  | 13
2024-11-26 | 1119 |  | 56692 | A | DONE | 3 | S |  | EXACT BIOSAFE 6230005 |  | 2024-11-27 | Z | 2024-11-21 | 60 | 0 | 0 |  | 0 | 90 |  | Stuff |  | 6
2024-11-27 | 2550 | bth | 56583 - 56587 | A | DONE | 13 | M |  | LABCORP 6240016 |  | 2024-12-03 | Z | 2024-11-20 | 310 | 0 | 0 |  | 0 | 740 |  | Roof Duct |  | 13
2024-11-27 | 2918 |  | 56582 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2024-12-03 | Z | 2024-11-19 | 30 | 0 | 0 |  | 0 | 30 |  | SI2I |  | 14
2024-11-27 | 2919 |  | 82556 | A | DONE | 2 | S | ss | LABCORP 6240016 |  | 2024-12-03 | Z | 2024-11-25 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor misc |  | 8
2024-11-26 | 130 |  | 69519 | A | DONE | 7 | S |  | MSN 2240069 | flex | 2024-12-02 | Z | 2024-11-18 | 60 | 0 | 110 | F | 0 | 270 |  | DR-6 Row 3 |  | 14
2024-11-26 | 3961 |  | 81046 | A | DONE | 2 | S |  | PECATONICA 6240005 | 2" liner | 2024-12-02 | Z | 2024-11-21 | 20 | 0 | 0 |  | 20 | 40 |  | Gym office SA |  | 11
2024-11-26 | 3962 |  | 79681 | A | DONE | 3 | S |  | PECATONICA 6240005 | 2" liner | 2024-12-02 | Z | 2024-11-25 | 20 | 0 | 40 | F | 0 | 60 |  | Gym SA |  | 7
2024-11-26 | 4293 |  | 79967 - 79968 | A | DONE | 13 | S-M |  | ST.BERNARD 6230023 | 3/4" nipple | 2024-12-02 | Z | 2024-11-15 | 310 | 0 | 0 |  | 0 | 590 |  | AHU-1,2 OA |  | 17
2024-11-26 | 4294 |  | 79970 | A | DONE | 4 | S-M |  | ST.BERNARD 6230023 | CD | 2024-12-02 | Z | 2024-11-20 | 100 | 0 | 0 |  | 0 | 190 |  | RF-4 |  | 12
2024-11-25 | 1193 |  | 83013 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-11-25 | Z | 2024-11-25 | 20 | 0 | 0 |  | 0 | 20 |  | Reducers |  | 0
2024-11-26 | 3893 |  | 82129 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | flex | 2024-12-02 | Z | 2024-11-21 | 20 | 0 | 0 |  | 0 | 20 |  | 1st floor TA |  | 11
2024-11-27 | 686 |  | 70475 | A | DONE | 2 | S | mix | UWRF 6230010 | angle rings | 2024-12-02 | Z | 2024-11-19 | 30 | 0 | 0 |  | 0 | 50 |  | Misc |  | 13
2024-11-26 | 687 |  | 70476 | A | DONE | 2 | S-M |  | UWRF 6230010 |  | 2024-12-02 | Z | 2024-11-20 | 40 | 0 | 0 |  | 0 | 110 |  | 2nd FSD tie in |  | 12
2024-11-27 | 1353 | bth | LPSA-02-16 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-12-03 | Z | 2024-10-29 | 180 | 0 | 120 | F | 30 | 420 |  |  |  | 35
2024-11-27 | 1380 |  | 81128 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-12-03 | Z | 2024-11-18 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 15
2024-11-25 | 1381 | sp | 81129 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-12-03 | Z | 2024-11-18 | 0 | 50 | 0 |  | 0 | 40 |  | Misc |  | 15
2024-11-27 | 1382 |  | 81130 | A | DONE | 6 | S |  | UWSP ALBERTSON 6230016 |  | 2024-12-03 | Z | 2024-11-21 | 130 | 0 | 0 |  | 0 | 170 |  | LPSA-01-14 |  | 12
2024-11-27 | 1383 |  | 81131 | A | DONE | 6 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-12-03 | Z | 2024-11-21 | 140 | 0 | 0 |  | 0 | 490 |  | AHU-1A |  | 12
2024-11-25 | 2614 | bth | L1W_SAMP 1 | A | DONE | 10 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 210 | 30 | 0 |  | 0 | 440 |  |  |  | 15
2024-11-25 | 2615 | bth | L1W_SAMP 2 | A | DONE | 7 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 150 | 20 | 0 |  | 0 | 420 |  |  |  | 15
2024-11-25 | 2616 | bth | L1W_SAMP 3 | A | DONE | 13 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 40 | 30 | 240 | F | 0 | 520 |  |  |  | 15
2024-11-25 | 2617 | bth | L1W_SAMP 4 | A | DONE | 16 | M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 20 | 20 | 360 | F | 0 | 650 |  |  |  | 15
2024-11-25 | 2618 | bth | L1W_SAMP 5 | A | DONE | 16 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 280 | 20 | 90 | F | 0 | 700 |  |  |  | 15
2024-11-25 | 2619 | bth | L1W_SAMP 6 | A | DONE | 13 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 100 | 20 | 190 | F | 0 | 630 |  |  |  | 15
2024-11-25 | 2620 | bth | L1W_SAMP 7 | A | DONE | 15 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 90 | 20 | 250 | F | 0 | 610 |  |  |  | 15
2024-11-25 | 2621 | bth | L1W_SAMP 8 | A | DONE | 13 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 110 | 30 | 170 | F | 0 | 420 |  |  |  | 15
2024-11-25 | 2622 | bth | L1W_SAMP 9 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 70 | 50 | 0 |  | 0 | 200 |  |  |  | 15
2024-11-25 | 2623 | bth | L1W_SAMP 10 | A | DONE | 9 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 110 | 20 | 90 | F | 0 | 320 |  |  |  | 15
2024-11-25 | 2624 | bth | L1W_SAMP 11 | A | DONE | 11 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 110 | 20 | 130 | F | 0 | 310 |  |  |  | 15
2024-11-25 | 2625 | bth | L1W_SAMP 12 | A | DONE | 8 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 60 | 20 | 110 | F | 0 | 230 |  |  |  | 15
2024-11-25 | 2626 | bth | L1W_SAMP 13 | A | DONE | 8 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 80 | 50 | 60 | F | 0 | 210 |  |  |  | 15
2024-11-25 | 2627 | bth | L1W_SAMP 14 | A | DONE | 10 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 70 | 40 | 120 | F | 0 | 310 |  |  |  | 15
2024-11-25 | 2628 | bth | L1W_SAMP 15 | A | DONE | 10 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 130 | 60 | 40 | F | 0 | 280 |  |  |  | 15
2024-11-25 | 2629 | bth | L1W_SAMP 16 | A | DONE | 13 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 100 | 50 | 160 | F | 0 | 370 |  |  |  | 15
2024-11-25 | 2630 | bth | L1W_SAMP 17 | A | DONE | 12 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-11-26 | Z | 2024-11-11 | 70 | 60 | 150 | F | 0 | 330 |  |  |  | 15
2024-11-26 | 2704 |  | 58813 | A | DONE | 3 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-03 | Z | 2024-11-26 | 70 | 0 | 0 |  | 0 | 130 |  | Misc |  | 7
2024-11-27 | 2005 |  | 73096 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-12-05 | Z | 2024-11-21 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd floor |  | 14
2024-11-25 | 135 |  | 112524 | A | DONE | 2 | S |  | VAN 331 LADDER RACK 20009121 | neoprene gasket | 2024-11-27 | Z | 2024-11-25 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 2
2024-11-26 | 1253 |  | 82523 - 82524 | A | DONE | 10 | S-M |  | WINDSOR 6240012 | 1/2" liner | 2024-12-02 | Z | 2024-11-13 | 230 | 0 | 0 |  | 180 | 330 |  | Vest. 103 / FCU 102A |  | 19
2024-11-26 | 1254 |  | 82535 - 82537 | A | DONE | 6 | S |  | WINDSOR 6240012 |  | 2024-12-02 | Z | 2024-11-13 | 140 | 0 | 0 |  | 0 | 160 |  | Mech 111 |  | 19
2024-11-26 | 1255 |  | 82538 | A | DONE | 4 | S-M |  | WINDSOR 6240012 | flex , bird s. , 1" liner | 2024-12-02 | Z | 2024-11-19 | 90 | 0 | 0 |  | 80 | 160 |  | FCU-131 |  | 13
2024-11-26 | 1256 |  | 82539 | A | DONE | 2 | S |  | WINDSOR 6240012 | flex | 2024-12-02 | Z | 2024-11-19 | 20 | 0 | 0 |  | 0 | 20 |  | FCU-131 |  | 13
2024-11-25 | 1885 | sp | 80840 - 80842 | A | DONE | 109 | L | neal | WSCC 6240006 | 1" liner/ Sp , s.mates | 2024-12-02 | Z | 2024-07-29 | 400 | 2310 | 0 |  | 500 | 3820 |  | RTU-3,5,7,13 |  | 126 |  |  |  |  | 2024-10-28
2024-11-26 | 1887 | bth | 80847 - 80849 | A | DONE | 99 | M | neal | WSCC 6240006 | 1" liner/ Sp , s.mates | 2024-12-02 | Z | 2024-07-29 | 870 | 480 | 100 | F | 1010 | 2440 |  | RTU-3,5,7,13 |  | 126 |  |  |  |  | 2024-10-28
2024-11-26 | 1924 |  | 71458 | A | DONE | 6 | S-M | neal | WSCC 6240006 | 1" liner | 2024-12-02 | Z | 2024-10-29 | 150 | 0 | 0 |  | 140 | 250 |  | RTU-5,7 |  | 34
2024-11-26 | 1952 |  | 71462 | A | DONE | 10 | M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-02 | Z | 2024-11-07 | 140 | 100 | 0 |  | 160 | 520 |  | RTU-3 RA |  | 25
2024-11-26 | 1954 |  | Pre-Fab Hangers | A | DONE | 7 | S | neal | WSCC 6240006 |  | 2024-12-02 | Z | 2024-11-07 | 160 | 0 | 0 |  | 0 | 420 |  | Hangers |  | 25
2024-11-26 | 1958 | sp | 71465 | A | DONE | 2 | S |  | WSCC 6240006 |  | 2024-12-02 | Z | 2024-11-20 | 20 | 0 | 0 |  | 0 | 60 |  | Cone Flashing |  | 12
2024-11-27 | 1959 | bth | 62071 | A | DONE | 13 | S-M | neal | WSCC 6240006 | 1" sprial , 1" liner | 2024-12-02 | Z | 2024-11-20 | 240 | 70 | 0 |  | 230 | 460 |  | RTU-4,6 outs |  | 12
2024-11-25 | 1960 |  | 71466 | A | DONE | 2 | S | ss | WSCC 6240006 |  | 2024-12-02 | Z | 2024-11-21 | 20 | 0 | 0 |  | 0 | 20 |  | IR heaters |  | 11
2024-11-26 | 1961 |  | 71468 | A | DONE | 3 | S | neal | WSCC 6240006 |  | 2024-12-02 | Z | 2024-11-21 | 60 | 0 | 0 |  | 0 | 80 |  | RTU-2 SA |  | 11
[6 empty] | 593 | [13 empty] | 20580 |  |  |  | 3150 | 15.31%
WEEK OF 12/2/2024
2024-12-03 | 2246 |  | 80079 | A | DONE | 9 | S-M |  | 121 E. WILSON 6230024 | paint | 2024-12-04 | Z | 2024-07-25 | 50 | 0 | 170 | F | 20 | 200 |  | DOAS-2 / OA-4 |  | 132
2024-12-03 | 3660 |  | 80100 , 80106 | A | DONE | 17 | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-04 | Z | 2024-07-30 | 90 | 0 | 320 | F | 0 | 420 |  | EF-3,4 , EA-5 |  | 127
2024-12-05 | 3903f |  | 80139 | A | DONE | n/a | M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-12-12 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 10th Fl. West unit plenums | Design Air | 122
2024-12-05 | 3904f |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-12 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 10th Fl. West unit Taps | Design Air | 122
2024-12-05 | 3905f |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-12 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 10th Fl. West unit sliders | Design Air | 122
2024-12-05 | 3906f |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-12-12 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 10th Fl. West Corr. HP's | Design Air | 122
2024-12-05 | 3909e |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-12-06 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. East unit plenums | Design Air | 116
2024-12-05 | 3910e |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-06 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. East Taps | Design Air | 116
2024-12-05 | 3911e |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-06 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. East sliders | Design Air | 116
2024-12-05 | 3912e |  | 80149 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-12-06 | Z | 2024-08-12 | 30 | 0 | 0 |  | 0 | 40 |  | 9th Fl. East unit SA | Design Air | 116
2024-12-05 | 3913e |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-12-06 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 9th Fl. East Corr. HP's | Design Air | 116
2024-12-02 | 3916f |  | 81903 - 81904 | A | DONE | 34 | M |  | 121 E. WILSON 6230024 |  | 2024-12-04 | Z | 2024-08-12 | 830 | 0 | 0 |  | 0 | 890 |  | 10th Fl. East EA |  | 114
2024-12-02 | 2250 |  | 84351 | A | DONE | 2 | S |  | BARTILLION 6240024 |  | 2024-12-03 | Z | 2024-11-27 | 40 | 0 | 0 |  | 0 | 70 |  | Sleeves |  | 6
2024-12-04 | 779 | sp | 80245 | A | DONE | 5 | S-M |  | BMH AHU-9 6240001 |  | 2024-12-12 | Z | 2024-11-20 | 30 | 80 | 0 |  | 0 | 130 |  | CS SAHP |  | 22 | 2024-12-05
2024-12-03 | 2061 |  | 69523 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-04 | Z | 2024-11-14 | 50 | 0 | 0 |  | 0 | 100 |  | Misc OA |  | 20
2024-12-03 | 2064 |  | 69526 | A | DONE | 3 | S-M |  | CDIS 6220028 |  | 2024-12-04 | Z | 2024-11-19 | 70 | 0 | 0 |  | 30 | 140 |  | EA PH |  | 15
2024-12-04 | 2072 |  | 81524 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-10 | Z | 2024-12-02 | 20 | 0 | 0 |  | 0 | 20 |  | Vent / drain covers |  | 8
2024-12-06 | 2073 |  | 81605 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-10 | Z | 2024-12-03 | 30 | 0 | 0 |  | 0 | 50 |  | 6530 |  | 7
2024-12-04 | 811 |  | Pre-Fab Hangers | A | DONE | 2 | S |  | DELLSHIRE 6240017 |  | 2024-12-06 | Z | 2024-11-26 | 30 | 0 | 0 |  | 0 | 70 |  | Hangers |  | 10
2024-12-05 | 1120 |  | 83251 | A | DONE | 3 | S-M |  | EXACT 650 2240053 |  | 2024-12-09 | Z | 2024-12-03 | 60 | 0 | 0 |  | 0 | 110 |  | Line set tray |  | 6
2024-12-05 | 142 |  | 83191 | A | DONE | 2 | S | ss | GIALAMIS BOILER 4240057 |  | 2024-12-06 | Z | 2024-12-05 | 20 | 0 | 0 |  | 0 | 20 |  | Vent adpt. |  | 1
2024-12-05 | 143 |  | 70233 | A | DONE | 2 | S |  | HEARTLAND 10058403 |  | 2024-12-06 | Z | 2024-12-05 | 20 | 0 | 0 |  | 0 | 20 |  | Furnace |  | 1
2024-12-03 | 137 |  | 79430 | A | DONE | 2 | S |  | HEARTLAND C.U. 10058405 |  | 2024-12-06 | Z | 2024-11-27 | 20 | 0 | 0 |  | 0 | 20 |  | F-3 |  | 9
2024-12-05 | 2920 |  | 56588 - 56590 | A | DONE | 84 | L |  | LABCORP 6240016 |  | 2024-12-09 | Z | 2024-11-25 | 680 | 0 | 1420 | F | 0 | 4590 |  | Roof duct |  | 14
2024-12-05 | 2921 |  | 56591 - 56593 | A | DONE | 34 | M |  | LABCORP 6240016 |  | 2024-12-09 | Z | 2024-11-25 | 560 | 0 | 270 | F | 0 | 1430 |  | Roof duct |  | 14
2024-12-05 | 2922 |  | 56594 - 56596 | A | DONE | 50 | M |  | LABCORP 6240016 |  | 2024-12-09 | Z | 2024-11-25 | 430 | 0 | 810 | F | 0 | 2530 |  | Roof duct |  | 14
2024-12-06 | 2923 |  | 56597 - 56598 | A | DONE | 30 | M |  | LABCORP 6240016 |  | 2024-12-09 | Z | 2024-11-25 | 240 | 0 | 510 | F | 0 | 1070 |  | Roof duct |  | 14
2024-12-06 | 2924 |  | 82553 - 82555 | A | DONE | 32 | M |  | LABCORP 6240016 |  | 2024-12-09 | Z | 2024-11-25 | 570 | 0 | 210 | F | 0 | 1390 |  | Roof duct |  | 14
2024-12-06 | 2925 |  | 82557 | A | DONE | 16 | M | pt.ss | LABCORP 6240016 |  | 2024-12-09 | Z | 2024-11-25 | 380 | 0 | 0 |  | 0 | 830 |  | PH |  | 14
2024-12-02 | 138 |  | 84255 | A | DONE | 2 | S |  | MENDOTA FOODS 6220027 | bird s. | 2024-12-02 | Z | 2024-12-02 | 20 | 0 | 0 |  | 0 | 20 |  | Birdscreens |  | 0
2024-12-05 | 136 | bth | 84301 - 84303 | A | DONE | 8 | S-M |  | OCTOPI 10058801 | bird s.,flex,1-1/2" FB | 2024-12-06 | Z | 2024-11-26 | 120 | 80 | 0 |  | 20 | 270 |  | Misc |  | 10
2024-12-06 | 141 | w | 84306 | A | DONE | 2 | S-M |  | OCTOPI 4240056 | 2" liner | 2024-12-10 | Z | 2024-12-03 | 40 | 0 | 0 |  | 20 | 120 |  | Roof rails |  | 7
2024-12-03 | 3962 |  | 79681 | A | DONE | 3 | S |  | PECATONICA 6240005 | 2" liner | 2024-12-04 | Z | 2024-12-02 | 20 | 0 | 40 | F | 50 | 60 |  | Misc |  | 2
2024-12-02 | 2519 | sp | 59820 | A | DONE | 2 | S-M |  | PROMEGA BTC 6230022 |  | 2024-12-04 | Z | 2024-11-25 | 20 | 30 | 0 |  | 0 | 50 |  | VAV-Warehouse |  | 9
2024-12-03 | 2520 |  | 81857 | A | DONE | 6 | S-M |  | PROMEGA BTC 6230022 |  | 2024-12-04 | Z | 2024-11-25 | 30 | 0 | 100 | F | 0 | 270 |  | SAMP-04 |  | 9
2024-12-06 | 2521 |  | 59824 | A | DONE | 2 | S |  | PROMEGA BTC 6230022 |  | 2024-12-11 | Z | 2024-12-05 | 20 | 0 | 0 |  | 0 | 20 |  | Hangers |  | 6
2024-12-02 | 2391 |  | 59821 | A | DONE | 2 | S | ss | PROMEGA FEYNMAN 6220014 | bird s. | 2024-12-04 | Z | 2024-11-25 | 20 | 0 | 0 |  | 0 | 20 |  | EA |  | 9
2024-12-03 | 4778 |  | 61187 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-12-04 | Z | 2024-11-25 | 20 | 0 | 0 |  | 0 | 20 |  | RA Main |  | 9
2024-12-03 | 4779 |  | 61188 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-12-04 | Z | 2024-11-26 | 40 | 0 | 0 |  | 0 | 60 |  | Kitchen |  | 8
2024-12-02 | 134 |  | 80763 | A | DONE | 2 | S |  | SSM O'KEEFE 8240002 |  | 2024-12-06 | Z | 2024-11-25 | 30 | 0 | 0 |  | 0 | 90 |  | Nail plates |  | 11
2024-12-02 | 384 | bth | L02_B_SALP_001 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 48
2024-12-03 | 385 | bth | L02_B_SALP_002 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 60 | 30 | 0 |  | 0 | 80 |  |  |  | 48
2024-12-03 | 386 | bth | L02_B_SALP_003 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 50 | 30 | 0 |  | 0 | 90 |  |  |  | 48
2024-12-03 | 387 | bth | L02_B_SALP_004 | A | DONE | 10 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 130 | 100 | 0 |  | 0 | 250 |  |  |  | 48
2024-12-03 | 388 | sp | L02_B_SALP_005 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 30 | 80 | 0 |  | 0 | 100 |  |  |  | 48
2024-12-03 | 389 | bth | L02_B_SALP_006 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 48
2024-12-04 | 390 | bth | L02_B_SALP_007 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 20 | 30 | 0 |  | 0 | 50 |  |  |  | 48
2024-12-03 | 391 | bth | L02_B_SALP_008 | A | DONE | 11 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 40 | 220 | 0 |  | 0 | 300 |  |  |  | 48
2024-12-03 | 392 | bth | L02_B_SALP_009 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 50 | 30 | 0 |  | 0 | 80 |  |  |  | 48
2024-12-03 | 393 | bth | L02_B_SALP_010 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 48
2024-12-03 | 394 |  | L02_B_SALP_011 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 20 | 50 | 0 |  | 0 | 80 |  |  |  | 48
2024-12-03 | 395 | bth | L02_B_SALP_012 | A | DONE | 9 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 50 | 170 | 0 |  | 0 | 220 |  |  |  | 48
2024-12-04 | 396 | bth | L02_B_SALP_013 | A | DONE | 10 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 60 | 190 | 0 |  | 0 | 310 |  |  |  | 48
2024-12-04 | 397 | sp | L02_B_SALP_014 | A | DONE | 13 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 70 | 240 | 0 |  | 0 | 290 |  |  |  | 48
2024-12-04 | 398 |  | L02_B_SALP_017 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-10-18 | 20 | 0 | 0 |  | 0 | 20 |  |  |  | 48
2024-12-03 | 399 |  | L02_B_TAD_001 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 50 | 0 | 0 |  | 40 | 70 |  |  |  | 48
2024-12-04 | 400 |  | L02_B_TAD_002 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 120 | 0 | 0 |  | 100 | 150 |  |  |  | 48
2024-12-04 | 401 |  | L02_B_TAD_003 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 48
2024-12-04 | 402 |  | L02_B_TAD_004 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 48
2024-12-03 | 403 |  | L02_B_TAD_005 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 50 | 0 | 0 |  | 40 | 80 |  |  |  | 48
2024-12-04 | 404 |  | L02_B_TAD_006 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 70 | 0 | 0 |  | 50 | 90 |  |  |  | 48
2024-12-04 | 405 |  | L02_B_TAD_007 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 70 | 0 | 0 |  | 60 | 90 |  |  |  | 48
2024-12-04 | 406 |  | L02_B_TAD_008 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 90 | 0 | 0 |  | 80 | 110 |  |  |  | 48
2024-12-04 | 407 |  | L02_B_TAD_009 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 60 | 0 | 0 |  | 50 | 80 |  |  |  | 48
2024-12-04 | 408 |  | L02_B_TAD_010 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 70 | 0 | 0 |  | 60 | 90 |  |  |  | 48
2024-12-04 | 409 |  | L02_B_TAD_011 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 70 | 0 | 0 |  | 60 | 90 |  |  |  | 48
2024-12-04 | 410 |  | L02_B_TAD_012 | A | DONE | 4 | S | neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 80 | 0 | 0 |  | 70 | 120 |  |  |  | 48
2024-12-04 | 411 |  | L02_B_TAD_013 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 80 | 0 | 0 |  | 60 | 110 |  |  |  | 48
2024-12-04 | 412 |  | L02_B_TAD_014 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-10-18 | 20 | 0 | 0 |  | 20 | 30 |  |  |  | 48
2024-12-03 | 1194 |  | 83014 | A | DONE | 2 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-11-26 | 40 | 0 | 0 |  | 30 | 120 |  | RA-2B |  | 9
2024-12-03 | 1195 |  | 93015 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-11-26 | 20 | 0 | 0 |  | 0 | 30 |  | SA |  | 9
2024-12-04 | 1196 |  | 83016 - 83017 | A | DONE | 6 | S-M | pt.neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-05 | Z | 2024-12-02 | 130 | 0 | 0 |  | 70 | 210 |  | Misc |  | 3
2024-12-03 | 364r | bth | L02_B_SAMP_011 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-05 | Z | 2024-11-26 | 80 | 0 | 0 |  | 0 | 100 |  | Size Change |  | 9
2024-12-02 | 139 |  | 83188 | A | DONE | 2 | S |  | THERMO FISHER 4240032 |  | 2024-12-02 | Z | 2024-12-02 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-12-03 | 140 |  | 83189 | A | DONE | 2 | S | ss | THERMO FISHER 4240032 |  | 2024-12-03 | Z | 2024-12-03 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 0
2024-12-03 | 4568 |  | 12325 | A | DONE | 2 | S | BI | UW-LEVY HALL 8230028 |  | 2024-12-10 | Z | 2024-12-03 | 20 | 0 | 0 |  | 0 | 20 |  | Caps |  | 7
2024-12-05 | 3894 |  | 82130 - 82131 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | flex | 2024-12-09 | Z | 2024-11-27 | 20 | 0 | 0 |  | 0 | 20 |  | BR EA |  | 12
2024-12-04 | 688 | w | 70477 , 70479 | A | DONE | 2 | M | BI | UWRF 6230010 | angle rings | 2024-12-09 | Z | 2024-11-21 | 50 | 0 | 0 |  | 0 | 330 |  | Dust Collector Inlet |  | 18
2024-12-02 | 689 |  | 83512 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-12-03 | Z | 2024-12-02 | 20 | 0 | 0 |  | 0 | 80 |  | Hangers |  | 1
2024-12-02 | 1354 | bth | LPSA-02-15 | A | DONE | 14 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-12-03 | Z | 2024-10-29 | 150 | 0 | 180 | F | 70 | 400 |  |  |  | 35
2024-12-02 | 1355 | bth | LPSA-02-14 | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-12-03 | Z | 2024-10-29 | 150 | 30 | 100 | F | 40 | 360 |  |  |  | 35
2024-12-02 | 1356 | bth | LPSA-02-13B | A | DONE | 13 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-12-03 | Z | 2024-10-29 | 70 | 90 | 150 | F | 0 | 340 |  |  |  | 35
2024-12-02 | 1357 | bth | LPSA-02-13A | A | DONE | 12 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-12-03 | Z | 2024-10-29 | 90 | 120 | 90 | F | 30 | 350 |  |  |  | 35
2024-12-02 | 1358 |  | LPSA-02-12 | A | DONE | 26 | M |  | UWSP ALBERTSON 6230016 | VD , 1" liner | 2024-12-03 | Z | 2024-10-29 | 240 | 0 | 400 | F | 40 | 850 |  |  |  | 35
2024-12-02 | 1359 | bth | LPSA-02-11 | A | DONE | 19 | S-M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-12-03 | Z | 2024-10-29 | 330 | 20 | 120 | F | 100 | 540 |  |  |  | 35
2024-12-02 | 1360 | bth | LPSA-02-10 | A | DONE | 19 | M |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-12-03 | Z | 2024-10-29 | 150 | 20 | 300 | F | 30 | 600 |  |  |  | 35
2024-12-02 | 1363 |  | SA-04-04 | A | DONE | 6 | M |  | UWSP ALBERTSON 6230016 | CD | 2024-12-03 | Z | 2024-11-04 | 130 | 0 | 0 |  | 0 | 520 |  |  |  | 29
2024-12-02 | 1364 |  | SA-04-03 | A | DONE | 29 | L |  | UWSP ALBERTSON 6230016 |  | 2024-12-03 | Z | 2024-11-04 | 720 | 0 | 0 |  | 0 | 2080 |  |  |  | 29
2024-12-04 | 2633 | bth | L1W_EA 1 | A | DONE | 7 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 40 | 120 | 0 |  | 0 | 160 |  |  |  | 16
2024-12-04 | 2634 | bth | L1W_EA 2 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 60 | 60 | 20 | F | 0 | 150 |  |  |  | 16
2024-12-04 | 2635 |  | L1W_EA 3 | A | DONE | 7 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 60 | 0 | 100 | F | 0 | 200 |  |  |  | 16
2024-12-04 | 2636 |  | L1W_EA 4 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 90 | 0 | 0 |  | 0 | 120 |  |  |  | 16
2024-12-04 | 2637 | bth | L1W_EA 5 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 40 | 20 | 30 | F | 0 | 100 |  |  |  | 16
2024-12-04 | 2638 | bth | L1W_EA 6 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 60 | 20 | 0 |  | 0 | 80 |  |  |  | 16
2024-12-04 | 2639 | bth | L1W_EA 7 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 90 | 60 | 30 | F | 0 | 190 |  |  |  | 16
2024-12-04 | 2640 | sp | L1W_EA 8 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 40 | 110 | 0 |  | 0 | 150 |  |  |  | 16
2024-12-04 | 2641 | sp | L1W_EA 9 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 40 | 90 | 0 |  | 0 | 140 |  |  |  | 16
2024-12-04 | 2642 | sp | L1W_EA 10 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 20 | 80 | 0 |  | 0 | 120 |  |  |  | 16
2024-12-04 | 2643 | sp | L1W_EA 11 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 20 | 90 | 0 |  | 0 | 100 |  |  |  | 16
2024-12-04 | 2644 | sp | L1W_EA 12 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 20 | 70 | 0 |  | 0 | 90 |  |  |  | 16
2024-12-04 | 2645 | sp | L1W_EA 13 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 20 | 110 | 0 |  | 0 | 110 |  |  |  | 16
2024-12-04 | 2646 | sp | L1W_EA 14 | A | DONE | 3 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 16
2024-12-04 | 2647 | sp | L1W_EA 15 | A | DONE | 3 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 16
2024-12-04 | 2648 |  | L1W_RA 1 | A | DONE | 9 | S |  | UWSP CHAMPION HALL 6240008 | VD | 2024-12-05 | Z | 2024-11-19 | 160 | 0 | 50 | F | 0 | 260 |  |  |  | 16
2024-12-04 | 2649 |  | L1W_RA 2 | A | DONE | 10 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 190 | 0 | 40 | F | 0 | 310 |  |  |  | 16
2024-12-04 | 2700 |  | L1W_RA 3 | A | DONE | 8 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-11-19 | 180 | 0 | 0 |  | 0 | 250 |  |  |  | 16
2024-12-04 | 2702 |  | 70127 - 70128 | A | DONE | 13 | S-M |  | UWSP CHAMPION HALL 6240008 | flex , 1" liner | 2024-12-05 | Z | 2024-11-21 | 320 | 0 | 0 |  | 310 | 480 |  | L1W-TA |  | 14
2024-12-02 | 2703 | sp | 70129 | A | DONE | 9 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-03 | Z | 2024-11-21 | 60 | 150 | 0 |  | 0 | 240 |  | Misc |  | 12
2024-12-02 | 2705 |  | 70130 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-03 | Z | 2024-11-26 | 20 | 0 | 0 |  | 0 | 20 |  | L2-SALP-11 |  | 7
2024-12-04 | 2706 | sp | 70131 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-05 | Z | 2024-12-03 | 20 | 30 | 0 |  | 0 | 50 |  | Misc |  | 2
2024-12-03 | 2004 | w | 73093 , 73095 | A | DONE | 2 | S-M | ss | UW-VET MED 6210014 |  | 2024-12-05 | Z | 2024-11-21 | 20 | 0 | 0 |  | 0 | 70 |  | 3rd floor |  | 14
2024-12-04 | 2188 |  | 67589 | A | DONE | 2 | S |  | WAUNAKEE MS 6230013 |  | 2024-12-06 | Z | 2024-11-27 | 30 | 0 | 0 |  | 0 | 50 |  | Temp curb caps |  | 9
2024-12-03 | 1925 |  | 80987 | A | DONE | 2 | S-M | neal | WSCC 6240006 | VD , flex | 2024-12-05 | Z | 2024-10-31 | 40 | 0 | 0 |  | 0 | 60 |  | Fan-09 |  | 35
2024-12-02 | 1926 | sp | 80988 | A | DONE | 3 | S | neal | WSCC 6240006 |  | 2024-12-05 | Z | 2024-10-31 | 0 | 70 | 0 |  | 0 | 80 |  | Fan-09 |  | 35
2024-12-04 | 1962 |  | 71469 | A | DONE | 4 | S-M |  | WSCC 6240006 |  | 2024-12-11 | Z | 2024-11-21 | 80 | 0 | 0 |  | 0 | 140 |  | Flashing |  | 20
2024-12-05 | 1963 | sp | 71470 | A | DONE | 9 | S-M | neal | WSCC 6240006 |  | 2024-12-09 | Z | 2024-11-27 | 20 | 190 | 0 |  | 0 | 260 |  | RTU-2 |  | 12
2024-12-03 | 1964 |  | 71471 | A | DONE | 2 | S | ss | WSCC 6240006 |  | 2024-12-05 | Z | 2024-12-02 | 20 | 0 | 0 |  | 0 | 20 |  | IR heaters |  | 3
2024-12-03 | 1965 |  | 84256 | A | DONE | 12 | S-M |  | WSCC 6240006 |  | 2024-12-03 | Z | 2024-12-03 | 280 | 0 | 0 |  | 0 | 420 |  | Flat stock |  | 0
[6 empty] | 835 | [13 empty] | 29950 |  |  |  | 3060 | 10.22%
WEEK OF 12/9/2024
2024-12-11 | 3907g |  | 80143 - 80144 | A | DONE | 32 | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-12 | Z | 2024-08-12 | 360 | 0 | 420 | F | 0 | 830 |  | 11th Fl. West EA |  | 122
2024-12-11 | 3908a |  | 80145 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-12 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 11th Fl. West EA |  | 122
2024-12-12 | 3912f |  | 80149 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 |  | 2024-12-20 | Z | 2024-08-12 | 30 | 0 | 0 |  | 0 | 40 |  | 10th Fl. East unit SA |  | 130
2024-12-12 | 3914d |  | 81901 | A | DONE | 2 | S |  | 121 E. WILSON 6230024 | 1" liner | 2024-12-18 | Z | 2024-08-12 | 30 | 0 | 0 |  | 20 | 30 |  | 11th Fl. IDF TA |  | 128
2024-12-11 | 3915g | sp | 81902 | A | DONE | 5 | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-18 | Z | 2024-08-12 | 20 | 90 | 0 |  | 0 | 90 |  | 11th Fl. OA |  | 128
2024-12-12 | 3916g |  | 81903 - 81904 | A | DONE | 34 | M |  | 121 E. WILSON 6230024 |  | 2024-12-18 | Z | 2024-08-12 | 340 | 0 | 500 | F | 0 | 870 |  | 11th Fl. East EA |  | 128
2024-12-12 | 3917a |  | 81905 | A | DONE | 2 | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-18 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 11th Fl. East EA |  | 128
2024-12-11 | 144 |  | 58168 | A | DONE | 2 | S | neal | BLACKHAWK BTC 6230025 |  | 2024-12-13 | Z | 2024-12-09 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 4
2024-12-10 | 778 |  | 80242 - 80244 | A | DONE | 38 | M-L |  | BMH AHU-9 6240001 |  | 2024-12-11 | Z | 2024-11-20 | 180 | 0 | 760 | F | 0 | 1250 |  | CS SAHP |  | 21 | 2024-12-05 | 2024-12-12
2024-12-10 | 780 |  | 80246 - 80247 | A | DONE | 26 | M |  | BMH AHU-9 6240001 |  | 2024-12-11 | Z | 2024-11-20 | 40 | 0 | 610 | F | 0 | 800 |  | CS RAHP |  | 21 | 2024-12-05 | 2024-12-12
2024-12-10 | 781 |  | 80248 - 80249 | A | DONE | 21 | S-M |  | BMH AHU-9 6240001 | CD | 2024-12-11 | Z | 2024-11-20 | 150 | 0 | 360 | F | 0 | 600 |  | EF-57 |  | 21 | 2024-12-05 | 2024-12-12
2024-12-09 | 2074 |  | 81606 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-12-10 | Z | 2024-12-03 | 30 | 0 | 0 |  | 30 | 50 |  | 6th - 7th |  | 7
2024-12-09 | 2075 |  | 69700 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-10 | Z | 2024-12-03 | 30 | 0 | 0 |  | 0 | 30 |  | 1st floor |  | 7
2024-12-09 | 2076 |  | 61390 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2024-12-10 | Z | 2024-12-04 | 50 | 0 | 0 |  | 60 | 220 |  | Basement |  | 6
2024-12-11 | 2078 |  | 61337 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2024-12-16 | Z | 2024-12-09 | 20 | 0 | 0 |  | 0 | 20 |  | 4th floor 4675 |  | 7
2024-12-12 | 2079 |  | 61391 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-13 | Z | 2024-12-11 | 20 | 0 | 0 |  | 20 | 20 |  | Basement |  | 2
2024-12-13 | 147 |  | 83192 | F | DONE | 2 | S |  | COTTAGE GROVE 4240033 |  | 2024-12-13 | Z | 2024-12-12 | 20 | 0 | 0 |  | 0 | 20 |  | St Collar / EC's |  | 1
2024-12-09 | 804 |  | 70691 - 70692 | A | DONE | 19 | M | pcd | DELLSHIRE 6240017 | spiral mate | 2024-12-16 | Z | 2024-11-26 | 190 | 0 | 280 | F | 0 | 760 |  | Pool SA |  | 20 | 2024-12-06
2024-12-09 | 805 | sp | 70693 - 70695 | A | DONE | 26 | M | pcd | DELLSHIRE 6240017 | spiral mate | 2024-12-16 | Z | 2024-11-26 | 210 | 430 | 0 |  | 0 | 840 |  | Pool SA |  | 20 | 2024-12-06
2024-12-09 | 806 | sp | 70696 - 70698 | A | DONE | 19 | M | pcd | DELLSHIRE 6240017 | spiral mate | 2024-12-16 | Z | 2024-11-26 | 130 | 330 | 0 |  | 0 | 540 |  | Pool SA |  | 20 | 2024-12-06
2024-12-09 | 807 | sp | 70699 - 70702 | A | DONE | 22 | M | pcd | DELLSHIRE 6240017 | spiral mate | 2024-12-16 | Z | 2024-11-26 | 70 | 460 | 0 |  | 0 | 690 |  | Pool SA |  | 20 | 2024-12-06
2024-12-09 | 808 | bth | 70703 - 70705 | A | DONE | 13 | M | pcd | DELLSHIRE 6240017 | spiral mate | 2024-12-16 | Z | 2024-11-26 | 130 | 0 | 180 | F | 0 | 390 |  | Pool SA |  | 20 | 2024-12-06
2024-12-09 | 809 | sp | 70706 | A | DONE | 4 | M | pcd | DELLSHIRE 6240017 | spiral mate | 2024-12-16 | Z | 2024-11-26 | 20 | 70 | 0 |  | 0 | 100 |  | Pool SA |  | 20 | 2024-12-06
2024-12-10 | 1125 |  | 83252 | A | DONE | 2 | S |  | EXACT 650 2240053 | bird s. | 2024-12-12 | Z | 2024-12-09 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 3
2024-12-09 | r1120 |  | 83251 | A | DONE | 2 | S |  | EXACT 650 2240053 |  | 2024-12-09 | Z | 2024-12-09 | 20 | 0 | 0 |  | 0 | 20 |  | Line set tray |  | 0
2024-12-11 | 1122 |  | 79125 - 79126 | A | DONE | 13 | S-M |  | EXACT B2 QC LAB 2240018 |  | 2024-12-12 | Z | 2024-12-09 | 220 | 0 | 90 |  | 0 | 450 |  | SAT SA |  | 3
2024-12-11 | 1123 | sp | 79127 | A | DONE | 10 | S-M |  | EXACT B2 QC LAB 2240018 |  | 2024-12-12 | Z | 2024-12-09 | 30 | 210 | 0 |  | 0 | 280 |  | HP SA |  | 3
2024-12-11 | 1124 |  | 79128 - 79129 | A | DONE | 11 | S-M |  | EXACT B2 QC LAB 2240018 |  | 2024-12-12 | Z | 2024-12-09 | 130 | 0 | 140 |  | 0 | 360 |  | EA LP |  | 3
2024-12-11 | 1126 |  | 79130 - 79132 | A | DONE | 21 | M |  | EXACT B2 QC LAB 2240018 |  | 2024-12-12 | Z | 2024-12-09 | 340 | 0 | 180 | F | 0 | 690 |  | EAT HP |  | 3
2024-12-12 | 1127 |  | 79133 | A | DONE | 3 | S-M |  | EXACT BIO SAFE 6230005 | spiral mate | 2024-12-17 | Z | 2024-12-09 | 60 | 0 | 0 |  | 0 | 130 |  | DOAS SA |  | 8
2024-12-09 | 1121 |  | 79124 | A | DONE | 2 | S-M |  | EXACT TL-5 6240014 | 1" liner | 2024-12-10 | Z | 2024-12-06 | 40 | 0 | 0 |  | 40 | 60 |  | TA |  | 4
2024-12-12 | 2926 |  | 82558 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2024-12-17 | Z | 2024-12-09 | 40 | 0 | 0 |  | 0 | 40 |  | 3rd floor misc |  | 8
2024-12-12 | 2927 | sp | 82559 | A | DONE | 3 | S | ss | LABCORP 6240016 |  | 2024-12-17 | Z | 2024-12-09 | 40 | 30 | 0 |  | 0 | 60 |  | 3rd floor |  | 8
2024-12-12 | 2928 |  | 82560 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2024-12-17 | Z | 2024-12-09 | 20 | 0 | 0 |  | 0 | 50 |  | 3rd floor |  | 8
2024-12-12 | 2929 | bth | 82561 | A | DONE | 4 | S | pt.ss | LABCORP 6240016 | coil | 2024-12-17 | Z | 2024-12-09 | 50 | 50 | 0 |  | 0 | 100 |  | 3rd floor |  | 8
2024-12-12 | 3963 |  | 79682 | A | DONE | 2 | S |  | PECATONICA 6240005 | 1" liner | 2024-12-16 | Z | 2024-12-11 | 30 | 0 | 0 |  | 20 | 30 |  | Gym Office RA |  | 5
2024-12-10 | 2392 | bth | 59822 - 59823 | A | DONE | 12 | S-M |  | PROMEGA BTC 2240009 | flex | 2024-12-11 | Z | 2024-12-04 | 100 | 30 | 150 | F | 0 | 340 |  | TA Culinary |  | 7
2024-12-11 | 2523 | sp | 81823 | A | DONE | 4 | S |  | PROMEGA BTC 6230022 |  | 2024-12-16 | Z | 2024-12-10 | 20 | 70 | 0 |  | 0 | 90 |  | Misc |  | 6
2024-12-11 | 2522 | bth | 59825 | A | DONE | 11 | S-M |  | PROMEGA MCBR 2240039 | flex | 2024-12-16 | Z | 2024-12-09 | 110 | 150 | 0 |  | 0 | 330 |  | EA Fans |  | 7
2024-12-11 | 145 |  | 70722 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-12-16 | Z | 2024-12-10 | 20 | 0 | 0 |  | 0 | 80 |  | Misc |  | 6
2024-12-12 | 146 | sp | 70723 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-12-16 | Z | 2024-12-10 | 20 | 20 | 0 |  | 0 | 40 |  | Punch list |  | 6
2024-12-10 | 4780 | bth | 61189 | A | DONE | 4 | S-M |  | ROCK CO. JAIL 6220018 |  | 2024-12-11 | Z | 2024-12-02 | 20 | 20 | 50 | F | 0 | 220 |  | 9K |  | 9
2024-12-11 | 4781 |  | 61190 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 | VD's | 2024-12-12 | Z | 2024-12-11 | 20 | 0 | 0 |  | 0 | 20 |  | Fleet Garage |  | 1
2024-12-10 | 417 | bth | L01_A_SAMP_001 | A | DONE | 18 | M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 190 | 20 | 230 | F | 0 | 660 |  |  |  | 42 | 2024-12-12
2024-12-10 | 418 | bth | L01_A_SAMP_002 | A | DONE | 10 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 90 | 50 | 110 | F | 0 | 350 |  |  |  | 42 | 2024-12-12
2024-12-10 | 419 | sp | L01_A_SAMP_003 | A | DONE | 3 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 30 | 40 | 0 |  | 0 | 90 |  |  |  | 42 | 2024-12-12
2024-12-10 | 420 | sp | L01_A_SAMP_004 | A | DONE | 7 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 50 | 120 | 0 |  | 0 | 200 |  |  |  | 42 | 2024-12-12
2024-12-10 | 421 | bth | L01_A_SAMP_005 | A | DONE | 10 | S-M | neal | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 120 | 30 | 80 | F | 0 | 320 |  |  |  | 42 | 2024-12-12
2024-12-10 | 422 | bth | L01_A_SAMP_006 | A | DONE | 9 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 50 | 20 | 150 | F | 0 | 310 |  |  |  | 42 | 2024-12-12
2024-12-10 | 423 | bth | L01_A_SAMP_007 | A | DONE | 9 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 60 | 80 | 70 | F | 0 | 250 |  |  |  | 42 | 2024-12-12
2024-12-10 | 424 | bth | L01_A_SAMP_008 | A | DONE | 10 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 120 | 20 | 100 | F | 0 | 290 |  |  |  | 42 | 2024-12-12
2024-12-10 | 425 | bth | L01_A_SAMP_009 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 90 | 30 | 30 | F | 0 | 180 |  |  |  | 42 | 2024-12-12
2024-12-10 | 426 |  | L01_A_SAMP_010 | A | DONE | 8 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 80 | 0 | 110 | F | 0 | 260 |  |  |  | 42 | 2024-12-12
2024-12-10 | 427 | bth | L01_A_SAMP_011 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 70 | 50 | 0 |  | 30 | 140 |  |  |  | 42 | 2024-12-12
2024-12-10 | 428 | sp | L01_A_SAMP_012 | A | DONE | 6 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-10-30 | 20 | 110 | 0 |  | 0 | 150 |  |  |  | 42 | 2024-12-12
2024-12-12 | 432 | bth | L01_A_EAD_001 | A | DONE | 10 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 80 | 120 | 30 | F | 0 | 230 |  |  |  | 50
2024-12-12 | 435 | bth | L01_A_SALP_003 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 50 | 20 | 0 |  | 0 | 80 |  |  |  | 50 | 2024-12-26
2024-12-12 | 436 |  | L01_A_SALP_004 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 50 | 2024-12-26
2024-12-12 | 437 |  | L01_A_SALP_005 | A | DONE | 3 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 70 | 0 | 0 |  | 0 | 100 |  |  |  | 50 | 2024-12-26
2024-12-12 | 458 | bth | L01_A_SALP_026 | A | DONE | 4 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 50 | 30 | 0 |  | 0 | 90 |  |  |  | 50 | 2024-12-19
2024-12-10 | 1197 |  | 83018 | A | DONE | 3 | S-M |  | STOUGHTON TRAILER 6240015 | paint | 2024-12-11 | Z | 2024-12-04 | 70 | 0 | 0 |  | 20 | 200 |  | Boxes |  | 7 | 2024-12-12
2024-12-10 | 1198 | bth | 83019 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-11 | Z | 2024-12-04 | 20 | 20 | 0 |  | 0 | 30 |  | 2nd floor |  | 7 | 2024-12-12
2024-12-10 | 1199 |  | 83020 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-11 | Z | 2024-12-06 | 20 | 0 | 0 |  | 20 | 40 |  | 2nd floor B |  | 5 | 2024-12-12
2024-12-10 | 2800 |  | 83021 - 83022 | L | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-11 | Z | 2024-12-09 | 30 | 0 | 0 |  | 20 | 30 |  | TA |  | 2
2024-12-13 | 2801 |  | 83023 | A | DONE | 16 | S-M |  | STOUGHTON TRAILER 6240015 | paint | 2024-12-19 | Z | 2024-12-10 | 390 | 0 | 0 |  | 250 | 380 |  | 2nd floor |  | 9
2024-12-13 | 2008 |  | 73099 | A | DONE | 2 | S | neal | UW VET 6210014 |  | 2024-12-19 | Z | 2024-12-12 | 20 | 0 | 0 |  | 0 | 30 |  | Flashing |  | 7
2024-12-11 | 3895 |  | 82147 | A | DONE | 2 | S |  | UWL-GRAFF 6230017 | flex | 2024-12-16 | Z | 2024-12-04 | 20 | 0 | 0 |  | 0 | 20 |  | 3rd Data |  | 12
2024-12-09 | 1365 |  | SA-04-06 | A | DONE | 42 | L |  | UWSP ALBERTSON 6230016 |  | 2024-12-10 | Z | 2024-11-04 | 1050 | 0 | 0 |  | 0 | 3180 |  |  |  | 36
2024-12-09 | 1366 | bth | SA-04-07 | A | DONE | 39 | L |  | UWSP ALBERTSON 6230016 |  | 2024-12-10 | Z | 2024-11-04 | 510 | 30 | 430 | F | 0 | 2290 |  |  |  | 36
2024-12-12 | 1367 |  | RA-04-08 | A | DONE | 85 | L |  | UWSP ALBERTSON 6230016 |  | 2024-12-17 | Z | 2024-11-04 | 2110 | 0 | 0 |  | 0 | 7100 |  |  |  | 43
2024-12-09 | 1371 | bth | SA-04-02 | A | DONE | 98 | L |  | UWSP ALBERTSON 6230016 |  | 2024-12-10 | Z | 2024-11-13 | 750 | 40 | 1640 | F | 0 | 4380 |  |  |  | 27
2024-12-09 | 1384 |  | 81132 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-12-10 | Z | 2024-11-27 | 20 | 0 | 0 |  | 0 | 20 |  | AHU-1A |  | 13
2024-12-11 | 2007 |  | 73097 | A | DONE | 2 | S |  | UW-VET MED 6210014 |  | 2024-12-13 | Z | 2024-12-09 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 4
2024-12-10 | 2190 |  | 79861 | A | DONE | 5 | S |  | WAUNAKEE MS 6230013 |  | 2024-12-13 | Z | 2024-12-06 | 120 | 0 | 0 |  | 0 | 200 |  | Vogel pour stop |  | 7
2024-12-11 | 884 | sp | 82468 - 82469 | A | DONE | 8 | S-M |  | WINDSOR 6240012 | flex | 2024-12-16 | Z | 2024-10-22 | 30 | 160 | 0 |  | 0 | 180 |  | FCU-220 , 222 SA |  | 55 | 2024-12-09
2024-12-11 | 885 |  | 82470 - 82471 | A | DONE | 6 | S-M |  | WINDSOR 6240012 | flex , bird s. , 1" liner | 2024-12-16 | Z | 2024-10-22 | 50 | 0 | 80 | F | 90 | 170 |  | FCU-220 , 222 RA |  | 55 | 2024-12-09
2024-12-11 | 886 | sp | 82472 | A | DONE | 8 | S-M |  | WINDSOR 6240012 |  | 2024-12-16 | Z | 2024-10-22 | 30 | 170 | 0 |  | 0 | 200 |  | FCU-214 , 216 SA |  | 55 | 2024-12-09
2024-12-12 | 887 |  | 82473 - 82475 | A | DONE | 13 | S-M |  | WINDSOR 6240012 | flex , bird s. , 1" liner | 2024-12-16 | Z | 2024-10-22 | 320 | 0 | 0 |  | 270 | 690 |  | FCU RA |  | 55 | 2024-12-09
2024-12-11 | 888 |  | 82476 - 82477 | A | DONE | 15 | M |  | WINDSOR 6240012 |  | 2024-12-16 | Z | 2024-10-22 | 150 | 0 | 220 | F | 0 | 370 |  | DOAS #2 |  | 55 | 2024-12-09
2024-12-11 | 895 |  | 82525 - 82526 | A | DONE | 7 | S-M |  | WINDSOR 6240012 | VD's | 2024-12-16 | Z | 2024-10-31 | 140 | 0 | 30 | F | 0 | 180 |  | FCU-102 A SA |  | 46 | 2024-12-09
2024-12-11 | 896 | sp | 82527 - 82528 | A | DONE | 4 | S-M |  | WINDSOR 6240012 |  | 2024-12-16 | Z | 2024-10-31 | 30 | 70 | 0 |  | 0 | 90 |  | FCU-102 A SA |  | 46 | 2024-12-09
2024-12-11 | 897 |  | 82529 | A | DONE | 6 | S-M |  | WINDSOR 6240012 |  | 2024-12-16 | Z | 2024-10-31 | 50 | 0 | 90 | F | 0 | 150 |  | FCU-209 SA |  | 46 | 2024-12-09
2024-12-11 | 898 | sp | 82530 | A | DONE | 4 | S |  | WINDSOR 6240012 |  | 2024-12-16 | Z | 2024-10-31 | 20 | 80 | 0 |  | 0 | 80 |  | FCU-209 SA |  | 46 | 2024-12-09
2024-12-12 | 899 |  | 82531 | A | DONE | 14 | S-M |  | WINDSOR 6240012 | VD | 2024-12-16 | Z | 2024-10-31 | 40 | 0 | 290 | F | 0 | 330 |  | 2nd floor EA |  | 46 | 2024-12-09
2024-12-11 | 1250 | sp | 82532 | A | DONE | 3 | S |  | WINDSOR 6240012 |  | 2024-12-16 | Z | 2024-10-31 | 20 | 40 | 0 |  | 0 | 50 |  | 2rd floor EA |  | 46 | 2024-12-09
2024-12-12 | 1251 |  | 82533 | A | DONE | 10 | S-M |  | WINDSOR 6240012 | flex | 2024-12-16 | Z | 2024-10-31 | 50 | 0 | 90 | F | 0 | 150 |  | FCU-202 SA |  | 46 | 2024-12-09
2024-12-12 | 1904 | sp | 80871 - 80873 | A | DONE | 19 | S-M | neal | WSCC 6240006 |  | 2024-12-19 | Z | 2024-10-11 | 50 | 410 | 0 |  | 0 | 530 |  | RTU-01 |  | 69
2024-12-12 | 1907 | sp | 80878 | A | DONE | 7 | S-M | neal | WSCC 6240006 |  | 2024-12-19 | Z | 2024-10-11 | 20 | 150 | 0 |  | 0 | 260 |  | RTU-01 |  | 69
2024-12-12 | 1911 | bth | 80888 - 80889 | A | DONE | 19 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-19 | Z | 2024-10-11 | 30 | 430 | 0 |  | 0 | 530 |  | RTU-01 |  | 69
2024-12-13 | 1914 |  | 80893 - 80895 | A | DONE | 16 | S-M | neal | WSCC 6240006 | 1" liner | 2024-12-19 | Z | 2024-10-11 | 290 | 0 | 100 | F | 300 | 450 |  | RTU-01 |  | 69
2024-12-12 | 1915 | bth | 80896 - 80897 | A | DONE | 7 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-19 | Z | 2024-10-11 | 30 | 130 | 0 |  | 30 | 190 |  | RTU-01 |  | 69
2024-12-13 | 1917 | sp | 80900 , 80952 | A | DONE | 19 | S-M | neal | WSCC 6240006 | spiral mate , bird s. | 2024-12-19 | Z | 2024-10-11 | 40 | 430 | 0 |  | 0 | 550 |  | RTU-01 |  | 69
2024-12-10 | 1918 |  | 71452 | A | DONE | 3 | S-M |  | WSCC 6240006 | flex , 1" liner | 2024-12-11 | Z | 2024-10-15 | 30 | 0 | 30 | F | 50 | 80 |  | Fan-01 |  | 57
2024-12-10 | 1919 | sp | 71453 | A | DONE | 7 | S-M | neal | WSCC 6240006 |  | 2024-12-11 | Z | 2024-10-15 | 20 | 140 | 0 |  | 0 | 170 |  | Fan-01 |  | 57
2024-12-10 | 1966 |  | 71472 | A | DONE | 2 | S-M |  | WSCC 6240006 | FB | 2024-12-10 | Z | 2024-12-10 | 20 | 0 | 0 |  | 0 | 40 |  | Sleeves |  | 0
2024-12-10 | 1967 | sp | 71473 | A | DONE | 24 | M | neal | WSCC 6240006 | spiral mate | 2024-12-10 | Z | 2024-12-10 | 0 | 580 | 0 |  | 0 | 620 |  | RTU-5,7,13 |  | 0
[6 empty] | 1041 | [13 empty] | 39380 |  |  |  | 5420 | 13.76%
WEEK OF 12/16/2024
2024-12-17 | 1205 |  | 81935 | A | DONE | 30 | M |  | 121 E. WILSON 6230024 |  | 2024-12-23 | Z | 2024-12-11 | 730 | 0 | 0 |  | 0 | 840 |  | EA |  | 12
2024-12-16 | 1206 |  | 121324 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 |  | 2024-12-17 | Z | 2024-12-12 | 40 | 0 | 0 |  | 0 | 40 |  | Misc |  | 5
2024-12-18 | 1207 | sp | 23913 | A | DONE | 3 | S |  | 121 E. WILSON 6230024 |  | 2024-12-19 | Z | 2024-12-18 | 20 | 40 | 0 |  | 0 | 40 |  | Temp Heat |  | 1
2024-12-19 | 1208 |  | 23914 | deleted |  | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-02 | Z | 2024-12-18 | 0 | 0 | 0 |  | 0 | 0 |  | Dampers |  | 15
2024-12-19 | 1209 |  | 23915 | deleted |  | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-09 | Z | 2024-12-18 | 0 | 0 | 0 |  | 0 | 0 |  | Dampers |  | 22
2024-12-17 | 3909f |  | 80146 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-12-20 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 10th Fl. East unit plenums |  | 130
2024-12-17 | 3910f |  | 80147 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-20 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 10th Fl. East Taps |  | 130
2024-12-17 | 3911f |  | 80148 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-20 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 10th Fl. East sliders |  | 130
2024-12-17 | 3913f |  | 80150 | A | DONE | n/a | S |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-12-20 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 10th Fl. East Corr. HP's |  | 130
2024-12-19 | 1129 |  | 79020 | A | DONE | 2 | S |  | B2 QC LAB 2240018 |  | 2024-12-20 | Z | 2024-12-19 | 30 | 0 | 0 |  | 0 | 40 |  |  |  | 1
2024-12-18 | 2077 |  | 69715 | A | DONE | 2 | S-M |  | CDIS 6220028 |  | 2024-12-23 | Z | 2024-12-06 | 100 | 0 | 0 |  | 0 | 200 |  | AHU-4 Tie ins |  | 17
2024-12-16 | 2080 |  | 69716 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-17 | Z | 2024-12-12 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 5
2024-12-17 | 2081 |  | 81609 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-23 | Z | 2024-12-17 | 20 | 0 | 0 |  | 20 | 20 |  | 2nd floor 2503 |  | 6
2024-12-19 | 2082 |  | 61338 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-19 | Z | 2024-12-19 | 20 | 0 | 0 |  | 0 | 20 |  | Basement 2550A |  | 0
2024-12-19 | 153 |  | 84263 | A | DONE | 3 | S |  | CUMMINS 30004497 |  | 2024-12-20 | Z | 2024-12-19 | 30 | 0 | 0 |  | 0 | 70 |  | Duct sock |  | 1
2024-12-19 | 812 |  | 70707 | A | DONE | 19 | S-M | pcd | DELLSHIRE 6240017 |  | 2024-12-30 | Z | 2024-11-27 | 40 | 0 | 420 | F | 0 | 550 |  | Pool RA |  | 33
2024-12-18 | 816 | sp | 70714 - 70716 | A | DONE | 8 | S-M | pcd | DELLSHIRE 6240017 |  | 2024-12-23 | Z | 2024-12-04 | 60 | 130 | 0 |  | 0 | 230 |  | Pool EA |  | 19
2024-12-17 | 817 | sp | 70717 - 70718 |  | DONE | 6 | S-M |  | DELLSHIRE 6240017 |  | 2024-12-23 | Z | 2024-12-04 | 20 | 130 | 0 |  | 0 | 140 |  | GE |  | 19
2024-12-18 | 818 | sp | 70719 - 70720 | A | DONE | 5 | S-M |  | DELLSHIRE 6240017 |  | 2024-12-23 | Z | 2024-12-04 | 20 | 100 | 0 |  | 0 | 100 |  | EF-5 |  | 19
2024-12-18 | 819 |  | Pre-Fab Hangers | A | DONE | 2 | S | pt.pcd | DELLSHIRE 6240017 |  | 2024-12-23 | Z | 2024-12-04 | 20 | 0 | 0 |  | 0 | 60 |  | Hangers |  | 19
2024-12-16 | 1128 |  | 36342 | A | DONE | 2 | S |  | EXACT 8240012 |  | 2024-12-16 | Z | 2024-12-16 | 20 | 0 | 0 |  | 0 | 20 |  | TEMP HANGER |  | 1
2024-12-16 | 1085 |  | 84352 | A | DONE | 2 | S |  | JPC OFFICE 6240002 |  | 2024-12-17 | Z | 2024-12-16 | 20 | 0 | 0 |  | 0 | 20 |  | Transfer |  | 1
2024-12-19 | 2930 |  | 82562 | A | DONE | 14 | L |  | LABCORP 6240016 |  | 2024-12-24 | Z | 2024-12-16 | 340 | 0 | 0 |  | 0 | 1070 |  | Roof-EF-EB7,8,9 |  | 8
2024-12-18 | 151 |  | 121824 | A | DONE | 2 | S | BI | MGCG 4240033 |  | 2024-12-23 | Z | 2024-12-18 | 20 | 0 | 0 |  | 0 | 80 |  | Plate |  | 5
2024-12-16 | 148 |  | 83193 | A | DONE | 6 | S-M |  | PLACON 10059531 |  | 2024-12-17 | Z | 2024-12-12 | 130 | 0 | 0 |  | 0 | 140 |  | Misc |  | 5
2024-12-18 | 150 |  | 70725 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-12-19 | Z | 2024-12-18 | 50 | 0 | 0 |  | 0 | 140 |  | Canvas covers |  | 1
2024-12-17 | 4782 | w | 61191 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-12-24 | Z | 2024-12-17 | 20 | 0 | 0 |  | 0 | 30 |  | Roof Cap |  | 7
2024-12-16 | 0423 | bth | L01_A_SAMP_007 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-16 | Z | 2024-10-30 | 50 | 0 | 70 | F | 0 | 140 |  | RE-MAKE NO LINER |  | 47
2024-12-16 | 0427 | bth | L01_A_SAMP_011 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-16 | Z | 2024-10-30 | 50 | 0 | 0 |  | 0 | 60 |  | RE-MAKE NO LINER |  | 47
2024-12-16 | 430 |  | L01_A_RAD_001 | A | DONE | 22 | M | neal | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-19 | Z | 2024-10-30 | 290 | 0 | 240 | F | 470 | 770 |  |  |  | 50
2024-12-18 | 431 |  | L01_A_RAD_002 | A | DONE | 19 | M | pt.neal | STOUGHTON TRAILER 6240015 | bird s. , VD , 1" liner | 2024-12-19 | Z | 2024-10-30 | 240 | 0 | 230 | F | 400 | 890 |  |  |  | 50
2024-12-16 | 433 | bth | L01_A_SALP_001 | A | DONE | 5 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 60 | 50 | 0 |  | 0 | 140 |  |  |  | 50 | 2024-12-26
2024-12-17 | 434 | bth | L01_A_SALP_002 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 20 | 0 |  | 0 | 30 |  |  |  | 50 | 2024-12-26
2024-12-17 | 440 |  | L01_A_SALP_008 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 40 | 20 | 0 |  | 0 | 70 |  |  |  | 50 | 2024-12-26
2024-12-17 | 441 | bth | L01_A_SALP_009 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 50 | 2024-12-26
2024-12-17 | 442 | bth | L01_A_SALP_010 | A | DONE | 10 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 70 | 180 | 0 |  | 0 | 290 |  |  |  | 50 | 2024-12-26
2024-12-17 | 443 | sp | L01_A_SALP_011 | A | DONE | 7 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 50 | 110 | 0 |  | 0 | 180 |  |  |  | 50 | 2024-12-26
2024-12-17 | 444 | bth | L01_A_SALP_012 | A | DONE | 3 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 50 | 2024-12-26
2024-12-17 | 445 | bth | L01_A_SALP_013 | A | DONE | 3 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 50 | 0 |  | 0 | 70 |  |  |  | 50 | 2024-12-26
2024-12-17 | 446 | bth | L01_A_SALP_014 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 30 | 0 |  | 0 | 40 |  |  |  | 50 | 2024-12-26
2024-12-17 | 448 | bth | L01_A_SALP_016 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 50 | 2024-12-26
2024-12-17 | 449 | bth | L01_A_SALP_017 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 50 | 2024-12-26
2024-12-17 | 452 | bth | L01_A_SALP_020 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 50 | 2024-12-26
2024-12-17 | 453 | bth | L01_A_SALP_021 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 50 | 2024-12-26
2024-12-17 | 456 | bth | L01_A_SALP_024 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 30 | 90 | 0 |  | 0 | 110 |  |  |  | 50 | 2024-12-19
2024-12-16 | 457 | bth | L01_A_SALP_025 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 70 | 20 | 30 | F | 0 | 120 |  |  |  | 50 | 2024-12-19
2024-12-17 | 459 | bth | L01_A_SALP_027 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 20 | 0 |  | 0 | 40 |  |  |  | 50 | 2024-12-19
2024-12-17 | 460 | bth | L01_A_SALP_028 | A | DONE | 2 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 30 | 0 |  | 0 | 60 |  |  |  | 50 | 2024-12-19
2024-12-17 | 461 | bth | L01_A_SALP_029 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-10-30 | 20 | 20 | 0 |  | 0 | 20 |  |  |  | 50 | 2024-12-19
2024-12-20 | 476 | sp | L01_A_EAD_002 | A | DONE | 3 | S | neal | STOUGHTON TRAILER 6240015 |  | 2025-01-02 | Z | 2024-10-30 | 20 | 40 | 0 |  | 0 | 60 |  |  |  | 64
2024-12-18 | 2803 | sp | L01_B_EAD_004 | A | DONE | 3 | S | alum | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-12-11 | 20 | 40 | 0 |  | 0 | 30 |  |  |  | 8
2024-12-16 | 2804 |  | 83024 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2024-12-19 | Z | 2024-12-13 | 30 | 0 | 0 |  | 0 | 40 |  | Cap Changes |  | 6
2024-12-16 | 690 |  | 83513 - 83514 | A | DONE | 2 | S |  | UWRF 6230010 | flex , angle rings | 2024-12-17 | Z | 2024-12-03 | 20 | 0 | 0 |  | 0 | 20 |  | EF canvas roof |  | 14
2024-12-19 | 691 |  | 83511 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2024-12-26 | Z | 2024-12-11 | 20 | 0 | 0 |  | 0 | 40 |  | PH Outs |  | 15
2024-12-19 | 692 |  | 83518 - 83519 | A | DONE | 8 | S-M |  | UWRF 6230010 |  | 2024-12-26 | Z | 2024-12-11 | 190 | 0 | 0 |  | 0 | 480 |  | AHU-4 OA |  | 15
2024-12-19 | 693 |  | 83521 | A | DONE | 6 | S-M |  | UWRF 6230010 | spiralmate | 2024-12-26 | Z | 2024-12-11 | 130 | 0 | 0 |  | 0 | 350 |  | RAMP 1 |  | 15
2024-12-17 | 1372 | bth | SA-04-08 | A | DONE | 28 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-12-23 | Z | 2024-11-13 | 280 | 120 | 300 | F | 0 | 1120 |  |  |  | 40
2024-12-17 | 1373 | bth | SA-04-09 | A | DONE | 19 | M |  | UWSP ALBERTSON 6230016 |  | 2024-12-23 | Z | 2024-11-13 | 110 | 20 | 330 | F | 0 | 580 |  |  |  | 40
2024-12-17 | 1374 | bth | SA-04-10 | A | DONE | 11 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-12-23 | Z | 2024-11-13 | 130 | 30 | 100 | F | 0 | 370 |  |  |  | 40
2024-12-17 | 1375 | bth | SA-04-11 | A | DONE | 14 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-12-23 | Z | 2024-11-13 | 90 | 50 | 210 | F | 0 | 430 |  |  |  | 40
2024-12-17 | 1376 |  | SA-04-12 | A | DONE | 42 | M-L |  | UWSP ALBERTSON 6230016 |  | 2024-12-23 | Z | 2024-11-13 | 330 | 0 | 710 | F | 0 | 2060 |  |  |  | 40
2024-12-17 | 1377 |  | SA-04-13 | A | DONE | 21 | M |  | UWSP ALBERTSON 6230016 |  | 2024-12-23 | Z | 2024-11-13 | 50 | 0 | 470 | F | 0 | 760 |  |  |  | 40
2024-12-17 | 1378 |  | SA-04-14 | A | DONE | 21 | M |  | UWSP ALBERTSON 6230016 |  | 2024-12-23 | Z | 2024-11-13 | 50 | 0 | 470 | F | 0 | 670 |  |  |  | 40
2024-12-18 | 1379 | bth | SA-04-15 | A | DONE | 13 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-12-23 | Z | 2024-11-13 | 50 | 50 | 210 | F | 0 | 500 |  |  |  | 40
2024-12-18 | 2707 | sp | 58814 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-12-24 | Z | 2024-12-13 | 20 | 20 | 0 |  | 0 | 40 |  | Misc |  | 11
2024-12-18 | 2708 |  | 58815 | A | DONE | 3 | S |  | UWSP CHAMPION HALL 6240008 | VD | 2024-12-24 | Z | 2024-12-13 | 50 | 0 | 0 |  | 10 | 60 |  | Misc |  | 11
2024-12-18 | 2709 |  | 58816 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-24 | Z | 2024-12-13 | 20 | 0 | 0 |  | 20 | 30 |  | VAV-22-224 |  | 11
2024-12-19 | 1081 |  | L02_F_SOA_002 | A | DONE | 16 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 70 | 0 | 330 | F | 0 | 490 |  |  |  | 31
2024-12-19 | 1082 | bth | L02_F_SOA_003 | A | DONE | 15 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 110 | 20 | 230 | F | 0 | 450 |  |  |  | 31
2024-12-19 | 1083 | bth | L02_F_SOA_004 | A | DONE | 16 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 80 | 100 | 220 | F | 0 | 470 |  |  |  | 31
2024-12-19 | 1085 | bth | L02_F_SOA_006 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 30 | 140 | 20 | F | 0 | 190 |  |  |  | 31
2024-12-20 | 1094 |  | L02_F_EAD_002 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 70 | 0 | 150 | F | 0 | 270 |  |  |  | 31
2024-12-17 | 2189 |  | 67600 | A | DONE | 4 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-20 | Z | 2024-12-06 | 80 | 0 | 0 |  | 0 | 160 |  | Print holder |  | 14
2024-12-18 | 1257 |  | 82540 | A | DONE | 2 | S |  | WINDSOR 6240012 |  | 2024-12-23 | Z | 2024-12-11 | 20 | 0 | 0 |  | 0 | 30 |  | Rm. 129 |  | 12
2024-12-18 | 1258 |  | 82541 | A | DONE | 2 | S |  | WINDSOR 6240012 | 1"liner | 2024-12-23 | Z | 2024-12-16 | 20 | 0 | 0 |  | 20 | 40 |  | FCU-131 |  | 7 |  |  |  |  | 2024-12-09
2024-12-20 | 1261 |  | 82547 | L | DONE | 3 | S |  | WINDSOR 6240012 |  | 2024-12-23 | Z | 2024-12-19 | 30 | 0 | 30 |  | 0 | 90 |  | DOAS #2 out |  | 4 |  |  |  |  | 2024-12-09
2024-12-18 | 1972 |  | 82542 | A | DONE | 2 | S |  | WINDSOR 6240012 | Paint | 2024-12-23 | Z | 2024-12-18 | 20 | 0 | 0 |  | 20 | 20 |  | Rm 119 |  | 5 |  |  |  |  | 2024-12-09
2024-12-18 | 1890 |  | 80854 - 80855 | A | DONE | 18 | M | neal | WSCC 6240006 | 1" liner | 2024-12-23 | Z | 2024-08-13 | 400 | 0 | 50 | F | 210 | 790 |  | ERV-06 |  | 132
2024-12-18 | 1891 | sp | 80856 - 80858 | A | DONE | 27 | M | neal | WSCC 6240006 |  | 2024-12-23 | Z | 2024-08-13 | 60 | 600 | 0 |  | 0 | 760 |  | ERV-06 |  | 132 |  |  |  |  | 2024-12-09
2024-12-18 | 1892 | sp | 80859 - 80861 | A | DONE | 26 | M | neal | WSCC 6240006 |  | 2024-12-23 | Z | 2024-08-13 | 80 | 570 | 0 |  | 0 | 750 |  | ERV-06 |  | 132
2024-12-17 | 1893 | sp | 80862 - 80863 | A | DONE | 21 | S-M | neal | WSCC 6240006 |  | 2024-12-23 | Z | 2024-08-13 | 60 | 450 | 0 |  | 0 | 610 |  | ERV-06 |  | 132
2024-12-18 | 1894 |  | 80864 | A | DONE | 2 | S | neal | WSCC 6240006 | flex | 2024-12-23 | Z | 2024-08-13 | 30 | 0 | 0 |  | 0 | 40 |  | Fan-07 , 08 |  | 132
2024-12-16 | 1901 |  | 80865 - 80866 | A | DONE | 17 | S-M | neal | WSCC 6240006 | VD's , 1" liner | 2024-12-19 | Z | 2024-10-11 | 270 | 0 | 150 | F | 250 | 720 |  | RTU-01 |  | 69
2024-12-16 | 1902 | sp | 80867 - 80868 | A | DONE | 21 | S-M | neal | WSCC 6240006 | spiral mate | 2024-12-19 | Z | 2024-10-11 | 230 | 230 | 60 | F | 0 | 660 |  | RTU-01 |  | 69
2024-12-16 | 1903 | bth | 80870 | A | DONE | 6 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-19 | Z | 2024-10-11 | 30 | 120 | 0 |  | 30 | 170 |  | RTU-01 |  | 69
2024-12-16 | 1905 | bth | 80874 | A | DONE | 3 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-19 | Z | 2024-10-11 | 30 | 30 | 0 |  | 20 | 60 |  | RTU-01 |  | 69
2024-12-16 | 1906 | sp | 80875 - 80877 | A | DONE | 16 | S-M | neal | WSCC 6240006 | 1" spiral accu | 2024-12-19 | Z | 2024-10-11 | 60 | 320 | 0 |  | 30 | 520 |  | RTU-01 |  | 69
2024-12-16 | 1908 | sp | 80879 - 80882 | A | DONE | 33 | S-M | neal | WSCC 6240006 | spiral mate | 2024-12-19 | Z | 2024-10-11 | 190 | 620 | 0 |  | 0 | 970 |  | RTU-01 |  | 69
2024-12-16 | 1909 | bth | 80883 - 80885 | A | DONE | 9 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-19 | Z | 2024-10-11 | 30 | 190 | 0 |  | 60 | 250 |  | RTU-01 |  | 69
2024-12-16 | 1910 | bth | 80886 - 80887 | A | DONE | 15 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-19 | Z | 2024-10-11 | 260 | 20 | 80 | F | 200 | 460 |  | RTU-01 |  | 69
2024-12-16 | 1912 | bth | 80890 | A | DONE | 6 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-19 | Z | 2024-10-11 | 30 | 120 | 0 |  | 30 | 160 |  | RTU-01 |  | 69
2024-12-16 | 1913 | bth | 80891 - 80892 | A | DONE | 11 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-19 | Z | 2024-10-11 | 70 | 190 | 0 |  | 30 | 320 |  | RTU-01 |  | 69
2024-12-16 | 1916 | bth | 80898 - 80899 | A | DONE | 28 | S-M | neal | WSCC 6240006 | spiral mate , 1" liner | 2024-12-19 | Z | 2024-10-11 | 500 | 130 | 50 | F | 270 | 870 |  | RTU-01 |  | 69
2024-12-18 | 1927 |  | 80953 | A | DONE | 8 | S-M | neal | WSCC 6240006 | s.mates , 1" liner | 2024-12-24 | Z | 2024-10-31 | 120 | 0 | 60 | F | 130 | 240 |  | RTU-1 |  | 54
2024-12-19 | 1928 | sp | 80954 - 80955 | A | DONE | 22 | M | neal | WSCC 6240006 | spiralmate | 2024-12-24 | Z | 2024-10-31 | 100 | 430 | 0 |  | 0 | 710 |  | RTU-1 |  | 54
2024-12-19 | 1929 | bth | 80956 | A | DONE | 4 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-24 | Z | 2024-10-31 | 50 | 50 | 0 |  | 60 | 120 |  | RTU-1 |  | 54
2024-12-19 | 1930 | sp | 80957 - 80958 | A | DONE | 12 | M | neal | WSCC 6240006 |  | 2024-12-24 | Z | 2024-10-31 | 30 | 250 | 0 |  | 0 | 340 |  | RTU-1 |  | 54
2024-12-19 | 1931 | bth | 80959 - 80960 | A | DONE | 29 | M | neal | WSCC 6240006 | spiralmate , 1" liner | 2024-12-24 | Z | 2024-10-31 | 240 | 480 | 0 |  | 30 | 880 |  | RTU-1 |  | 54
2024-12-18 | 1932 |  | 80961 | A | DONE | 10 | S-M | neal | WSCC 6240006 | paint , VD | 2024-12-24 | Z | 2024-10-31 | 90 | 20 | 120 | F | 40 | 400 |  | RTU-1 |  | 54
2024-12-19 | 1933 | sp | 80962 - 80963 | A | DONE | 31 | M | neal | WSCC 6240006 | spiralmate | 2024-12-24 | Z | 2024-10-31 | 40 | 730 | 0 |  | 0 | 950 |  | RTU-1 |  | 54
2024-12-19 | 1934 |  | 80964 | A | DONE | 21 | M | neal | WSCC 6240006 | VD | 2024-12-24 | Z | 2024-10-31 | 230 | 0 | 290 | F | 40 | 720 |  | RTU-1 |  | 54
2024-12-19 | 1935 | sp | 80965 - 80966 , 71454 | A | DONE | 48 | M | neal | WSCC 6240006 | spiralmate | 2024-12-24 | Z | 2024-10-31 | 80 | 1110 | 0 |  | 0 | 1460 |  | RTU-1 |  | 54
2024-12-19 | 1936 | bth | 80967 - 80968 | A | DONE | 16 | M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-24 | Z | 2024-10-31 | 80 | 310 | 0 |  | 60 | 450 |  | VAV-1-7 |  | 54
2024-12-19 | 1937 | bth | 80969 - 80970 | A | DONE | 15 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-24 | Z | 2024-10-31 | 50 | 310 | 0 |  | 50 | 420 |  | VAV-1-8 |  | 54
2024-12-19 | 1938 | bth | 80971 - 80973 | A | DONE | 53 | M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-24 | Z | 2024-10-31 | 80 | 490 | 0 |  | 50 | 670 |  | VAV-1-4 |  | 54
2024-12-19 | 1939 | bth | 80974 - 80975 | A | DONE | 14 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-24 | Z | 2024-10-31 | 60 | 290 | 0 |  | 30 | 410 |  | VAV-1-6 |  | 54
2024-12-18 | 1940 |  | 80976 | A | DONE | 6 | S-M | neal | WSCC 6240006 | 1" liner | 2024-12-24 | Z | 2024-10-31 | 130 | 0 | 0 |  | 120 | 200 |  | VAV RA |  | 54
2024-12-18 | 1941 | bth | 80977 | A | DONE | 12 | S-M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-24 | Z | 2024-10-31 | 40 | 240 | 0 |  | 20 | 320 |  | VAV-1-5 |  | 54
2024-12-19 | 1942 | bth | 80979 - 80980 | A | DONE | 19 | M | neal | WSCC 6240006 | 1" spiral , 1" liner | 2024-12-24 | Z | 2024-10-31 | 50 | 410 | 0 |  | 50 | 530 |  | VAV-1-1 |  | 54
2024-12-19 | 1943 |  | 80981 | A | DONE | 2 | S | neal | WSCC 6240006 | VD , flex | 2024-12-24 | Z | 2024-10-31 | 50 | 0 | 0 |  | 0 | 90 |  | Fan-02 |  | 54
2024-12-18 | 1944 | sp | 80983 | A | DONE | 10 | S-M | neal | WSCC 6240006 |  | 2024-12-24 | Z | 2024-10-31 | 30 | 210 | 0 |  | 0 | 270 |  | Fan-02 |  | 54
2024-12-19 | 1945 |  | 80984 | A | DONE | 4 | S-M | neal | WSCC 6240006 | VD , flex | 2024-12-24 | Z | 2024-10-31 | 80 | 0 | 0 |  | 0 | 150 |  | Fan-03 |  | 54
2024-12-19 | 1946 | sp | 80985 - 80986 | A | DONE | 24 | M | neal | WSCC 6240006 |  | 2024-12-24 | Z | 2024-10-31 | 50 | 500 | 0 |  | 0 | 620 |  | Fan-03 |  | 54
2024-12-19 | 1947 | bth | 80989 | A | DONE | 2 | S-M | neal | WSCC 6240006 |  | 2024-12-24 | Z | 2024-10-31 | 20 | 30 | 0 |  | 0 | 50 |  | TA |  | 54
2024-12-19 | 1968 | sp | 71474 | A | DONE | 8 | S-M | neal | WSCC 6240006 | 1" DW , spiralmate | 2024-12-24 | Z | 2024-12-12 | 140 | 50 | 0 |  | 60 | 260 |  | DHU-1 |  | 12
2024-12-16 | 1969 |  | 71475 | A | DONE | 2 | S | neal | WSCC 6240006 |  | 2024-12-19 | Z | 2024-12-12 | 30 | 0 | 0 |  | 20 | 40 |  | RTU-13-RA |  | 7
2024-12-16 | 1970 |  | 71476 | A | DONE | 2 | S | neal | WSCC 6240006 |  | 2024-12-19 | Z | 2024-12-13 | 50 | 0 | 0 |  | 0 | 70 |  | Section D |  | 6
2024-12-17 | 1971 |  | 71478 | A | DONE | 2 | S |  | WSCC 6240006 | 1"liner | 2024-12-19 | Z | 2024-12-16 | 30 | 0 | 0 |  | 20 | 40 |  | RTU-2 |  | 3
[6 empty] | 1142 | [13 empty] | 35540 |  |  |  | 3380 | 9.51%
WEEK OF 12/23/2024
2024-12-27 | 3907h |  | 80143 - 80144 | A | DONE | 30 | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-03 | Z | 2024-08-12 | 770 | 0 | 0 |  | 0 | 850 |  | 12th Fl. West EA |  | 144
2024-12-23 | 782 |  | 63391,93 | deleted |  |  | S-M |  | BMH AHU9 6240001 |  | 2025-01-02 | Z | 2024-12-20 | [9 empty] | 13
2024-12-27 | 784 |  | 67235-38 | A | DONE | 28 | S-M |  | BMH AHU9 6240001 |  | 2025-01-02 | Z | 2024-12-20 | 290 | 0 | 410 | F | 0 | 880 |  |  |  | 13
2024-12-27 | 785 |  | 67242-43 | A | DONE | 4 | S-M |  | BMH AHU9 6240001 |  | 2025-01-02 | Z | 2024-12-20 | 100 | 0 | 0 |  | 0 | 140 |  |  |  | 13
2024-12-27 | 786 |  | 67244-45 | A | DONE | 2 | S |  | BMH AHU9 6240001 |  | 2024-01-02 | Z | 2024-12-23 | 50 | 0 | 0 |  | 0 | 70 |  | CS-SAHP/RAHP |  | 10
2024-12-26 | 2083 |  | 69717 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-30 | Z | 2024-12-19 | 30 | 0 | 0 |  | 0 | 40 |  | L1-EAD-006 |  | 11
2024-12-26 | 2084 |  | 69719 | A | DONE | 3 | S | neal | CDIS 6220028 |  | 2024-12-30 | Z | 2024-12-20 | 10 | 30 | 0 |  | 0 | 50 |  | EAD-16 |  | 10
2024-12-26 | 2085 |  | 81610 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-12-30 | Z | 2024-12-23 | 20 | 0 | 0 |  | 0 | 20 |  | 3RD FL-TA |  | 7
2024-12-24 | 1132 |  | 79136 | A | DONE | 3 | S |  | EXACT B2-QC 2240018 |  | 2024-12-26 | Z | 2024-12-23 | 80 | 0 | 0 |  | 0 | 90 |  | EA-Out |  | 3
2024-12-24 | 154 | w | 84264 | A | DONE | 2 | S | ss | JOE N. 1000379 |  | 2024-12-30 | Z | 2024-12-19 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 11
2024-12-27 | 2393 |  | 81825 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2024-12-30 | Z | 2024-12-26 | 20 | 0 | 0 |  | 0 | 20 |  | MISC |  | 4
2024-12-23 | 2524 | bth | 59831,33,35 | A | DONE | 4 | S |  | PROMEGA MCBR 2240039 | paint | 2024-12-24 | Z | 2024-12-20 | 80 | 0 | 0 |  | 30 | 120 |  |  |  | 4
2024-12-26 | 2525 | sp | 59830,32,34 | A | DONE | 4 | S |  | PROMEGA MCBR 2240039 |  | 2024-12-27 | Z | 2024-12-20 | 50 | 30 | 0 |  | 0 | 100 |  |  |  | 7
2024-12-26 | 2526 | sp | 59836 | A | DONE | 2 | S | ss | PROMEGA MCBR 2240039 |  | 2024-12-27 | Z | 2024-12-20 | 40 | 0 | 0 |  | 0 | 40 |  |  |  | 7
2024-12-26 | 152 |  | 84701 | A | DONE | 3 | S |  | QBE 4240058 |  | 2024-12-31 | Z | 2024-12-19 | 70 | 0 | 0 |  | 0 | 80 |  |  |  | 12
2024-12-26 | 155 |  | 70726 | A | DONE | 2 | S |  | RAMC 6230009 |  | 2024-01-02 | Z | 2024-12-23 | 20 | 0 | 0 |  | 0 | 20 |  | MISC OUTS |  | 10
2024-12-26 | 4784 | sp | 61192 | A | DONE | 4 | S |  | ROCK CO. JAIL 6220018 |  | 2025-01-03 | Z | 2024-12-20 | 30 | 50 | 0 |  | 0 | 80 |  | Misc |  | 14
2024-12-26 | 4783 | w | 33244 | A | DONE | 2 | S |  | ROCK CO. JAIL 8220022 | 1" FB | 2025-01-06 | Z | 2024-12-17 | 20 | 0 | 0 |  | 0 | 20 |  | Sleeve |  | 20
2024-12-27 | 149 |  | 68139 | A | DONE | 2 | S |  | SPH SURGERY 6240039 |  | 2024-12-30 | Z | 2024-12-16 | 40 | 0 | 0 |  | 0 | 90 |  | Floor Protection |  | 14
2024-12-27 | 1405 |  | 68140 | A | DONE | 6 | S-M |  | SPH SURGERY 6240039 |  | 2025-01-06 | Z | 2024-12-18 | 150 | 0 | 0 |  | 0 | 180 |  | Angle |  | 19
2024-12-27 | 1406 |  | 01227 | A | DONE | 2 | S | bi | SPH SURGERY 6240039 | To Pipe Shop | 2024-01-06 | Z | 2024-12-27 | 20 | 0 | 0 |  | 0 | 30 |  | BI CAPS |  | 10
2024-12-26 | 4295 |  | 79972 | A | DONE | 3 | S |  | ST.BERNARD 6230023 |  | 2025-01-02 | Z | 2024-12-18 | 30 | 0 | 0 |  | 0 | 40 |  | Flashing |  | 15
2024-12-24 | 429 |  | L01_A_TAD_015 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2024-12-26 | Z | 2024-10-30 | 100 | 0 | 40 | F | 120 | 160 |  |  |  | 57
2024-12-23 | 438 | bth | L01_A_SALP_006 | A | DONE | 9 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-26 | Z | 2024-10-30 | 60 | 150 | 0 |  | 0 | 250 |  |  |  | 57
2024-12-23 | 439 | sp | L01_A_SALP_007 | A | DONE | 6 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-26 | Z | 2024-10-30 | 30 | 120 | 0 |  | 0 | 170 |  |  |  | 57
2024-12-23 | 447 | bth | L01_A_SALP_015 | A | DONE | 10 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-12-26 | Z | 2024-10-30 | 30 | 210 | 0 |  | 0 | 280 |  |  |  | 57
2024-12-23 | 450 | bth | L01_A_SALP_018 | A | DONE | 12 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-26 | Z | 2024-10-30 | 50 | 230 | 0 |  | 0 | 320 |  |  |  | 57
2024-12-23 | 451 | sp | L01_A_SALP_019 | A | DONE | 5 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-26 | Z | 2024-10-30 | 30 | 80 | 0 |  | 0 | 110 |  |  |  | 57
2024-12-23 | 454 | bth | L01_A_SALP_022 | A | DONE | 14 | S-M | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-26 | Z | 2024-10-30 | 60 | 270 | 0 |  | 0 | 400 |  |  |  | 57
2024-12-23 | 455 | sp | L01_A_SALP_023 | A | DONE | 5 | S | pt.neal | STOUGHTON TRAILER 6240015 |  | 2024-12-26 | Z | 2024-10-30 | 30 | 90 | 0 |  | 0 | 130 |  |  |  | 57
2024-12-26 | 462 |  | L01_A_TAD_001 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 70 | 0 | 0 |  | 60 | 170 |  |  |  | 64
2024-12-27 | 463 |  | L01_A_TAD_002 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 70 | 0 | 0 |  | 60 | 160 |  |  |  | 64
2024-12-27 | 464 |  | L01_A_TAD_003 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 70 | 0 | 0 |  | 60 | 160 |  |  |  | 64
2024-12-26 | 465 |  | L01_A_TAD_004 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 130 | 0 | 0 |  | 90 | 180 |  |  |  | 64
2024-12-27 | 466 |  | L01_A_TAD_005 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 70 | 0 | 0 |  | 60 | 120 |  |  |  | 64
2024-12-27 | 467 |  | L01_A_TAD_006 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 70 | 0 | 0 |  | 50 | 120 |  |  |  | 64
2024-12-27 | 468 |  | L01_A_TAD_007 | A | DONE | 6 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 130 | 0 | 0 |  | 120 | 210 |  |  |  | 64
2024-12-27 | 469 |  | L01_A_TAD_008 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 30 | 0 | 0 |  | 20 | 50 |  |  |  | 64
2024-12-27 | 470 |  | L01_A_TAD_009 | A | DONE | 9 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 150 | 0 | 0 |  | 80 | 180 |  |  |  | 64
2024-12-27 | 471 |  | L01_A_TAD_010 | A | DONE | 11 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 140 | 0 | 0 |  | 130 | 210 |  |  |  | 64
2024-12-27 | 472 |  | L01_A_TAD_011 | A | DONE | 10 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 140 | 0 | 0 |  | 110 | 200 |  |  |  | 64
2024-12-27 | 473 |  | L01_A_TAD_012 | A | DONE | 10 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 130 | 0 | 0 |  | 120 | 210 |  |  |  | 64
2024-12-27 | 474 |  | L01_A_TAD_013 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 60 | 0 | 0 |  | 40 | 70 |  |  |  | 64
2024-12-27 | 475 |  | L01_A_TAD_014 | A | DONE | 3 | S |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-10-30 | 60 | 0 | 0 |  | 40 | 90 |  |  |  | 64
2024-12-23 | 477 | sp | L01_A_EAD_003 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-02 | Z | 2024-10-30 | 0 | 30 | 0 |  | 0 | 20 |  |  |  | 64
2024-12-27 | 480 | bth | L02_SAMP_001 | A | DONE | 18 | M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-11-14 | 320 | 20 | 90 | F | 160 | 590 |  |  |  | 49
2024-12-27 | 481 | bth | L02_SAMP_004 | A | DONE | 15 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-11-14 | 220 | 10 | 40 | F | 120 | 460 |  |  |  | 49
2024-12-23 | 2805 |  | 83025 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | paint , 1" liner | 2024-12-26 | Z | 2024-12-19 | 40 | 0 | 0 |  | 40 | 70 |  | Finsih items |  | 7
2024-12-26 | 2806 |  | 83026 | A | DONE | 2 | S | alum | STOUGHTON TRAILER 6240015 |  | 2024-01-02 | Z | 2024-12-23 | 20 | 0 | 0 |  | 0 | 20 |  | DRYER |  | 10
2024-12-26 | 4586 | w | 83909 | A | DONE | 3 | S |  | UW-LEVY HALL 6230028 |  | 2024-12-31 | Z | 2024-12-18 | 40 | 0 | 0 |  | 0 | 80 |  | 4th floor EX Sleeve |  | 13
2024-12-26 | 4590 |  | 2919 | A | DONE | 2 | S | bi | UW-LEVY HALL 6230028 | to pipe shop | 2024-01-14 | Z | 2024-12-23 | 20 | 0 | 0 |  | 0 | 20 |  | BI CAPS |  | 22
2024-12-26 | 1385 | bth | 81555 | A | DONE | 2 | S |  | UWSP ALBERTSON 6230016 |  | 2024-12-31 | Z | 2024-12-18 | 30 | 10 | 0 |  | 0 | 50 |  | 4th floor |  | 13
2024-12-27 | 1386 |  | 81158 | A | DONE | 3 | S |  | UWSP ALBERTSON 6230016 | 1" liner | 2024-12-31 | Z | 2024-12-18 | 30 | 0 | 0 |  | 20 | 30 |  | Misc |  | 13
2024-12-27 | 1387 |  | 81159 - 81162 | A | DONE | 4 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-12-31 | Z | 2024-12-18 | 80 | 0 | 0 |  | 0 | 90 |  | Misc |  | 13
2024-12-26 | 1388 |  | 81163 | A | DONE | 5 | S-M |  | UWSP ALBERTSON 6230016 |  | 2024-12-31 | Z | 2024-12-20 | 130 | 0 | 0 |  | 0 | 180 |  | Hanger Strap |  | 11
2024-12-27 | 2710 |  | 58818 | A | DONE | 15 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-02 | Z | 2024-12-18 | 200 | 0 | 0 |  | 180 | 290 |  | SA plenum boxes |  | 15
2024-12-26 | 2711 | sp | 58819 | A | DONE | 2 | S-M |  | UWSP CHAMPION HALL 6240008 |  | 2025-01-02 | Z | 2024-12-18 | 0 | 40 | 0 |  | 0 | 40 |  | SA plenum boxes |  | 15
2024-12-23 | 2712 | bth | L1W_SALP 1 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 100 | 0 | 40 | F | 30 | 160 |  |  |  | 8
2024-12-23 | 2713 | bth | L1W_SALP 2 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 50 | 20 | 80 | F | 30 | 160 |  |  |  | 8
2024-12-23 | 2714 | bth | L1W_SALP 3 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 20 | 0 | 30 | F | 30 | 60 |  |  |  | 8
2024-12-23 | 2715 | bth | L1W_SALP 4 | A | DONE | 3 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 50 | 20 | 0 |  | 30 | 80 |  |  |  | 8
2024-12-23 | 2716 | bth | L1W_SALP 5 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 120 | 20 | 0 |  | 30 | 150 |  |  |  | 8
2024-12-24 | 2717 | bth | L1W_SALP 6 | A | DONE | 5 | S | pt.neal | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 70 | 40 | 0 |  | 20 | 160 |  |  |  | 8
2024-12-23 | 2718 | bth | L1W_SALP 7 | A | DONE | 10 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 170 | 20 | 60 | F | 40 | 290 |  |  |  | 8
2024-12-24 | 2719 | bth | L1W_SALP 8 | A | DONE | 8 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 100 | 20 | 70 | F | 30 | 250 |  |  |  | 8
2024-12-24 | 2720 | bth | L1W_SALP 9 | A | DONE | 9 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 120 | 20 | 70 | F | 30 | 260 |  |  |  | 8
2024-12-24 | 2721 | bth | L1W_SALP 10 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 110 | 20 | 20 | L | 40 | 200 |  |  |  | 8
2024-12-24 | 2722 | bth | L1W_SALP 11 | A | DONE | 7 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 130 | 20 | 20 | L | 40 | 190 |  |  |  | 8
2024-12-26 | 2723 | bth | L1W_SALP 12 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 40 | 20 | 70 | F | 30 | 150 |  |  |  | 8
2024-12-24 | 2724 | bth | L1W_SALP 13 | A | DONE | 6 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 80 | 60 | 0 |  | 40 | 140 |  |  |  | 8
2024-12-24 | 2725 |  | L1W_SALP 14 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 90 | 20 | 0 |  | 60 | 120 |  |  |  | 8
2024-12-24 | 2726 | bth | L1W_SALP 15 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 60 | 40 | 0 |  | 30 | 100 |  |  |  | 8
2024-12-26 | 2727 |  | L1W_SALP 16 | A | DONE | 9 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 90 | 100 | 0 |  | 40 | 210 |  |  |  | 8
2024-12-26 | 2728 | bth | L1W_SALP 17 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 30 | 40 | 30 | F | 30 | 90 |  |  |  | 8
2024-12-26 | 2729 | bth | L1W_SALP 18 | A | DONE | 8 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 130 | 10 | 20 | F | 40 | 180 |  |  |  | 8
2024-12-24 | 2730 | bth | L1W_SALP 19 | A | DONE | 9 | S-M |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 160 | 40 | 0 |  | 30 | 260 |  |  |  | 8
2024-12-26 | 2731 | bth | L1W_SALP 20 | A | DONE | 3 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 30 | 10 | 0 |  | 20 | 50 |  |  |  | 8
2024-12-26 | 2732 | bth | L1W_SALP 21 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 70 | 20 | 0 |  | 40 | 100 |  |  |  | 8
2024-12-26 | 2733 | bth | L1W_SALP 22 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 40 | 50 | 0 |  | 20 | 90 |  |  |  | 8
2024-12-26 | 2734 | bth | L1W_SALP 23 | A | DONE | 3 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 40 | 20 | 0 |  | 20 | 60 |  |  |  | 8 |  |  |  |  | 2024-12-09
2024-12-26 | 2735 | bth | L1W_SALP 24 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 50 | 20 | 0 |  | 40 | 80 |  |  |  | 8
2024-12-26 | 2736 | bth | L1W_SALP 25 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 60 | 30 | 0 |  | 40 | 90 |  |  |  | 8
2024-12-26 | 2737 | bth | L1W_SALP 26 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 60 | 20 | 0 |  | 30 | 80 |  |  |  | 8
2024-12-26 | 2738 | bth | L1W_SALP 27 | A | DONE | 5 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 40 | 10 | 30 | F | 30 | 90 |  |  |  | 8
2024-12-26 | 2739 | bth | L1W_SALP 28 | A | DONE | 7 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 45 | 10 | 70 | F | 40 | 140 |  |  |  | 8
2024-12-26 | 2740 | bth | L1W_SALP 29 | A | DONE | 4 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 50 | 10 | 0 |  | 30 | 70 |  |  |  | 8
2024-12-26 | 2741 |  | L1W_SALP 30 | A | DONE | 15 | S |  | UWSP CHAMPION HALL 6240008 | 1" liner | 2024-12-26 | Z | 2024-12-18 | 120 | 0 | 220 | F | 40 | 1180 |  |  |  | 8
2024-12-27 | 2009 | bth | 79701 - 79702 | A | DONE | 16 | S-M |  | UW-VET MED 6210014 |  | 2025-01-02 | Z | 2024-12-19 | 220 | 0 | 180 | F | 0 | 470 |  | CB-274 |  | 14
2024-12-23 | 2010 | w | 79703 | A | DONE | 2 | S | ss | UW-VET MED 6210014 |  | 2024-12-26 | Z | 2024-12-19 | 20 | 0 | 0 |  | 0 | 20 |  | BSL-3 |  | 7
2024-12-23 | 1080 |  | L02_F_SOA_001 | A | DONE | 14 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 160 | 0 | 180 | F | 0 | 530 |  |  |  | 31
2024-12-23 | 1084 | bth | L02_F_SOA_005 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 70 | 130 | 30 | F | 0 | 230 |  |  |  | 31
2024-12-23 | 1086 | bth | L02_F_SOA_007 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 60 | 80 | 0 |  | 0 | 150 |  |  |  | 31
2024-12-23 | 1087 | bth | L02_F_SOA_008 | A | DONE | 12 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 150 | 20 | 120 | F | 0 | 330 |  |  |  | 31
2024-12-23 | 1088 | bth | L02_F_SOA_009 | A | DONE | 11 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 80 | 40 | 140 | F | 0 | 290 |  |  |  | 31
2024-12-23 | 1089 | bth | L02_F_SOA_010 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 60 | 30 | 120 | F | 0 | 250 |  |  |  | 31
2024-12-23 | 1090 | bth | L02_F_SOA_011 | A | DONE | 8 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 40 | 20 | 140 | F | 0 | 250 |  |  |  | 31
2024-12-23 | 1091 | bth | L02_F_SOA_012 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 20 | 100 | 60 | F | 0 | 180 |  |  |  | 31
2024-12-23 | 1092 | sp | L02_F_SOA_013 | A | DONE | 5 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 20 | 110 | 0 |  | 0 | 120 |  |  |  | 31
2024-12-23 | 1093 | bth | L02_F_EAD_001 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 90 | 20 | 60 | F | 0 | 170 |  |  |  | 31
2024-12-23 | 1095 | bth | L02_F_EAD_003 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 70 | 20 | 120 | F | 0 | 240 |  |  |  | 31
2024-12-23 | 1096 | bth | L02_F_EAD_004 | A | DONE | 7 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 50 | 40 | 70 | F | 0 | 180 |  |  |  | 31
2024-12-23 | 1097 |  | L02_F_EAD_005 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 190 | 0 | 60 | F | 0 | 330 |  |  |  | 31
2024-12-23 | 1098 | bth | L02_F_EAD_006 | A | DONE | 13 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 80 | 30 | 200 | F | 0 | 380 |  |  |  | 31
2024-12-24 | 1099 | bth | L02_F_EAD_007 | A | DONE | 9 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 70 | 30 | 110 | F | 0 | 240 |  |  |  | 31
2024-12-23 | 2100 | bth | L02_F_EAD_008 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 50 | 20 | 60 | F | 0 | 160 |  |  |  | 31
2024-12-23 | 2101 | bth | L02_F_EAD_009 | A | DONE | 6 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 30 | 50 | 60 | F | 0 | 140 |  |  |  | 31
2024-12-23 | 2102 |  | L02_F_EAD_010 | A | DONE | 10 | S-M |  | WAUNAKEE MS 6230013 |  | 2024-12-27 | Z | 2024-11-26 | 150 | 0 | 100 | F | 0 | 410 |  |  |  | 31
2024-12-26 | 1259 |  | 82543-44 | A | DONE | 25 | SM |  | WINDSOR 6240012 | flex, 1" liner | 2024-12-30 | Z | 2024-12-19 | 370 | 0 | 0 |  | 270 | 530 |  |  |  | 11
2024-12-26 | 1260 |  | 82545-46 | A | DONE | 4 | SM |  | WINDSOR 6240012 | flex, 1" liner | 2024-12-30 | Z | 2024-12-19 | 100 | 0 | 0 |  | 80 | 190 |  |  |  | 11
2024-12-26 | 1262 | sp | 82548 | A | DONE | 5 | S-M |  | WINDSOR 6240012 | flex | 2024-12-30 | Z | 2024-12-19 | 40 | 90 | 0 |  | 0 | 110 |  | FCU-206 |  | 11
2024-12-26 | 1973 |  | 62076 | A | DONE | 2 | S | neal | WSCC 6240006 |  | 2024-01-02 | Z | 2024-12-23 | 40 | 0 | 0 |  | 0 | 50 |  | D-OUTS |  | 10
2024-12-27 | 157 |  | 69531 | A | DONE | 2 | S |  | WYSO 6220013 |  | 2024-01-02 | Z | 2024-12-27 | 20 | 0 | 0 |  | 0 | 20 |  | Flashing |  | 6
[6 empty] | 725 | [13 empty] | 20080 |  |  |  | 8400 | 41.83%
WEEK OF 12/30/2024
2024-12-30 | 1210 |  | Roof-2 | A | DONE | 2 | S | BI | 121 E. WILSON 6230024 | To Pipe Shop | 2024-12-31 | Z | 2024-12-30 | 20 | 0 | 0 |  | 0 | 30 |  | BI Caps |  | 1
2024-12-30 | 2247 |  | 80074 | A | DONE | 11 | S-M |  | 121 E. WILSON 6230024 | paint | 2025-01-03 | Z | 2024-07-25 | 50 | 0 | 190 | F | 20 | 280 |  | DOAS-1 / OA-5 |  | 162
2024-12-30 | 3661 |  | 80087 , 80094 | A | DONE | 19 | S-M |  | 121 E. WILSON 6230024 |  | 2025-01-03 | Z | 2024-07-30 | 50 | 0 | 420 | F | 0 | 490 |  | EF-1,2 , EA-6 |  | 157
2025-01-02 | 3692 |  | Stairwell A-EA 5 | A | DONE | 21 | M |  | 121 E. WILSON 6230024 |  | 2025-01-03 | Z | 2024-08-07 | 170 | 0 | 350 | F | 0 | 750 |  |  |  | 149
2024-12-30 | 3903g |  | 80139 | A | DONE | n/a | M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-12-31 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 11th Fl. West unit plenums |  | 141
2024-12-30 | 3904g |  | 80140 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-31 | Z | 2024-08-12 | 20 | 0 | 0 |  | 0 | 20 |  | 11th Fl. West unit Taps |  | 141
2024-12-30 | 3905g |  | 80141 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 |  | 2024-12-31 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 11th Fl. West unit sliders |  | 141
2024-12-30 | 3906g |  | 80142 | A | DONE | n/a | S-M |  | 121 E. WILSON 6230024 | flex , 1" liner | 2024-12-31 | Z | 2024-08-12 | 0 | 0 | 0 |  | 0 | 0 |  | 11th Fl. West Corr. HP's |  | 141
2025-01-03 | 783 | w | 63394 | A | DONE | 3 | S | ss | BMH AHU9 6240001 |  | 2025-01-08 | Z | 2024-12-20 | 70 | 0 | 0 |  | 0 | 170 |  | Misc |  | 19
2024-12-30 | 789 |  | 80211 | A | DONE | 2 | S |  | BMH Ultrasound 2240011 |  | 2024-12-31 | Z | 2024-12-30 | 20 | 0 | 0 |  | 0 | 20 |  | SALP |  | 1
2025-12-31 | 2086 |  | 61392 - 61393 | A | DONE | 23 | L |  | CDIS 6220028 |  | 2024-01-06 | Z | 2024-12-23 | 560 | 0 | 0 |  | 0 | 1870 |  | GENERATOR |  | 13
2025-12-31 | 2087 | sp | 81611 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2024-01-06 | Z | 2024-12-27 | 20 | 10 | 0 |  | 0 | 30 |  | 3RD FL 3610 |  | 10
2025-01-02 | 2088 |  | 69720 | A | DONE | 2 | S | neal | CDIS 6220028 |  | 2025-01-06 | Z | 2024-12-31 | 20 | 0 | 0 |  | 0 | 30 |  | EAD 35 |  | 6
2025-01-02 | 2089 | bth | 69721 | A | DONE | 3 | S-M | neal | CDIS 6220028 |  | 2025-01-06 | Z | 2024-12-31 | 40 | 30 | 0 |  | 0 | 100 |  | Misc |  | 6
2025-01-03 | 2091 |  | 81612 | A | DONE | 2 | S |  | CDIS 6220028 | paint | 2025-01-07 | Z | 2025-01-02 | 20 | 0 | 0 |  | 20 | 30 |  | 7th floor TA |  | 5
2025-01-03 | 2092 |  | 69722 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-01-07 | Z | 2025-01-02 | 20 | 0 | 0 |  | 0 | 50 |  | Mezz Flashing |  | 5
2025-01-03 | 2093 |  | 69723 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-01-10 | Z | 2025-01-03 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2025-01-03 | 2094 | sp | 69724 | A | DONE | 2 | S |  | CDIS 6220028 |  | 2025-01-10 | Z | 2025-01-03 | 20 | 0 | 0 |  | 0 | 20 |  | Dampers |  | 7
2025-01-02 | 1130 | sp | 79134 | A | DONE | 3 | S |  | EXACT BIOSAFE 6230005 | spiralmate , 2" DB | 2025-01-07 | Z | 2024-12-20 | 70 | 0 | 0 |  | 10 | 120 |  | Caps |  | 18
2025-01-02 | 1131 |  | 79135 | A | DONE | 2 | S | ss | EXACT BIOSAFE 6230005 |  | 2025-01-07 | Z | 2024-12-20 | 20 | 0 | 0 |  | 0 | 30 |  | Floor Sinks |  | 18
2025-01-02 | 1133 |  | 79137 | A | DONE | 2 | S |  | EXACT TL-5 6240014 |  | 2024-01-07 | Z | 2024-12-23 | 20 | 0 | 0 |  | 0 | 20 |  | CABINET |  | 15
2024-12-30 | 1134 |  | 85508 | A | DONE | 2 | S | ss | EXACT TL-5 8240012 |  | 2024-12-30 | Z | 2024-12-30 | 20 | 0 | 0 |  | 0 | 20 |  | PADDLE |  | 1
2024-12-30 | 3379 | bth | 78642-43 | A | DONE | 2 | S |  | JANESVILLE 6230011 |  | 2024-01-02 | Z | 2024-12-30 | 20 | 20 | 0 |  | 0 | 30 |  | GRILLE |  | 3
2024-12-30 | 2931 |  | 82563 | A | DONE | 2 | S |  | LABCORP 6240016 |  | 2024-01-03 | Z | 2024-12-30 | 20 | 0 | 0 |  | 0 | 20 |  | 3RD FL-EXH |  | 4
2025-01-03 | 2933 |  | 82565 | A | DONE | 5 | S-M |  | LABCORP 6240016 |  | 2025-01-08 | Z | 2024-12-31 | 120 | 0 | 0 |  | 0 | 270 |  | Rool Channels |  | 8
2025-12-31 | 2654 | sp | 78776 | A | DONE | 5 | S-M |  | MONROE HS 6240018 | 1" FB | 2025-01-03 | Z | 2024-12-20 | 130 | 0 | 0 |  | 0 | 190 |  | E-Section sleeves |  | 14
2025-01-02 | 2527 |  | 59827 , 59829 | A | DONE | 25 | S-M |  | PROMEGA BTC 6230022 |  | 2025-01-06 | Z | 2024-12-20 | 470 | 0 | 160 | F | 0 | 1170 |  |  |  | 17
2025-01-02 | 2394 | sp | 59659 | A | DONE | 2 | S |  | PROMEGA MCBR 2240039 |  | 2025-01-06 | Z | 2024-12-31 | 20 | 0 | 0 |  | 0 | 20 |  | EA hood |  | 6
2025-01-02 | 158 |  | 79431 | A | DONE | 2 | S |  | QBE 4240058 |  | 2025-01-03 | Z | 2025-01-02 | 20 | 0 | 0 |  | 0 | 40 |  | Misc |  | 1
2025-12-31 | 4785 |  | 61193 | A | DONE | 2 | S |  | ROCK CO. JAIL 6220018 |  | 2024-01-03 | Z | 2024-12-27 | 30 | 0 | 0 |  | 0 | 60 |  | ATTY |  | 7
2024-12-30 | 486 |  | L02_RAD_001 | A | DONE | 47 | M-L | pt.neal | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-11-14 | 300 | 0 | 320 | F | 550 | 1140 |  |  |  | 49
2024-12-30 | 487 |  | L02_RAD_002 | A | DONE | 37 | M | neal | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-11-14 | 170 | 0 | 330 | F | 410 | 850 |  |  |  | 49
2024-12-30 | 488 | bth | L02_SAMP_002 | A | DONE | 13 | S-M |  | STOUGHTON TRAILER 6240015 |  | 2025-01-02 | Z | 2024-11-14 | 200 | 50 | 80 | F | 0 | 420 |  |  |  | 49
2024-12-30 | 495 | bth | L02_SAMP_010 | A | DONE | 7 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-02 | Z | 2024-11-14 | 130 | 30 | 30 | F | 0 | 210 |  |  |  | 49
2024-12-30 | 496 | bth | L02_SAMP_011 | A | DONE | 5 | S |  | STOUGHTON TRAILER 6240015 |  | 2025-01-02 | Z | 2024-11-14 | 60 | 0 | 60 | F | 0 | 180 |  |  |  | 49
2024-12-30 | 497 |  | L02_RAD_003 | A | DONE | 19 | S-M |  | STOUGHTON TRAILER 6240015 | 1" liner | 2025-01-02 | Z | 2024-11-14 | 190 | 0 | 70 | F | 220 | 480 |  |  |  | 49
2024-12-30 | 2807 |  | 83027 - 83028 | A | DONE | 2 | S | neal | STOUGHTON TRAILER 6240015 |  | 2024-01-02 | Z | 2024-12-30 | 20 | 0 | 0 |  | 0 | 30 |  | SAMP-9/SALP-19 |  | 3
2025-01-03 | 2810 |  | 83031 | A | DONE | 2 | S |  | STOUGHTON TRAILER 6240015 | paint | 2025-01-09 | Z | 2025-01-02 | 20 | 0 | 0 |  | 0 | 20 |  | Misc |  | 7
2025-01-03 | 1000 |  | 70480 | A | DONE | 2 | S |  | THE SHRINE 6240034 |  | 2025-01-09 | Z | 2025-01-02 | 20 | 0 | 0 |  | 0 | 30 |  | Cone flashing |  | 7
2025-01-02 | 4578 |  | LL - RAMP 7 | A | DONE | 7 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-07 | Z | 2024-12-17 | 70 | 0 | 30 | F | 80 | 140 |  |  |  | 21
2025-01-03 | 4579 |  | LL - RAMP 8 | A | DONE | 19 | S |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-07 | Z | 2024-12-17 | 140 | 0 | 120 | F | 210 | 350 |  |  |  | 21
2025-01-03 | 4580 |  | LL - SAT-3-L-6.1 | A | DONE | 35 | M |  | UW-LEVY HALL 6230028 | VD , 1" liner | 2025-01-07 | Z | 2024-12-17 | 200 | 0 | 270 | F | 390 | 670 |  |  |  | 21
2025-01-03 | 4581 | bth | LL - SAT-3-L-6.2 | A | DONE | 37 | M |  | UW-LEVY HALL 6230028 | VD , 1" spiral, 1" liner | 2025-01-07 | Z | 2024-12-17 | 160 | 30 | 340 | F | 410 | 720 |  |  |  | 21
2025-01-03 | 4587 | bth | LL-SAMP 8 | A | DONE | 3 | S | neal | UW-LEVY HALL 6230028 |  | 2025-01-07 | Z | 2024-12-19 | 40 | 20 | 0 |  | 0 | 70 |  |  |  | 19
2025-01-03 | 4588 |  | LL-EAMP 6 | A | DONE | 6 | S | pt.alum | UW-LEVY HALL 6230028 | VD | 2025-01-07 | Z | 2024-12-19 | 90 | 0 | 40 | F | 0 | 150 |  |  |  | 19
2024-12-30 | 3896 | bth | 82132 - 82134 | A | DONE | 21 | S-M |  | UWL-GRAFF 6230017 | VD | 2025-01-06 | Z | 2024-12-05 | 100 | 370 | 60 | F | 0 | 520 |  | SAT's |  | 32
2025-12-31 | 3897 | bth | 82135 - 82138 | A | DONE | 10 | S-M |  | UWL-GRAFF 6230017 |  | 2025-01-06 | Z | 2024-12-05 | 60 | 140 | 50 | F | 0 | 290 |  | Misc |  | 32
2025-12-31 | 3898 |  | 82299 , 84403 | A | DONE | 9 | M |  | UWL-GRAFF 6230017 |  | 2024-01-06 | Z | 2024-12-23 | 210 | 0 | 0 |  | 0 | 300 |  | MECH RM |  | 14
2025-12-31 | 694 |  | 83522 - 83523 | A | DONE | 2 | S |  | UWRF 6230010 |  | 2025-01-07 | Z | 2024-12-18 | 50 | 0 | 0 |  | 0 | 120 |  |  |  | 20
2025-12-31 | 695 |  | 83524 | A | DONE | 2 | S | pcd | UWRF 6230010 |  | 2025-01-07 | Z | 2024-12-18 | 20 | 0 | 0 |  | 0 | 40 |  |  |  | 20
2025-01-02 | 696 |  | L3Z1-RAMP-PLENUM | A | DONE | 15 | M |  | UWRF 6230010 |  | 2025-01-07 | Z | 2024-12-17 | 180 | 0 | 180 | F | 0 | 730 |  |  |  | 21
2025-12-31 | 697 |  | 70402 | A | DONE | 4 | S-M |  | UWRF 6230010 |  | 2025-01-07 | Z | 2024-12-18 | 100 | 0 | 0 |  | 0 | 130 |  | Angle |  | 20
2025-01-03 | 698 | bth | 83525 - 83527 | A | DONE | 30 | M | pcd | UWRF 6230010 | flex , spiralmate | 2025-01-07 | Z | 2024-12-18 | 570 | 160 | 0 |  | 0 | 1320 |  | EA Outs Roof |  | 20
2025-01-03 | 699 | bth | 83528 | A | DONE | 8 | S-M |  | UWRF 6230010 | flex , spiralmate | 2025-01-07 | Z | 2024-12-19 | 140 | 0 | 50 | F | 0 | 270 |  | Misc |  | 19
2025-01-03 | 3300 |  | 83529 | A | DONE | 5 | S-M |  | UWRF 6230010 |  | 2025-01-07 | Z | 2024-12-19 | 110 | 0 | 0 |  | 0 | 190 |  | Misc |  | 19
2025-01-03 | 1389 |  | OA-04-01 | A | DONE | 38 | M |  | UWSP ALBERTSON 6230016 |  | 2024-01-07 | Z | 2024-12-24 | 840 | 0 | 100 | F | 0 | 2030 |  |  |  | 14
2025-01-03 | 1390 |  | OA-04-02 | A | DONE | 10 | M |  | UWSP ALBERTSON 6230016 |  | 2024-01-07 | Z | 2024-12-24 | 240 | 0 | 0 |  | 0 | 540 |  |  |  | 14
2025-01-03 | 1392 |  | OA-04-04 | A | DONE | 10 | M |  | UWSP ALBERTSON 6230016 |  | 2024-01-07 | Z | 2024-12-24 | 250 | 0 | 0 |  | 0 | 480 |  |  |  | 14
2024-12-30 | 2742 |  | 58820 | A | DONE | 2 | S |  | UWSP CHAMPION HALL 6240008 |  | 2024-01-02 | Z | 2024-12-27 | 30 | 0 | 0 |  | 0 | 30 |  | MISC OUTS |  | 6
2025-01-03 | 2744 |  | 58822 | A | DONE | 8 | S-M | neal | UWSP CHAMPION HALL 6240008 |  | 2025-01-07 | Z | 2025-01-02 | 160 | 40 | 0 |  | 0 | 270 |  | Misc |  | 5
[6 empty] | 565 | [13 empty] | 18620